## ITP Cover Page
Landscape Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210-SP2 - 033 -001 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 033 -001
Project Number: |  |  | DN1210-SP2 |  |  |  |  | ITP Status: |  |  | Draft
ITP Description: |  |  | Landscape |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-UDL
Customer: |  |  | NZTA |  |  |  |  | Specification: |  |  | Project Specification, NZTA P39:2013 Section F, Section 3.9
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft | 2025-01-04 |  | Cordelia Girdler-Brown & Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler-Brown | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Landscape Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210-SP2 - 033 -001 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRODUCT DATA SHEETS FOR ENGINEERS APPROVALS
3.1 | Landscape Methodology | The Contractor shall submit the construction and QA methodology, for each element of Landscape including, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to Earthworks | HP | ENG
3.2 | Geotextile Fabric | Geotextile fabric approval | Class D geotextile fabric | PS 21.5.15 | Data sheet Delivery Docket | Once prior to commencement of works | HP | ENG
3.3 | Topsoil Analysis | Testing of on-site and imported topsoil for quality. | Topsoil must meet the criteria specified in the project standards. | NZTA P39: 2013, Section F | Soil Testing Report | Once per source | HP | SE
3.4 | Mulch Material Verification | Verify that the mulch used meets the specified criteria (e.g., pallet mulch, arborist mulch). | Mulch material should be free of contaminants, sufficiently aged, and appropriate to site and slope conditions | NZTA P39: 2013 Section 3.9 | Data sheet Delivery Docket | 100% of mulch used | HP | ENG
3.5 | Biodegradeable Weed Mat | Biodegradeable weed mat approval | 450 GSM, 7mm thick, biodegradeable weed mat | PS 27.3.8 | Data sheet Delivery Docket | Once prior to commencement of works | HP | ENG
3.6 | Hydro-seeding | Grass mix approved | Send seed mix to engineer for approval | NZTA P39: 2013, Section F | Data sheet Delivery Docket | Once prior to commencement of works | HP | ENG
SECTION 4 – CONSTRUCTION - CUT BATTERS
4.1 | Batters | Required slope of 2h:1v, or follow the design drawings if they differ, regular inspections of the exposed soil. | 2h:1v Slope shear vane (2.5%) | PS:16.6.4 | Report Photos | Regular inspections | I | SE
SECTION 5 – CONSTRUCTION - LANDSCAPE
5.1 | Setting out Notice | Confirm that the site has been marked out according to the project plans and specifications before construction begins. | The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out. | PS 27.3.2 | Setting Out Notice Report | Before each stage | HP | ENG
5.2 | Site Grading | Grading for planting areas to ensure drainage. | Smooth, flowing contours with proper drainage. | NZTA P39: 2013, Section G PS 16.6.3 | Visual Inspection | 100% of areas | I | SE
5.3 | Tree Pit Excavation | Excavation of tree pits according to specified dimensions. | #VALUE! | 2-32735.02-WSP-DR-UDL 0402 Rev 1 | Checksheet | Per tree pit | I | SE
SECTION 6 – CONSTRUCTION - PLANTING
6.1 | Specimen and street trees | Correct staking and tree placement as per plan and specifications | Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation. | NZTA P39: 2013, Section G | Checksheet Photos | Each Tree | I | SE
6.2 | Timber Stakes | Timber stakes used for landscaping must be of specified type, treated to prevent decay, and meet size and quality requirements. 50mmx50mmx1500mm H4 Treated Pine Stakes | #VALUE! | NZTA P39: 2013, Section I | Delivery dockets Checksheet Photos | Per order | I | SE
6.3 | Fertilising | All plantings shall have two-year slow-release fertilizer tablets installed at the time of planting. | Fertiliser tablet placed in bottom of hole before planting. Fertiliser composition: 6:15:3 (N:P:K). Up to 14l is 1 tab, 45l is 4 tabs | NZTA P39: 2013, 3.13 | Checksheet Photos | Each Area | I | SE
SECTION 7 – CONSTRUCTION - MULCHING
7.1 | Mulch Spreading | Correct mulch application on flat sites | On sites flatter than a 1:3 grade (1.0m high by 3.0m metres long), mulch shall be spread evenly to a depth of 80-100mm after settlement, over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems. | NZTA P39: 2013, Section G | Checksheet Photos | Each Area | I | SE
SECTION 8 – CONSTRUCTION - WEED MAT
8.1 | Weed mat laps | Lap joints | On slopes steeper than 1:3 biodegradeable matting shall over lap 100mm between adjacent rolls and 500mm longitudinally | NZTA P39: 2013, Section G | Checksheet Photos | Each Area | I | SE
8.2 | Weed mat keys | Key in edges | On slopes steeper than 1:3 edges shall be keyed in to topsoil 150mm x 150mm | NZTA P39: 2013, Section G | Checksheet Photos | Each Area | I | SE
8.3 | Weed mat pins | Freqency of pins | On slopes steeper than 1:3 biodegradeable matting shall be pinned with frequency of 2 per m2 min. | NZTA P39: 2013, Section G | Checksheet Photos | Each Area | I | SE
SECTION 9 – CONSTRUCTION - GRASSING
9.1 | Establishment of sown areas | Apply grass seed as soon as practical after area is prepped. Protect newly established grass areas. | Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces. | NZTA P39: 2013, Section G | Checksheet Photos | Each Area | I | SE
SECTION 10 - POST CONSTRUCTION - AS-BUILTS
10.1 | As-Builts/ Red pen markup | As-Built records and drawings shall accurately record the layout and extents of all the work. | Record of work completed | PS 16.7.6 | Red pen markups | During Earthworks | D | SV
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - and Material data sheet
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - material data sheets and engineers approval
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - material data sheets and engineers approval
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - material data sheets and engineers approval
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - do we have a setting out notice report?
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - would this be part of your check sheet? if so add the check sheet number here not inspection report
Note on F22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - would this be in your check sheet? if so add the check sheet number here and remove site records
Note on F23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - delivery dockets?
Note on F24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - as per comment at 6.1
Note on F26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - remember that we close the ITP with red pen markups as survey as-builts form part of the final handover of the project, are you sure you will have as-builts at the time of closing this work pack out? or should this again just be photos and checksheet?
Note on F28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - as per comment in 6.1
Note on F32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - as per 6.1