## ITP Cover Page
Retaining Wall 3 - Magnum Stone Block Installation
Project: Tauriko Enabling Project SP2
Number and Revision: DN1210 - SP2 - 017-002 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 | [5 empty] | ITP Number: |  |  | 017-002
Project Number: |  |  | DN1210 - SP2 | [5 empty] | ITP Status: |  |  | Draft
ITP Description: |  |  | Retaining Wall 3 - Magnum Stone Block Installation | [5 empty] | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 | [5 empty] | Drawing Sets: |  |  | 2-32735.02-WSP-DR-GEO
Customer: |  |  | Waka Kotahi | [5 empty] | Specification: |  |  | Project specification
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [10 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval |  |  | Nick Adams & Cordelia Girdler-Brown | [6 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[11 empty] | B | Report by Breach |  | CR | Customer Rep
[11 empty] | C | Check |  | PD | Project Director
[11 empty] | D | Dimension Inspection |  | PM | Project Manager
[11 empty] | E | Examine |  | OP | Operations Manager
[11 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[11 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[11 empty] | I | Inspection |  | PE | Project Engineer
[11 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[11 empty] | O | Operation |  | QE | Quality Engineer
[11 empty] | R | Review |  | SUP | Superintendent / Supervisor
[11 empty] | S | Subcontractor |  | SV | Surveyor
[11 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[11 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [8 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: |  | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [6 empty] | Downer PM
Downer QM |  | Cordelia Girdler Brown | [6 empty] | Downer QM
Client (If Applicable) | [8 empty] | Client (If Applicable)
Note on P8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: what workpack number are we using here?
Note on P13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please add specific items of project spec

## ITP Master Body
Retaining Wall 3 - Magnum Stone Block Installation
0
Number and Revision: DN1210 - SP2 - 017-002 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
3.1 | Methodology | The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to construction | HP | ENG
3.2 | Ecology Sign Off | Confirmation from Ecology that earthworks and sheet piling can proceed | Email | Internal Hold Point | Email from Ecology NZ | Prior to construction | H | PE
3.3 | Erosion & Sedimentation Controls | Confirm that Erosion and Sedimentation Controls bunds are in place | As-built Completed | Internal Hold Point | ESC As-built | Prior to construction | H | PE
3.4 | Geotextile | The Contractor shall submit the full details of the Class C non-woven geotextile fabric to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Material certificate/NTC | Results to Engineer for Approval | HP | ENG
3.5 | Duraflow Drainage Mat | The Contractor shall submit the full details of the Duraflow Draininage fabric to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Material certificate/NTC | Results to Engineer for Approval | HP | ENG
3.6 | Crushing Resistance: Drainage aggregare /Structural fill - Used in subsoil fill | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.7 | Partical size distribution: Drainage aggregate/ structural fill - used in subsoil fill - | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Max Particle Size 53mm Max 10% passing 13.2mm sieve | Appendix XVIII | IANZ Accredited Report | 1 Test per 100m3 Results to Engineer 2wks before importing | HP | ENG
3.8 | Weathering Resistance : Drainage aggregate / Structural fill - used in subsoil fill - | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.9 | Magnum Stone Block | Magnum Stone blocks are to be supplied by an approved supplier. Concrete Compressive Strength Moisture Absorption Defects, chips and cracks | Minimum 28-day Compressive Strength of 30MPa (min.) Less than 6% Every Block | NZS 3104: 2003 AS/NZS 4456:2003 Method 14 | Supplier to provide QA Documents Visual Inspection | Prior to construction | H | PE
3.1 | Subsoil Drainage | Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated pipe with filter sock | Engineers Approval | P.S. 21.5.17 | Material certificate/NTC | Prior to construction | HP | ENG
3.11 | Concrete Footing | Concrete strength shall be min. 17.5MPa | Engineers Approval | A s per Drawing (232735.02-WSP-DR-UDL-0407) | Material certificate/NTC |  | HP | ENG
SECTION 4 – CONSTRUCTION - CUT SUBGRADE TESTING
4.1 | Cut Subgrade Inspection | Engineer to inspect all foundation surface inspections | Engineers Approval | Appendix V | Visual Observation | Across stripped area | HP | ENG
4.2 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa Single Test Min SU: >50kPa 2-3m deep | Appendix XVIII | Shear Vane Report | 0.5m interval 4 test per 400M2 | I | SE
4.3 | Cut Subgrade - Import Structural fill Release of Hold Point | To release the subgrade hold point and be able to start placing the Magnum Stone Blocks, the Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6 | Engineers Approval | PS 16.9.3 | CONQA Approval | Engineers Approval | HP | ENG
SECTION 5 – MAGNUM STONE BLOCK
5.1 | Leveling Pad and Duraflow Drainage | The Contractor shall construct a 150 mm thick levelling pad on top of the subgrade using AP40 to accept the Magnum Stone Block wall. Aggregate to be placed on geotextile filter fabric | Engineers Approval | As per Drawing (23273502-WSP-DR-GEO-0427) | Site Photo / Checksheet | Prior to Magnum Stone Block installation | I | SE
5.2 | Installation of blocks | Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances | Engineers Approval | As per Drawing (23273502-WSP-DR-GEO-0427) | Site Photo / Checksheet | Each layer | W | ENG
5.3 | Drainage Installation | A 110mm Drainage pipe wrapped in filter sock is to be installed along the internal perimeter of the blocks. Core through Magnum Stone blocks at 10m c/c, install PVC subsoil outlet. Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer. | Engineers Approval | PS 16.5.8 PS 16.6.10 PS 17.6.3 TNZ F/6 | Delivery Dockets/Installation Checksheet | No less than 24 hours prior to placement of backfill | W | ENG
5.4 | Duraflow Drainage Mat | · Side-to-side overlap: Ensure at least a minimum of 500mm overlap between adjacent rolls and at any joins. | Engineers Approval | As per Drawing (23273502-WSP-DR-GEO-0414) | Site Photo / Checksheet | During Insallation | W | ENG
5.5 | Backfill Installation | All backfill is to be installed in 300mm lifts and tested as below | Engineers Approval | As per Drawing (23273502-WSP-DR-GEO-0414) | Site Photo / Checksheet | Each layer | W | ENG
5.6 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Structural Fill Min CIV 18 Ave CIV 20 Non-Structural Fill Min CIV 10 Max CIV 12 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
5.7 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD Non Granular Material Max Air Voids 8% | Appendix XVIII | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE
SECTION 6 – AS-BUILTS
6.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. | As-build record | PS 16.7.6 | Survey Records/redpen markups | During Earthworks | D | SV
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NDM and Cleggs Reply: @is this NDM's or Clegg? if we need to do clegg we need a clegg requirement. Reply: See below tests Reply: @Jotham Makini thank you thought so