## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-033-001 ITP Landscaping | itp |  |  |  |  | DN1210-SP2-033-001 ITP Landscaping Rev 0
section | SECTION 3 – PRODUCT DATA SHEETS FOR ENGINEERS APPROVALS
checkpoint | 3.1 - Landscape Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Landscape including, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Geotextile Fabric
label | Detail - Geotextile fabric approval
label | Acceptance / Conformance Criteria - Class D geotextile fabric
label | Standard / Specification - PS 21.5.15
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Topsoil Analysis
label | Detail - Testing of on-site and imported topsoil for quality.
label | Acceptance / Conformance Criteria - Topsoil must meet the criteria specified in the project standards.
label | Standard / Specification - NZTA P39: 2013, Section F
label | Verifying Document - Soil Testing Report
label | Testing Quantity Required (based from schedule qtys) - Once per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Mulch Material Verification
label | Detail - Verify that the mulch used meets the specified criteria (e.g., pallet mulch, arborist mulch).
label | Acceptance / Conformance Criteria - Mulch material should be free of contaminants, sufficiently aged, and appropriate to site and slope conditions
label | Standard / Specification - NZTA P39: 2013 Section 3.9
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - 100% of mulch used
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Biodegradeable Weed Mat
label | Detail - Biodegradeable weed mat approval
label | Acceptance / Conformance Criteria - 450 GSM, 7mm thick, biodegradeable weed mat
label | Standard / Specification - PS 27.3.8
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Hydro-seeding
label | Detail - Grass mix approved
label | Acceptance / Conformance Criteria - Send seed mix to engineer for approval
label | Standard / Specification - NZTA P39: 2013, Section F
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Once prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION - CUT BATTERS
checkpoint | 4.1 - Batters
label | Detail - Required slope of 2h:1v, or follow the design drawings if they differ, regular inspections of the exposed soil.
label | Acceptance / Conformance Criteria - 2h:1v Slope
label | ○ Shear vane (2.5%)
label | Standard / Specification - PS:16.6.4
label | Verifying Document - Report, Photos
label | Testing Quantity Required (based from schedule qtys) - Regular inspections
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION - LANDSCAPE
checkpoint | 5.1 - Setting out Notice
label | Detail - Confirm that the site has been marked out according to the project plans and specifications before construction begins.
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out.
label | Standard / Specification - PS 27.3.2
label | Verifying Document - Setting Out Notice Report
label | Testing Quantity Required (based from schedule qtys) - Before each stage
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Site Grading
label | Detail - Grading for planting areas to ensure drainage.
label | Acceptance / Conformance Criteria - Smooth, flowing contours with proper drainage.
label | Standard / Specification - NZTA P39: 2013, Section G, PS 16.6.3
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - 100% of areas
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3 - Tree Pit Excavation
label | Detail - Excavation of tree pits according to specified dimensions.
label | Acceptance / Conformance Criteria - TABLE 1
label | – – – – – – – – – – – – –
label | PLANT SIZE (LITRE / PB) ¦¦ NO. OF STAKES ¦¦ TREE PIT SIZE
label | LESS THAN 15 LT / PB28 ¦¦ 1 ¦¦ 2X SIZE OF ROOT BALL
label | 45LT / PB95 ¦¦ 3 ¦¦ 1000x1000x1000 mm
label | – – – – – – – – – – – – –
label | Standard / Specification - 2-32735.02-WSP-DR-UDL 0402 Rev 1
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - Per tree pit
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – CONSTRUCTION - PLANTING
checkpoint | 6.1 - Specimen and street trees
label | Detail - Correct staking and tree placement as per plan and specifications
label | Acceptance / Conformance Criteria - Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Each Tree
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2 - Timber Stakes
label | Detail - Timber stakes used for landscaping must be of specified type, treated to prevent decay, and meet size and quality requirements. 50mmx50mmx1500mm H4 Treated Pine Stakes
label | Acceptance / Conformance Criteria - TABLE 1
label | – – – – – – – – – – – – –
label | PLANT SIZE (LITRE / PB) ¦¦ NO. OF STAKES ¦¦ TREE PIT SIZE
label | LESS THAN 15 LT / PB28 ¦¦ 1 ¦¦ 2X SIZE OF ROOT BALL
label | 45LT / PB95 ¦¦ 3 ¦¦ 1000x1000x1000 mm
label | – – – – – – – – – – – – –
label | Standard / Specification - NZTA P39: 2013, Section I
label | Verifying Document - Delivery dockets, Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Per order
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3 - Fertilising
label | Detail - All plantings shall have two-year slow-release fertilizer tablets installed at the time of planting.
label | Acceptance / Conformance Criteria - Fertiliser tablet placed in bottom of hole before planting. Fertiliser composition: 6:15:3 (N:P:K). Up to 14l is 1 tab, 45l is 4 tabs
label | Standard / Specification - NZTA P39: 2013, 3.13
label | Verifying Document - Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 7 – CONSTRUCTION - MULCHING
checkpoint | 7.1 - Mulch Spreading
label | Detail - Correct mulch application on flat sites
label | Acceptance / Conformance Criteria - On sites flatter than a 1:3 grade (1.0m high by 3.0m metres long), mulch shall be spread evenly to a depth of 80-100mm after settlement, over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 8 – CONSTRUCTION - WEED MAT
checkpoint | 8.1 - Weed mat laps
label | Detail - Lap joints
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 biodegradeable matting shall over lap 100mm between adjacent rolls and 500mm longitudinally
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.2 - Weed mat keys
label | Detail - Key in edges
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 edges shall be keyed in to topsoil 150mm x 150mm
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.3 - Weed mat pins
label | Detail - Freqency of pins
label | Acceptance / Conformance Criteria - On slopes steeper than 1:3 biodegradeable matting shall be pinned with frequency of 2 per m2 min.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 9 – CONSTRUCTION - GRASSING
checkpoint | 9.1 - Establishment of sown areas
label | Detail - Apply grass seed as soon as practical after area is prepped. Protect newly established grass areas.
label | Acceptance / Conformance Criteria - Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces.
label | Standard / Specification - NZTA P39: 2013, Section G
label | Verifying Document - Checksheet, Photos
label | Testing Quantity Required (based from schedule qtys) - Each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 10 - POST CONSTRUCTION - AS-BUILTS
checkpoint | 10.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work.
label | Acceptance / Conformance Criteria - Record of work completed
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP2-017-002 ITP Retaining Wall 3 Magnum Block | itp |  |  |  |  | DN1210-SP2-017-002 ITP Retaining Wall 3 Magnum Block Rev 0
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1 - Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Ecology Sign Off
label | Detail - Confirmation from Ecology that earthworks and sheet piling can proceed
label | Acceptance / Conformance Criteria - Email
label | Standard / Specification - Internal Hold Point
label | Verifying Document - Email from Ecology NZ
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.3 - Erosion & Sedimentation Controls
label | Detail - Confirm that Erosion and Sedimentation Controls bunds are in place
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.4 - Geotextile
label | Detail - The Contractor shall submit the full details of the Class C non-woven geotextile fabric to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7, Appendix V
label | Verifying Document - Material certificate/NTC
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Duraflow Drainage Mat
label | Detail - The Contractor shall submit the full details of the Duraflow Draininage fabric to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7, Appendix V
label | Verifying Document - Material certificate/NTC
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Crushing Resistance: Drainage aggregare /Structural fill - Used in subsoil fill
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Partical size distribution: Drainage aggregate/ structural fill - used in subsoil fill
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Max Particle Size 53mm
label | ○ Max 10% passing 13.2mm sieve
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per 100m3
label | ○ Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Weathering Resistance: Drainage aggregate / Structural fill - used in subsoil fill
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Magnum Stone Block
label | Detail - Magnum Stone blocks are to be supplied by an approved supplier.
label | ○ Concrete Compressive Strength
label | ○ Moisture Absorption
label | ○ Defects, chips and cracks
label | Acceptance / Conformance Criteria - Minimum 28-day
label | ○ Compressive Strength of 30MPa (min.)
label | ○ Less than 6%
label | ○ Every Block
label | Standard / Specification - NZS 3104: 2003, AS/NZS 4456:2003, Method 14
label | Verifying Document - Supplier to provide QA Documents, Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.10 - Subsoil Drainage
label | Detail - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated pipe with filter sock
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - P.S. 21.5.17
label | Verifying Document - Material certificate/NTC
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Concrete Footing
label | Detail - Concrete strength shall be min. 17.5MPa
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - A s per Drawing (232735.02-WSP-DR-UDL-0407)
label | Verifying Document - Material certificate/NTC
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION - CUT SUBGRADE TESTING
checkpoint | 4.1 - Cut Subgrade Inspection
label | Detail - Engineer to inspect all foundation surface inspections
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Cut Subgrade Testing - Cohesive Soil, Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU:
label | ○ > 60kPa
label | Single Test Min SU:
label | ○ >50kPa
label | ○ 2-3m deep
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 0.5m interval, 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3 - Cut Subgrade - Import Structural fill, Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing the Magnum Stone Blocks, the Contractor shall provide written certification that all inspected and tested subgrade complies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - CONQA Approval
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – MAGNUM STONE BLOCK
checkpoint | 5.1 - Leveling Pad and Duraflow Drainage
label | Detail - The Contractor shall construct a 150 mm thick levelling pad on top of the subgrade using AP40 to accept the Magnum Stone Block wall.
label | ○ Aggregate to be placed on geotextile filter fabric
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0427)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Magnum Stone Block installation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2 - Installation of blocks
label | Detail - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances
label | – – – – – – – – – – – – –
label | Table 4: MSE Tolerances
label | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
label | – – – – – – – – – – – – –
label | Soil Surface ¦¦ ±100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
label | Facings and wall structures ¦¦ ±50mm ¦¦ ±50mm ¦¦ ±20mm in 30m ¦¦ ±20mm in 3m
label | Footings or supports ¦¦ ±50mm ¦¦ ±50mm ¦¦ ±20mm in 3m ¦¦ ±20mm in 3m
label | – – – – – – – – – – – – –
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0427)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each layer
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.3 - Drainage Installation
label | Detail - A 110mm Drainage pipe wrapped in filter sock is to be installed along the internal perimeter of the blocks.
label | ○ Core through Magnum Stone blocks at 10m c/c, install PVC subsoil outlet.
label | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.8, PS 16.6.10, PS 17.6.3, TNZ F/6
label | Verifying Document - Delivery Dockets/Installation Checksheet
label | Testing Quantity Required (based from schedule qtys) - No less than 24 hours prior to placement of backfill
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.4 - Duraflow Drainage Mat
label | Detail - Side-to-side overlap: Ensure at least a minimum of 500mm overlap between adjacent rolls and at any joins.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0414)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Insallation
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.5 - Backfill Installation
label | Detail - All backfill is to be installed in 300mm lifts and tested as below
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - As per Drawing (23273502-WSP-DR-GEO-0414)
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each layer
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 5.6 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill
label | ○ Min CIV 18
label | ○ Ave CIV 20
label | Non-Structural Fill
label | ○ Min CIV 10
label | ○ Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.7 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Non Granular Material:
label | ○ Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 – AS-BUILTS
checkpoint | 6.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - As-build record
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records/redpen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature