## ITP Cover Page
Landscape Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210-SP2 - 033-002 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 033-002
Project Number: |  |  | DN1210-SP2 |  |  |  |  | ITP Status: |  |  | Approved
ITP Description: |  |  | Landscapeencing |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-UDL
Customer: |  |  | NZTA |  |  |  |  | Specification: |  |  | Project Specification, NZTA P39:2013 Section F, Section 3.9
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft | 2025-01-04 |  | Cordelia Girdler-Brown & Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved | 29/04/2025 |  | Cordelia Girdler-Brown & Nick Adams | [5 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams |  |  | #VALUE! |  | 29/04/2025 | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 29/04/2025 | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Landscape Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210-SP2 - 033-002 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION - PERSONELL, MATERIAL APPROVAL AND THIRD PARTY APPROVALS
3.1 | Extent of Line Setout | Ensure line and level of Fences has been marked out and agreed with Engineer in accordance with fence drawings. | Engineers Approval | Design Drawings | ITP Sign Off | Prior to Construction & Every Revision of IFC Drawings/Data. | HP | ENG
3.2 | Timber (Rails/palings/battens) Posts | Treatment | H4 H5 if touching ground otherwise H4 | PS 27.5.5 NZS3607:1989 | Data sheet Delivery Docket | Prior Construction | HP | SE
3.3 | Steel (Post/Metal fence) | 6063 T5 aluminium or equivalent metal | New Zealand building code clauses B1, F4. design loading is up to 0.75kN/m | PS 27.5.1 PS 22.5.6 PS 2-32735.02-WSP-DR-UDL-0407 | Data sheet Delivery Docket | Prior Construction | HP | SE
3.4 | Material (Fixings/fasteners/hinges) | Jointing | Hot dip galvanised | PS 27.5.1 | Data sheet Delivery Docket | Prior Construction | HP | SE
3.5 | Concrete | Ground planted posts | 17.5MPa | PS 27.5.5 | Data sheet Delivery Docket | Prior Construction | HP | SE
SECTION 4 – CONSTRUCTION - 1.5m BALUSTRADE FENCE
4.1 | Subgrade testing | Install around the Carpark Black powder coated finish Shear vane testing of every 4th post | min 100 kpA | DN1210-WSP-NTC-0574 | Testing Dockets | During installation | H | SE
4.2 | 1.5m Balustrade Fence | Install around the Carpark Black powder coated finish | 1.5 metres high, hot dipped galvanised and installed as per the drawings | PS 2-32735.02-WSP-DR-UDL-0407 PS 27.5.1 PS 27.5.3 | Delivery docket CKT1210-033-001 | During installation | M | SE
4.2 | Carpark Vehicle Gate | Install around the Carpark Black powder coated finish | Double swing gate hinges both sides two lockable post Pad Lock supplied to school | PS:27.5.3 | Delivery docket CKT1210-033-001 | During installation | M | SE
4.3 | Carpark Pedestrian Gate | Install around the Carpark Black powder coated finish | To be fitted with child safety locks Gate to be open with no obstructions | To be fitted with child safety locks Gate to be open with no obstructions | Delivery docket CKT1210-033-001 | During installation | M | SE
SECTION 5 – CONSTRUCTION - 1.8m TIMBER PALING FENCE
5.1 | Timber fence | Preserve timber exposed faces Post imbedded in ground | 1.8m high Exposed timber faces neatly protected with 2 coats of timber preservative (Metalex) 1800mm in ground with 17.5MPa concrete Minimum 100mm extend around the post | PS 27.5.5 | Delivery docket CKT1210-033-002 | During installation | M | SE
SECTION 6 – POST CONSTRUCTION - AS-BUILTS
6.1 | As-Builts/ Red pen markup | As-Built records and drawings shall accurately record the layout and extents of all the work. | Record of work completed | PS 16.7.6 | Red pen markups | After instalation | D | SV
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - remember pre-construction approvals of materials is before the material is delivered to site, therefore this will be product data sheets and Engineers approval, this will be for all pre-construction material approvals, item 3.1-3.5 Reply: Can I put both Data sheet and Delivery doc in the section just so it's easier to close out if I can't find the data sheets? Reply: @Daniel Barnard that's fine but it has to have the engineers approval
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard - for these you can add the check sheet number as you have already populated these
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Daniel Barnard as above