## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-033-002 ITP Landscape Fencing | itp |  |  |  |  | DN1210-SP2-033-002 ITP Landscape Fencing Rev 1
section | SECTION 3 – PRE-CONSTRUCTION - PERSONELL, MATERIAL APPROVAL AND THIRD PARTY APPROVALS
checkpoint | 3.1 - Extent of Line Setout
label | Detail - Ensure line and level of Fences has been marked out and agreed with Engineer in accordance with fence drawings.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction & Every Revision of IFC Drawings/Data.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Timber (Rails/palings/battens) Posts
label | Detail - Treatment
label | Acceptance / Conformance Criteria - H4
label | ○ H5 if touching ground otherwise H4
label | Standard / Specification - PS 27.5.5, NZS3607:1989
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Steel (Post/Metal fence)
label | Detail - 6063 T5 aluminium or equivalent metal
label | Acceptance / Conformance Criteria - New Zealand building code clauses B1, F4. design loading is up to 0.75kN/m
label | Standard / Specification - PS 27.5.1, PS 22.5.6, PS 2-32735.02-WSP-DR-UDL-0407
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Material (Fixings/fasteners/hinges)
label | Detail - Jointing
label | Acceptance / Conformance Criteria - Hot dip galvanised
label | Standard / Specification - PS 27.5.1
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Concrete
label | Detail - Ground planted posts
label | Acceptance / Conformance Criteria - 17.5MPa
label | Standard / Specification - PS 27.5.5
label | Verifying Document - Data sheet, Delivery Docket
label | Testing Quantity Required (based from schedule qtys) - Prior Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - SE
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION - 1.5m BALUSTRADE FENCE
checkpoint | 4.1 - Subgrade testing
label | Detail - Install around the Carpark
label | ○ Black powder coated finish
label | ○ Shear vane testing of every 4th post
label | Acceptance / Conformance Criteria - min 100 kpA
label | Standard / Specification - DN1210-WSP-NTC-0574
label | Verifying Document - Testing Dockets
label | Testing Quantity Required (based from schedule qtys) - During installation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.2 - 1.5m Balustrade Fence
label | Detail - Install around the Carpark
label | ○ Black powder coated finish
label | Acceptance / Conformance Criteria - 1.5 metres high, hot dipped galvanised and installed as per the drawings
label | Standard / Specification - PS 2-32735.02-WSP-DR-UDL-0407, PS 27.5.1, PS 27.5.3
label | Verifying Document - Delivery docket, CKT1210-033-001
label | Testing Quantity Required (based from schedule qtys) - During installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.2 - Carpark Vehicle Gate
label | Detail - Install around the Carpark
label | ○ Black powder coated finish
label | Acceptance / Conformance Criteria - Double swing gate hinges both sides two lockable post
label | ○ Pad Lock supplied to school
label | Standard / Specification - PS:27.5.3
label | Verifying Document - Delivery docket, CKT1210-033-001
label | Testing Quantity Required (based from schedule qtys) - During installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 4.3 - Carpark Pedestrian Gate
label | Detail - Install around the Carpark
label | ○ Black powder coated finish
label | Acceptance / Conformance Criteria - To be fitted with child safety locks
label | ○ Gate to be open with no obstructions
label | Standard / Specification - To be fitted with child safety locks
label | ○ Gate to be open with no obstructions
label | Verifying Document - Delivery docket, CKT1210-033-001
label | Testing Quantity Required (based from schedule qtys) - During installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION - 1.8m TIMBER PALING FENCE
checkpoint | 5.1 - Timber fence
label | Detail - Preserve timber exposed faces
label | ○ Post imbedded in ground
label | Acceptance / Conformance Criteria - 1.8m high
label | ○ Exposed timber faces neatly protected with 2 coats of timber preservative (Metalex)
label | ○ 1800mm in ground with 17.5MPa concrete
label | ○ Minimum 100mm extend around the post
label | Standard / Specification - PS 27.5.5
label | Verifying Document - Delivery docket, CKT1210-033-002
label | Testing Quantity Required (based from schedule qtys) - During installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 6 – POST CONSTRUCTION - AS-BUILTS
checkpoint | 6.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work.
label | Acceptance / Conformance Criteria - Record of work completed
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - After instalation
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature