## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Generic - Bus Infrastructure - Bus Shelter | itp | ITP - Bus Shelter | 054cec3f-15e8-4056-9121-e77d4a866dac
| section | Construction
| checkpoint | 1 - Survey Setout
c3943d97-1a49-59ed-9fd0-7fd8ff01fc30 | note | VERIFICATION ACTIVITY: Survey
babe8996-0ca3-5017-9956-6c01b21d5082 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
81d7c0e9-ea2a-56bb-8378-783f12bfd08b | note | FREQUENCY: Prior to commencement.
a4d35720-8ec8-5181-870c-ab64f573541c | note | ACCEPTANCE CRITERIA: Survey
df66a6cf-1cd5-545e-86f6-7d2d281f79cc | note | HOLD POINT: As per Drawings
c0452d5b-a9ae-58cb-aa67-9f742405696d | note | RECORDS: Survey Receipt.
a07dcf43-ca53-5142-901f-f5e3546ce0f5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Bus Shelter pad
8347d1c7-b702-56f0-8cd2-f48406e573c9 | note | VERIFICATION ACTIVITY: QA FORM/ Drawings
12def047-9b42-56ee-a9d4-62e9c3339aa6 | note | METHODS OR REFERENCE: Construction Drawings
e282b915-b82b-50a8-854b-78ed47fb2c95 | note | FREQUENCY: Each Site
00a6f39a-b3d7-556c-95cb-82f6f2e5c627 | note | ACCEPTANCE CRITERIA: 200mm depth of 20MPa Concrete with 2 layers of 665 mesh, 4kg/m3 black oxide and Broom Finish
69174623-7f43-545a-9b88-e2042d067612 | note | HOLD POINT: Inprocess Inspection
71db93a4-8af0-5bed-a101-284da0934238 | note | RECORDS: Photos
14a20aba-4760-5c49-8c90-a68075841865 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 7 - As built information
ed194f42-d87a-5fab-8511-fc98efc66137 | note | VERIFICATION ACTIVITY: Drawings
3346bf15-a17b-5989-9725-d4eaeb955406 | note | METHODS OR REFERENCE:
dc3ea939-e100-5787-99d6-cc7c2fcbc3e5 | note | FREQUENCY: Every Site
70e13b1b-0324-5776-9d25-40be28977557 | note | ACCEPTANCE CRITERIA: As built drawings
10995edf-32aa-5d07-b1d1-ea6b724b4060 | note | HOLD POINT: In Process Inspection
d5bf2a20-ee02-5b31-a246-c944e8c30aa2 | note | RECORDS: Asbuilt records
a86c7373-73d0-50a4-95f9-6d30469fc9d1 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
3a7a1281-9fef-5945-be76-a4bcb20f1126 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
16c12c1a-3bfe-552d-af37-0e1dc68a4ffe | note | METHODS OR REFERENCE:
8a1c752a-44ed-5761-a371-694d6d596acf | note | FREQUENCY: Every Site
f7a042bd-7f31-5cf1-9b1f-f0271edff38e | note | ACCEPTANCE CRITERIA: RAMM SHEET
9b2bbed8-dbb9-5d81-8e5f-617654b74397 | note | HOLD POINT: In Process Inspection
5989db73-0794-5b24-8535-396f976addd0 | note | RECORDS: Asbuilt records
e80ac088-a1b8-5058-b859-ffe7a79fdf46 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
041d8bdd-0ca1-5fb2-b425-d8e7591b6526 | note | Prepared by: Nithin Thomas
2b9116d1-881b-569d-afa4-b8f7163508d7 | note | Approving Delegate: Daniel Tat
| checklist | Generic - Bus Infrastructure - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | 4c43840d-7b3c-44ab-aa37-8f5b1855810e
| section | Site Set Out
| checkpoint | 1 - Site Set out
935eac04-fa8b-5d7c-97a3-eff1f94f5217 | note | VERIFICATION ACTIVITY: Surveyor
7ff4f390-255e-5b39-9f14-cbe95fe51d95 | note | METHODS OR REFERENCE: Surveyor
1e53c8c4-d5a1-5b20-93c4-8e348df1e58a | note | FREQUENCY: Everysite
0302ad36-c6d2-5e75-a83f-359d8f54b461 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers.
4986d3d9-cb59-5ff5-b93e-0676ec97a1f0 | note | HOLD POINT: Mandatory HOLD POINT -
63242006-4cc8-51a8-ac46-80d49a085963 | note | RECORDS: Onsite records/photos
1f0f2d68-c4ba-56ad-9b7b-07de0ea9e7b6 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
55b3f212-5673-58d6-b7a2-f0792975a0d1 | note | VERIFICATION ACTIVITY: QA FORM
b5225fbf-9f9e-52c1-9b12-de28c3d63106 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
95e6bad1-c87e-5873-96ec-276646ad79ac | note | FREQUENCY: Everysite
eda51093-a639-5ec6-94f7-8ed750350bd3 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
1f1431f0-48e2-55e9-acdd-155b271c721b | note | HOLD POINT: Inprocess Inspection
69bdcd1c-6d67-5f5d-988e-0bb7d1e7ec26 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
15af9321-fa29-5bd7-bfb5-e8c407d974a9 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Channel Level
44a6b62c-ac5e-55aa-b6a4-bce346a92865 | note | VERIFICATION ACTIVITY: QA FORM
a7bd5157-c961-5ae6-9ad2-99c2cc2e2446 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
4afadc93-b3c2-552d-8ac0-613ab2e4d485 | note | FREQUENCY: Everysite
116392ba-1017-50ff-9a65-cb42d1b65557 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
3a1e996d-9993-5906-9f2c-162a03676e21 | note | HOLD POINT: Inprocess Inspection
6dbcf3c2-4300-52a1-97dd-f3ea8e69e828 | note | RECORDS: FH concrete QA sheet, Photos
e8ab455a-1874-5e6d-be3f-d156518d85d9 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
b754f9d2-5e48-518c-b512-665d34829b25 | note | VERIFICATION ACTIVITY: QA FORM
16ca6a98-fe58-5579-817c-a3d13abfe2f2 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
e4b2f3ec-9abc-5f4b-825f-b1016765f0b0 | note | FREQUENCY: 10m Intervals
aa58c35d-7927-5614-94f7-6c65e23de8fa | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
954e4332-be4b-56d9-9eea-877e057679ad | note | ○ Clegg CIV > 12
cffb2d8a-592c-5ac5-9540-488e2a7f2165 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
f2ad8763-381b-55ce-8e3f-1c0d3bbedf2f | note | HOLD POINT: Inprocess Inspection
142001d2-08ed-58e2-81f8-f57ca2b04de5 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
dbe788c9-5fb4-55d0-bdff-77bdcd8c7a4c | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Tactiles
66beebe9-c271-5b22-aa01-c527e508dd7a | note | VERIFICATION ACTIVITY:
61a70e2d-06d6-5224-8a8a-df2c1b60c34f | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
79c6c2a3-e62f-56e7-8817-091523d7e2ec | note | FREQUENCY: Each PX
2b8147e7-5c4e-5c3b-b02a-262c3ba0bbce | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 150mm concrete slab underneath
306b7780-09b0-54cf-a644-81e48e7d1c6f | note | HOLD POINT: Inprocess Inspection, Measurement
f18ed93f-d6d5-572b-88e1-9954e1166c60 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
9c185195-e1e2-54f7-bcb8-2925e61ab921 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5.1 - Tactiles
8ea72a42-2902-5260-865f-3a28a1f34b37 | note | VERIFICATION ACTIVITY: Visual
54f9e5e7-0dde-5d9c-b075-18456b5a4cda | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
eaade4e5-237b-5c82-a8fc-f1ffb29efabe | note | FREQUENCY: Everysite
4eb3442c-5735-57c3-80b3-580df17a781c | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
c733c6c3-d4d1-5556-942d-acee66f58642 | note | HOLD POINT: Inprocess Inspection
58f4054a-0596-5266-a321-e06140120312 | note | RECORDS: Photos
4ee68c75-8673-5c50-8e1d-a874ebeee661 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Grass Berms
17ed4f1b-f6cc-5403-b208-033ce9ab11ab | note | VERIFICATION ACTIVITY: Visual
1271b429-20c0-5ef0-8ddb-536617679c15 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
87cfded4-2b92-5b0d-88c3-3f3d2d123b74 | note | FREQUENCY: 10m Intervals
3789ab50-65ad-5aa8-91c3-10105af661c2 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
e24cd327-b744-5490-8343-230ce7b987c8 | note | HOLD POINT: Inprocess Inspection
d418998f-46e6-57d2-90af-a1ee690332e5 | note | RECORDS: Photos
792b2c28-ea16-5fb4-9911-420c711001ef | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 7 - As built information
bed8227b-7af3-581e-8406-614bfaaec54b | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
d92d91f1-c9d0-5cf7-be03-1c091870a34b | note | METHODS OR REFERENCE:
0ba3cb2e-752f-5429-9060-cc53a5b6e79f | note | FREQUENCY: Every Site
cf1b5abe-d118-5805-be37-81fa8e4a8e94 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
36ed947e-20ae-5828-b0e2-1047fc6094c4 | note | HOLD POINT: In Process Inspection
0882c022-a8b4-57b6-b867-7213a75a4792 | note | RECORDS: Asbuilt records
61ddec4a-8518-5082-9c69-e2820b76f350 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
f99b2e6d-8438-5201-99b3-092a114ce577 | note | Prepared by: Nithin Thomas
b555e364-5542-569e-9538-c1b186786023 | note | Approving Delegate: Daniel Tat
| checklist | Generic - Bus Infrastructure - Signage | itp | ITP - Signage | 265e0d08-6e31-4f8f-aecf-6585d9011c82
| section | Site Set Out
| checkpoint | 1 - Site Set out
9fecc43d-6d49-5c66-b760-53ebcbf3091d | note | VERIFICATION ACTIVITY: Surveyor
078e4f56-c979-5cf7-9f68-75bfa8ac127c | note | METHODS OR REFERENCE: Surveyor
e42bc0d9-9fa1-5aee-a687-5e5282a7065b | note | FREQUENCY: Everysite
7eab3776-7514-519e-b3a3-380380aa3e62 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
f44e1a12-1846-575b-9714-1fbde0d62511 | note | ○ Alternatively like for like
a20a1e26-2d1e-5fe1-b509-0969df6edd60 | note | HOLD POINT: Mandatory HOLD POINT -
382a7e07-1b2e-5e3e-9dec-7de043d220eb | note | RECORDS: Survey Receipt
623b30d8-dadd-52b3-8fd5-751bff21ecdb | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Pole, Impact recovery post and Ground Socket
0ada7ab3-a3c9-5dc4-9526-fd12b75b7d51 | note | VERIFICATION ACTIVITY: QA FORM
2dd218e8-ac4b-5d6b-9885-c8e3c8506d3d | note | METHODS OR REFERENCE: TDM Technical Standards
e98625cc-a71c-544e-9a47-5493ac52b9d5 | note | FREQUENCY: Every site
a5279c5e-8bc0-5294-b3e7-0a898f6dcde0 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
b1cd75fd-377d-5047-8c70-944db3b6f013 | note | HOLD POINT: Inprocess Inspection
29550d61-4a4a-5d30-8b16-f5de9d73b03e | note | RECORDS: Dockets/Photos
4649ae1c-c6b3-5b95-a159-19860cb113c9 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Ground Socket
8f16286d-9ac8-5ab2-a31c-0b83b6b8473d | note | VERIFICATION ACTIVITY: QA FORM
bd62749b-e4ad-5f33-9f5d-dd4118ce50bd | note | METHODS OR REFERENCE: TDM Technical Standards
08f56f5f-1019-5e3d-8363-f81a756881bf | note | FREQUENCY: Each Socket
76673ff7-cce8-5133-adb2-152a01dd85d1 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
57692653-e397-5c32-afa9-b6f53effb5e3 | note | HOLD POINT: Inprocess Inspection
5bda6f5e-9806-5b78-b2e8-1dbd820280e7 | note | RECORDS: Dockets/Photos with tape measurement
4c3f31a1-bc9d-57c7-806b-78d092d34afa | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 4 - As built information
b7e5eac2-3dd5-5fd1-8072-3e5514d0c72c | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
b3075286-20fa-5e84-9de4-1a3041363485 | note | METHODS OR REFERENCE:
bd190e6c-f30c-53c8-b3c0-638f379617dc | note | FREQUENCY: Every Site
919b7770-ead5-56aa-a459-d72dd522ba42 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
efc54e68-ca23-5cef-89d4-2e05a6954c3b | note | HOLD POINT: In Process Inspection
6b540506-4377-5257-bdab-743f0555bd74 | note | RECORDS: Asbuilt records
fa73c7a6-5cdc-5d5c-8d87-2965daac69c5 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
ecc2360a-9fd4-5bc6-aa88-0309ffed60c0 | note | Prepared by: Nithin Thomas
fe27343b-3144-5c41-a963-5829fb165e35 | note | Approving Delegate: Daniel Tat
| checklist | Generic - Bus Infrastructure - Traffic Islands | itp | ITP - Traffic Islands | 8daaaa8b-93aa-4111-8b21-b2d152832e44
| section | Materials
| checkpoint | 1 - Mountable Kerb
2af43f67-8dc6-567f-9816-b8d09ee7e82f | note | VERIFICATION ACTIVITY: QA FORM
979c0afe-1ee5-55ba-b278-0804b9a666c9 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
4b64f82b-6b4c-59b1-ad53-d93c6480e6ae | note | FREQUENCY: Everysite
8978eb7e-927b-5932-8d1c-92a39772d9d8 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
f799698b-4cc5-556a-b055-f1dad40e6008 | note | HOLD POINT: Inprocess Inspection
30ebbcc9-5061-5a3e-8dd8-2c66999f5cd1 | note | RECORDS: FH concrete QA sheet, photos.
938ef849-5c41-51ab-b88d-fa6ea39e56ab | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
fdecbb99-d130-54f7-95a8-9a55fbf69ae5 | note | VERIFICATION ACTIVITY: Survey
4f53c7d5-7bc5-50b9-a083-f6d2c903c457 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
45142fb5-39ea-5b3b-b0ee-090982e65037 | note | FREQUENCY: Prior to commencement.
61c30623-5ef5-5c23-8e38-14123b21fc47 | note | ACCEPTANCE CRITERIA: Survey
7ff96b78-3fec-5ca5-b538-7ddfa57a9250 | note | HOLD POINT: As per Construction Drawings
9f3bd67e-b154-5f79-8798-4b1f5773efc2 | note | RECORDS: Survey Receipt.
2e816f4f-d755-5bc0-8586-58a694ddbcb4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
802ebf7f-5123-59bc-b7dd-022b5820794f | note | VERIFICATION ACTIVITY: QA FORM
5d8a9446-8d60-5f19-8a1e-32a64699871e | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
be7ccdc4-8fb5-56a4-b554-a3df3be8fdf0 | note | FREQUENCY: Each Site
3d3feb6d-b2f8-52e3-85da-9d34b52db2aa | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
58785a0f-5660-5332-9e0c-a6a75fa5c69b | note | HOLD POINT: Inprocess Inspection
a999765e-2150-5be5-a2d1-d19f8414f4d1 | note | RECORDS: Photos
1c202af7-dcf0-58e5-abe5-920bf6632acf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
a046f1bf-5bb1-50af-b980-862312530a37 | note | VERIFICATION ACTIVITY: QA FORM
0d897077-95da-5fe3-92eb-01abe5ad8136 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
02a43fcf-51ce-5780-8ffe-ee31699aa9b4 | note | FREQUENCY: Each Site
12eaf165-24df-55ee-af3c-28d16074ecf0 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
d2c0af07-0dd4-53f1-847f-0e4d9282d309 | note | HOLD POINT: Inprocess Inspection
25dfd585-97d5-5102-b8bf-5de9af4f20f1 | note | RECORDS: Photos
953f2395-a473-57ba-9e30-91574c206924 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
9dbb9539-5bd6-5b5a-bb65-c76c2cae5218 | note | VERIFICATION ACTIVITY: QA FORM
cce26bd6-156d-5679-aa54-d733ba312a16 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
db6ca193-da82-5b60-aef7-3fec43815dad | note | FREQUENCY: Each Site
83f0fe3e-6adc-5011-b36d-dafd5902919f | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide
efc6a48b-7f92-5e4d-acf8-8c1173280362 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
4e9ce296-0e0d-595f-8a49-f8d3c6858b65 | note | HOLD POINT: Inprocess Inspection
66bd105a-2547-5ec7-9f3c-c4bce97f2cf7 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
550da1ce-3ec9-53cd-aff0-efcdc8f71a72 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
174080a3-9e76-5c65-b287-777b9b35071e | note | VERIFICATION ACTIVITY: Drawings
56e15461-3805-5359-afe3-29aa919b9659 | note | METHODS OR REFERENCE:
f69e5d9f-83f1-5775-9e60-889f22bd8d18 | note | FREQUENCY: Every Site
85f91bf8-6c2a-5164-973e-b99b3ca4e58a | note | ACCEPTANCE CRITERIA: As built drawings
c52ba5d5-c953-5894-b02c-3362ff53c3f8 | note | HOLD POINT: In Process Inspection
e86cd3a9-248d-5bab-bb60-03086f01f7ed | note | RECORDS: Asbuilt records
30609af5-6034-5a43-b2fd-7934b0eec6b9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
beedae63-e54b-5924-a4f7-0d6c99c95f42 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
e11bbb0f-0ab4-5352-8c6b-29853bb90482 | note | METHODS OR REFERENCE:
98cad007-b05a-504a-9370-2d7c558b4d70 | note | FREQUENCY: Every Site
695b8b2c-334d-56f4-b11a-75d21e9f3b89 | note | ACCEPTANCE CRITERIA: RAMM SHEET
4518c7a9-2246-5569-857d-a3b7749bcc98 | note | HOLD POINT: In Process Inspection
fd11d08f-5cad-5a83-b6cb-3007d6e90fd7 | note | RECORDS: Asbuilt records
8918707a-4e85-5ea8-9578-ce53743011b8 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
ab9e5af8-305e-5fe3-b118-64a6132f5f4c | note | Prepared by: Nithin Thomas
81a816d9-d4c1-5963-a001-03deb04f0a7f | note | Approving Delegate: Daniel Tat
da57a902-208d-4c85-9df7-9278c15d3cb5 | checklist | Generic - ITP - ACO Drain | itp | ITP - ACO Drain | 09783a54-e995-4ab9-bd88-ebd58c5968fd
ccb5bd5b-ad47-423a-90f4-a865057ce7ea | section | Site Set Out
2de6b696-bf11-4d02-ad27-af6f26fb1790 | checkpoint | 1 - Site Set out
86de905c-4389-5d2f-896c-1dc3e7252e42 | note | VERIFICATION ACTIVITY: Surveyor
c07916e4-1f40-5a1a-a49b-f185fa293daa | note | METHODS OR REFERENCE: Surveyor
d95152e1-c2d1-51f7-98bd-3c56e000cd3f | note | FREQUENCY: Everysite
fbae5a7a-2c9f-529b-96d4-77a507eab427 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
831fbf20-aac7-54e6-8ca3-998b16fdf225 | note | ○ Alternatively like for like
7357143e-1f53-55d1-baf0-a883690a6161 | note | HOLD POINT: Mandatory HOLD POINT -
0236a910-96c5-5981-a7b9-9c18e310b446 | note | RECORDS: Survey Receipt
48a16922-2e8d-5001-aa88-cc26afb7fb47 | note | ONSITE RESPONSIBILITY: Site Engineer
f3cb48cc-e051-40f9-9ace-3e6bc97108e4 | signoff | AUTHORITY HOLDPOINT
61743067-3e5a-4ac6-8464-022ad99e444b | section | Materials
cf705fcc-0785-41a3-8570-aac75e59872e | checkpoint | 2 - Aco Drain K300
a702ec18-378b-562b-bd03-0e04f66b4e31 | note | VERIFICATION ACTIVITY: QA FORM
75e8cabd-2849-5da1-9dc6-675c704d1b11 | note | METHODS OR REFERENCE: TDM Technical Standards
28e46da3-dd72-58ac-84fd-43695a32d981 | note | FREQUENCY: Every site
7ad6cedc-d198-5570-8998-9d63791b9c8b | note | ACCEPTANCE CRITERIA: All the block and the grate should be inspected before installation.
c7b46845-dd17-5c24-b1b9-c63b6db7f135 | note | HOLD POINT: Inprocess Inspection
83b32ecf-2fb4-5f6e-8efc-2376ac403025 | note | RECORDS: Dockets
6e6ab72c-b969-566e-beee-8fb85ee51a4f | note | ONSITE RESPONSIBILITY: Site Engineer
62d9e29f-3817-4d0a-821b-0d3cc12ab3a5 | section | Construction
72d1821d-4f07-437d-85fe-8a403eb86f26 | checkpoint | 3 - Prep and Level Check
0cc9446c-0a0e-5021-b8c5-d9b832aa755b | note | VERIFICATION ACTIVITY: QA FORM
30c24ff6-f0f8-5daa-af02-bdaa05dd95dc | note | METHODS OR REFERENCE: TDM Technical Standards
19cd8624-f811-58ed-bd07-ba644110990e | note | FREQUENCY: Each block
3d8c6e09-cd7e-5518-aab9-461712a60d39 | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
ebccfb0b-0311-5f9e-8ff8-6e1a156df761 | note | ○ Base course - 100mm min. thickness GAP40
9d98ae7b-14f3-5446-b0f4-9dff7691953c | note | ○ Clegg CIV > 12
27828e2c-7117-582e-8514-78fbb8bfc1e1 | note | ○ water flow check
bfc19191-d182-58b6-b6c8-1d26992ec3c6 | note | HOLD POINT: Inprocess Inspection - Engnieer to check
34784a24-6af5-527a-9c0e-5eda106766e2 | note | RECORDS: Depth check photos, fall check photos
6701d7f7-c115-5cfc-b26b-905b88837e46 | note | ONSITE RESPONSIBILITY: Site Engineer
a7c5b0cb-d07a-4095-8dc9-1a1f5acab08f | checkpoint | 4 - Lay Kerb Drain
ec34daf7-4be2-585a-a5d2-fb198bafc476 | note | VERIFICATION ACTIVITY: QA FORM
49a8cab7-7299-5df6-b9c4-49835362cc95 | note | METHODS OR REFERENCE: TDM Technical Standards
333987c0-2f21-58ee-92cb-4f8703a38dcc | note | FREQUENCY: Each Block
865dacb4-3cd5-5a5a-9059-16204e53779e | note | ACCEPTANCE CRITERIA: Boxing to be done along the aco drain
3bca4364-8c39-552b-99d8-e5b6dcac9698 | note | ○ Surfacing - Concrete 150mm and 25 MPa @ 28 days.
042e1ae4-1845-5394-b401-94b87e22472a | note | ○ Side Haunching for 150mm thickness
49c52a32-700c-598a-93c9-67145943edcd | note | ○ Vibrator to be used to avoid voids
25acc08f-9328-51a5-bf5c-fbfac60f165c | note | ○ Finished level of concrete to match with the grate
0e9589b6-d55d-54ad-83fb-95e44ecb7365 | note | HOLD POINT: Inprocess Inspection - Engnieer to check
c4a783f5-4b95-513d-b378-b4f20a037a4b | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
b79b618d-1a12-5604-9c87-106fa02230aa | note | ONSITE RESPONSIBILITY: Site Engineer
0347b472-0ab5-400c-9cf2-63035635b1d8 | section | Asbuilts
d428844c-7448-454d-8cd2-846cd6e5f3f6 | checkpoint | 5 - As built information
2f7fcdf4-174e-5eb8-b1d1-aa09be15b454 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a317da31-3ab3-5d03-8a7c-8555907302f9 | note | METHODS OR REFERENCE:
ab09b696-cf90-5a52-91ac-ec9a9a69227b | note | FREQUENCY: Every Site
68a74132-d8e2-574b-9652-7ab0518467cc | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
c8e98fba-d432-5f0b-9191-2f2826e08612 | note | HOLD POINT: In Process Inspection
2f5c5189-9472-5157-bf48-a8b8fac7b211 | note | RECORDS: Asbuilt records
7d3815b6-2bc2-56dd-b734-d772a6c716f6 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
1c9f8727-63c7-4f32-bbff-628a41dbaa4e | section | ITP APPROVAL
5296d877-932f-4471-bef6-54e5a831907e | checkpoint | ITP Approval
91ff1a09-2ab9-5440-bdb5-ff5c2afdd223 | textbox | Prepared by:
cf9ff8f0-5f43-5041-ad16-85c54bb3247c | textbox | Approving Delegate:
c16e26e7-5dc6-4c0c-8fa1-ac1f05cf038e | checklist | Generic - ITP - ACO Drain |  | Generic - ITP - ACO Drain | 1ebab725-7179-4dcd-948a-0d3cb9e83558
8d4265ea-2d86-4ac5-8aa1-18c1aec1fc78 | section | Site Set Out
c1a1f7b2-1817-4780-8685-5de3197a3fa5 | checkpoint | 1 - Site Set out
ff5bbdca-ff3e-53f5-9001-e3349dcdfb40 | note | VERIFICATION ACTIVITY: Surveyor
d124904c-d4a6-5087-8391-237c93beba82 | note | METHODS OR REFERENCE: Surveyor
4d7a6196-a3c9-5302-92dc-eeeaf7a9ab31 | note | FREQUENCY: Everysite
14867c09-0cb4-593c-87f7-84c24b434310 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
3002204c-acf5-5cc6-befd-f37bd7c4e92a | note | ○ Alternatively like for like
665b964f-0304-5d9d-a5de-e6aa531871d1 | note | HOLD POINT: Mandatory HOLD POINT -
010f1b57-ecdf-56a1-9f85-9748e50144c4 | note | RECORDS: Survey Receipt
a20e5e60-e692-5ad3-9470-f6533317796c | note | ONSITE RESPONSIBILITY: Site Engineer
5fb8dfb3-1bfe-4587-aafa-5548b6d46db9 | signoff | AUTHORITY HOLDPOINT
75af41bf-9f99-4467-99e3-c26fe5f6b226 | section | Materials
9f39c956-6e17-4dfe-90b0-e51ea90d65fe | checkpoint | 2 - Aco Drain K300
215cccdc-f07e-59d2-bd86-71e938944972 | note | VERIFICATION ACTIVITY: QA FORM
5269ea8e-416e-515a-8fd5-18c27c070f23 | note | METHODS OR REFERENCE: TDM Technical Standards
7711f668-6b5c-57dc-8d88-203cabf87a33 | note | FREQUENCY: Every site
96ad1475-9211-5b71-9b21-d970b9cf722c | note | ACCEPTANCE CRITERIA: All the block and the grate should be inspected before installation.
002a8e4b-795f-57f3-822e-c97dc130035b | note | HOLD POINT: Inprocess Inspection
f01c4cb3-147b-5a6e-834e-92d6b300c2f2 | note | RECORDS: Dockets
393cbe39-79af-56ad-9606-b26ba10410f1 | note | ONSITE RESPONSIBILITY: Site Engineer
39b7a761-b589-46fd-9bbf-b5afd728d844 | section | Construction
cb08a9d7-1a2b-4a36-b618-3f9f75af9b24 | checkpoint | 3 - Prep and Level Check
256cc425-12f5-52a7-9f80-e3b101516a63 | note | VERIFICATION ACTIVITY: QA FORM
53c69049-a33d-5650-bc35-ee416a20384e | note | METHODS OR REFERENCE: TDM Technical Standards
df9ba017-1dc7-5b74-9cb3-67e4437e4930 | note | FREQUENCY: Each block
76cf880d-c2c0-5741-bcb9-69ffe197f37a | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
f89a9492-5fd7-509f-b1f3-5df1eb5ced25 | note | ○ Base course - 100mm min. thickness GAP40
aa176d9d-8ba1-58e4-be66-c3795b2c8032 | note | ○ Clegg CIV > 12
ec425b9b-cf01-55fa-80e4-9fe6fe2856fd | note | ○ water flow check
8ddbeb48-b705-5565-af8f-a6f67c7e6177 | note | HOLD POINT: Inprocess Inspection - Engnieer to check
0c22bdda-c0b3-5092-b36c-62b0ac740e67 | note | RECORDS: Depth check photos, fall check photos
633416e6-a645-545e-8966-0823c63f9b56 | note | ONSITE RESPONSIBILITY: Site Engineer
1135e31a-25be-4a23-9bc6-4141c8f4cace | checkpoint | 4 - Lay Kerb Drain
0b93d776-23d2-5bf2-9cda-8d6d1a12aa17 | note | VERIFICATION ACTIVITY: QA FORM
ed0c3d0c-ef25-5af3-a0b6-b2202416e512 | note | METHODS OR REFERENCE: TDM Technical Standards
f0a994a4-c660-5c6b-b348-2fd737187d95 | note | FREQUENCY: Each Block
ea4c5a08-5983-5d67-bc60-e03f8a7f6fff | note | ACCEPTANCE CRITERIA: Boxing to be done along the aco drain
f3c7ccf4-8619-5681-9c54-c383c8e5467b | note | ○ Surfacing - Concrete 150mm and 25 MPa @ 28 days.
d15a40d8-1b70-5582-a1ad-a5270dd8b483 | note | ○ Side Haunching for 150mm thickness
875f16c5-3c66-5f91-a147-95821dd9f6fd | note | ○ Vibrator to be used to avoid voids
7b4bfc45-be08-5acb-98c5-02cb5eee1c3b | note | ○ Finished level of concrete to match with the grate
8ab11bc0-7492-5824-ad55-f37e2a2d57b7 | note | HOLD POINT: Inprocess Inspection - Engnieer to check
68d3605b-7173-5ee8-a34f-bb2f00f00ac8 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
29a21b32-05a4-5a97-8921-02cf8520d7e3 | note | ONSITE RESPONSIBILITY: Site Engineer
19ddc850-5949-41d3-9459-02caabe7e530 | section | Asbuilts
a0b55c73-b567-4bfb-b593-5b64584a5ad4 | checkpoint | 5 - As built information
dd73c842-3c63-5e7a-845f-42bbccfd893f | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
e784b473-f7b0-52e3-8db2-8b93ecd610ed | note | METHODS OR REFERENCE:
d994ca37-d983-5465-80c2-2b3fa7702289 | note | FREQUENCY: Every Site
8ccf5f9b-d367-581b-be93-715e95b1f096 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
a505571a-d69a-5c62-98ee-467fc9ddaab7 | note | HOLD POINT: In Process Inspection
3165be87-a215-5bbb-852a-629618ae209a | note | RECORDS: Asbuilt records
15603495-cff1-510f-ac45-d0db544d4f56 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
6244bed8-2b88-4dcc-8fcc-de41cad06c75 | section | ITP APPROVAL
b5889270-4edf-4517-bd60-bda490804026 | checkpoint | ITP Approval
2da5bdb0-464e-57ae-8741-05b5c0a30147 | textbox | Prepared by:
7f753368-e69d-55c3-847e-e1ef109db75f | textbox | Approving Delegate:
e7bc5f5a-834d-47ae-a585-386185c51703 | checklist | Generic - ITP - Concrete Raised Crossing | itp | ITP - Concrete Raised Crossing | 9f7ea823-9fb0-4ba5-b4b2-cfb09129a3bd
b6309632-f6de-4299-8432-c97b4b6a2969 | section | Concrete Raised Crossing
4f07bef2-6b14-41ae-b162-e5850323755e | checkpoint | 1 - Permits
95e97041-62a6-5761-9bcc-13bb4569306c | note | ACTION (Hold, Monitor, Witness): H
d5cf6bc5-9cab-5b06-8d92-886384d62eee | note | DETAIL: Obtain Permits
029e2929-c88e-5ca4-a681-659e64376ada | note | FREQUENCY: As required
37c51597-3385-5b28-a71d-8bb18886f95d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
31c17a8a-7247-58da-b04c-a3d36886c24c | note | CONFORMANCE CRITERIA: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
c8159bbc-7c5b-5d97-991b-56fab87dd634 | note | RECORDS: Permit attached or permit number noted
7d3e9679-850f-4f46-adf5-cca06284e7cf | signoff | AUTHORITY HOLDPOINT
c4da4ce7-04d9-4816-8887-e0ad6e2a3f6b | checkpoint | 2 - Pre-construction sign offs
67c2c185-2255-5a2a-835c-fdf73387bee6 | note | ACTION (Hold, Monitor, Witness): H
76f2bb51-c3aa-5157-915e-c43277766716 | note | DETAIL: Ensure that Sub-Contract and Supplier Agreements are signed
6a3c7e66-c770-583d-928d-33e2f5dbbd39 | note | FREQUENCY: Prior to commencement
cff2616f-dc2b-5178-a5c1-99a4430a2018 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
a807b075-241e-5019-b971-4469699b220b | note | CONFORMANCE CRITERIA: Signed Subcontractor and Supplier Agreements
67182375-fe21-5a46-b42c-b322f30718eb | note | RECORDS: Subcontract and Supplier Agreements
592328c0-adcb-4cae-9ba8-df6448dd0333 | signoff | AUTHORITY HOLDPOINT
3a4f15cb-371c-4ee7-bd84-3ba6c4700317 | checkpoint | 2.1 - Pre-construction sign offs
fc55b4dd-5c77-5cd0-b9de-9b0bf6fcd7a0 | note | ACTION (Hold, Monitor, Witness): H
a2605ed8-c44a-5139-9499-5abcdf88a63c | note | DETAIL: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
162e8681-1ed1-5b09-9ca4-7c2ea561eecc | note | FREQUENCY: Prior to commencement
7cac2b3e-2ac2-5122-8dc6-570cb9656523 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
73f84525-4fc6-595f-9cc8-173c085ed8cd | note | CONFORMANCE CRITERIA: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
5da16ac1-c9a8-5798-a04c-b804bde837bb | note | RECORDS: TMP on MyWorksites/On Site
7263dd95-11ca-4bd9-b4f6-9953e5decb53 | signoff | AUTHORITY HOLDPOINT
366631ae-8cdb-4884-b7e8-e1d656b868f5 | checkpoint | 2.2 - Pre-construction sign offs
1d2203ff-b2e4-5ee9-a059-ca8d5c3eba52 | note | ACTION (Hold, Monitor, Witness): H
501ef55f-ed4c-5c0b-b5a4-5fed9ea5566f | note | DETAIL: Ensure all Sub-Contractors and Suppliers go through FH induction
979a3b15-a6a2-5839-9e92-f76c67373597 | note | FREQUENCY: On site daily
d85d7b9d-9713-5317-96c6-2d75dc7c953c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Induction
40a6ec95-e346-511e-a2ea-0d0b214ff968 | note | CONFORMANCE CRITERIA: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
179ef5b3-6af3-5515-9f81-c27486b279d9 | note | RECORDS: Hazard ID and Pre-starts to safety team
5813b38e-b4b3-4df4-be56-43ba0b9828ca | signoff | AUTHORITY HOLDPOINT
67bff72a-19d9-434b-92c0-7e8f09184be4 | checkpoint | 3 - Design
6eeb6fe4-da0c-5df9-a808-9183e0653a98 | note | ACTION (Hold, Monitor, Witness): H
0601e56e-e44d-50fd-8213-8aa2eb9fa72f | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
301f6fb8-2aa1-5e2a-bd0a-898d91e3034e | note | FREQUENCY: Prior to commencement
b74f7152-c8a7-54f3-aaf6-1743e3d1bbb2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
ce37fc90-8ad2-5395-8eb0-f483390cda99 | note | CONFORMANCE CRITERIA: IFC drawings have been received by Contractor
4faa0498-785a-5822-83b8-95ac38f3a591 | note | RECORDS: Check Drawing Register
da5408b7-86ee-4f8a-9e54-b20c6779f25e | signoff | AUTHORITY HOLDPOINT
77a2ce3a-327b-4c18-8dfa-67e20a63bff4 | checkpoint | 4 - Installation of Erosion and Sediment Controls
2141f8e8-8e3a-5dd3-8b1f-3a87761ec251 | note | ACTION (Hold, Monitor, Witness): H
fd8f207d-886f-5636-923c-045d1c4d6214 | note | DETAIL: Ensure that Erosion & Sediment Control in place
f0b928c5-e505-5e0a-87cc-a1e8e58a9c17 | note | FREQUENCY: Prior to commencement
2448a91f-c081-596a-8680-33a38bb34e41 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
ae1981db-5631-59f5-9093-04e6140ae524 | note | CONFORMANCE CRITERIA: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
fa042531-a5ce-5552-a3be-6ba43bda0bca | note | RECORDS: Environmental Controls Audit
edd46690-c073-4f47-9b40-aca0ee883f74 | signoff | AUTHORITY HOLDPOINT
7f191014-3b89-44a5-9c4c-d90e0626cfda | checkpoint | 5 - Survey Setout
c7994a9f-2bb3-51d8-9380-57e02f2f8ace | note | ACTION (Hold, Monitor, Witness): H
9a527608-f0e8-5a32-97a3-121156228ed2 | note | DETAIL: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
99bed2d1-fa11-51e3-af41-67da38bba685 | note | FREQUENCY: Prior to commencement
47dc86c5-81c2-5338-bc76-03822540504e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey + Smart Level
c9609f27-2530-5ba8-8118-fc85db4b1bc7 | note | CONFORMANCE CRITERIA: Consistency with Construction Drawing
dd0c42fb-1b26-57aa-9443-d8ec0b6fb218 | note | RECORDS: Site Photos post surveying
b61d628c-c9c1-462c-9818-331fc5f218ef | signoff | AUTHORITY HOLDPOINT
dc6a9b05-b54d-465d-90e1-48fdd3898e62 | checkpoint | 6 - Locate Existing Services by Hand Digging
f9a87130-f0ec-5c53-bcb9-7d8f7807e7cd | note | ACTION (Hold, Monitor, Witness): H
856303c4-327f-5643-97a0-9d844f761762 | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging
26cb7005-897f-5e89-8d72-9d428be7fa05 | note | FREQUENCY: Prior to commencement
ae68e025-142a-547a-9a44-dc2513885cc8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
e5a9dc7e-e3d5-5091-9ac7-8e77082120f2 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
4bfce028-1773-5f27-b02c-df6a2a46767e | note | RECORDS: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
cecd1cb5-a61d-4f21-8e9a-81c70cfe5908 | signoff | AUTHORITY HOLDPOINT
1bef2ecd-f42d-4eee-b8c2-6652d7f59a5a | checkpoint | 7 - Material Compliance
a5840fe8-4dfb-52e4-9c40-9a7f28aa1714 | note | ACTION (Hold, Monitor, Witness): H
a9e14725-1756-543b-ba1b-533ce52fc8a2 | note | DETAIL: LESA dowels to be used at all construction joints at 600mm clearance
180ef1d4-c273-5e64-a3be-98a8b01590dd | note | FREQUENCY: Prior to pouring concrete
242af566-3a04-5937-bb19-3ea88f5a1629 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
58df0076-95c3-5853-b9c5-ff235cd27e3f | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
3d16c1c4-7de2-5d31-b370-3c10c9278c88 | note | RECORDS: Delivery Dockets / Photos
e0ea024b-1d60-4d75-9651-0a36be5d02a3 | signoff | AUTHORITY HOLDPOINT
ed5a9b25-7f1f-4998-a325-df43e5c820cb | checkpoint | 7.1 - Material Compliance
223f592b-d58f-542f-bce2-456cf65f18ce | note | ACTION (Hold, Monitor, Witness): H
ce9b577b-3c2e-5d8d-bec0-cddb73e528e7 | note | DETAIL: 0.25mm polythene layer placed across all surface area at bottom of raised table
bfffab26-c484-5bbf-9489-55bffa8ce834 | note | FREQUENCY: Prior to pouring concrete
a423fc87-cecc-5478-a552-8e84b7d1c7d2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Document Review
f8e2b46e-11e4-526c-897d-ceeb07f6c26b | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
2402f48f-7cb5-5bb0-850e-ed1b9f56dd61 | note | RECORDS: Delivery Dockets / Photos
0e428433-121f-449d-bcfd-00b9e7b515eb | signoff | AUTHORITY HOLDPOINT
946f9e84-e48d-4adb-a340-3d9b3dcce6d1 | checkpoint | 7.2 - Material Compliance
6e83ee25-ffc4-52e4-ba84-153adf599145 | note | ACTION (Hold, Monitor, Witness): H
040cb8b1-b767-529c-a745-b6ff2b469247 | note | DETAIL: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
903f6211-cbc0-57f4-9791-1fa912cd0886 | note | FREQUENCY: Prior to pouring concrete
39f978ce-4a05-53a1-b577-110017c1658e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
1a4cd3d6-d905-5d45-983b-8f7e22c1b2c5 | note | CONFORMANCE CRITERIA: CIV >15
d2116429-a0c5-5874-ad5d-101fc7f2aa97 | note | RECORDS: Delivery Dockets
24958fe4-a91d-4be8-bb38-25e5ff20971b | signoff | AUTHORITY HOLDPOINT
3eb92120-77a6-4955-a967-5bdd25e2f655 | checkpoint | 7.3 - Material Compliance
bcf62c70-5fae-5e2b-bb54-6dbcbe2f463a | note | ACTION (Hold, Monitor, Witness): H
7dd4c3a9-6909-5ab8-8dcc-a1e739914cf9 | note | DETAIL: Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
23522723-3087-51d3-9cad-ad49acf476d7 | note | FREQUENCY: Prior to pouring concrete
a1954a46-c9f3-591b-8802-4eb251842750 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
d8f3b208-2e15-5092-afdf-37578a29c59d | note | RECORDS: Photos
8f742a03-7d5d-4e6d-96dc-ec40bc181fe7 | signoff | AUTHORITY HOLDPOINT
6b432eff-7034-437e-933a-90687fc101b7 | checkpoint | 7.4 - Material Compliance
7b95003b-ea23-51d1-a3c1-b6f5bb0284ea | note | ACTION (Hold, Monitor, Witness): H
22027e51-544a-5cac-84b2-ce4a729ec68f | note | DETAIL: All concrete delivered to site shall have 40MPa 28 day compressive strength.
34c686bc-6b0d-5d78-8244-ce3b9891b6ba | note | FREQUENCY: Prior to pouring concrete
30e8c348-1916-57cd-be15-91cff9d950db | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Concrete Delivery Dockets
276513cd-fec6-5ac1-9444-0a82f08ee02a | note | CONFORMANCE CRITERIA: Delivery Docket added to QA folder
4e9d1267-17d1-5714-a6ab-884eb316cc15 | note | RECORDS: Concrete Delivery Dockets
6a6b0309-8b44-4541-a707-68303c62be58 | signoff | AUTHORITY HOLDPOINT
2d52de85-3b7c-4e57-8ae8-78baadfa5afc | checkpoint | 8 - Temporary Works (Formwork)
61cca7bb-99ed-59f1-a2cf-5a407d2f8395 | note | ACTION (Hold, Monitor, Witness): W
a8965f3c-1558-524e-a725-2b1271a7364a | note | DETAIL: Formwork to be set to correct line and level
5f17447d-afe8-5a37-befb-739372edd3d0 | note | FREQUENCY: Prior to pouring concrete
41bdcf19-ddb6-5356-bfcb-d144a1597200 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
6745f6ac-a9c4-5f86-a65c-b146c15798d8 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
9bf93012-2537-5372-8aef-14cde8bf38da | note | RECORDS: Concrete Formwork Checklist
b596408b-cfbf-4e5d-b4d3-c89cc4596173 | checkpoint | 8.1 - Temporary Works (Formwork)
c1d3fb09-c5ed-5243-a744-fa6731097a3f | note | ACTION (Hold, Monitor, Witness): H
e575f27d-c0cf-5380-b044-ad5b3b515f63 | note | DETAIL: Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:20)
0db61ea1-8d22-57b1-966b-f28a420a57ab | note | FREQUENCY: Prior to pouring concrete
309eadcf-472f-5ef1-b012-28650c8db62f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
318210e3-337a-522d-a591-25a2b61c6506 | note | CONFORMANCE CRITERIA: Designer to inspect formation level
ef1bd814-65e3-551d-a9bc-320865f4e211 | note | RECORDS: Site photos
cb6d6028-cbd2-4aa0-892d-be72c27594ae | signoff | AUTHORITY HOLDPOINT
6915c16d-756d-477a-b528-6cd9052352cf | checkpoint | 8.2 - Temporary Works (Formwork)
2d5336e6-19f8-5eaf-b643-bb4e627ef3be | note | ACTION (Hold, Monitor, Witness): H
5574883d-0fa5-54b7-b263-04faf2ad30cb | note | DETAIL: Raised Table ramps to have 225mm depth at entry point and tie into 300mm depth to meet raised table
c162e0e0-8125-554f-8a69-72df6122010c | note | FREQUENCY: Prior to pouring concrete
9d79eb4b-635e-568a-9be2-480ca793b6b8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
a1766a80-10fc-54b1-a809-92e417ec9275 | note | CONFORMANCE CRITERIA: Designer to inspect formation level
b35bd205-4667-5652-8331-cef136232789 | note | RECORDS: Site photos
3677cc8b-7395-45ff-b9bd-bcdaa79905cd | signoff | AUTHORITY HOLDPOINT
248344cc-7e00-4b3f-995a-523136c3acda | checkpoint | 8.3 - Temporary Works (Formwork)
3c7eb204-5694-5352-977e-992901151a77 | note | ACTION (Hold, Monitor, Witness): H
f6784c0b-94e9-5c6c-a940-902d688b6f7d | note | DETAIL: Raised Table ramps to be 1.125m across for entry and 1.5m for departure ramp.Toe to be 500mm across for both entry and departure with 50mm asphaltic wearing course
8a1e6adf-e9d4-5fde-aa21-a75db13c37de | note | FREQUENCY: Prior to pouring concrete
82bcb177-2e5d-5d7f-8133-3259bdc118cf | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
94791982-0bd6-5bfb-b4f6-4535921055ed | note | CONFORMANCE CRITERIA: Designer to inspect formation level
c7078814-fb66-5306-93c4-15988757ff63 | note | RECORDS: Site photos
db1cc49b-198a-4a51-b8e7-8628ec03dc8e | signoff | AUTHORITY HOLDPOINT
28a504ca-3160-47fa-9164-dd2c6df7ed71 | checkpoint | 8.4 - Temporary Works (Formwork)
0adcae27-d258-5f04-a8da-1f7752b41c07 | note | ACTION (Hold, Monitor, Witness): H
4a49d4d7-5f0d-5c8e-a6b4-9f599c360531 | note | DETAIL: Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:20 relative to the road
a8256b07-d7bd-5fcf-a760-ac330e128312 | note | FREQUENCY: Prior to pouring concrete
8cc60873-3f6f-5fde-9a4f-6b779bc9dbb0 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
3f076479-cc6a-5488-ba31-66affc70cad0 | note | CONFORMANCE CRITERIA: Designer to inspect gradient level
c903a880-4aaa-56e1-b2b4-d2e5cd35acbf | note | RECORDS: Site photos / Concrete Formwork Checklist
344980c7-908a-40eb-887d-d1e259e668f4 | signoff | AUTHORITY HOLDPOINT
f398252d-641c-4fe1-987a-4213e9c9efef | checkpoint | 8.5 - Temporary Works (Formwork)
ba5162dd-22af-5bf3-a017-c2bea5668790 | note | ACTION (Hold, Monitor, Witness): H
42570039-d935-501a-b360-8576206c35ab | note | DETAIL: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
8d4d92e2-475a-5d29-85cb-67ff09cb9ef4 | note | FREQUENCY: Prior to concrete pour
b7cae3fa-51fb-5254-9ff5-d39548eebfbd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d738db9b-0999-5335-af15-3b7c35245e06 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
854d902a-bc63-5f88-a820-af832134acf7 | note | RECORDS: Concrete Formwork Checklist
ddec472a-c9f3-4be3-88e6-4fc25deb199a | signoff | AUTHORITY HOLDPOINT
7c97d0d5-0cde-46fb-95d9-c185a078d26b | checkpoint | 9 - Reinforcing
1ae398fe-2aec-5ed7-bf18-9a4cd66960f4 | note | ACTION (Hold, Monitor, Witness): H
5f0057f1-970f-549e-af71-749819daa154 | note | DETAIL: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
349f45ee-c523-5638-bc5a-33394a22e962 | note | FREQUENCY: Prior to pouring concrete
890e774b-d964-5755-ad96-924e4b9442cd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
cda2e274-46cd-52c5-9569-5bfc3097b14e | note | CONFORMANCE CRITERIA: Concrete Inspection Record
ab7e3206-07fa-5268-97bf-9dc1f5e2303e | note | RECORDS: Site photos/Concrete Formwork Checklist
3161a186-8dc8-4a38-a46b-f982e817c085 | signoff | AUTHORITY HOLDPOINT
aca8a3fb-192c-4c9b-9f19-d13c4121b97b | checkpoint | 10 - Concreting
b53c2eae-5c65-5188-84f8-007931f51a37 | note | ACTION (Hold, Monitor, Witness): H
27bd4bd3-7c37-51b4-b6c4-3fa2e469dfef | note | DETAIL: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
6a59fb3d-241b-5d53-9afd-b925872d9015 | note | FREQUENCY: Prior to concrete pour
d3596fc8-5b2e-5dae-88c7-4c84d6af84cc | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
5bbdb07f-904a-5eb7-ba41-11a328455a37 | note | CONFORMANCE CRITERIA: Engineer will be notified via email/SMS at least 24 hours before required for inspection
524b4144-6040-5648-b8e3-15dae9eb5d7c | note | RECORDS: Email / SMS
aed5ecd4-fed6-45e0-a490-1807ca28b61e | signoff | AUTHORITY HOLDPOINT
69e87410-bfb1-4ed6-9831-faaea648ad1e | checkpoint | 10.1 - Concreting
14c319cf-0898-560a-bf13-88c40ff7b296 | note | ACTION (Hold, Monitor, Witness): W
5e936c68-367c-5abe-a5ce-f776005aaea9 | note | DETAIL: Vibrator to be used throughout concrete pour
714bf71d-a26d-5dda-959f-df9f0213eeef | note | FREQUENCY: When pouring concrete
2c6d7e36-f5b1-5e98-ad20-4eefe211d84b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
2a144c83-a31c-5f14-9dc4-e31f876c91bb | note | CONFORMANCE CRITERIA: Concrete Inspection Record
33fb61b2-9b01-529f-9ccc-2a0d5440711a | note | RECORDS: Concrete Formwork Checklist
d16e9b37-be1d-4269-b1af-5534d32bc557 | checkpoint | 10.2 - Concreting
91de4fea-cd48-50f8-88fd-7cc1970abbb7 | note | ACTION (Hold, Monitor, Witness): H
9752a50e-c686-56d1-9f5a-7dfc9000d968 | note | DETAIL: Concrete surfaces shall be U5 broomed finish for ramps, and Broom finish for table top.
0143abe0-0c6f-5dfa-91e6-3fd0e0bbc704 | note | FREQUENCY: At completion of pour
a2650c67-a922-592f-9381-822dd9375bf4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
0bb56f8f-7c7b-5268-b530-38a4a6aaad10 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
70947108-cb48-5fd8-a402-73f2a16d1fc8 | note | RECORDS: Concrete Formwork Checklist
6fbc5044-a4a0-429b-b4e8-29e4e3ec3a5a | signoff | AUTHORITY HOLDPOINT
6e1828c0-1b26-4e38-9040-e2636c4bab85 | checkpoint | 11 - Curing
4af4c4f3-ee6a-5913-9a05-5283a928330c | note | ACTION (Hold, Monitor, Witness): M
db98f241-6f69-51cb-be2f-7f6a7907c00e | note | DETAIL: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
a36d04aa-e1d9-5244-9d71-b1f8a265356a | note | FREQUENCY: Post Pour
6fc2caa3-b7dc-5a20-893b-bf99a2eba455 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Monitoring the time allowed for curing
9141fc23-1c3a-5ac9-8b45-2042cce6c1f4 | note | CONFORMANCE CRITERIA: 48 hours minimum have passed
b4d2be11-f22c-5868-acba-2918a705f16c | note | RECORDS: Concrete Formwork Checklist
ae24423f-fc95-415b-bed9-80b6ad494376 | checkpoint | 12 - Remove formwork
de36fe5a-dbae-5cc7-907e-fc4a5c40a53c | note | ACTION (Hold, Monitor, Witness): W
29fc3abe-5df4-5339-99da-eaef2ccc3701 | note | DETAIL: Remove formwork after 48 hours
865c6abd-0398-554b-9bd0-5b00ca1079fe | note | FREQUENCY: Post Curing
45a6debe-6971-54e0-9020-4d1516febd5c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
7cd61336-7a0f-51ca-a4fc-7af5c180d31e | note | CONFORMANCE CRITERIA: Concrete Inspection Record
ae9f8829-f79a-523e-9c00-fe2d5cbe9ef0 | note | RECORDS: Concrete Formwork Checklist
a9157346-dcd4-4098-8bf9-a48243ab80b4 | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
66ea1372-0c42-550e-8100-d29270c914f0 | note | ACTION (Hold, Monitor, Witness): H
eec94770-c75b-563f-a425-604299b2a53e | note | DETAIL: Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
09d15f6f-f717-5162-9692-27b55a665af6 | note | FREQUENCY: Prior to pouring concrete
00c61015-57e8-5ecd-b28b-3206362b2e64 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
3e8370e9-8740-5168-accb-165202c8089c | note | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
190a918b-30fd-530f-8f72-77a4dc861102 | note | RECORDS: Site photos,delivery dockets
58fea03b-e98f-4f01-8733-5f19918e1beb | signoff | AUTHORITY HOLDPOINT
fbfdb68b-1724-490d-bc31-c6639b02feec | checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
cfc5c662-27cd-58e5-a79f-0cf9d32b2aa9 | note | ACTION (Hold, Monitor, Witness): H
9c911825-f71c-566b-8d8c-4e9e872d3946 | note | DETAIL: 200mm thick 40MPa Concrete with two layers of 663 mesh
fa9ab5d9-fadb-58d9-9f9f-aa29d78b725a | note | FREQUENCY: Prior to pouring concrete
b15400a7-1d8c-58dd-9001-32e608453b22 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
78570084-04ad-502a-a3d2-dfddd3ae3c86 | note | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
6169e081-ef02-5482-b7bf-0ef85e4959bd | note | RECORDS: Site photos,delivery dockets
2f8bedd0-b608-43f1-8073-e9d352264de6 | signoff | AUTHORITY HOLDPOINT
1ee30a4c-b267-4665-bc40-1465426805c1 | checkpoint | 13.2 - Asphalt- Concrete extension slab/ Toe
fac5686a-7ad0-5bea-9c05-399f0813b658 | note | ACTION (Hold, Monitor, Witness): W
f1f40bfd-842d-5316-ac4e-8f55888b4904 | note | DETAIL: Tack Coat between AC and Concrete slab
b52ce7c4-7e21-534d-9cf0-fb7bcb54b2f6 | note | FREQUENCY: Post Curing
5d59a074-b3c0-5ebf-aff8-c1fce735d216 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
4cebe56b-872b-5eb8-a227-0945be8f1491 | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
b5ec72b8-63b1-55c1-b64b-9c3d0647dfe0 | note | RECORDS: Site photos
65bcec68-2fef-4d4b-9513-9ba45218bbc9 | checkpoint | 13.3 - Asphalt- Concrete extension slab/ Toe
df45e869-ae94-5831-bbc7-473c01108dfb | note | ACTION (Hold, Monitor, Witness): W
0fc0d8d8-4dfa-568b-864f-01823c771bec | note | DETAIL: 50mm thick DG10 / Mix 7
f7246591-67e8-5462-9c97-33abf34c4d96 | note | FREQUENCY: Post Curing
91ce146c-c98e-5315-94a3-d20191648ad9 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
4c469448-c8de-5a1b-936d-941eb65a0a4a | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
3c9b1b51-3036-5142-85ca-59ce93b4c365 | note | RECORDS: Site photos,delivery dockets
ae7b452b-b15c-4006-8fd9-a22c9ebc46e6 | checkpoint | 14 - Lot Number QA File
8892e00a-492a-5ac2-aa05-520f3574bf50 | note | ACTION (Hold, Monitor, Witness): W
2cb1888e-c9be-5939-a783-f36fa5f48c26 | note | DETAIL: Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
05cd1556-61c7-5148-8d7d-604986bc0665 | note | FREQUENCY: At completion of Lot
ec68d1fa-2983-5a77-962d-5b0efa2f70bc | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
a51dcf39-6e7c-5798-b7de-59eea2116e1d | note | CONFORMANCE CRITERIA: All QA files compiled and sumbitted to client
6d3d1914-e630-5768-b87f-ca71bc8a1556 | note | RECORDS: QA records
cd2df7ef-e837-4853-ad5f-65e1b12e62ab | checkpoint | 14.1 - Lot Number QA File
0c0daeda-4891-502c-8706-48a3b23e6c7d | note | ACTION (Hold, Monitor, Witness): W
7a9d74c3-4bda-516a-8a66-3b4889da012b | note | DETAIL: Delivery Dockets to be included in QA file
a7c73caf-b694-5eba-9a36-4bee1cc2de26 | note | FREQUENCY: At completion of Lot
265eb3af-d21e-5cf0-833a-f6d0fd80553f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9636c416-298b-5540-8361-99994a7515af | note | CONFORMANCE CRITERIA: Delivery Dockets to be included in QA file
9995c6fa-bb79-5a22-afc9-ed8ccf2c15d2 | note | RECORDS: QA records
2cf09fc3-588e-467e-9011-5b9bd7f6a23d | checkpoint | 15 - As-builts
42a11925-dffc-506d-bad9-ab7c9a9ef6ec | note | ACTION (Hold, Monitor, Witness): H
6cffec87-051a-5e59-8ee6-e1784e114237 | note | DETAIL: Red pen mark up drawings to be included in QA file
9de5d59e-7123-5346-a3ac-424b33928991 | note | FREQUENCY: At the completion of the Lot of work
e83160b3-1b1d-5921-afe5-f7de3ea744c7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
351b408f-8f98-565b-ae17-925f9cc10e12 | note | RECORDS: Asbuilt Drawing
3536bff1-c109-4a68-aa70-8271c499ede5 | signoff | AUTHORITY HOLDPOINT
69245cac-0313-46a5-9635-906fa2f46076 | section | ITP APPROVAL
0df3363b-d14b-4e3a-bb16-a33dcf5f10b9 | checkpoint | ITP Approval
059928d9-0941-5a4c-98dd-085661bcc357 | textbox | QA checked By Quality Manager:
54b40064-a87d-5521-8031-1cf92d9c4371 | textbox | Accepted By Engineers Rep:
| checklist | Generic - ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | itp | ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | 26b1df68-75ca-4d60-968f-f4eb8ad7bbf5
| section | Site Set Out
| checkpoint | 1 - Site Set out
37348add-c5a3-51c6-bdda-2b198cbd3eb9 | note | VERIFICATION ACTIVITY: Surveyor
741fa328-4969-5a30-aaa8-eafa4a9d807c | note | METHODS OR REFERENCE: Surveyor
1e18f068-af91-5705-b7b2-aa6affab2644 | note | FREQUENCY: Every site
3bc3215d-6800-5f1b-b82d-b20e5e4ebf39 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
d5e8afb3-14c4-584b-8479-0fe8a0a23ffd | note | HOLD POINT: Mandatory HOLD POINT -
cc2a8aff-38c4-52d4-8d4a-a783365a81bd | note | RECORDS: Onsite records/photos
6bc8d6b5-717d-5b93-bba8-ea524d6281d5 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Kerb and Channel
| checkpoint | 2A - Kerb & Channel
f2e3c2d7-8160-525a-a12c-36eddf756fb8 | note | VERIFICATION ACTIVITY: QA FORM
b311c14b-dcae-5e86-b94d-92419b5e196c | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
00b083d9-532c-56b1-8773-87375f88a9de | note | FREQUENCY: Every 10m for Scalar
49718849-30c3-56db-91f0-5a7876240eea | note | ACCEPTANCE CRITERIA: Subgrade CBR > 5
77a48ebf-13c1-5f8c-adf1-2f34627b89d8 | note | HOLD POINT: In process Inspection
5b3306c6-15de-5f2a-a31f-b4d01894c939 | note | RECORDS: Scalar Sheet
dbfa145b-7928-50ab-bcc0-bff00fa87f34 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2B - Kerb & Channel
9a48ee6d-91b0-5da3-909c-a4e02593c26b | note | VERIFICATION ACTIVITY: QA FORM
1ac037d2-de20-5774-b0be-fa4d84944dcc | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
15461fe5-bc4d-5ac9-a8d9-107b138f0dd5 | note | FREQUENCY: Every 10m for Clegg
356ab40b-3494-50c0-868a-d1310d8f03bf | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted GAP40.
978bd73a-88be-537d-9cc3-2f0c5afd4cff | note | ○ Thickness - 100mm on Footpath / 300mm on roads
095a8c5f-9573-532d-8744-57fb03170f93 | note | ○ CVI > 12
294f028d-3c5b-5b9d-aad7-379919f4c864 | note | HOLD POINT: In process Inspection
91c0420c-870e-5801-82dc-485eae46c192 | note | RECORDS: Clegg Sheet, Photos
427d9e3d-ef43-5618-aff8-43dac9ce9440 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2C - Kerb Setout
4624b3bf-a496-53d8-b381-6993575445e6 | note | VERIFICATION ACTIVITY: QA FORM
9d1031d6-7ce9-5cf7-b9be-d3a5abea9fd0 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
1ba52203-6b83-5386-800f-0c5e9417d9e6 | note | FREQUENCY: Every site
f9743e3f-b67e-59b8-aeee-b82ee9345079 | note | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified
04cebf37-522e-5f7a-a8e3-a923221cf68b | note | HOLD POINT: Mandatory HOLD POINT -
ee063951-e692-5784-a995-c55e4e3c650d | note | RECORDS: K&C Pre-pour Checklist
b4f249d5-26ba-575d-81ac-a70131af5126 | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2D - Channel Material
6e765a50-3dad-59b4-ad83-b597707f3b61 | note | VERIFICATION ACTIVITY: QA FORM
939fa9d4-f90c-52bc-91a5-3f1e06374e5f | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
b4d09b5a-16b1-5ef3-baed-a93b26e5eb06 | note | FREQUENCY: Every site
05eb1f79-5d88-5e24-8d1f-6090a182fc26 | note | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
0db649a3-2fb0-5622-8ad4-33fe40c79e79 | note | HOLD POINT: In process Inspection
ce6c6184-6a6c-5fe2-afb0-d272436b0468 | note | RECORDS: Concrete Docket
2e6c777c-2d3c-5912-b083-adc1a3146857 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2E - Channel Level
53075479-3df6-5710-a88f-d642b0ea86ac | note | VERIFICATION ACTIVITY: QA FORM
90d7abc6-57df-58b3-a715-2b934eef7f4b | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
68be5fec-1cd0-5072-9cae-3bac6f57f1c1 | note | FREQUENCY: Every site
f3b94cf5-27de-5f55-94b0-376cc0e9ba74 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
67d23cdb-9c14-547b-9f5d-2936f661d41d | note | HOLD POINT: In process Inspection
cbce98d4-0d21-5d05-9f45-c99edbe7c90b | note | RECORDS: Photos
a7fcb097-cccc-5e49-9a71-b627a86ea386 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Footpath
| checkpoint | 3A - Concrete Footpaths
1f0c6cca-e8df-50ca-82ce-d5ae20bb18da | note | VERIFICATION ACTIVITY: QA FORM
aa03a965-a063-5f34-98ac-e8e2baa956ab | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
431fc44c-ed9f-50fc-9487-117650677329 | note | FREQUENCY: 10m intervals
ff615669-f94b-5b6f-9e09-7e9b0bd43c3b | note | ACCEPTANCE CRITERIA: Subgrade CBR > 3
f510cbbd-2256-56e0-b40a-da2654a82f78 | note | HOLD POINT: In process Inspection
200ead51-9b9d-5a8f-b216-716dafd2314d | note | RECORDS: Scalar Sheet
9259d270-1e6a-5713-b0cf-dda4979f7f41 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3B - Concrete Footpaths
8281f1ad-e748-5afc-9949-ce6475a695ed | note | VERIFICATION ACTIVITY: QA FORM
6488d403-02b9-53cc-8d94-59be7b2e7de5 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
cacca5e3-40e7-5282-bd4a-a02ce99dd4c2 | note | FREQUENCY: 10m intervals
3eb73cf1-1914-5e17-8790-0fc1c3a47b7c | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
361f7126-f3b8-5906-9f25-ffdeb630c9a0 | note | ○ Clegg CIV > 12
2c96ee10-73e2-5acc-8f17-8a3b3d1997a9 | note | HOLD POINT: In process Inspection
fe743841-c62e-54bf-b93c-92cb9efd60bc | note | RECORDS: Clegg Sheet, Photos
3cd39fbd-dbcf-5070-90d8-805025993f30 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3C - Footpath Setout
794a7d94-e21b-5d18-abbb-e314fbe01e02 | note | VERIFICATION ACTIVITY: QA FORM
8a9eadad-f3ea-5d4f-802d-b0790c95c319 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
bfcac348-655c-5b4b-80a4-f763ae2d083f | note | FREQUENCY: 10m intervals
a7ceef4f-8d49-5069-802b-6ce1d41fb148 | note | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
04d04f9b-a03b-5e28-babf-330b7a7353de | note | HOLD POINT: Mandatory HOLD POINT -
6ece6da1-8d4a-5e9f-8ca2-ea0640f91fab | note | RECORDS: Pre-pour Concrete Sheet, Photos
1eaaf716-31f5-5a25-989a-9b7000cb316c | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3D - Footpath finishing
9bf1b369-000f-5de3-aecb-c4dcd4fd53d8 | note | VERIFICATION ACTIVITY: QA FORM
94c588da-837d-556f-8e6c-2882d98f0a63 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
a3b008c6-3408-59c5-aa29-4fcc60669334 | note | FREQUENCY: Every site
4a85379f-2c8f-5195-b2ac-50094bf90ed6 | note | ACCEPTANCE CRITERIA: Concrete Strength 20 MPa @ 28 days.
43613606-bfad-518e-8e6a-7fbf1740355a | note | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
77b8414b-5cc7-559c-a79c-23f56ca5db9f | note | ○ Standard Footpath - 100mm thick
f8cdd8e2-166b-5822-940e-8104cc3588d7 | note | ○ Heavy Duty - 150mm thick
dd4ce1b2-7dea-5241-87c1-52121b25956c | note | HOLD POINT: In process Inspection
5349694a-9639-5115-8897-733f8eb5aea3 | note | RECORDS: Concrete Docket, Photos
1385ca46-ab54-5a11-8945-636ac120a82b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Grass Berms
4b467a0b-0a35-5b05-a16d-376bbbe0b4cb | note | VERIFICATION ACTIVITY: Visual
e75a70c2-8adc-5e96-a22d-c3f0462812cc | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
c166e7b8-d418-556f-9881-e042d914042c | note | FREQUENCY: 10m Intervals
3a380300-f83f-5d24-951e-3fb9ca3ef34f | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
ad1f50c9-90d0-5af1-bbda-e66289f07811 | note | HOLD POINT: In process Inspection
af1ebbae-0f0c-5bf0-bb66-8f633fa00d7b | note | RECORDS: Photos
deb3f735-57fc-5484-ab62-061184420471 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Service Covers and Street Furniture
88287524-c2a7-51b6-8d40-1e08df0a2efc | note | VERIFICATION ACTIVITY: Visual
861d10a6-269c-55d3-b045-502d48452f49 | note | METHODS OR REFERENCE: AT Contract Specification 14000
877d3f87-d07d-5dd5-9819-06252bd47480 | note | FREQUENCY: Every site
b95016c2-ca36-567a-9a53-ea5f72775462 | note | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
942594f8-828e-5379-b048-19b02e73f05e | note | HOLD POINT: In process Inspection
3f8e2ee7-7bf8-579a-be1c-d0612513e436 | note | RECORDS: Nil
ddfabd5e-90f2-5d4d-9439-db805286f9d0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6A - Tactiles /Pram crossing
25cbbb58-c435-5f82-8384-d4907840dba7 | note | VERIFICATION ACTIVITY: Visual
3ec6ef76-a5ea-5684-868b-b9d3f08425a6 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
9ccb8f92-122a-5381-a161-d2c49184979d | note | ○ TDM Technical Standards - FP0010
a7289436-a690-5e07-8912-b2bdb04478b2 | note | FREQUENCY: Every site
b293a988-6c92-5952-80af-9e607ef99ecf | note | ACCEPTANCE CRITERIA: Tactiles set out must be agreed with MSQA
12e42f24-a925-53f6-b342-21b730f29138 | note | ○ Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
d58073cf-e4b5-5637-a650-22f70bc972dc | note | ○ Warning TGSI tiles should have 100mm concrete slab underneath
32848c5c-75fc-5aa9-80ec-72370637bf3f | note | HOLD POINT: Mandatory HOLD POINT -
6b11d507-66e4-5f53-a91d-9740120173b2 | note | RECORDS: Photos
3f46f9bf-2ea9-5603-9343-6ca88fea8008 | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6B - Tactile Material
82e7f228-009b-5a79-9388-f1c1deeeafa5 | note | VERIFICATION ACTIVITY: Visual
83b2fdf9-82f3-5645-b909-68eed9879ae4 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
66f8bc46-93d8-5cfe-a169-0698385792fc | note | FREQUENCY: Every site
7af24fb0-aee6-546f-8aad-537360e180b7 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type - 300x300mmx60mm
ffd4fd1e-04da-512c-9768-04a2e8833cb6 | note | HOLD POINT: In process Inspection
c0dfbed5-e14b-5ca0-8532-ac5266c90eff | note | RECORDS: Photos
5c7e22d6-d671-5051-af3f-b52b1658d4f4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6C - Tactile
06a93128-f936-5aaf-af49-868046347e49 | note | VERIFICATION ACTIVITY: Visual
6275b83f-e061-50dd-8c96-43558d63b7f4 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
69888d02-4ea5-56d4-8f19-8f5364985d1c | note | FREQUENCY: Every site
8208dc74-eb23-583f-bb80-648692bbcd06 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
492d1d45-38d0-58ae-bb47-795f1b55b4e1 | note | HOLD POINT: In process Inspection
c8af76b7-11d4-526e-b94e-3686514c504c | note | RECORDS: Photos
d1b58b30-0f49-5e51-866e-f09a3de1cda7 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 7 - As built information
1aa74bc8-36b8-5205-aed5-54f5a0b353fb | note | VERIFICATION ACTIVITY: Drawings
7e9a9d1d-7ce9-5338-b72d-37af444666d4 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
ace26f81-f860-524e-af23-bcfc9068d2ee | note | FREQUENCY: Every Site
d689586a-bb74-5dc2-91c9-7b0a5700a9be | note | ACCEPTANCE CRITERIA: As-Built drawings
93ed5fa2-7d36-586e-965d-e24645044cf6 | note | HOLD POINT: In Process Inspection
046b2374-6c2f-5537-90c6-f8d8825b5f35 | note | RECORDS: As-built records
ec84a75e-c3da-5d07-bc1a-dc220b8405b9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 8 - RAMM DATA
df32f3a6-1f2f-5fa2-98f7-2bf43db0ad0d | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
0b257ce2-23cd-53e9-ad82-a348028d4e93 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
dab57434-41fa-5e3f-8a08-e56937718bf9 | note | FREQUENCY: Every Site
8c7a4884-e585-5d88-b94c-d537c6dad5e0 | note | ACCEPTANCE CRITERIA: RAMM SHEET
f094e2a8-94db-5a13-ac87-41b803da9a6f | note | HOLD POINT: In Process Inspection
d0a67be1-081f-53ad-8aa9-97706b0e4c9c | note | RECORDS: As-built records
948d75ca-ebf3-53bd-a1ab-bfa90bb07d6e | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
0560b2a0-be32-5915-9716-db9a1702be3b | note | Prepared by: Daniel Tat
099508fc-8a77-5ec0-80b9-1a8c133094c3 | note | Approving Delegate: Daeyoung Jeong
| checklist | Generic - ITP - Enabling Works - Vehicle Crossing | itp | ITP - Enabling Works - Vehicle Crossing | e5312353-c81f-4ea3-b091-049573bc67b2
| section | Site Set Out
| checkpoint | 1 - Site Set out
bed02b40-dd4a-5f7a-8ce6-105a3b9d875d | note | VERIFICATION ACTIVITY: Surveyor
896ac3fd-84e3-5352-9d47-12cdb01aeba3 | note | METHODS OR REFERENCE: Surveyor
03381a6f-b18e-5c3c-9446-dd55026d541d | note | FREQUENCY: Every site
6e516294-c5a2-5564-b187-17f9bf372ce7 | note | ACCEPTANCE CRITERIA: Site set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
66054417-5178-58bb-9606-28df12d42ca8 | note | HOLD POINT: Mandatory HOLD POINT -
4260c472-7d0f-561d-9853-ecddbdfe3e19 | note | RECORDS: Onsite records/photos
17af8160-3767-552e-9a79-07d72f725adb | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Standard VX
| checkpoint | 2A - Residential VX
54ef2463-fcf6-59a3-beb7-d712b297b54a | note | VERIFICATION ACTIVITY: QA FORM
20896e55-e538-5d98-99c9-37c5f1913f54 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
1fae260a-701c-5d61-86de-75b59cf1a4fd | note | FREQUENCY: Each VX
9dfca79b-51de-5438-b51c-8432d6727ac4 | note | ACCEPTANCE CRITERIA: Subgrade CBR > 3
e091bbe9-66a5-5375-82ae-b337c9f53aed | note | HOLD POINT: In process Inspection
d11e5d75-3f61-527d-95d4-3ba546dfa446 | note | RECORDS: Scalar Sheet
117dce22-a29a-5747-b950-0a66c7376dc7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2B - Residential VX
8435a116-108c-5bab-8ba0-a847c40fdeba | note | VERIFICATION ACTIVITY: QA FORM
0a86e80f-d917-5dcd-9f27-1ea7a81c641c | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
56bfece6-51e1-5967-96e1-639cb317303c | note | FREQUENCY: 4 Cleggs per VX
a0c162a7-a993-5c12-bbfe-f0b052756eb3 | note | ACCEPTANCE CRITERIA: VX to be laid using on compacted 100mm min GAP40.
1b163744-d040-54b9-8c24-dcfbbef6872a | note | ○ CVI > 12
66b20e56-05bf-57d2-b6e3-820f510376fe | note | HOLD POINT: In process Inspection
4735aab6-7257-5f71-88dc-a2d12227782f | note | RECORDS: Clegg Sheet, Photos
d1702fd8-d84b-5632-a25f-72b39106610f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2C - Residential VX
1aa2a9a7-9c6a-58eb-aceb-bfaa1412e2b9 | note | VERIFICATION ACTIVITY: QA FORM
34f75734-bbd4-58b7-b234-b3d8b0e299e2 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
c54b9fb7-627a-5c2b-a380-31dbaa53b307 | note | FREQUENCY: Every VX
d4686c70-9e02-506a-9d24-b37e5786c822 | note | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
bc04dffd-f300-5c35-bb6e-314bd758c079 | note | HOLD POINT: Mandatory HOLD POINT -
a1ead34a-20bc-54c5-89e3-3aa27ad67870 | note | RECORDS: Concrete Pre-pour Checklist
53b05a5b-cd28-524c-87c5-8cebdc95c81f | note | ONSITE RESPONSIBILITY: Site Engineer / MSQA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | VX Material
149f6bfc-be0e-50a2-9604-16021a91c517 | note | VERIFICATION ACTIVITY: QA FORM
8c43a39d-6cd9-56c9-adfc-feb9275b030d | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0756d50a-3af5-5ee1-9770-c03ea751b02e | note | FREQUENCY: Every VX
1b08e0bd-a4d4-519f-a180-2cfd6c6234e5 | note | ACCEPTANCE CRITERIA: 665 Mesh Required if 4 or more dwellings
c8fe4d38-78d2-5ba7-85d3-fcd34f9e5fb4 | note | HOLD POINT: In process Inspection
6a2a493b-6b1a-5c6a-9d5d-f12cf5d49333 | note | RECORDS: Photos
b6b929c1-5ac0-53ff-a3a9-f97bd1260a59 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2D - VX Material
f4f6d837-eb0d-50d3-b733-b9eec1401bf1 | note | VERIFICATION ACTIVITY: QA FORM
ce23f722-1f7b-5fc8-84ec-d09776f0e00a | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0d498d5d-3af0-5f88-bd6b-d02e1185d34e | note | FREQUENCY: Every VX
f4b3e8c0-87b5-52ae-a2e5-c5bac89e97b2 | note | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
78849114-06eb-5f71-b9a0-96c963649295 | note | ○ Thickness - 150mm
9add2ed5-3350-50c5-8a73-80741f783bd5 | note | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
852d979f-9b2f-557e-862f-ee94be78dbc4 | note | HOLD POINT: In process Inspection
6629e02b-128c-5d77-9f86-9bd07d1b1d3d | note | RECORDS: Concrete Docket
de9a7b9a-e2d9-5889-b6ae-b454920e611d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2E - Residential VX
a64d511c-c264-523e-9571-f9479f576267 | note | VERIFICATION ACTIVITY: QA FORM
bad96865-803b-59a0-8d6c-5dc5b08c9bad | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
0c88cde6-252b-5415-b760-27d2feadae38 | note | FREQUENCY: Every VX
d3c7e49b-8eef-5ba6-807b-7b0c6a873a59 | note | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
fa1b504c-e1ec-56ef-ab57-c03c8d0d0849 | note | HOLD POINT: In process Inspection
f4fe6a70-2447-5140-ac9e-5d88cc4f48ff | note | RECORDS: Photos
7d85ef4f-d162-5c3a-b902-bdf0e592cc3b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2D - Residential VX
0c24fe6f-3140-5ff4-a715-88c74141d863 | note | VERIFICATION ACTIVITY: QA FORM
18238588-6247-5cf6-b2f7-f010b0e2b976 | note | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
4ae295a1-06e3-5e3e-993b-73d39800467f | note | FREQUENCY: Every VX
59e8d854-8049-520e-9d3e-0cb27410116d | note | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
4ffdf3c2-60b5-5fc2-9fe5-5d9f3df6f4aa | note | ○ 1m reinstatement on carriageway
5a99b73c-8d68-57e9-980e-358c9b7f242a | note | HOLD POINT: In process Inspection
3e42cb2e-a576-5b27-9f67-c986aeae3763 | note | RECORDS: Photos
f17d9ae0-2c27-5b3e-9242-54df1ae0783d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Grass Berms
8037378e-b276-5612-a48a-53b575fd1f92 | note | VERIFICATION ACTIVITY: Visual
a2d32f7a-a67d-5a01-a10b-aca88cdfc069 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
7b6d3572-7542-5474-995c-0096a0775bc3 | note | FREQUENCY: 10m Intervals
a39546b0-f4d6-52a0-a6ed-4d771ac240e5 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
91eae4f6-47e3-50e2-a687-ea74bf85cf8d | note | HOLD POINT: In process Inspection
b9ca45a3-dc8d-5bf9-bb13-4819eb1bbb4f | note | RECORDS: Photos
ddf83711-1016-5335-a5f9-363e197dc511 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 4 - As built information
5baada23-e50d-5e35-8f3f-7a456b5c9fd8 | note | VERIFICATION ACTIVITY: Drawings
62740f1e-4f0e-50e3-886e-d2adf001dcf5 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
b7723ec7-60ab-5aca-81bf-c9d1e017f931 | note | FREQUENCY: Every Site
05db6444-64b7-57c9-b255-b1bbb59783ea | note | ACCEPTANCE CRITERIA: As-Built drawings
a72d370d-db53-52ea-86ca-d73fae3b919e | note | HOLD POINT: In Process Inspection
7d098185-1dfc-5d14-902c-fa703a35feef | note | RECORDS: As-built records
315868a8-3b18-5f01-b34c-61d6d2cb5718 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 5 - RAMM DATA
6adfb29a-bf91-5bd9-b66b-ef51b67dda4d | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
b6df0cf4-caae-555f-9d8c-a6bb4d69b8f5 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
3f7f1317-1da0-5409-b998-215fc4f99e3b | note | FREQUENCY: Every Site
9f66039c-1cb2-5859-99fa-531a872958ba | note | ACCEPTANCE CRITERIA: RAMM SHEET
6939521f-3742-5064-b6c8-4708185dcf1f | note | HOLD POINT: In Process Inspection
8cb1904a-beac-5d82-89ad-61cd802ac45a | note | RECORDS: As-built records
bc85957b-04a9-5896-b69a-a3564ed02647 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
a95c1163-6fb9-5ba9-be91-8cf8253d58a8 | note | Prepared by: Daniel Tat
aa26d8f3-144b-587b-910f-8538b6f17490 | note | Approving Delegate: Daeyoung Jeong
dcd2250d-f5fe-41e5-bea3-7ee0ce76e22b | checklist | Generic - ITP - Roundabout | itp | ITP - Roundabout | 83efb0f6-8291-4025-901b-5de4cf28c5a8
edd27201-4f72-4a12-bcf6-2fcbea662219 | section | Materials
a824971d-ab3c-4cda-bc65-5f62c33cc8ed | checkpoint | 1 - Kerb
a5733a1e-ea59-5889-9f7f-1f143d082fad | note | VERIFICATION ACTIVITY: QA FORM
01bd122e-e791-5c3e-a903-b688fc1800ec | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
9c3992c4-d677-55cd-ad95-4e95aa5c82de | note | FREQUENCY: Every site
2557ec0a-e97f-5186-88ef-91350fdc46a9 | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
80640386-1e74-53ec-8873-3451b164ecb5 | note | HOLD POINT: In process Inspection
f72f458d-a865-545c-b764-f375af4f13d4 | note | RECORDS: FH Concrete QA sheet, Photos
385e47d9-9f82-5389-bab9-cdf89f58b8b0 | note | ONSITE RESPONSIBILITY: Site Engineer
ea5a61d0-0b43-4f39-b099-fe922964a77b | section | Construction
617a615a-3d57-4b89-b1be-38fa337cd1a2 | checkpoint | 1 - Survey Setout
95138c47-6c78-574f-9a7e-f8e1a51c7987 | note | VERIFICATION ACTIVITY: Survey
33de4de3-62ae-52dd-8174-24ec482fcd56 | note | METHODS OR REFERENCE: Roundabout shape and heights to be set-out by the surveyor
db23239d-502a-52e4-be14-9fbbe6349a61 | note | FREQUENCY: Prior to commencement.
2de8bb7f-7d7d-5e6e-bc99-c52dfd4669e9 | note | ACCEPTANCE CRITERIA: Survey
3622a0cd-b4a8-5e7c-a089-e4406cf388da | note | HOLD POINT: In process Inspection
6d941818-b34d-5e18-8192-0bed9eed08f8 | note | RECORDS: Survey Receipt.
464c5307-5242-5d84-83ca-7822e8a54554 | note | ONSITE RESPONSIBILITY: Site Engineer
0a49e2c4-ef49-48e3-bf26-6c8e0041948e | checkpoint | 2 - Roundabout Apron
15e4f3a8-8b29-5c8f-b7b8-bfaebfbd3051 | note | VERIFICATION ACTIVITY: QA FORM
70e59b85-ef5d-5b38-b45d-0eefca42c203 | note | METHODS OR REFERENCE: Construction Drawings
14ddf861-768e-5c42-9c1a-57b8762479de | note | FREQUENCY: Every site
c668d141-bec3-5396-a1e6-3afe76bed6c0 | note | ACCEPTANCE CRITERIA: Chamfer shape to be handformed in-situ concrete pour with with two layers of 65 mesh with minimum 50mm cover.
f42330a6-0286-544e-8702-b7530d6444a0 | note | ○ 200mm thickness with broom finish NO OXIDE
9fcd5977-a667-5bbd-885b-ea64ff5adae8 | note | ○ CIV > 25
9acb4e1f-e039-5d60-a8d6-941b4b4761de | note | HOLD POINT: In process Inspection
57ff50f3-959e-55de-bca2-590becdb5f03 | note | RECORDS: FH Concrete QA sheet, Photos
9e59bfef-3bcc-51e7-a1c0-01f466cc76a0 | note | ONSITE RESPONSIBILITY: Site Engineer
b60a63c9-a27c-4a13-a749-80946a575e06 | checkpoint | 3A - Precast Kerb & Nib
0651469b-04fb-54b3-ab6b-4da3a7d4acc3 | note | VERIFICATION ACTIVITY: QA FORM
09f09c54-e171-500d-b20f-24885e6e935a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001
b93a3b54-a803-5df7-a42b-56adae22e125 | note | FREQUENCY: Each Site
f2ce983c-05a5-5193-8613-508fa1fd96ac | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
4676c5c3-b35c-56a0-86ca-0d60a0c69abf | note | ○ CIV > 25
7546feb7-9988-5bbf-bd56-b133dc243e87 | note | HOLD POINT: In process Inspection
a33ca80f-5735-5003-be19-4774f6e5d34f | note | RECORDS: Photos
65343a1a-8ee6-59c7-8a97-f570112f9b5b | note | ONSITE RESPONSIBILITY: Site Engineer
8b62c7ea-d7ed-46e6-a1b4-c6b73f2b2f91 | checkpoint | 4 - Concrete Infill
341e9f0c-f5c7-58e9-ac63-6d661038cab4 | note | VERIFICATION ACTIVITY: QA FORM
9076d6d8-2c0a-56f7-973c-e83e5c940705 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
e913b785-b61c-5263-bd9d-97538cf1c6db | note | FREQUENCY: Each Site
5f72c255-12db-579c-9902-2491a31d0a6a | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa Concrete
ef48b824-e881-5a5c-a26a-5eabcacc17a8 | note | ○ 6kg/m3 red oxide broom finish
3a58d00a-3de6-5b74-aaf9-cd8b09f318ec | note | ○ On minimum 150mm of GAP65
c67e06af-6914-5a5c-bccf-62267f0fbfa5 | note | ○ CIV >25
a90d4db7-810e-53ce-9802-c58fccd61584 | note | HOLD POINT: In process Inspection
1391fb58-dc7b-5a60-a742-ea950baabf5a | note | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets
4627e5b9-34d3-50fc-a9d5-cec1a901aa98 | note | ONSITE RESPONSIBILITY: Site Engineer
17f4b2a3-55a9-4c59-b9ca-f53c2734e281 | section | As-builts
9a85f7b6-0d31-42c5-a34c-90661d0c2a8e | checkpoint | 5 - As built information
ca008768-793d-513f-b761-167687d03ca2 | note | VERIFICATION ACTIVITY: Drawings
403105ab-5700-5715-a7cd-82f6c4dc82e8 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
fc5adb75-bcb3-5c13-9487-0dc613dc0b68 | note | FREQUENCY: Every Site
daa0d4a6-02cf-51d5-acee-c28d47a5ea81 | note | ACCEPTANCE CRITERIA: As built drawings
d313934b-4e75-54a2-9664-98b806017ef8 | note | HOLD POINT: In Process Inspection
1cd8c80e-9698-5426-a239-962b18035d5e | note | RECORDS: As-built records
78b74898-8b29-579e-9c77-3d31cc9570e9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
7e7635f1-b8d4-4f9d-9e35-5bde8e9d2555 | checkpoint | 6 - RAMM DATA
dca048bd-3a59-55ef-bc94-40fe57911346 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
1e64ed89-9e32-54cf-8e8a-0e7e7ca6a732 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
507a63d4-9832-5cbd-86f1-b878aa4877a9 | note | FREQUENCY: Every Site
e9468858-140e-5b65-aada-7008f4222532 | note | ACCEPTANCE CRITERIA: RAMM SHEET
b788bf8e-cfe0-5c27-8b1f-31c13520d114 | note | HOLD POINT: In Process Inspection
cc0e1e6d-bbec-514c-ba0a-576ba958b32f | note | RECORDS: As-built records
1399e6da-71c1-58d2-abcf-d5e7ee81a040 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
f7883bda-756f-427a-b554-1d7d59542df5 | section | ITP APPROVAL
eab5c2f8-1245-47c4-ba33-50d3f1776014 | checkpoint | ITP Approval
70b61432-b7c9-59c2-9f90-59deef309f3a | textbox | Prepared by:
812bce6f-7d14-5352-b515-836fd4898e87 | textbox | Approving Delegate:
| checklist | Generic - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | fca8b23f-0592-4444-b4ac-3fae6b65521e
| section | Stormwater Drainage
| checkpoint | 1 - Permits & Services (1)
d9657bf7-0559-596f-b173-8156a76b9581 | note | ACTION (Hold, Monitor, Witness): H
aad2db34-0f7c-5a32-b4bd-d3e8a65415ea | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
504e12ae-a716-5516-9489-7bf31f5af5a4 | note | FREQUENCY: Prior to any construction commencing
3db0b98d-834b-5deb-ae18-2d5f95d2905a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
210d0a6f-754d-5eca-a5ec-7ffe1fcfd38a | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
036251e2-c2f1-5306-a6fb-692ae559a9b7 | note | ○ AT Access Authority approved and signed by RCA Authority.
b79ce247-28e5-52f4-b627-a12474086f3d | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
aa98ec73-8591-5f93-911b-982f3edfef56 | note | ACTION (Hold, Monitor, Witness): H
176ac649-7c32-58a7-a15c-b2767ad1269b | note | DETAIL: Locate and mark out all existing services
3937805c-45da-5e7a-93c3-4571e2e85e98 | note | FREQUENCY: Prior to any construction commencing
2e003d4e-7755-518e-88dc-105d61c21e00 | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
60826fc1-ed88-52d7-9ccf-8ebb8d87c107 | note | RECORDS: B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
fdf6beda-f82c-5908-8b3c-00664dda814d | note | ACTION (Hold, Monitor, Witness): H
7e719661-877d-5c8c-9f87-44fb0d301673 | note | DETAIL: Sub-Contract and Supplier Agreements
01bae753-283b-5f45-a6cf-084f5b6b5ab7 | note | FREQUENCY: Prior to commencement.
ff1fb197-3689-5ee9-a780-ddca81c2ce3c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
8497c4bc-1c56-5caf-a80d-5c0dcf4e5f3a | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
affc836f-9a5d-5fc0-a47c-530742dc76f6 | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
108a964d-20ab-5627-807d-f37b4c1064f0 | note | ACTION (Hold, Monitor, Witness): H
33ca76a0-3455-505b-8816-ec1465c5fea9 | note | DETAIL: Design is approved and Drawings are of the latest revision.
4c624232-7ddc-5396-9005-307f83335c0a | note | FREQUENCY: Prior to commencement.
fd48cf73-fea7-519b-94e4-a244d3723db5 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
06a2667d-8ae1-5589-ab49-a3a6821c57b2 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
634cabee-a56e-59bf-907f-63a5d83c0438 | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
369fd83d-4a21-5236-8119-c1e59211a73e | note | ○ HOLD POINT of not issued to IFC.
1f9167ca-b36d-5fe8-8a91-50133fe1b00d | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
46b7873d-d589-57ff-9a96-149512b986ae | note | ACTION (Hold, Monitor, Witness): H
a3b3e953-9add-5cb1-bce7-c17de5ec8b4b | note | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
aeedebdf-5339-5dad-898d-21a658447050 | note | FREQUENCY: Prior to commencement.
1bf5f663-5dd4-5573-9bc7-5f27e1f1a9f6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
2cd2361b-44fc-5cbc-9097-bfce538ceb1b | note | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
71811587-13d7-537b-87e1-7c2b419d011c | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
c2fda340-a0d4-5c4d-91eb-6f79dd6aee31 | note | ACTION (Hold, Monitor, Witness): H
37065efb-d081-5abe-af8e-5198f8f21a6a | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
2796061a-b9bb-5549-9e29-460b7e802d0b | note | FREQUENCY: Prior to commencement.
da21c052-2ce8-5905-8d29-f82e1417e1db | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
c2c9c3a3-afb2-5b47-9b87-d87a809781e1 | note | CONFORMANCE CRITERIA: Pipe shall be check for freshly formed pipes and return if required
81e51974-b496-5ddc-9443-70932efb2b5a | note | 1) Class 4 RCRRJ pipes AS/NZS 4058
f4f33ee5-cfee-5067-a1c2-4f19a3b28872 | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
dd56c407-129d-58db-a507-1b49ab104291 | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
6aea91dd-b819-5f4c-be6e-782e15b6dbc6 | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards
3532b749-6bee-59cb-8abf-8344b7793017 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
83bdc7dd-f2ae-5037-882c-d66d5fa95726 | note | ACTION (Hold, Monitor, Witness): H
cb38dca6-881b-5e7d-8638-f65229ef4443 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
6741b398-387b-549d-8bbe-f50fb119cf65 | note | FREQUENCY: Prior to commencement.
1db7f5cc-a496-5665-9f3e-ea6b4f35ae56 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
e720e941-18de-576b-bd14-63ead5e8f2b8 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
f077fe5d-d9d9-5993-bcdc-ffc40c606ef3 | note | RECORDS: As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (1)
e84e010e-1b03-5e9e-9879-1cf20e2ed625 | note | ACTION (Hold, Monitor, Witness): H
d31e6df1-a791-5cec-95ca-9cd69eb0b02e | note | DETAIL: Excavation methodology
d2bab0f0-bf62-5f43-9842-13f26fa11cdf | note | FREQUENCY: Daily
4658c5af-9024-50a5-adf8-cbd663dd683c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
4a3c62ef-7fdf-519e-b815-ab89c4d57b8d | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
5e4e870d-c1a1-57a8-b465-dd5e12ef957d | note | RECORDS: Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
67ed6917-09e9-5907-acac-83751b2cbb33 | note | ACTION (Hold, Monitor, Witness): M
1d29e5c4-0536-5265-80c8-e55fff357f02 | note | DETAIL: Trench Profile - Width
a648b4cf-76a0-5e0a-a731-01127815456c | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
d5b1df48-dfee-5d1f-8e2f-454e33681515 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
4998c72f-4d4d-568e-b74b-c3e457a06fd1 | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
d0b5597a-8850-53c1-ae22-4a00bdf1030c | note | RECORDS: Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
ade2ed53-39f2-5988-bfa6-500d5daf56e9 | note | ACTION (Hold, Monitor, Witness): W
8ce57310-e086-519b-a5d6-8de7594d6ee9 | note | DETAIL: Trench Profile - Depth
7ba40026-8c2f-50a1-99e8-d986b1b685bf | note | FREQUENCY: Daily / as trenching takes place.
a40ea081-8a3a-5797-9b9f-fafe236f6b83 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
3f703f36-b8a7-510a-b9cd-d96d952a778b | note | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
63878052-2478-52bd-83b0-04afff02c627 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 7 - Trenching & Excavation (4)
3bca4336-2ad3-52a9-b3e1-19e24ee188e1 | note | ACTION (Hold, Monitor, Witness): M
a2c4a10b-d6cd-50e7-b081-25ca2902d3b9 | note | DETAIL: Trench Base
78b008d4-275f-5b3b-a9bd-e7433a4adeb5 | note | FREQUENCY: Every 10m
cbcc35f5-8fff-5d67-9e5b-0fdb44fe0f21 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
3490e826-74e9-5be7-9436-eb43408735d6 | note | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
730e7153-0b26-5153-9a17-a493b725b7bf | note | RECORDS: Test reports / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
bde5bf4f-1377-59a5-b966-4c4626541b88 | note | ACTION (Hold, Monitor, Witness): W
770ad3f1-9ebf-545e-8b95-394dadcf1faa | note | DETAIL: Placing and compaction of Bedding Material.
f1f96cbd-d56a-5655-8c04-b3ea1fb04356 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
5c6220c9-35c6-5dcd-8fe4-915ed179dfb8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
cb146afe-6f5e-5f26-8d92-df340a035400 | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
8f9ef139-bf94-5cfc-b372-85d352c8541e | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
2ca13bae-57b5-50c8-b409-89e9c6f6c52e | note | ACTION (Hold, Monitor, Witness): M
dcce34df-0598-548c-82d3-161be388e5f1 | note | DETAIL:
0a33ffc1-5c9e-5f6f-878e-4a53d6a8c78c | note | FREQUENCY: At any point of pipe
c8e13a75-782d-5de8-974f-6712f32d80c1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review):
14380e5c-27f0-5ab9-8d56-fb5803079b44 | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
b1a983b6-de22-569f-8712-70b946ac025b | note | RECORDS: FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
7d35f43e-caea-5e65-af60-4d13881fd400 | note | ACTION (Hold, Monitor, Witness): M
f650cdd9-e340-5af9-974a-7a4f94f1aa49 | note | DETAIL: Placing and compacting of Trench Backfill Material
fb75b25b-848f-578c-862d-a434744ac19f | note | FREQUENCY: Throughout Trench Backfilling operation.
f684c402-9df9-5006-bcde-a4814cd4dd56 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
9e29e5d2-e360-52f7-87f6-8052ec679e99 | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick.
3a46ea98-7bf9-566e-a3b4-854b0850eb48 | note | ○ Compacted backfill material to be free of Lumps > 150mm
31a3f656-5451-57d4-bdd2-b5d616af590c | note | ○ ATAP40 for subbase/basecourse.
1c245534-bfb1-539e-a8c0-27ea9898eea4 | note | RECORDS: Construction Photos
| section | Subsoil Construction
| checkpoint | 13 - Subsoil Material Compliance (1)
67092dd5-ce8f-5e21-a8a5-dafeb58e40b4 | note | ACTION (Hold, Monitor, Witness): H
9f11e025-1fc5-5c2a-b870-e80a9da2dd21 | note | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
05c732cc-5d51-5206-a5aa-181c2f011244 | note | FREQUENCY: Upon delivery to site
dff3c663-b27e-57d1-aa9b-0f881b1c7bb6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
97024ec8-7826-5382-a14e-fe24e5b6dd2e | note | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
e7c1385a-0ac5-542f-ad7a-827e0172ad49 | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Subsoil Material Compliance (2)
3c62a128-7553-5499-82fc-8b30f3c92dc3 | note | ACTION (Hold, Monitor, Witness): H
a344ae64-421f-5ec2-a009-0596283385b5 | note | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
757bf801-9730-5f72-ad56-e306e0e3e1ae | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3f3734cc-4b24-57e1-ac6e-be97d49e742e | note | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
89716549-cffb-5e80-9ea2-12f0f2a03e75 | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching (1)
a6be9cff-a11a-5407-a51c-ca178d5a5084 | note | ACTION (Hold, Monitor, Witness): H
a610ffe4-52e0-5ae1-9425-7f69f65206b3 | note | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
1b4522d0-db49-5956-8d5e-ef604e6d1148 | note | FREQUENCY: 10m intervals
170b0429-b7e0-5a6a-97a6-edc3a064a3a2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
0a61720a-7946-566a-8569-79520f35f19b | note | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
dbeee922-14c4-52cc-94bf-c88e18a9b4ea | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching (2)
6b9efa27-0a62-5baf-9e98-84713707f8bd | note | ACTION (Hold, Monitor, Witness): H
b90f343a-a97d-5d16-b861-aab7843fe48e | note | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
1139518d-346c-5276-b463-0d0c8727b26e | note | FREQUENCY: 10m intervals
1cd5c552-8af5-5ccf-9a57-9823a9850cc3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
a8c558d1-2090-5088-bc91-4b4c5d7a5573 | note | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
8486f481-c2fe-573f-bf77-7480a4c0ef81 | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Bedding, pipe installation and Backfill (1)
e5e3705e-3a93-56a7-b7a3-5ff0072b992a | note | ACTION (Hold, Monitor, Witness): W
86224cd0-daf9-51f9-a131-e8ee4b091049 | note | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
0d085919-6cac-5379-96c2-7fe5f69b2cd4 | note | FREQUENCY: 10m intervals
afe7047e-27c9-5aa6-943e-20a6fa95d037 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
b678af7a-3daf-5977-af4b-9e6bda1ffff4 | note | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
f5d5e11f-82b1-539e-b83c-3c713fb4cd82 | note | RECORDS: Photo / subsoil log
| checkpoint | 15 - Bedding, pipe installation and Backfil (2)
fcc075c7-410d-577e-b809-debc5b9fc3c3 | note | ACTION (Hold, Monitor, Witness): W
9f08dd79-d59c-59f1-9a12-b708c88f8f47 | note | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
8c24c07d-9cdf-5121-bb1f-49d1f4ace835 | note | FREQUENCY: 10m intervals
5ff5c979-ed6d-5335-ad8e-60b1e61567ef | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
ac778684-425d-50fd-a312-4e5c8c4fadbb | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
ad5205eb-c5a9-583b-9e19-b728e7e19061 | note | RECORDS: Photos
| checkpoint | 15 - Bedding, pipe installation and Backfill (3)
1926e600-94b7-593a-bda3-e8f970294513 | note | ACTION (Hold, Monitor, Witness): W
fe29e17a-d096-592f-8fae-4e5e28fc3175 | note | DETAIL: Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench
db994f66-38a5-587f-8e92-bb549d2d7d5d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
4e51c836-52ad-5a1d-86b2-b8d5596ab046 | note | CONFORMANCE CRITERIA: Ensure good coverage
ce8fd680-466f-59c8-843c-ebcf8d2a6de8 | note | RECORDS: Photos
| checkpoint | 16 - Catchpit Connection (1)
0d176cb1-3c66-5582-94c3-b9b1e7959bc7 | note | ACTION (Hold, Monitor, Witness): W
a728849a-defb-51ef-8b91-ff95ad7bf335 | note | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
6922785c-374e-5ddb-860d-b3218b6eaf3c | note | FREQUENCY: As required
bfa49746-e605-5396-beb5-8c25cc7fa26f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
27ea2d70-6190-57b3-b5a1-30d7c5171dbd | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
6376c198-c9b9-518a-8dd9-26db5636c3e2 | note | RECORDS: Photo
| checkpoint | 16 - Catchpit Connection (2)
0eadeffa-755d-53ca-8d3f-3e823f7408f4 | note | ACTION (Hold, Monitor, Witness): W
d0d191e6-61c1-549b-b16e-0e72d77351e6 | note | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
4532f19f-34e6-556a-a30c-4f38ed4be978 | note | FREQUENCY: As required
59cca33c-a20c-545f-8605-ed5f5c0259a6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
e69dd3e8-17b2-5b71-a679-65a45bfa2e19 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
1c83133a-8081-588c-9e41-75ef4573554e | note | RECORDS: Photos
| checkpoint | 17 - As-Built Drawings
99158f6c-2b7f-5cf5-a76f-fa0869deb968 | note | ACTION (Hold, Monitor, Witness): W
0fb19bbf-d006-5007-950c-98a47df1ca32 | note | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
133ef5ea-a39b-54d4-883b-e8c22feb0124 | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
235309aa-844e-5a8b-8566-0396b0a50e32 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
bb5aaa10-7650-503c-a533-0a8d9ede4fc2 | note | CONFORMANCE CRITERIA: As Built and GIS Data
f141db4a-08fd-5206-8ef3-240b17473e2c | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
| section | ITP APPROVAL
| checkpoint | ITP Approval
8f491406-94ba-5b33-919a-e89b4c19cee6 | textbox | QA checked By Quality Manager:
76771dc8-f8ae-53dd-974b-278821f72d04 | textbox | Accepted By Engineers Rep:
| checklist | Generic - ITP - Traffic Islands | itp | ITP - Traffic Islands | 8d432edf-9a02-4dc2-b5a6-47ca24049b24
| section | Materials
| checkpoint | 1 - Kerb
b6b1331c-bee0-59dc-ba66-57b87ca51037 | note | VERIFICATION ACTIVITY: QA FORM
30c02fc5-83f1-5c05-ad84-bb422541657a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
1a435718-8f7d-5a6f-af82-0cf5534e8ba0 | note | FREQUENCY: Every site
fd2fa1c0-5614-598e-91e9-46c1a9ce5d63 | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
64bd602a-ab93-54e1-924b-259e5af3c9fc | note | HOLD POINT: In process Inspection
88d67bac-9b94-52f2-9fe5-1c713643d6ad | note | RECORDS: FH Concrete QA sheet, Photos
f6ac72ad-6e8c-52ef-85bb-9269b3175349 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
675ca2d7-3ec6-55da-81b2-13c6c52512e5 | note | VERIFICATION ACTIVITY: Survey
b587fd66-268e-5178-ab4b-4288e824130a | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
af3848bc-1c15-53c4-8277-f527e824e417 | note | FREQUENCY: Prior to commencement.
58f29129-6d1d-548f-b69c-0f32f35819ea | note | ACCEPTANCE CRITERIA: Survey
ea52c2c3-8c88-5175-a197-5b74c4dbb077 | note | HOLD POINT: In process Inspection
e2e66c26-7866-562f-b12e-51272e0c8dc4 | note | RECORDS: Survey Receipt.
7f76d810-4bfd-5ab5-a341-00f3cde33c77 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3A - In-Situ Concrete Island
81ea597e-97eb-5a46-a7b1-38b4f131e284 | note | VERIFICATION ACTIVITY: QA FORM
7201b883-eb67-5dfa-a49d-ae33df941fc8 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001
7629092c-acce-5a9f-a050-98abed965b7f | note | FREQUENCY: Each Site
f547a132-6bc7-522a-95ad-498613601383 | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
c6c46c66-960b-5062-96c8-715354a085e3 | note | ○ CVI > 12
9a8bba41-8481-5b9d-8167-770529bb3c80 | note | HOLD POINT: In process Inspection
3a05ba5f-efe2-5ad9-afdb-c010d6d20987 | note | RECORDS: Photos
db0dd4ae-c15a-5639-8270-c2c1634f51e0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3B - Stick On Concrete Island
26f56ea0-e26e-5d42-8043-07931cbb0736 | note | VERIFICATION ACTIVITY: QA FORM
a07458e8-f959-58bb-ac09-cf9dfed34aac | note | METHODS OR REFERENCE: TDM Technical Standards - IS0002
89f506f0-4202-5e5d-b7e5-322739c7e969 | note | FREQUENCY: Each Site
01fca360-4f4f-5c3c-969a-15b5828a0d97 | note | ACCEPTANCE CRITERIA: Bonding Agent to be applied on existing surface
63ddb4b8-ae1b-5207-9c5e-99047a64eeb6 | note | ○ Mountable Kerbs laid flat to be sticked on to the existing road using Epoxy Mortar Mix.
63ec1ed4-a79b-51f1-847b-fe857882569e | note | ○ Gaps between kerbs shall be no larger that 10mm
9b345f5e-6dc9-5731-80f0-71922ac93a0a | note | HOLD POINT: In process Inspection
df5ec3be-06af-5166-aa6c-46ec16bb1e49 | note | RECORDS: Photos
264d0d2d-fda4-5d05-bc74-9ee74b5d4011 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infill
23a2fe1b-ca31-5c2a-8ed1-9dc72b55912b | note | VERIFICATION ACTIVITY: QA FORM
c3e01d96-d3d2-5818-95ce-b5253fd5efa3 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
abea870f-3419-5506-b035-c6665776aa1a | note | FREQUENCY: Each Site
cd6bd56e-b0cc-55fd-bea7-d1d065c5f1b5 | note | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete
ad3e73c8-1079-57af-b199-1e500b90f5c9 | note | ○ Surface finish to confirm with Engineer's Rep
d591df67-0f62-57d6-a229-30eb5b19dd89 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
19adb25f-1910-58f0-a721-0dfc2da68027 | note | HOLD POINT: In process Inspection
4439c73b-7ddc-515d-b2c9-3c0bf80e6fb1 | note | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets.
895da5e2-26ac-504a-b6e9-26c4072e465a | note | ONSITE RESPONSIBILITY: Site Engineer
| section | As-builts
| checkpoint | 7 - As built information
d76e706a-dee5-5dcd-a542-b1177fb5e830 | note | VERIFICATION ACTIVITY: Drawings
9b6cc1ea-9663-55fb-b68d-cf6b5532f0e9 | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
b90a7cdf-3c9e-5f2e-a634-8b75636512f0 | note | FREQUENCY: Every Site
8d3623ae-d19c-5c73-a14c-f9cc0857f6c2 | note | ACCEPTANCE CRITERIA: As built drawings
269c5e51-270a-5a9f-9968-0a3f4ec5a88e | note | HOLD POINT: In Process Inspection
7492fb5f-b865-53ed-b48d-30a128c48063 | note | RECORDS: As-built records
90ec0da8-12fa-5722-a79c-73d93b62c688 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
459f196e-3906-5e40-99f8-2f2c5c19ce94 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
dd577764-5f37-5f5d-914d-90e6dedd75bc | note | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
53204457-2828-500d-a8cc-c876428fb339 | note | FREQUENCY: Every Site
32f9d37c-004a-5e85-a0e0-94dfdeced8fb | note | ACCEPTANCE CRITERIA: RAMM SHEET
f35d9566-8cb2-503b-9934-ff9960b2c350 | note | HOLD POINT: In Process Inspection
258a79a9-782f-5858-a676-0377ccc05caf | note | RECORDS: As-built records
17e144b9-696e-59a3-a473-de66902585b2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
36b7d6d5-b552-5438-815d-509e9fbdcda8 | textbox | Prepared by:
6704840e-23ed-5273-bcb6-899b08d23aca | textbox | Approving Delegate:
| checklist | Generic - ITP - Traffic Signal Ducting and Pole Erection | itp | ITP - Traffic Signal Ducting and Pole Erection | 2ecd5b50-ac21-4d8e-9b6e-c8170cc554d6
| section | Ducting
| checkpoint | 1 - Permits
3b5734d7-06da-5eee-9970-881157c5d371 | note | ACTION (Hold, Monitor, Witness): H
f2ee16c2-9cf6-5b13-940b-48d17495fb27 | note | DETAIL: Obtain Permits
4ba0e0f4-b961-577f-acb9-5733f6dbf132 | note | FREQUENCY: As required
80f46b79-0c99-5d69-938d-b4315c665af6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
813d294d-8542-580d-836e-16c278cd6ac8 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and first gas permit obtained
5eafa57e-e1dc-5478-91f7-948b8e04e6a1 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
c509cb16-afd5-5524-9a9c-6f2b0f8930af | note | ACTION (Hold, Monitor, Witness): H
ae9c463c-532e-5a6d-86ec-f87a42da12ab | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
18c590bc-a0e0-599f-a21b-ce62474ef87b | note | FREQUENCY: Prior to commencement
0e994853-a223-57ef-aae9-15179048af91 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9f201086-355e-565a-a252-0b609587fc25 | note | CONFORMANCE CRITERIA:
ff88dcdd-df57-5ff0-bd35-3b94145a8efc | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (1)
bf7b3f76-bf53-5acf-adbf-9e08079c234b | note | ACTION (Hold, Monitor, Witness): H
16a29511-1d9b-5692-a6ad-33bcb4ad4ce1 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
08b0ce5c-15c7-572b-b90f-dbaab33f4652 | note | FREQUENCY: Prior to commencement
0b789db4-6ab8-5f2a-8b00-5abede2e02e6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
18fe5986-b9f0-57cd-9024-46da31e75bea | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
a6326975-11be-5ea7-aec0-c6b27689137e | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (2)
14147ea1-90eb-57c6-a36c-4e609b76f071 | note | ACTION (Hold, Monitor, Witness): H
5fbc985a-cb45-549b-8879-1c71b39607e2 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
71c82c4c-0f0e-5f95-89d0-ca6044e7ffe4 | note | FREQUENCY: Prior to commencement
0c6a45bc-1bbc-5d5a-acf1-4ccf69fa0e9a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
eb165579-fceb-5d1f-8b36-906614b3e39d | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
93220056-63f3-5c59-acb6-85d4c86e424d | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
0ce9df33-dd85-5843-85c9-865c5ab0d499 | note | ACTION (Hold, Monitor, Witness): W
170a294d-69f9-5dce-8c13-e9e3a3d728ed | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
2f167019-7e4f-5846-9fd5-c47c44ae3ae6 | note | FREQUENCY: Prior to Installation
f59eaebf-d7a8-52cd-947c-cd43c80bd7e8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
58a52e74-6900-5f81-a324-1861519a422c | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
f428f649-e4f1-5d6a-9e4e-a80315f3d3fe | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5 - Material Compliance (1)
b3e981e1-b504-5801-b590-4cb6e5af6a86 | note | ACTION (Hold, Monitor, Witness): H
214aff81-cdc6-5983-90ab-1edad995c239 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
1abe4ac4-77c4-59b5-ab06-7d128c73cd4c | note | FREQUENCY: Upon delivery to site
597e9d72-140d-54cb-a139-f8ae92b770ba | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
d041da6b-5878-5b49-91ba-455d0819de03 | note | CONFORMANCE CRITERIA:
75f41205-b6f7-5244-905e-904ccbe36932 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance (2)
ad9e5cf0-5768-57c9-9916-75b5790531ef | note | ACTION (Hold, Monitor, Witness): H
1bee89ee-6f95-57f2-a434-a4dc6f0cade9 | note | DETAIL: Ensure all concrete used is 20MPa mix
4ac1184d-751d-5677-bc89-6e359def2ebb | note | FREQUENCY: Upon delivery to site
41b0b80f-0aa8-528c-b5c2-6f2575fbbf6f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
de9fba26-9d8b-516e-bde3-ef89af3129d3 | note | CONFORMANCE CRITERIA:
8ebd71fb-2fec-5f56-a59e-d3f768e21f9c | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Trenching
7f76e2b0-23e7-5849-b86a-030ac8cd5c5f | note | ACTION (Hold, Monitor, Witness): H
50735309-0009-536d-82e9-df135e9ac975 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
3771b107-fc58-5f6d-94dd-f46382a08db1 | note | FREQUENCY: 10m Intervals
8a51b0e7-d741-58a1-9948-44cf0e91ae0f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
1376a80d-d528-56d0-8f28-bb69466fb9b8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
b798af3f-aa7d-5312-b23d-e6b19c9dca02 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
af6ba2cf-6666-581a-97b2-50b60644b7e5 | note | ACTION (Hold, Monitor, Witness): H
8c1f2d86-2ef9-55b2-817f-d7dae22258e2 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are laid at correct depths, grades and alignment as per design dwgs
6cd96e42-4653-5a8b-8861-35e6c69aab92 | note | FREQUENCY: 10m Intervals
abc08934-6594-514f-99d7-e6d167002a29 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
67c581ff-80bf-5491-a0c4-0a39a4745046 | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
52ad6a29-9aa9-533c-a423-84165512f811 | note | RECORDS: Dip sheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Duct Installation
34e867e2-a55b-5396-8904-c2d50f971d4e | note | ACTION (Hold, Monitor, Witness): W
02aa9ca1-0c85-5b59-bf1f-edd694e64bcf | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
270d539a-cb04-5575-ba16-76d81e32bb48 | note | FREQUENCY: Prior to Installation
8ec15d67-4d49-5d53-9e2b-290104551af6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3c693cf1-dec3-5fcf-9dd2-c196f93300fe | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
5a68b619-b7b3-554f-844d-1b9133e9d344 | note | RECORDS: Photos
| checkpoint | 7.1 - Duct Installation
df50ae25-c0d8-50b7-939b-83777b3155d1 | note | ACTION (Hold, Monitor, Witness): H
187da16e-8fa6-571a-85a1-77eea1204c03 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and Atop min spacing tables
ab3af74f-1d98-5e0d-8e31-9e0885708d60 | note | FREQUENCY: 10m Intervals
6531f0d0-b61f-543c-aaed-795d0241575c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d5247c9b-2221-5532-be61-975f7d397ce8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
56c374b3-5612-5042-aa8f-8261bad483dd | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Duct Installation
8484eec6-0725-5a1c-b309-e23f187fe9b5 | note | ACTION (Hold, Monitor, Witness): H
b4f549a3-a658-5bff-9c44-1c8724e3394f | note | DETAIL: As-built Survey
7c4c6537-f48e-5a99-888b-d06164bf3be6 | note | FREQUENCY: 20m Intervals
ccf5b2ea-819e-5df1-a0f3-628c9cf947a7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
79a6d0d1-ac5b-5db3-b765-9db0bc57acaa | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
aedf4d3b-5e29-5bc0-a5f7-85637b7c830a | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
786e7f21-4a9a-5df1-9849-e60197915b69 | note | ACTION (Hold, Monitor, Witness): H
4df2ad16-e3aa-5b97-a125-4afa6675e3a9 | note | DETAIL: Lay min. 150mm GAP<12 for bedding and haunching
5cf51500-a012-52ad-89bf-fe85f2fb26e0 | note | FREQUENCY: 10m Intervals
f94ebb91-d8fa-5d31-bddf-d84c22380415 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
0b6d3300-3860-596a-8a16-bde6ea933712 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
c7e663ee-4ad3-5e87-b197-fd9e26d117ae | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
effc4780-8506-55a7-8501-0d11461cc10b | note | ACTION (Hold, Monitor, Witness): H
df3fa227-0c5c-5272-889a-23a773e3cd32 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
a5d9d127-9d0b-5470-b1d2-2b79cff362b8 | note | FREQUENCY: 10m Intervals
fe8729bd-da2d-55be-86fb-ce063303a57a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
cc204c6b-6fd3-5b78-b41f-7c4d7b6b09aa | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
7f5ed50e-39dc-596e-849c-99459248d153 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Traffic signal pole erection
3ec81107-ee76-579f-9c21-6d174fd573c8 | note | ACTION (Hold, Monitor, Witness): H
2299daa7-6664-51aa-a26f-d990c6cae8b4 | note | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding
b331737b-58f6-52b0-846c-0c77927a6184 | note | FREQUENCY: Per pole
c215dac7-30ac-5898-81a7-d5f93823ab45 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
251dd912-6438-5fea-acc8-018ad1b27a42 | note | CONFORMANCE CRITERIA: Sign off by design engineer
4efdfd48-c35d-5e0d-89e7-7396e57be12b | note | RECORDS: Engineer sign off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 - Traffic signal pole erection
1652bfb0-f65d-55b9-9e14-4e1574432bb5 | note | ACTION (Hold, Monitor, Witness): H
93756d7e-c93a-5178-9099-3f779c88948c | note | DETAIL: Ensure Pot hole is as per design with required depths and widths
7ec2d110-9466-5081-9ade-99979df4b494 | note | FREQUENCY: Per pole
b6d24561-ccc1-573e-a8dd-ebdba188ad66 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
a88e5ffd-7d7d-564a-895c-fa2564e4ce5f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
7d5f8101-5a67-531c-b4c8-2e2789fcd598 | note | RECORDS: Dip sheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 - Traffic signal pole erection
bb6a3003-8a2c-5ebc-9d89-75eb7970f732 | note | ACTION (Hold, Monitor, Witness): H
9564b367-fd75-5cfd-b05a-51fa18d1222a | note | DETAIL: Ensure Poles are plumb and within design tolerances
aa3551cc-b636-5abd-80c5-fa2195924266 | note | FREQUENCY: Per pole
c3f1eb58-f7fb-5a10-bcdc-93b309b9704c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
0a106116-f05b-5f27-b860-0e59d44b3c86 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
2ecbd602-27fd-5e6d-9007-2799ef419ffe | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - As-builts
b092e487-5656-56b8-9fa4-b0baec5d9089 | note | ACTION (Hold, Monitor, Witness): H
b6df8043-ba37-58da-acbe-f6f8d6963174 | note | DETAIL: Red pen mark up drawings to be included in QA file
7fc23052-8b90-53d8-81df-1ac70f79db20 | note | FREQUENCY: At the completion of the Lot of work
18457e70-4ecc-534c-8f88-0cebf2c22826 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
878f8de0-2c1b-5a86-9d32-32f83cba3de6 | note | CONFORMANCE CRITERIA:
3250c3b0-581c-57f0-8786-c3a2bc70a9f7 | note | RECORDS: As-built Drawing
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
d392a3b6-8012-5994-a830-d61e3cbcdc8b | textbox | Drawings used for Construction incl. Rev numbers:
7cbabded-fdd3-566b-b7fa-e34eb7ea5b34 | textbox | Reference Documentation (Notices/OFIs etc):
77b34d7c-4b1c-53cb-83c2-ec51927f4fa6 | textbox | QA Compiled By:
94e5f33d-29c7-5c0e-a8e7-974fd95d6166 | textbox | QA checked By Project manager:
c25cfc0a-8890-5961-bff6-2785dd154609 | textbox | QA checked By Contract Manager:
93ffed73-55cb-5d92-8234-c8c4b0738bfc | textbox | Accepted By Design/AT Engineer:
8cdc9506-08d6-41fe-9a4a-28c371c1837e | checklist | ITP - Albany Bus Layovers - Enabling Works - Footpath, Kerb and channel, Pram Crossing, Vehicle Crossing, and Berm | itp | ITP - Enabling Works - Footpath, Kerb and channel, Pram Crossing, Vehicle Crossing, and Berm | 4bb52ed4-2e4b-4fb8-8c03-639c6fb6c814
495a0c93-9ca4-47a0-96a4-fe40f722780a | section | Survey - Set out
09ca7252-453e-4014-9448-0cc005558679 | checkpoint | 1 - Site Set out
d65f1553-05de-5e71-ad65-66263b4bbb2a | note | VERIFICATION ACTIVITY: Surveyor
aa56ca37-f7bf-5fcd-a8d2-1435e8960250 | note | METHODS OR REFERENCE: Surveyor
93bc7dbd-4d78-520a-ad15-4c62af3f0524 | note | FREQUENCY: Everysite
41839126-8c26-566c-82e5-4a45ede6c8b1 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
15425676-b216-5322-ae2d-330838f20234 | note | HOLD POINT: Inprocess Inspection
d29dacd0-0c03-55ec-9403-aa986781b20f | note | RECORDS: Onsite records/photos
43de06a9-7a1d-5ae9-aec3-a2ffbaa5a45f | note | ONSITE RESPONSIBILITY: Site Engineer
52887547-5f72-4fed-8d81-e641a384e492 | section | Kerb and Channel
da0db0bd-0b51-4d6d-b7f3-e01e045570c7 | checkpoint | 2 - Kerb & Channel
ab061c3a-c2e1-5ce5-bac1-0c7d44886202 | note | VERIFICATION ACTIVITY: QA FORM
da327151-ac8a-5689-8da7-c1fc83a9f4c2 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001, KC0030, KC0031
1e658e52-69ad-5393-80ed-fca7b78052fe | note | FREQUENCY: Everysite
3fac40ad-4c77-52b5-ac29-a91ecf1f83e5 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days
e7fbe3e4-496a-5b19-a3c7-3e6df03a4082 | note | HOLD POINT: Inprocess Inspection
082a8bb5-ddad-51d9-bf41-dd826e469d8d | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
74c0de2a-5fd1-5bdb-86d9-0d547c39406c | note | ONSITE RESPONSIBILITY: Site Engineer
c87ebaf5-0e3b-461a-a54a-e0a5b1bc996f | checkpoint | 3 - Channel Level
703a79d0-7e6e-52a2-b964-38e2f04a1677 | note | VERIFICATION ACTIVITY: QA FORM
fcef575d-2201-5b66-9345-e1e71f0fa63d | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
13cfdb45-8273-5e95-9ec0-e9774223036e | note | FREQUENCY: Everysite
ebca9714-a8ac-560f-9217-556fdaf57bf4 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
d9f0d81f-0927-5930-a616-d64682322ecf | note | HOLD POINT: Inprocess Inspection
cdeaecde-ad0d-550b-acf4-f1c83d792c74 | note | RECORDS: FH channel QA sheet/photos
b74d16c2-2fed-5238-bd6c-40b8408f050a | note | ONSITE RESPONSIBILITY: Site Engineer
1dc5afe9-1b69-4e0f-bae5-3e7a0620d36b | section | Footpath
d49da0ea-8f23-44f0-a9b6-eb83fe308d95 | checkpoint | 4 - Concrete Footpaths
67e927b3-8379-5e63-895a-2835446efb2e | note | VERIFICATION ACTIVITY: QA FORM
f4577169-5cd0-5303-92de-fa4265382170 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
6b347cb2-60f5-52ea-be8f-23fc4f03e84f | note | FREQUENCY: 10m Intervals
e3008b81-fb2b-5cf3-8f5e-6170bf53a7df | note | ACCEPTANCE CRITERIA: Basecourse - 100mm Gap40 min. thickness
f86ecc3f-96bc-56e8-867a-89d8538ed857 | note | ○ Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX)
5453f533-e091-5aec-a814-71b2a2eadf0f | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
fa76c29f-c3cb-5bcb-9b48-7ebd5ae52dc9 | note | HOLD POINT: Inprocess Inspection
7d21f1c6-5a4e-53cb-9698-2da08fbfe80f | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
160919da-1c79-5d92-84b7-d12d695a0a91 | note | ONSITE RESPONSIBILITY: Site Engineer
57947b53-2f63-4530-ad7c-490024253e6f | section | Pram Crossing
f0e42aa1-c526-40ed-a802-d4b59441035d | checkpoint | 5 - Service Covers and Street Furniture
75d07126-e83a-5693-8b2c-6286d5c2b696 | note | VERIFICATION ACTIVITY: Visual
af07cde6-04f5-5a9e-adee-9fbde86607cf | note | METHODS OR REFERENCE: AT Contract Specification 14000
f11b91a8-408f-5458-82d0-7d42f976551a | note | FREQUENCY: Everysite
1fc4fcac-f439-5250-b91d-c209d6bfd38d | note | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
e42e62ad-f34f-56e8-8f01-9049bc4d6952 | note | HOLD POINT: Inprocess Inspection
d27a6772-3d8c-5a32-a8c6-942456953a11 | note | RECORDS: Nil
5d94daf4-a461-55bc-8cf7-a0dd9d7fdd5a | note | ONSITE RESPONSIBILITY: Site Engineer
e19a96d9-5704-4ade-80a7-3dee25f5d14e | section | Grass Berm
a6a98bc0-83e4-4433-844c-83654cbf7033 | checkpoint | 6 - Grass Berms
d96b01cf-071f-5857-a607-970d61a19aed | note | VERIFICATION ACTIVITY: Visual
35a75397-6675-58d2-8318-1f0c055e1327 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
b32a4330-11b5-504c-8b60-6d8016e33d6f | note | FREQUENCY: Everysite
399a621f-012c-56d6-bec0-38352797a326 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds.
4cc45631-9a06-5069-86a7-39f8560c2772 | note | HOLD POINT: Inprocess Inspection
ac19fbfa-1a2a-5b80-97ca-ee17d2ab4db7 | note | RECORDS: Photos
e613ff98-7e07-5030-ad04-159ece531221 | note | ONSITE RESPONSIBILITY: Site Engineer
a6d81d15-a81b-46b6-b4f1-2b00db437905 | section | Wooden Bollard
8de0baf8-183a-4b94-b331-8a4ce014087c | checkpoint | 7 - Wooden Bollard & chain fence
73c7b7b0-c1ce-5182-997d-1658f295ab43 | note | VERIFICATION ACTIVITY: Visual
a266ad80-d1d8-53f0-a7d9-61122d8b231e | note | METHODS OR REFERENCE: TDM Technical Standards - FE0012
526c1179-6164-5861-95c2-f58f675fc26e | note | FREQUENCY: Everysite
3ac512e9-cc96-5db7-8103-18de64c0afd6 | note | ACCEPTANCE CRITERIA: 150mm post and 2500 spacing connected with chains.
03ac9157-e451-5424-99d2-1998e6a9c957 | note | ○ Post 600mm inground with 75mm thick around and 150 thick at top collar with rebar.
af177cda-6cc3-59dd-ba8a-855857c5ebc8 | note | HOLD POINT: Inprocess Inspection
fdb316a4-8bb9-5b0d-9474-43e0c3060379 | note | RECORDS: Photos
8ee6e056-90ac-5dd4-acc1-e4ea845abaa3 | note | ONSITE RESPONSIBILITY: Site Engineer
ed2147ca-227c-42f6-9586-c5bf6dc70f1b | section | Timber boardwalk
2dc91bd7-abeb-4cf7-be62-4f3c3ef9e360 | checkpoint | 8 - Timber board walk
9f1f9322-8478-5495-8117-80d36a00ccaf | note | VERIFICATION ACTIVITY: Visual
5815f482-0943-5652-9549-981c2b96c678 | note | METHODS OR REFERENCE: TES Design drawing RD-001 REVA
89b3b7f0-55ac-57c6-958b-0385027dcbad | note | FREQUENCY: Everysite
1e41240e-0580-52b6-83e6-57c6c8e50ea2 | note | ACCEPTANCE CRITERIA: 150mm x 50mm H5 Timber Blocking
9b503a12-d364-507a-b90d-327e44ba5953 | note | ○ 200mm x 100mm H5 Timber Bearer
337b9ea7-08ba-52fc-b396-9196558fa338 | note | ○ 250mm x 75mm H5 Timber joists 490mm centres.
df0c91ec-0b14-5958-a761-02c53a55ea31 | note | ○ 150mm x 50mm rough sawn H5 Timber decking with non-slip geogrid
b7587233-3059-5ccd-9667-161dcb320a44 | note | ○ M16 Bolts Marine Grade stainless steel expansion bolts into concrete rain garden wall
ce0f67b4-8e8d-55e5-92cd-3d8d01151bee | note | HOLD POINT: Inprocess Inspection
dfb29257-e034-558c-a28b-be1cc998f776 | note | RECORDS: Photos/dockets
f1fe8f12-7c21-53ce-b567-f3b5a8324fc3 | note | ONSITE RESPONSIBILITY: Site Engineer
c6698926-877c-45d6-880f-3841d20f4388 | section | Asbuilts
c3b2b494-b69b-4067-b130-c854fa53a980 | checkpoint | 9 - As built information
b69a282b-4ddd-5264-9081-cd09d3a6174a | note | VERIFICATION ACTIVITY: Drawings
15abc1f3-0589-595a-9200-2663166a38dc | note | METHODS OR REFERENCE:
2712d20f-b568-5a9a-a7ac-2b4a55dd7def | note | FREQUENCY: Every Site
ea87b09a-1ec1-555c-adec-079e701f38c3 | note | ACCEPTANCE CRITERIA: As built drawings
03c51d79-eeca-5801-b190-1ad4199bd084 | note | HOLD POINT: In Process Inspection
d1574a7c-e35a-5e6b-a9b4-95013bceefa1 | note | RECORDS: Asbuilt records
90e64eab-1673-5e95-85d9-c70a4bce3237 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
cdd802d9-6418-434f-a65b-62d6909e2df9 | checkpoint | 10 - RAMM DATA
76f510d6-d03e-5d6a-9f4e-d2cf41d24229 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
6c177de1-70b4-5c05-8742-2badeb66fb45 | note | METHODS OR REFERENCE:
4f0a9a71-34b8-582d-8a0f-92ffaffd8f42 | note | FREQUENCY: Every Site
3b1a4d95-b78a-51e8-b87d-9c6a3aac316a | note | ACCEPTANCE CRITERIA: RAMM SHEET
f7b67b82-5417-5f4d-9410-20ea9be937e2 | note | HOLD POINT: In Process Inspection
eba72a48-2af6-5cd5-85d6-758626cf95d5 | note | RECORDS: RAMM Sheet
7d805053-5782-5b2d-820e-3a394adc850b | note | ONSITE RESPONSIBILITY: Site Engineer & PM
7388f3c1-2a73-490a-bde8-f943c064cb81 | section | ITP APPROVAL
6fc01d76-ff7e-4c31-89df-a02baaff9592 | checkpoint | ITP Approval
0ebd8fe6-5212-58d5-93c4-38bcc040a40a | note | Prepared By: Ajithkumar Ayyanar
b2f4403e-4f4f-5ff1-9112-3a7e1363f3b7 | note | Approving Delegate: Denny Jeong
bf51e5ef-78cb-4974-8591-3e67825a2c05 | checklist | ITP - Albany Bus Layovers - Pavement Widening | itp | ITP - Pavement Widening | f4dc342e-cf0c-40ac-ace8-8fc0e5b32c90
d6a0a513-c752-416e-974f-144a1cd99bdd | section | Excavation
8791f85e-c3b8-4448-b9aa-fe71736346b1 | checkpoint | 1 - Identification and location of shallow services
8f9101d2-38d6-5623-b4e7-0f2e862f885b | note | VERIFICATION ACTIVITY: Measure depth of cover to utility services
2e59a0bd-d49e-5a60-90ec-d4395ce87c9c | note | METHODS OR REFERENCE: Trained contractor staff
91312475-9910-5b16-868e-d58d259d7e81 | note | FREQUENCY: Two measures per service (each side of the road)
1deb7d19-045d-559d-9973-a2fec01368d1 | note | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage.
d27bceeb-e463-5afe-80b6-2977b07c04dc | note | ○ Otherwise consider relocation or concrete cap
187f8eaa-8973-5779-b08e-66979ae10ce7 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
bce9d486-d949-5853-b53b-651605e9e7b3 | note | RECORDS (Responsibility): Marked up sheet
bea4cf79-68c0-571e-9ff1-dd9ab783a942 | note | ONSITE RESPONSIBILITY: Project Engineer
4ed42c15-7516-513e-9643-03d8b3f49bdc | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
3d1f1cbc-fd97-4379-b669-dbae2ae3fb0b | signoff | AUTHORITY HOLDPOINT
9342b0e9-73d8-4e7e-a239-c28b84981917 | checkpoint | 2 - Milling / Cut to Waste Existing Pavement Area = 650mm or match adjacent existing pavement depth to avoid water ponding
70aea2f7-4484-5c45-8b47-0eba41fd7b3a | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
78bfaf9b-8635-5b47-85f9-6af89318d984 | note | METHODS OR REFERENCE: Survey As-built / Stringline
fc83bb74-d668-5157-bcc6-37874adaccf3 | note | FREQUENCY: 10m each lane
dcd16561-2716-5512-97de-fe59e033687f | note | ACCEPTANCE CRITERIA: +0 / -20mm to design level
e1c4c421-9a3f-5a7f-9cde-0a82475128e7 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
fd68e18f-5091-52f7-bcee-322f5f908cad | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
0536c157-4c0e-52e5-a4a0-e6d9860acec7 | note | ONSITE RESPONSIBILITY: Project Engineer
da3570db-278f-5aef-9720-69b9705bfde2 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
863254b1-0bf7-4dea-a020-7ea116a0f7ea | signoff | AUTHORITY HOLDPOINT
d93197d1-e994-4a0b-a8ef-0840067568ca | checkpoint | 3 - Subgrade
a1253418-79ed-57c2-83da-8ad32d43fa11 | note | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
2bd8ad63-0d04-5804-9209-d2336874de05 | note | METHODS OR REFERENCE: Visual Inspection
d7d3112d-35ff-59a3-a5df-b7630bdf24eb | note | FREQUENCY: NA
843ae737-66eb-5790-8dc7-7a56b18f9960 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
e3db9800-1207-5071-8152-9f97725e7f76 | note | TYPE: Inprocess Inspection
de8533e2-062a-51d7-9602-80cd4306a8cb | note | RECORDS (Responsibility): Photos
74fb750d-0d23-57ad-b757-149f64909440 | note | ONSITE RESPONSIBILITY: Project Engineer
51b71128-c03f-44a0-83aa-11ba1bbebe87 | section | Undercutting Contingency
78a68961-e66a-4818-9b37-cd48d83b2122 | checkpoint | 4 - Contingency Weak / Soft Spot
b24a4b64-35e1-5cb8-b9bd-cea820a9bc66 | note | VERIFICATION ACTIVITY: Scala Pentrometer tests
c38ef092-0253-54a1-812e-093895561319 | note | METHODS OR REFERENCE: Design Report
8a0b8741-6f64-5473-b358-ae1c63c1fa7c | note | FREQUENCY: At 10m intervals in each lane
dbe6dbb7-3b7b-532a-ad20-9e23a907c9fa | note | ACCEPTANCE CRITERIA: Subgrade CBR ≥ 3.5
9a3a4539-ebc5-5442-a542-e3dde8214d84 | note | ○ If CBR < 3.5 but ≥ 2, Excavate further 200mm and place a bidim A29 geotextile on subgrade and replace with GAP65 subbase
9c29a57b-cdbc-5602-936a-ec8068481be5 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
32e9f9e1-db12-586f-958c-7acc91ac5f40 | note | RECORDS (Responsibility): Marked up drawing
5533c87b-d42b-5de4-b230-4ae5b1f1d5a9 | note | ONSITE RESPONSIBILITY: Project Engineer
c4f47e13-f36c-5c63-b231-72fec044668b | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
5a7c7f9b-e13d-491e-a1f9-19f1b4eed3a1 | signoff | AUTHORITY HOLDPOINT
12dba874-70fd-4a47-815d-883320bb3aa0 | checkpoint | 5 - Contingency Weak / Soft Spot
38cb87c8-b49c-5032-8e44-15c3f8ef1183 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
04d684cd-2786-5dca-b36c-a58ab5db1a0c | note | METHODS OR REFERENCE: Survey As-built / Stringline
a1e005cd-5f73-5775-9526-124f2d521736 | note | FREQUENCY: 10m each lane
15c73a5f-7d4c-5ba6-b2d6-ec1f5fa921e9 | note | ACCEPTANCE CRITERIA: +0 / -20mm
d9e525ee-5334-54ef-9f24-aeba0913f351 | note | ○ No trafficking of the excavated subgrade
71d7ff4a-9c4d-5d67-89d9-ae970c9870e1 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
cb3f6fcb-8c21-50ce-b5c7-2d6fa15e6504 | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
621efb4f-7fef-5ca1-9996-bfed9f11f5f1 | note | ONSITE RESPONSIBILITY: Project Engineer
e3b4587b-098a-5604-9c78-ffa191e6a738 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
6dd54f86-a532-4b4f-b967-5669a1cb9dfc | signoff | AUTHORITY HOLDPOINT
c99675eb-8125-4347-b38a-20b0a1eb3323 | checkpoint | 6 - Subgrade
e8eca98f-4ccf-5ac1-b969-b1689a843a46 | note | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
09d7de77-e8f7-5041-b8b6-1af8d786525f | note | METHODS OR REFERENCE: Visual Inspection
45e30816-ecd6-5ee2-b37e-f3c9eb450045 | note | FREQUENCY: NA
ce862a58-3b73-5184-a777-2ace375b1f70 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
cfe4fce8-da84-5a59-b933-f0dcb6ee500e | note | TYPE: Inprocess Inspection
19eeb51d-7ca2-5bf3-9827-aa4636b09976 | note | RECORDS (Responsibility): Photos
50a1ecab-6102-5e00-97f0-9394d1ff3d27 | note | ONSITE RESPONSIBILITY: Project Engineer
9d135f01-811d-40bd-bd18-e913642852b1 | section | AT AP65
69ed59ea-639a-418d-9870-63eb08f3a5fd | checkpoint | 7 - ATAP65 (material)
3c00ec12-9ae6-5d49-a1b3-e8415a2e472c | note | VERIFICATION ACTIVITY: No non-compliant results
bf0cad77-90a3-5be5-a4ec-87b0f72eae99 | note | METHODS OR REFERENCE: Material test results
9e001244-bbc9-5065-8923-113756afacce | note | FREQUENCY: Once
1786ea31-b379-5e1c-9085-435e13242959 | note | ACCEPTANCE CRITERIA: Compliance with AT Series 800 Specification for the Supply of Aggregates
9f78c71b-8107-57f1-835b-1e3a23503836 | note | TYPE: Contractor Records
e4941250-858f-50ab-9e27-c588839d5e93 | note | RECORDS (Responsibility): Testing Results
1746a6ad-9b13-5d9b-a126-6903156ae4af | note | ONSITE RESPONSIBILITY: Project Engineer
4a0673b5-b020-44b8-87cb-c1786a78aa60 | checkpoint | 8 - ATAP65 (Compaction)
fbfab5f7-bce2-518e-9343-97cb9fac5d4c | note | VERIFICATION ACTIVITY: Density Testing
08501375-1cdd-50ff-a6de-18fbef27ede2 | note | METHODS OR REFERENCE: Clegg Testing
82df60e6-4d1d-566a-ba39-84086fe82812 | note | FREQUENCY: 5m grids
2c03af48-8ec0-5827-ac8d-d8b2ce14d4e3 | note | ACCEPTANCE CRITERIA: CIV > 27. to be compacted in 150mm layers
a36160e8-5c0f-5725-837d-7924714e87cf | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
428c41af-720e-5b5e-8df5-e3dea714040b | note | RECORDS (Responsibility): Testing Results
1cb2e1ea-89ca-553e-a55a-ec1b42cbd536 | note | ONSITE RESPONSIBILITY: Project Engineer
803c0640-5e6f-5297-b65a-f27da783955f | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
ea53f997-7d9d-4548-bd08-8fca3dd8ebaf | signoff | AUTHORITY HOLDPOINT
1d89486f-e2f8-4dae-9767-2019ac6598fe | checkpoint | 9 - ATAP65 (Level Tolerance) Backfill areas to bring up levels to -225mm below FSL
467dff22-8f5d-5adf-bbe3-ebeaf1ba0a20 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
5bddd4fb-30d3-5287-bf1b-351b207d7285 | note | METHODS OR REFERENCE: Survey As-built / Stringline
ad99867a-97e2-5ea6-bea6-bfeb50581a82 | note | FREQUENCY: 10m each lane
7376e2db-866f-5a2d-86c9-31daf3e11dbe | note | ACCEPTANCE CRITERIA: +0 / -20mm
2b4fb7fc-577f-50b5-b1b9-7206b3e0b153 | note | ○ No trafficking of the excavated subgrade
1536eee0-320d-51bf-9047-3c1b6eb863ec | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
ebd9f605-8194-55cd-ab10-e1aafdce2d16 | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
58db4e51-4e9d-5983-842e-8da87b7883df | note | ONSITE RESPONSIBILITY: Project Engineer
cc435f89-d7e0-5827-baba-ca25322e84bf | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
aee3b498-ed5c-4b6e-912e-3b921e6f9f16 | signoff | AUTHORITY HOLDPOINT
5d371ad4-1121-4a58-bfba-98beb97facc8 | checkpoint | 10 - ATAP65 (Surface finish)
547df5ef-49e2-55c5-bff6-338388f0bffb | note | VERIFICATION ACTIVITY: N/A
2d1bc8d5-ead5-5bec-badd-b5a340193d50 | note | METHODS OR REFERENCE: Visual Inspection
a71ace64-6d5b-5756-91de-7da33abab6de | note | FREQUENCY: NA
03a47ae5-8875-5bce-8f3a-fdcfe8b10c3c | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
9b3db6ea-0ce7-5b32-ab60-5a5fb00fe918 | note | TYPE: Inprocess Inspection
a952dcaf-e9e7-5f3a-8d4b-5f4eb05eec82 | note | RECORDS (Responsibility): Photos
dc4f2b3d-e899-5821-b78b-22f94be1896e | note | ONSITE RESPONSIBILITY: Project Engineer
f6c41af8-f461-4250-9557-02428f9f3e8f | checkpoint | 11 - ATAP65 (Deflection Testing)
17d0d053-e0b6-5130-bae9-cc383e3be09b | note | VERIFICATION ACTIVITY: N/A
02305a83-4d8f-5e04-a827-0fe2e19e1ea2 | note | METHODS OR REFERENCE: Benkleman Beam Deflection Testing
4fe1d094-2b5f-5007-8041-6b920a3b714d | note | FREQUENCY: NA
426984cc-f709-5a05-b6a9-9ff364f5dfd0 | note | ACCEPTANCE CRITERIA: Target Deflection:
bb7b0a94-ceb6-56ec-bf15-fe29722eac7e | note | ○ Maximum Deflection = 1.6mm
7e3f2d8e-1ace-5906-a3a2-974f0fb668e9 | note | ○ 90th Percentile Deflection = 1.4mm
e3519c4c-fede-560e-9b72-9b72d895f9a6 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
d31eb9e8-58e7-5d75-9afb-719187aa2419 | note | RECORDS (Responsibility): Test Report
b38804cd-e88d-5e21-8fea-4dc77770c959 | note | ONSITE RESPONSIBILITY: Project Engineer
4744c489-6994-5364-8abd-16068218d2c0 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
d2e9a869-8722-401a-be27-bc09439c1a6c | signoff | AUTHORITY HOLDPOINT
3862007c-994d-4068-909d-0d09296ef534 | section | Emulsion (Concrete and AC layer)
17bfadd7-b69c-437b-a287-6757c4a78a37 | checkpoint | 12 - Heavy Tack coat and blinding
3f171509-9745-526b-a5a8-1cf4578a025a | note | VERIFICATION ACTIVITY: CAT60 cationic emulsion or approved alternative
07c2f6eb-187e-5a0d-8577-e20f91aec112 | note | METHODS OR REFERENCE: Visual Inspection
13f3bc3a-24ac-52f8-bd28-63bd2175782a | note | FREQUENCY: each lot
2d958f47-be46-597c-9784-2cba43ca3ce6 | note | ACCEPTANCE CRITERIA: Hand spray tack coat emulsion (residual bitumen 0.6L/m2)
6b4dcc0d-d08c-5322-96ef-216ee496c377 | note | ○ Blinding mix or milling max 5mm depth
f3f15bd5-1fa8-5bd7-9e3b-72e7067e94ee | note | TYPE: Inprocess Testing
fea67088-c7ff-5645-92a0-f4dab73ec9b7 | note | RECORDS (Responsibility): Photos
045eab0b-ca3b-59b5-8261-6935d564c888 | note | ONSITE RESPONSIBILITY: Project Engineer
913d830c-b3d9-4411-a879-775f33111e11 | section | Structural Asphalt (65mm AC14HF & 105mm AC20)
62d6feee-f91e-423d-a570-1bcfd01d6848 | checkpoint | 13 - AC14HF & AC20
622a650d-3cf7-5217-a23a-03d811bc17ac | note | VERIFICATION ACTIVITY: Mix Design
92149866-57f3-516f-979c-330139fef327 | note | METHODS OR REFERENCE: Sign-off by Designer
78545fa8-e220-5758-b340-d6fe0087ff2d | note | FREQUENCY: Prior to starting
de415504-8701-5d4d-afa4-8127722e2a19 | note | ACCEPTANCE CRITERIA: Sign-off by Designer
bc7b9dca-5fd5-541a-b045-b20ba2ebb682 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
5fe8488c-b3be-57d5-a586-528813fc0ef1 | note | RECORDS (Responsibility): Mix Design Report
6dcd2132-4035-5890-8981-c8946f13199b | note | ONSITE RESPONSIBILITY: Project Engineer
3d110dcc-3e06-506c-8fa5-6bf8b80cb4bf | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
72ba117b-e556-4ce5-9612-90fa12d01d1c | signoff | AUTHORITY HOLDPOINT
69e5e09a-7ed6-4037-a762-1cf2e8ca1034 | checkpoint | 14 - AC14HF & AC20
d9ed640d-6872-560e-85e5-4c71fe7cb2c0 | note | VERIFICATION ACTIVITY: Check weather reports
14cb8192-84fc-5398-98fe-9b1a0bd93d20 | note | METHODS OR REFERENCE: Check weather reports
963909c2-2887-5265-bd97-91e5683a894e | note | FREQUENCY: Daily
dc155dfd-d6ab-5d00-953e-e25f02bd3144 | note | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
163554c4-2047-5f80-bba1-e380b28a0c18 | note | TYPE: Inprocess Testing
cae571aa-f882-598b-ba2c-e6da73c828de | note | RECORDS (Responsibility): AC check sheet
1e54664d-34d0-51ca-921e-fd1a5f82c69c | note | ONSITE RESPONSIBILITY: Project Engineer
f634d3c7-03fc-4222-8b50-2132e98405dc | checkpoint | 15 - AC14HF & AC20
c08c955b-a43e-5820-9d91-2802802a1b74 | note | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
a4c244c4-3c60-5a07-9130-ad030e526720 | note | METHODS OR REFERENCE: Visual
dd1b68a7-2a04-5735-8f29-ace1570cc449 | note | FREQUENCY: Prior to starting
7ee4ca6f-b3f5-5f02-b3ec-03b13cedcad8 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
4650e7be-a700-57ed-a7bf-3b0a3a0b38a8 | note | TYPE: Inprocess Testing
0cf60e44-c2d4-56b1-b1f4-19ddf53b423c | note | RECORDS (Responsibility): AC check sheet
21066ae8-b8fb-5f26-b548-dd21dfc6b05b | note | ONSITE RESPONSIBILITY: Project Engineer
efc3afd5-699e-4954-8ae3-a2435e123023 | checkpoint | 16 - AC14HF & AC20
d30ddcab-35d9-59fa-8793-02b97a632d6b | note | VERIFICATION ACTIVITY: Production tests
79d2e57a-6bdb-5278-9e1c-7c1a66a772ce | note | METHODS OR REFERENCE: Grading, binder content, max density, temp
764ca51b-a058-50bd-bced-5f831108e78a | note | FREQUENCY: As per M/10
ba0f5101-7975-5cd7-80fb-4507e5d71a04 | note | ACCEPTANCE CRITERIA: NZTA M/10
87052a1c-5aef-50e4-8449-d2d2b8934aed | note | TYPE: Inprocess Testing
58aedd06-6b0d-5890-a7a9-bfde10a71549 | note | RECORDS (Responsibility): Lab test
b535b5b7-6c18-58ef-9a65-ccebc12c7a54 | note | ONSITE RESPONSIBILITY: Project Engineer
672436a5-b960-44b1-8d4c-12a30bb59a39 | checkpoint | 17 - AC14HF & AC20
9969d6b3-733a-5d39-9893-1ff9b1493026 | note | VERIFICATION ACTIVITY: Surface finish inspection
3946fe34-3c46-52f6-86e0-0c4c027b4472 | note | METHODS OR REFERENCE: Visual inspection by the Engineer
4bb91751-c00a-5079-a8d2-340626168fe9 | note | FREQUENCY: Each lot
bdabd153-1dcd-56d0-bafd-5626123a525b | note | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
9872ee57-5039-5694-a32e-5e7759232ac7 | note | TYPE: Inprocess Testing
e29bc638-7130-56be-99a4-eb45b3ef6e52 | note | RECORDS (Responsibility): Inspection sheet
4f859d06-a297-56da-abc0-e426cd5584c0 | note | ONSITE RESPONSIBILITY: Project Engineer
b79dfb81-de5b-40b5-b180-d2c90f874243 | checkpoint | 18 - AC14HF & AC20
e660c596-fa84-5dd2-9842-6c2ab44cebf6 | note | VERIFICATION ACTIVITY: Density testing
c898a949-4ae6-5524-89d1-d29f92d0e643 | note | METHODS OR REFERENCE: NDM
79d58fed-a239-53d1-8f35-18c035305f2b | note | FREQUENCY: Every 10m each lane staggerd
405bb9ea-314d-5505-b83d-7eefcb335ae3 | note | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
dd3f0605-4b0c-5e40-ab0b-aa5d05f9d44c | note | TYPE: Inprocess Testing
783b1c87-494e-50d8-9fdc-29aa76b7833c | note | RECORDS (Responsibility): Inspection sheet
91ba405e-09e3-5412-b683-8903c17ef237 | note | ONSITE RESPONSIBILITY: Project Engineer
11a501fa-cd5c-5328-b717-1f48adea6108 | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
a69214d0-9ec8-4780-b88f-940798933967 | checkpoint | 19 - AC14HF
2008e032-376a-5512-a766-d06ec7b58731 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
3c556c00-1f65-5e7e-a165-985b1730a3ec | note | METHODS OR REFERENCE: Survey As-built / Stringline
bb1ab7ec-be15-537b-b92e-01581a27bb3c | note | FREQUENCY: 10m each lane
17c3897f-cb74-503a-9fe3-e9f2ade3299c | note | ACCEPTANCE CRITERIA: Thickness no less than 65mm
f4467c0d-bfe7-5382-af29-35a2b997a26a | note | ○ Height discrepancy +/- 5mm
54f770e6-85e8-5aaa-b503-3b8c4e77b7bd | note | TYPE: Inprocess Testing
c6ca72aa-5d27-515e-8927-8a802d89a8ff | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
620926bf-5d28-5082-a402-e4c1c929ca9b | note | ONSITE RESPONSIBILITY: Project Engineer
693dbf92-6214-4f4a-8fdd-5e40fda72129 | checkpoint | 20 - AC20
629c3b4b-bd66-5c4b-886a-fbb03eb53722 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
f3633d19-c221-5bea-9100-e749ee14a94f | note | METHODS OR REFERENCE: Survey As-built / Stringline
54727753-6d39-560e-920e-5b0e30c61623 | note | FREQUENCY: 10m each lane
5edd4215-1e70-5c7f-b5ea-ac8fd75f3d83 | note | ACCEPTANCE CRITERIA: Thickness no less than 105mm
e6d6e849-c0af-5609-955b-ef19d4a036c4 | note | ○ Height discrepancy +/- 10mm
49882702-3d82-5c9c-969a-5f106fe5c667 | note | TYPE: Inprocess Testing
6aaaa9d8-fb05-567c-8779-7a37f3e094e5 | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
9f4aca2b-6d21-5f1d-b6a4-d17b006f1dd8 | note | ONSITE RESPONSIBILITY: Project Engineer
8dc6426b-b397-48f6-a2ae-bdaaf1f89f21 | checkpoint | 21 - AC14HF & AC20
eec2e8ab-c44f-5fbb-b88a-812d36239b69 | note | VERIFICATION ACTIVITY: Density testing
37543752-d1e8-5923-9120-bb8ff015be23 | note | METHODS OR REFERENCE: Cores air voids
7a02012a-d7ad-5e78-beb1-6fe43ed0c4f6 | note | FREQUENCY: Minimum 8 mat cores & 3 joint cores
334cb881-f2b2-5047-86c5-89ca38f1263c | note | ○ Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
46a865fe-b150-5faf-8993-40ec8f9e18c2 | note | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
9d133012-b0cd-5dd4-906e-f61037f9360d | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
05fe88f2-fc41-56e6-888c-c232e4cca19f | note | RECORDS (Responsibility): RFI response
72c6a570-b1e4-54ae-b2f8-1a2eeae82e68 | note | ONSITE RESPONSIBILITY: Project Engineer
eeeec3da-0263-57bb-8089-bfbc60edf9cc | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
6e8b637c-d3d8-4b44-b5d2-6b284612592d | signoff | AUTHORITY HOLDPOINT
18f7a5c3-cc8b-4e26-95bb-208941055c93 | checkpoint | 22 - AC14HF & AC20
f7a236cf-db1b-5a26-ac90-5c0375dbc002 | note | VERIFICATION ACTIVITY: Thickness
43623dfe-00de-5c60-80a2-4055195d57fc | note | METHODS OR REFERENCE: Cores depth
f0808fd4-1109-5a92-a720-8648e40a6ea5 | note | FREQUENCY: Minimum 8 mat cores & 3 joint cores
5150ca37-6ff3-5364-81f9-2b39f9db77cb | note | ○ Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
805f8299-550b-5d1b-8c66-383f3aabcb4f | note | ACCEPTANCE CRITERIA: Target thickness 170mm (no less than 170mm thickness for AC14HF and AC20 combined)
9a16b71f-2378-5591-ba05-6a6aaa19f912 | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
437fe9b3-5918-50de-91b9-e6d6b6fae8af | note | RECORDS (Responsibility): Core test report
aa0c8807-bb1c-56a4-b842-bf067ddebbbd | note | ONSITE RESPONSIBILITY: Project Engineer
ff24c781-5bbb-52a9-a3fb-b12439e1c329 | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
3fe0f977-4459-4300-910b-59ed7dc58bc3 | signoff | AUTHORITY HOLDPOINT
7392416a-4190-40f4-9c97-ab13596508b5 | section | Asphalt Surfacing - 55mm AC14
007f6907-f172-4818-bbb0-0bf653c069af | checkpoint | 23 - Shape of road
888bf7f2-3c94-52ad-9ef8-bf0fa42ba0d6 | note | VERIFICATION ACTIVITY: 3m straight edge
c0387b51-6a36-577d-9741-6b627dbd5862 | note | METHODS OR REFERENCE: NZTA M/10 spec
daa7ab11-a286-5cb3-ad44-ef0cfbe67229 | note | FREQUENCY: At joints and any other areas of concern
4aa9e588-3f17-556e-a4ca-d7c59bae22c9 | note | ACCEPTANCE CRITERIA: Irregularities < 5mm under straight edge
5e0c77f9-25a3-5591-b195-99d17dff2dda | note | TYPE: Inprocess Inspection
638888dc-8785-5d59-b3b7-a0539cea952f | note | RECORDS (Responsibility): Check sheet
3f8036bc-0934-5cb4-9657-76dec22645ac | note | ONSITE RESPONSIBILITY: Project Engineer
4c33cfa2-41b9-4a78-b32e-33db0d4cd4f1 | checkpoint | 24 - Temperature Limitations
2bae6d2f-eb66-596a-8fd4-6473062de76f | note | VERIFICATION ACTIVITY: Temperature
3a3f1aa7-c2da-588f-9621-cde99243414e | note | METHODS OR REFERENCE: Contract Spec / M10 Spec
de23bc55-86de-5c1e-aef9-d72a859f6d81 | note | FREQUENCY: Every Site
9a00d2db-9059-5eaa-9e87-d34312fa6348 | note | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree
ce797836-53c3-5dfd-83ad-3af087884828 | note | TYPE: Inprocess Inspection
2184ee56-00f8-5052-a600-03c21546efe5 | note | RECORDS (Responsibility): Asphalt QA
19686f88-175e-579f-ab9d-659b1b95be9c | note | ONSITE RESPONSIBILITY: Project Engineer
bfbba310-6570-457a-8540-0d4a379cb4f6 | checkpoint | 25 - Surface Preparation
0ef629c6-d714-58ad-b425-00385026b0b4 | note | VERIFICATION ACTIVITY: Visual
07eaec86-0e8b-52c5-85c9-cebf9ff98e89 | note | METHODS OR REFERENCE: NZTA M/10 spec
ce991bef-6d1e-57e8-ac7c-1de55a033856 | note | FREQUENCY: Every Site
f637fca8-a631-5341-a121-c11d422d6250 | note | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
930e8d85-e6ff-5291-a33f-f8a52223bb9c | note | TYPE: Inprocess Inspection
78180b27-7b48-5dd3-a990-9564c73f50e5 | note | RECORDS (Responsibility): Visual
f882c9d5-6fb4-5bf4-9af2-ddebac373382 | note | ONSITE RESPONSIBILITY: Project Engineer
6a04cdd1-c509-4310-8281-0849aedd0a40 | checkpoint | 26 - Asphalt Production Tests for AC14
c8ffbc65-a62d-506a-906f-39622d7a6182 | note | VERIFICATION ACTIVITY: Production Tests
9979737e-2b25-57e3-9bcc-2b843a43110c | note | METHODS OR REFERENCE: Grading, binder content, max density, temp
b11e7aed-971a-5e4f-bbec-5ab7b72b2578 | note | FREQUENCY: As per M/10
30605f69-1441-51d8-98a4-1b10f50f84fd | note | ACCEPTANCE CRITERIA: NZTA M/10
53d73e65-f4c5-5e36-bee2-2b9d247ea3e6 | note | TYPE: Laboratory Testing
96b9981f-5b06-5352-8de7-c7da444e4c19 | note | RECORDS (Responsibility): IANZ Lab
a3f40422-f89e-590e-84ac-82a658adf8ab | note | ONSITE RESPONSIBILITY: Project Engineer
3c56eddd-3645-4c6b-96b5-fda798ad4052 | checkpoint | 27 - AC14 - Layer thickness - 50mm compacted depth
c01182f2-3e4e-59a7-8ae5-54e1637c29c8 | note | VERIFICATION ACTIVITY: Insitu
adc5cccf-5ade-5401-93ad-0cc9ba4c1cf9 | note | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
a526ccb3-d3ca-53f3-b7bc-d94c07d02c65 | note | FREQUENCY: Continuous
e5ad6741-349d-57ec-afc1-19f63092d165 | note | ACCEPTANCE CRITERIA: 55 mm minimum and 60 mm maximum compacted depth
3e175316-be5a-57cd-84fb-7a676e015966 | note | ○ Final asphalt level to be 5mm proud of lip of channel
e4d1f41d-d1b2-5db5-965d-985558028a47 | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
a9c15b02-9c31-5f21-aa1c-797931fa1461 | note | RECORDS (Responsibility): Asphalt QA
612b4678-cff4-583f-b0c3-7b1d4375783e | note | ONSITE RESPONSIBILITY: Project Engineer
27ad7701-97a2-5ce7-8cf7-6892b7d15fdc | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
18490e13-15dc-457d-b118-1482f14396d2 | signoff | AUTHORITY HOLDPOINT
a69f9092-dd8e-4cf2-860c-b6eeee684262 | checkpoint | 28 - AC14
bcd88d43-ae43-5f8c-b4a6-b4564d88fd8b | note | VERIFICATION ACTIVITY: Density testing
0a927cf6-d747-58fb-ac67-93ee0020f752 | note | METHODS OR REFERENCE: NDM
966666b4-f4c9-56b7-a936-cde78fca9dc7 | note | FREQUENCY: Every 10m each lane staggerd
e9898853-eda7-5607-8b85-4d9d835ad6d6 | note | ACCEPTANCE CRITERIA: NZTA M/10
f5e6e8ae-a6f9-514d-a537-9cd432f6c224 | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
3aabeed9-6e3b-518d-bd8c-5b6750103107 | note | RECORDS (Responsibility): RFI response
defe9d64-d453-56c7-a20a-e7e30fee5da1 | note | ONSITE RESPONSIBILITY: Project Engineer
b59ac8f0-caec-5a3f-8096-92d217d255c7 | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
2a365a81-9781-4d5d-b1b1-af095ae72288 | signoff | AUTHORITY HOLDPOINT
a2bd620c-1423-4316-a450-dd5f2264e152 | checkpoint | 29 - AC14 (Deflection Testing)
ccb87b10-815a-5089-b1a4-991ca397ad8f | note | VERIFICATION ACTIVITY: N/A
ea1f8f03-309c-5d4b-abab-f3f1b7517833 | note | METHODS OR REFERENCE: Benkleman Beam Deflection Testing
d13eb62e-18eb-5c31-b9c1-ca1e2356db31 | note | FREQUENCY: NA
1c2e25f2-6b65-5076-9024-8a203dea9a43 | note | ACCEPTANCE CRITERIA: Target Deflection:
d8fbe835-3b89-5790-989d-aca7d7518336 | note | ○ Maximum Deflection = 1.0mm
6e8f9ad6-2982-548e-b9e1-0e3c5ecbf854 | note | ○ 90th Percentile Deflection = 0.8mm
c959223b-6185-57f7-8c20-90acf2d9cf03 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
bea2337f-9bd8-586f-b0ef-6f405bc6ea6f | note | RECORDS (Responsibility): Test Report
382f47f9-3ed8-502a-a698-67e1c60035cb | note | ONSITE RESPONSIBILITY: Project Engineer
a2ae1807-14f4-57c6-a5da-794ff130c5f8 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
8fea91ca-5c25-4a46-a81b-a828225dcce9 | signoff | AUTHORITY HOLDPOINT
5ffab88a-3a84-40bb-be2f-127a7843c48b | checkpoint | 30 - Reinstatement of Linemarking and RRPM's & Apply Joint sealing
d2e29872-5879-5c58-adf8-4d26bf7e9a6d | note | VERIFICATION ACTIVITY: Visual
47dbe470-2635-5bb7-b6d8-8d47cc752d22 | note | METHODS OR REFERENCE: Visual inspection
5da7481d-1147-5154-843b-4bb3c6d504d3 | note | FREQUENCY: Every site
846b00fb-f5df-5aec-a4b6-350477730c61 | note | ACCEPTANCE CRITERIA: Visual inspection
dd42c7d6-cba9-5d0d-ab2c-1c1122ab553b | note | TYPE: Inprocess Inspection
36f2bf12-7e98-53a7-a890-3f5ad64405cd | note | RECORDS (Responsibility): Photos
ccf25e77-9a51-52c8-9e78-281a34ebe534 | note | ONSITE RESPONSIBILITY: Project Engineer
7eb3372d-47ad-4efc-9d85-ff07fc73f9ae | section | APPROVALS
1253187a-ee13-46af-b785-e583410f18e0 | checkpoint | ITP Approval
814eaf4d-bc92-544e-95a1-4c4b3716ec9e | note | Approved by Project Engineer: Ryan Simon
9685f6d2-0b5d-57cc-a3e0-259d4075a58a | note | Approved by Contract Manager: Daeyoung Jeong
2c320978-b0dd-52d3-af0b-db31b43faf96 | textbox | Approved by Client Rep:
22ef14bd-dd6f-45fe-a188-0580da013446 | checklist | ITP - Albany Bus Layovers - Signage | itp | ITP - Signage | 0f96e401-b7fe-45c9-9685-65304da31d11
11bb58b0-e14c-46f0-bbd8-2aa4f56d573a | section | Site Set Out
65179e02-0855-4fd6-94de-596f87704f30 | checkpoint | 1 - Site Set out
e43bd1ed-f944-5baf-9465-0b1d5d79c5da | note | VERIFICATION ACTIVITY: Surveyor
2330f403-06ea-5fb6-8ede-6298676e1c39 | note | METHODS OR REFERENCE: Surveyor
250fd8c7-ef87-546c-9943-8f9d3ea6619f | note | FREQUENCY: Everysite
e960ebe9-eb16-56b7-9a6b-a59a97db4360 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
037865a9-15a3-5e35-89c5-de4b78e26150 | note | ○ Alternatively like for like
9f19f588-c2e8-51db-92bb-20012c3a0285 | note | HOLD POINT: Mandatory HOLD POINT -
a5b9903d-0e58-5d44-b0e7-e430a2eac276 | note | RECORDS: Survey Receipt
8b405112-b49b-5599-9547-27c70b433dab | note | ONSITE RESPONSIBILITY: Site Engineer
1d4f3842-5b42-43f4-95bf-e0c2c11d6c96 | signoff | AUTHORITY HOLDPOINT
213f7700-6e7d-4a10-9cf9-d077eb774203 | section | Materials
0ac92825-17aa-4437-8199-032ee7f02c1f | checkpoint | 2 - Signs/Belisha Disk
57969f19-210a-534d-9756-e82455ca4018 | note | VERIFICATION ACTIVITY: QA FORM
c136f187-267f-5b2b-8ff3-7ac1cb8ea51e | note | METHODS OR REFERENCE: TDM Technical Standards
c2ba956b-ea6e-5976-b171-e552220924fd | note | FREQUENCY: Every site
4cdc940b-6999-5fd5-b3be-4845b3e099ca | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
46484195-a212-5f31-b75d-5c9d62bee26e | note | HOLD POINT: Inprocess Inspection
0d72c3fa-7a46-589a-b627-ac06d170c090 | note | RECORDS: Dockets/Photos
f9af39f2-d796-5677-85a9-43adfdd10739 | note | ONSITE RESPONSIBILITY: Site Engineer
80fc445e-bba1-40c4-8096-369c2c3869d6 | checkpoint | 3 - Pole, Impact recovery post and Ground Socket
bd9061ab-a2eb-53e3-9bfb-447af560b686 | note | VERIFICATION ACTIVITY: QA FORM
6e6f3ea5-974f-5bf4-8bdd-1e2d30469548 | note | METHODS OR REFERENCE: TDM Technical Standards
24761aca-fca5-5cfd-bce6-5e38d95ae4cd | note | FREQUENCY: Every site
8605a611-9f45-5837-88d3-7d67e2eff77b | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
5cf54de5-29b3-59d8-80e5-40a16ba800a7 | note | HOLD POINT: Inprocess Inspection
9667ccea-6d09-5f04-a055-0521d358b6d3 | note | RECORDS: Dockets/Photos
21e40787-f887-5752-815a-f9eeb0cfda09 | note | ONSITE RESPONSIBILITY: Site Engineer
e2f9c6cb-a1f4-43e7-aa95-4474adfdc80d | section | Construction
30d5437c-d561-454e-a961-7c0d03c1ce6a | checkpoint | 4a - Ground Socket
46efce13-f7da-58f9-bcb2-cc412d500b6f | note | VERIFICATION ACTIVITY: QA FORM
01106581-5686-527a-96b5-a095d30eb8a1 | note | METHODS OR REFERENCE: TDM Technical Standards
95efef4c-90a9-5378-935f-ba4f46bc7f13 | note | FREQUENCY: Each Socket
cdcbd42c-9186-550c-b67b-62aa62f07c74 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
c052e462-e50d-5388-99f1-cc3420dbb32d | note | HOLD POINT: Inprocess Inspection
c5b0ec42-ee7f-5e4e-9330-91184da7d9fd | note | RECORDS: Dockets/Photos with tape measurement
846d0deb-522b-500d-9724-5d214acf0663 | note | ONSITE RESPONSIBILITY: Site Engineer
5d5c4cc4-7c6d-467d-a3ae-c765e8e57efa | checkpoint | 4b - Pole and Impact recovery post
fa1b768b-9cda-599a-b422-14e837a4ca4d | note | VERIFICATION ACTIVITY: QA FORM
0220ae96-2597-547d-b0d4-534c3805f75a | note | METHODS OR REFERENCE: TDM Technical Standards
129b66b8-74a1-5771-abc9-4f21ea6eb3ec | note | FREQUENCY: Each Post or pole
70dc5206-b5a8-59a9-9531-1e94fdf4f26e | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation.
af602f4a-4b0e-52b0-8a0c-1bce7ed7d04d | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
9863979e-3551-5a15-ae0a-dde706dcaf9e | note | HOLD POINT: Inprocess Inspection
d7f6a1a1-0cdc-54a6-b9a6-4feb6d002219 | note | RECORDS: Dockets/Photos
6eff796f-28d7-5681-8235-4db30dd1d8b6 | note | ONSITE RESPONSIBILITY: Site Engineer
96575209-03af-49d4-8082-b66c20ead8e7 | checkpoint | 5 - Signs/Belisha Disk
2d191207-336f-5fb0-b52e-c48a7bc006c5 | note | VERIFICATION ACTIVITY: QA FORM
09fa0f67-65f6-5066-880b-d1071811ead6 | note | METHODS OR REFERENCE: TDM Technical Standards
cbe9fe71-201b-50d9-a26d-1ca1b5a8bc47 | note | FREQUENCY: Each Sign
418a06ef-eef6-5959-866f-0fca37ed2b03 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
5597b938-6dcc-518e-825d-c3b6d299dbad | note | HOLD POINT: Inprocess Inspection
a286dc82-760e-5cd6-9599-84c87db02a93 | note | RECORDS: Dockets/Photos
5abb3b04-cbff-5dc8-8b80-d91eb9f30ef7 | note | ONSITE RESPONSIBILITY: Site Engineer
a5e08353-b817-4499-86c1-f00c132a0b18 | section | Asbuilts
69d864aa-91a4-4264-931c-9c0e2f1b7615 | checkpoint | 6 - As built information
475a6fd5-ebbe-55b5-aeb3-ef6715157691 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
063d002b-fc30-553c-8a0a-8effd3ba03f9 | note | METHODS OR REFERENCE:
a7282cae-92f2-51ff-9f03-64de8c2373c2 | note | FREQUENCY: Every Site
6c5f4c4f-42be-59bc-ad4f-3b8d38b4ec33 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
489f35a4-ff26-5857-b0ac-395f9dd0eb7d | note | HOLD POINT: In Process Inspection
c7f66028-db22-5e20-b602-50aaefb332e1 | note | RECORDS: Asbuilt records
f0d7feba-961b-5885-a595-5c647c5ab46f | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
5ff9ad39-0bed-4b93-94f7-09387a132576 | section | ITP APPROVAL
dd115f9f-10ef-49e9-ae71-acf989826257 | checkpoint | ITP Approval
07034d50-f2a8-5131-8014-922305b702cb | textbox | Prepared By:
4bf885b1-31bf-5dc5-806e-1d98b89a28a7 | textbox | Approving Delegate:
d2aa9bee-fe3f-4612-b22e-f7f823fa3f9c | checklist | ITP - Albany Bus Layovers - Stormwater Drainage | itp | ITP - Stormwater Drainage | 1610c966-74b9-46c7-b37a-7718d16decc6
30d60d04-b362-4f1e-a395-76135b9fdb89 | section | Design
3f5e28f4-ec7c-4a4d-afaf-941270d22152 | checkpoint | 1 - Design
339a2fab-1903-5085-a3ae-d217a146fd77 | note | VERIFICATION ACTIVITY: Survey Setout
ff1893ad-d24d-5e53-8379-44742e7c86b3 | note | METHODS OR REFERENCE: Issued for Construction Drawings
b6f2d6f1-cb84-511d-82f5-b2d11a0799bf | note | FREQUENCY: Each site
6e4f6050-953e-5d27-ad8e-f4c9cf0c65e7 | note | ACCEPTANCE CRITERIA: Setout Pipe Alignment and catchpit locations and with inlet & outlet points and inverts as required to construct to design
eaf7adff-912f-5e87-862d-f57e7282ff09 | note | HOLD POINT: Inprocess Inspection
f580b97d-b641-5f42-8839-917b3296ec93 | note | RECORDS: IFC Drawings
20351792-62ef-59b6-ae39-514328be0cbf | note | ONSITE RESPONSIBILITY: Site Engineer
4bb63688-0f83-4ba6-8f83-33afcab63769 | section | Material Compliance
e19fda3f-93b1-4702-a9ed-6b899f47447c | checkpoint | 2 - Material Compliance - Pipe
5a7ad36c-9a42-5535-bee1-ef876f4db8b1 | note | VERIFICATION ACTIVITY: Visual Inspection
6680955e-ea4a-5ca0-b427-8c90bcf6cdeb | note | METHODS OR REFERENCE: Drawings and Dockets
04fb1fca-a235-59e2-b30f-fec30b8f016b | note | FREQUENCY: Prior to construction
e857a23f-48b7-5243-a4d4-668851073c01 | note | ACCEPTANCE CRITERIA: Pipe shall be
ae218cfe-f670-5a05-bc86-87d495493c2a | note | Check for freshly formed pipes and return if required
41107d13-bc72-552c-bb46-921e564eed5e | note | 1) DN225 Class 3 RCRRJ pipes AS/NZS 4058
362170a7-51c4-5664-a794-4206d2c62dbb | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
a57bb8d5-c573-5b86-97d5-0dcd3ec5a793 | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
c8f5e93c-d0bd-5c7f-9c4c-1d918d5b7935 | note | 4) Prefabricated concrete Manhole/cesspit shall be in accordance with TDM Standards/SWCOP
4685b60c-2cdb-51d9-9e54-039cfcc57a9f | note | HOLD POINT: Inprocess Inspection
16122487-0347-5bbf-8ce4-8086e8795366 | note | RECORDS: Photos/Dockets
b7cbfc85-4123-5ef0-be61-b7416a7f2954 | note | ONSITE RESPONSIBILITY: Site Engineer
ddf43186-dc1a-4485-92ba-ae6fd3b83a59 | checkpoint | 3 - Subsoil Pipes
8b4f266d-0100-5b3c-9329-999654660aa1 | note | VERIFICATION ACTIVITY: Visual Inspection
08ec19ad-f642-5a22-b337-5ad8a19352e9 | note | METHODS OR REFERENCE: TDM Technical Standards - RD0010
7e027e12-6417-51f6-9602-0f9b73b20145 | note | FREQUENCY: Prior to construction
fdd827aa-2bfe-5742-a9b4-4dd886128325 | note | ACCEPTANCE CRITERIA: Subsoil pipe should have punched holes and filtersok
60dfd97b-4f0f-5a39-9162-93e3f4352fb4 | note | ○ Depth to be 375mm from subgrade level to invert of pipe or as possible to achieve invert of subsoil pipe to be above soffit level of outlet pipe in the downsteam cesspit.
13d2cb43-10f6-5298-bdac-6c43846d0002 | note | ○ 50mm bedding.
1cb507bc-f10b-5f51-83f8-80e373f5012b | note | ○ Backfilled with scoria 30/10 or similar approved product.
86ca8fa3-10ba-5ff3-aac9-05c018b91c77 | note | HOLD POINT: Inprocess Inspection
f1d829c3-0576-502c-94dc-a9872e299c72 | note | RECORDS: Photos/Dockets
6f8cee4d-a70e-57b7-8c28-173feb0932e6 | note | ONSITE RESPONSIBILITY: Site Engineer
6b3effd8-bc7d-4f18-acc4-99dac8f7715c | checkpoint | 4 - Catchpit/manhole
81f64105-18da-5541-8fe0-f5657f1c052c | note | VERIFICATION ACTIVITY: Visual Inspection
56b63f22-2387-5257-9bc1-b8412785cfe1 | note | METHODS OR REFERENCE: TDM Technical Standards - RD0025, RD0026, RD0027 and SWCoP - drawing SW05 revision 2
a86b8abf-16c0-5d75-8b2b-9b59840b5de5 | note | FREQUENCY: Prior to construction
df42a39b-473f-5f77-8c1e-fbf43f655176 | note | ACCEPTANCE CRITERIA: No Damage or cracks- Material should compliance with TDM standard
6eee7cce-af52-5def-b8dc-2c30dffe3a0c | note | HOLD POINT: Inprocess Inspection
3fd0ca9d-22d4-55a6-b5ed-d58247de7ff9 | note | RECORDS: Photos/Dockets
9b75c605-ba83-5bae-a8ba-12b055f74db6 | note | ONSITE RESPONSIBILITY: Site Engineer
fc442ef1-b076-429d-8ac2-5c1b2b5c98e2 | checkpoint | 5 - Kassel kerb drainage pit/grate
2b3f51ba-3af5-5bb8-8bbc-ffb90310d0f2 | note | VERIFICATION ACTIVITY: Visual Inspection
e171f2b1-a2f1-5e8b-8dcb-2f0752c2b6a9 | note | METHODS OR REFERENCE: as per supplier (busck) guidelines
44f6f24c-1829-5a18-8ac5-662646696309 | note | FREQUENCY: Prior to construction
fbcdeded-7b55-51b3-86be-a7525f3f6a4e | note | ACCEPTANCE CRITERIA: No Damage or cracks- Material should compliance with TDM standard
fdbd0e72-5054-58e7-8344-6f3265903e73 | note | HOLD POINT: Inprocess Inspection
4a35b42e-15da-556c-a7c6-84287f14923b | note | RECORDS: Photos/Dockets
69f18f77-d273-55d7-bcca-7e124947444b | note | ONSITE RESPONSIBILITY: Site Engineer
e341dd19-ffb9-455d-a75c-4a32ad9d4de0 | section | Construction
8f0c0f99-5c05-4cd2-8097-5b14583fa4df | checkpoint | 6 - Construction
39f0043e-585a-5e69-a94f-1abcc74e72f9 | note | VERIFICATION ACTIVITY: Trench Profile - Width
17d2c58c-8cb5-5110-b1af-17aada7b2ccb | note | METHODS OR REFERENCE: SWCOP
b15ac814-9183-5dfc-8d45-7b82284a5a44 | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
1f7d764d-000e-574a-997e-afce9dea5675 | note | ACCEPTANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing. provide a minimum of 100mm bedding below each pipe
1c955666-1727-5b1e-b144-75877c25be77 | note | HOLD POINT: Inprocess Inspection
bf62c200-0c48-5bed-a54e-ad8fe71bf7b0 | note | RECORDS: Visual Inspection, Measurement
7c4ac7fd-6411-5540-9598-e6a7e7b0bdb8 | note | ONSITE RESPONSIBILITY: Site Engineer
dbd01592-5945-4d05-98ad-1fd3d4fc078c | checkpoint | 7 - Construction
67695f89-5cc6-5495-807b-2bcf1ba4db4a | note | VERIFICATION ACTIVITY: Bedding for Concrete Pipe Laying & Manhole & Cesspit
cf4e331c-b679-5b32-bc62-3c815a701f24 | note | METHODS OR REFERENCE: Placing and compaction of Bedding Material.
004b9848-537c-5c64-aa7d-eca2bdf35766 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
9c4dc9d4-efe1-5327-884d-23ac74da9492 | note | ACCEPTANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material
281bc1fd-bce8-5e8c-b609-7a39597bcd17 | note | ○ CIV>25
f4f9c348-ca90-5c0a-82d0-f411568b428b | note | ○ TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - drawing SW05 revision 2, to be followed
62ecc103-3cb8-50e3-8b1f-35dd3d7532a7 | note | HOLD POINT: Inprocess Inspection
e2bfd9cc-7086-546b-9b38-b3da31928dec | note | RECORDS: Visual Inspection, Photos showing depths of trench and trench reinstatement, Clegg Sheet
72cb16cb-6899-56a4-bc11-3e3cb766bcf2 | note | ONSITE RESPONSIBILITY: Site Engineer
a7231374-8df2-46da-8535-3a2fca90ae90 | checkpoint | 8 - Construction
9ed7622c-833d-5a71-80ee-d8d7663fa4e4 | note | VERIFICATION ACTIVITY: Trench Backfill - Placing & Compacting
d63f55b5-7c29-58c4-9649-1e924e277c10 | note | METHODS OR REFERENCE: Placing and compacting of Trench Backfill Material
b71a2435-3118-52a3-ac89-ba0d3b9a02f0 | note | FREQUENCY: Throughout Trench Backfilling operation.
a133eeb6-954c-50c5-8b54-839d42129000 | note | ACCEPTANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
f7211876-596b-5c7a-955f-f13abdc7ee79 | note | ○ TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - drawing SW05 revision 2, to be followed
78524974-1857-5291-83b8-95a5f01551ac | note | HOLD POINT: Inprocess Inspection
239bf6eb-4c91-55e2-846e-77feac6a867d | note | RECORDS: Visual Inspection
2f33592e-0363-532f-865f-2233c758c78e | note | ONSITE RESPONSIBILITY: Site Engineer
492b9074-26b1-4a37-8bbc-14f70ac1e904 | checkpoint | 9 - Construction
db10d9b7-740a-5a00-9a37-7ed8d660f2f7 | note | VERIFICATION ACTIVITY: Subsoil
17c6417a-8d0d-5847-854f-65791d20dcd6 | note | METHODS OR REFERENCE: Trench, install, bedding and backfill
89f9265f-b21b-5e5b-b1e0-558b7883255d | note | ○ TDM Technical Standard RD0010
986d4234-cf7b-5326-804a-d2adb2388d57 | note | FREQUENCY: Throughout Trench Backfilling operation.
c1dc9ff1-acf4-56fd-8d3e-3276ce3f7b8e | note | ACCEPTANCE CRITERIA: Depth to be 375mm from subgrade level to invert of pipe or as possible to achieve invert of subsoil pipe to be above soffit level of outlet pipe in the downsteam cesspit.
c2990038-73fc-500c-9127-315f5738c5c7 | note | ○ 50mm bedding.
6e98157d-3616-5ef4-af61-c3f16a87ed1b | note | ○ Backfilled with scoria 30/10 or similar approved product.
f30a567a-b52e-5eb4-9c72-af824b4f52ad | note | HOLD POINT: Inprocess Inspection
794a61ff-937c-541f-9879-4d6e0dc8ac0e | note | RECORDS: Visual Inspection, Photos showing depths of trench and trench reinstatement
1bfe9e2c-c329-5a9d-9174-2f5142cf6f5d | note | ONSITE RESPONSIBILITY: Site Engineer
bb131f8e-7f4f-437f-9258-a5661812dd1e | section | Asbuilts
3b613f14-2838-4312-97e7-d121b116a346 | checkpoint | 10 - As built information
f3768b0b-d74e-551f-9bd6-9e86d4b5b474 | note | VERIFICATION ACTIVITY: Drawings
5398d291-7d81-5683-8bc5-07758d376a20 | note | METHODS OR REFERENCE:
b130e720-c1bb-5ca2-850f-76fbb1985ec7 | note | FREQUENCY: Every Site
433f04f7-2c71-5376-b4a6-7a019ddb5a64 | note | ACCEPTANCE CRITERIA: As built drawings
26d52b16-d6db-51bf-aef3-2231dc49484c | note | HOLD POINT: In Process Inspection
64476653-8f2c-5242-aca5-79905edb310b | note | RECORDS: Asbuilt records
d344e3d2-f7a1-5352-82b0-b353b877469e | note | ONSITE RESPONSIBILITY: Site Engineer & PM
88214c0f-3301-47c3-b463-5c38ee197b5f | checkpoint | 11 - RAMM DATA
cd3fc561-d8f6-58e3-9f5b-eea1493c86ba | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
da7194a8-4d75-5b3a-b49c-2609b594ea9d | note | METHODS OR REFERENCE:
96fa7467-2d67-5f51-a479-87f3acd3c8d2 | note | FREQUENCY: Every Site
76e773d4-a088-5d76-82a7-689962ccb408 | note | ACCEPTANCE CRITERIA: RAMM SHEET
c40e74f6-e764-503e-8e63-d6674686eda1 | note | HOLD POINT: In Process Inspection
8a980dd4-9f36-5025-b724-70858008fc16 | note | RECORDS: RAMM Sheet
becf8c37-93e8-5a7b-a76f-0fcd1ae736f2 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
2bbe66ef-dd5c-472e-b3ed-d73656f30f30 | section | ITP APPROVAL
1f74782a-f5c6-45e7-8605-d1f402371a9d | checkpoint | ITP Approval
09ba4478-3627-5ef3-9fc1-8c66c4e58276 | note | Prepared By: Ajithkumar Ayyanar
d5509460-e09d-5cc5-92de-01a8a64f7023 | note | Approving Delegate: Denny Jeong
a4593703-3d72-4976-a62c-d8e9f341a3a9 | checklist | ITP - Opaheke/Chapel St - Enabling Works - Footpath, Kerb and channel, Vehicle Crossing, Pram Crossing | itp | ITP - Enabling Works - Footpath, Kerb and channel, Vehicle Crossing, Pram Crossing | 3ca0d916-49c2-4182-9f45-96be42f44738
1b19d9ca-fb5b-4a39-9060-26ff960c596f | section | Site Set Out
c103bac9-f5fb-4ad6-8eff-68e0229a1eb7 | checkpoint | 1 - Site Set out
c6e8eaaf-3ca9-5e3b-87af-c339078c6b39 | note | VERIFICATION ACTIVITY: Surveyor
ddc1facd-d9d3-57b6-862a-9b8b3e727d2c | note | METHODS OR REFERENCE: Surveyor
3c471a7f-c27c-56c0-b3c1-82b13a37727e | note | FREQUENCY: Everysite
e946840a-f176-57be-ba3b-e543ea35ce43 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
e1e8ddf9-1e0c-5429-8c96-953b0be51120 | note | HOLD POINT: Mandatory HOLD POINT
4bb8b62e-a8e4-5246-9c84-f6ede359e2ad | note | RECORDS: Onsite records/photos
6adf175e-a0e8-5a0c-8f01-525cc73089d5 | note | ONSITE RESPONSIBILITY: Site Engineer
c9ec67bb-60ea-45e0-a5c5-d0b44b672168 | signoff | AUTHORITY HOLDPOINT
d17bbba8-a292-4f97-91f7-297b203a9462 | section | Kerb & Channel
4d0c2c1a-8ed4-484e-974a-2955fad56fba | checkpoint | 2 - Kerb & Channel
0befd496-6802-5867-9bf6-cc0f502debd0 | note | VERIFICATION ACTIVITY: QA Documentation
0c00742e-2f63-5b0d-8fe0-73ee394af441 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
13a8c6ce-6be8-5a7d-aeaf-e1e1d97c27f1 | note | FREQUENCY: Everysite
201bd9f9-7f2e-58f8-9b0a-2830ddcd66ba | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (Subgrade CBR>5). Concrete 20MPa @28 Days
c7e975f1-686d-505f-b536-c1573d27f6ae | note | HOLD POINT: Inprocess Inspection
a3ada793-ff00-57ae-b144-4c48e6f78989 | note | RECORDS: Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
e09bad55-237f-5b78-9e57-ab516be0433f | note | ONSITE RESPONSIBILITY: Site Engineer
49f2f93d-6a45-4966-97e8-97a4be98e4ce | checkpoint | 3 - Channel Level
ecf793c7-d67c-5890-b28d-9da32c94fb05 | note | VERIFICATION ACTIVITY: Visual inspection
c033919e-2a9a-59bd-8a6e-7ae39098a781 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
16f55d8d-0b41-5803-b1ed-fc1e4f806c1d | note | FREQUENCY: Everysite
085bd8c4-7623-5f22-8662-ec3a5651146f | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
a94fb104-fc8c-5810-afd2-0f3381c97e68 | note | HOLD POINT: Inprocess Inspection
2c633ddb-8014-5768-8509-618c4862137a | note | RECORDS: Visual inspection
8f55d3ad-bd91-53a2-a81c-99c1dc6a770a | note | ONSITE RESPONSIBILITY: Site Engineer
a8e6dca2-8984-442f-aec7-54bc41689308 | section | Footpath
4def0ba7-4020-4374-b3a9-99f5067851bc | checkpoint | 4 - Concrete Footpaths
dedb502b-6af2-532e-9a13-94a6c6511367 | note | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
9abe12cb-b45a-5cfb-90a9-67efaab28460 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
8f3c81c3-3426-555d-8f60-a05aeec3bb19 | note | FREQUENCY: 10m Intervals
d81c3efc-2e21-5314-9fc0-7b44f21a3bae | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
b418a661-7b37-5212-93a0-10d736a41d0e | note | ○ Basecourse - 100mm min. thickness
ad72c598-cafb-5536-b3ef-c1e59feecc2f | note | ○ Clegg CIV > 12
ac17fa4f-191e-5a6f-b6cb-96810a4e2261 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
9a5082e1-b725-5ab5-a905-093f0819a968 | note | HOLD POINT: Mandatory HOLD POINT
00f26ed4-04ff-5d63-b6ae-5cfb00fffded | note | RECORDS: Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
98f221dc-5ab2-5ff1-bee4-29a6129cf256 | note | ONSITE RESPONSIBILITY: Site Engineer
1d8a185f-2258-4566-82d7-6400b23ca480 | signoff | AUTHORITY HOLDPOINT
79364353-0e06-48fb-a089-7a13de0b84bd | checkpoint | 5 - Fall Gradients
562005b9-25a2-5c90-8b2e-2b22101139f0 | note | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
072c415c-5ba1-56d2-8b65-37bef15d8c9a | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
c200662c-ad99-52ed-9db9-4ee4cf5fb954 | note | FREQUENCY: Everysite
28d5ef44-8ff9-554b-b05e-33438e6cc3a5 | note | ACCEPTANCE CRITERIA: Cross falll = 2% preferred (Min 1% and Max 3%)
1418bb46-4a17-5c7d-b84f-efedd3091529 | note | HOLD POINT: Mandatory HOLD POINT
86ac60d5-edff-527d-af13-bbda93afa70a | note | RECORDS: Photos of smart level
4bd7a05a-4636-53a1-b078-140da838f118 | note | ONSITE RESPONSIBILITY: Site Engineer
96597b79-0656-4a15-8d07-c8e389c20d86 | signoff | AUTHORITY HOLDPOINT
aa02e1b7-4f83-4e22-8c27-7766a9b88063 | section | Pram Crossing
c2b5e08d-2a82-47f9-a611-1cdb280b870c | checkpoint | 6 - Tactiles (1)
87596c5c-c60b-5309-b918-f03d78c8dede | note | VERIFICATION ACTIVITY: QA Documentation / Visual
6e02cc15-dc86-50f8-a36c-9b9861967eca | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
9ce1c7e8-2659-5494-b069-9c452d547ea5 | note | FREQUENCY: Every PX
32654890-0ede-5a05-8736-e1b069dd194b | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with MSQA
3c81d089-e7dc-52ad-a0d5-138e8abe3e9e | note | ○ Warning and Directional TGSI tiles should have 100mm concrete haunching underneath
b894bc11-af96-5c10-97d2-986616c0e264 | note | HOLD POINT: Inprocess Inspection
e4e3b9cf-ba37-5f81-ba0f-5f6a09b233b5 | note | RECORDS: Photos, Concrete Plant Docket
8cd7dd1d-3675-5e0f-b519-d7d6d35e08a6 | note | ONSITE RESPONSIBILITY: Site Engineer
34a88106-c96b-41d3-97d4-fb003a77f3ce | checkpoint | 6 - Tactiles (2)
6e43e4a0-1f25-56b6-a9f5-2418d305b4b5 | note | VERIFICATION ACTIVITY: QA Documentation / Visual
7a0cc787-d1d0-5b88-b950-3595131c7763 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
e5ba5bab-c201-5b5a-ab56-4fe14a763e9e | note | FREQUENCY: Every PX
aae686e7-de98-5598-b331-33b09a1d7ee0 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back minimum 300mm from the face of the kerb or lane.
50ae4549-44bf-537b-bf08-6e1e1667c86c | note | HOLD POINT: Inprocess Inspection
1ecdd039-eb00-5314-9ee2-7c2952189953 | note | RECORDS: Photos
ed67000c-4517-54fe-a30e-2c6658cfb66c | note | ONSITE RESPONSIBILITY: Site Engineer
b227accf-156c-492d-bc67-34e55648c791 | checkpoint | 6 - Tactiles (3)
ef9a2cbb-c63e-5225-87d8-e8da30e3c287 | note | VERIFICATION ACTIVITY: QA Documentation / Visual
0fdc2680-e410-5d09-a71a-9843ad574727 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
464aa7f7-33d5-5a19-b6ac-6126fea1b3c8 | note | FREQUENCY: Every PX
829b2353-e294-52d0-ab61-46090bc871b1 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete paver slab type B in footpath and pedestrian crossing.Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
ac25912c-8270-548f-a51a-f9e3a08b292d | note | HOLD POINT: Inprocess Inspection
99e1efc9-a6c1-594f-be87-9156107495d8 | note | RECORDS: Materials Dockets
b13fb67a-64d2-558b-bad7-f1fe6438972f | note | ONSITE RESPONSIBILITY: Site Engineer
ada0105e-3e85-4d29-9a41-de4ef9d219ec | checkpoint | 7 - Pram Crossing
3124b0b8-5230-5031-ac37-c46716febdd2 | note | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
23b71d65-2143-5525-b5d4-9a1c3156c6d4 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
3423b8b6-1952-5d35-8e45-91ff10575dbf | note | FREQUENCY: Each Crossing
c03c09c1-7dc0-54a2-8837-d59ce00472fc | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
af4cb0e5-b13a-5764-95c9-b7138a431348 | note | ○ Tactiles Directional & warning - 60mm thick; 600mm flares;width as per design;
6b7fe103-8558-54f9-85f0-7cba4745d557 | note | ○ Slope no greater than 1:12 where practicably possible
d8eaca0c-9e3f-5587-9c56-0e68ba0f5b3f | note | ○ Clegg CIV > 12
0df07055-7503-5e8d-8932-1907266a81cb | note | ○ 20MPA concrete
6941e891-d30e-564a-a2ab-88e72a45d61c | note | HOLD POINT: Mandatory HOLD POINT
ba7f4424-13e0-5939-93db-91850b88cd12 | note | RECORDS: Photos, Photos of smart level, Clegg Test Sheet, Concrete Plant Docket
eedaeb98-da4c-5b21-9b9b-2c02f43a6d7c | note | ONSITE RESPONSIBILITY: Site Engineer
aa34b86e-33fc-450f-a56f-bf9cf84797e4 | signoff | AUTHORITY HOLDPOINT
0ac32929-0d69-4adc-be6e-8d828ac5943a | section | Vehicle Crossing
33370f90-e411-4aa7-92f2-fe790c034b8b | checkpoint | 8 - Vehicle Crossing
5dd45b00-f54b-55b4-b365-0841c9b4f409 | note | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
f5b00bde-9d2b-57cb-a7c9-69361de418d7 | note | METHODS OR REFERENCE: TDM Technical Standards - VX0103
c2a1dbb4-c11b-5b84-be3a-c66de25b773c | note | FREQUENCY: Each VX
f4db4c14-8d1d-5f60-b90a-5a724691ea53 | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
5419b3e1-1f05-503c-bc6f-fb6ad7d1749f | note | ○ Base course - 100mm min. thickness GAP40
c6e259e9-f186-51e3-b3d0-39007d73e29d | note | ○ Clegg CIV > 12
43c7bc4c-2d45-5295-974a-ddd4e210bc85 | note | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide
2c1332f3-5a17-55f9-af57-79951d18a0b9 | note | ○ Broom Finish
0dca2f45-acd4-5304-8735-4b285e01e85b | note | ○ Vehicle crossing 2%-3% for footpath area
e333e1c5-e664-5555-a9ac-94d085fcaf92 | note | ○ Vehicle Crossing Ramp 900mm wide at max 15% with total 40mm lip (20mm chamfer, 20mm vertical) above channel invert.
37a2ccc5-0b63-5029-86bc-5144b8a565ba | note | ○ Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
8cf6d3b6-b09e-58b4-adc7-6fed0f67f2b0 | note | HOLD POINT: Mandatory HOLD POINT
d257421d-a9a4-5fcf-aaf5-1931b43b70be | note | RECORDS: Photos, Photos of smart level, Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
1b733d9c-3d38-5701-9e3d-1cfe9640a061 | note | ONSITE RESPONSIBILITY: Site Engineer
844a1567-538c-4a63-8767-a4ed375d081b | signoff | AUTHORITY HOLDPOINT
1e21f3b8-2c47-4961-908e-f2c560fe38a3 | section | Refuge Island centre footpath
7315d079-64aa-4c76-8844-6f4b8ee37209 | checkpoint | 9 - Refuge Island centre footpath
d1f7d365-bd10-5980-9830-c2c10ffb61af | note | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
fb559d37-37a4-594c-a35f-824eba1754e9 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
913cdae9-676e-5127-9ec4-a591fb07993d | note | FREQUENCY: Each location
98063e82-9480-56db-9c18-6871ddb5bf40 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
cc41bee2-a785-5265-8564-eae7c731192a | note | ○ Basecourse - 100mm min. thickness
e056ea3c-5e7d-5487-8e07-717e3ef1e25a | note | ○ Clegg CIV > 12
910b8fa0-0508-5409-b04b-cd1ff38c0f8a | note | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
3ab003c9-ec60-5c58-9283-dcd1e24a1bf4 | note | HOLD POINT: Mandatory HOLD POINT
94efa142-7e78-5365-af07-c845f49d1e38 | note | RECORDS: Photos, Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
438c7825-b316-52ca-abc8-9290f86b7657 | note | ONSITE RESPONSIBILITY: Site Engineer
93d7e088-57a6-4090-bf5a-432a53ab17d6 | signoff | AUTHORITY HOLDPOINT
e12f89ae-4a87-4603-8748-f806f20700db | checkpoint | 10 - Fall Gradients
f04beac7-15a1-5532-b091-e497b9864376 | note | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
2aec99a5-590b-59f0-a401-8a58523f73b0 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
5a411b3e-9dfc-5cd5-9ab0-5a5e0f612a09 | note | FREQUENCY: Everysite
b3645657-f431-58bb-b79b-c082bd492c2e | note | ACCEPTANCE CRITERIA: Fall Gradients to follow shape of the final asphalt surfacing
59aefa8f-e55f-5aed-a624-847a89bf9b55 | note | HOLD POINT: Mandatory HOLD POINT
ec97b16a-a52d-56a5-a287-a403ebd21576 | note | RECORDS: Visual inspection
6129fadc-6915-59e0-a7ef-83984a65175d | note | ONSITE RESPONSIBILITY: Site Engineer
1006badd-2719-49e2-b929-78c940231977 | signoff | AUTHORITY HOLDPOINT
ab1fe08d-b271-4db6-8a9c-78edecd86d51 | section | Grass Berm
fdd30048-c094-415d-84c0-161b476eaecb | checkpoint | 11 - Grass Berms
0611eb3e-e08a-547f-b711-f51696155a03 | note | VERIFICATION ACTIVITY: Visual
e186b50b-2688-53a5-9f5b-6733e157e8f7 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
99ebe0b1-072e-564d-9f37-5738d802386b | note | FREQUENCY: 10m Intervals
7f4eeca2-c1a6-58dd-a776-643bffd2b407 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
7b375a4f-9324-510e-8fa3-69c4557e688f | note | HOLD POINT: Inprocess Inspection
34233070-6acd-5882-bd7d-beb11762f00f | note | RECORDS: Photos
2dd1c4f6-c3cd-5143-bcfd-455c41a0e95d | note | ONSITE RESPONSIBILITY: Site Engineer
292a1ae3-38e2-473a-a51f-c4d20c6b1618 | section | Asbuilts
2a303bd0-be5a-4c94-b14f-e32012a54bf6 | checkpoint | 12 - As built information
cacf241a-9d9f-5937-8ca3-272f565882a1 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
31981a91-0adf-56a4-801f-80a62cb3e4fc | note | METHODS OR REFERENCE:
21de923d-dcc0-53ee-8599-64b09f145c96 | note | FREQUENCY: Every Site
c9fc4e17-3fa1-5d27-a939-0042da19d141 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
50cd8e94-dd10-50dc-987b-de5bc865f7c7 | note | HOLD POINT: In Process Inspection
f6687268-85a3-5db7-a420-779e37173633 | note | RECORDS: Asbuilt records
2095f6ea-ab34-5d02-915a-09f8aa10aa19 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
c6b19bdd-d837-4ba9-97f6-960c0c086a1c | checkpoint | 13 - RAMM DATA
58df1b88-6cca-5c01-b669-c4c0412d1fc9 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
67e6ccf3-b062-5456-9e70-d8c560d757c2 | note | METHODS OR REFERENCE:
0e0ac0b1-6c0a-5dcc-a81c-f9162aae17e9 | note | FREQUENCY: Every Site
87193caa-d0cf-5483-8c38-72c0100c9c55 | note | ACCEPTANCE CRITERIA: RAMM SHEET
4b501949-b748-55c9-912d-de33e2c8a913 | note | HOLD POINT: In Process Inspection
21e81bbb-5caf-554a-b08b-ffbce94213ec | note | RECORDS: RAMM Sheet
fef87cec-8b18-5093-88c9-9c5cf700db75 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
cbd778dd-9b10-402d-8919-0163b0912da1 | section | APPROVALS
c4ee4ae2-8d59-4de7-ad86-be33bc5a9537 | checkpoint | ITP Approval
b2898e8b-499b-50b5-8997-d9d8129ba76e | note | Prepared By: Ajithkumar Ayyanar
3c2b721e-798e-5a75-8f11-656342fcafd3 | textbox | Approving Delegate:
56ea2838-7543-43fb-bea1-3a010e5d547f | checklist | ITP - Opaheke/Chapel St - Pavement | itp | ITP - Pavement | c6eea149-6191-403d-b8c7-859a8ecae1f7
4c386516-1ffc-4b9f-9f2e-00e4518621e1 | section | Excavation/Milling - Widening Area, Structural AC on Concrete and Structural AC
e301b461-5146-4452-8597-8941f6c7f306 | checkpoint | 1 - Identification and location of shallow services
723df95c-9465-587f-b41f-5220cf51f313 | note | VERIFICATION ACTIVITY: Measure depth of cover to utility services
43872b18-6180-5bc0-abaa-3f288ad26966 | note | METHODS OR REFERENCE: Trained contractor staff
ed50e44e-2c21-5778-8500-0698dfc43a17 | note | FREQUENCY: Two measures per service (each side of the road)
d39cf145-e6f3-53dd-934f-0d8ace06c373 | note | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage.
53f59251-8cde-5a9e-a193-d30bafaf0003 | note | ○ Otherwise consider relocation or concrete cap
a2a12b20-56f6-5acb-b2b3-0e4131a0d81b | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
c418d6a3-4eb9-5cac-8983-c894368631da | note | RECORDS (Responsibility): Marked up sheet
327c1f68-a501-5063-b0e8-1020fdb1b8b3 | note | ONSITE RESPONSIBILITY: Site Engineer
57e8b720-c659-5a47-be8a-0719b41a3e94 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
554468d2-c153-4328-8d66-7d77b91cd690 | signoff | AUTHORITY HOLDPOINT
6897d4d0-faab-4949-8976-2df99b80b2cc | checkpoint | 2 - Milling / Cut to Waste
6f699f98-f8f3-5acc-8697-7b410a381e43 | note | ○ Type O = 210mm
15f4c108-90ae-5ec7-8238-bc534a09d161 | note | ○ Type C = 305mm
8d8bb8df-8a08-513c-a536-7d2b6e3128f2 | note | ○ Type W = 500mm
472dc03b-ae6d-535f-8b27-5759de0fd8e5 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
51db5e96-6a8a-5391-9ad7-199ee48e4020 | note | METHODS OR REFERENCE: Survey As-built / Stringline
6ad5ad36-b4be-5d87-b942-4d728be8896c | note | FREQUENCY: 10m each lane
f67255ab-9e98-59cf-8047-14beddf3667f | note | ACCEPTANCE CRITERIA: +0 / -20mm to design level
f5b547ff-50be-5866-80eb-f64b85960c04 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
d27ae4c4-ec49-597f-a15b-4b031d6fdec0 | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
48eba30a-9a8c-50aa-9542-2af1014a01e0 | note | ONSITE RESPONSIBILITY: Site Engineer
77562d7a-b7f1-57c9-a499-408b922c7f7f | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
ccc26ccf-995c-49c6-880b-61c5c21d2754 | signoff | AUTHORITY HOLDPOINT
03fbf21e-dc8a-4583-b7a0-44836c7498a5 | checkpoint | 3 - Existing subgrade / subbase
d3dad184-9e0c-5611-8fa6-026e344c52ec | note | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
44aaa779-7b54-5666-bb61-bed26c2155e2 | note | METHODS OR REFERENCE: Visual Inspection
a7d072a0-3d63-5fd6-918d-abfa7f8796fd | note | FREQUENCY: Sitewide
eea687c9-6f11-5121-ad47-20322d9deb60 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
86658320-7794-523b-96aa-4557093dc79c | note | TYPE: Inprocess Inspection
a242c807-b6b4-5055-a553-57546db98b34 | note | RECORDS (Responsibility): Photos
e4a36b09-6fe1-5336-b630-f939d821080b | note | ONSITE RESPONSIBILITY: Site Engineer
2495ec1a-0ba4-5286-8e21-e47920d51f3e | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
d7dfdcfa-939e-4aa6-9f09-4af21bf71d9a | section | Contingency Undercut Areas
42353f3b-0001-48ce-8a4c-a4967751a94d | checkpoint | 4 - Type O = Contingency weak / soft spot
1676e4b2-4aea-5e70-882a-71d6f96bfd12 | note | VERIFICATION ACTIVITY: Benkelman Beam Test
a91533d9-dbce-5a13-bba6-76a66caaaf57 | note | METHODS OR REFERENCE: BB Test on exisitng Subbase
720d478c-914d-589f-bdea-7cc06d442441 | note | FREQUENCY: 10m interval alternative wheelpath
5732a166-e427-5647-ab32-e1fdea68cc48 | note | ACCEPTANCE CRITERIA: If BB Deflection >2.1mm and <3.5mm, Mill Further 70mm & replace with AC20 asphalt
c13ea81e-f492-5b56-a9eb-bcf747bd8d32 | note | ○ If BB Deflection > 3.5mm - Designer to review and advise
6420b65d-fb3b-5802-a8e5-0016661eb109 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
a1415a91-3dad-5fce-9e2c-c92aaff8f2cc | note | RECORDS (Responsibility): BB test results
7e54ec2b-fe97-5c7d-87cd-0dc21cc41d9f | note | ONSITE RESPONSIBILITY: Site Engineer
086f2e13-d5bc-5936-92db-f2258f26045f | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
5e375bfb-432e-4344-9e92-f72eef087061 | signoff | AUTHORITY HOLDPOINT
b39175a7-2603-4a13-94c3-34a5e71cdcf5 | checkpoint | 5 - Type C & W = Contingency weak / soft spot
9518edce-b546-56c5-99e0-042551013531 | note | VERIFICATION ACTIVITY: Scalar Testing
d737bc2e-cf4b-5d13-b825-4953928aecd5 | note | METHODS OR REFERENCE: Scalar Testing on existing subgrade/subbase
fb627b58-d576-5754-a196-4e3c4f48087b | note | FREQUENCY: 5m grid
97306407-b683-5056-9974-1445e4b791b2 | note | ACCEPTANCE CRITERIA: Ensure exposed subgrade CBR ≥ 2.
c4ec1a6c-c710-530b-801a-cc26a497f095 | note | ○ If CBR between 2 and 1 undercut 300mm and replace with woodhill sand wrapped in bidim A29 geotextile
61d9f2a5-2d41-5839-9bed-ecb5e6a806e0 | note | ○ If CBR < 1 - designer to review and advise
2aa26843-8285-517e-84b5-6c96c51c1ad2 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
4a0e53c1-7ef4-54ad-a4f2-742553024ead | note | RECORDS (Responsibility): BB test results
b01515b4-f2ed-5feb-bd15-6a8abb2ef2e3 | note | ONSITE RESPONSIBILITY: Site Engineer
4f0e83dc-3447-58aa-af0d-a5f90457ab72 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
d78ac069-a83b-484f-ad1b-9d2c5fcd7ea4 | signoff | AUTHORITY HOLDPOINT
118a8abe-37b6-4cda-b5fe-75462cfa32a6 | checkpoint | 6 - All Areas Contingency Weak / Soft Spot
4f218f8a-95c0-5499-9c24-2ac8dd90dc62 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
56f73585-8b56-5452-823b-375d3d940d43 | note | METHODS OR REFERENCE: Survey As-built / Stringline
07664b9a-8cba-519d-9a34-6fed8cc5cc5f | note | FREQUENCY: 10m each lane
6e19e7ba-a257-5352-b2fe-9299449b8ae6 | note | ACCEPTANCE CRITERIA: +0 / -20mm
74b41f57-bf4b-500c-8f34-969d4bc05803 | note | ○ No trafficking of the excavated subgrade
6a0d444f-3eb1-5ac0-9103-ff70816f23d1 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
32dfc5be-bf24-5af2-922b-50d7e4cf2f3b | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
a6179ce0-ab79-5133-adad-b7591c4cb8c4 | note | ONSITE RESPONSIBILITY: Site Engineer
a6e33385-c390-5661-8cdb-44d8f417ebcd | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
0ded2eaf-d0e3-4cc8-a5fc-f49d943e5410 | signoff | AUTHORITY HOLDPOINT
c5082a5e-9a1d-4427-b91d-4e8a3d16eb39 | checkpoint | 7 - Existing subgrade / subbase
5afec264-e739-567f-9f3b-79c6d05630d5 | note | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
b7566538-70bf-5b19-9de7-9bb23115555e | note | METHODS OR REFERENCE: Visual Inspection
7dc96005-079b-5fcf-a0cf-cb6f8ecf47ef | note | FREQUENCY: NA
92529617-d9f8-5bbb-a5be-b411381612f0 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
f92486d1-c154-5dcc-af50-8af8965827f9 | note | TYPE: Inprocess Inspection
1c6f7934-44b7-53ed-b874-27cf9e1f021d | note | RECORDS (Responsibility): Photos
a24773b7-53e8-5713-8035-c8e88e34e8cb | note | ONSITE RESPONSIBILITY: Site Engineer
4f84f9a9-7e5b-5ee9-82a4-0c477162ed7b | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
1887d1ef-f9d8-4801-8908-c0bced01ca57 | section | Subbase
3e880e25-89da-48e8-99f6-1e97f7728e90 | checkpoint | 8 - AT AP65 = Pavement Type W
36d240c2-e222-5e36-8416-1f8b3ffd5d1b | note | VERIFICATION ACTIVITY: No non-compliant results
55ba0c0b-8220-5bd8-ae5d-ce4632b07822 | note | METHODS OR REFERENCE: Material test results
227c51a9-1920-539f-b18a-295dbef66d03 | note | FREQUENCY: Once
0b378337-99ce-5a55-9451-038177cc8094 | note | ACCEPTANCE CRITERIA: Compliance with TNZ B/2
f3c2e765-19a7-502c-89dd-6820ebdb29ee | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
3efc294e-2aeb-56c4-9d16-683a1f08e558 | note | RECORDS (Responsibility): Testing Results
12c36bb3-329d-5a9d-a60f-f9eb164ad0ac | note | ONSITE RESPONSIBILITY: Site Engineer
302651f4-518e-4030-a29b-ae3002a12c01 | signoff | AUTHORITY HOLDPOINT
4dd0ae9a-c185-4937-b7f5-71b1c8665f56 | checkpoint | 9 - AT AP65 = Pavement Type W
feeef8a4-e743-56c8-93e8-17fbe2fbd310 | note | VERIFICATION ACTIVITY: Compaction Testing
dfb89f6f-8b84-5f1e-876c-4abadf7b10f6 | note | METHODS OR REFERENCE: Clegg Testing
b1280ba2-decd-5e7e-bfa8-09fdd2713ffb | note | FREQUENCY: 5m grids
b669554f-2b9e-5a19-a5ec-0cc4524da0ee | note | ACCEPTANCE CRITERIA: CIV > 35. to be compacted in 150mm layers
d11875e2-3385-5c91-b828-cde14ecc30e2 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
66caa335-a5cd-5f1a-8273-88fc47199249 | note | RECORDS (Responsibility): Testing Results
b2fc6f8a-443b-5083-902b-331af831d0c1 | note | ONSITE RESPONSIBILITY: Site Engineer
6c176833-074a-5ca5-9a60-c543f57800bc | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
8ef15fb4-1489-4907-a947-89d8bed243d3 | signoff | AUTHORITY HOLDPOINT
43652a6b-bcc9-4287-b11f-0868db38e43f | checkpoint | 10 - AT AP65 = Pavement Type W
9f9be3a2-3685-5d1d-9538-aa097e36e94c | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
b02b1a0a-7252-591c-958a-b5acd5bf4d65 | note | METHODS OR REFERENCE: Survey As-built / Stringline
95b0dbb6-c1c9-5813-82a5-4c1396ee15d0 | note | FREQUENCY: 10m each lane
c200dfe9-09af-5a43-88e7-3889b04807d0 | note | ACCEPTANCE CRITERIA: +0 / -20mm
77e4e32f-509d-53d3-a97e-067659af3730 | note | ○ No trafficking of the excavated subgrade
18944246-06c9-52c9-b726-87a03e94d47f | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
75937683-e181-5013-8d8a-5a43e1a02b73 | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
f3009421-4164-5630-a6a4-3e77580f24a4 | note | ONSITE RESPONSIBILITY: Site Engineer
74f42213-1aaf-52d9-87b8-9a86fbb5fd49 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
0363b3b1-5cdc-4ca6-ad95-2bc1277620f8 | signoff | AUTHORITY HOLDPOINT
125b7169-05cc-44d5-bb6e-8d128edc045a | checkpoint | 11 - AT AP65 = Pavement Type W
d1f1935f-08c4-584f-85dc-303cbe0f19a4 | note | VERIFICATION ACTIVITY: Surface finish
0e375d96-f5d9-5a6d-97b3-ec324f52a7b1 | note | METHODS OR REFERENCE: Visual Inspection
a82e3ead-c1fc-543e-adda-fd6b32ace321 | note | FREQUENCY: All area
4d67e530-76a2-5fd0-b61a-2a115eb0e13a | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
504edfdb-baa8-51be-b2bb-700ff2679619 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
027cb385-8fe4-5e96-880e-4b871da0a284 | note | RECORDS (Responsibility): Photos
a7fd3f14-0f1d-5a78-9236-cc17dd4d0ab3 | note | ONSITE RESPONSIBILITY: Site Engineer
da3a6f79-aa47-42f0-a33c-faa89db06827 | signoff | AUTHORITY HOLDPOINT
fbaa291a-0ce2-4bfe-8a8f-e26e6561ef6d | checkpoint | 12 - Concrete Subbase = Pavement Type W & C
8049fa5b-193f-51c8-948a-eb8354d53cec | note | VERIFICATION ACTIVITY: Strength and slump
d6a122b0-21cf-594a-aee2-cf84aa1a1e37 | note | METHODS OR REFERENCE: Concrete dockets & Lab Testing
a27c782f-5f8c-5521-98db-3943871832e1 | note | FREQUENCY: each pour
6e4785da-a5f1-5f0c-af22-28d23cda2d4d | note | ACCEPTANCE CRITERIA: Strength = 20MPa
a1ec56c3-f9ec-5b0d-bf0b-afbb7a702c36 | note | ○ Slump = 130mm pump mix
17303ace-b6e7-5199-a982-f6087e219cb7 | note | ○ Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface
d58c627f-7d71-571b-93ff-d5717812cc4f | note | TYPE: Inprocess Inspection
7a6ad62b-b3b1-5fb9-aee5-afed787c43c4 | note | RECORDS (Responsibility): Concrete Dockets, Slump Testing Report, Cylinder Testing Report
e72aa332-4993-5d51-ba7b-7735d27db935 | note | ONSITE RESPONSIBILITY: Site Engineer
ef72fe7f-a2f8-40fb-8be4-ebd9f3d06b0d | checkpoint | 13 - Concrete Subbase = Pavement Type W & C
82749c6c-6231-5b92-8fe6-a05f37d4abd0 | note | VERIFICATION ACTIVITY: Levels / thickness
b32c2838-2b46-52d2-80c3-11e6b2b6443e | note | METHODS OR REFERENCE: Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour)
4ba650ea-2c31-530e-8f13-c8b3ac23f99e | note | FREQUENCY: 10m each lane
176f352b-3f76-5006-9725-f0a202a5ffad | note | ACCEPTANCE CRITERIA: +0 / -20mm
6f4858e4-8ae9-54b8-803d-6d6654edd125 | note | ○ Target thickness = 150mm
4d66d899-6928-50c4-82a0-d9942ebdf352 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
162c5689-aa39-50b1-83f9-5560d4bda3f3 | note | RECORDS (Responsibility): Stringline Sheet
d2ce011c-e3c7-5f02-8891-fd684cb4c217 | note | ONSITE RESPONSIBILITY: Site Engineer
b6bf7504-3f49-517b-84f4-f90669731f46 | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
40ff88c1-a6e1-4542-84e3-eb344207abb0 | signoff | AUTHORITY HOLDPOINT
309f5176-5c35-494d-8a55-cf6639d09970 | checkpoint | 14 - Concrete Subbase = Pavement Type W & C
be86fb6e-4b5e-506d-b471-076366467be4 | note | VERIFICATION ACTIVITY: Rough trowel or Broom surface finish
5e9fc4c2-3a6b-5854-9066-869623bf3058 | note | METHODS OR REFERENCE: Visual Inspection
dfbc446d-490c-5c32-825f-81dfa59a26b4 | note | FREQUENCY: All area
4311536a-a8b5-5d04-a09e-09fd41ba6691 | note | ACCEPTANCE CRITERIA: Rough surface verified over 100% of surface area
a45b5116-85d8-5538-aafb-5bafc9215e3e | note | TYPE: Inprocess Inspection
767666a7-e53c-571e-b913-1ca99306c045 | note | RECORDS (Responsibility): Production Recurs
41d76713-b485-5292-b21a-6d7412452c10 | note | ONSITE RESPONSIBILITY: Site Engineer
f83f498e-35df-4953-8dad-b850218c0cdd | section | Sealing & Hatelit XP Grid
efcc7e2f-485b-4dae-bc7d-30f2ed49f64a | checkpoint | 15 - Type W & Type C
649e4765-2d97-5e60-8261-1efaca30fd36 | note | VERIFICATION ACTIVITY: Blinding/CAT60
2b3838a1-1af4-5b22-bad5-c997192f9783 | note | METHODS OR REFERENCE: Visual Inspection
ff01c17b-a71e-5d68-a669-16ad15610bd0 | note | FREQUENCY: each lot
962ffca6-0ae0-5914-a8c7-c2caf1780349 | note | ACCEPTANCE CRITERIA: ON CONCRETE SUBBASE
4f7c94d0-4878-5272-9e88-ecf3573e6732 | note | ○ Hand spray heavy tack coat emulsion (residual bitumen 1L/m2)
010f2785-784b-5f45-9648-b3860271747c | note | ○ Blinding sufficient to protect emsulsion from construction movement
53bb8ffd-cbf4-5618-ac8f-00d7b055455b | note | TYPE: Inprocess Testing
5b53e670-af98-5051-b2ad-fea59e1a0540 | note | RECORDS (Responsibility): Photos
e2d0235c-9a3a-5c1a-b925-c3c05bbe2803 | note | ONSITE RESPONSIBILITY: Site Engineer
17336e97-eac0-4150-aa7a-a9ee4d5aded7 | checkpoint | 16 - Type O = Contingency weak / soft spot
2558f390-09d1-593c-aa0e-f4ee5cda7a9c | note | VERIFICATION ACTIVITY: Grade 4 Membrane
d14c1ed2-e6a6-51df-ba15-131303ca1e8b | note | METHODS OR REFERENCE: Visual Inspection
dc0d430e-79f1-509b-b7ff-379d84338ed3 | note | FREQUENCY: each lot
16a1ee76-21df-5ed3-a4df-7185d8e3dd95 | note | ACCEPTANCE CRITERIA: ON EXISTING PAVEMENT
c8a2d362-4bda-52af-ba46-dbd9bef13e07 | note | ○ Hand spray Heavy tack coat emulsion (residual bitumen 1L/m2)
b5fcefbd-a946-5134-a6f5-7ca84339281f | note | ○ Grade 4 chip
58109be4-e33f-5063-9f01-1d8b672349bd | note | TYPE: Inprocess Testing
6057943a-d667-5018-be4b-0f6dab3cf1e8 | note | RECORDS (Responsibility): Photos
66bf07b7-6953-5ea2-9480-2f027120854e | note | ONSITE RESPONSIBILITY: Site Engineer
f2430dd6-2ddd-43d0-be86-5611d817bf05 | checkpoint | 17 - Hatelit XP Grid
52c122d6-5af9-5ad5-ae62-18c56effdf0f | note | VERIFICATION ACTIVITY: Photos
d2584fea-52e3-562e-bb2b-01774cc3fe34 | note | METHODS OR REFERENCE: Visual Inspection
ab351b05-6248-5959-bdf2-4f0bf0a7a1e6 | note | FREQUENCY: each lot
aef20013-1387-58d9-8f0b-7eaca572a0b0 | note | ACCEPTANCE CRITERIA: Type W &C = required over concrete subbase
5a375e94-e179-55b0-847b-70c4d4f4f3b3 | note | ○ Extend 500mm into existing pavement (with <20mm asphalt blinding)
f926fdd4-8e0e-5c30-bb76-b05cb2dedf12 | note | ○ Extend 1m into Type O
878fb108-1cca-5b2e-960d-8ae26fed6f14 | note | TYPE: Inprocess Testing
4949e91f-4745-5ae8-9258-86834546ae20 | note | RECORDS (Responsibility): Photos
098c692b-e1eb-58d2-a47a-880b88e5b880 | note | ONSITE RESPONSIBILITY: Site Engineer
f91923b6-09bc-4ea0-b889-cce1af7cec1b | checkpoint | 17 - AC14HF & AC20
770d683c-bc17-5fdb-8202-557cbaf31f6b | note | VERIFICATION ACTIVITY: Mix Design
7d4c4d92-3a94-5bdc-ac7f-7c26e202da64 | note | METHODS OR REFERENCE: Sign-off by Designer
26b0f01b-716d-5d3c-843f-a8e0553dbb0a | note | FREQUENCY: Prior to starting
60971a96-76ec-502b-9c92-7cface3ca91b | note | ACCEPTANCE CRITERIA: Sign-off by Designer
dd1388f6-8e9a-5061-ab58-eb27d233e0f3 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
2f26019a-581a-57c5-8c8f-dc24fbd5428f | note | RECORDS (Responsibility): Mix Design Report
336c6cca-1c15-5207-a484-369fa0b4b741 | note | ONSITE RESPONSIBILITY: Site Engineer
ddcb169c-e5a1-54ba-9129-90668a3bdc5e | note | CONTRACT MANAGER SIGNOFF: Designer Signoff
0c2ad78a-ba96-4ca9-a49f-7eb229ce4f86 | signoff | AUTHORITY HOLDPOINT
80459fa0-bdd5-456f-99c9-17c3ee0f5fb2 | checkpoint | 18 - AC14HF & AC20
6e543dac-5299-5c80-971f-ff7d41be215e | note | VERIFICATION ACTIVITY: Check weather reports
250648ca-eb4f-5049-a2ef-e537a00ebdfa | note | METHODS OR REFERENCE: Check weather reports
c89560ac-22b1-521e-a022-d7ea6ce61d46 | note | FREQUENCY: Daily
1dc4d3ea-42f1-5572-b473-539163c03bc3 | note | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
cf6fca67-2e8b-5fd8-8b57-6dbcc7778305 | note | TYPE: Inprocess Testing
f7d0f6f9-9ce3-533e-a5a0-31f252181766 | note | RECORDS (Responsibility): AC check sheet
98f99f03-3c38-5e0b-ac0a-134c3e542169 | note | ONSITE RESPONSIBILITY: Site Engineer
e5a60d39-33d2-4bb9-8f41-403c9eabe9bc | checkpoint | 19 - AC14HF & AC20
d8dcf565-fb9c-59cc-9452-bd03b3956985 | note | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
45e03313-d270-53fc-a4d7-478319a6e24e | note | METHODS OR REFERENCE: Visual
fa2a669c-d0bc-576d-8821-9424f7ddddad | note | FREQUENCY: Prior to starting
c1d3288b-034d-53c3-8cb7-e14677a5e759 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
bc25082d-5026-5ab4-9f9c-13191765c950 | note | TYPE: Inprocess Testing
79e1aded-fccd-5ca8-b068-57b686a2dd70 | note | RECORDS (Responsibility): AC check sheet
1c13a707-244e-5ef4-8f3f-85cfffc37be9 | note | ONSITE RESPONSIBILITY: Site Engineer
1bb6e02c-5f0f-44b7-a590-7effe2157cc0 | checkpoint | 20 - AC14HF & AC20
39f9c31e-6e49-5414-925c-4662aafa37ff | note | VERIFICATION ACTIVITY: Production tests
8f9ef21d-2d53-5498-a75c-9741bba1c281 | note | METHODS OR REFERENCE: Grading, binder content, max density, temp
41c7f50d-3a24-50c9-b102-4fd78e403faa | note | FREQUENCY: As per M/10
94a9fe49-20c3-5bcb-abf0-b931289d4322 | note | ACCEPTANCE CRITERIA: NZTA M/10
7ec73576-b23a-544f-a3d7-75652ad1cb88 | note | TYPE: Inprocess Testing
451b708b-e830-5926-adb5-4dee5d7b4cdd | note | RECORDS (Responsibility): Lab test
1007cd51-c8d0-5cb4-a3a5-8b723c336e65 | note | ONSITE RESPONSIBILITY: Site Engineer
995835df-7fa8-4b45-a802-5d9c9da0c782 | checkpoint | 21 - AC14HF & AC20
09bbf7cd-d65f-5e18-b244-e7e224b08c1a | note | VERIFICATION ACTIVITY: Surface finish inspection
d9925f59-dd06-5a2a-9f25-a9373ed17799 | note | METHODS OR REFERENCE: Visual inspection by the Engineer
d901f7a8-e1c3-5433-b099-6e89e39bc72e | note | FREQUENCY: Each lot
898e451b-e69f-5ff9-8dc0-cbd76a467b34 | note | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
4a5fe105-43ad-5177-a17f-fe4720bbc8ef | note | TYPE: Inprocess Testing
8115d2c3-422e-54a3-abd3-c2856d3242b1 | note | RECORDS (Responsibility): Inspection sheet
d4415d99-4b1a-5d87-b099-ce65ae926804 | note | ONSITE RESPONSIBILITY: Site Engineer
420da1c3-bb22-4449-8045-163cb43dd372 | checkpoint | 22 - AC14HF & AC20
0ba80e2e-25c4-5a28-8432-6b1a297c3212 | note | VERIFICATION ACTIVITY: Density testing
17671aea-c4f3-5be0-a7f1-40192f6fb218 | note | METHODS OR REFERENCE: NDM
d785bd6d-5aaf-514f-8d09-f6e46dfe3244 | note | FREQUENCY: Every 10m each lane staggerd
8b8833b2-344f-5a19-b0ae-8b6a34fab798 | note | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
b04ecc4f-49de-5438-898f-9c961f46cb1c | note | TYPE: Inprocess Testing
2ad49e62-3221-5ee8-bb7c-4e87f4834c45 | note | RECORDS (Responsibility): Inspection sheet
e67b27f0-3537-5c21-81c2-c08a0c2ffc99 | note | ONSITE RESPONSIBILITY: Site Engineer
0d24fdfe-0fda-52e5-b650-ba566bcef004 | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
a45d1f24-46ea-4e0e-8a6b-3228c28ebea2 | checkpoint | 23 - AC14HF (Type O)
569bdca5-200b-5486-aad7-b35046d0d960 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
6f3c2990-f22c-5307-a720-830e9c1e838b | note | METHODS OR REFERENCE: Survey As-built / Stringline
18f003ef-32cb-5f2f-b804-1b041c522138 | note | FREQUENCY: 10m each lane
054e5003-6546-5e4d-8a7c-4c1118a93733 | note | ACCEPTANCE CRITERIA: Thickness no less than 55mm
f115763a-6e9a-52bb-a3fa-552e0b2a28ef | note | ○ Height discrepancy +/- 5mm
827046bc-67d8-54d7-b0f5-3a862976e70e | note | TYPE: Inprocess Testing
a6ea4edb-835c-5f13-aafb-4e101bec12ce | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
8e9df148-ed51-5d2b-99e9-ad0e8b1301fc | note | ONSITE RESPONSIBILITY: Site Engineer
193561f0-9222-433d-9310-8131a532ebd2 | checkpoint | 24 - AC20 (All three types)
2b211b6e-70ee-559f-991e-8b41d2becc51 | note | VERIFICATION ACTIVITY: Survey As-built / Stringline
ff8cc84e-bd4a-5f42-ae50-d786ef485075 | note | METHODS OR REFERENCE: Survey As-built / Stringline
2ed4cf3c-cffe-5b14-9db7-368f22bca551 | note | FREQUENCY: 10m each lane
f9571437-d685-5c26-af92-88e5945ccd1e | note | ACCEPTANCE CRITERIA: Thickness no less than 100mm
2062a635-9720-5d75-b86f-4f475c71738a | note | ○ Height discrepancy +/- 10mm
8a2c77cd-83a6-537b-b8d2-20094550b90b | note | TYPE: Inprocess Testing
2345f084-852c-51ac-9f02-decec91cb204 | note | RECORDS (Responsibility): Survey As-built / Stringline sheet
8befbd2f-42c6-5ed3-b038-fc86e7f77b49 | note | ONSITE RESPONSIBILITY: Site Engineer
7e2e1e63-9acf-4207-841d-46fff13cbd59 | checkpoint | 25 - AC14HF & AC20
668b176b-8d20-5f16-ab3e-93b3918c37af | note | VERIFICATION ACTIVITY: Density testing
df39d296-0986-56a7-add8-79722171788a | note | METHODS OR REFERENCE: Cores air voids
f4bc3b4c-ba80-506b-a51f-2f40b1d42fce | note | FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
b8911901-2612-5814-9a9a-f1d1e3c0ba23 | note | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
dfd3d2a2-a328-5470-b42e-937461344e99 | note | ○ Cores shall be cut from the pavement at a rate of one core for every
8828dfd8-501d-57b3-8aa1-3eab1a9d022e | note | ○ 300 m² with a minimum of eight cores representing each lot.
333afa6a-c86d-5d67-996a-9d59fb4678f9 | note | ○ 3 joint cores where possible/practicable
68704d18-fe7d-5dc0-9e83-8f9d56c7f3e7 | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
e36dd4ab-05f7-5121-bb29-4a9977c69b20 | note | RECORDS (Responsibility): RFI response
37c03c65-478f-5e41-a00e-82b82b3132d4 | note | ONSITE RESPONSIBILITY: Site Engineer
739cec23-c184-50fd-86f6-383bdb1a4c31 | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
ccb4f354-6f6e-40df-a864-39c1a379da0c | signoff | AUTHORITY HOLDPOINT
6a495544-0fc6-4b9d-a25f-b1567ed905d9 | checkpoint | 26 - AC14HF & AC20
4169ca3c-e47b-5da4-861b-7b19b6f8f9d5 | note | VERIFICATION ACTIVITY: Thickness
4cfa3532-01da-5907-96ce-82c8b78affdb | note | METHODS OR REFERENCE: Cores depth
9a1a494a-7d94-52f4-8114-c12bb70799cc | note | FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
455e029b-e1b4-5f54-90dc-1a45176fad9e | note | ACCEPTANCE CRITERIA: Target thickness 155mm (no less than 155mm thickness for AC14HF and AC20 combined)
8856a3a6-8315-5295-9900-9b083e3b2223 | note | ○ Target thickness 100mm (no less than 100mm thickness for AC20)
594363fe-fe77-52c2-9ff2-43a503ff76cd | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
c4b64fb6-a632-568c-9bd3-508db9957710 | note | RECORDS (Responsibility): Core test report
7db6d42e-ecf3-5568-9bcd-4ab8c07bdd9a | note | ONSITE RESPONSIBILITY: Site Engineer
699cd4db-caae-5118-af49-c2d877b4efdf | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
4284c5e4-99d8-4bfc-8cd0-86d52fe75d53 | signoff | AUTHORITY HOLDPOINT
028322c7-b51c-4a38-89aa-022fb6f25175 | section | Asphalt Surfacing - 55mm AC14 (PG64V)
dc14b3d5-8185-4646-bcd5-dbb19ded4ac1 | checkpoint | 27 - Shape of road
712281a1-975f-518c-9d9c-4d875efb5309 | note | VERIFICATION ACTIVITY: 3m straight edge
be97c971-0d83-5921-ad06-bffdfbf4b7aa | note | METHODS OR REFERENCE: NZTA M/10 spec
f9ddfa5e-1b85-5b88-8995-7728a70eb64d | note | FREQUENCY: At joints and any other areas of concern
e60c754e-012b-54ad-808c-b60fc80a0abd | note | ACCEPTANCE CRITERIA: Irregularities < 5mm under straight edge
5fea7d40-6c8f-5409-8d76-fab057628e58 | note | TYPE: Inprocess Inspection
9b1220dd-6144-5f98-bc7e-a88a82f824f1 | note | RECORDS (Responsibility): Check sheet
7d04bd61-9d1f-52d3-b09c-fdbd3e0a7512 | note | ONSITE RESPONSIBILITY: Site Engineer
f0c55852-0db7-4684-942f-18fc1787b12e | checkpoint | 28 - Temperature Limitations
7e80585c-e6a3-512c-a04e-c93f6b4fc8f1 | note | VERIFICATION ACTIVITY: Temperature
b7fac1d8-d036-5be5-b3d2-f4c16eb74432 | note | METHODS OR REFERENCE: Contract Spec / M10 Spec
9ade5540-a67d-52c4-bb46-de816c9f2721 | note | FREQUENCY: Every Site
627afb15-b414-5db8-ba04-be27a212c8e4 | note | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree
9308e9e4-14b6-5379-9d5c-861cb7356321 | note | TYPE: Inprocess Inspection
1ef9d30c-ac2a-5ac1-b9d3-ab30f4526ea8 | note | RECORDS (Responsibility): Asphalt QA
8441ec84-254c-54f9-a37f-3a67b3aed331 | note | ONSITE RESPONSIBILITY: Site Engineer
15210cc4-2023-401a-83dc-b2702222a907 | checkpoint | 29 - Surface Preparation
9541f0c7-10cc-5a20-be88-dba05eaa5af0 | note | VERIFICATION ACTIVITY: Visual
d2db64a4-4eac-515f-8552-ae159e47ed6b | note | METHODS OR REFERENCE: NZTA M/10 spec
d42bae8d-b5b8-51bf-b23b-8cce45d534e9 | note | FREQUENCY: Every Site
c7e640ed-c48c-5884-8eda-058f07812343 | note | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
cbae897c-d036-5570-a98b-530fcf6775e2 | note | TYPE: Inprocess Inspection
e4ba0c9c-aacc-5193-b816-3996c23d9792 | note | RECORDS (Responsibility): Visual
885ee228-87a2-5050-b651-abe7ab941693 | note | ONSITE RESPONSIBILITY: Site Engineer
6839422c-7e3c-48d0-b97b-d57e04da80a5 | checkpoint | 30 - Asphalt Production Tests for AC14
32a8b3bd-35ea-51ff-a77c-455217669eaa | note | VERIFICATION ACTIVITY: Production Tests
976936c8-8e52-5099-9d5f-68f49db6eeb8 | note | METHODS OR REFERENCE: Grading, binder content, max density, temp
aa9962e5-baec-59bb-9325-7bdbca7f26b2 | note | FREQUENCY: As per M/10
45571860-4afa-5eb3-843d-d34279522702 | note | ACCEPTANCE CRITERIA: NZTA M/10
a118e933-537a-514a-8fe3-682ec3570c44 | note | TYPE: Laboratory Testing
cd110671-f2ce-5c6d-a891-0e543c69f9cd | note | RECORDS (Responsibility): IANZ Lab
e8e5b1c8-cb67-55da-9722-4f984603e919 | note | ONSITE RESPONSIBILITY: Site Engineer
016e9793-99b3-464f-9a9a-cfa232d43ec6 | checkpoint | 31 - AC14 - Layer thickness - 55mm compacted depth
6f9ad727-f5ea-5ea6-8083-1d933f27ae45 | note | VERIFICATION ACTIVITY: Insitu
fd6ee6df-d7fa-578d-ac73-3593cb38aad4 | note | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
06d0a877-9d4b-5887-96db-9813c426d196 | note | FREQUENCY: Continuous
48ba7cd6-226b-5fad-b621-c3eaf4a257e9 | note | ACCEPTANCE CRITERIA: 55 mm minimum and 60 mm maximum compacted depth
7d53e42e-8cb3-502c-ac6c-0d152f3fa64d | note | ○ Final asphalt level to be 5mm proud of lip of channel
8a7ba271-0879-5445-a91a-9bfbe91f1dbc | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
8b6b8cd6-4f0a-587a-8c4d-92b05b686f9e | note | RECORDS (Responsibility): Asphalt QA
6fe694b7-9e2d-5c90-97b4-15b4886ac39a | note | ONSITE RESPONSIBILITY: Site Engineer
1a87c3ad-5cb7-5791-b76d-9d4901c6a2ff | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
e746a891-bbe8-4250-98b8-cbf3e9fee3a3 | signoff | AUTHORITY HOLDPOINT
91fbbe55-bc00-4650-9d40-ff77e1bb60ed | checkpoint | 32 - AC14
5d010bc0-18f0-5525-a356-fa741824c5d2 | note | VERIFICATION ACTIVITY: Density testing
8b1eef65-62d7-57ce-83bd-64cb5280aa3a | note | METHODS OR REFERENCE: NDM
d910003e-185d-5f7e-beb9-5b027b3a1dcd | note | FREQUENCY: Every 10m each lane staggerd
b88b5198-cb71-5820-bbc1-0854d7b77a9f | note | ACCEPTANCE CRITERIA: NZTA M/10
3ea730d2-4d3d-58cd-864f-35be9555d56c | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
cf7f63c2-a280-5150-b487-d935c60afc01 | note | RECORDS (Responsibility): RFI response
88c67aca-b293-57ae-a8b5-55b0b5f21a89 | note | ONSITE RESPONSIBILITY: Site Engineer
07caab0f-2146-5d85-ba8d-462fa25a656d | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
f0915fb1-d4ca-4407-be05-7246a267e02e | signoff | AUTHORITY HOLDPOINT
6bc9c950-012e-4a9b-a425-745890976bd6 | section | Reinstatement
6c375d7c-872b-467d-8f0d-6c6d2b2f9916 | checkpoint | 33 - Reinstatement of Linemarking and RRPM's & Apply Joint sealing
60ce4bd7-de6c-502c-bfc0-d9d35aa2842a | note | VERIFICATION ACTIVITY: Visual
cbf78570-f9de-547d-a5c3-a94371eca002 | note | METHODS OR REFERENCE: Visual inspection
d847dd02-d18f-55f9-87fb-4d35825c055e | note | FREQUENCY: Every site
e434fe33-a53d-5916-811e-5b058b36bec0 | note | ACCEPTANCE CRITERIA: Visual inspection
5a2b01c7-09e7-57b0-864c-192c46a9a9de | note | TYPE: Inprocess Inspection
ae8414f9-bb17-5278-93a4-c9f314b5629f | note | RECORDS (Responsibility): Photos
d431d13e-dcb5-5e2c-b2ca-ecfca6d88e3d | note | ONSITE RESPONSIBILITY: Site Engineer
c5623302-3125-48dd-afcc-39a1e2449901 | section | As-builts
adee6db3-fe02-4978-8326-11e613e8b9f1 | checkpoint | 33 - As-built information
6366c83b-62b6-586d-a95a-1644b0ba8cd0 | note | VERIFICATION ACTIVITY: Documentation
d6997be2-7562-5fd2-ac93-fa785f883105 | note | METHODS OR REFERENCE: As-built drawings and ramm sheets completed
83adca16-34ab-5372-9388-8caf8480e32d | note | ACCEPTANCE CRITERIA: As-built records
fa2f5325-213a-5f0a-87f8-844189ecb0fd | note | TYPE: Inprocess Inspection
14d6bce9-27c0-5ad2-b9e9-adcb3917e72d | note | ONSITE RESPONSIBILITY: Site Engineer
dbbecd1f-9d4e-5bfe-bb3b-5892f05b91de | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
873c1d2e-6749-4022-9a88-1d0f17305112 | checkpoint | 33 - RAMM DATA
180006db-6b11-514e-ad2f-ba03ea0e56b8 | note | VERIFICATION ACTIVITY: Documentation
7f3896e2-c738-51da-9fa6-17b0bfdad632 | note | METHODS OR REFERENCE: RAMM Sheet
25863a46-bdc4-595b-8c76-ae233491366d | note | ACCEPTANCE CRITERIA: RAMM Sheet
af88f696-413b-5b0d-8281-db70f6ce62e0 | note | TYPE: Inprocess Inspection
ebdd2cff-1c07-5b4c-bed6-f48244d6e7b6 | note | ONSITE RESPONSIBILITY: Site Engineer
6d49938e-cf12-5525-ab6a-b593dfb87091 | note | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
1ad5d30d-0463-4263-9ea1-cfcfc4f45209 | section | APPROVALS
006c879b-ad8c-42d8-b4c8-e0ef10f2640c | checkpoint | ITP Approval
e94b657a-8580-51c3-b6f9-fd2aaa6179e4 | note | Approved by Project Engineer: Ajithkumar Ayyanar
8eff3056-9223-5b88-9c17-45f2b9464d82 | note | Approved by Contract Manager: Daeyoung Jeong
111315bf-fd68-53d3-b447-3a6b4bab9310 | textbox | Approved by Client Rep:
36e95c94-4508-4863-8fdd-75a4b425cdae | checklist | ITP - Opaheke/Chapel St - Roundabout and Apron | itp | ITP - Roundabout and Apron | 11696118-cd29-4338-b660-629d65da0f01
9dcf199f-7b05-4031-a623-0ca6e8c6713b | section | Survey - Set Out
c4ee85a5-976c-4718-98c4-a1792b49c8e9 | checkpoint | 1 - Survey Setout
c9f4aa8b-7de9-5011-9b47-b2064eae1ce7 | note | VERIFICATION ACTIVITY: Survey
a73f6302-d295-50f6-8801-476c02d42dc8 | note | METHODS OR REFERENCE: Setout for Roundabout and Apron as per the drawings issued for construction
51b4af24-4f40-51b1-9089-76ea6103e39b | note | FREQUENCY: Prior to commencement.
99819397-7cb2-5ee0-86e5-57dfbca7248e | note | ACCEPTANCE CRITERIA: Survey
c0f103c1-7690-5fa4-a7e3-7df16925a634 | note | HOLD POINT: Inprocess Inspection
84ee5de6-8507-523c-95ba-8f96ef65acb5 | note | RECORDS: Survey Set-out on site
852e3411-5e50-594d-a0d8-677b41d98b8c | note | ONSITE RESPONSIBILITY: Site Engineer
00ac98f3-9fd1-47a2-9092-2739a23c0a2a | section | Roundabout construction
e7ad85b2-086d-4f33-bb7f-47c1947174e7 | checkpoint | 2.1 - Kerb
b71ba309-db69-557b-bbf8-dce0b541bff8 | note | VERIFICATION ACTIVITY: QA Documentation
b239022c-d039-5b5a-a1e5-f0da3e606866 | note | METHODS OR REFERENCE: Type 2B Mountable Kerb as per TDM Technical Standards - KC0001
487c07af-052d-54e4-b58b-e05e582246f4 | note | FREQUENCY: Circumfrence centre island
dac74071-b60d-5f2f-a0d4-1e690cca43cf | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base or Structural AC20. Laid 100mm high from finish level of apron. Concrete 20MPa @28 Days
d334eb21-5fdb-5312-9e4b-45299a83b7f2 | note | HOLD POINT: Inprocess Inspection
00ca8eb0-798d-5d0a-8bea-cd07efedc0a6 | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
e4b932f1-f0ed-5376-86a8-1fb4cb2161c2 | note | ONSITE RESPONSIBILITY: Site Engineer
d539a47a-815a-4602-8876-d9905f05a8d3 | checkpoint | 2.2 - Infill
3b7213a0-3a43-50c0-b1c0-2c3994ab57f0 | note | VERIFICATION ACTIVITY: QA Documentation
5fa9ef80-cc30-5b30-abfc-87b5ae02896c | note | METHODS OR REFERENCE: As per Drawings
d7ecae38-9523-5917-96df-aee3e40fe7cd | note | FREQUENCY: Roundabout infill
e9499277-066a-5039-a42e-33050fef9a99 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish reinforced(1 row of 663 Mesh with 60mm cover) Concrete with 6 kg/m3 Red oxide
ed42862d-a2b6-5331-95e5-ecc2e8ecb5f5 | note | HOLD POINT: Inprocess Inspection
1960c216-21a4-5e69-8726-0189c13cfe30 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
a0651a29-5e53-5e2c-8db3-6b8092662b4a | note | ONSITE RESPONSIBILITY: Site Engineer
a12d354d-1a28-4d9b-993a-45144911236f | section | Apron Construction
dd73440a-a2e0-4e59-ae68-1be26b11bdb9 | checkpoint | 3.1 - Concrete Apron
53b3af0f-fa74-5251-be17-91a39fbf6d9e | note | VERIFICATION ACTIVITY: QA Documentation
e0dd983c-5410-5f4a-a26b-7cfefc0451f0 | note | METHODS OR REFERENCE: As per Drawings
d75f0736-66b7-5947-90a3-7bfd6874e961 | note | FREQUENCY: Apron Infill
2a88dbbd-0d71-55b3-af52-29bd741dac17 | note | ACCEPTANCE CRITERIA: 250mm thick reinforced with two layer of 663 Mesh with 50mm cover of 40MPa Concrete with 4kg/m3 Black oxide-Broom finish,on 100mm AP40 with 0.25mm polythene layer.
1c981283-4e41-56ca-9a84-89328bc77605 | note | ○ Total reveal from road level = 50mm
b361bb52-8667-586b-89e5-e19d178876e6 | note | ○ Chamfer - 25mm
93d1ce5b-d9b9-5ba4-920e-ba4faec7d227 | note | ○ Upstand - 25mm
d4f889e6-e781-576f-8c51-e95af5294ea5 | note | HOLD POINT: Inprocess Inspection
c3cc912f-8397-525e-80bd-51f55602177b | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
74d00338-67d8-5fd4-8b51-a67b295c4dbb | note | ONSITE RESPONSIBILITY: Site Engineer
669aa8b3-a682-49d9-a5bb-f48008f7467a | section | Asbuilts
0752332b-18d9-4817-b971-0c829f05005a | checkpoint | 4.1 - As built information
e991c209-5e58-54cf-a86b-961570bc4c3d | note | VERIFICATION ACTIVITY: Drawings
9ddd722e-7cb0-5b1e-827e-7ef9e214bd07 | note | FREQUENCY: Every Site
6d2ce6ea-0fa8-5c81-886f-30b20b1d3215 | note | ACCEPTANCE CRITERIA: As built drawings
6b71513a-1f89-5e27-9ae5-df83480ad827 | note | HOLD POINT: In Process Inspection
9b78ce88-fbc5-5a30-8847-f11a0e60da83 | note | RECORDS: Asbuilt records
c12ab7ce-747e-540a-9100-3cfd37245fb8 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
275aebc9-b5c3-445e-b767-26b0a9b2c189 | checkpoint | 4.2 - RAMM DATA
569fbe0d-8759-5a95-a2a8-8e0c7670a4a6 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
9fec5478-37b6-5702-b904-3657da9277d2 | note | FREQUENCY: Every Site
df13e6b9-61b6-5a37-b4ed-bcd731f6fcd8 | note | ACCEPTANCE CRITERIA: RAMM SHEET
49b9340c-ed9d-5e9e-937f-6e1cec0992be | note | HOLD POINT: In Process Inspection
81246ea4-a2a2-5275-8bbc-b70ab6671266 | note | RECORDS: Asbuilt records
442a4b92-ee53-5fdc-9317-878e23e16605 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
c3388d83-0b1d-4671-97de-9c7cf5dd3f36 | section | APPROVALS
1ebb491b-952c-4ea3-afe8-d68af6e2562f | checkpoint | ITP Approval
9e8d3aac-a1eb-58e0-8114-c34277e51946 | note | Prepared By: Ajithkumar Ayyanar
8643f622-b323-5d4d-b81f-fb8c0a352941 | textbox | Approving Delegate:
0b6aacc8-71f4-44bd-8166-133ff939d568 | checklist | ITP - Opaheke/Chapel St - Signage | itp | ITP - Signage | c7f0350d-4333-42f7-ae32-ae801c4f855d
f2e603fd-2616-404b-80bc-0dde36a2a16d | section | Site Set Out
90f5de41-6b13-4b5b-8e8d-e7630289a60e | checkpoint | 1 - Site Set out
df427cf8-d81c-5700-86bc-ff93d3afbfb1 | note | VERIFICATION ACTIVITY: Surveyor
ff8f7e8d-fdb4-5d93-ad9d-74eb996ce9c0 | note | METHODS OR REFERENCE: Surveyor
66b4706e-5fde-5ae3-bacb-2a2acd3234b0 | note | FREQUENCY: Everysite
001c3738-e3f6-5d6a-b9cc-3c87f32e8e97 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
0842e915-c750-5765-b428-40d58c6e2d67 | note | ○ Alternatively like for like
81ed47db-c501-50cb-be57-e811ac138a4e | note | HOLD POINT: Mandatory HOLD POINT
c9a180f8-06bc-5f1c-8fc4-3db2fba3e6c5 | note | RECORDS: Photos
a4793f84-b78e-5f76-b2e1-f0586d557b01 | note | ONSITE RESPONSIBILITY: Site Engineer
a72ec6a3-4c50-44d2-bd6a-4ff46bf0078a | signoff | AUTHORITY HOLDPOINT
c19f824b-f54f-4d0f-952f-85158d562b19 | section | Materials
37235504-fc53-428c-978c-5ed228c6ad52 | checkpoint | 2 - Signs
0a56298c-069f-5b15-87f5-d7b6821e4ab9 | note | VERIFICATION ACTIVITY: QA Documentation
69be9845-2567-54d4-a3dc-9bc6445cde22 | note | METHODS OR REFERENCE: TDM Technical Standards
6d580850-d2bb-551a-8727-bd5216ccc7c4 | note | FREQUENCY: Every site
7b72ef5a-643f-5d5d-92fe-07f08cebc67d | note | ACCEPTANCE CRITERIA: All signs to be in good condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
f63d7f05-6d3f-5225-a906-f87d1c49f8e0 | note | HOLD POINT: Inprocess Inspection
bab38c18-e0ab-5229-8bf6-68df90693122 | note | RECORDS: Dockets/Photos
8832b93a-8038-5c40-ae5c-4277f00c03ea | note | ONSITE RESPONSIBILITY: Site Engineer
9e365d39-21e3-4344-a507-543ac35bea42 | checkpoint | 3 - Pole, Impact recovery post and Ground Socket
42522c94-cfd3-593f-a11b-30a05c187cca | note | VERIFICATION ACTIVITY: QA Documentation
6d94223f-d1d5-5021-a5e7-a1db0d320196 | note | METHODS OR REFERENCE: TDM Technical Standards
591b2d4d-136a-5a02-9bf5-bf2a0b1189a0 | note | FREQUENCY: Every site
4c28e7d2-b4fd-5d6f-8215-9d5f99c5332a | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be in good conditon with end caps.
648e15d8-6b10-5b07-b396-23f537d8d5cd | note | HOLD POINT: Inprocess Inspection
43639f91-27ba-5f17-9149-9d4e439c7510 | note | RECORDS: Dockets/Photos
60d86c66-8e43-50cf-82f9-0dc0e658749a | note | ONSITE RESPONSIBILITY: Site Engineer
849917f3-f498-4049-b406-e58ec854dbb5 | section | Construction
a0857453-ee4e-445d-a546-e1b3219ee277 | checkpoint | 4 - Ground Socket
289bce04-a793-5985-a285-adab1e170481 | note | VERIFICATION ACTIVITY: QA Documentation
b54f47a4-88f3-5ffc-b585-5ab4c14d8a9a | note | METHODS OR REFERENCE: TDM Technical Standards
0b8ddc90-bdbd-53bc-9ada-3b8ca12c025a | note | FREQUENCY: Each Socket
107169ec-195e-5e82-8cd4-92325db9ae60 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
2a92fbdc-466d-5d3a-8c1e-a342871c0d38 | note | HOLD POINT: Inprocess Inspection
258424a3-397b-5ab3-890b-3b0f04202c8e | note | RECORDS: Dockets/Photos with tape measurement
a37192c1-f0e8-5c51-ae25-5e4d4ca47f55 | note | ONSITE RESPONSIBILITY: Site Engineer
ae0ad16c-1b47-4679-88fa-d9abb65d1f2e | checkpoint | 5 - Pole and Impact recovery post
1f5a37c1-152e-5d6b-ac3e-74a7d6365e33 | note | VERIFICATION ACTIVITY: QA Documentation
e133ff1e-d085-5059-b45a-7cda8ab11c83 | note | METHODS OR REFERENCE: TDM Technical Standards
ca004347-875f-531d-b0df-a891169ea859 | note | FREQUENCY: Each Post or pole
5c618e26-8510-57d0-9d7e-e0771bbc4dec | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
7383b21c-f09f-5bfd-b908-53bd83699313 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
be15b9b3-5f81-5bc7-8433-92229bd2d5c0 | note | HOLD POINT: Inprocess Inspection
bb6328e3-5d17-56a5-b9a1-e9715908c480 | note | RECORDS: Dockets/Photos
8af3be22-748a-53e9-a675-0678a2542ba3 | note | ONSITE RESPONSIBILITY: Site Engineer
a5c8dc5f-405f-4523-8648-909bea7fdeed | checkpoint | 6 - Signs
88427634-3e39-5029-988b-d63a3890f0e1 | note | VERIFICATION ACTIVITY: QA Documentation
9a0c1a67-2820-50d8-b9bc-407e5e45e676 | note | METHODS OR REFERENCE: TDM Technical Standards
54b767cf-fb02-5aea-b04a-481093d532a6 | note | FREQUENCY: Each Sign
6a06afd4-783f-5a4c-8f8f-4fc0985191ac | note | ACCEPTANCE CRITERIA: All the sign to be fixed to the pole or post with ARC brackets and tightened adequately.
6c430c81-0a17-5828-9bfc-ca88d92b6e01 | note | ○ Ensure good visibility to road users & secured to prevent rotation around pole/post.
b5c7f957-cfbc-526e-afac-c91abe2d5963 | note | ○ Ensure sufficient offset from road & pedestrians/cyclists - as practicable as per existing environment/surroundings
79fcde9e-a150-5c0c-ad96-1fb7cf6e4de7 | note | HOLD POINT: Inprocess Inspection
ddfc920b-1f67-5af0-bbbe-2f256130457d | note | RECORDS: Dockets/Photos
0197fc62-af2f-53db-b0f4-3199e8a47fff | note | ONSITE RESPONSIBILITY: Site Engineer
676e08ba-98c6-4f3f-a642-2c60058545a7 | section | Asbuilts
e7fb0d8a-4b6b-431a-b659-efba77a91ddb | checkpoint | 7 - As built information
b1af2ef0-ae8e-5cab-abd9-64044f79ebcd | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
cb69a005-3488-5c48-9b03-a66cce6e70fb | note | FREQUENCY: Every Site
fcba16dd-07dc-5603-bb34-0742159e8483 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
13d8d478-96c0-5191-97c3-064178244f78 | note | HOLD POINT: In Process Inspection
87370976-f4e6-50bb-a700-3f8d81e8c8d7 | note | RECORDS: Asbuilt records
68b0e05a-6f8c-55eb-aaa1-898cd432e1a8 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
9f6b5bd2-20f2-43d3-8e94-ded85100d74d | section | APPROVALS
ca3cc39b-773a-402e-90be-4399e36766dd | checkpoint | ITP Approval
abe67221-e81d-5ad5-b983-ea64894cb53f | note | Prepared By: Ajithkumar Ayyanar
afda5a09-cc85-537c-af7d-1a8119c7aa72 | textbox | Approving Delegate:
3c1d1154-5a14-4eb4-8ae6-99ac6dd78528 | checklist | ITP - Opaheke/Chapel St - Stormwater Drainage | itp | ITP - Stormwater Drainage | 8e40a7e2-5013-4b26-9ce0-d59e907a75f5
17981597-de50-470c-a59f-ae4661bc8a77 | section | Stormwater Drainage
10605f99-2188-4125-a3cc-2698a260c010 | checkpoint | 1 - Permits & Services (1)
0c9b2752-358e-5cc1-b3d0-89e783f2d3d5 | note | ACTION (Hold, Monitor, Witness): H
c868aae8-f781-52cd-99b1-e1e91bed53c5 | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
38415623-c888-526c-a879-e80602fa7471 | note | FREQUENCY: Prior to any construction commencing
17cb7ef2-a1b2-55fe-a2d8-58360b32a623 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
1da223ad-4254-56a7-b6de-eb1b81608fdf | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
2defec35-23df-5cbc-99a0-0216a479bd53 | note | ○ AT Access Authority approved and signed by RCA Authority
d68d5702-2227-5af4-92e5-2dddc885a589 | note | RECORDS: Permit attached or permit number noted.
23ac07e2-4389-44f2-b2ff-d38c41531d96 | signoff | AUTHORITY HOLDPOINT
2bef9ffb-d371-4ca8-852f-cba9514501eb | checkpoint | 1 - Permits & Services (2)
953bbc72-5d6d-5093-86bb-5b8b19d366a9 | note | ACTION (Hold, Monitor, Witness): H
9dbeead4-9e71-5e89-9f85-30c3cee3a10b | note | DETAIL: Locate and mark out all existing services
840b114f-c931-52f9-9c8d-86d4ab3d8c8c | note | FREQUENCY: Prior to any construction commencing
5fd26f2a-247b-5628-b9ea-dc7ed2371784 | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
ccde5280-5412-5af3-809e-e33cdca96079 | note | RECORDS: B4u dig plans & GPR report attached
c06646c9-066a-46a3-a132-7c3a8e124cdf | signoff | AUTHORITY HOLDPOINT
794834f3-2189-4e57-9a55-eb88b4b73c1d | checkpoint | 2 - Pre-Construction Sign Offs
70473b76-468f-5ed9-9082-144243429852 | note | ACTION (Hold, Monitor, Witness): H
463b584c-49fe-5d01-b5ef-6be37baebfb5 | note | DETAIL: Sub-Contract and Supplier Agreements
eda4e4a6-386b-5431-adf6-ca7984fa047d | note | FREQUENCY: Prior to commencement.
ed8bfa42-22b8-5c7b-936a-30b585f435a9 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
0c022e89-cd58-5010-ba4e-a78d83be9ecb | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
9f7ad938-1795-5caa-a30c-6ae51dd5a22a | note | RECORDS: Subcontract and Supplier Agreements
6ec16292-b068-4800-8602-d1eb417f3c8d | signoff | AUTHORITY HOLDPOINT
23cabef0-2a75-448f-9714-5d295c7358a1 | checkpoint | 3 - Design
a0de9ba9-4bb1-5175-862b-cafd21a49419 | note | ACTION (Hold, Monitor, Witness): H
e422c19a-dbf9-5d40-8cd0-537e06787a95 | note | DETAIL: Design is approved and Drawings are of the latest revision.
9a8ff526-0e6b-5b1a-b82a-36e79d004add | note | FREQUENCY: Prior to commencement.
859387ee-fbdd-57c4-8da9-3a890e02c192 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
eb12d7f1-ae8a-5c68-aec5-c71362bfddc8 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
abf0ffd6-b662-51a4-9403-e2cc0fe38d52 | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
0dee944c-c155-56ae-ab88-7d6d6aaa1415 | note | ○ HOLD POINT if not issued to IFC.
1cbec1fc-8fe0-5123-aea5-5f784236d118 | note | RECORDS: Drawing Register.
897941ff-2697-4d29-b9ba-92b4c0b185e4 | signoff | AUTHORITY HOLDPOINT
1b02769b-f39f-43ef-9ef6-dc86b9da466c | checkpoint | 4 - Survey Setout
66246a6a-c743-5a2e-8100-69725cf7221a | note | ACTION (Hold, Monitor, Witness): H
872800ef-be9c-56b4-a6da-f396958b4af4 | note | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
1cd57087-71a8-52cb-b1cd-a2e87a32f8dd | note | FREQUENCY: Prior to commencement.
b8ba92c5-22f3-50e9-9c35-b532793d4e2e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
f290b963-9249-5a5e-929b-b08d74f2f124 | note | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
9ea27b2c-1c5a-5e66-b8f9-18390431cf2f | note | RECORDS: Survey Receipt.
b994d4a9-bafd-47cb-8a75-6d8e03b232f8 | signoff | AUTHORITY HOLDPOINT
8cd0f1b3-5556-4105-aa0e-8122818a07c3 | checkpoint | 5 - Pipe and Manhole Material Compliance
8574b7e9-1f5b-55af-a249-022f6bbb5809 | note | ACTION (Hold, Monitor, Witness): H
4ae29bd8-3a57-50ff-8c15-a67c18995e44 | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
89e1cb9c-f1f5-50f2-a312-8bd6520c0182 | note | FREQUENCY: Prior to commencement.
3d671959-435c-5ca4-afcd-111bd3050b08 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
df82a6d0-b962-514d-8c4d-485ef3383da8 | note | CONFORMANCE CRITERIA: Pipe shall be
1d7e24f3-698c-52c0-a133-30da9952f152 | note | ○ Check for freshly formed pipes and return if required
3d49fc7c-dba3-5dbc-b5f0-32abd5441079 | note | 1).Class 4 RCRRJ pipes AS/NZS 4058
2f099718-12a8-5c2a-b3c9-e5fdaa67a9e5 | note | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
490850e3-5dfc-53f2-aae5-65c5b7f8a400 | note | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
3c4fb740-b2f6-515c-a3ea-329e313cad40 | note | ○ Prefabricated concrete Manhole shall and street catchpit be in accordance with TDM Standards
8e6770f0-2c82-57cf-b011-0cd32354d5c4 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
ba717dbd-cfbc-4058-80ce-d17f4e04d6f0 | signoff | AUTHORITY HOLDPOINT
b5018eb3-cc36-4a55-bfbf-12866204f990 | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
6a66c9c2-ce89-5b3b-a05d-9058b53b1b6b | note | ACTION (Hold, Monitor, Witness): H
fe3b2260-a7c1-5610-925f-78183e712f43 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
c0263ffd-4df6-586b-b471-86e05eccf300 | note | FREQUENCY: Prior to commencement.
b822d88e-4fa4-5e4f-a59e-d5894c0a5268 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
dd36ce3c-31b5-5356-8b3f-503c7555b341 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
f5aa9e3e-b878-5569-9caa-0744a27b0726 | note | RECORDS: As-built Drawings. Doc. Review
a5bdbf94-3f09-4c0f-a7f8-dd3afca3848f | signoff | AUTHORITY HOLDPOINT
c78b9fce-1702-412b-93e0-d25ced45cb34 | checkpoint | 7 - Trenching & Excavation (1)
a01de89c-9b25-5a58-b24b-44e3f5c5285f | note | ACTION (Hold, Monitor, Witness): H
5f4d6137-63e5-53fd-addf-260b2326c0a2 | note | DETAIL: Excavation methodology
7a67030f-5c95-5de6-8465-48ef3a0e6ca8 | note | FREQUENCY: Daily
41dc63a0-bc53-5a49-9fbd-302192e5902c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
a6e3a9e7-61d8-57f5-a020-fd13ba634f70 | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
9e1b027b-d5b6-56b9-925c-9469beb6154d | note | RECORDS: Prestart RCP
95404310-cac0-4816-b303-282700f45217 | signoff | AUTHORITY HOLDPOINT
ac340d7f-e634-4f97-bbf5-edcbdd07c9d5 | checkpoint | 7 - Trenching & Excavation (2)
4f023cc8-147f-54b8-b496-4790d64ea92a | note | ACTION (Hold, Monitor, Witness): M
154b6ef4-a861-54fa-b06f-d0143313a604 | note | DETAIL: Trench Profile - Width
98b96253-d21f-5a30-a29c-7809e4fa2867 | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
29b76b05-c7d0-57d3-bf7a-266201263d06 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
2b57b7fa-f592-56ce-86a8-e0c866624e90 | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
4382499d-37ba-5672-b182-b7d2dbd47836 | note | RECORDS: Construction Photos
43499c05-b041-4bf6-b229-417f2bf4a9da | checkpoint | 7 - Trenching & Excavation (3)
c8e6d4a9-0ffb-5044-9ddc-deb0c42c8c8c | note | ACTION (Hold, Monitor, Witness): W
fdbbad33-6a09-5463-bc21-e23534b85dce | note | DETAIL: Trench Profile - Depth
5336eabf-c79f-50df-8abe-c219c73678fc | note | FREQUENCY: Daily / as trenching takes place.
ffbf17f8-d70a-52e3-878c-72fbafa711db | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
a9e92e9a-9b9b-56ce-b658-71b70dc69107 | note | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
bcee69d9-3788-5c1f-8dbb-0a72575ab56a | note | RECORDS: FH Drainage Line Record / Construction Photos
b0fffa56-5e15-4688-8611-9361f22226c4 | checkpoint | 7 - Trenching & Excavation (4)
4bbc802e-bd4f-5ddd-a07e-a009276b081e | note | ACTION (Hold, Monitor, Witness): M
1f512086-ae2c-53f2-bfa0-a6946e952806 | note | DETAIL: Trench Base
d94fce74-7766-5409-8d39-9b8727f3abbc | note | FREQUENCY: Every 10m
3d52b694-4fb9-56cb-8b04-dccc660315b4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
29d5115c-5ca2-5554-82af-0e2f173e802b | note | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
6271a564-7082-5b83-8332-a2a42c0970d4 | note | RECORDS: Test reports / Construction Photos
49b6c693-8e7b-4f1e-879f-9188e4620744 | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
59275c1f-e172-543b-aa9d-4c368fa0d667 | note | ACTION (Hold, Monitor, Witness): W
72dd3125-1298-55e6-a34c-4e4f71c84df1 | note | DETAIL: Placing and compaction of Bedding Material.
00e2157e-16cf-5f37-837f-67e2f1d5d0d6 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
2b733bc7-3944-545f-98e5-a614060689f8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
15d56c96-4ec7-527d-ae63-48ae0dc26b5c | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
23f944a7-ec6b-5650-b49b-93dcd719357e | note | RECORDS: FH Drainage Line Record / Construction Photos
26a083d5-d95c-46c7-bd44-3eb77ebee405 | checkpoint | 9 - Pipe Position Tolerance
4ced8122-11fa-5e6e-ab48-9aceca728f95 | note | ACTION (Hold, Monitor, Witness): M
ec89f7aa-a50e-5451-8d87-5fdcc037b93c | note | FREQUENCY: At any point of pipe
18fd97e2-0721-52e5-b4dc-5322d4bb8f40 | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
b6325ebb-6d8e-5cae-9923-8358510618df | note | RECORDS: FH Drainage Line Record, Survey Data.
e73d7143-ba44-4749-b3d7-795efa6bbf98 | checkpoint | 10 - Trench Backfill - Placing & Compacting
a339a45c-677c-57de-8859-9e0831256e3b | note | ACTION (Hold, Monitor, Witness): M
3b4449cb-38b0-5ec3-8e22-ba30298d0a56 | note | DETAIL: Placing and compacting of Trench Backfill Material
a2a02160-ced0-512b-8aeb-f11398024c40 | note | FREQUENCY: Throughout Trench Backfilling operation.
8806a125-f880-58cc-8424-6c990d6b237c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
7a61e0a0-e0ab-52ab-9494-35ccb516030e | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
ae3a5733-8cf8-5567-968c-81db6f2b46cc | note | ○ ATAP40 for subbase/basecourse.
b80373ae-8b20-5ee7-9ca3-a6e9de25c3d4 | note | RECORDS: Construction Photos
b0a2c42f-1fa3-47c6-903f-9fabc58b960c | section | Subsoil Construction
7f7cacad-ceb1-4f09-8f0c-2a095376eed6 | checkpoint | 13 - Subsoil Material Compliance (1)
3e8a5026-a9a0-5a9e-997e-7af13e75b503 | note | ACTION (Hold, Monitor, Witness): H
9ca831bd-7c0b-5c3b-8054-129932244275 | note | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
7ece00fc-d8ee-5fd2-87b4-343ccf0177db | note | FREQUENCY: Upon delivery to site
d23bf396-4466-5177-8431-56be1eabc7f7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
5b30ce45-2f33-56a1-b98f-759f4f1c4843 | note | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
7238e6df-3cac-526a-828f-298e8147bee7 | note | RECORDS: Delivery docket
b7637f1b-2c04-48bb-92d3-605517a43a4e | signoff | AUTHORITY HOLDPOINT
4a385dee-b01d-4359-9c25-b23ebc88d513 | checkpoint | 13 - Subsoil Material Compliance (2)
074f45ff-db44-585f-a34f-b3e32a6edad9 | note | ACTION (Hold, Monitor, Witness): H
563ee7db-8a35-5e2a-a37b-6e60eab723c5 | note | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
ebdb23dd-4a2c-5c99-bcc3-cf2b2b3a99a7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
29794297-2194-51f4-9798-2aef1ce3db29 | note | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
134d2bae-7503-52b9-981b-d2a152dfe643 | note | RECORDS: Delivery docket
cba2f640-3faf-483a-9a40-017b4878a6b3 | signoff | AUTHORITY HOLDPOINT
85ebbc39-26af-45bb-ae8c-f2ae9ad6b640 | checkpoint | 14 - Trenching (1)
b9ced2af-3196-50e1-81cb-75e93b681e6e | note | ACTION (Hold, Monitor, Witness): H
424aab2a-be58-5125-98ff-0047b8bc5535 | note | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
468cc67c-8188-5eeb-ba69-40e2d6ae9076 | note | FREQUENCY: 10m intervals
16cd342f-4c95-5e54-8a29-61d4b9aac128 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
90425af1-4022-5a80-b4c6-94621d464328 | note | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
23f31a4e-564a-5a02-aa16-b7be567f7203 | note | RECORDS: Photo / subsoil log
220543f4-a910-4569-bb69-23b44ccd2a00 | signoff | AUTHORITY HOLDPOINT
3d50acf3-d384-446f-818f-5a7f18650448 | checkpoint | 14 - Trenching (2)
2fc877f3-98b0-5a08-a7ed-ab83b39a361b | note | ACTION (Hold, Monitor, Witness): H
7ff686cb-4a48-537a-8fb6-c4a6ec399b7f | note | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
90d603e0-e951-5abc-ba41-ecbca40eeb40 | note | FREQUENCY: 10m intervals
3adb2e58-44ef-5394-a0db-31fb7f698c04 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
a16db5c5-9079-58b7-bc0d-e29ca5026b0a | note | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
87bf8dc8-9d4d-5790-9ff2-baeca6f751d4 | note | RECORDS: Photo / subsoil log
183f4dc3-8bcd-4976-b5bf-e6609f9a3d67 | signoff | AUTHORITY HOLDPOINT
6580f2ca-845f-4233-ba83-b4889dedd2e6 | checkpoint | 15 - Bedding, pipe installation and Backfill (1)
68e0e611-45c2-52d1-a2d6-07d3d81a0015 | note | ACTION (Hold, Monitor, Witness): W
f62eb732-d75b-5559-a30b-52b5fd549641 | note | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
675db98a-d46c-5beb-b740-5583da25ec0b | note | FREQUENCY: 10m intervals
7dbbf5fa-01e4-5acb-bf57-4f7ed2153acb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
a524f1e8-ee7e-5b68-a649-6c7dd4e696a9 | note | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
4124ec75-cc89-549e-8fde-511bc25b5d80 | note | RECORDS: Photo / subsoil log
20703764-cf76-4a3e-8624-756ad93cfcac | checkpoint | 15 - Bedding, pipe installation and Backfill (2)
10b39fee-7f4e-5d6a-83ca-30c4c7607e0b | note | ACTION (Hold, Monitor, Witness): W
43bf016b-0293-5053-9a53-6dec0778102f | note | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
a6cc82f5-60e0-5f01-8355-53bf74790064 | note | FREQUENCY: 10m intervals
b7d833f1-10f2-55f0-a773-573485fcfd2b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
2bff4f11-08c6-5832-b06f-487a4af04d56 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
61ad9339-2d42-5df4-a982-ff35a08c70da | note | RECORDS: Photos
3910c15d-e03d-4ef2-9d5f-91b4038918a5 | checkpoint | 15 - Bedding, pipe installation and Backfill (3)
1927adcb-d651-5e23-96f4-f8f3a370a0fd | note | ACTION (Hold, Monitor, Witness): W
3d360b93-d084-598e-a9f1-203d91084874 | note | DETAIL: Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench
3ff644ca-a70d-55eb-8b87-691e40c8cf44 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
7337da8d-8673-5020-b53e-247889450510 | note | CONFORMANCE CRITERIA: Ensure good coverage
5a27add1-8a75-5330-b1bd-bbf095fcce74 | note | RECORDS: Photos
74d90994-e5ae-4ada-ba30-81b3332f38ad | checkpoint | 16 - Catchpit Connection (1)
e4676f0d-8a35-575f-8bb8-99ffc3934afd | note | ACTION (Hold, Monitor, Witness): W
d9fa4823-16b4-550b-9fb5-d7be7331b00f | note | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
f00bafcf-4265-5f8f-8429-d9d43f751e4f | note | FREQUENCY: As required
69422a28-6dcf-5289-970d-659e2922e23d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3487a220-535e-5268-b379-f3ad1bd84a97 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
3e182e7c-c6da-5dc3-9ffd-431a086575f2 | note | RECORDS: Photo
01c49920-90a9-4188-9f8c-0c6357b680f2 | checkpoint | 16 - Catchpit Connection (2)
034bd0b8-8aad-54ff-a1ca-e3388a4c3c7d | note | ACTION (Hold, Monitor, Witness): W
0523c64e-76e7-57e8-bbca-6fc4bb78f256 | note | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
b38c23c6-1834-5413-a78b-736b677ff9d7 | note | FREQUENCY: As required
23fc5d84-c31c-55e7-b0b3-90787d65dc1c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
af632cb0-d1f2-5d4b-b7e6-0d9de2faae17 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
8b02306e-0b98-5437-a622-ca5b4c591e9c | note | RECORDS: Photos
53bd30e5-7674-4b07-b9c1-e2c40473c01b | checkpoint | 17 - As-Built Drawings
90f0a0ae-9c83-5ef7-94d8-fadc21bc4532 | note | ACTION (Hold, Monitor, Witness): W
719fde6e-a1a9-53a8-91ef-e23ea7f1aa89 | note | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
82222917-9428-5d27-a58c-966857fd9f0e | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
1b5121f1-29d3-5a5d-a567-88d611e27803 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
149d8077-64d2-5cab-83fd-03fdc301fa07 | note | CONFORMANCE CRITERIA: As Built and GIS Data
887b4156-249c-5f3c-82a1-db9e8d440627 | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
a49d476a-c4a0-413e-83f2-8b9742bf30cc | section | APPROVALS
f3d687a2-88a3-4787-b01c-fe9d691147d8 | checkpoint | ITP Approval
6284d6c3-5c21-5c8d-b5f9-62df79245555 | textbox | QA checked By Quality Manager:
3c7991c5-28d9-500e-9909-dc97810f2a90 | textbox | Accepted By Engineers Rep:
c75aabc6-4938-483c-a83e-e568dc9223e4 | checklist | ITP - Opaheke/Chapel St - Traffic Islands | itp | ITP - Traffic Islands | 84a37c26-f2f9-4b6b-9ef4-e32f59f34279
5ebd57bb-4c9c-49a8-aae6-554b2b1b112a | section | Materials
92ef314f-bb5a-4b52-ad8d-272ec0fba7c6 | checkpoint | 1 - Mountable Kerb
c4575a77-ca3b-5f1c-8b06-9fe18b9b500e | note | VERIFICATION ACTIVITY: QA FORM
1726423c-967a-56c2-a8d3-0835a068e5cf | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001
09c93a61-eb98-5aee-834f-808b7e3bde42 | note | FREQUENCY: Each Island
209a133b-8de8-5a12-8486-88f8b3ab0b3a | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid (Stick-on with epoxy mortar on structral AC20)
cf5f08f8-f667-5aaa-8809-e5c7ee8d2a6c | note | HOLD POINT: Inprocess Inspection
0a5a4a6c-921b-5942-8008-183cebac1171 | note | RECORDS: Photos.
aed57717-a925-57b7-912c-2fee5ed52ac5 | note | ONSITE RESPONSIBILITY: Site Engineer
0085283d-f5a9-4bb8-8d4b-c345e2e35da7 | section | Construction
0468fe3b-539f-400e-bf9f-a1aad0e6fb12 | checkpoint | 2 - Survey Setout
49cecaaa-22ea-5314-b158-bf0a68d9d89f | note | VERIFICATION ACTIVITY: Survey
922a1bb6-547f-58b1-87f8-c90eb6ba35c7 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct as per design
df693511-a2f1-55e3-adac-f95767e5e1d7 | note | FREQUENCY: Prior to commencement.
b76ebc40-e278-5869-a29a-0d712a4871d0 | note | ACCEPTANCE CRITERIA: Survey
3bf39ae5-8f0c-5946-9bc8-644ba398fe9f | note | HOLD POINT: As per Construction Drawings
bf637741-2c19-5875-9756-eee2fc745d34 | note | RECORDS: Survey Receipt.
6259fa13-643f-52b4-9159-18aeb6fff89c | note | ONSITE RESPONSIBILITY: Site Engineer
692f0da5-50f4-4941-b9f6-5f6f8fec63e0 | checkpoint | 5 - Concrete Infill
15ba6067-c25a-5997-a48a-21fd2a210df3 | note | VERIFICATION ACTIVITY: QA Documentation
16cb7283-ad50-5180-91c0-f0ffa1044bc4 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
9d564300-7612-5a33-8110-628c0bf5e9c5 | note | FREQUENCY: Each Site
25a9b844-9ac3-5821-8ff7-31149358a26a | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 6 kg/m3 Red oxide
c1bde1c9-1fb2-53dd-91d8-50dab037cc2e | note | HOLD POINT: Inprocess Inspection
7fa3ea97-02a0-5c5f-b6b5-90dc69f63204 | note | RECORDS: Photos, Concrete dockets
2999d64f-6008-57be-98e6-df29811515b1 | note | ONSITE RESPONSIBILITY: Site Engineer
6c6fa3eb-b5fb-4090-97ef-57228a5868c8 | section | Asbuilts
2b5dcef5-513f-437c-9dd6-1e9f5cd523a1 | checkpoint | 6 - As built information
4562dd7d-1f8a-5e0b-a3f9-fdd2b47bc85a | note | VERIFICATION ACTIVITY: Drawings
6d7ff48c-3ba2-5eeb-8ae2-4e0f313cd694 | note | FREQUENCY: Every Site
6f41fa99-7fb2-5c77-8284-a8fa6d651290 | note | ACCEPTANCE CRITERIA: As built drawings
ecae2226-0095-548f-8bcc-6d3fc74af521 | note | HOLD POINT: In Process Inspection
8a255de0-dacc-5802-bf2d-8c14b820a934 | note | RECORDS: Asbuilt records
15bd9ed1-8d1a-5177-8e87-74fe789d5576 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
289c77ff-3ef7-4f91-be51-9bc7f32c32a2 | checkpoint | 7 - RAMM DATA
e80ea077-fc97-5a1f-a812-891c58a38b8a | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
c744f2e3-4f46-5e45-8ebd-2d1887f82989 | note | FREQUENCY: Every Site
dbfdd63a-6d0d-51e4-ae4b-15b7170cdb94 | note | ACCEPTANCE CRITERIA: RAMM SHEET
2182ca6e-d540-53d4-bf45-8a4ccefc1a80 | note | HOLD POINT: In Process Inspection
6d500722-b8b6-5c22-954d-eeba01b302f4 | note | RECORDS: Asbuilt records
27ea159a-776e-5116-a554-e55bdba61c40 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
b27cd915-e1ac-4e18-b63b-bca57d9f341b | section | APPROVALS
a034304f-c4fa-4093-9a56-512df8fec0a4 | checkpoint | ITP Approval
6bb3efee-b108-5bb2-8c65-d714ff70cb63 | note | Prepared By: Ajithkumar Ayyanar
9de58997-754c-550d-a414-359e9ce475a2 | textbox | Approving Delegate:
95f519eb-7bb3-4d7b-9096-5041f01bce06 | checklist | ITP - Picton Street and Ridge Road - Enabling Works - Footpath, Kerb and channel | itp | ITP - Picton Street and Ridge Road - Enabling Works - Footpath, Kerb and channel | 5559d5c4-de66-44ce-95e7-95282f0e3ec7
2a896c85-185c-4318-ac10-b2e01bb2dd9e | section | Site Set Out
df6c1d9e-fa55-4591-aa53-cb070449d357 | checkpoint | 1 - Site Set out
ac6f8060-e748-58a1-8adc-4ec4fb6dd165 | note | VERIFICATION ACTIVITY: Surveyor
49bb53b8-fd5e-5df4-b198-40dcb81dc6b1 | note | METHODS OR REFERENCE: Surveyor
c5d88320-f85e-524b-a921-d15a18598ce4 | note | FREQUENCY: Every site
38aea417-7d5a-5a2b-bca1-da3479b632cd | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
a1e2caac-279c-509e-8719-35b0e4754039 | note | HOLD POINT: Mandatory HOLD POINT -
fb3674db-0567-5beb-9804-ee01f07cc433 | note | RECORDS: Onsite records/photos
d9ceaac8-cfea-504e-b9bd-38ef463ea22f | note | ONSITE RESPONSIBILITY: Site Engineer
c78ef98a-d6c2-42fc-ac2b-a8c288d277c0 | signoff | AUTHORITY HOLDPOINT
f70a6533-374c-4af8-92b1-dc148e87ef87 | section | Materials
6ce6c2c4-58bc-48e9-84c5-cff184b7b86f | checkpoint | 2 - Kerb & Channel
f571e1fa-47ab-58a0-9fd6-f0c16ca307e8 | note | VERIFICATION ACTIVITY: QA FORM
a8750c00-14c6-568f-b2fc-3e5be304dcc4 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
5b163089-2bf2-5fd3-aa3d-08287f669505 | note | FREQUENCY: Every site
82b2ee2a-90e8-574c-a393-20e09c3bcf58 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
614a79d5-e49f-566a-9e6a-527bcff37d7f | note | HOLD POINT: In process Inspection
c2dfc18d-ca76-50cf-ac29-53bb3128de5f | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
5c233ced-8f42-532d-9821-95a2bc67b778 | note | ONSITE RESPONSIBILITY: Site Engineer
1dc1e396-f18b-484e-a25f-dd25180e0912 | checkpoint | 3 - Channel Level
e8a26672-9b4d-5e92-9c32-0d5afb691ca0 | note | VERIFICATION ACTIVITY: QA FORM
1f467cf1-0d8c-5450-a182-ca5e125d75d3 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
48508549-d26e-5616-945f-1a440f99e38c | note | FREQUENCY: Every site
3da4256b-d367-5a33-9976-da5027a1b436 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
d8c7d5e2-b032-5ac8-a340-801caddae83f | note | HOLD POINT: In process Inspection
89d36a1e-1fb5-595e-9261-816b8c7c56ee | note | RECORDS: FH concrete QA sheet
cedb04d2-3429-5f3f-a808-a7f1489512d4 | note | ONSITE RESPONSIBILITY: Site Engineer
a7941f0d-5c81-4a31-bb88-56e2920d8be7 | section | CIVIL WORKS
55414bcc-41b2-49cf-8426-d459d0035782 | checkpoint | 4 - Concrete Footpaths
f9dcdb0b-1796-5548-bf30-262d92006adc | note | VERIFICATION ACTIVITY: QA FORM
c1c1a8ea-aa57-5d86-a5cc-bdaa2ade61fa | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
26a9b818-3cc0-5bc5-8564-5d759451e302 | note | FREQUENCY: 10m Intervals
247928ed-10a3-50c5-b5cc-805deabd43e3 | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
9c0749e4-3d3f-5aa4-baef-e67b95746485 | note | ○ Clegg CIV > 12
9295645d-803d-52a1-b9a2-f4acfe360a8e | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
20308bcd-22f7-585c-8fae-7cf5e0aea6fe | note | HOLD POINT: Inprocess Inspection
4d89e3df-3386-574f-89a0-fe8adf2764ca | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
c2971eb4-f722-5503-b530-98864db8e375 | note | ONSITE RESPONSIBILITY: Site Engineer
780f8f8a-9d8b-4a56-8b4a-95f88d8765d2 | checkpoint | 5 - Tactiles
90a97913-484e-5ba8-87dc-1ac12c0dfa77 | note | VERIFICATION ACTIVITY: Visual
15d7bfb6-afe5-5d90-8a8b-80c69f36fa7f | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
7ca41f35-e7b1-5240-9ad7-408186da36a7 | note | FREQUENCY: Each PX
192cda0f-bd5d-5e61-ac68-2e06d49dacfa | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
b1271f57-6ca8-5671-afd1-b4e6462de362 | note | HOLD POINT: Inprocess Inspection, Measurement
96461d9a-988c-5c57-9ef0-4454b81eb839 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
6a08e670-6741-59cf-9890-025369a8eedd | note | ONSITE RESPONSIBILITY: Site Engineer
9e9f4a40-3d46-4006-adbc-a9ae2871c7a5 | checkpoint | 5.1 - Tactiles
c76dd92c-517d-551b-a1db-4d05e1950369 | note | VERIFICATION ACTIVITY: Visual
d29b59f8-97c9-5f92-a632-9a681d13bfdd | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
99d4ce03-1375-589e-a04a-1ed78f1e0b04 | note | FREQUENCY: Every site
81d75167-8722-5ba8-b779-eb09dee76e8d | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
c586102a-fbe0-5782-9f32-14c75480f439 | note | HOLD POINT: In process Inspection
e3f63d30-cdda-53c5-9a7e-6bc30b0d4e4a | note | RECORDS: Photos
57f25c38-e7af-5de6-9f59-48266160b044 | note | ONSITE RESPONSIBILITY: Site Engineer
510457d5-5c8b-4b8d-9000-3a0059588d03 | checkpoint | 5.2 - Tactiles
49663ad3-183b-5101-b5af-cd4d4940f8c6 | note | VERIFICATION ACTIVITY: Visual
d0b7985d-6ff2-51f6-ae02-822c90f9be4d | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
da9c8f62-45da-52e5-afe8-90a88edee66f | note | FREQUENCY: Every site
ff876a49-e8b4-5db7-904c-87108c37f2f3 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
0ec64bab-d32a-5bc5-aa13-03a345b56ebc | note | HOLD POINT: In process Inspection
d77d019d-edff-54d5-840c-76d2b3072420 | note | RECORDS: Photos
52a13628-e50a-50f1-9908-5f81aa1c4672 | note | ONSITE RESPONSIBILITY: Site Engineer
3c7155e7-f0c8-4db9-8271-a81841934ed5 | checkpoint | 5.3 - Tactiles
e08cafb7-aec2-5a98-99ac-b0f0e851c450 | note | VERIFICATION ACTIVITY: Visual
df8084ed-095e-5a1a-9ec8-4db5d0a5911c | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
8a8f4fda-3b16-57a2-a6ba-93d6f890fb37 | note | FREQUENCY: Every site
5713d4c0-97d2-51e0-8f99-0e3bb9228e30 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
2cfd6852-4c40-5b8b-9fcb-4ff5afe1eb76 | note | HOLD POINT: In process Inspection
81f17ae4-588a-5224-9817-5df1d745aaa4 | note | RECORDS: Photos
a9af9d6d-9943-52c6-837a-848d6a5ba370 | note | ONSITE RESPONSIBILITY: Site Engineer
5b9c463b-227b-43f8-a01e-4be0849f8f0d | section | RAMM DATA
67a692a2-d49f-4d14-a9e8-ec26e3101d33 | checkpoint | 6 - As built information
4ec8e029-3f16-5a36-9b39-c23c9920ec89 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
0234daad-2bc4-51cc-b9a9-52816f7fb4c4 | note | METHODS OR REFERENCE:
625da771-e28a-5560-8da6-0a6d45de6150 | note | FREQUENCY: Every Site
03773f61-54b3-5ad8-a0bf-df951aef77de | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
a9843e30-abe7-5771-9b54-5c1573b3f9b0 | note | HOLD POINT: In Process Inspection
4d772c73-2a76-554e-803c-4cd5faa3ad18 | note | RECORDS: As built records
e920a895-b1b3-5404-8041-95ba6e2f30a9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
e58ffae5-2d7a-4608-a8b5-81a6d4ed8a7c | section | ITP APPROVAL
595b8fe0-4943-47c3-a74f-e27e15d318ce | checkpoint | ITP Approval
e8c74388-d825-5969-9631-daca502c6954 | note | Prepared By: Divnish Chand
9059f76a-2ba6-5308-8b4e-0b328527d97f | note | Approving Delegate: Sumesh Sharma
6e547835-4044-4445-9167-4e957290a16e | checklist | ITP - Picton Street and Ridge Road - Stormwater Drainage | itp | ITP - Picton Street and Ridge Road - Stormwater Drainage | be5edfcd-5614-4956-9ee6-2cf93dbd0ed7
81c653a8-6364-4ad8-a1bb-890f6f59352c | section | Stormwater Drainage
d6d6b2cf-46b8-4d75-a681-0208531a8e64 | checkpoint | 1 - Permits & Services (1)
f5002718-c872-5196-87f0-52b97a1be120 | note | ACTION (Hold, Monitor, Witness): H
56b2b508-016f-5a4f-8288-a408e8b5c28c | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
05299859-656f-5a73-9cc5-43e210b32f42 | note | FREQUENCY: Prior to any construction commencing
26f29d01-dc16-5617-9195-b1a76cb5c574 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
814b9a77-5b6e-51c6-934c-f048dfa4c948 | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
7552f84c-fe75-5f8c-8b61-9ea94595b5af | note | ○ AT Access Authority approved and signed by RCA Authority
b8edb32d-20c4-519c-8519-404ebb9cf8e3 | note | RECORDS: Permit attached or permit number noted.
ef4ef6fe-0830-4c30-a518-83a9e92f1f03 | signoff | AUTHORITY HOLDPOINT
811b38f7-9a5c-438b-aa53-d0606bad90c4 | checkpoint | 1 - Permits & Services (2)
041095cf-7426-542e-a1a0-c4fa4a3a6d9c | note | ACTION (Hold, Monitor, Witness): H
6f7c63f1-56bd-5329-8ff0-7b02b4dc8806 | note | DETAIL: Locate and mark out all existing services
14308c90-d7ad-5add-81b3-e14cf45b9290 | note | FREQUENCY: Prior to any construction commencing
6a9c3dc0-e7c9-5040-bd5a-309ff18ff17f | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
4264921e-768f-5ca1-a5c6-4288faea6a1f | note | RECORDS: B4u dig plans & GPR report attached
462d1a8c-96af-4940-b5d5-6e9ade4867ea | signoff | AUTHORITY HOLDPOINT
b3d88753-9d00-416f-a57d-825c647da261 | checkpoint | 2 - Pre-Construction Sign Offs
11ef4908-8416-5561-9b2a-62e073aad2c3 | note | ACTION (Hold, Monitor, Witness): H
59731494-5b31-588d-b852-e6636bb272ee | note | DETAIL: Sub-Contract and Supplier Agreements
51a665c9-9dc9-5bcd-bdbd-4dc206a53e2f | note | FREQUENCY: Prior to commencement.
44de8671-03e5-5bcc-a6b1-9ac5993f1866 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
96873677-3bf9-5be2-8e7f-864c87c60060 | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
5759bffc-fcde-5d13-a6d7-2b872470df38 | note | RECORDS: Subcontract and Supplier Agreements
2f08d543-1cdf-4a01-91f5-f2011ca47a76 | signoff | AUTHORITY HOLDPOINT
7e5eb5ed-7e28-4b4a-b258-ca63b3ace854 | checkpoint | 3 - Design
304d7d5e-9dd8-5e19-bdc4-ade4559b0023 | note | ACTION (Hold, Monitor, Witness): H
566fbcbf-85b4-51b0-92c2-4df458dfaa63 | note | DETAIL: Design is approved and Drawings are of the latest revision.
3bad969a-18ff-566b-82b8-482a374d2ec9 | note | FREQUENCY: Prior to commencement.
88d080e5-53c1-541c-bbad-8d52e76a34c3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
a924f671-6a0d-5fab-9005-0e677ad34d78 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
3f94e788-5dce-511b-ae5d-f724b99726bb | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
29ce5485-c63a-52a9-b33c-3c44accdc9a4 | note | ○ HOLD POINT of not issued to IFC.
72e5f484-fbf8-559c-b1cf-d618063dd35f | note | RECORDS: Drawing Register.
1c9ae687-faaf-41d4-92bc-834b0165187e | signoff | AUTHORITY HOLDPOINT
fb74a8d9-af03-430a-a438-cbf3e8d9def5 | checkpoint | 4 - Survey Set out
b68defac-7ab7-5672-8d9b-26ace1cc2262 | note | ACTION (Hold, Monitor, Witness): H
e964dd5b-9401-5973-b903-3d8335ca7e21 | note | DETAIL: Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
c6c432f1-c538-58af-83fc-04286ac2103c | note | FREQUENCY: Prior to commencement.
07618ee4-cd80-5f40-9604-267a3df1498b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
13ed5635-94fc-5fe6-9b27-ffaa79663a48 | note | CONFORMANCE CRITERIA: As per GHD Engineering Drawings: 12549626-CS07 & Set out files
5226e1c1-5e1a-5d1c-b0ea-cf2839bd6dd7 | note | RECORDS: Survey Receipt.
b67b712c-b1ac-43e8-a5fc-b597c4d24b31 | signoff | AUTHORITY HOLDPOINT
82555a74-a4db-4db1-9856-853a2b888bd4 | checkpoint | 5 - Pipe and Manhole Material Compliance
81b10187-fe44-58be-8d1a-91a2c240c078 | note | ACTION (Hold, Monitor, Witness): H
9d9e87b1-7534-5ac8-a341-2b6d96a17c38 | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
d423b02e-a40a-5d82-aba9-0b10869feeb4 | note | FREQUENCY: Prior to commencement.
b5c03782-d4b4-5e6b-af47-62558f5eec1f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
a7b5b555-8396-589c-91a8-1eb5f98d98ef | note | CONFORMANCE CRITERIA: Pipe shall be:
02714135-46e8-552e-b641-2732d722ccb8 | note | ○ Check for freshly formed pipes and return if required
dd0e5876-29ee-5d9e-a35e-168b8371079f | note | 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058
e506a87e-7b3e-5109-ba29-c51d80308743 | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
795975a8-09a8-5de2-8253-c1a0046b5be5 | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
99ec61f0-fac9-5ef4-bca0-5b449074021f | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
ebf469a5-93ed-5fcf-a9ab-521d2e191f41 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
3f87b4a1-6e1b-47ff-a8f8-faac0bc1b478 | signoff | AUTHORITY HOLDPOINT
ef6ebc47-0a03-43f1-8c88-34816bf7594d | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
aaafbb5e-ccfb-51eb-b446-936e4655bd95 | note | ACTION (Hold, Monitor, Witness): H
577b904a-5518-5fe6-8032-93db97d37874 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
8a6307c2-ab2a-5088-a663-86fa4909fdf1 | note | FREQUENCY: Prior to commencement.
7ce0e908-0ad8-5d46-9b02-5647dc384086 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
7bab7746-b50a-58a3-a492-d07eb7f66ca4 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
8850e157-04cd-5b24-8a2a-d01e944bb208 | note | RECORDS: As-built Drawings. Doc. Review
7f24368e-e4df-40bd-b9a9-bf863e24b7ff | signoff | AUTHORITY HOLDPOINT
66a770ca-cb9c-4e08-b796-2790079d1bcc | checkpoint | 7 - Trenching & Excavation (1)
31fde4b2-d23f-5084-afe4-b0b91f076337 | note | ACTION (Hold, Monitor, Witness): H
7cd27e3e-c7ae-560e-bf0b-4ff03c9849f9 | note | DETAIL: Excavation methodology
fe06a649-3409-5e67-8268-9fd123e001e0 | note | FREQUENCY: Daily
51ac1149-50c3-5b5a-b051-854f2904c4a6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
aca3448a-0e58-5485-83a8-ec1c4dea0971 | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
e8ede702-4374-5b5c-a746-4a306b2d375b | note | RECORDS: Prestart RCP
5505d47f-6219-490c-b44d-f91de47cca03 | signoff | AUTHORITY HOLDPOINT
c3d898f6-397b-4b99-aea7-6e47405e3a2e | checkpoint | 7 - Trenching & Excavation (2)
a9581c95-c43a-5912-a4e1-839aa5d67f95 | note | ACTION (Hold, Monitor, Witness): M
5ed16cc3-6d83-50b3-9305-c556f11c0911 | note | DETAIL: Trench Profile - Width
b15d5b67-6c31-5e28-9b90-582fe27edb4b | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
56c60929-9909-5276-8b80-f7b2812baf9d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
9687150c-cb10-5af7-8e65-421a13d7454e | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
1c7286bf-776a-5bbc-b655-5b0968bfcc91 | note | RECORDS: Construction Photos
37080c8a-724b-4bde-99e5-b79ac76c2e45 | checkpoint | 7 - Trenching & Excavation (3)
307a0542-fb01-5586-9659-4e9b9bbcc282 | note | ACTION (Hold, Monitor, Witness): W
61d21f31-85ca-5f9c-b90c-b2671e2b05de | note | DETAIL: Trench Profile - Depth
bd15cb42-e417-52ba-876c-acb8a15ece3a | note | FREQUENCY: Daily / as trenching takes place.
2bc60476-addd-52e1-98c7-3e7156ddd066 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
8a87f1cd-ff45-5e68-b316-703c01859a8f | note | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
aac954b3-6019-5999-8a51-a43e9509023e | note | RECORDS: FH Drainage Line Record / Construction Photos
13dd9013-06d0-4546-b5d6-8733a2c6fef6 | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
4992ac56-3a60-54a2-b9e6-0dcb2a7986da | note | ACTION (Hold, Monitor, Witness): W
b6b81d3c-2aee-59ef-be6d-d2d9ad98f079 | note | DETAIL: Placing and compaction of Bedding Material.
254270c9-5ef2-5b80-a73f-9b18c6438b74 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
13c182f3-4060-57bb-abe2-e6ba03be75d4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
6e68307c-b67d-5f5d-b7c6-0042f2ce29d4 | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
5ac81a26-5d29-5501-8de9-68d4820cfd10 | note | RECORDS: FH Drainage Line Record / Construction Photos
6b8a00ec-b180-4b14-a652-0a7b5467bd64 | checkpoint | 9 - Pipe Position Tolerance
ba7bf018-a054-5be2-b378-900e2423ff07 | note | ACTION (Hold, Monitor, Witness): M
16b768ee-f144-5c43-b57f-5b51d3477bff | note | FREQUENCY: At any point of pipe
af0da70f-192f-558e-b45e-2338599cf131 | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
d885a1a3-9278-5e97-9e10-edfae601ca40 | note | RECORDS: FH Drainage Line Record, Survey Data.
9180fc0e-61f4-43a7-a66b-1742e6a48d27 | checkpoint | 10 - Trench Backfill - Placing & Compacting
c9cefc74-c3dc-57a4-9361-bece3c3f081b | note | ACTION (Hold, Monitor, Witness): M
d79532c6-8583-5dde-aeed-1f003fd514ce | note | DETAIL: Placing and compacting of Trench Backfill Material
23131c1a-b72b-58a2-8214-182ddd365c09 | note | FREQUENCY: Throughout Trench Backfilling operation.
3377abe8-5b75-5a1f-a2f8-304935738aba | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
cd705095-34f5-5771-a603-faf8fdaa0e82 | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
ae17e622-fbec-5047-8214-3744418974da | note | RECORDS: Construction Photos
5f729d9d-5f71-465b-b246-f54d5a32526d | checkpoint | 11 - As-Built Drawings
2f75c4f0-675a-589b-95f4-ebbbcad99dab | note | ACTION (Hold, Monitor, Witness): W
1f7779f2-f1fa-549d-a4a2-a020dd11af39 | note | DETAIL: Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
2c6601b7-f321-57f7-ac60-707887e5f8e7 | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
2d8987fe-b199-5b09-a942-9d4d470f6243 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
652f2bef-2fef-58e4-9a31-3beea3d7f932 | note | CONFORMANCE CRITERIA: As Built and GIS Data
61c47306-f383-5563-acf6-097c82e911ba | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
4fc1254a-caef-4e26-8c05-dbcfaa1c48c3 | section | ITP APPROVAL
dce5df7b-0d34-4542-ae25-59a167fa87f1 | checkpoint | ITP Approval
86663de3-a27d-5c3e-9e8f-ca3112ff4d8c | textbox | QA checked By Quality Manager:
b7a86fb4-c13a-55d3-a735-0f007fbc2385 | textbox | Accepted By Engineers Rep:
bb93a3bd-e4ca-47da-a911-d4780706e4f6 | checklist | ITP - Picton Street and Ridge Road - Traffic Islands | itp | ITP - Picton Street and Ridge Road - Traffic Islands | 863aaecd-7de5-45f8-9104-c3797858f137
651a9f84-4468-49c9-8f01-065d8e497332 | section | Site Set Out
f5987bcc-5d57-4ada-8c02-f1c5673e1b51 | checkpoint | 1 - Mountable Kerb
d5f7d9f6-ecfb-5aff-87a6-dc1019ad7186 | note | VERIFICATION ACTIVITY: QA FORM
aabccdbd-75d9-5ea5-b159-81d353b90c04 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
a9fff952-e02f-5dc5-809c-c3b857f2bcd4 | note | FREQUENCY: Everysite
f226be4d-89bd-589a-8b36-02749d9fc2a5 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
d271637e-53da-5ffb-b1b1-1eff7548af95 | note | HOLD POINT: Inprocess Inspection
f6bf604e-65fd-5a8e-9609-4c079e41c810 | note | RECORDS: FH concrete QA sheet, photos.
d06ed964-f420-59a7-9868-4385e0a33d99 | note | ONSITE RESPONSIBILITY: Site Engineer
bc250e27-9257-4860-a044-7e8aef75c873 | checkpoint | 2 - Survey Setout
b24a9ca8-a360-56e6-b1f9-850d2304993d | note | VERIFICATION ACTIVITY: Survey
85e74177-8885-51a0-9a1c-29cd8f85b93c | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
ce49747f-9f1d-5e5e-8132-2ff92b457034 | note | FREQUENCY: Prior to commencement.
a154cf9e-11fe-5bba-bb24-d6adb628d322 | note | ACCEPTANCE CRITERIA: Survey
6205fb97-2dbe-5fa3-9746-5da248b1833e | note | HOLD POINT: As per Construction Drawings
e29c60a4-1d35-545c-86c1-6acaba38fd8e | note | RECORDS: Survey Receipt.
c44913da-1b9b-5b16-8a01-8d96484a4301 | note | ONSITE RESPONSIBILITY: Site Engineer
b1f41847-c96f-4203-9079-203cfef2597e | checkpoint | 3 - Concrete Island (1)
26ed9d2c-c9e8-532e-a4d3-56e25a658e95 | note | VERIFICATION ACTIVITY: QA FORM
06df4662-3706-5edb-8cb9-628eea01abd5 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
b72ed669-f356-5e42-a249-c842de03c55c | note | FREQUENCY: Each Site
867e089e-075c-5830-820a-c635f162ccf0 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
4c41a451-7b1f-570e-8336-b758e189bfd0 | note | HOLD POINT: Inprocess Inspection
d3bbfdbf-41db-53f2-a44c-eed0deabe929 | note | RECORDS: Photos
8ae7e66b-49b4-5c0f-a516-3c16afd80fad | note | ONSITE RESPONSIBILITY: Site Engineer
9effef1d-b5ac-4b70-a038-149698cdc740 | checkpoint | 3 - Concrete Island (2)
7bedd219-8b34-5b69-90b3-a09bab29671d | note | VERIFICATION ACTIVITY: QA FORM
08ccdd0d-f5ea-5094-b377-5e13b951c629 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
50983022-c5ee-506b-bf46-a0155eff7511 | note | FREQUENCY: Each Site
872a67ac-fc45-5b01-80c3-1170f1d5561a | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
14e16f5a-fbdf-53a6-912c-821de31ad96f | note | HOLD POINT: Inprocess Inspection
1c7ea15e-f7aa-560c-bb91-9601448c25f4 | note | RECORDS: Photos
64cce006-0c34-585b-bef8-eeb30ae5221f | note | ONSITE RESPONSIBILITY: Site Engineer
42641bf7-ca10-451f-9780-3a213c28841b | checkpoint | 4 - Concrete Infil
a53c5696-469a-5d37-adeb-232bd9061b76 | note | VERIFICATION ACTIVITY: QA FORM
c23c9554-3b1f-532e-b603-d94a45361f6f | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
afe8d2d1-397a-5a3a-9da4-7553d722e767 | note | FREQUENCY: Each Site
c6446d5d-04e1-597e-816c-670d800928b9 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide
9e476ae3-eefc-5f13-9e3c-c6f0d79b0725 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
8d726923-9e94-59bc-b480-59e4467b1bdd | note | HOLD POINT: Inprocess Inspection
3e181790-8d85-543c-903b-cee21e5aef2a | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
52226f7f-51bb-5517-9366-2a9b271e70e7 | note | ONSITE RESPONSIBILITY: Site Engineer
2da6ee29-0391-471a-a7fd-6795d873fc91 | checkpoint | 5 - As built information
b4cad1e9-63b3-5f1c-87ff-000bc3c23c6d | note | VERIFICATION ACTIVITY: Drawings
9e090790-d208-568e-a8cf-f9cd0642de95 | note | METHODS OR REFERENCE:
19c9059f-bb6b-55a1-aa85-13a90825b013 | note | FREQUENCY: Every Site
433f5a18-4d24-5353-a412-0db1ee5afe0d | note | ACCEPTANCE CRITERIA: As built drawings
a2dddf7c-d100-564a-a77a-86224e9a8148 | note | HOLD POINT: In Process Inspection
af6601ce-1673-598a-9092-7b517d38a70b | note | RECORDS: Asbuilt records
420d4387-e24a-57c8-9388-f479d0de2771 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
692eb733-cf84-41cf-9ff1-a105aa9122f6 | checkpoint | 6 - RAMM DATA
6a7f30d3-038d-56d4-862f-9f1ba856d6ea | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
64fdab50-5c39-5972-8b24-c1f2609bb189 | note | METHODS OR REFERENCE:
12f209c3-a47c-5441-938c-ad84f520836f | note | FREQUENCY: Every Site
c3f2fa48-7aa5-5c32-91bb-4231c5897efa | note | ACCEPTANCE CRITERIA: RAMM SHEET
fc1f9d53-141c-5ae3-9205-5fe92269c287 | note | HOLD POINT: In Process Inspection
b681eaa2-36d1-54e1-909c-927efb1c8fb2 | note | RECORDS: Asbuilt records
75257508-b815-50f1-97c9-b7517a7cab2c | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
42386ab1-68b9-44aa-a892-5a8fbe229299 | section | ITP APPROVAL
ef4e8794-8fcf-4dea-bf7e-ed7a1d99d84b | checkpoint | ITP Approval
193e65de-3081-59c3-8d29-02bb464c44ab | note | Prepared By: Divnish Chand
ca56d593-28ee-5eb0-80ed-228a502cb190 | note | Approving Delegate: Sumesh Sharma
75b389f6-7c5d-46a8-be12-19105967b65a | checklist | ITP - Richardson Road / Owairaka Speedtable - Concrete Speedtable | itp | ITP - Richardson Road / Owairaka Speedtable - Concrete Speedtable | f55569a7-1b18-4f49-8814-e32aa4a669ae
d7f9c4c8-307a-46ae-bcc7-57c8de40ba4c | section | Materials
f6920277-06cf-49ce-a52a-a2bf8b008a0f | checkpoint | 1 - Permits
5f3d0bf5-7f80-509b-8082-5e09ea03763f | note | ACTION (Hold, Monitor, Witness): H
c34b36da-4d01-5253-b9b5-a34d13d3eb75 | note | DETAIL: Obtain Permits
e2d5bcc0-e9cc-5aed-ab17-a4e3bdea8c22 | note | FREQUENCY: As required
d064ab53-04ea-583f-9334-b6cff894dac4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
f5d68781-ae6b-56ee-9faf-0d20d7a1ebb7 | note | CONFORMANCE CRITERIA: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
939035a2-ee13-58e5-adc2-cb69414ef319 | note | RECORDS: Permit attached or permit number noted
9d6a79d5-9ff3-4a77-8c05-ea907a919346 | signoff | AUTHORITY HOLDPOINT
6a48a256-2575-47e0-b32b-67a516560c96 | checkpoint | 2 - Pre-construction sign offs
7ebcb0ca-0972-5bea-ab30-93d18135182c | note | ACTION (Hold, Monitor, Witness): H
99843840-68a0-5f4c-8419-3d337512901f | note | DETAIL: Ensure that Sub-Contract and Supplier Agreements are signed
a495ad04-bd3c-5257-97d1-69e518231da8 | note | FREQUENCY: Prior to commencement
f3ff7eea-3683-56dd-9621-c717c0b91950 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
fe6b9c53-ef36-5428-b548-ce7bcd29b3d7 | note | CONFORMANCE CRITERIA: Signed Subcontractor and Supplier Agreements
71924e6c-82fe-5d05-b7f5-52a9adc56f95 | note | RECORDS: Subcontract and Supplier Agreements
e6953b31-0094-4021-9852-d6d91a4bafbf | signoff | AUTHORITY HOLDPOINT
36b015c6-7c36-4263-8833-4f71d93809c6 | checkpoint | 2.1 - Pre-construction sign offs
7c15fb50-31c6-5817-858a-142eb4facc70 | note | ACTION (Hold, Monitor, Witness): H
f968dca7-b7e9-554f-b71c-43f973f63851 | note | DETAIL: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
f845700c-ced6-56a0-b216-796d50697776 | note | FREQUENCY: Prior to commencement
897e82fa-3cf6-559c-b5b0-9f4750c62363 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
b0ab4369-144c-536f-ae5b-4a446b3a55f1 | note | CONFORMANCE CRITERIA: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
5b7c95da-5860-519a-93ae-77960ea6765b | note | RECORDS: TMP on MyWorksites/On Site
fd1d9812-1bc4-4267-803b-3058375cf831 | signoff | AUTHORITY HOLDPOINT
550fd52a-1193-450a-aa59-81ab96bcc9c5 | checkpoint | 2.2 - Pre-construction sign offs
c3cb68d7-c9f4-5732-bd00-877032a5af9e | note | ACTION (Hold, Monitor, Witness): H
3dc90276-a9b4-5618-a18b-0d19098b7c19 | note | DETAIL: Ensure all Sub-Contractors and Suppliers go through FH induction
043e2bb2-96b6-577c-8f56-30146f723d98 | note | FREQUENCY: On site daily
c60c22ad-6921-5c03-ab08-24c5c0db73ab | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Induction
d5be64f9-20d5-5380-bacc-6251c8c3b3e2 | note | CONFORMANCE CRITERIA: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
8d030f54-e962-5860-a684-6a7e599618ec | note | RECORDS: Hazard ID and Pre-starts to safety team
d5ea4b68-2011-46f9-a57a-8562b972f7b2 | signoff | AUTHORITY HOLDPOINT
18a430b4-262a-4d05-8fbe-c37dada01756 | checkpoint | 3 - Design
b9c671a0-c56e-512e-a14c-1a105a8bf994 | note | ACTION (Hold, Monitor, Witness): H
2f5b1f01-a3ce-59ed-8be1-701ece3ba07b | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision.
1a8eef18-a39a-554c-b452-427ac4a37aa1 | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
ece0a64b-65ac-585c-aef5-5be02ea72533 | note | FREQUENCY: Prior to commencement
a467a3b8-d94d-549f-aa55-7bef4dd267f2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
bb1f4dfb-aa5a-5e10-8d12-d1a7301f5e02 | note | CONFORMANCE CRITERIA: IFC drawings have been received by Contractor
205944b0-d669-508d-b700-193f0d67c94e | note | RECORDS: Check Drawing Register
97921de6-8176-4b0f-9baa-a819f134c0c8 | signoff | AUTHORITY HOLDPOINT
8885cc36-05d0-44b0-8cb3-df6ede6da4ca | checkpoint | 4 - Installation of Erosion and Sediment Controls
528f85fd-1bcf-5a5b-a9ed-302768ff9b90 | note | ACTION (Hold, Monitor, Witness): H
f2b29de7-8721-5a42-8430-7094d41f759c | note | DETAIL: Ensure that Erosion & Sediment Control in place
64273957-3614-524f-8524-da37cc9d8824 | note | FREQUENCY: Prior to commencement
f7fbe46b-b76a-5c64-a0c1-056439f119af | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
dd93e635-9535-54a5-b4d0-e7e0e44e7da9 | note | CONFORMANCE CRITERIA: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
c9ca9a69-f52c-528e-afa3-e78cc3668542 | note | RECORDS: Environmental Controls Audit
5a6cac6c-5d51-40ef-93c8-33735e20147d | signoff | AUTHORITY HOLDPOINT
a2984c45-32c7-4a12-aa75-e78f97a1d3b5 | checkpoint | 5 - Survey Setout
8fafaa12-7027-561d-b7f2-7af5d0266b3c | note | ACTION (Hold, Monitor, Witness): H
154012c4-e10b-50bf-a70a-f9594abe5fbf | note | DETAIL: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
4e6a14a8-1e28-54d8-a919-6da4caec883d | note | FREQUENCY: Prior to commencement
eb951dee-5371-5cb7-8681-ac9238c4b634 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey + Smart Level
fc8bda2e-ffe4-5765-a5ae-b53ceb3f9c55 | note | CONFORMANCE CRITERIA: Consistency with Construction Drawing
38c50a51-ee3b-54f1-96d0-e2aee37eb0ba | note | RECORDS: Site Photos post surveying
e8d8530f-a542-4f94-9215-2c21712c98a4 | signoff | AUTHORITY HOLDPOINT
0cd5f8b9-6b88-4fd1-801e-8571e31900fe | checkpoint | 6 - Locate Existing Services by Hand Digging
0c333ad0-72e4-5180-bbb1-d672cd1c3cb9 | note | ACTION (Hold, Monitor, Witness): H
a4c25e32-1f2e-50ab-bf88-0b66b3f336ac | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging
8bd571b5-fd15-5642-a1f2-e2b5e38877da | note | FREQUENCY: Prior to commencement
24c403c8-c2d8-50ad-bae7-f1c9c8fc715f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
50373ce0-c4d8-5d2f-b3ea-421dcef36c36 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
a9b11ac4-b7e6-562f-b819-86a7333aae84 | note | RECORDS: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
ccd496d6-40c1-4f5f-b1d8-66a4e0079ff5 | signoff | AUTHORITY HOLDPOINT
02003ccc-3370-43c5-8f64-c33c007d429e | checkpoint | 7 - Material Compliance
358eca5b-9630-554e-83be-695e381d986b | note | ACTION (Hold, Monitor, Witness): H
4c5a8082-935c-56a3-bad2-dc134f0c0724 | note | DETAIL: LESA dowels to be used at all construction joints at 600mm clearance
e9818f2e-e6c4-50b3-9dfc-23b3af961ec5 | note | FREQUENCY: Prior to pouring concrete
eb68da3f-0087-55b4-bfca-419cbedfc65f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
e780f4fb-e29d-581e-93fe-cd3bfe7c2532 | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
0e618b84-e54e-53cb-b716-fee16b62bc26 | note | RECORDS: Delivery Dockets / Photos
1667e7f9-40a3-4f8c-b792-63b2f7f25046 | signoff | AUTHORITY HOLDPOINT
5e0415aa-e706-4941-87dd-7d2cbea3577b | checkpoint | 7.1 - Material Compliance
d84f2363-bcca-5f15-a0a0-6579da0ac57a | note | ACTION (Hold, Monitor, Witness): H
18bae8b3-c978-5909-8dc9-a397d416af6b | note | DETAIL: 0.25mm polythene layer placed across all surface area at bottom of raised table
c704f5e5-084c-535f-8818-53b6d52a364b | note | FREQUENCY: Prior to pouring concrete
4848e1d4-477d-5d37-93f9-c32f12545a32 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Document Review
aa21ef67-e10c-51bb-bb34-bed2b2b081b7 | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
e630509e-30d6-5f13-a92b-ca6ff05aff27 | note | RECORDS: Delivery Dockets / Photos
71d4c1d9-b72f-47b5-811e-49ab7f4aa6e5 | signoff | AUTHORITY HOLDPOINT
78724824-0340-45f9-b55a-9de078184ac2 | checkpoint | 7.2 - Material Compliance
f125cf34-3063-5b9d-8743-83f2f5a54a06 | note | ACTION (Hold, Monitor, Witness): H
e4e8f606-fbe6-5674-895e-d81bf39759b5 | note | DETAIL: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
0051447e-e9ef-51b7-9057-b925a33208d0 | note | FREQUENCY: Prior to pouring concrete
266aa932-8472-5f53-a108-76629b52ac37 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
69b50cf2-62fd-5c40-879a-f9ff914fbdd7 | note | CONFORMANCE CRITERIA: CIV >15
5c67a74d-df84-5ff6-a47d-8657fb68678f | note | RECORDS: Delivery Dockets
4d370762-b80e-40bc-9c01-a6dc3345162d | signoff | AUTHORITY HOLDPOINT
80683ea7-bbbc-4714-bbc5-10b8ef6be55f | checkpoint | 7.3 - Material Compliance
c64d5e1f-d282-5d16-8d9e-458df3239f43 | note | ACTION (Hold, Monitor, Witness): H
10d560e3-993c-55a8-8b74-dcdced92df03 | note | DETAIL: Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
24137c6e-ecf0-523a-ab64-09ec41f2cd42 | note | FREQUENCY: Prior to pouring concrete
d641fdfd-940f-56b2-acc9-028c768fb08f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
c41a2111-e149-521f-97d1-d6c5b878c31b | note | CONFORMANCE CRITERIA: Photos
c17a6ba5-3aa7-5660-a345-7efd0423d8cc | note | RECORDS: Photos
1be91315-e51c-4f90-9b2e-41424aead8c1 | signoff | AUTHORITY HOLDPOINT
ed523d28-edda-4e66-aa26-3fa8732350d0 | checkpoint | 7.4 - Material Compliance
f51dbe42-86fc-5e0f-8de6-dd3c7145ec22 | note | ACTION (Hold, Monitor, Witness): H
df676c45-8958-5972-9c78-ddb77e2bf17c | note | DETAIL: All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
4a4a4a3a-de7e-5713-a8f7-89448e8d418e | note | FREQUENCY: Prior to pouring concrete
04557963-51a8-591a-8391-bafa8fb3e38a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Concrete Delivery Dockets
7b9b637e-4842-5b8e-b222-a43d97961a95 | note | CONFORMANCE CRITERIA: Delivery Docket added to QA folder
8106c1c3-e54d-5c76-bbd8-590091aa531d | note | RECORDS: Concrete Delivery Dockets
74c58cb9-24ab-497e-afdb-1bfe3c9555aa | signoff | AUTHORITY HOLDPOINT
12bfcaa9-d635-42cb-892c-f3a8d944d2cf | checkpoint | 8 - Temporary Works (Formwork)
fd46fd86-2354-51b8-b6f3-6b71535606aa | note | ACTION (Hold, Monitor, Witness): W
ddc52418-bc2b-5871-94f1-81b06c9caffa | note | DETAIL: Formwork to be set to correct line and level
400f366a-2360-5be8-a544-84029b227559 | note | FREQUENCY: Prior to pouring concrete
b11c91aa-770f-5683-b5ec-13890b69537f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
fc78fc89-f283-5efe-a603-e25e1cb35b2b | note | CONFORMANCE CRITERIA: Concrete Inspection Record
cdc3d642-7d19-56f8-8702-3694e7ce7ad6 | note | RECORDS: Concrete Formwork Checklist
d6f8b031-1c68-4317-84d6-c8b5963d9c45 | checkpoint | 8.1 - Temporary Works (Formwork)
30eff3cb-e1a0-54bf-b641-bd9a65927fc7 | note | ACTION (Hold, Monitor, Witness): H
9429a496-e0b4-5c70-b2d0-ba7f094edeb0 | note | DETAIL: Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:30)
bc7fa2a5-d7d7-5166-ae57-8b9354191c37 | note | FREQUENCY: Prior to pouring concrete
04ccd0ea-71b3-5273-b0f3-9654a3854017 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
ab164322-cf46-5e2f-9235-9ca38505ea67 | note | CONFORMANCE CRITERIA: Designer to inspect formation level
6440e55f-8620-53e6-a30b-8340004baa8b | note | RECORDS: Site photos
9419ee67-e382-447e-99f8-603e2494feeb | signoff | AUTHORITY HOLDPOINT
4803fd4f-a168-47b7-8972-530d91f82f8f | checkpoint | 8.2 - Temporary Works (Formwork)
cb5f606c-bf00-5aa9-9a78-c5db31a88ac7 | note | ACTION (Hold, Monitor, Witness): H
f8fa59ac-4704-571d-b714-7d505c27ecdd | note | DETAIL: Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
d384c3d9-d8ad-5cd3-a884-60f0a38bfb1e | note | FREQUENCY: Prior to pouring concrete
17ca59bf-bc66-5499-a460-78fa1c316112 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
0deb149b-f456-50ff-960f-49f42f0ce542 | note | CONFORMANCE CRITERIA: Designer to inspect formation level
44562cd4-53aa-51f1-b46a-108934c5f3ae | note | RECORDS: Site photos
207dc35c-4b92-40a0-ae03-a24088d7fa0c | signoff | AUTHORITY HOLDPOINT
caad839b-de49-4a5b-9f3e-68e1bba5766b | checkpoint | 8.3 - Temporary Works (Formwork)
b2b971d8-467d-54a0-aef4-a5ca286e8db7 | note | ACTION (Hold, Monitor, Witness): H
d13330ec-626c-5a1d-906d-40fd36d121f8 | note | DETAIL: Raised Table ramps to be 1.15m across for entry and for departure ramp.Toe to be 0.5m to 1m across for both entry and departure with 50mm asphaltic wearing course
bfa33905-566f-501a-9fe2-700b5ab89c72 | note | FREQUENCY: Prior to pouring concrete
8e16ef74-e0cb-5d79-95b7-9082e5b0f542 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
6a5fd98d-c3fd-5191-9bd4-6a042fd92f7e | note | CONFORMANCE CRITERIA: Designer to inspect formation level
bf41467c-2f0c-5316-99e1-e2d0d3e37119 | note | RECORDS: Site photos
b56dc996-969b-441a-b883-f5aefb3252f0 | signoff | AUTHORITY HOLDPOINT
e5b01139-56ec-4c48-b88a-c4c7c163808a | checkpoint | 8.4 - Temporary Works (Formwork)
1f4ecfd3-f79d-52eb-84af-580c0da5fa52 | note | ACTION (Hold, Monitor, Witness): H
357dfdaa-2e9c-58d9-b611-8ff985a32384 | note | DETAIL: Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
41b34d73-ee0e-5ee2-abaa-401f1cc3dfdc | note | FREQUENCY: Prior to pouring concrete
26525ea2-c5ee-56f7-9f2a-e9af9610eef4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
78adcd2a-35f4-580f-b92f-945f28b08667 | note | CONFORMANCE CRITERIA: Designer to inspect gradient level
f64067b0-36a7-5ccc-ac08-8e63c0820c90 | note | RECORDS: Site photos / Concrete Formwork Checklist
8529141a-0140-46a5-b29c-f5ea35be98eb | signoff | AUTHORITY HOLDPOINT
7103d5ce-7da0-4563-b24f-8bd6bc152d46 | checkpoint | 8.5 - Temporary Works (Formwork)
6d479e9c-42e4-5bdd-9461-261ae15cfd17 | note | ACTION (Hold, Monitor, Witness): H
596d275d-9520-598d-99cf-1e7d423b0be4 | note | DETAIL: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
dc3d24be-8bac-589e-b67d-aa99c544d436 | note | FREQUENCY: Prior to concrete pour
de99a954-3a7c-576e-afae-164ebdd3ef78 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
dd786080-4bd6-5faa-a501-1423a10ad16a | note | CONFORMANCE CRITERIA: Concrete Inspection Record
c36a8582-6937-5387-b794-2fc92106fc1d | note | RECORDS: Concrete Formwork Checklist
b89d2ce1-4f79-4801-ac8b-264fa2f3871c | signoff | AUTHORITY HOLDPOINT
116e7d14-26c6-4552-b42c-b601f7c1d5cd | checkpoint | 9 - Reinforcing
61203745-7b33-5069-a46b-85f7caf97c9b | note | ACTION (Hold, Monitor, Witness): H
08ce9613-901c-5e4e-9a81-7e9a5a413b6a | note | DETAIL: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @300mm centres placed across the construction joint
b61ff6ac-f6a9-5c5e-8b71-a1de3e3fd650 | note | FREQUENCY: Prior to pouring concrete
ef7a0bc9-0bc4-533e-8c34-d8d563cfae87 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
812014fd-5a87-5760-ac9c-195df5509a1e | note | CONFORMANCE CRITERIA: Concrete Inspection Record
5eb93800-4e35-594f-b81c-de7c07976103 | note | RECORDS: Site photos/Concrete Formwork Checklist
55380bc2-41a1-452b-8824-6bfc5349e033 | signoff | AUTHORITY HOLDPOINT
adf1422f-561e-447e-820d-4cea2bc7edbf | checkpoint | 10 - Concreting
5667a262-f507-50cb-aa36-7312c615f26f | note | ACTION (Hold, Monitor, Witness): H
b5a3de33-3b64-58d9-ad77-c856eb579b6f | note | DETAIL: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
afbdf0a6-dc41-5508-b08c-b9c4a574f995 | note | FREQUENCY: Prior to concrete pour
65e1d8d4-c605-5f47-bd78-9f34b7c292b5 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
f75dab97-8e46-5f3d-b7a4-f01b59f6e5a9 | note | CONFORMANCE CRITERIA: Engineer will be notified via email/SMS at least 24 hours before required for inspection
6e715192-652e-5c89-93bf-61b240355f87 | note | RECORDS: Email / SMS
b4a02f15-00d0-4cdf-a79a-76fca061c96e | signoff | AUTHORITY HOLDPOINT
09eb1925-55f3-472b-8d37-5473914db41b | checkpoint | 10.1 - Concreting
2094cca1-f920-584d-8d01-7a5587a8c2b0 | note | ACTION (Hold, Monitor, Witness): W
3d955aae-5c98-5bcd-bf97-3ff0dee6b0f9 | note | DETAIL: Vibrator to be used throughout concrete pour
5265ae42-d688-5bc9-b6db-26077bf66b07 | note | FREQUENCY: When pouring concrete
fb692484-90cd-58f1-8320-b64656e8ce74 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
aa7e44ae-c8ff-5f8e-abf4-6bcf1772b9da | note | CONFORMANCE CRITERIA: Concrete Inspection Record
e6bd4561-dafb-5734-9ab8-e730eefc552c | note | RECORDS: Concrete Formwork Checklist
7b9c9797-d155-4d5d-85b0-6051ed1078ac | checkpoint | 10.2 - Concreting
9120fdf0-dbdc-5ef5-9d64-f15de4ec82af | note | ACTION (Hold, Monitor, Witness): H
2b4f575f-8751-5588-8c38-3c2a560cc495 | note | DETAIL: Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
2831c852-491e-577f-bcb0-72f765b53fff | note | FREQUENCY: At completion of pour
b58aeb9f-7455-5064-ae86-545c36ab23be | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
6f5712b8-a2c7-5760-b41b-0b002ce0982b | note | CONFORMANCE CRITERIA: Concrete Inspection Record
5fff7e94-a5eb-52a3-93d5-068e423edb63 | note | RECORDS: Concrete Formwork Checklist
6f5be124-0c6d-4e83-8912-8a901db0f24d | signoff | AUTHORITY HOLDPOINT
f59ab32f-d17b-4f22-be68-0855ed3fb11f | checkpoint | 11 - Curing
daa25d80-74a0-566c-9f34-67ce4f260075 | note | ACTION (Hold, Monitor, Witness): M
54a19087-e36d-514e-b34e-713dabc4cb21 | note | DETAIL: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
64cf923b-7659-5a92-8561-a13805d2b8ad | note | FREQUENCY: Post Pour
0664f7a0-1ceb-5a9b-9a32-f071f0691a7b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Monitoring the time allowed for curing
d1f63184-4394-5eb2-b3d4-86c7c5d7be87 | note | CONFORMANCE CRITERIA: 48 hours minimum have passed
0d6b1f85-3e2a-5a1d-9979-303c90f92a42 | note | RECORDS: Concrete Formwork Checklist
ae761057-a531-47f8-a643-4b6bafd589b3 | checkpoint | 12 - Remove formwork
84e2b5d9-fc9c-5c9a-9949-b0bf6a86b6d4 | note | ACTION (Hold, Monitor, Witness): W
dadba602-2285-5331-aa31-d922aa2bd03d | note | DETAIL: Remove formwork after 48 hours
5e2d0eb9-f1e1-5de5-9515-09303eb33d40 | note | FREQUENCY: Post Curing
4f174e59-4f69-56b0-aed0-deb78b7ba4ca | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
772029aa-b866-5830-9eb4-71acfdfebdfa | note | CONFORMANCE CRITERIA: Concrete Inspection Record
ed765318-3634-51ab-8da8-2891f27796c4 | note | RECORDS: Concrete Formwork Checklist
4d40804c-add4-4385-b4e7-c9be8fe6870d | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
82693cce-480d-5464-a465-95b3d959def8 | note | ACTION (Hold, Monitor, Witness): H
6f0029db-d919-57c1-a1a3-f3bd11f5098e | note | DETAIL: 600mm long D12 bars, 300c/c between ramp and table top.
a41b5b5a-092e-5d41-b48c-c162c0e5fc30 | note | FREQUENCY: Prior to pouring concrete
abebda32-c1e0-5269-885f-390432be6053 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
3b4fa8b0-f727-5025-9805-3a25b939a227 | note | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
03000af3-1d63-5d4c-abb9-fd00280bec15 | note | RECORDS: Site photos,delivery dockets
09121a20-c81b-4b18-b951-a180e627b17b | signoff | AUTHORITY HOLDPOINT
33de2581-6905-4ad5-9f49-d4849ffa62ab | checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
d3e32bac-3e53-5273-ba7c-484c7906baf6 | note | ACTION (Hold, Monitor, Witness): H
a9f4fb20-6341-5942-bfbe-611822d39759 | note | DETAIL: 200mm thick 40MPa Concrete with two layers of 663 mesh
2e31256c-6eb6-5b3c-af66-046b20a1c761 | note | FREQUENCY: Prior to pouring concrete
c21ee994-ef56-590c-91d7-33ee30ca3541 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
0c9fe2f9-b5a4-5924-806c-75e580b2fbe7 | note | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
204799e1-8f38-5204-b3a7-ce695eca1d70 | note | RECORDS: Site photos,delivery dockets
6407359f-eac3-4af8-9f02-3c3e48b6c342 | signoff | AUTHORITY HOLDPOINT
fa42eb9b-7dff-456a-8c5e-32923cc4db2e | checkpoint | 13.2 - Asphalt- Concrete extension slab/ Toe
020558f3-ae4e-52b4-9f28-9f5d1332b462 | note | ACTION (Hold, Monitor, Witness): W
8814084f-d741-5d11-a322-d074df277534 | note | DETAIL: Tack Coat between AC and Concrete slab
6bef3057-a9e2-57f5-b601-45de61a2ef9a | note | FREQUENCY: Post Curing
3d1b0045-9b44-5de5-b5b2-5f323720e172 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
10597b63-c21f-5efa-bae8-f6bb947b2ce6 | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
f274f4f8-e23d-5ff8-b9a3-d7ec288cb1fc | note | RECORDS: Site photos
06633ebd-f3c6-4b8b-b94a-e11ccc7994e4 | checkpoint | 13.3 - Asphalt- Concrete extension slab/ Toe
db85092c-a927-548d-86c3-b9208385ab90 | note | ACTION (Hold, Monitor, Witness): W
762cea23-7fda-58e8-b897-c8db2f2fcf27 | note | DETAIL: 50mm thick AC10
58953c0c-dd95-551d-9273-06589f1e2218 | note | FREQUENCY: Post Curing
4beccba2-ac49-5861-a19c-08f1086a84ed | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
4b11784f-bfb1-53db-b1be-15b4ce487a4a | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
e52f17ee-c884-563d-95e1-a7df52407f7a | note | RECORDS: Site photos,delivery dockets
3eb62ab4-ce2c-42f7-acfc-ab455e62fd51 | checkpoint | 14 - Lot Number QA File
3c2d18db-90c9-544b-8b23-1d8db65fc843 | note | ACTION (Hold, Monitor, Witness): W
69d58cb6-acc2-579a-bbc0-a07cd446e6a1 | note | DETAIL: Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
47d4497e-2226-5c38-98bd-22bb689ae037 | note | FREQUENCY: At completion of Lot
fba4fd51-2c6d-5ae0-abb2-4e956c74d7f8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
f00d5e38-730e-5664-bb69-060decb394a0 | note | CONFORMANCE CRITERIA: All QA files compiled and sumbitted to client
828e768a-e155-5b0e-b106-d72231ba1780 | note | RECORDS: QA records
30f19d61-1036-4a5a-89cf-984eb040de7e | checkpoint | 14.1 - Lot Number QA File
d1f861c3-64ac-58c2-af0d-2fb8f423425f | note | ACTION (Hold, Monitor, Witness): W
1483bcaa-af85-57eb-8080-50964ed8db15 | note | DETAIL: Delivery Dockets to be included in QA file
8742e7e2-a70e-51c0-81ea-fab02bdb74f0 | note | FREQUENCY: At completion of Lot
43c50329-acea-5aa8-8b27-24a7fbb84e2f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
2a3018a3-d9f5-5b5a-973d-4ac8f46e097f | note | CONFORMANCE CRITERIA: Delivery Dockets to be included in QA file
c3421fdd-98f7-5e5c-84b5-2e5c6770ee7b | note | RECORDS: QA records
76bd9ed6-1fc5-4848-82ab-0a120e0c8ee4 | checkpoint | 15 - As-builts
30e798f7-4282-52f7-82c7-3977714c6bad | note | ACTION (Hold, Monitor, Witness): H
36bf13eb-497c-52b8-be03-8f784a5bba11 | note | DETAIL: Red pen mark up drawings to be included in QA file
6c82aecb-7b29-5a0f-8491-b734b53736da | note | FREQUENCY: At the completion of the Lot of work
2979b6a4-4a0f-5145-b244-dc292814310e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
4b4f3fa1-c16f-52ac-880a-83aab9657474 | note | CONFORMANCE CRITERIA:
ebe7f0d3-ad2f-5353-bda0-a62fb14612e8 | note | RECORDS: Asbuilt Drawing
4d23fd4c-7fbf-42d6-a92e-56268c7a70b4 | signoff | AUTHORITY HOLDPOINT
340aea22-c146-4dbb-9133-f9b5c8238044 | checklist | ITP - Richardson Road / Owairaka Speedtable - Enabling Works - Footpath, Kerb and channel | itp | ITP - Richardson Road / Owairaka Speedtable - Enabling Works - Footpath, Kerb and channel | e7993fc3-a0ef-4f31-b715-5cbe711ec871
c3330f3d-d98a-4877-a5e5-dda966fed363 | section | Site Set out
cb57a2e4-9265-4773-9fe8-d653930a042b | checkpoint | 1 - Site Set out
12318a70-21f4-59f6-b557-4ec1d7f0790e | note | VERIFICATION ACTIVITY: Surveyor
4c8f1d22-3558-54e2-9525-2ace59eafc75 | note | METHODS OR REFERENCE: Surveyor
e6c964f2-cb1f-5060-bfa6-df83e46e5955 | note | FREQUENCY: Every site
95518e77-697f-51b6-a258-263bae0bc68c | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
5a0df1a2-999e-5911-b6fd-891b4f89f24b | note | HOLD POINT: Mandatory HOLD POINT -
6bb4fc37-1f1c-54f6-b660-c83420c4bc68 | note | RECORDS: Onsite records/photos
10969f47-fa9f-5cdc-8ffe-8c1f3af28cfd | note | ONSITE RESPONSIBILITY: Site Engineer
c9ecc291-06b2-4cf1-8e79-fe298175d96a | signoff | AUTHORITY HOLDPOINT
606b1a49-c180-4247-bb81-c7cace410f98 | section | Materials
4e22ae9c-c2db-47ca-8a76-c1bd4d2cbb28 | checkpoint | 2 - Kerb & Channel
ee5d509e-6ced-5ddf-aabf-570cb7221ade | note | VERIFICATION ACTIVITY: QA FORM
541366c1-3162-557a-bb4e-c9fae891d23c | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
3d96f36c-36b6-5aee-ab02-6e239261fef2 | note | FREQUENCY: Every site
699d5262-ba58-5e4c-b5ad-6e346915f73e | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
ae38c108-bebc-58c8-bbc7-4eb9c722d6bf | note | HOLD POINT: In process Inspection
dbbc89ad-2bb1-58bf-b943-556055f5f6f6 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
6b79908e-0818-59bb-b8c0-c4268137a3ae | note | ONSITE RESPONSIBILITY: Site Engineer
d8542c41-2e6f-433c-8e8a-0eb305f3478c | checkpoint | 3 - Channel Level
cc4e14d6-ca9e-526f-a374-611b26f5dfec | note | VERIFICATION ACTIVITY: QA FORM
649fcc21-1452-524b-8d63-c06dff96efbf | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
a4ddd6a0-703a-5cf3-9fcd-515c04e869c5 | note | FREQUENCY: Every site
a5272a5d-9d7b-5429-ae1a-c497ba560766 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
37d02e89-8702-5b74-8ea4-0ec3bcc8506d | note | HOLD POINT: In process Inspection
99f1ab42-bac4-5407-b9b0-8c12184dd1cc | note | RECORDS: FH concrete QA sheet
8fb1a27f-2357-5d90-b187-ee2cc8c2aa7b | note | ONSITE RESPONSIBILITY: Site Engineer
5aa17976-1f9f-42db-a8f7-60bd6795dad7 | section | CIVIL WORKS
76be279f-1737-49a8-af53-5ce40ef35af9 | checkpoint | 4 - Concrete Footpaths
9306e718-dab9-5bc5-a958-f837206f41df | note | VERIFICATION ACTIVITY: QA FORM
327060ae-c1cb-5749-9862-148ec3727e8b | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
38806561-2e93-55c8-9536-699a0ec2a70c | note | FREQUENCY: 10m Intervals
0d30522f-948b-51c8-b0e9-f12a81f70ed9 | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
58eaf050-ed9b-57bd-ac95-af54b5820b82 | note | ○ Clegg CIV > 12
e3758014-2eb0-5ec0-aca9-2212801fd0ac | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
02dfb058-390b-5123-8f3a-1d7b7bc8f774 | note | HOLD POINT: Inprocess Inspection
3d06a6c0-53b4-5627-895d-1c22a31da311 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
38ef1482-5c49-5f82-b22e-d2717a5547b1 | note | ONSITE RESPONSIBILITY: Site Engineer
78391008-8164-4599-8759-d143e7e81523 | checkpoint | 5 - Tactiles
4822fc3a-3574-5ee3-83c4-7eec65909145 | note | VERIFICATION ACTIVITY: Visual
de5f0c86-c994-5d3f-b9e9-e853375cc0e5 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
b00d364e-3c8e-5e4c-a16c-ceb1831ea159 | note | FREQUENCY: Each PX
162736ce-623d-5a81-9a67-ce632e1c90e8 | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
2da07680-0a5a-5f4c-884e-7a32ee14cdde | note | HOLD POINT: Inprocess Inspection, Measurement
91e1a554-4c16-5e95-b9d8-24a2a2fc78ae | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
680e52f0-2b07-5940-b961-0e63de19e05a | note | ONSITE RESPONSIBILITY: Site Engineer
e578742f-f985-4220-909e-c13fbebdb39e | checkpoint | 5.1 - Tactiles
e604e14d-4311-5c0d-b460-4b4290cb0ca4 | note | VERIFICATION ACTIVITY: Visual
70af647b-3b71-5a61-8939-08575707c6d3 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians
f3043c04-4e64-5007-bf5b-7830be5b57cc | note | ○ AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
6bce2427-3536-5c76-b987-ae922b1aae74 | note | FREQUENCY: Every site
6a934816-06fc-5ed2-b881-d48114d57a57 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
feb79c32-22c1-5f83-85a8-47b88f6e8e63 | note | HOLD POINT: In process Inspection
ef686090-ac28-5d39-a248-7542f77916ac | note | RECORDS: Photos
6d85e3a5-68d2-5fcf-83e3-27f980d166fc | note | ONSITE RESPONSIBILITY: Site Engineer
ef3e2e29-addb-4fe2-9fd0-9c8406606404 | checkpoint | 5.2 - Tactiles
8e2bbfe4-71f9-5c49-b016-ab681ff69dfa | note | VERIFICATION ACTIVITY: Visual
fdad66ac-11c3-540c-a797-db881fdcc899 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
6366d713-5ce7-5ba4-bef4-7553a5cda87a | note | FREQUENCY: Every site
4776d007-dd0a-5cfb-b884-61f5793d4c51 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
e654d2d2-7faa-5870-a2e5-b6209ed9176a | note | HOLD POINT: In process Inspection
6f5e5145-f709-5396-b60b-34cf48a77515 | note | RECORDS: Photos
ee5bf841-7c7e-523f-a5e9-c1a889e6dd07 | note | ONSITE RESPONSIBILITY: Site Engineer
a0da03cf-2e61-46ba-bc65-4c182775c7e7 | checkpoint | 5.3 - Tactiles
48514382-5e21-591b-aab2-a6ac236fd9a5 | note | VERIFICATION ACTIVITY: Visual
56ec8a9b-ec7f-5cde-8e6c-164b2bf7e4bc | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
9ca81816-ff58-5bc0-8d96-cf77fc9a0a1a | note | FREQUENCY: Every site
a757a11a-8d14-5caf-9307-017666610116 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
245e1195-32b3-5902-9e26-ff11d9212889 | note | HOLD POINT: In process Inspection
269d7e9f-5b9e-53a2-bde3-19e0166285c2 | note | RECORDS: Photos
24ed968b-176c-5c06-b011-04841f95ee8a | note | ONSITE RESPONSIBILITY: Site Engineer
2334d723-bd16-41c2-9fa6-979d23276d3b | section | RAMM DATA
4f255ac9-916f-472c-9a69-9f21d23d244e | checkpoint | 6 - As built information
6f6de5c5-7034-5399-b174-350702911cde | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
70af6fef-9c52-5aa7-b4eb-8822d4e3408a | note | METHODS OR REFERENCE:
fae67502-cc13-500c-967b-f2fd9a69f474 | note | FREQUENCY: Every Site
b912e8be-725b-5727-873e-f9695ca09be5 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
d66c7565-40c0-5001-96fb-252617c62402 | note | HOLD POINT: In Process Inspection
d77d9f16-427f-53d2-8385-c44d45e9aad2 | note | RECORDS: As built records
31d3ac16-731e-5ae6-8364-aee95e20c08d | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
eda32b44-1ae7-40f6-9506-a3b2073a2c84 | section | ITP APPROVAL
87e78494-785a-41e0-b030-89963e562f7e | checkpoint | Approvals
2612a00f-e64c-5b54-9f3e-6e7123adf896 | note | Prepared By: Divnish Chand
dc95463b-2268-589c-bd65-83574149a800 | note | Approving Delegate: Sumesh Sharma
28a50a5d-802c-4e9d-9196-3b406c641ee1 | checklist | ITP - Richardson Road / Owairaka Speedtable - Traffic Islands | itp | ITP - Richardson Road / Owairaka Speedtable - Traffic Islands | 6e4956d9-e67d-46ae-9d59-d30520012437
1f4cf883-e5a4-43a4-b317-c0c0fe5db4db | section | Materials
b1352c31-daa2-4cd7-bc6a-bbdfd70f7528 | checkpoint | 1 - Mountable Kerb
79ab8ac6-9ff5-597a-a875-df62b938dd4a | note | VERIFICATION ACTIVITY: QA FORM
8b173b35-8b3c-5cbe-b297-14f787bbf492 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
885ab9f4-3e96-5319-a69b-b9366cdaf742 | note | FREQUENCY: Everysite
0d39e0a9-683f-5980-889d-9ba71c34e0f8 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
4c939dbd-d88c-53e2-8cf6-97e852088cbb | note | HOLD POINT: Inprocess Inspection
ec4395b1-f863-5901-a081-2761492fa634 | note | RECORDS: FH concrete QA sheet, photos.
a8630d28-f180-57c8-b017-8e9c32276188 | note | ONSITE RESPONSIBILITY: Site Engineer
e04e555a-b210-4391-abd2-1cfefe8c4813 | section | Construction
1f949a70-da8d-4058-b39a-c708e6cb9840 | checkpoint | 2 - Survey Setout
66b6e4ef-fa4e-52c6-9a17-88936403d398 | note | VERIFICATION ACTIVITY: Survey
86e81f7a-0f36-56de-9cd6-27ebbacc32e0 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
4b259c66-09ab-5a9a-b12d-b4c5cfc6036a | note | FREQUENCY: Prior to commencement.
c0167f1e-7f99-5fe3-b823-ecc73acefe20 | note | ACCEPTANCE CRITERIA: Survey
a4eab85b-00ee-516a-80bf-662991b2db34 | note | HOLD POINT: As per Construction Drawings
eea21df3-d371-5eed-89d8-08c82b8c207b | note | RECORDS: Survey Receipt.
ff874462-37bd-5be7-85fc-b7c27dd24aaa | note | ONSITE RESPONSIBILITY: Site Engineer
7f502883-3644-417a-9f08-baadc3d8094a | checkpoint | 3 - Concrete Island (1)
bb76ef9f-d70c-53a5-b391-2004970b241d | note | VERIFICATION ACTIVITY: QA FORM
d3803a6c-8e67-5da3-bbf2-cf6e9e328ed9 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
3bb98926-8da8-57fa-b5ce-38dc0cf1cde2 | note | FREQUENCY: Each Site
5025ab9c-3380-535c-83b9-45019a625fa7 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
2aa0ba2f-c6de-536b-9ad8-af87b7365f7c | note | HOLD POINT: Inprocess Inspection
fdf6e3d7-5027-52c5-8528-d0966eb7a461 | note | RECORDS: Photos
91da5f88-8c35-55c1-9123-befb4b655082 | note | ONSITE RESPONSIBILITY: Site Engineer
96520a3e-9ddc-427f-904b-573bc0a4402f | checkpoint | 3 - Concrete Island (2)
a9a2b56f-8bf4-5c95-8157-709d4761ddf7 | note | VERIFICATION ACTIVITY: QA FORM
3b00970b-a6b5-5ac9-bf61-6de1f5a2f003 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
30220363-64fe-5907-a2ae-8b6a620a6310 | note | FREQUENCY: Each Site
fa163619-50bb-51d4-aa71-b5496a3aa215 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
ef03a786-0471-5a99-b5b0-583817588a91 | note | HOLD POINT: Inprocess Inspection
6fa1eb0b-0dce-5a9a-aa69-64b4591c17c6 | note | RECORDS: Photos
57ee3848-7d18-5585-ac1b-2b374b987a1c | note | ONSITE RESPONSIBILITY: Site Engineer
b7c19b3f-e97d-4a9b-bd8e-8466ec7144fe | checkpoint | 4 - Concrete Infil
807d4428-ebc2-5e18-a80d-5cf3d2d353d9 | note | VERIFICATION ACTIVITY: QA FORM
7f633c2e-bbe6-59c3-8d0b-57087548c775 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
1e1d12af-212a-5cd4-aadc-754340f9afa4 | note | FREQUENCY: Each Site
c0fbfb65-3841-5627-875f-ac3ce261bc52 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide
626c49ee-0f8b-5fe0-837b-7c4944a700d9 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
a50b3894-f3f9-531d-a941-cede0eeeac48 | note | HOLD POINT: Inprocess Inspection
a3911748-d0a7-58ea-bfc1-ca56cc628b05 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
8e30cb8b-578a-5ac7-a1bc-63a58648402f | note | ONSITE RESPONSIBILITY: Site Engineer
ca276c29-218b-451d-9526-e1b56e6954a4 | section | Asbuilts
36b7b6a7-8afa-45ae-a979-47561d0a29c0 | checkpoint | 5 - As built information
f21e3ccf-c0ba-5fa1-bcc5-4d9b9c8a91fa | note | VERIFICATION ACTIVITY: Drawings
02c22c91-4853-5b43-adc4-6b00385a9d03 | note | METHODS OR REFERENCE:
ac9a2b59-1060-5c1a-9474-b7cadad3cf7a | note | FREQUENCY: Every Site
42f6b52d-060a-51a0-b6e2-00a7585d4c6e | note | ACCEPTANCE CRITERIA: As built drawings
61ff0e01-28fa-53e7-ad94-108b2ccbfa29 | note | HOLD POINT: In Process Inspection
b515d4d4-3c01-509d-a3bf-0d42fe72c0c8 | note | RECORDS: Asbuilt records
ac6ed26a-9adb-54f3-9d2d-ade0b88af61f | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
bfa6189b-f8a8-4257-8ecb-cc942f42c848 | checkpoint | 6 - RAMM DATA
a45cce99-0752-5174-aee7-2f7765ac9107 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
d8654198-0913-5f98-aaba-d4331b9ba0ee | note | METHODS OR REFERENCE:
a3a69041-a08f-5c6e-926d-47f80ba623c5 | note | FREQUENCY: Every Site
fb2f2462-6337-5ecf-8bd0-17a5c75b0757 | note | ACCEPTANCE CRITERIA: RAMM SHEET
91057b0c-5266-5b1e-8bac-f60b0845901a | note | HOLD POINT: In Process Inspection
b76b97f7-1475-52e8-b4ca-6ad992782232 | note | RECORDS: Asbuilt records
4d2c3397-e6bd-57a5-9063-2ff52b7e86be | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
c814bd67-85f6-4564-aedb-f80f7ecd26e1 | section | ITP APPROVAL
f2d11e80-02bd-4db4-958d-b8b3ec8aa9d3 | checkpoint | Approvals
21277f33-f950-5af6-b818-46892d70c91b | note | Prepared By: Divnish Chand
a7b74e12-a75b-5992-9901-a74064aa3a52 | note | Approving Delegate: Sumesh Sharma
d755d53e-bd0e-4f0d-a69e-25918f5933a7 | checklist | ITP - Route 377 Bus Stop Extension - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | 65af7f3e-60ea-4298-af8c-d6196f89a02b
bb7db6c1-1020-4ae9-8078-84fc9051eb8f | section | Site Set Out
daf0537d-5c6e-401a-b2bb-a5f17b051f4a | checkpoint | 1 - Site Set out
12c69baf-75dc-57a9-8dc3-c2acb08c7c7e | note | VERIFICATION ACTIVITY: Surveyor
016f3409-0b58-50c7-b518-c575713b1b8f | note | METHODS OR REFERENCE: Surveyor
c4052a76-4228-5a18-86dc-26c7cdef28b0 | note | FREQUENCY: Every Site
8e4697ed-be8c-5d29-8bf7-b4b16909c286 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers.
5b94c2ef-8ad2-559d-bb50-4b87329d5c61 | note | HOLD POINT: Mandatory HOLD POINT -
a352f017-5675-5c59-9718-038675f47a71 | note | RECORDS: Onsite records/photos
bece4d45-408c-5561-894a-ffe6bf0563d1 | note | ONSITE RESPONSIBILITY: Site Engineer
db018d99-0db7-4b88-88e9-898737d404a0 | signoff | AUTHORITY HOLDPOINT
068a17f6-a756-4f54-9b3d-0c4124dabb52 | section | Materials
cd32164f-54d5-44b1-b7cf-4b96ef657307 | checkpoint | 2 - Kassel Kerb & Channel
ed862d3d-0720-55e2-8bb7-f952fd7f7d07 | note | VERIFICATION ACTIVITY: QA FORM
8d1c4c8f-8e16-56fe-8085-d51e514e0ee4 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0030 &KC0031
66bc20df-70e8-5f20-af22-b7e11a6d7b48 | note | FREQUENCY: Every Site
f96610ea-d6b7-5df3-9fe0-813b65cd888c | note | ACCEPTANCE CRITERIA: Kassel kerb and channel including 1m transitions at both ends as per standard.
d90ce978-906a-5a1b-aba0-3a3426f841e9 | note | ○ Half channel at 3% cross fall.
9a9db1d6-c9ef-5092-9025-3567d5494d42 | note | HOLD POINT: Inprocess Inspection
3782c374-50af-52f8-b7fd-b5bf9c7b784b | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
9681a9fe-6ba6-5e3e-b1bb-39148f369d4d | note | ONSITE RESPONSIBILITY: Site Engineer
1181ce1d-4efa-44eb-aa85-6adb10531d14 | checkpoint | 2.1 - Bedding
e14139eb-2ffd-5803-ac02-937ddc14634c | note | VERIFICATION ACTIVITY: QA Form
7dbc6191-e28a-57ed-beb2-e2421093f23d | note | METHODS OR REFERENCE: TDM Technical Standard - KC0002
ea8f8ba4-f4f4-59f3-9672-a31b3907334c | note | FREQUENCY: Every Site
20521db6-18b3-58b7-96ca-ce24db048af4 | note | ACCEPTANCE CRITERIA: GAP65 subbase in roads (CBR>5)
fb7224ad-f32f-560b-9f13-a9989ee65678 | note | ○ Concrete subbase must be 20MPa
b9b0dbc7-e91b-59de-ada6-abde320b261b | note | HOLD POINT: Inprocess Inspection
831e8a6a-9539-5926-908f-f34c4c536465 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
c7f732cc-6494-580a-9cb5-89b5aa6c9a0a | note | ONSITE RESPONSIBILITY:
ae90533e-d8c2-433e-ab33-db749767bc3a | checkpoint | 3 - Channel Level
d00cfe0b-0ce4-5c13-87e3-7b9c4724128a | note | VERIFICATION ACTIVITY: QA FORM
e658f375-406c-5976-a72b-b9589c6be0c8 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
2587bdc5-e3be-5eaa-aedd-8978af6284a6 | note | FREQUENCY: Every Site
1d6f581c-c395-59db-adf4-33dc38ca6724 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
d2754491-f297-5f01-a85e-40fb97ddd8c2 | note | HOLD POINT: Inprocess Inspection
5429eaca-0ba4-5a61-95a9-5db6bb08d985 | note | RECORDS: FH concrete QA sheet, Photos
2ebc91bf-dfe7-512e-a464-ab4ef96c8e83 | note | ONSITE RESPONSIBILITY: Site Engineer
66928d95-a144-4b72-8c9a-5bfa75a9e82e | section | CIVIL WORKS
9ba35c1c-d3f5-42cd-b684-a45de4a2db58 | checkpoint | 4 - Concrete Footpaths / Pram Crossing
b9ae362c-b088-5051-bdd2-df0ea43cf588 | note | VERIFICATION ACTIVITY: QA FORM
bf0df385-16c8-5cf0-a0c1-5641a08fab59 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
20ef3cf5-1c72-5158-9fb8-9759a0ece256 | note | FREQUENCY: 10m Intervals
83513b49-1170-589d-aed3-164f994f366f | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
9e57c9d4-1f09-5556-b121-29347248ef88 | note | ○ Clegg CIV > 12
7b9f1187-d04d-5432-8443-c68732a9cc60 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
71d07b76-2072-5658-8183-a1f59f66e2e4 | note | ○ Pram crossing
29d7eb14-ac8a-54c8-aebe-bdf005fe0ad7 | note | ○ MAX gradient to be 1:12
cc9ca11d-d132-5152-96f3-814707460dc7 | note | ○ 4kg/m3 blackoxide with broom finish
dc0fd77e-ba07-5473-97e0-375d054c4b1c | note | HOLD POINT: Inprocess Inspection
30c1e0d6-577e-5c25-9089-c172c9c7e5ad | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
0fa3237e-49be-5e06-8128-17359420122a | note | ONSITE RESPONSIBILITY: Site Engineer
865b5169-5a6e-47ab-8ea1-738c6281a15f | checkpoint | 5 - Tactile Pavers (1)
fb4208f6-c06e-593b-9678-77626af5b064 | note | VERIFICATION ACTIVITY: Visual
98d6ea7a-e733-5917-9607-866b53f161ed | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006 (Pram Crossing)
1095f805-6e86-5bd2-abb3-0940b41e5309 | note | ○ TDM Technical Standards - FP0010 (Footpath)
1b2312d0-8aaf-5471-807a-3fa9da435ccc | note | ○ TDM Technical Standards - IS0002 (Traffic Island Pavers)
7abda895-43af-5d6f-ba54-6c2ebf16593d | note | FREQUENCY: Every Site
dcf238a8-aec5-5c31-8448-8411ed4b6721 | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 150mm concrete slab underneath
ac22b8f3-4346-5d7e-a324-12751afbb597 | note | ○ Must comply to TDM standard
3e18e791-f607-5700-bbee-67df8ade2936 | note | ○ FP0006 &FP0010
a2de8245-d3fe-5c76-9953-89b99385f9c5 | note | ○ Traffic Island pavers must comply to TDM standard - IS0002
3042951e-bbb6-5943-8797-3fe0fb8bfff6 | note | HOLD POINT: Inprocess Inspection, Measurement
3a0e9cd7-201a-55a7-87d7-61ffa530e127 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
9059ae63-8fc2-5f11-ae33-5cfdd6e82bf3 | note | ONSITE RESPONSIBILITY: Site Engineer
75a998d8-2c18-4fc4-bd89-fa4c81ebf405 | checkpoint | 5 - Tactile Pavers (2)
c6d9f4e7-f19d-516a-91a9-eb8422b04760 | note | VERIFICATION ACTIVITY: Visual
ee3df88f-7e81-5265-b6b6-6c209d69ea74 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians
3e5dbe76-8985-5ef1-96d8-a0b9de7d2712 | note | ○ AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
e1a5a753-e1a0-533d-8f4e-c5ca2700d36b | note | FREQUENCY: Every Site
f32035af-5904-5cec-a0ef-4c36d5f08a3a | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
ef5c0920-703a-5bb1-8b8f-f0cafbe08e08 | note | HOLD POINT: Inprocess Inspection
95b39ef1-127d-5f01-b552-c0ca1ab2b8a8 | note | RECORDS: Photos
6ecf5294-9da9-563f-9c6d-a8fd8e6fedd1 | note | ONSITE RESPONSIBILITY: Site Engineer
5337fdc8-ebf2-4fd9-bcd6-1495ebb12ecf | checkpoint | 6 - Grass Berms
9d3eb810-f5f3-5111-a8d9-5266b9598ca9 | note | VERIFICATION ACTIVITY: Visual
86ca29ac-3c4c-5e40-b281-be55f950ddba | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
0111f1c5-d40a-57e1-8ef7-8b2d5637196d | note | FREQUENCY: Every Site
cfeb8c4a-e0a5-5130-9621-f3fcd994884d | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
58e02296-0bf3-5ab7-ae78-5df7beaa04f8 | note | HOLD POINT: Inprocess Inspection
b596a681-235d-5b4b-806e-d482375bada7 | note | RECORDS: Photos
53cfa193-6ccb-5448-a3a1-dacf355ef3f8 | note | ONSITE RESPONSIBILITY: Site Engineer
1195d1a6-2704-4016-bc7d-9cc4c728dc0d | section | As Built
dd6f06d4-031c-429c-b898-35088537465b | checkpoint | 7 - As built information
b297b1eb-d04f-5a8e-a245-d5a4b4044559 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
be232a8a-21c2-5154-8d60-09681f91df6c | note | METHODS OR REFERENCE:
30ec86ac-8cd8-567f-b1b0-de7e11bfc29a | note | FREQUENCY: Every Site
003b066e-5a01-58bd-aba1-709047b35ace | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
bdff6e2f-8813-572a-b457-403530001650 | note | HOLD POINT: In Process Inspection
609f4f6e-35f1-5ee2-bdcc-60a29d4cbfff | note | RECORDS: Asbuilt records
fb4cf7c2-42cc-5e7b-823d-07c7848e2dc6 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
d25724f1-c67b-4c0d-b806-f4a7d045350b | section | APPROVALS
24c00799-26c4-4719-93bf-68cac854095d | checkpoint | ITP Approval
1af75951-9d92-522e-a8e6-ee0062ef5093 | note | Prepared By: Nithin Thomas
abeb7a1c-6ae1-53ec-864e-98ec2d324bfe | note | Approving Delegate: Daniel Tat
b6cb9b72-c525-4bf7-a443-e1bf5e5ce082 | checklist | ITP - Route 377 Bus Stop Extension - Signage | itp | ITP - Signage | 172b095d-b000-4675-8367-8392a7dccd80
fdfe3256-3b40-4962-9453-b070bf5c9227 | section | Site Set Out
07902735-ba97-4f36-9224-6443c7a4bed8 | checkpoint | 1 - Site Set out
1f14efc4-f525-5991-905b-80fdf96b9ea1 | note | VERIFICATION ACTIVITY: Surveyor
75584ea2-7c4e-5b3a-931a-f84d603786a0 | note | METHODS OR REFERENCE: Surveyor
46210c71-a670-53b9-be9d-0dcebbebc988 | note | FREQUENCY: Everysite
18e48394-bcec-57e0-b5b1-b4eb10e8f4f6 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
11ca1f18-0dfc-5d91-bd05-ae60ca5ae26b | note | ○ Alternatively like for like
479d181a-02dc-5fb6-aded-7961dbe54c14 | note | HOLD POINT: Mandatory HOLD POINT -
906c4bc2-bea4-5c62-b6d3-ed65a9167cd7 | note | RECORDS: Survey Receipt
1562360d-d1f3-52e0-a91e-b2d2ff4105c6 | note | ONSITE RESPONSIBILITY: Site Engineer
baaa4450-2074-4574-a133-4e5fd5352196 | signoff | AUTHORITY HOLDPOINT
29d2f202-d04f-4270-9f00-e134ca9903dd | section | Materials
8b057bbe-fee0-4071-a445-17a71166fcf1 | checkpoint | 2 - Pole, Impact recovery post and Ground Socket
7fa52b7a-b554-515b-8cf4-2ddc99d07ab8 | note | VERIFICATION ACTIVITY: QA FORM
73d592b7-a3da-5462-a463-9bbbf0274505 | note | METHODS OR REFERENCE: TDM Technical Standards
72bc6ceb-3ecf-57cb-807b-63b5d0b1c956 | note | FREQUENCY: Every site
e9df066f-c09e-518d-bfd3-06fcf69fe93d | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
60ec33ff-b263-59e9-89ee-193e96dca5a9 | note | HOLD POINT: Inprocess Inspection
692381a3-9217-51e1-b0a7-47e0edea2825 | note | RECORDS: Dockets/Photos
40a70c82-c2f9-51f7-8699-4b04f3363ad4 | note | ONSITE RESPONSIBILITY: Site Engineer
737c1453-3a60-4dd1-b376-17c817abecd3 | section | Construction
8aae8767-b07b-4436-bdf0-a0939bfd2cd1 | checkpoint | 3 - Ground Socket
38f579dd-a48d-5b04-a9bf-51a4aa999c33 | note | VERIFICATION ACTIVITY: QA FORM
ae5667a1-4189-5a6f-80cd-8a0906d91991 | note | METHODS OR REFERENCE: TDM Technical Standards
1c8b059a-2123-5bbb-b50f-05a4e90e2b18 | note | FREQUENCY: Each Socket
b83d6bb4-a7ae-5706-9a60-fa3a94ce24de | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
d6fe86d4-ceb7-5a0a-b08b-c7bac305c6e0 | note | HOLD POINT: Inprocess Inspection
664aa22a-2cb7-525f-a74b-2beb7fa20fb1 | note | RECORDS: Dockets/Photos with tape measurement
cf114eb1-5e54-51a2-bc86-0b25bd820493 | note | ONSITE RESPONSIBILITY: Site Engineer
e192cd95-06eb-4ba6-813f-eb66bc0e8a98 | section | Asbuilts
cacddf48-1e7b-49c5-b8e7-1b31a259ba44 | checkpoint | 4 - As built information
edc69964-9c1d-5e42-81ca-d171d9acaa4c | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
f45ff246-aa68-536e-8b25-54f4292d589d | note | METHODS OR REFERENCE:
7d355fe6-03e5-5c0b-ac9e-579ee1f55dfe | note | FREQUENCY: Every Site
dad95f43-a358-515c-9d2a-60fc06689558 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
7ff5b770-3918-5943-b13f-8c2e7b5120fb | note | HOLD POINT: In Process Inspection
028e783a-d24f-5a39-9957-0b8018bb8a6c | note | RECORDS: Asbuilt records
765820cd-2124-55d3-be5e-8d4dbf3acec4 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
59e8ead1-c6d2-437c-829f-eefa7a9cba52 | section | APPROVALS
3915aadc-16eb-4dbb-95d1-bf60adb1d615 | checkpoint | ITP Approval
e7708811-ef49-5925-af8a-cc2975371f45 | note | Prepared By: Nithin Thomas
d67258a6-97cd-5b03-b75a-58b3a49d26cd | note | Approving Delegate: Daniel Tat
fec4d39b-15ab-4f24-a803-7bb5b14d9a58 | checklist | ITP - Route 377 Bus Stop Extension - Traffic Islands | itp | ITP - Traffic Islands | 5979aa4e-23a5-4b40-8a02-ebc72644f519
afec138a-26ec-4876-a989-a17ffb19e368 | section | Materials
74d487f3-a500-49fe-8ad2-7601ed5be3de | checkpoint | 1 - Mountable Kerb
f0bb8480-6aae-5dee-bc6f-889a96b57d64 | note | VERIFICATION ACTIVITY: QA FORM
62202822-cbc5-5425-8bea-fb0ee6cfc3a4 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
c216de89-e6d0-52b0-813b-92e4107d0c6b | note | FREQUENCY: Everysite
b6319028-0896-594f-bcd6-ff8358872f01 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
f038b4e1-2f94-5ecf-9211-bbaefa9fd029 | note | HOLD POINT: Inprocess Inspection
6c6ca207-4e15-5e30-924c-3dae269dc26b | note | RECORDS: FH concrete QA sheet, photos.
59248d1a-2383-5364-ad2b-3bd1a2e2989e | note | ONSITE RESPONSIBILITY: Site Engineer
7d4f7030-9286-49a8-a43b-e13788ee1d5c | section | Construction
57853564-f47c-42b3-be03-c8f97955a3e0 | checkpoint | 2 - Survey Setout
04f7c441-520e-509f-842d-afb291ee0aa6 | note | VERIFICATION ACTIVITY: Survey
2d277178-b022-5635-8679-210eb3d2115b | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
7d7d17f9-d070-55ed-8f8b-9d61870177e3 | note | FREQUENCY: Prior to commencement.
0aa3e50c-b8c0-584a-80eb-71d3aa9622bb | note | ACCEPTANCE CRITERIA: Survey
ead7f026-f870-5e74-a7a2-e8b885ecdc6c | note | HOLD POINT: As per Construction Drawings
92fc2090-5696-593c-ab42-b54f280fb13f | note | RECORDS: Survey Receipt.
0b67d95b-19a4-59a2-bc03-0ed436286ba7 | note | ONSITE RESPONSIBILITY: Site Engineer
cf4effa5-a865-46b9-a498-e63807f532e3 | checkpoint | 3 - Concrete Island (1)
512564d0-18fe-5442-ae63-beaa6c4a21b9 | note | VERIFICATION ACTIVITY: QA FORM
f1316acc-ad65-5fbd-8235-52d9cb37456f | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
80dcecb2-8ee0-57eb-895e-ca7f70f5e6a6 | note | FREQUENCY: Each Site
dbd9de4d-d499-52e4-a22d-a792314d2219 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete and Sand Cement Mortar
90699449-b3ce-5202-92e3-ff5c5b022bcc | note | HOLD POINT: Inprocess Inspection
2831a65d-63e6-5c52-9503-8a21098e4fa6 | note | RECORDS: Photos
5243385d-0307-5bec-8cce-d0b209c7d1fb | note | ONSITE RESPONSIBILITY: Site Engineer
751fa1f0-ff91-4365-862d-9e37a2443452 | checkpoint | 3 - Concrete Island (2)
3653da01-4bd4-53b5-9d44-fea40fb071eb | note | VERIFICATION ACTIVITY: QA FORM
b2b2e320-b4a4-5bad-902a-10c984814e20 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
fb3e962c-3cbf-5eea-a4c5-76a231800aee | note | FREQUENCY: Each Site
a19b4810-a0fc-5b0b-8887-b3bff413f7a3 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
e39b21cc-3d32-5652-ac4b-73d81af5dfba | note | HOLD POINT: Inprocess Inspection
5025d52e-198f-5686-85ef-3d64c8890b66 | note | RECORDS: Photos
a4ead178-c9be-5710-a865-6575536039b7 | note | ONSITE RESPONSIBILITY: Site Engineer
3dbee12b-f1b3-4275-b3bb-e6ab76db249d | checkpoint | 4 - Concrete Infil
b20d742a-43c0-5054-84ea-0292842503f2 | note | VERIFICATION ACTIVITY: QA FORM
e7c2786a-3ef8-5acb-b130-f4dd0becb3c8 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
2d18a41c-66d9-57c2-ab68-f9acf212289c | note | FREQUENCY: Each Site
79243879-6935-5d2c-85a7-1c745e93f8d9 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide
48bf9939-9e4e-5ff3-b669-b06d48b274e3 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
2c5f0044-8015-59ff-988a-2394d2475e16 | note | HOLD POINT: Inprocess Inspection
721deb77-ea0f-500a-9cce-54d001ed300c | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
1a9b1240-f92b-5c86-961d-b329f0560dc2 | note | ONSITE RESPONSIBILITY: Site Engineer
9ca80b3d-548c-4797-9bae-7fedbfb5d1a6 | section | Asbuilts
7b7140be-61d5-41ff-b3da-5f26bdd92543 | checkpoint | 5 - As built information
cf139c20-0ab0-5bcc-9545-d7d461d4c7d8 | note | VERIFICATION ACTIVITY: Drawings
b15c5b54-b824-5531-a639-b40b4bb4ac62 | note | METHODS OR REFERENCE:
942bcdca-e2af-5fc2-82ac-d62d8a4b1f69 | note | FREQUENCY: Every Site
49b1eef4-3d58-5355-8461-d294a422c2de | note | ACCEPTANCE CRITERIA: As built drawings
a4008aae-14dc-5c00-9a2d-96b2a4c75171 | note | HOLD POINT: In Process Inspection
f9e48eaa-9c8c-57c4-b920-83de9e5d0e58 | note | RECORDS: Asbuilt records
88484b35-bac9-5f75-838c-e212483ff854 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
433c7e8e-b916-4c0b-a853-287a61d5578e | checkpoint | 6 - RAMM DATA
33fa45fe-7189-51dd-8be4-ef5cd71e73ed | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
e3c9abe0-565f-57c4-8587-7508f4e24904 | note | METHODS OR REFERENCE:
c1db83a6-b58b-57f1-bcda-44936906ac92 | note | FREQUENCY: Every Site
f62b99a1-f10d-5e76-83e9-c9fc1e253570 | note | ACCEPTANCE CRITERIA: RAMM SHEET
215ed9d2-e5b5-5bdc-b897-cf383cb51d14 | note | HOLD POINT: In Process Inspection
2199c9b1-e4ce-50ac-8d76-62546f85c565 | note | RECORDS: Asbuilt records
33144845-45f3-5bb4-b0ba-24c21460519b | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
29a83072-af87-490d-a205-57902ca9e6d5 | section | APPROVALS
2036458c-0311-4b6e-af13-9412eff208ba | checkpoint | ITP Approval
581b15e6-da86-5cfe-acbe-d95effa374a6 | note | Prepared By: Nithin Thomas
526732d7-8394-54c7-8e27-6f3e22d8c14e | note | Approving Delegate: Daniel Tat
| checklist | QA Photos |  | QA Photos | 2f5e868a-dbe1-470b-a4fa-ea5658af03f4
| checkpoint | Add photos here:
| checklist | Weymouth Construction - Mahia Road - ITP - Ducting | itp | ITP - Ducting | c461435d-266c-467f-93e4-1ec4b813646f
| section | Ducting
| checkpoint | 1 - Permits
c5ab7cd5-11cf-5d40-9f6a-948991dffeef | note | ACTION (Hold, Monitor, Witness): H
86f061c2-e28e-5716-8110-5c68a252afde | note | DETAIL: Obtain Permits
3d88a201-44b6-59ba-ace8-76d9afba35ca | note | FREQUENCY: As required
40ede74d-4006-575e-b99c-bac66c474614 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
00eeebab-1df0-5f86-ab29-84092f0117a6 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
692bc24f-bb8d-599f-9c9d-f75f0832dac3 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
1373f2cf-5a1e-51b4-bd3d-aef11fa2a9bd | note | ACTION (Hold, Monitor, Witness): H
5b0581e7-5b4e-5b4c-9ea7-8bd10c06c83e | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
006da8c1-bbb1-5da8-bd02-c3e1c4c65d23 | note | FREQUENCY: Prior to commencement
6186c630-08f6-5b95-9418-a7292dcbf6c6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
3aabb1fb-8208-5db2-bc2f-b26b5674212f | note | CONFORMANCE CRITERIA:
45f927bf-4bb6-534e-8273-5ba79001ca78 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
189b1f2d-0429-5898-a015-aac7c117d3c3 | note | ACTION (Hold, Monitor, Witness): H
6fd2e227-6f4e-59a3-984c-ad1edba7068d | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
15271c32-681b-52c0-8bd8-b3ad0e2ab126 | note | FREQUENCY: Prior to commencement
4864b2c4-4057-5a83-9250-3ab026c326af | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
43a4bea6-92b3-5cb8-a3f2-a3e33ed5b3a2 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
15e26e17-2e2c-5bb0-bf96-773ab5ee766c | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
75b81d24-9ad6-502b-a481-1038a9a2a479 | note | ACTION (Hold, Monitor, Witness): H
4172c487-51d2-54e2-9d0c-09b7b733f301 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
b823bcee-32db-5ccb-84b3-a68151558fc5 | note | FREQUENCY: Prior to commencement
5b617aef-edf4-5497-b167-1d2e4a95dceb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
ac85d431-ab12-5329-9d1d-6175f1b8c42b | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
691a2a37-91a0-5cb8-8d5a-b5faa8e8624f | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
7da33ee6-91a5-586f-96fc-aafd8c1d1006 | note | ACTION (Hold, Monitor, Witness): W
97aa9163-056e-5ea1-9f68-7a083b6b814f | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
79bc805d-8b2b-5914-8f37-3a24bf573005 | note | FREQUENCY: Prior to Installation
a839faea-97c4-58fa-84e9-c2dcf43a6670 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
7f9db7ac-ebc5-526c-84ef-0adb2f4cfcc5 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
d02d25ff-64e9-5ddf-85e2-b2e5224ff41c | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
c22f0ff4-afa2-5495-ba79-58c0c3805aa1 | note | ACTION (Hold, Monitor, Witness): H
157a4daf-53d6-5801-95d6-dd5d737ef267 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
86c42350-bd2a-54eb-9d15-27f51d43f7e4 | note | FREQUENCY: Upon delivery to site
f251f0ce-8ed3-5cd6-8ed3-38187ed12ac3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
a244baa4-f28b-5438-8fb6-94eb25cdda2d | note | CONFORMANCE CRITERIA: 50mm Ducts
937699b5-8230-5698-a3a4-b1aa1641c484 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
9438b980-d66a-5487-8a07-80ce6b3dc9a5 | note | ACTION (Hold, Monitor, Witness): H
6d594c91-3982-561e-8d46-cd06a7009348 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
a0e5ed8c-f9be-503b-9483-3f61399930fd | note | FREQUENCY: 10m Intervals
d891371c-1438-5927-8cdd-d7f2b0c4f26c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
372f17ac-0685-5977-9e1c-70c1289f436d | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
94ba6ffa-1289-5665-8b76-10ca22aa5623 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
2a502064-bf50-58f1-9d52-4598cfcb3c07 | note | ACTION (Hold, Monitor, Witness): H
f68ae614-2f10-52e1-a453-f92fb01d02f6 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
47b56f5e-183d-56c8-89fb-da38715b2252 | note | FREQUENCY: 10m Intervals
b3b89e08-bfc7-56e4-9d3b-8d99d3c42740 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
5c6af5b1-9aa3-564b-928d-01637e444baa | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
9afd833d-5e8b-52eb-8b95-074b5a04c50c | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
520bd29e-6b1a-59dc-94bb-a656d62bd48e | note | ACTION (Hold, Monitor, Witness): W
558d7b78-68e2-576b-8bef-0aef9c92b576 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
59c32466-044c-5b0b-9bd9-1ac1cc69bc53 | note | FREQUENCY: Prior to Installation
b70f08c2-7dfe-59df-8951-194d253fe33b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3a2cbad6-49f2-5d8b-89d2-45164ad6ad47 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
44a4c2ea-4ac5-53b0-b607-10de9ee535ae | note | RECORDS: Photos
| checkpoint | 7.2 -
1af06f8a-a821-5484-9d62-91f9f58f7719 | note | ACTION (Hold, Monitor, Witness): H
723f4821-c50f-5cc6-974a-d8a13401cb39 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
effa2a58-b040-5335-9bb9-374537cbfe0f | note | FREQUENCY: 10m Intervals
d46faa09-0276-595c-a635-dbef9aa50b82 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
4108b62f-7ddd-5df5-9b94-02aecd873db9 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
93b98b81-10fe-5ab6-88de-5da325e3c767 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
4c49b4d1-c2fe-5672-bb93-04c22a0286b1 | note | ACTION (Hold, Monitor, Witness): H
de44c03e-4b9f-5763-b604-8575a8f8bb21 | note | DETAIL: Asbuilt Survey
e0012547-7ef5-526e-b323-1613a00c2d0f | note | FREQUENCY: 20m Intervals
c36311c2-9fe6-52f0-a1a8-0429dd121c8a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
5cd34fdd-6fe7-5632-bcac-8123145f0c12 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
792cf62f-86a0-5090-9b50-15bc5fa38e3f | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
5cdfe692-bff0-5063-ae7e-b9d946dc2a85 | note | ACTION (Hold, Monitor, Witness): H
b69c09ab-b5d3-55ec-a80c-263533689a35 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
68606bd4-0148-5a75-a2ad-50d0f657cbc6 | note | FREQUENCY: 10m Intervals
eff654d6-013e-5e9f-bcfc-2dfb174ec2cd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
921ea9ba-8540-52dc-ad8b-1dd773028ac1 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
9719cf48-31e0-5434-b663-c613d555b137 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
075193dd-1d38-5839-8d62-7e0f1b9cbc02 | note | ACTION (Hold, Monitor, Witness): H
cf6f223c-e15e-5fb7-8017-57b9650acf0f | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
ac323b51-3bf5-599e-8f05-862f68995929 | note | FREQUENCY: 10m Intervals
4f95cbff-a721-5bd9-bec8-40da4560862a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
657a081a-2a5d-5af1-9ace-afdbe03f9c8c | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
d157e430-c245-5b98-a5f6-f06ed2bafc72 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
34108a2f-35e9-57de-987d-25619de07ac0 | note | ACTION (Hold, Monitor, Witness): H
244f21bb-10a7-58b1-afa4-99adae7081cd | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
da540adc-0146-5ba0-ab74-11dca839b079 | note | FREQUENCY: Eash Site
032db15f-6cd5-544c-ba46-e5370c273812 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
86cdec97-7c67-59e0-9f66-47f687465607 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
33ef5c13-283b-51a7-b972-586f920eb5e2 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
cd439d91-253b-5ac1-9929-98906fa174f7 | textbox | QA Compiled By:
b382a2fd-6014-55dd-96b1-5aa9b03d815a | textbox | QA checked By Project manager:
59e5e59e-5e18-54bd-b667-3ea918bd4124 | textbox | QA checked By Contract Manager:
cc91479e-63f5-5ecc-aeb0-5684a36bb9b3 | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Mahia Road - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | fe63e828-b5fd-4c2e-a258-83411c9575ec
| section | Site Set Out
| checkpoint | 1 - Site Set out
96848049-0747-5dc7-9f45-b04b8708869b | note | VERIFICATION ACTIVITY: Surveyor
b4b2ca2d-01f1-5caf-a76f-e842caa91678 | note | METHODS OR REFERENCE: Surveyor
1b073fab-b43d-521c-b08a-59ad53cbfe4d | note | FREQUENCY: Everysite
3a7a1987-cd58-5db2-a0cf-a1fc1d51e0a3 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
cc9a8914-c4c6-5548-8750-8d72b344f00c | note | HOLD POINT: Mandatory HOLD POINT -
07b9c511-370e-596f-b519-cb9e3d8464bb | note | RECORDS: Onsite records/photos
c8a96b79-b379-5afd-9da5-f484e2878826 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
936d9691-89a6-5bc5-ba9a-a36cd8a8e74c | note | VERIFICATION ACTIVITY: QA FORM
fa41c859-c062-57b9-aa02-e77ab0756077 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
68a2c501-520b-530f-9d20-dbe7b7c760f1 | note | FREQUENCY: Everysite
05fa5863-c85a-5ad7-bae2-e0124df69bf1 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
cccbf212-c126-50cb-bca3-03cde65a1244 | note | HOLD POINT: Inprocess Inspection
725939d8-a404-5a24-821d-4772fca1dad8 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
6077fba9-89c1-5014-8fd4-f2c0e7daf90a | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
56cdc858-5ea3-514c-bc73-72c5f29e5028 | note | VERIFICATION ACTIVITY: QA FORM
456ec7d3-9430-59be-a130-302845385e6d | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
2d9a6e85-f44d-5871-8a36-62602230a65e | note | FREQUENCY: Everysite
908d618d-2127-52ea-ac76-c38a30dce150 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
73ffa330-a920-5821-ab40-dd853e16f438 | note | HOLD POINT: Inprocess Inspection
d0ebe95e-8e94-5e34-960f-a27507683f49 | note | RECORDS: FH concrete QA sheet
08afe1bb-a527-56b3-84fe-4f40b446d358 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
1eaddcbf-fc6b-56be-a896-dbf2c3dc17eb | note | VERIFICATION ACTIVITY: QA FORM
7f4f6fe8-1981-5078-a8e9-aa45080a49a9 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
9db757ba-cc95-5875-af7f-0f3c65daa8a1 | note | FREQUENCY: 10m Intervals
9465c966-62d3-5962-9842-199d5d414b75 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
00a4d928-929c-5ecd-b1b1-6d3f0b51c1cd | note | ○ Basecourse - 100mm min. thickness
02c3b56a-468e-5533-b77c-5fa1ae664fda | note | ○ Clegg CIV > 12
0c8b0afd-7ffa-5506-8029-71c7b4e2f91c | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
1aa5603c-3ee9-5e52-9802-6c7453f7f43c | note | HOLD POINT: Inprocess Inspection
ad54f0d6-7353-5f42-92d0-5edd59e0fc4c | note | HOLD POINT: Prepour inspection
0166b964-42c1-5afe-9462-90d2049a4e47 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
9a893ce8-5dcc-5ac5-9144-a9366cd81b81 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
1fb2d1ca-1343-5b92-9202-43276ec5bd0a | note | VERIFICATION ACTIVITY: Visual
354006ae-696e-52e2-a3f7-fa2914b425c8 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
348b384e-fc33-570b-9a0e-21face051958 | note | FREQUENCY: Everysite
830645bc-0865-5d07-9df6-8ae1735969c3 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
b5e619a4-0742-5512-a515-c5c76128191f | note | HOLD POINT: Inprocess Inspection
2ddad824-554b-5bfc-bc5c-7ba1e3dbcd53 | note | RECORDS: Photos
f89c02b6-6855-5d3d-95d7-79c40e4c0a9d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
fe117190-1b72-5214-8dae-478bb77dd945 | note | VERIFICATION ACTIVITY: Visual
2da29b19-f653-5732-9097-ef30d97f6c2f | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
4bcece6b-a1af-5558-95e3-bc39fef00420 | note | FREQUENCY: Everysite
bdeac491-4eb7-52e5-98f6-3d85170c74b0 | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
c75fa20f-d0f8-5993-831c-66060fc35607 | note | HOLD POINT: Pre-pour inspection
8311d52f-cd26-55cc-82c7-4c1bdf478a9c | note | RECORDS: Photos
c89a90f7-e48e-5da1-a4c2-bb05a653b40f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
891a3c7b-5067-556b-9e42-589bbac47c96 | note | VERIFICATION ACTIVITY: Visual
a2e53721-df37-5296-8cf0-ce2d19138585 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
ccd3f032-728d-5f35-b636-f12de205809c | note | FREQUENCY: 10m Intervals
84eb6755-d126-5860-8348-5acbfc151a46 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
82af732a-96cd-5ca5-9aa4-f288f84d6e3c | note | HOLD POINT: Inprocess Inspection
35599632-32a1-56d2-95d0-fb7ca27b7602 | note | RECORDS: Photos
322a610e-f6a6-5376-9c11-39f0712abe6c | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
58ae846c-8ae6-5075-aded-a10159c4478c | note | VERIFICATION ACTIVITY: Visual
71d31abb-20f1-5641-80fc-dd47ec23bbc0 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
a35cfbdd-1509-579e-a1a9-7eb31e87388e | note | FREQUENCY: Each PX
348b8289-3f0c-5e02-a466-f516db7e33d6 | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
fa74f1b7-7a87-57ee-96d4-419dfe1c695f | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
c2066c44-f989-5812-b2b0-c252f3cbb058 | note | HOLD POINT: Inprocess Inspection, Measurement
21767062-8995-5a3a-acf8-28688b7fca57 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
a526df01-b4e9-5aa8-b32b-d97c31aeefa4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
66283c10-855a-5c2c-bbc9-7095dafead0b | note | VERIFICATION ACTIVITY: Visual
0b276594-a81f-5655-a6a0-c43904fa36ec | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
ba64472e-12a7-584d-a0cd-27e4ada7e5ad | note | FREQUENCY: Everysite
6890cfda-2a34-5b96-b917-c0fa784c93ff | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
74d92e8a-accd-5303-9886-145e0f8bf103 | note | HOLD POINT: Inprocess Inspection
f1eaf141-6a0e-51ce-af8b-9fa81ac2672d | note | RECORDS: Photos
ae2dce3e-b4ba-5f08-be32-7906af443daa | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
9199592e-a69f-52bb-a3a3-9d3228e072ab | note | VERIFICATION ACTIVITY: Visual
0fda8703-a279-5a35-a5a2-f9e87466a125 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
51ae2992-d550-5556-b99e-75e83c3f50cd | note | FREQUENCY: Everysite
1cd9a8ed-b168-5ef8-822d-2e3ddc2cccfc | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
e64506cd-f114-53da-83e8-ee8d8ac095a8 | note | HOLD POINT: Inprocess Inspection
5964e790-62a0-598c-bf54-1884a2dbf9b5 | note | RECORDS: Photos
b38cb7c7-4f87-57a5-a8dd-dd0dbf87791f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
37532c69-e204-5590-ac1b-03e2c5fc65c4 | note | VERIFICATION ACTIVITY: Visual
625501da-3919-5f93-b08c-b5ea43fa3242 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
3c859566-6ade-5271-bcde-b4cac6cd9f0c | note | FREQUENCY: Everysite
a5d2dfa8-0c09-5ad4-b5a6-79466c401ecd | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
dfd3e529-aa9e-58c8-8d86-851bcf7f8209 | note | HOLD POINT: Inprocess Inspection
a8a8b6c5-d024-5657-8fd0-f91396935650 | note | RECORDS: Materials Dockets
0a719033-7a33-5059-bf89-c0ef989cc6ee | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
b0b0493d-173d-50eb-b8ca-078e68a8ff6e | note | VERIFICATION ACTIVITY: QA FORM
b650e797-1b61-5073-9193-3984732a286b | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
7cdf546e-899d-5796-ab35-c11338bfadb1 | note | FREQUENCY: Each Crossing
30cb8214-1bcb-5726-9830-b4e4d80aeb6b | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
e01fe79a-8844-5069-b003-94e17fedf675 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
9081e882-6c6e-5cd2-a24d-3096c5857d20 | note | ○ Slope no greater than 1:12 where practicably possible
ad6a7fbf-5768-5d65-be4a-eadeaac83510 | note | ○ Clegg CIV > 12
9190214e-7971-5330-9ed1-83bd7347e185 | note | HOLD POINT: Inprocess Inspection
3ce8713d-26e6-52ff-95fb-a70a689ce0b7 | note | RECORDS: Photos
d37911be-47af-5f29-be5e-fb499eaf351c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
562156db-0947-5398-836d-89d5cf6334d2 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
ddc3fceb-41e0-5518-b634-eca95de4e971 | note | METHODS OR REFERENCE:
afad6005-6583-58ed-8ed5-4dab8fe4269b | note | FREQUENCY: Every Site
968693ae-8348-59d1-b816-33efb57b3668 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
6e49a71c-0e9d-5860-ac0c-89c24f5cafa7 | note | HOLD POINT: In Process Inspection
de8e8f1f-175e-5ad3-9279-60fcee2bbf29 | note | RECORDS: Asbuilt records
51bfa835-2cd4-5f0f-8ef2-29c7ade28ede | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
1f1ad4ad-ed8b-582f-9eb3-9509a8cb96b7 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a529e758-5546-5fe4-b3f8-31d4e6965efa | note | METHODS OR REFERENCE:
04f5b4e6-c805-58ad-aa29-f009e379a752 | note | FREQUENCY: Every Site
099316e0-2a44-5ebc-8740-c8163df11b08 | note | ACCEPTANCE CRITERIA: RAMM SHEET
6f306503-755a-56a4-930b-180b25ed4709 | note | HOLD POINT: In Process Inspection
0b017a23-7990-549e-b2a9-b2b12bc2d8b1 | note | RECORDS: RAMM Sheet
eb2d5127-bc08-57d2-85bb-53caf9b8b12d | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
4ffb6063-e194-505f-be90-e55d7f0b2a25 | note | Prepared by: Ajithkumar Ayyanar
1e767eb2-6a41-5994-8dd3-a7f503ee71f1 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Mahia Road - ITP - Signage | itp | ITP - Signage | 4fa6065b-99e2-4b0f-820c-2098ed9b7202
| section | Site Set Out
| checkpoint | 1 - Site Set out
783f53c2-3b2b-505d-894b-2abe5ded9c7b | note | VERIFICATION ACTIVITY: Surveyor
255e519b-13b3-5109-b55a-763a7a46a8c3 | note | METHODS OR REFERENCE: Surveyor
cc07637a-d367-5ab0-8776-00c2cd5564fb | note | FREQUENCY: Everysite
36e71730-8319-58d1-8e9a-ae7b6a4948d2 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
c10defdc-cbb8-583b-be40-0353d30043c0 | note | ○ Alternatively like for like
eb0c6730-0e16-5a0f-a824-5ca60ac08858 | note | HOLD POINT: Mandatory HOLD POINT -
0bdc3286-a799-5ec6-b479-6499167aa1ac | note | RECORDS: Survey Receipt
831d3584-d41b-5da4-ac83-088786455994 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
09f5f3e9-efce-5355-9f74-16bcce13a1ae | note | VERIFICATION ACTIVITY: QA FORM
866cb14e-c4fc-5bd1-9d4e-2f625dce11e0 | note | METHODS OR REFERENCE: TDM Technical Standards
ca04f91a-0466-5b7d-8e9a-c062eb8094a1 | note | FREQUENCY: Every site
16873573-110b-567d-83e3-0a67b7982443 | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
2391fc16-1a87-5e12-9388-89ed972ba756 | note | HOLD POINT: Inprocess Inspection
afc48459-dd47-5e98-952c-8538c9cbdcd0 | note | RECORDS: Dockets/Photos
8413b768-b88b-54fc-b689-e49ec7658259 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
15285099-b3cf-535d-afba-b490746cf833 | note | VERIFICATION ACTIVITY: QA FORM
843e60f2-647d-5cc5-a8bf-b31bb8020aaf | note | METHODS OR REFERENCE: TDM Technical Standards
29afdad7-6741-512e-8d07-cb6771a55e9d | note | FREQUENCY: Every site
c2dc911e-a926-5c19-91d2-d916af1c70fc | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
7ea49092-5b93-5d0e-8264-ff4d8ebec95f | note | HOLD POINT: Inprocess Inspection
71aa82f2-9727-5241-abfd-09c82d0518ff | note | RECORDS: Dockets/Photos
6cb1cdad-66af-5e3e-8983-7cdabc829d76 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
3c5afd7d-c1e8-50cd-a958-1b4bac9cc071 | note | VERIFICATION ACTIVITY: QA FORM
85363d50-4676-5202-abb2-5e2be86461b0 | note | METHODS OR REFERENCE: TDM Technical Standards
13c9b06f-f328-580e-b634-e2a16468d7b6 | note | FREQUENCY: Each Socket
ff6c1eea-e9c6-5eb9-be5c-0438490047d2 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
1fbe9afb-e9b4-5ced-84d8-c94d99907c0c | note | HOLD POINT: Inprocess Inspection
1487b02e-4c9e-5ca6-b8b6-81ff34d69456 | note | RECORDS: Dockets/Photos with tape measurement
79a218ef-19ce-5cc1-b1f8-1b6160ee06d1 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
fdf7025f-c82c-584b-b818-4ebd54647d02 | note | VERIFICATION ACTIVITY: QA FORM
290c8d2c-7e86-5222-9d81-1720eac99cdf | note | METHODS OR REFERENCE: TDM Technical Standards
14c6892f-0458-5ef3-b15e-f1563db40e76 | note | FREQUENCY: Each Post or pole
0d41189a-079a-52c7-8fa0-01fcec73d15e | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
8b4871ca-e96a-503f-ab38-1109bad1f690 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
ef43d370-2bcf-59c6-8504-eba2538767dc | note | HOLD POINT: Inprocess Inspection
f2a4d785-c5aa-5422-af97-3fdc49767c52 | note | RECORDS: Dockets/Photos
f7f10d67-e7ab-529a-9312-c91d50c5b1c5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
3c1ef5df-0341-514a-801e-9501df6049af | note | VERIFICATION ACTIVITY: QA FORM
ede061bf-304e-57e4-a730-f6992d221111 | note | METHODS OR REFERENCE: TDM Technical Standards
552776f1-2d98-5912-9fc3-242605dd08b7 | note | FREQUENCY: Each Sign
4ce19822-dd89-572e-aec4-ce84d5fc1329 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
a6f65ba2-c41e-5ca8-b5cf-5546367ae82e | note | HOLD POINT: Inprocess Inspection
798d8840-0f4d-515d-8365-9fe8d404d77f | note | RECORDS: Dockets/Photos
29d99d81-1d82-5e5a-97ce-15b0152946ab | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
d03af897-425b-5173-9429-adced6e73156 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
b4794797-d10d-5eb5-ac3c-12c6dcadbb1e | note | METHODS OR REFERENCE:
9abca91c-e269-5282-8ddb-8fa3e1c1e3be | note | FREQUENCY: Every Site
20dfe3f1-c97d-5bc4-8200-71a2a8ef5678 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
259226c7-42cb-5062-92e5-46c49f8e7741 | note | HOLD POINT: In Process Inspection
c00eb91b-22e8-509a-ae5e-014be024b986 | note | RECORDS: Asbuilt records
19da38e5-d839-5275-932e-f6950b0ab4ec | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
9b39b756-b87f-528e-8ef7-3c9315c1962e | note | Prepared by: Ajithkumar Ayyanar
ae13c77b-702e-5aeb-93a1-4c3596d9b945 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Mahia Road - ITP - Traffic Islands | itp | ITP - Traffic Islands | 3186035c-1722-49c7-acb5-0a0ed57a326b
| section | Materials
| checkpoint | 1 - Mountable Kerb
fe174a6b-6723-5158-8a17-3da66be3a6f2 | note | VERIFICATION ACTIVITY: QA FORM
5be71edd-df72-5ff9-9d59-9798dedd5d5e | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
05ffdd7a-d29b-5ff3-8e6e-570da65b8c9e | note | FREQUENCY: Everysite
eb13f27f-287e-5230-b8a5-287712bb887d | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
0c12f35e-2b2a-53fc-93f5-3dbaabe69266 | note | HOLD POINT: Inprocess Inspection
87b5e3b0-7889-5b24-bf8b-ebfe440aab0f | note | RECORDS: FH concrete QA sheet, photos.
e57d32b7-4b61-5558-93cb-5b523a9ae774 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
066b14b4-bfc2-576a-bc66-d04d1f216768 | note | VERIFICATION ACTIVITY: Survey
3d5e93dd-2f93-591a-a904-fef1538a6844 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
fb86f84a-5f8a-5dcc-a43e-b7f64a33a9a2 | note | FREQUENCY: Prior to commencement.
5f27d883-0058-5980-8a3d-0e1290bcdcb6 | note | ACCEPTANCE CRITERIA: Survey
66cc6992-2a4e-52f2-826a-b3c79d251718 | note | HOLD POINT: As per Construction Drawings
17d2a201-242e-588d-8566-9ab6edb1c194 | note | RECORDS: Survey Receipt.
8cdb16ee-2b2a-5bea-91eb-5deb67999374 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
6bd2dba6-569e-5de6-bd4b-ec520000a320 | note | VERIFICATION ACTIVITY: QA FORM
138ea537-68d1-581a-bc48-380bf1044c23 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
a7abd9af-82a5-5af0-b4cd-c729775fcb02 | note | FREQUENCY: Each Site
038fcaae-619d-5398-8875-a950ed690747 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
27667a82-5f04-5c55-8ecc-1efa7fc56cc8 | note | HOLD POINT: Inprocess Inspection
15eb0847-eae6-5ae9-841a-9178f1767615 | note | RECORDS: Photos
6e77a1b9-fc07-5475-acd9-b412aa8f4dcb | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
4dcd0b7f-4ccb-591c-8be3-2ffbef799750 | note | VERIFICATION ACTIVITY: QA FORM
21a4391d-50df-54a1-866a-82d9628f7e89 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
21c3e60e-5013-5739-a08f-86c57d63ebb3 | note | FREQUENCY: Each Site
c3517d4f-433d-54a6-bec8-f335ff5f0789 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
856bb750-859e-5972-920f-e3e1275febb5 | note | HOLD POINT: Inprocess Inspection
6860482e-4733-598c-999a-077100d4af05 | note | RECORDS: Photos
28302420-9c61-5692-9b9b-3a1fbbbe88a4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
6e8a2146-c5fa-5d3d-85e1-538d723e8bb3 | note | VERIFICATION ACTIVITY: QA FORM
90e60718-aec6-598a-b584-dc4970389fb7 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
939e7332-8faa-51cd-8b78-932d566d3eaf | note | FREQUENCY: Each Site
a674be69-ed51-5e48-8f0d-e7249d09d821 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
ae04f648-4f02-5f5f-b7e9-e8cbf6a95015 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
907cddde-62cc-5a7c-915e-14fc59dbb15c | note | HOLD POINT: Inprocess Inspection
e56cb83e-ec9a-5c06-bb34-ad42683efa63 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
6025ffb0-c8f6-58c1-b791-b782bcb51616 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
50d0a20c-6ed4-5163-9fe8-8dfc0fb0149f | note | VERIFICATION ACTIVITY: Drawings
067d36ec-3851-5ffc-bbd7-0cf15fca0e6d | note | METHODS OR REFERENCE:
ae01d63a-4b43-526d-a374-7702f1d4d6b2 | note | FREQUENCY: Every Site
c24ba52f-51b0-5410-973a-2eed5ce3f6ab | note | ACCEPTANCE CRITERIA: As built drawings
781202b4-3958-53fc-bc29-2ce30ec5372c | note | HOLD POINT: In Process Inspection
2d30cbc6-2527-5998-a74d-0f81f5fdcc13 | note | RECORDS: Asbuilt records
d2d88143-65b8-57c5-aa97-bd611d36b3e9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
6f0586ab-c4c2-5365-a538-bcef564da5ff | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
5ee3a77a-9d97-5886-87a4-7f044bb945a4 | note | METHODS OR REFERENCE:
9c4cb526-99c1-5c18-aa8d-cda8877dc741 | note | FREQUENCY: Every Site
253ad8d1-cab8-5336-b3c4-e540e8f7b398 | note | ACCEPTANCE CRITERIA: RAMM SHEET
f7cf996d-ab63-5d1f-9e93-1fd713e2f55e | note | HOLD POINT: In Process Inspection
b63039a2-cb25-54a1-9cfb-2b5b7b857ceb | note | RECORDS: Asbuilt records
3559af44-7b26-5494-a68e-ad11a2ac8ce2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
60cda86c-9a70-5ddb-a9a1-a1b88c0e4eee | note | Prepared by: Ajithkumar Ayyanar
be60142a-1fc4-5058-b84c-11ef05240f26 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Palmers Road - ITP - Ducting | itp | ITP - Ducting | cd112284-f56e-4c05-ae28-e8b8c96d1336
| section | Ducting
| checkpoint | 1 - Permits
87ac5ddb-faac-5cfc-8e4a-e39c0d717798 | note | ACTION (Hold, Monitor, Witness): H
e0ee80a5-f04c-5a8c-93bb-edc8a90387fb | note | DETAIL: Obtain Permits
1d5c047a-a4dc-59d5-9295-5416c4a78124 | note | FREQUENCY: As required
7cbf931c-ff79-50ad-8dbe-8919d6cbed68 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
4bc17724-b698-5a22-b9eb-a4afcb6f0bb1 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
787b6029-d78b-58bd-bc82-8c24d51765c3 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
056edd68-0fb7-5fd2-9c73-d19ca9e1a535 | note | ACTION (Hold, Monitor, Witness): H
713a3070-3546-588f-816e-3d5a52ce7fa0 | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
0f9c22e6-4805-5029-bb23-4bff06a3fb3e | note | FREQUENCY: Prior to commencement
e70f3948-5916-55d6-9740-ce4d4f58c856 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
299ce91a-7c9e-5df8-998a-1d282be6d237 | note | CONFORMANCE CRITERIA:
343dcc10-4096-5bb8-a68d-7fceeab81ba2 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
25b63098-6689-527f-a475-87ce0bb2cf2a | note | ACTION (Hold, Monitor, Witness): H
e7b55f22-b28c-5595-b10c-c918bf670224 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
e8681f87-5b47-5df2-a574-ac0becd88f2b | note | FREQUENCY: Prior to commencement
16272108-c899-5aef-80d4-b92ab30cbd37 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
9c75e188-1302-5190-b317-eeaa36d861cc | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
857c80cd-6ad1-5887-8bde-742f6abae934 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
07c17487-42a9-545c-a44f-2f65aedb60da | note | ACTION (Hold, Monitor, Witness): H
008f8206-a5cf-5fe4-ad3e-c1f7d56c4f07 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
011282a5-dc69-539c-9935-89b15ad79ffc | note | FREQUENCY: Prior to commencement
f4a7ba2a-5c57-5061-b633-693d0bbe03ca | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
bd601d40-2d2c-56d3-963f-686f16dc7035 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
5f8e6524-37be-5b76-8a38-6159262e317d | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
4861ec82-cf03-569b-85b0-0b209451abae | note | ACTION (Hold, Monitor, Witness): W
f9acec5e-4875-5945-a91d-c2b78d028d0c | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
8273dd72-8cc9-5889-b56d-acf6fad0f559 | note | FREQUENCY: Prior to Installation
485bde59-a4e3-5507-8fd3-22d22ec44f9c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
28f99703-fac2-5ab6-92f3-9e9e3d095738 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
8c48ea42-4475-5e44-a1d2-203c7b3b24fd | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
45f11850-1db3-5608-8085-7e44e85cfc93 | note | ACTION (Hold, Monitor, Witness): H
272a2242-5cbc-5a59-ae45-193b7421b11b | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
b7cd8bac-f64e-5c4e-bc3d-18b57a99be02 | note | FREQUENCY: Upon delivery to site
ceed8924-fa94-5130-99db-6db9238e6db3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
64002284-a910-5600-bf5d-05c70039af94 | note | CONFORMANCE CRITERIA: 50mm Ducts
c406663e-11db-504c-984a-ca90724de650 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
e26755d7-c5c9-5750-8a85-544b7782a8a1 | note | ACTION (Hold, Monitor, Witness): H
aa8caafe-79ac-52b2-bd2c-87fd26fea574 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
52f0e170-ab5b-5a8a-94b4-4fd82fb8929d | note | FREQUENCY: 10m Intervals
9c5cbe83-b5c8-534f-bbe1-27792ddc5e23 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
b7fa8e10-c953-5a79-a0a0-399994d8a434 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
8550b33a-bba9-53e6-8674-730a3462528d | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
9b21b867-15d5-5894-b081-1e523b6e5814 | note | ACTION (Hold, Monitor, Witness): H
51b6f494-eb49-5653-8166-368d41e5de3c | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
5381ae36-b967-5804-9aca-04ca1fe48518 | note | FREQUENCY: 10m Intervals
5c9d4a69-799e-54bc-9497-fc7d7c929982 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
77336391-e873-55b5-bce1-db83f7b94a1e | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
06230039-f255-51f1-bf29-032079741642 | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
2c2d5ca7-4f27-5e65-8e51-f96e17bbd782 | note | ACTION (Hold, Monitor, Witness): W
f9401567-3e4c-5300-9281-b56d7ae69dc6 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
f2a42656-063b-5f71-8ba8-782a7c50b578 | note | FREQUENCY: Prior to Installation
821d78d9-f33d-52c6-84fd-97b1789e71bd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
37d207ee-1c9a-5403-9f53-fd31348414e7 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
4cc1e001-6683-5eb3-8f6e-1cd0ea73f510 | note | RECORDS: Photos
| checkpoint | 7.2 -
1a6ae1b4-d526-5dff-a11d-fce5850feb81 | note | ACTION (Hold, Monitor, Witness): H
ef2f7050-c06d-586c-82ce-87f7fa56927e | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
01f135fe-4042-58d5-98dd-aada8d73ef69 | note | FREQUENCY: 10m Intervals
3aecd127-aff0-5c91-a64c-e0ce88ec9905 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
1fec1f72-cc0d-501a-96b2-43dcf6261733 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
c1a40eac-cbbe-565f-953b-f5710e1a77fc | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
580200c8-f16f-5f3e-8708-90c0467f746c | note | ACTION (Hold, Monitor, Witness): H
e0453632-f4f0-50fb-9d56-2f47a79d46b8 | note | DETAIL: Asbuilt Survey
e41fe8fe-1ab7-5445-adc8-b92e1d54ddd0 | note | FREQUENCY: 20m Intervals
8d4fcd84-28fb-519a-b735-e923caaf9ef7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
45fc1684-8ff9-5c9f-acdb-5cc6d51cb150 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
537aefe0-0ace-50b7-a77e-ae378491b02e | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
70696ad4-70c2-594c-9e5c-81fe785d0667 | note | ACTION (Hold, Monitor, Witness): H
a945d2d9-abff-51b7-b6c6-c2baa20fad15 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
db72c925-dd57-5eb1-a38b-a671f5d6ae54 | note | FREQUENCY: 10m Intervals
ab7a8650-2f76-51dd-8874-001ad7e5c3a1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
19dd2111-55e7-51ed-a520-29e8df700f5e | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
aee434bf-44bd-537b-a3b6-cf30139dd797 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
14fee9ac-b605-5f13-a16c-8122944a16dd | note | ACTION (Hold, Monitor, Witness): H
6ab62827-cd04-5cad-8a3b-79ffe8e027e1 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
41628328-d1ae-57ec-818f-39c76a1950da | note | FREQUENCY: 10m Intervals
39767205-671a-55be-a673-0f0e899ea6ec | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
59d9f3c2-09a5-5151-a358-06bb919d1db7 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
e97f4f21-6bc5-549f-a573-883e24bfc6bd | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
8096cbab-9536-51b4-a65b-768a073e01a6 | note | ACTION (Hold, Monitor, Witness): H
8f4928bc-423e-551f-bebe-cfbb2a80c6e9 | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
eed9b7e6-4199-58bb-a0b8-7ef356468462 | note | FREQUENCY: Eash Site
bc68abf5-8c1a-5630-9463-49ae136a03bf | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
0f5f1776-ae66-5438-a034-652fc3998840 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
b06eadad-0368-589a-a8a8-cb78e6022335 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
97c0ab12-8efb-5da3-828d-acabd258e987 | textbox | QA Compiled By:
7221211d-bc35-551a-8ae3-830ad50f59c7 | textbox | QA checked By Project manager:
fe12e82d-7fa9-53de-a1a3-54a7ac82eb8e | textbox | QA checked By Contract Manager:
35917884-bcbc-5d6c-8000-0b708f5d064e | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Palmers Road - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 545559bc-d335-4df1-b5a5-f17001837c7c
| section | Site Set Out
| checkpoint | 1 - Site Set out
6fbb5e43-e803-5146-9ab5-0de6d2bd18d8 | note | VERIFICATION ACTIVITY: Surveyor
73ec3169-0952-527d-a513-3c9f4d7e068a | note | METHODS OR REFERENCE: Surveyor
021baf75-fcbe-5a28-ac69-a52351ccda01 | note | FREQUENCY: Everysite
58b2bb2f-9249-5d91-8bcc-6731feda141c | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
3bd7f82c-cac0-519e-8e31-ebb144bee802 | note | HOLD POINT: Mandatory HOLD POINT -
e1c74e2c-b65a-5b9b-82c4-ad614e75c0df | note | RECORDS: Onsite records/photos
db776aeb-c8c7-5c8c-bcd0-9e621255e5b8 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
e6574596-d255-5650-a753-736a702b68fb | note | VERIFICATION ACTIVITY: QA FORM
18014137-e7dd-5c50-81f1-acfbc2a05c0a | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
c9028680-8617-54d2-b686-46ecfef6cb6a | note | FREQUENCY: Everysite
6951d833-8a4f-5344-b468-95fca65b3766 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
46839cb7-3d9e-5c9b-8b5a-83faf3257a4f | note | HOLD POINT: Inprocess Inspection
1a1dc05b-b713-5502-83ee-790770b6424b | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
b0d1d4c7-e5dd-591c-bf25-9fb454c42da7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
2d45c041-414a-504c-ba0e-93b220faeba0 | note | VERIFICATION ACTIVITY: QA FORM
6d0963d8-b330-51a2-b8d9-42d8fdc861fe | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
3598aa00-d03f-5f30-b89b-4bbe480a655f | note | FREQUENCY: Everysite
611c14b4-b899-5b3c-a390-c1ab75f8a404 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
4b83d36c-cc51-58ca-9b78-2691ab323381 | note | HOLD POINT: Inprocess Inspection
841844ce-e3c0-5c7d-8273-77777b39fa3f | note | RECORDS: FH concrete QA sheet
743cefa1-e29b-51b9-9cf4-0f26544ef7b7 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
4764375b-ba33-52fa-92cb-0b9973f00790 | note | VERIFICATION ACTIVITY: QA FORM
b77ad718-dcdd-5907-9e87-95accaf3cd59 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
283818eb-dea4-582d-afa3-f896a18f61b9 | note | FREQUENCY: 10m Intervals
0da893a1-4760-532a-89a9-44efa2893a23 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
3e51db9c-a881-545c-9018-fd3737aaf0bb | note | ○ Basecourse - 100mm min. thickness
51934837-e62d-5b03-95eb-228dfb66ce4b | note | ○ Clegg CIV > 12
1f8c23dc-0150-5f9f-bc8b-89eb0980178f | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
d38e8d72-3c89-5be9-b84c-45938119dcb8 | note | HOLD POINT: Inprocess Inspection
9cb3a87f-89ca-5f83-9d24-590cda58648e | note | HOLD POINT: Prepour inspection
60fdf6e3-ca5c-5291-8c2f-40d184bd33b9 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
915afa74-1866-5c34-ba91-0df5c3297dcf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
08a293cb-3b80-5657-837a-8368040fb706 | note | VERIFICATION ACTIVITY: Visual
a75abd3f-55bd-50d4-bb90-04464f82e213 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
e79d2bb7-0e72-5802-ba07-2d3f45e13015 | note | FREQUENCY: Everysite
51a90bf5-7884-5553-903e-429cc7b381a7 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
ca1efac6-0bb9-5559-9500-6ad1fe2a18cc | note | HOLD POINT: Inprocess Inspection
2a390f13-d181-59bc-9a21-89e27d867df7 | note | RECORDS: Photos
98cba227-d61a-5c20-8561-dd090e01eeaf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
c944cae1-2c7b-559b-9893-cf67130ae175 | note | VERIFICATION ACTIVITY: Visual
f04f3da8-3d31-53dc-9893-0191c06c0c38 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
98100c3b-44d6-5321-bfe6-a9d0191d7a7a | note | FREQUENCY: Everysite
462cf4d2-2a47-5494-b1d3-ac41b29648ee | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
7aa34d42-410a-5433-9729-04128423a6de | note | HOLD POINT: Pre-pour inspection
49578548-1f75-5faa-b193-a8304289c384 | note | RECORDS: Photos
82b2f359-a2b6-54d5-a423-7c0c7200b2b0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
128c3e6d-6000-5dec-868d-87abf30289c4 | note | VERIFICATION ACTIVITY: Visual
20622b54-66bc-58f1-81d7-b25948603216 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
5e5117e1-e138-5767-9aaa-994769350388 | note | FREQUENCY: 10m Intervals
236fcf96-552c-5959-874d-3f2f89b4f655 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
442b4239-5ff8-592d-a6c0-9fc7ad2143f1 | note | HOLD POINT: Inprocess Inspection
6b26843e-c307-5e4f-8bfc-ad8a63181357 | note | RECORDS: Photos
e7ed6574-92ee-57fd-9114-c3be42b47558 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
4142b104-bf71-5498-9f33-05d347413180 | note | VERIFICATION ACTIVITY: Visual
668279f9-e1e8-5a0a-925c-37cb0ea3d4c8 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
6947e3a9-be9f-5b1e-b646-258399c28484 | note | FREQUENCY: Each PX
4c0b4985-c492-5c94-a556-252b9c594c2b | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
d7e415c0-5a52-5d31-b0a4-13b82dfb5a2c | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
e8fe92d4-e781-57ce-bc9f-c5aa6dbc4961 | note | HOLD POINT: Inprocess Inspection, Measurement
20ec18b0-b329-5809-b609-c4e10bb5c808 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
bededd7e-c00e-5287-ad59-5d8471f36b5a | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
67031294-3e15-5d9b-b571-b7b2107a5e81 | note | VERIFICATION ACTIVITY: Visual
1e1b1c13-a0f8-5173-a508-3003cc1161e7 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
5659468b-c018-5415-b6a5-ab0b54832e00 | note | FREQUENCY: Everysite
0a5885f2-a0c8-5d9d-881c-68c734abcbe4 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
bbe641e3-f1f8-53cf-809a-dda666bf823d | note | HOLD POINT: Inprocess Inspection
a728379b-83f3-5ca2-9d20-19a246d40b57 | note | RECORDS: Photos
fd78f1a5-3acc-5776-9b35-dd7333033e33 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
36484a20-ca01-5b9e-942f-af550a6d84a8 | note | VERIFICATION ACTIVITY: Visual
91322380-7df1-588a-939c-28dbe6fcef5b | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
e4e73f47-5ccd-51ea-a166-b699bdd715aa | note | FREQUENCY: Everysite
2c0b7dae-4cca-5990-80db-b4fc86afb34d | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
97db0f0b-160a-5c5e-9c3d-020d6a39322a | note | HOLD POINT: Inprocess Inspection
60601f57-6852-5169-bec0-4574658a330b | note | RECORDS: Photos
68b3b0c6-578a-51e7-88a8-6b204003d338 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
92b34fcd-596b-5caf-b768-79294cc4339e | note | VERIFICATION ACTIVITY: Visual
51e43a43-e9ad-57b4-8e5f-a90073da8583 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
b03ccc9c-7db3-5baf-879d-1b837d17101c | note | FREQUENCY: Everysite
b84666ac-b911-5548-be10-c0512349ca76 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
25004537-5fb1-51d1-a42a-c7e3a908c8c5 | note | HOLD POINT: Inprocess Inspection
76da4592-6448-5c45-b9ef-71b28d4963b5 | note | RECORDS: Materials Dockets
1df9eead-262a-50ef-8b6c-eabb11f6e7f0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
818582d1-61b2-59a4-a6a5-e39ff3b61663 | note | VERIFICATION ACTIVITY: QA FORM
020fa514-0a6e-5ac5-8348-779a4c564bdf | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
2f70c251-8606-53d7-9dee-bfdc0a6385b4 | note | FREQUENCY: Each Crossing
06c07ac5-2a69-50c3-a222-23c2e029bb33 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
a91f30af-ca2d-550a-89fd-433742478421 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
b049b87f-86ff-5736-9e09-7081c09ad7e3 | note | ○ Slope no greater than 1:12 where practicably possible
8292caba-7dfa-5421-9e42-405c1a938940 | note | ○ Clegg CIV > 12
abc970df-2a26-5ad2-817d-c1f3cb90b3c5 | note | HOLD POINT: Inprocess Inspection
bbb640f9-3f50-58b8-ab54-0edf6c5866d7 | note | RECORDS: Photos
301defc7-9d74-55e4-82d4-aebd0ddb5981 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 10 - Timber Retaining Wall
70198eba-63bc-505e-a986-2ba20b0b9f17 | note | VERIFICATION ACTIVITY: Visual
40cc6f89-d0cc-5cfd-ae92-5fe32f2407bc | note | METHODS OR REFERENCE: TDM ST0004 - Version A, Timber Retaining Wall Detail
4e1a2d85-4abe-59f3-9805-0144e70f219b | note | FREQUENCY: Everysite
6d4ef828-1011-5774-855d-6d479d6fc55e | note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
20e827fa-c72b-5077-bb57-f053079c7ea3 | note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
804aaf30-eedf-5442-9932-c9672cf3b0e5 | note | ○ Retaining wall slope to be 10:1 grade.
ebbe8b97-ec4d-58b7-9394-e46b0b4394e9 | note | ○ Maximum height of wall = 1499mm.
8fa1dd8f-fcc2-5f96-801f-7d79dfe4bbfe | note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
0dca7510-a061-5f1b-b771-27c56a9f8237 | note | ○ Subsoil pipe to be lay as per TDM and connected to the nearest CP
c92f2868-2891-5933-86cc-3a70fa7cfed9 | note | HOLD POINT: Inprocess Inspection
77d275e8-c93e-5c16-a841-7bac4d8b8724 | note | RECORDS: Photos, Material Dockets, Dimension checks
15adf062-7166-52f9-b24a-b0524bd3a73c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
a0cd9137-a8dc-51be-9d1d-7aa24a506bae | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
48ee0d62-02fe-51e4-8ac1-98ec5c1d75d3 | note | METHODS OR REFERENCE:
9764b8be-55a0-5cae-b6be-891e01184fc9 | note | FREQUENCY: Every Site
3adf5a3b-2aeb-5160-a045-fe8e781f3939 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
6be55967-939e-5717-9b4a-6709636fe119 | note | HOLD POINT: In Process Inspection
504e3005-b7d4-57d7-978b-acaf452ab8be | note | RECORDS: Asbuilt records
a76dfb4b-8827-5afd-ad3f-eae1da471bdd | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
1e08c428-cb7e-5183-9451-01c3dc7efc07 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
8a009a08-d339-5881-b68d-af9eef5d53ee | note | METHODS OR REFERENCE:
9842cb5b-e0c0-5498-a472-b49b23935c42 | note | FREQUENCY: Every Site
377ecb79-de3d-5035-ad20-0851cade6af3 | note | ACCEPTANCE CRITERIA: RAMM SHEET
1a27f0a0-b710-5840-bc3d-9a54e1f26acf | note | HOLD POINT: In Process Inspection
bcd314bb-f972-5715-b49a-38fa5d0b5aad | note | RECORDS: RAMM Sheet
13cf1956-8bd4-5bec-8929-0e35bce87e90 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
c7e2bbe4-e0d0-5fa7-8021-20881de3b19e | note | Prepared by: Ajithkumar Ayyanar
1b51dc0b-f5ec-59d9-af11-82d9a00e8104 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Palmers Road - ITP - Signage | itp | ITP - Signage | efc13daf-2942-4911-be3a-7881a99b8adb
| section | Site Set Out
| checkpoint | 1 - Site Set out
f64f24f8-3aac-56ba-b4f3-fb0c9dfff817 | note | VERIFICATION ACTIVITY: Surveyor
d836490c-496c-537a-96f7-584b5068e62b | note | METHODS OR REFERENCE: Surveyor
69a363a8-6e3e-583a-a84c-638ea5ebff03 | note | FREQUENCY: Everysite
e5c859c7-84ed-5e44-af08-0c03fc520d17 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
6afd4ffd-9a73-5038-81da-d660e38a4c96 | note | ○ Alternatively like for like
a1082aca-da44-578e-8cef-4cf4d72a9a2f | note | HOLD POINT: Mandatory HOLD POINT -
d514a795-ea21-5918-9f29-c03d6c7520e2 | note | RECORDS: Survey Receipt
a6c1237c-5b1d-5db7-81c6-c7fe03d63279 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
6e52a0e4-5f4d-5c9d-a20d-e988c79608bf | note | VERIFICATION ACTIVITY: QA FORM
729278dc-37ef-5f2c-bff9-746ca9b13e02 | note | METHODS OR REFERENCE: TDM Technical Standards
4e6b3f2b-7bec-5587-b021-791616b0e7c4 | note | FREQUENCY: Every site
3f3d6026-57ae-54f7-8cd9-22040c9f745e | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
db85241e-78c2-57ee-b578-ea9b4326a831 | note | HOLD POINT: Inprocess Inspection
fb44889f-7432-5cf8-bf9e-8cd2e0b57e06 | note | RECORDS: Dockets/Photos
607304e2-2eda-5363-9cc9-8ac18a08fe7b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
d6e635cb-9070-5a7c-8759-5166092a29d3 | note | VERIFICATION ACTIVITY: QA FORM
d5649292-1ae9-5f86-a65a-24c3fada63f5 | note | METHODS OR REFERENCE: TDM Technical Standards
b11e5c8b-1af4-5a90-bace-c130fc8045f3 | note | FREQUENCY: Every site
78cbe1bc-f51f-51d8-a1ea-faf808e590c8 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
e9a838f5-f512-5c71-917f-ecdab39bca4d | note | HOLD POINT: Inprocess Inspection
7d54ba78-cd9d-5f12-8fa0-b5bf2278dafd | note | RECORDS: Dockets/Photos
a94193eb-1afe-5f7c-9a84-5cbd39bcdcda | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
01a85680-e682-5ca1-a8e1-34d49b27a60a | note | VERIFICATION ACTIVITY: QA FORM
0172b7e2-8277-585c-ab97-11db5d28f474 | note | METHODS OR REFERENCE: TDM Technical Standards
c7b2fd4d-9392-5e33-8aa2-16ec0cad2f1f | note | FREQUENCY: Each Socket
ea1b6ee3-91d2-509d-925b-b6b454d21ad3 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
9a94fd68-d307-5a96-b5fa-e5740f0e0955 | note | HOLD POINT: Inprocess Inspection
b056b44a-51de-526b-ad9d-41de1d1f52af | note | RECORDS: Dockets/Photos with tape measurement
61063e25-b95a-58a9-b4de-d61e929c7cd1 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
8c983a0a-bf83-5729-98c2-1fc6bec0e14a | note | VERIFICATION ACTIVITY: QA FORM
ad36abbc-59ea-500c-839e-f78c7a31238c | note | METHODS OR REFERENCE: TDM Technical Standards
912fe86d-de0b-5f12-a383-7a4440176696 | note | FREQUENCY: Each Post or pole
cf36d4ab-d0dc-5ee9-9c68-3475e485c393 | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
0d661d82-0d1b-5789-9d0f-d5fde7b320b0 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
635432e5-428f-5ed7-a453-93dfec6e648c | note | HOLD POINT: Inprocess Inspection
b26c68ab-d252-515e-bd7b-d7e3736de3cb | note | RECORDS: Dockets/Photos
63b94e51-6a7a-5792-bf74-d0ea539b3a7d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
1972820b-3024-5210-bf48-4ff0b0836a72 | note | VERIFICATION ACTIVITY: QA FORM
0e3a7412-3592-53a9-8cdc-ed68d8dae88d | note | METHODS OR REFERENCE: TDM Technical Standards
066274ab-4c7f-5e43-8fcc-c78153385dac | note | FREQUENCY: Each Sign
a129345a-bebd-5575-b57b-e97d5bb63878 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
a11d4402-fe79-52a7-b8f3-7130429bf1db | note | HOLD POINT: Inprocess Inspection
9b23ff1e-f483-5e0f-bb58-32c9e89c3cab | note | RECORDS: Dockets/Photos
77556e56-34c9-56be-b6ca-6b1fb6d20593 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
4b31a462-74b1-59ef-ba0f-39b832abc47f | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a5ff20b9-8ba4-55a0-9f22-d951af397385 | note | METHODS OR REFERENCE:
3d74b0b7-5243-5e41-8f0a-1bac80b67f86 | note | FREQUENCY: Every Site
c26eb674-3d3e-516a-914c-14914ced5908 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
9b975f82-9acc-56e2-9bf3-b0f473840d51 | note | HOLD POINT: In Process Inspection
c32b0877-50e8-5bbd-97dd-d0bcac9ad2c0 | note | RECORDS: Asbuilt records
54d72810-5a83-537f-ad98-4442111753ec | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
0d5923f8-5a5a-5feb-83ee-857b934cacec | note | Prepared by: Ajithkumar Ayyanar
397cac36-39b5-5c11-baa2-1fe2ca158d92 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Palmers Road - ITP - Traffic Islands | itp | ITP - Traffic Islands | fc062a4c-ae42-42df-a2e7-748a1b4fe1cd
| section | Materials
| checkpoint | 1 - Mountable Kerb
1574b79b-b059-5965-8244-c0abe0aec4e2 | note | VERIFICATION ACTIVITY: QA FORM
ac82a58f-feae-5598-9f1f-63b4bbbbddb7 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
4f563a70-087b-5394-b976-9beb90d68ba3 | note | FREQUENCY: Everysite
6339b494-2682-5889-a368-6e5b40454005 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
ae72cae1-8063-5ef1-8b5d-14a3b7f6aa68 | note | HOLD POINT: Inprocess Inspection
76b6a873-19f0-57da-b70a-1a32a4159e4a | note | RECORDS: FH concrete QA sheet, photos.
88dc8494-a660-5a49-98cf-c8208483353d | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
6d33833c-6b60-5306-a8f5-8879ea98d1ac | note | VERIFICATION ACTIVITY: Survey
695ddb19-acd6-55c8-a497-c56f8ea47c8a | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
0c46a87c-0d59-5f05-be13-ae39125dbcb4 | note | FREQUENCY: Prior to commencement.
f0afd62a-481b-569d-93c4-3f45fc372116 | note | ACCEPTANCE CRITERIA: Survey
eabd0875-c8e6-5057-9a10-8be24cdb33fc | note | HOLD POINT: As per Construction Drawings
fec71435-8bc9-5192-b98b-af75042cadc7 | note | RECORDS: Survey Receipt.
681808ba-b4a6-56e8-9a97-9426c6eaa97f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
985d8752-a8cc-5f7f-95a3-763853f2261f | note | VERIFICATION ACTIVITY: QA FORM
d37b38bb-87d4-55d8-8d4a-a8477845212a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
b9c4dde3-9069-55c9-8d51-fee12e7ab236 | note | FREQUENCY: Each Site
adef8c7a-550c-51c2-abcb-08634b972a6e | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
4d49ed79-2972-530c-a9f9-755a0abb2ec5 | note | HOLD POINT: Inprocess Inspection
39386409-8b6c-50b8-9f2d-28e88233ccfe | note | RECORDS: Photos
6c4a6e18-812a-596e-824b-2071e3783795 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
ae9e5a02-6380-50b4-96f6-9ede22c76a27 | note | VERIFICATION ACTIVITY: QA FORM
237e4ad9-3f91-590f-943c-13a55f3e819e | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
7757caed-05a4-5125-8b90-6a7fc5cc358f | note | FREQUENCY: Each Site
3a06c8f9-a847-5259-8345-6b3b80f9fa95 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
999fa942-39c0-538a-902d-77b8e44d94ad | note | HOLD POINT: Inprocess Inspection
9248efda-7f9e-5e52-bf4f-ff05f45f7ed6 | note | RECORDS: Photos
959cceb0-593b-5e56-8e0b-e2b57bfc518f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
40480d91-22b4-5a07-89b1-0c867238e2ae | note | VERIFICATION ACTIVITY: QA FORM
45fe81d2-12b8-5465-8194-115c7cf6f7bb | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
06ad5892-a3ad-5f1f-8a27-e38e198924d9 | note | FREQUENCY: Each Site
ff104520-26e0-568d-b66f-dfbabb8b46e7 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
7fdea0cb-61cc-5a83-872f-4539676cfd97 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
908d6b78-c337-530f-b2ca-e1bcbbfcd8c9 | note | HOLD POINT: Inprocess Inspection
ab7e8efc-0856-55f3-ab95-98eaa92e8b29 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
1b943fd6-ea75-55ef-b14f-9a4c0c0f1be5 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
8e8a505c-354c-55bd-8309-b7c00d8c8bfc | note | VERIFICATION ACTIVITY: Drawings
f7062c09-9757-59e2-82e4-f269c1f694f2 | note | METHODS OR REFERENCE:
9d7d53f4-0826-5ee6-9856-5b8cfa7bb4e9 | note | FREQUENCY: Every Site
fb0bfcca-e3cc-5029-8582-5669098ab045 | note | ACCEPTANCE CRITERIA: As built drawings
9d249c01-6fde-5ef4-a4b7-48d3d2807920 | note | HOLD POINT: In Process Inspection
40cbf358-6aba-5b51-9ed6-f879a8331017 | note | RECORDS: Asbuilt records
797d12d3-7503-591d-a466-eeeedf571742 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
0c1be3f0-8460-55bd-a2b1-c56414aed892 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
ccd6c562-f58f-5b4b-82d3-9cea66021155 | note | METHODS OR REFERENCE:
d5d0ebc3-9c1f-5b05-bcd9-2427f917861f | note | FREQUENCY: Every Site
1b3e0d40-e529-5c1b-b27d-6d0b4aae2666 | note | ACCEPTANCE CRITERIA: RAMM SHEET
68152a24-3a16-5614-99a0-3d31fd3f3b20 | note | HOLD POINT: In Process Inspection
eaef7b36-0e8c-582d-b414-c13f80ff5d0e | note | RECORDS: Asbuilt records
7a5a015c-22a4-509e-b169-7bea50e7ecf2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
7570a1e2-1892-545c-8e85-e50c08b66bd8 | note | Prepared by: Ajithkumar Ayyanar
c0973a17-1e1a-5622-947d-72e51844cdca | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Rosscommon Road - ITP - Ducting | itp | ITP - Ducting | 7f0fa349-e029-4e51-9d66-32fb3301743b
| section | Ducting
| checkpoint | 1 - Permits
4a221597-9bc0-5c8f-aa76-b99a60e57bf2 | note | ACTION (Hold, Monitor, Witness): H
d5ff6365-ba6f-5ab7-b5ed-d55333cca5de | note | DETAIL: Obtain Permits
34f0db00-e40a-54a2-9cd7-9693f7fda208 | note | FREQUENCY: As required
2380ec96-ac14-5451-97c8-fca715962e69 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
681d41c5-2f43-50c0-ac1a-1b5c4f081d52 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
c5366427-d6d9-5c16-ab92-ed9948c2e20d | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
a5bc1782-d5a1-52ed-8c0d-72ea8bf8517f | note | ACTION (Hold, Monitor, Witness): H
79f07508-f36d-5f31-ad70-6992ef8c93fe | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
aa9ca726-be9c-549b-9a0b-76dbefaf6e56 | note | FREQUENCY: Prior to commencement
a645970c-b7df-5ed5-9c70-4e5aa3d79c33 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
31d50583-75cf-5ae7-a578-cab7c666ed8d | note | CONFORMANCE CRITERIA:
eeb69524-113d-5a80-84e7-e0503ec72407 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
2a93afd3-24c3-5528-80d4-d6c394249b28 | note | ACTION (Hold, Monitor, Witness): H
ab38d576-9269-5651-88d0-d61b4cb408eb | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
8d1ef973-a301-5a41-a882-0178b3eedb73 | note | FREQUENCY: Prior to commencement
c33d2f0e-695e-5832-a7d8-ece50acb40f3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
299402f0-2e53-55bb-8eaa-4d9c74886000 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
b0c99f58-7f2c-5cdb-a344-f7aeb13bc619 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
bd60b85a-b0e0-582e-8fbf-ac85eb01d6c3 | note | ACTION (Hold, Monitor, Witness): H
6bd5e31a-241f-5d8f-95db-30d472481571 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
e503cbee-ec64-52f6-8362-07f610c2fac6 | note | FREQUENCY: Prior to commencement
f6f68020-26f1-5673-a35c-d19bf47232f7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
0df04988-95b8-50a1-9e54-008a5501c768 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
bd493de2-7b1c-58c2-b940-c853f89e61a9 | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
7113b9b2-d1f6-5c22-9b53-a3b08761cd9b | note | ACTION (Hold, Monitor, Witness): W
89b24d41-9718-5edf-bdaf-6bf40bff2e03 | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
ae4a6a12-5221-5553-84f7-2c8398608c37 | note | FREQUENCY: Prior to Installation
a2ca2205-596d-5e66-9560-64e2ee4ae46c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
6014a47d-80c5-57b4-8d88-56b01bf6d05e | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
7f2d8381-4b60-578d-a519-c7e7df76ef0a | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
aed2c862-6cd3-5e49-a941-0b6dfb6b0964 | note | ACTION (Hold, Monitor, Witness): H
0666b199-925d-5493-9917-8d4168973544 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
b79d54c7-380d-5924-8320-288f061b02c2 | note | FREQUENCY: Upon delivery to site
96367c2c-a4d2-5c45-9799-21569e509656 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
8985ed2b-e8ce-5aa4-812e-73bab90f3283 | note | CONFORMANCE CRITERIA: 50mm Ducts
e36446cf-30bc-5e69-9323-f786705c10ed | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
58e1a336-6176-5779-9bb2-47f39b5350ef | note | ACTION (Hold, Monitor, Witness): H
7a104d59-dfcf-5d30-b539-8be1bec7c9ef | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
da7319c6-e873-58ea-9044-2146aae15873 | note | FREQUENCY: 10m Intervals
63962fb3-db87-58c7-b9b5-514a5469e329 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
e0208620-694e-5f1f-9320-d628c60397cd | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
93fc8904-6dd9-57b2-a47c-a3101f6ad399 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
9cf809aa-f599-5a68-b53e-f6cd70ac3e38 | note | ACTION (Hold, Monitor, Witness): H
29f645ac-19c7-5bf8-b34f-d941522bd487 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
1d89d8d4-9534-51d3-bb0f-712859a81645 | note | FREQUENCY: 10m Intervals
2b30ffc4-1b3b-5007-a2d2-5983e55d8e31 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
bf80fa42-8a75-5ba5-ad55-fd53601d344d | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
ecf3643c-8846-59b0-b08a-9c5f540f441c | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
33bda02d-20f4-5b38-a42c-8bf11a11b3d0 | note | ACTION (Hold, Monitor, Witness): W
8135dd66-183b-5045-9459-e28c80c78241 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
d63304eb-86de-5d24-ad94-7e496c5fe561 | note | FREQUENCY: Prior to Installation
1ef96e12-163f-5544-8b19-bcbc4322e7fb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d530962a-4a08-5ce6-b9c4-465cbc41d6c9 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
282491a2-2df8-5caf-9769-592a5f88f790 | note | RECORDS: Photos
| checkpoint | 7.2 -
4c5cb439-9ef7-55ba-841d-6a33c2492e3d | note | ACTION (Hold, Monitor, Witness): H
6a030f02-c491-5bf8-814a-b45bd528c361 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
3962bad5-d8bc-59e9-b322-7625086d83ed | note | FREQUENCY: 10m Intervals
b9f9d515-d031-5986-ab08-5936dae91b94 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d0ba2a58-0058-5056-a3c0-52f1c559469f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
ef714c03-3afc-5dad-ba76-33db5ab999b8 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
c98ec84d-e8c8-5653-bd17-133bd71a6f75 | note | ACTION (Hold, Monitor, Witness): H
bd13b432-0696-5656-b9f3-b7856200d43c | note | DETAIL: Asbuilt Survey
fe6cb270-d07b-5ae6-8893-8d2c3cb8a9a2 | note | FREQUENCY: 20m Intervals
90e79b25-c222-527e-98b7-dc64e997d985 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
b54b27ff-37d7-50ec-a68d-c35e36d40096 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
8ba697e1-e706-5e5d-aff7-1dfbcc4e46aa | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
449ea463-7d48-5760-a5a9-9c91faee65b0 | note | ACTION (Hold, Monitor, Witness): H
fcd93864-39d3-5629-95dc-c0960b026cc5 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
23391681-692d-5630-92d6-a8e909d86e2e | note | FREQUENCY: 10m Intervals
49f7b020-bb5b-5969-8ef5-55638d4a7146 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
c7d0405d-39e2-56cc-8724-d76c233245da | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
b356984d-ab31-529f-a4ab-d2050a7e3930 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
c2f3a9d3-c0e1-5ed2-9dcf-3d0736d496d6 | note | ACTION (Hold, Monitor, Witness): H
8bdcf7d2-16fc-5488-a430-1d0b9b6812ce | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
b54fd821-96ea-5783-9774-20fb5cf4c1be | note | FREQUENCY: 10m Intervals
12c84b78-6d60-5a1f-aba1-92be4e4988c4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
9041da5c-e7f7-56c3-a541-79b8651a0802 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
d0616623-a263-5fe2-96dd-8864c97ad279 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
9aa1de18-4b96-5fa1-bd14-f545f1ac8c44 | note | ACTION (Hold, Monitor, Witness): H
5ba87367-d0da-51de-aedc-9221bcd3d5a0 | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
5e3952da-ae28-5066-b2c7-402d344d2e11 | note | FREQUENCY: Eash Site
c63013aa-11fa-5aa2-8a4b-23de965d77ae | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
a992c9fe-149c-5237-b46c-4787205ac716 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
728ddd54-2667-5bcb-860d-0dc451c25911 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
17378975-b57f-5ee6-b14e-98d44666ce0b | textbox | QA Compiled By:
29ba0863-ee05-52ac-8303-b70583e994ce | textbox | QA checked By Project manager:
623a06a6-f1fa-5c3d-9069-4e8e959c094a | textbox | QA checked By Contract Manager:
1f81f9f3-003a-5684-911d-53d5d1e3469f | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Rosscommon Road - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 5af6fe44-4e08-4912-a5a8-74c8bb573a45
| section | Site Set Out
| checkpoint | 1 - Site Set out
ad657e25-e5f6-5f3b-aa10-dbbb7b221141 | note | VERIFICATION ACTIVITY: Surveyor
5c8d16b6-a73f-5856-8465-abea0b823a92 | note | METHODS OR REFERENCE: Surveyor
8ddeb1c1-0c8d-5f4c-bb26-9dce66491480 | note | FREQUENCY: Everysite
55b037f3-e84b-59dd-bbb5-8c849db04a02 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
70085e01-db35-563a-86df-648b7aaa8800 | note | HOLD POINT: Mandatory HOLD POINT -
a27250e0-4a7c-5552-96b7-511efd3cff15 | note | RECORDS: Onsite records/photos
e75cb62a-48c0-5548-b592-918c87eec5fe | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
e688d384-bd51-593f-b627-f1c5234b0ebc | note | VERIFICATION ACTIVITY: QA FORM
f9fcbdb0-61a3-53ba-ad5c-c19053c45633 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
ba9d4ac5-505b-504d-bb0d-cf26c23bbef8 | note | FREQUENCY: Everysite
9db3b742-ece7-5fbb-a0d7-34edb85f1eac | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
06c26e4e-4188-57a8-a5d0-e347a9139be5 | note | HOLD POINT: Inprocess Inspection
a347b743-aeb7-5281-a668-890f90cfe0a4 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
37b667b4-5487-5467-bc88-8734a42fed5f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
93e6a675-47c4-500f-b033-98723f093507 | note | VERIFICATION ACTIVITY: QA FORM
f147c23e-d2d8-5809-bd7d-7f142967d273 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
02ebee4a-baa5-50d6-a5b2-65fc5d9ca535 | note | FREQUENCY: Everysite
9d142f39-7a2e-57c7-8ff2-e380f691dff5 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
057b21a0-ff89-51e9-b88b-a73ee3ce4e34 | note | HOLD POINT: Inprocess Inspection
6f2cb095-1fd5-5207-8a1b-7124dca79df3 | note | RECORDS: FH concrete QA sheet
1d9d27cc-ef9c-5e64-8105-03d58e151d9b | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
9335c84f-cadf-5a21-bcb0-039429112e68 | note | VERIFICATION ACTIVITY: QA FORM
9c4bcd75-48b9-521d-80b9-c1ff2471bcbb | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
1e46deca-2f91-5360-9461-de4bf216bf69 | note | FREQUENCY: 10m Intervals
c44b2cea-0847-5de2-ab22-b469fefedb60 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
272ac8d6-b03f-5a0b-bb9f-a8cac495e9ff | note | ○ Basecourse - 100mm min. thickness
d288566c-5f97-5d7f-8c4e-e521f732d884 | note | ○ Clegg CIV > 12
1e181211-1443-5fbf-928e-b576d148aa00 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
eb8c946b-cf17-52fe-a817-86ab748843a5 | note | HOLD POINT: Inprocess Inspection
b6cb0330-3ff2-5073-bd0c-8a0a07a5991a | note | HOLD POINT: Prepour inspection
a0dedd2a-906d-56f5-b390-3c87366fee0b | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
eb6ae857-8438-5c07-88ef-fd7026bdfbde | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Shared Path Pavement
aad7e60d-2f09-5499-86be-f4db08d93b7d | note | VERIFICATION ACTIVITY: QA FORM
d8ca3500-a523-5abf-98d2-dd826a3ffb4f | note | METHODS OR REFERENCE: IFC
ad97bb8c-17da-5331-90ce-4175d8bc1a17 | note | FREQUENCY: 10m Intervals
dfef0460-9f83-5df9-b029-674c22b236c4 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
04dd2765-8a0d-51a9-955e-ae777c127ccf | note | ○ Basecourse - 100mm min. thickness
e0332ee2-e9f4-5f93-b397-476916974ce9 | note | ○ Clegg CIV > 12
805eed83-b8d4-535f-bf8c-b3645e3874b9 | note | ○ Surfacing - Concrete 150mm with single layer of 665 mesh(50mm cover) and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
743e9b51-2856-5c5c-b9e2-c9f2a23a7af1 | note | HOLD POINT: Inprocess Inspection
4f2c5b7d-878e-5b08-978d-96e70e937da1 | note | HOLD POINT: Prepour inspection
526289c0-d291-5f29-a1af-ba7388b2bd83 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
e91fe197-2aa1-5bd3-b256-532f8e4bd2c7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
71ec8d30-5efb-5939-9228-6bf75570061f | note | VERIFICATION ACTIVITY: Visual
48ffc612-7a85-5757-b3bf-0812e3c29964 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
ebe26c94-b68f-539a-b3af-cb37b1a97552 | note | FREQUENCY: Everysite
52ead3e4-67e5-5311-819a-385b560a4924 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
93364fd0-a886-5f39-b68d-eaabc1e57ba0 | note | HOLD POINT: Inprocess Inspection
c71e2f42-e887-516e-92d9-e25325d273a9 | note | RECORDS: Photos
f2f3db85-0812-53dd-9023-05f2e3408620 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
423903bc-b2d7-5731-8a2f-6dd5cb26fcb4 | note | VERIFICATION ACTIVITY: Visual
40e0938d-0e01-5b42-8745-765c8d6d703c | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
f1bab4b6-773b-5d42-8d3a-f31cbe39d5ec | note | FREQUENCY: Everysite
da8bd5f8-f7e9-5985-bad0-d0c9d34c92fd | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
af995dfb-f397-5335-ad1d-1781bc4c46f4 | note | HOLD POINT: Pre-pour inspection
042c2dea-9881-5f30-b2c6-008be1e15052 | note | RECORDS: Photos
36bd5157-5ab4-53d5-8289-679eb34f8684 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
6a34858d-af78-5f5f-b57b-4fb0b8a8e9c7 | note | VERIFICATION ACTIVITY: Visual
24adfd9a-7599-5e49-b464-f94338f216fe | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
d7279d7a-1472-5fc3-b1f7-5a5b9cff34a7 | note | FREQUENCY: 10m Intervals
3aec6760-d1a0-5da1-b248-817ac387d4dd | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
7f1f77de-eaa0-550a-a3f5-9b40c662ff94 | note | HOLD POINT: Inprocess Inspection
55332ac3-5cb5-57a9-bfdd-ac061412df1e | note | RECORDS: Photos
6522c511-f49b-5c3d-a4e4-80e8b5c93a14 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
cfb198ad-48f7-5300-9869-58044bf27ea9 | note | VERIFICATION ACTIVITY: Visual
cfed74a5-0387-5488-9d6b-588aadb38edb | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
67db75c0-125f-589d-942f-b5eb804dad47 | note | FREQUENCY: Each PX
850aadad-14db-5eba-800e-71b5640445ec | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
d940eee6-a21d-5568-80ee-3efa06e215e4 | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
b20fd525-d0fd-5bc7-b892-11ca36444199 | note | HOLD POINT: Inprocess Inspection, Measurement
c71cc9c4-f939-5cc1-81fe-9fea4cf75695 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
9a876590-bbcf-58a3-8785-5994b6848c7f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
c2cc17d0-e899-505d-96c1-5cfbeec0a5c2 | note | VERIFICATION ACTIVITY: Visual
45e7419d-c87d-5fb0-94b8-67856ccb9cd9 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
68cd3f1f-4465-5f1f-b0d3-69c2767f9c05 | note | FREQUENCY: Everysite
69088a0d-0ebc-56a9-91ff-05524584f728 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
a6248d3a-b139-5e1e-bb37-cb478f68f79b | note | HOLD POINT: Inprocess Inspection
6038f1ab-741a-58e7-84f1-273eb6aab868 | note | RECORDS: Photos
46d8b2b4-d560-56ab-b818-8e01b199171d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
d7714dbe-cd83-568f-83c9-1bd9e54dace2 | note | VERIFICATION ACTIVITY: Visual
47eb83a7-a595-5db4-9a0d-dde606dce3c1 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
25d45751-f512-5d20-a156-029016ca818d | note | FREQUENCY: Everysite
13e50a40-3a61-5d74-86c7-1c763666fc53 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
c4c346d1-ac49-59ab-ba87-fbc8603472a2 | note | HOLD POINT: Inprocess Inspection
63f762b6-8e76-5312-bcc7-5cdfff3e1c0f | note | RECORDS: Photos
f29fd258-460f-5a3e-bfc6-aad86e56698c | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
162eb682-ba17-5318-8af1-ba7cdfa888c6 | note | VERIFICATION ACTIVITY: Visual
880ff57c-0324-5405-ba27-aa39e461d762 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
3210675c-870e-5fae-8499-00a75f1c3a72 | note | FREQUENCY: Everysite
9f1b9715-0272-5fb7-8d09-f168c6e15eb5 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
c905bfc0-a3b6-50df-b904-0d4fe3595ec5 | note | HOLD POINT: Inprocess Inspection
b7760072-e8a5-5afe-b9f9-40e4eb3a7668 | note | RECORDS: Materials Dockets
371f1269-60e2-5135-9018-d9a63b63e364 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
5b575850-84f3-5845-aca8-3ffae2ab42ba | note | VERIFICATION ACTIVITY: QA FORM
89d89e25-3092-545b-81ff-876daa76b115 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
587e518a-8925-540d-90d1-05a0e2e50b54 | note | FREQUENCY: Each Crossing
d6dec8f1-c088-5ab6-bedc-c8f54aa11603 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
0244e018-740c-512b-8b20-4a5671ffbc82 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
49bbe417-4902-5b93-b6c7-2c8bf94d640f | note | ○ Slope no greater than 1:12 where practicably possible
df304344-02f8-53f3-b1a8-c5e6356f782d | note | ○ Clegg CIV > 12
2f3739ba-7c06-52ff-9d11-a43489e0302e | note | HOLD POINT: Inprocess Inspection
cda5d1e8-d294-5ee3-9332-c58857fadf2f | note | RECORDS: Photos
60e3d030-c38b-5962-b719-a402335001ba | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
f5623ea3-0c6d-5806-a95d-037ad9c33441 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a38fbf3c-acf4-53f8-9078-74ba87459830 | note | METHODS OR REFERENCE:
bc56d303-2715-5640-8815-1f9e6343fd3c | note | FREQUENCY: Every Site
39fa6c41-e1f7-5d4d-b2a2-3d575879440d | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
4cb9ca49-a036-5cd0-a265-cb41b1ab3219 | note | HOLD POINT: In Process Inspection
df5f59e0-d413-5f40-b656-c0c93d6d480a | note | RECORDS: Asbuilt records
88e44dc6-d4d5-503a-9d95-632c432ab58a | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
a1f831ae-3a4f-50cb-b248-5b094abf7d65 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
90139ece-d80c-5d4c-9e73-63215f7de54d | note | METHODS OR REFERENCE:
cb1e4fed-8cc6-549a-a9a8-7b019000ee75 | note | FREQUENCY: Every Site
26a4791a-bb80-51ff-9e7e-8cd902a1c77f | note | ACCEPTANCE CRITERIA: RAMM SHEET
eeb595d6-d254-5817-ab29-ce79790e0656 | note | HOLD POINT: In Process Inspection
0988b582-7897-5a2e-8651-939f0ac237b0 | note | RECORDS: RAMM Sheet
d3638afa-1a74-553b-a5bd-c8f6cd2e40ec | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
d82b09cc-807d-5de2-8a2d-5f9957bf8862 | note | Prepared by: Ajithkumar Ayyanar
a232d79d-3af9-5b8a-8387-a2123dde2523 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Rosscommon Road - ITP - Signage | itp | ITP - Signage | b834e4ec-957d-457b-ad64-4c3b900b2ab1
| section | Site Set Out
| checkpoint | 1 - Site Set out
91e591c3-eea4-53e2-bf7b-5b45dd0311e6 | note | VERIFICATION ACTIVITY: Surveyor
081a38e7-0450-5d3d-9649-8d30af5ecf1f | note | METHODS OR REFERENCE: Surveyor
9e9590ce-ffd3-57eb-a587-a13f8acf76ea | note | FREQUENCY: Everysite
97ba3b04-1a46-54af-9db4-33fb594f8cf0 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
fc97f051-9ebe-5bbc-bfe3-65a4bf736ae8 | note | ○ Alternatively like for like
0c4cf3d0-0507-57a5-a339-77c806d54c5d | note | HOLD POINT: Mandatory HOLD POINT -
912b2c61-2db0-57a1-8ffb-361eb8151b13 | note | RECORDS: Survey Receipt
2498ddc5-f96f-527b-80b5-ca132f2a89f8 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
fa5e5290-8a4a-5b2d-a5da-0c4365eff2a5 | note | VERIFICATION ACTIVITY: QA FORM
4dd16ce5-32d5-545e-81f3-7b0a064a4896 | note | METHODS OR REFERENCE: TDM Technical Standards
1caf06e4-d3ec-52a6-8832-9ee94755872b | note | FREQUENCY: Every site
9cf8cc79-a179-5685-94da-8eebb904bf0f | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
702b33fd-135e-572a-b14f-eefbb1703ba3 | note | HOLD POINT: Inprocess Inspection
b82e81b3-7772-5dcf-962b-19ff9c2313ca | note | RECORDS: Dockets/Photos
1e122543-13d1-5e58-8e16-fef8b950c3be | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
67748084-11f6-5da3-a7cc-bb0462a1dea5 | note | VERIFICATION ACTIVITY: QA FORM
efe4453c-bb77-539e-a9bc-b31104890154 | note | METHODS OR REFERENCE: TDM Technical Standards
d40d1b5f-5741-5dab-9d4e-49d13d990971 | note | FREQUENCY: Every site
763d897d-4042-588f-9606-e94fbb4294d4 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
917ac5f8-90e2-5445-b50b-b3438bfcadba | note | HOLD POINT: Inprocess Inspection
269db4d3-7c3f-5d09-b54d-5664a4ee1eea | note | RECORDS: Dockets/Photos
ac8819df-2b5e-5664-83cc-b529f2b043f1 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
2b873446-0557-55db-899c-aa75472529de | note | VERIFICATION ACTIVITY: QA FORM
e8240590-7dec-5962-b838-fa38d2f6d0f8 | note | METHODS OR REFERENCE: TDM Technical Standards
8cf0caea-b44a-5749-9a96-7a3f188b126a | note | FREQUENCY: Each Socket
f2f04472-2ed0-57da-9fd4-6478faa7aa39 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
02497600-a14f-548c-8f62-a597765a4433 | note | HOLD POINT: Inprocess Inspection
6b49a861-e9b6-5346-a359-0abc2f1f077a | note | RECORDS: Dockets/Photos with tape measurement
d81f4a07-0ece-54d4-8dcb-60e1b7d73c76 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
5162e6df-ed97-562c-a502-7b0aa603b10d | note | VERIFICATION ACTIVITY: QA FORM
ec373dd9-02a5-56bb-bae7-eb4ab5e07eb4 | note | METHODS OR REFERENCE: TDM Technical Standards
91182b53-93ab-509a-8f49-03b3edf4b287 | note | FREQUENCY: Each Post or pole
2c9bce8e-f56b-5e5e-8efc-9ce14a57e3ab | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
4e53f6a7-71b4-535f-833b-a52b80773364 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
71889895-1fcd-50bc-9c8b-41458e3c41e7 | note | HOLD POINT: Inprocess Inspection
33cb9fda-d699-57ae-948f-8c1049d58140 | note | RECORDS: Dockets/Photos
d96c2760-46d5-5359-a037-7f3eca2bec40 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
c443bc2c-14fd-54d9-b641-b425deb78258 | note | VERIFICATION ACTIVITY: QA FORM
afc7a1f7-01e2-5d28-9d84-f7d8132a94bd | note | METHODS OR REFERENCE: TDM Technical Standards
69a2cde0-c1dd-5772-a835-9b0050efae8c | note | FREQUENCY: Each Sign
92befb44-210a-58ba-bd6f-eb6dab66e17f | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
581bac7b-a913-5f99-82f1-019ee62665f7 | note | HOLD POINT: Inprocess Inspection
29d3b6a2-74f7-526c-851b-ede102700419 | note | RECORDS: Dockets/Photos
9e80646a-ba4c-5a3e-a862-2b07963e8f2b | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
75e4ce3c-6908-5ec6-99d8-bc520f5f9264 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
a21fbd9e-2fc6-56d6-aacc-ef2addcb4c6c | note | METHODS OR REFERENCE:
3754a573-fe01-5d08-aef0-2f27f0c06a18 | note | FREQUENCY: Every Site
0fa5be3f-44ac-5ee4-afba-90f5fd0cb101 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
4cc85ad9-05a9-5445-ac36-49682ba7002d | note | HOLD POINT: In Process Inspection
2e2e7499-f534-556d-b4fe-6ef197b2795e | note | RECORDS: Asbuilt records
9a77713a-e213-5bc6-b6cb-2136d42ef612 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
b2f0ab71-1eac-566a-a618-5e23e7f24490 | note | Prepared by: Ajithkumar Ayyanar
66555f31-9353-53f9-ba6d-0c98daf7fbd2 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Rosscommon Road - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | 44a38bae-26fc-49a0-92c3-7197341c1660
| section | Stormwater Drainage
| checkpoint | 1 - Permits & Services (1)
45ef7703-effe-548a-a1f2-746e2f96ce56 | note | ACTION (Hold, Monitor, Witness): H
e067f26d-e47e-54de-9c27-572079b4e029 | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
2e806ee0-2412-583e-8f9c-ef6567860495 | note | FREQUENCY: Prior to any construction commencing
d4a677c7-5051-51b4-b609-05e7f1d7c275 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
112943d8-d6dc-5cef-bad4-b65e62c29728 | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
bc3de477-1d17-5a49-b006-e3e51aacef62 | note | ○ AT Access Authority approved and signed by RCA Authority
0538e900-4074-5c89-81ac-7ed7b540a0ec | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
d1736ff5-3b6a-5d02-8e80-b9a4ee042d3f | note | ACTION (Hold, Monitor, Witness): H
40796680-a219-5ded-b4f6-d52210916d5c | note | DETAIL: Locate and mark out all existing services
d9eabb99-0403-5fba-a6fd-39e6100ca4af | note | FREQUENCY: Prior to any construction commencing
cf7fb2a2-381a-55c7-967e-141ca07cdcea | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review):
f9d17918-aed8-5db8-b8d6-91a0e718524d | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
d2e3da43-0f92-51ec-bbf1-24363067f580 | note | RECORDS: B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
174eef8e-2bbd-50ba-bfb9-1cc96c3dd403 | note | ACTION (Hold, Monitor, Witness): H
02e24a0e-2997-57c9-95ef-9f8001e71b88 | note | DETAIL: Sub-Contract and Supplier Agreements
200f994d-d1b0-5a79-a97f-01e88fa86fcd | note | FREQUENCY: Prior to commencement.
1a6ac4a7-500d-5af9-ac44-68b25ba3228c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
0c12f079-680d-50cb-a914-de6c88b4a4c6 | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
6978a445-9a72-5991-afa6-b258014b3c6d | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
f32ebffa-ff95-588a-8ec3-faf9f15c9f5e | note | ACTION (Hold, Monitor, Witness): H
5884806d-5434-5c69-871a-93741be97931 | note | DETAIL: Design is approved and Drawings are of the latest revision.
d30fe687-b521-5d68-8b42-88707da45c99 | note | FREQUENCY: Prior to commencement.
3bee52dd-8b56-559a-84ce-93b8e341779e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
a66140bf-8ef7-5922-b2c1-f061637a02cd | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
a2d83bf4-f8e6-5df3-8409-dff8bd005db1 | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
b0397d17-8d83-5953-8f15-b99ad1838ff3 | note | ○ HOLD POINT of not issued to IFC.
c0c0844f-6dfb-5736-a48a-1615c5f0d4fc | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
172429f5-2a61-5a1f-911d-74d75a917746 | note | ACTION (Hold, Monitor, Witness): H
11ac8c2c-d258-5ea4-ae17-65ac6a7f66f8 | note | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
abeffc44-8bfc-5c3e-8933-45909ef448a4 | note | FREQUENCY: Prior to commencement.
fc6abf30-de75-5465-8f35-51e6d044618f | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
97ceca21-2a2e-5cd4-b56e-1aaf09057483 | note | CONFORMANCE CRITERIA: As per Stellar Engineering Drawings: 2789-C3060 or setout files
a0c178cc-12a4-5434-b6e0-d2caba700076 | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
054f02d8-1890-5d51-88a5-c22e56cc2f69 | note | ACTION (Hold, Monitor, Witness): H
0454d2e7-3788-5f7c-9cfe-829937b8acb6 | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
91ffff7c-2bbb-5e38-bfed-5de2b8b6d2c5 | note | FREQUENCY: Prior to commencement.
85a6a3b3-1357-5b0e-a10c-790d06aa9cc7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
3329fd54-5558-55fe-9fcb-fcc4cf9e762d | note | CONFORMANCE CRITERIA: Pipe shall be
e414fe3d-cc69-5bc8-8d91-6c97af992b9a | note | ○ Check for freshyly formed pipes and return if required
48431ef2-c1ef-506b-8c3a-bd042029ab7e | note | 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058
aa0d8d2f-7edb-5c88-bbfe-53f870be4c8d | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
aa8e44ff-523c-5d6f-9dd2-2d0c6e75286e | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
7b87e185-1402-55bb-a4a9-b1a7f36945dc | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
2f25addd-55c7-5e63-b272-94bd20f4f100 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
50a1c066-0b87-56b7-b1f5-ab914a0bb562 | note | ACTION (Hold, Monitor, Witness): H
3c814e2c-7714-5c5a-b22a-c68f0280e0c9 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
4a07b826-fccd-5595-91ce-cef90037590e | note | FREQUENCY: Prior to commencement.
91998f0c-84b0-5525-979d-e8ed0d95ad7c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
6b32e11a-d3fe-5266-b737-5b3295446b4c | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
b8da985e-a33c-5019-883a-a5d55be951e4 | note | RECORDS: As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (1)
92a1fd0b-01bd-573e-ac4d-985e5df2e6fe | note | ACTION (Hold, Monitor, Witness): H
54b4b7ae-d18b-5f61-bb0c-9990fcc0a7a9 | note | DETAIL: Excavation methodology
64a00bde-debd-5f01-8ed2-343160804a65 | note | FREQUENCY: Daily
6793c19b-c048-5e0f-844e-506f3d4497d7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
f86ea05f-7bb2-5413-a393-9c6fcf681a6b | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
04cf1eaa-38c5-545b-9f61-db13d055e9ea | note | RECORDS: Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
530e34f0-6c14-5fc0-bd5e-95d1aaa6f161 | note | ACTION (Hold, Monitor, Witness): M
63ef0df0-cb2c-567d-a0fd-364fa3097369 | note | DETAIL: Trench Profile - Width
4b76146a-b823-53c2-b82c-99c8507ca6a8 | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
3474aad9-4db1-5159-8e67-e6069a6450a4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methdology
6851eb76-458c-5d98-8462-f5be7db3df46 | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
5b9553fc-c013-5479-899a-d93b055eef75 | note | RECORDS: Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
b9be021f-c196-54e8-ac52-bc759134bc13 | note | ACTION (Hold, Monitor, Witness): W
9ecc1708-de6c-5bc0-877b-60bca2bbbb61 | note | DETAIL: Trench Profile - Depth
2773f667-4c70-577b-9965-8c8b0dd6db0f | note | FREQUENCY: Daily / as trenching takes place.
dc96d7e7-629a-5d4c-9477-58e47477e0ea | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
1fea4f9e-53e7-57ba-8888-39c6efb19a78 | note | CONFORMANCE CRITERIA: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
9bc5012f-a423-504e-850f-080aba509e3b | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
4ad623f9-9d37-5b9f-9b83-9f9ec310cfec | note | ACTION (Hold, Monitor, Witness): W
0b460172-59d5-55c5-ad23-80b98b2f784d | note | DETAIL: Placing and compaction of Bedding Material.
f1fad383-2045-50fd-9bc8-f6e882ac7186 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
f6f17a13-2221-51ce-b9bc-f68083c72631 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
6a88b4f7-6ba1-5d5d-975f-55781a081765 | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
1860770d-bffd-5920-a5ef-1ad81a1944c6 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
08113572-acb6-574c-8717-e78aee899e6c | note | ACTION (Hold, Monitor, Witness): M
78ef0c2a-e891-5e3d-b5ca-c0faa59ce0c6 | note | FREQUENCY: At any point of pipe
cc4d2c14-5aa7-5bd8-a665-3b8a59f07e73 | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
a2d37038-331c-5f9e-8a2c-0abe1901f5e4 | note | RECORDS: FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
f2241d25-a121-5f1b-8b3b-cd1f277d17ee | note | ACTION (Hold, Monitor, Witness): M
2f3937d5-4785-5d60-aa82-366116bb4f8e | note | DETAIL: Placing and compacting of Trench Backfill Material
bee91f60-91b2-5e30-88ee-24667b0525fe | note | FREQUENCY: Throughout Trench Backfilling operation.
68e3067e-3c1c-533f-a8db-c820c4c3c0e1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
bf141f95-003e-5628-81ec-cdfbfe28de39 | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
f0880356-bf8f-512c-a81c-03acf7dacba3 | note | RECORDS: Construction Photos
| checkpoint | 11 - As-Built Drawings
f5a7f5e5-afc0-5180-b1d4-0224ba00765c | note | ACTION (Hold, Monitor, Witness): W
538968df-bf0f-57f1-99b5-e04bb7ae68ad | note | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
243dcbc4-8c12-5292-9c05-a3e5b74f5329 | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
18a8c7a8-04a4-58d2-b2bc-5be6af6309f2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
2bae34b0-ae97-5e8e-9077-f67b69c0ce34 | note | CONFORMANCE CRITERIA: As Built and GIS Data
e73f11a6-0366-50c7-b49b-cff027f337c9 | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
| section | ITP APPROVAL
| checkpoint | ITP Approval
5bb41e59-87e5-50d3-ae37-5393e0105fe6 | textbox | QA checked By Quality Manager:
f60c1b92-747d-5654-9d35-56c7303d03de | textbox | Accepted By Engineers Rep:
| checklist | Weymouth Construction - Rosscommon Road - ITP - Traffic Islands | itp | ITP - Traffic Islands | 45426574-f069-4464-b547-fcdd8f961101
| section | Materials
| checkpoint | 1 - Mountable Kerb
7dfcc24f-c123-5e79-8c1a-e4a7f9fa491a | note | VERIFICATION ACTIVITY: QA FORM
eb165097-4e47-5fa0-8ef4-73163f2cfcd9 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
b9fb4e4d-1a45-5ac1-b245-b1df92cc2c7a | note | FREQUENCY: Everysite
f6e76216-ef90-543b-978a-aeafd8613b97 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
f3e94928-dce3-5324-a3ac-a280c2397651 | note | HOLD POINT: Inprocess Inspection
ede2b78d-88ef-58cd-8879-b2e1fbb7ee4b | note | RECORDS: FH concrete QA sheet, photos.
e02d037f-634b-5a88-b1fd-79f8f39f93cd | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
20255afe-fd57-5095-9b48-3fe9320dfea9 | note | VERIFICATION ACTIVITY: Survey
1d6df150-ae37-5932-be5e-840f59b8f2b2 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
5520b1f2-7052-5f84-b3ab-874b69b53644 | note | FREQUENCY: Prior to commencement.
7ce61fe2-22be-55b9-b37c-23fac4e52b4d | note | ACCEPTANCE CRITERIA: Survey
2e9860e0-ae89-5227-bfb5-13a28c3ffd61 | note | HOLD POINT: As per Construction Drawings
466c20a2-1bcb-590c-8faf-f528af527e34 | note | RECORDS: Survey Receipt.
8c09ae75-d425-51bd-8c3c-81a17494938b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
c011890f-5237-5268-b369-1c11454d3683 | note | VERIFICATION ACTIVITY: QA FORM
e92b3ff4-3bea-5c41-9f72-1c0e5cfe9125 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
9a1e417d-d3c8-54e9-94cb-889ad7e9b71f | note | FREQUENCY: Each Site
3ee86d5b-9395-5a5f-9891-9e321f7d6085 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
77cc449d-7ff2-514a-82cc-6ff26a4ebe1e | note | HOLD POINT: Inprocess Inspection
e5b7d5b3-fde8-5a2d-8c76-af02af1308a8 | note | RECORDS: Photos
416217ab-8d03-5eb9-b1f8-18253d76d1fe | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
9ad4eb3e-3b98-56ba-98b2-76da4597dad6 | note | VERIFICATION ACTIVITY: QA FORM
782882ba-bc06-51e0-b254-04e0c8162723 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
941793cf-3fa0-54ac-8d0e-b49fafb63e21 | note | FREQUENCY: Each Site
ce05fd15-86d7-597d-a773-e6b87627c517 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
cf6c953b-398d-5d50-8540-227d6b62a2ee | note | HOLD POINT: Inprocess Inspection
6461118a-93b9-5da0-864d-1ca8af4c6cac | note | RECORDS: Photos
040ff9f4-2440-5e2e-b527-429e96c383a7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
cf053852-6eae-5b05-9efd-759e500e4212 | note | VERIFICATION ACTIVITY: QA FORM
bd8d163f-aa2e-534f-8cb2-8ba278a58c55 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
d20ce8a5-f21f-5d75-a35c-c5557ab9d630 | note | FREQUENCY: Each Site
c7e107db-3f3f-570f-a20d-cff3dba2ee2f | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
b9bfd73c-47ab-5f73-95df-8192dabb5748 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
0ca10de5-2512-5e65-abf1-0351819fd25e | note | HOLD POINT: Inprocess Inspection
8ba69030-4c59-5457-b285-40c0d603369f | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
aac44e50-fe33-5ba6-8d8f-263f8abf5e86 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
3badcebb-464a-59cb-9169-7c22035ef4a4 | note | VERIFICATION ACTIVITY: Drawings
7bd0ee5f-5c01-5c0b-9e5f-7d34f717e2a3 | note | METHODS OR REFERENCE:
a4d22258-19bb-541a-af9b-c5092afcf925 | note | FREQUENCY: Every Site
208bceaf-92b9-5e6b-96dd-43a9cb212c48 | note | ACCEPTANCE CRITERIA: As built drawings
0d8a160c-ac1d-57b6-975f-db29e2b8ff4c | note | HOLD POINT: In Process Inspection
fb07b86e-e8b7-5f08-8494-f8bd1b8ecac9 | note | RECORDS: Asbuilt records
e6bf600b-2eb9-5e6a-8728-29fe89200799 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
2f108d70-6277-51c6-8f57-1fbbee3dd22a | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
77f52180-3579-53ea-8f88-72f3f05a6b0a | note | METHODS OR REFERENCE:
a0283409-ad63-581e-bc2b-5e45bc5cd3ec | note | FREQUENCY: Every Site
b5403cd6-0edd-5df6-b7d0-e5f8ef4ac2ed | note | ACCEPTANCE CRITERIA: RAMM SHEET
54b6908b-0c47-51e9-9001-4abf099e7071 | note | HOLD POINT: In Process Inspection
af51f6a8-bd6b-5a7e-8c02-20528150788e | note | RECORDS: Asbuilt records
f5178392-8e0f-5ee0-a541-308950276057 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
27ebe6f0-eeac-55de-86a5-71f1b6e03595 | note | Prepared by: Ajithkumar Ayyanar
830874c5-ed76-5f1e-8d7b-00835a0fbd9c | note | Approving Delegate: Sumesh Sharma
05db1198-0074-4bc4-afb2-5c665369eed0 | checklist | Weymouth Construction - Stage 7 - Pavement Construction - ITP - Pavement - Structural Asphalt on Concrete | itp | ITP - Pavement - Structural Asphalt on Concrete | a78aa53f-ccef-4051-bff3-fbd3940a9a97
fa922007-7bc3-4f42-aead-db5f48894ba8 | section | Milling/Excavation
a6d7fd8a-2683-4db5-882c-6810870d088e | checkpoint | 1 - Identification and location of services
e517c9b1-75c3-5d7b-99c6-35b9585b8f9d | note | VERIFICATION ACTIVITY: Service plans and GPR Markouts
7ebdb1b3-d11f-5ce3-be97-db50f5a1d2ec | note | METHODS OR REFERENCE: Trained contractor staff
7e3df492-a0d9-5ecd-b6a1-bb926ef67e96 | note | FREQUENCY: Full Pavement Extent
ef986e81-2b31-5815-8967-56736900de4d | note | ACCEPTANCE CRITERIA: Services sufficiently deep to avoid damage.
08b5f910-7065-59d4-984c-d7b1dce599d5 | note | TYPE: Mandatory HOLD POINT Engineer Signoff Required
8b077036-8e39-51c6-9c11-ae621b1623f5 | note | RECORDS: Photos and Report
1effc39e-b3ea-5b57-930b-d7aff3803401 | note | ONSITE RESPONSIBILITY: Project Engineer
9967bc02-b67b-5b7c-8d57-a63a77d3711b | note | SIGNOFF: MSQA Signoff
ac11c6a8-4ebc-4e7e-b369-b022e6ba147f | signoff | AUTHORITY HOLDPOINT
13004e44-422d-4af3-a53a-69b4a7af700a | checkpoint | 2 - Milling / Cut to Waste (350mm at Weymouth and 400mm at Roscommon)
16f4228c-7eda-5142-874a-6edbbdda9719 | note | VERIFICATION ACTIVITY: Stringline
50664999-99b8-5376-9d20-62813dff86f4 | note | METHODS OR REFERENCE: Dip from stringline or survey as- built
8d064ea4-b2df-5e50-ac8a-b2cc25210600 | note | FREQUENCY: 5m each lane
85ee7ddf-6a0c-5dbb-8bff-52f3fd66bfcd | note | ACCEPTANCE CRITERIA: +0 / -20mm to design level
7bf77697-2b9f-5455-a086-82c3ed83a044 | note | TYPE: Mandatory HOLD POINT Engineer Signoff Required
58854565-9d20-595c-a372-81474d701b65 | note | RECORDS: Stringline Sheet
64104ced-3326-5595-9c79-3dcdcb67a14d | note | ONSITE RESPONSIBILITY: Project Engineer
c426f8f5-5ded-50fd-b5b1-dbd528c9963f | note | SIGNOFF: MSQA Signoff
8e19e9c2-1655-4644-9dd3-50485e4b3371 | signoff | AUTHORITY HOLDPOINT
45fdd471-096b-4f9c-8104-d23f8ebba5f6 | checkpoint | 3 - Subgrade
e6f460ea-6d19-53bb-9b8c-4db839fb45a2 | note | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
794e5cd2-7905-59b7-bbf8-615cd564585f | note | METHODS OR REFERENCE: Visual Inspection
f0dbc7ed-bfbb-5376-b72c-d601c2961010 | note | FREQUENCY: NA
0809cf0c-472c-5192-b4de-e2c400f0a5c3 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material. Subgrade Treatment may Required
d23b885f-a25a-56a2-9de5-f688fa83785a | note | TYPE: Inprocess Inspection
ca08dec0-0344-556c-9eb7-3011d55f4e64 | note | RECORDS: Site diary
29ea36b8-5706-55c1-9086-9c5f85d268b5 | note | ONSITE RESPONSIBILITY: Project Engineer
5ce3cadb-a024-4a3f-b104-02610a91c3c7 | section | Subgrade Treatment
fad6dc9a-c2b0-493c-9755-c8bb6533d643 | checkpoint | 4 - Subgrade Testing and Treatment
adb6645a-5016-51ad-9b0c-69fee4b3ef97 | note | VERIFICATION ACTIVITY: Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling
6a03cf10-74d2-5e3d-acc8-2558313f6919 | note | METHODS OR REFERENCE: Design Report
d4ac32ec-defc-513b-b0be-f8a54ff4aac8 | note | FREQUENCY: At 10m intervals staggered in each wheel path
bf466ddb-a72a-5bc9-917c-208b98a88117 | note | ACCEPTANCE CRITERIA: For,
a2546e34-b981-58b4-8877-d202f1cf98a1 | note | ○ Subgrade CBR > 3%, Scala < 50mm per blow, shear vane >= 60kPa and no visual movement under static roller.
e9d66a5f-6896-5399-829f-aeedd179e434 | note | – No Undercut required
a3d43dd9-b739-59a0-a6d3-f59d5294196d | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
212c489b-f993-587b-8e0d-1e4fd1a2a75a | note | RECORDS: Testing results, QA and video of proof rolling.
204d7267-87a7-519d-8e3e-601b47f51149 | note | ONSITE RESPONSIBILITY: Project Engineer
b6f17227-4e9f-5f87-9868-c9e5b2e56c3f | note | SIGNOFF: MSQA Signoff
8559660f-3ee9-43af-95a1-7b0464ced122 | signoff | AUTHORITY HOLDPOINT
c9465bc8-1c08-4ce8-9d4a-0a5bc41d9c37 | checkpoint | 5 - Subgrade Testing and Treatment
d581991a-f4d3-52a8-8666-78e62e6df67c | note | VERIFICATION ACTIVITY: Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling
05556dc5-34eb-5849-8214-92d6c267f495 | note | METHODS OR REFERENCE: Design Report
4f19d456-8db2-5b41-8ae1-c8a61f220a47 | note | FREQUENCY: At 10m intervals staggered in each wheel path
6583095d-898a-5160-a6e2-aa5bf637034f | note | ACCEPTANCE CRITERIA: For,
52e1734b-b7b5-5a52-b6c6-1906a78140ee | note | ○ Subgrade CBR 2 - 3%, Scala 50 - 100mm per blow, shear vane 40 - 60kPa and visual movement under static roller.
5540e063-bf25-5f74-ba17-bac394913315 | note | – No Undercut required at Weymouth East and Geotextile to remain at bottom of concrete subbase.
f6780cad-ad09-539d-9dea-50bad2229e17 | note | – 150mm undercut required at Roscommon Road and geotextile placed before backfilling with granular
484da7fb-6418-56dd-ab22-6272a710780d | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
08051f07-40ea-5e29-bf7b-862ab0f98221 | note | RECORDS: Testing results, QA and video of proof rolling.
bbab267d-7e51-559c-8f91-8bd46ce933d6 | note | ONSITE RESPONSIBILITY: Project Engineer
97cf797e-7f0b-549a-9e9f-efc37e7492af | note | SIGNOFF: MSQA Signoff
bafaac01-683f-4310-8a17-4a030a560b9c | signoff | AUTHORITY HOLDPOINT
5f6bf135-af9e-4bd6-b26d-1095b716f531 | checkpoint | 6 - Subgrade Testing and Treatment
b9e1b532-ad73-5ca4-b7e4-abc6af4cb519 | note | VERIFICATION ACTIVITY: Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling
c69facc3-a0eb-58a1-9884-63a0718cebf5 | note | METHODS OR REFERENCE: Design Report
161fa73c-8f5e-5baf-b956-e9cb08e7985b | note | FREQUENCY: At 10m intervals staggered in each wheel path
0efc8ae5-e0a6-522a-9395-d21463f1a0fe | note | ACCEPTANCE CRITERIA: For,
8896e454-5076-57ba-b59f-9a174200fb72 | note | ○ Subgrade CBR 1 - 2%, Scala >= 100mm per blow, shear vane 20 - 40kPa and visual movement under static roller.
00d0493b-4961-50b0-9f65-d0be86e379da | note | – 200mm Undercut required at Weymouth East and geotextile placed before backfilling with granular.
5f5f6f59-8c5c-557d-9816-c5f8da5ab92e | note | – 250mm undercut required and geotextile placed before backfilling with granular
60b55427-905d-5a88-bf62-bb6e822538f0 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
826a7e8b-c241-577f-92c6-567570024517 | note | RECORDS: Testing results, QA and video of proof rolling.
0c5f0336-66c8-5c17-a12a-afdc9dfcbba1 | note | ONSITE RESPONSIBILITY: Project Engineer
99815bd3-138b-5b45-82d9-17584bbf3f16 | note | SIGNOFF: MSQA Signoff
3bb48ef3-efcf-4c26-ac49-c4faf4b4cbb8 | signoff | AUTHORITY HOLDPOINT
037a7fe4-04da-4b65-a387-f85751561a9d | section | AP40 Layer (Subgrade improvement layer)
ae9fe678-934b-4cd3-98ec-696127659272 | checkpoint | 7 - 150mm or 200mm or 250mm Excavation
7a7eefec-0d09-568e-b5b6-4017a3981237 | note | VERIFICATION ACTIVITY: Stringline
d55b1c1d-2569-59b4-a7f1-a9251ecf5e1d | note | METHODS OR REFERENCE: Dip from string line
02f42855-b06d-58b3-9f03-2cb912aa777f | note | FREQUENCY: 10m each lane
5d2721f2-a61d-5c3e-b919-e8fe27f6fc1d | note | ACCEPTANCE CRITERIA: +0 / -20mm
04071faa-88f6-5ad4-b6f3-459e4a960ea7 | note | ○ No trafficking of the excavated subgrade
90ce28e8-52c8-5253-9608-aafe50aaaf2c | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
895491b5-7e02-53ec-b891-430f050aa32e | note | RECORDS: Marked up drawing
4b4def93-9c3e-55fb-9d09-55281fe36234 | note | ONSITE RESPONSIBILITY: Project Engineer
135f4d49-4459-5188-9dc1-b3ad35992945 | note | SIGNOFF: MSQA Signoff
3fc536ed-7586-4ee6-a02c-e57a45fa1956 | signoff | AUTHORITY HOLDPOINT
f95a4e7c-ee3f-4928-90fd-dc9bfc92c5e3 | checkpoint | 8 - Class C Geotextile
2cf2ad68-f3c8-5c81-ab25-a8c37b7823b0 | note | VERIFICATION ACTIVITY: N/A
d581422a-ba96-5e11-bdbb-8d093dabbc9e | note | METHODS OR REFERENCE: NZTA F/7
282fb4d3-a130-5ad0-a718-a1ff289e14b6 | note | FREQUENCY: NA
6851acd8-968f-5aa1-9028-5d7911ee6a0e | note | ACCEPTANCE CRITERIA: Geotextile material and construction in accordance with NZTA F/7 Placed as per subgrade treatment
7e943f27-c5b7-5865-a84b-c0805fa8e680 | note | TYPE: In process Inspection and Contractor Records
30d71921-af35-5823-bf84-6c8d83468216 | note | RECORDS: Testing Results
961bc706-3205-5be9-95c5-54f1c3899ec5 | note | ONSITE RESPONSIBILITY: Project Engineer
8499578e-dd19-4dab-b136-43eb1270c994 | checkpoint | 9 - ATAP40 (material)
36f4a274-2a6f-59bf-8324-8b351b5868a6 | note | VERIFICATION ACTIVITY: No non-compliant results
3505e049-ae9b-583b-9626-f5c16207e613 | note | METHODS OR REFERENCE: Material test results
443ee224-ee2b-570d-9eda-4b6a4293af20 | note | FREQUENCY: Once
0ee08853-e90a-535c-bc3f-77a3c658e855 | note | ACCEPTANCE CRITERIA: Compliance with AT Series 800 Specification for the Supply of Aggregates
0b972f6d-ff77-5921-bc97-073252eddb7e | note | TYPE: Contractor Records
17c0012d-fa74-55f8-ac54-0fa5c9d11d5a | note | RECORDS: Testing Results
c8c4f54e-6435-544a-82d3-a5f5da54840c | note | ONSITE RESPONSIBILITY: Project Engineer
cd319944-ba7e-42ba-b6ab-057e476ac26a | checkpoint | 10 - ATAP40 (Compaction)
c917c806-9ed3-5972-b506-ef0b15f284b4 | note | VERIFICATION ACTIVITY: Compaction
eb1ffa03-57fd-5a00-8367-2da1eef2451d | note | METHODS OR REFERENCE: CIV
bbf81bbc-60a5-5c05-ba81-c5d5c77c4940 | note | FREQUENCY: Every 10m in each lane
c003aeb0-9248-5b4d-8a82-42f5a46c8c73 | note | ACCEPTANCE CRITERIA: CIV>=35
ca71cdda-8848-5c9b-a78e-5e395fc6586b | note | TYPE: Contractor Records
27ac2476-65b2-5813-996d-a2a673d41696 | note | RECORDS: Testing Results
16202208-7486-5646-a39d-5ec03475d301 | note | ONSITE RESPONSIBILITY: Project Engineer
4b8f03c0-52b1-4837-9309-11e9531d3f46 | checkpoint | 11 - ATAP40 (Level Tolerance)
1b33fa1c-fbf2-5986-af66-0c199e424a34 | note | VERIFICATION ACTIVITY: Stringline
ed1a6a5c-c9d8-5f6b-b2a8-c3c3780bac29 | note | METHODS OR REFERENCE: Dip from string line
230f9fab-6c04-5a44-b34e-4665dd5d2a25 | note | FREQUENCY: 10m each lane
a975cd97-870e-5df8-88af-0045928c8d43 | note | ACCEPTANCE CRITERIA: +5 / -25mm
16958cb1-941b-59c4-96d5-405686ab19df | note | ○ No trafficking of the excavated subgrade
76c82ea5-7f2f-5f44-b3e8-8dcc2b25248a | note | TYPE: Contractor Records
13fe916c-35e7-5c56-94ac-c323a441b4f4 | note | RECORDS: Testing Results
eb33c818-bb57-584d-9e91-eb54a38a9683 | note | ONSITE RESPONSIBILITY: Project Engineer
429173ca-8f13-4cec-a6b0-4abca6241e10 | checkpoint | 12 - ATAP40 (Surface finish)
5e57c473-0818-5354-a227-d07dbcda5612 | note | VERIFICATION ACTIVITY: N/A
ce1bf6a7-10a5-5db3-9824-f58ec4487c40 | note | METHODS OR REFERENCE: Visual Inspection
a3dc47d8-4d00-5ac7-99db-c31b9c74d8f2 | note | FREQUENCY: NA
9059ca31-8af0-5582-a120-4971db3e8543 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
b00d9416-26d1-5438-b996-e137c9cdf632 | note | TYPE: Inprocess Inspection
12cee443-9a8c-5446-b629-7a5c0e6ab1ef | note | RECORDS: Site diary
649b19b6-2e8e-566d-9e02-6f49b1df1a2c | note | ONSITE RESPONSIBILITY: Project Engineer
ea6a1bb2-c885-4723-afbb-240bd0918e88 | section | New Pavement Joint
9262cf4a-c73f-4fc9-b6d1-d089127a3d20 | checkpoint | 13 - Transverse Tie In To existing pavement
0e84917e-9b7c-52ec-bb8e-b8a74f1f04b4 | note | VERIFICATION ACTIVITY: Pavement Joint
300b3bea-ac9a-5e84-8844-5568394cc912 | note | METHODS OR REFERENCE: Visual Inspection
24d5afd1-3133-57f9-99aa-68febf6c6d7f | note | FREQUENCY: Each Subsection
2403980b-0b68-5413-83cf-0637746af076 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
3fd9ce29-af9a-5b5b-b32f-c86a932b010d | note | RECORDS: Photos and Report
3432fcc1-047e-55cb-8559-5d06ec1681e1 | note | ONSITE RESPONSIBILITY: Project Engineer
6df543c8-6627-5900-829c-c9d9356e8250 | note | SIGNOFF: MSQA Signoff
cf0abdff-7c0a-472d-abd9-b59f96664c86 | signoff | AUTHORITY HOLDPOINT
d73698f2-2d91-4b60-aa82-1862d492d331 | checkpoint | 14 - Longitudinal Tie In To existing pavement
f66b34b9-563f-5eba-b2dc-d41d8d13363b | note | VERIFICATION ACTIVITY: Pavement Joint
994e3a0a-fc3d-58f6-9bc7-c1d5edc2f82e | note | METHODS OR REFERENCE: Visual Inspection
c71273c3-4f43-5c47-a300-ca4393afcbee | note | FREQUENCY: Each Subsection
4a290864-32be-59a1-967e-856adc4a2d19 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
75670bc8-6ec7-5862-bc48-848b406fa9e3 | note | RECORDS: Photos and Report
4a7f49de-6334-5807-a678-46460690f015 | note | ONSITE RESPONSIBILITY: Project Engineer
75ebccc2-bd3a-5887-ae49-8c2dc736731d | note | SIGNOFF: MSQA Signoff
296e13c9-3ee8-490b-aa8b-c956404743b8 | signoff | AUTHORITY HOLDPOINT
ce00b335-7f9d-496a-8879-057654307246 | section | Concrete Subbase
3313ad22-f80c-4eab-a61c-aca14cca76a0 | checkpoint | 15 - Concrete Subbase
4e149342-9ea2-525a-a8dd-f0a3ebda3191 | note | VERIFICATION ACTIVITY: Strength and slump
7d330b86-945b-5ab5-9a9d-4cbcbdaf5c75 | note | METHODS OR REFERENCE: Concrete dockets
64d59994-aa07-587e-a30b-66526df144e2 | note | FREQUENCY: each pour
321a69fa-72d2-57c6-bf2e-be036de4ba40 | note | ACCEPTANCE CRITERIA: Strength = 20MPa Slump = 130mm pump mix
8495ae34-f0c9-5be6-af1d-2353ec8f6f7f | note | ○ Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface
0a373d24-f729-54f0-b15c-1b52015213e3 | note | TYPE: Inprocess Testing
5c554c60-f7d4-5b92-b3eb-b10155b32174 | note | RECORDS: Docket
cebc9dac-c10c-5f66-b3cf-4b2b40a21602 | note | ONSITE RESPONSIBILITY: Project Engineer
11b2def8-f10c-4182-a2e5-47c9aa7b2eca | checkpoint | 16 - Concrete Subbase
5be55b5e-3e7c-5957-a969-28b8f2107658 | note | VERIFICATION ACTIVITY: Levels / thickness
896155d4-f727-58cb-9a47-860205438491 | note | METHODS OR REFERENCE: Dip from stringline or survey as- built to top of subbase (Surveyor to provide set-out information prior to concrete pour)
64def766-befb-5fe3-92b0-823ff9966f49 | note | FREQUENCY: 10m each lane
e2ed1212-9b5a-5fc2-8ce6-21084125e4f3 | note | ACCEPTANCE CRITERIA: For Weymouth Road,
16250567-423d-551d-bec4-226051ebc352 | note | ○ Target Depth = 150mm below design surface
8970a1d9-42d0-55e3-a653-fead7fc7b546 | note | ○ -0 / +10mm
efa38a9d-5e56-51ac-b623-779dcaade7dd | note | For Roscommon Road,
5af2f16b-5f8c-5639-9910-161fd95bff36 | note | ○ Target Depth = 200mm below design surface
74b420ff-4d80-59aa-b7aa-b1adbd6329a4 | note | ○ -0 / +10mm
973c8e4b-f7fb-5443-803a-4e1579aec604 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
bfafb134-cfae-5e9c-8873-c0de55bc9291 | note | RECORDS: Stringline Sheet
95c6ac5c-0ddd-547c-91f1-3fdfb4c45a8f | note | ONSITE RESPONSIBILITY: Project Engineer
1e935d17-9b6b-5614-9d2f-d257f634c181 | note | SIGNOFF: MSQA Signoff
52c839a0-9b29-459b-9632-bdc8cbecab1e | signoff | AUTHORITY HOLDPOINT
c8853afe-0e24-417a-9f4f-af97f1eb83cc | checkpoint | 17 - Concrete Subbase
11bd8809-9493-527e-876a-2df045f8f05a | note | VERIFICATION ACTIVITY: Rough trowel surface finish
0c26739b-36bf-5b6f-901d-64995ab53815 | note | METHODS OR REFERENCE: Visual Inspection
548157fd-7db1-5d58-b934-9aeff1bf635f | note | FREQUENCY: NA
95ed7b12-80fe-5c73-b604-f7e484a7eb7c | note | ACCEPTANCE CRITERIA: Rough surface verified over 100% of surface area
283e8534-9449-504d-b755-6c93f0f35adf | note | TYPE: Inprocess Inspection
8f41b387-3446-569d-9367-71fc32ac6230 | note | RECORDS: Production Recurs
60fb031d-a7f5-57b1-a2fc-bd9712662e6b | note | ONSITE RESPONSIBILITY: Project Engineer
fd457608-5abf-4251-9e48-740dff78a116 | checkpoint | 18 - Concrete Joint – if two different pours
b631d9d5-7324-5fd2-8fcc-0ab89b34e819 | note | VERIFICATION ACTIVITY: Joints
e15905c3-0dc8-51ca-ab9d-0ab83fabdb4d | note | METHODS OR REFERENCE: Visual Inspection
40cf77d1-6477-58e4-9bbf-1405d9c0ed17 | note | FREQUENCY: Each Subsection
1e1b6119-18d3-521b-9022-64bbe57c0601 | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
b05315d4-9da8-5a22-9a22-f605f345b568 | note | RECORDS: Photos and Report
e7bedd96-4caf-5a64-a97a-277eca3d952e | note | ONSITE RESPONSIBILITY: Project Engineer
dea73dd4-2eec-5ac6-a078-5b8ae4e2e81a | note | SIGNOFF: MSQA Signoff
83d6dfa8-79cf-47c4-af90-029beecea7d2 | signoff | AUTHORITY HOLDPOINT
0428fe55-9d3e-41b6-913d-004c235f52e0 | checkpoint | 19 - Crack Bandage if crack occurs
c0a4ee8a-6132-559f-a3ce-adae801e3d5f | note | VERIFICATION ACTIVITY: Cracks
e64b0aad-c60d-515d-86e5-c36bf8c18937 | note | METHODS OR REFERENCE: Visual Inspection
756f70a6-8416-5511-86bf-057d0e29df63 | note | FREQUENCY: Each Subsection
c104e87b-467a-58ad-905d-4d9e7260659a | note | TYPE: Mandatory HOLD POINT Designer Signoff Required
effb8608-3e7c-59b0-82cd-c315037b5a7e | note | RECORDS: Photos and Report
30d44c82-a48d-5f81-a28b-7bc3a5c15901 | note | ONSITE RESPONSIBILITY: Project Engineer
4515db32-3083-5f74-8dc3-a682bf38d5c1 | note | SIGNOFF: MSQA Signoff
d9225857-2a27-474c-a838-e61700d5b872 | signoff | AUTHORITY HOLDPOINT
f5ea2b1e-b47f-44c9-8aa3-acc8b8741422 | section | Emulsion – Tack and Blind (Concrete and AC layer)
0e03f043-859b-4946-b922-d6c1ee75f221 | checkpoint | 20 - Emulsion tack coat
a282bcec-43a5-511b-9266-b511d43917d9 | note | VERIFICATION ACTIVITY: CAT60 cationic emulsion or approved alternative
90b57d26-a08c-5c0f-a3c0-a5a26e0f20db | note | METHODS OR REFERENCE: Visual Inspection
e31202f5-9797-5c83-accc-80c829fb3373 | note | FREQUENCY: each lot
b1383184-7b40-557d-baab-6e7bb130b04c | note | ACCEPTANCE CRITERIA: Hand spray tack coat emulsion
0e882760-e37e-5146-bf20-54024fb63c1e | note | TYPE: Inprocess Testing
20b40490-f7d0-5026-9956-f25da293af9c | note | RECORDS: Photos
3409d0fb-4726-5bb2-9ed5-2435bdff9e3f | note | ONSITE RESPONSIBILITY: Project Engineer
24066913-d0b8-4eb9-aca7-0910c3d030d8 | section | Structural Asphalt (AC20 – 160mm in two lifts 80mm each)
a21f75bf-74f7-40e2-b02b-9e45021d86b7 | checkpoint | 21 - AC20
e8b5e664-4150-5823-a21b-9c3ca6661b75 | note | VERIFICATION ACTIVITY: Check weather reports
0e7ea2ba-bb12-5c2d-8a53-da1287e5d4f0 | note | METHODS OR REFERENCE: Forecast and thermometer
3bec666d-7543-5609-8f2a-11fb2a453002 | note | FREQUENCY: Daily
16416743-29b6-566c-9d9d-882a93dd4cc9 | note | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
2b8b09da-3683-5bfb-b70b-349af41104cb | note | TYPE: Inprocess Testing
ac0642c2-5c03-59bf-9637-2787e6ca8557 | note | RECORDS: AC check sheet
216e86b7-d56c-5f0a-96ab-d2adfc48a683 | note | ONSITE RESPONSIBILITY: Project Engineer
edd404d1-66d4-45d6-a230-6f95a8fd6865 | checkpoint | 22 - AC20
50d2e28a-2537-54cd-9cbe-8fe9a8ef0f5d | note | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
097e7b40-f3c8-55ae-ac8c-cd368f4b9990 | note | METHODS OR REFERENCE: Visual
9b1f7455-c4c7-57ce-a1b6-5b3335745d01 | note | FREQUENCY: Prior to starting
1fb2484a-5703-5c7d-af2f-e7b3262e0555 | note | ACCEPTANCE CRITERIA: Free of detritius and loose material
46086de5-1bcd-58ee-b92f-c2b9a8d79cc3 | note | TYPE: Inprocess Testing
7060d8f4-8cdb-5214-812e-bf83941912ae | note | RECORDS: AC check sheet
e0043dda-f97f-5b28-b5d6-3c24e991dd83 | note | ONSITE RESPONSIBILITY: Project Engineer
244eafcf-aedf-4ed9-ac80-48c1af966cab | checkpoint | 23 - AC20
0e5dc4da-243c-5a92-afe3-641f7b5434a7 | note | VERIFICATION ACTIVITY: Production tests
6a96b6cf-1b2a-54b5-86ed-2ef34047dfca | note | METHODS OR REFERENCE: Grading, binder content, max density, temp
e71a8960-8a3f-55dc-a2a2-d36ce56ecdad | note | FREQUENCY: As per M/10
ec1842e6-abd1-5f94-8c7b-140a9abebd06 | note | ACCEPTANCE CRITERIA: NZTA M/10
7b02366a-aa7c-588c-bd01-7208513493a6 | note | TYPE: Inprocess Testing
90fce151-e862-544d-9936-e786580dd471 | note | RECORDS: Lab test
2e5393a2-56f5-5818-b321-923e5d125a2a | note | ONSITE RESPONSIBILITY: Project Engineer
f65f9fbb-7cfc-4f42-8ff7-5a51cd979bfa | checkpoint | 24 - AC20
6586b23d-b865-5aa1-9492-a7f9ef9593f0 | note | VERIFICATION ACTIVITY: Surface finish inspection
f5d450a1-6dbf-5b37-8b40-f73c0d4f824b | note | METHODS OR REFERENCE: Visual inspection by the Engineer
c9466842-ff78-5fde-8f6e-18df90d50bd0 | note | FREQUENCY: Each lot
c2a4888b-7de6-5618-8214-1dfdb665780f | note | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
eed7ed56-6cc9-5ea6-b25c-a3de3a9eb599 | note | TYPE: Inprocess Testing
2ed79f7a-a0a9-5a43-8922-026fc24fa3a9 | note | RECORDS: Inspection sheet
045b01fa-8e08-5ecd-8955-294998cfe3af | note | ONSITE RESPONSIBILITY: Project Engineer
33e7d387-2831-4bce-8389-d1f534e31bc1 | checkpoint | 25 - AC20
cdaed445-4ac9-5a66-a743-4dafcd4dadfe | note | VERIFICATION ACTIVITY: Density testing
26042570-18aa-5891-98c4-f4422faa37eb | note | METHODS OR REFERENCE: NDM
2564f8c0-a840-5fe4-b74b-c4a3bee8adc6 | note | FREQUENCY: Every 30m2
1bdf0f4f-bd95-5a30-8739-d67ed6348114 | note | ACCEPTANCE CRITERIA: Air voids (4% - 6%)
382177f6-d474-52a0-bc6d-4efb2501d9d4 | note | TYPE: Inprocess Testing
bcefc9e8-4854-52d8-a396-d1c9f8c9bed8 | note | RECORDS: Inspection sheet
0c502335-f7f1-5672-ba31-2a278565a142 | note | ONSITE RESPONSIBILITY: Project Engineer
35ba22ce-85d5-5d87-9c8d-130d5df28275 | note | SIGNOFF: MSQA Signoff
daf31012-e798-42c4-9450-30f99e679dab | checkpoint | 26 - AC20
4dfe974d-0906-5a8d-9ad0-162d6d7c9887 | note | VERIFICATION ACTIVITY: As-built layer
052006e4-63ff-59ae-b9f7-513387d77d88 | note | METHODS OR REFERENCE: Stringline
eaf892e1-59c2-5193-af71-20f85c68d639 | note | FREQUENCY: Each lot
4c4e2a45-448d-54ce-99c6-760f5e6efc8a | note | ACCEPTANCE CRITERIA: First layer = 60mm +/- 10mm
e7221fd1-be5e-5047-8b5b-13451e214b69 | note | TYPE: Inprocess Testing
fa59eb56-5925-5287-bf90-d5e5f148ae22 | note | RECORDS: As-build drawings & stringline measures
269561ad-172a-5cbb-875b-0a368050ee0d | note | ONSITE RESPONSIBILITY: Project Engineer
c58067bb-e2f5-4bd8-aa64-8e564e1f80d1 | checkpoint | 27 - AC20
c81634fe-f876-5602-9026-1943a307ed70 | note | VERIFICATION ACTIVITY: As-built layer
4062eb1d-45ec-5425-93c4-d329d0d3c2af | note | METHODS OR REFERENCE: Stringline
171ef5b9-5366-5cbd-87a2-047bc8455fc4 | note | FREQUENCY: Each lot
d7de618e-4eca-54d2-9dd6-c179e1a5648a | note | ACCEPTANCE CRITERIA: Second layer = 60mm +/- 10mm
a3a21702-438c-5dee-8d13-57afd9bc259b | note | TYPE: Inprocess Testing
f5e2ab86-8bed-5c32-a2a2-64aaeef8a47c | note | RECORDS: As-build drawings & stringline measures
ed13d7be-1ece-5a2f-90ec-e93a882d1311 | note | ONSITE RESPONSIBILITY: Project Engineer
4f8e2718-64ce-4d42-b873-c38b45af20f8 | checkpoint | 28 - Joint Inspection
71edee68-c39c-56d6-b858-c5a01096fbdd | note | VERIFICATION ACTIVITY: Joint Inspection
cd2dac1e-eef8-5c1e-9f4b-50b316c86f3e | note | METHODS OR REFERENCE: Design Report
cc520eb7-bb6c-513e-9265-d6d4a383aedb | note | FREQUENCY: Each Subsection
c782dd4e-6df8-5930-ae53-e2c6c9c67447 | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
2782100f-f522-5df5-b223-cb9cf86743b7 | note | ONSITE RESPONSIBILITY: Project Engineer
8f1339dc-cb86-5aad-b9a6-233e22adcab1 | note | SIGNOFF: MSQA Signoff
55509be5-b973-4a87-8d5b-45852792f588 | signoff | AUTHORITY HOLDPOINT
72e4fe26-cad3-40bc-94f0-0824adf58529 | section | No Cores on AC20
92a85bb8-f2ff-4d49-bb52-94b0c0cbe22c | checkpoint | 29 - AC20
742c29c6-0a2e-5e8a-91fd-15e21a55740c | note | VERIFICATION ACTIVITY: Density testing
2f573a71-60ef-5ee9-a960-a2532a65782b | note | METHODS OR REFERENCE: Cores (Random testing plan to be agreed with client)
77bdec7f-ab84-5837-ae1b-e614e0fd5e28 | note | FREQUENCY: 1/300m2 or min 4 no.
6e1cbc66-09ee-5e60-9b86-4e5d73fd826d | note | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
4f619795-6998-5815-805f-549e12f9ab5b | note | TYPE: Air voids to meet NZTA M/10:2020
e98e5242-cb52-5030-b924-5e5672f46dc8 | note | RECORDS: RFI response
c4997e60-cd95-55f4-9fb9-a919dace2585 | note | ONSITE RESPONSIBILITY: Project Engineer
a5ebf764-2d4a-5155-869b-9714376118a3 | note | SIGNOFF: MSQA Signoff
0c663d1a-6c41-481f-b7e0-23ee590f97fc | checkpoint | 30 - AC20
b3a830d7-ad75-53e1-9e30-3f6b9c2e8ca1 | note | VERIFICATION ACTIVITY: Thickness
6ca979aa-f4f3-58e9-a6a7-ca5bf31926f1 | note | METHODS OR REFERENCE: Cores depth (Random testing standard)
058813d6-a30d-5b52-a059-41d21a97a894 | note | FREQUENCY: 1/300m2 or min 4 no.
adc3a7a7-a0fb-59b7-ad7a-947b366c1dde | note | ACCEPTANCE CRITERIA: Target depth 160mm
1509f382-48d9-5dbe-abcf-af30442f2c39 | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
9edb6e6a-470b-5417-9a81-f5ad690bf287 | note | RECORDS: Core test report
e8c74d38-9d5c-5da3-a0d6-ad4c6ab4b3aa | note | ONSITE RESPONSIBILITY: Project Engineer
7689af21-c90f-55ef-afee-c92f9d485001 | note | SIGNOFF: MSQA Signoff
8cd36877-6786-4208-846b-2a6e0302518d | signoff | AUTHORITY HOLDPOINT
c4fc6f45-9b27-4e75-8c0b-47b4c72d7119 | section | Hatelit grid to be laid in between asphalt layers
f19136b1-7216-4130-80f3-fa17e4beae39 | checkpoint | 31 - Hatelit C40/17
bdc2ccfa-e462-5635-8b67-2c5a49f4e882 | note | VERIFICATION ACTIVITY: Length direction grid overlap
fc90a339-4abd-566b-8c5d-c1051bc156bc | note | METHODS OR REFERENCE: Visual inspection
88038cfe-9672-5621-9312-aac5b3ba0754 | note | FREQUENCY: Ongoing during install
8ab42e94-4e54-50e7-a72c-a5806fb5b37a | note | ACCEPTANCE CRITERIA: Min. 250mm
00d1c307-c8a0-5329-876a-ebfffaf09d2a | note | TYPE: Inprocess Testing
07b9327b-72da-5064-afc7-3ebb4b2152b5 | note | RECORDS: Photo / diary note / check sheet
ce978eb0-210c-5849-bf5b-5dc5920423bd | note | ONSITE RESPONSIBILITY: Project Engineer
7c7a2f28-7d65-44e9-9122-051d21d89271 | checkpoint | 32 - Hatelit C40/17
e8bf638b-2896-5c55-90e6-608fc36c26f9 | note | VERIFICATION ACTIVITY: Cross direction grid overlap
c4a476b4-7598-5f1e-a76b-5540a51b9135 | note | METHODS OR REFERENCE: Visual inspection
ecb7709f-1bf0-5171-9c97-8309e11c0aea | note | FREQUENCY: Ongoing during install
c8ecd383-449a-5c67-a8b2-52291ee6f8c4 | note | ACCEPTANCE CRITERIA: Min. 150mm
3072eb58-530d-58c8-a2ba-bb5e10c2eea1 | note | TYPE: Inprocess Testing
f2571f43-8258-5e88-b1e2-8c428b01a090 | note | RECORDS: Photo / diary note / check sheet
78ff48af-f873-5f7b-9a54-0f1be971816c | note | ONSITE RESPONSIBILITY: Project Engineer
6365835b-c84e-4d24-8db0-51687d2a8935 | checkpoint | 33 - Hatelit C40/17
9fd360e2-6146-57f7-92dc-4cc841e72b91 | note | VERIFICATION ACTIVITY: Tack coat
6119fd9f-7ec8-58b5-b70d-808ea85cb25b | note | METHODS OR REFERENCE: Visual inspection
f63a14d6-7c8f-506f-89fd-29676d743487 | note | FREQUENCY: Ongoing during install
7fb7d730-50e3-57f9-8878-7e4e6c2a8c6a | note | ACCEPTANCE CRITERIA: 0.5 lt / m2, residual bitumen emulsion (depending on surface condition)
305a5918-ef23-5137-bce2-92dfe2070f91 | note | TYPE: Inprocess Testing
f4ebb12d-d3dc-5e05-9f9d-9ac76fd194c3 | note | RECORDS: Photo / diary note / check sheet
4cfaf605-491f-583a-99a1-0217b5b1cf97 | note | ONSITE RESPONSIBILITY: Project Engineer
23d191d8-f51a-45b5-a259-448f47e6e67d | checkpoint | 34 - Hatelit C40/17
38033821-5c5e-52b8-978a-921e595fee88 | note | VERIFICATION ACTIVITY: Emulsion on overlaps
00f4cde0-4315-52de-b6c4-b276f4ec842d | note | METHODS OR REFERENCE: Visual inspection
5376ab91-1224-5ec5-81be-0fcfb9225767 | note | FREQUENCY: Visual inspection
6d3463be-7c6b-5343-93cc-4a1f0650fe18 | note | ACCEPTANCE CRITERIA: 0.5 lt / m2 if required
7d419d88-151a-54ad-b50c-d379eba43420 | note | TYPE: Inprocess Testing
22f24085-0db2-5948-aa13-ac6246072f42 | note | RECORDS: Photo / diary note / check sheet
55dc67e4-d1af-51b3-a393-f29c49df9053 | note | ONSITE RESPONSIBILITY: Project Engineer
e6f700f7-4420-469e-a56f-eb799494210e | checkpoint | 35 - Hatelit C40/17
e75a7133-f777-5279-a61f-b1808e7cf968 | note | VERIFICATION ACTIVITY: Evenly laid grid
c1f81bc4-29b7-5da3-9c99-a66511bccccd | note | METHODS OR REFERENCE: Visual inspection
aadae70c-2e41-5269-9152-ed736386ba94 | note | FREQUENCY: Ongoing during install
4743a2c8-fe0d-5526-a2db-4ea0391b8331 | note | ACCEPTANCE CRITERIA: Minimal air voids in grid, grid pulled tight
cadf00c2-ab15-5af7-9695-3d1db6e92311 | note | TYPE: Inprocess Testing
6ebf664f-6703-5cec-a5f0-7033f1fa6968 | note | RECORDS: Photo / diary note / check sheet
bb8d07c6-391b-54ce-aebd-698fac75fab1 | note | ONSITE RESPONSIBILITY: Project Engineer
bd05484e-8ec0-4364-9b06-402a4448b967 | section | Asphalt Surfacing 40mm – AC10
93722bff-fe34-42de-ada2-85de42d1f420 | checkpoint | 36 - Rougness of Road
9434ece0-cd98-536a-a4f6-2b1c3fffa221 | note | VERIFICATION ACTIVITY: Insitu
e6a3b5f7-bd19-5fbc-ad57-13145136cc8f | note | METHODS OR REFERENCE: Contract Spec 4415
7aef245e-69ab-5e89-b9a6-a705579382a0 | note | FREQUENCY: Every 100m
42639e8c-a853-511b-96ce-9b11498fb08a | note | ACCEPTANCE CRITERIA: The new pavement shall have an average dynamic roughness, when measured over a length of 100m, of less than 60 NAASRA counts/km for any three consecutive results and no individual value greater than 70
5683c6c8-2d18-55f0-b5f9-84ac14987efd | note | TYPE: Inprocess Inspection
0cb74b48-c2c3-51f8-9a4c-43245dc62cd5 | note | RECORDS: NAASRA count
3a419569-cab3-5b32-aed6-93e40a7d5b6a | note | ONSITE RESPONSIBILITY: Project Engineer
04005aca-dec0-4d97-bf54-15079a28f18f | checkpoint | 37 - Shape of road
6931746f-41dd-5116-95b8-c4934962e2f9 | note | VERIFICATION ACTIVITY: 3m straight edge
5a043c4f-619c-5f6f-a20f-7ae95dc699e1 | note | METHODS OR REFERENCE: NZTA M/10 spec
81c8f7c7-8c68-5fbb-96e2-0182e08a8bc8 | note | FREQUENCY: At joints and any other areas of concern
1e8626fb-45f2-5b7f-8215-07f5609e683a | note | ACCEPTANCE CRITERIA: Irregularities < 5mm under straight edge
9eb99e9c-3087-57a5-88b0-82ae6555f376 | note | TYPE: Inprocess Inspection
5b5863c1-b3aa-5718-9425-f321f9a43c8f | note | RECORDS: Check sheet
98ab93d0-5b05-5384-9578-5644da029df2 | note | ONSITE RESPONSIBILITY: Project Engineer
c8bda25c-5800-461d-a7e3-41918df97033 | checkpoint | 38 - Temperature Limitations
d1f9e22f-0080-5a0d-b661-72572352d08c | note | VERIFICATION ACTIVITY: Temperature
e27c7941-f94c-544f-a664-be08ab4efaa1 | note | METHODS OR REFERENCE: Contract Spec / M10 Spec
d6c255a0-6940-5ff3-be10-e1a8d1498594 | note | FREQUENCY: Every Site
008cbb80-4ba1-5bec-91b6-6565189a2d97 | note | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 120 Degree
604a6772-2855-5898-8ff2-f1bd5f8c8291 | note | TYPE: Inprocess Inspection
96cd490f-0fd1-5829-9f35-58970fa15d2a | note | RECORDS: Asphalt QA
80f4c701-5ae0-5f6c-9c8e-95586b6533b3 | note | ONSITE RESPONSIBILITY: Project Engineer
e61cd482-e287-4d47-9125-a27a1f687d47 | checkpoint | 39 - Surface Preparation
8c7ef207-5cab-5f28-8661-5982779db2cb | note | VERIFICATION ACTIVITY: Visual
3eb8ce39-25d9-5f7b-ba71-49c2ca166469 | note | METHODS OR REFERENCE: NZTA M/10 spec
ef6ee83b-685f-592f-bd81-18d4e86101f7 | note | FREQUENCY: Every Site
c0714d1a-65dd-520a-a154-a1097c477e6b | note | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
a585498f-2786-58a8-81bd-750be07492f0 | note | TYPE: Inprocess Inspection
e1ef541d-d224-5106-aa8e-d90b4dd62c00 | note | RECORDS: Visual
b2089790-3279-548c-a2ca-b4ba57f5167c | note | ONSITE RESPONSIBILITY: Project Engineer
408d0b82-e62c-486a-b73f-8217baa13009 | checkpoint | 40 - Asphalt Production Tests for AC10
561aff4c-a865-52af-bed2-d5fbce5c97ec | note | VERIFICATION ACTIVITY: Production Tests
e23a4b0c-3232-5155-9fb2-a98cccef153b | note | METHODS OR REFERENCE: Grading, binder content, max density, temp
df03eb94-0b54-54e2-bedb-9c15b662cee2 | note | FREQUENCY: As per M/10
0568eb77-6ac3-5f91-b16d-2ac628804997 | note | ACCEPTANCE CRITERIA: NZTA M/10
1721cd02-e6ff-5be5-a60a-78df453f9b30 | note | TYPE: Laboratory Testing
404ee30c-5fe9-5862-a126-6ce8bfd2f122 | note | RECORDS: IANZ Lab
acec4398-901d-5887-a551-ffb2ec71323d | note | ONSITE RESPONSIBILITY: Project Engineer
b5a7ec0e-4249-4252-86fd-88046e1da34b | checkpoint | 41 - Joint Placement
564ec683-249c-5f58-a51d-d162bf6c239a | note | VERIFICATION ACTIVITY: Paving Plan
607d2fbf-6280-5c7f-be2e-59f28906294f | note | FREQUENCY: Every Site
af36b81e-9078-5a6b-a793-8865c9dfd761 | note | ACCEPTANCE CRITERIA: Paving Plan to be completed for every site with dimensions. Joint sealing shall be applied between new and existing surfacing. Joints off-set 150mm
0eae5c83-b80a-51f5-9374-e94f38ec722e | note | TYPE: Inprocess Inspection
e32e1417-262f-5ebe-93e1-64b227652404 | note | RECORDS: Nil
70ba28f7-409e-5096-b5a7-2028793cbc32 | note | ONSITE RESPONSIBILITY: Project Engineer
19ef3033-f544-4f1d-9c67-23f76c3fe7b7 | checkpoint | 42 - AC10 - Layer thickness – 40mm compacted depth
ccef8ce1-ea7b-5afd-830f-4cc400b7b42c | note | VERIFICATION ACTIVITY: Insitu
734a303a-b7c1-5179-9df2-e3d70736aee4 | note | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
851ddea6-7d0a-5f78-a289-d7cb32468d43 | note | FREQUENCY: Continuous
f6eb79a4-0adf-5d5f-b6f6-ecbd491494ae | note | ACCEPTANCE CRITERIA: 40 mm minimum and 45 mm maximum compacted depth
9785e211-903f-5b94-8efb-07dba4a17a62 | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
f44750fd-4bc0-5c18-94b4-5105c30df241 | note | RECORDS: Asphalt QA
fa188271-c404-53a1-b169-1ddbc1c53b39 | note | ONSITE RESPONSIBILITY: Project Engineer
6784e39d-0789-5df7-9681-ab0abbf02284 | note | SIGNOFF: MSQA Signoff
6dafaf15-a478-4082-b07d-991163650c4a | signoff | AUTHORITY HOLDPOINT
64c7915a-c5d4-42dc-b620-1cc4d06ba87c | checkpoint | 43 - AC10
1d183fd1-55a3-5117-9b8b-0ac049fb4358 | note | VERIFICATION ACTIVITY: Density testing
2c02055a-fe9c-51c3-a2ec-4567ced14a59 | note | METHODS OR REFERENCE: NDM
34e58e87-2688-5589-a8e5-349d8b807859 | note | FREQUENCY: Every 30m2
02f36945-c638-5d19-b3e7-c6cd9ef1682b | note | ACCEPTANCE CRITERIA: NZTA M/10
e67e8564-52e6-573a-aec7-4cc64a52feac | note | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
9c40bcdf-6fa8-5aa5-aa62-69d577701426 | note | RECORDS: RFI response
cb97c07c-8d83-536f-92a2-4a51c7a240eb | note | ONSITE RESPONSIBILITY: Project Engineer
dac735ef-ebc5-5a9a-9025-9f54f4aa7cdd | note | SIGNOFF: MSQA Signoff
5000c2d8-7521-4f0a-a8b4-f99558ed73d2 | signoff | AUTHORITY HOLDPOINT
406e1a99-3529-43bf-81cc-49c65bf125f9 | checkpoint | 44 - Reinstatement of Linemarking and RRPM's
294b1017-3079-5e37-b6cb-0e71dc951a38 | note | VERIFICATION ACTIVITY: Visual
cd9362cc-6e9d-5ee8-ae33-d6cbd39489f5 | note | METHODS OR REFERENCE: NZTA M7 approved (Class B or C as required for anticipated traffic level)
3806d432-724c-5d3c-bdc4-50c3c7d1954c | note | FREQUENCY: Every site
91673ce4-35d4-59fb-bd99-d1ee093b7edd | note | ACCEPTANCE CRITERIA: Carried out within 12 hours of each shift completed and as per the existing markings
d6cd9fad-66a8-5907-a492-870d000e2544 | note | ○ Suitable Traffic Control to remain in place until pavement markings have been reinstated
8332ecda-97a7-5cd6-a73b-14374b20c62d | note | TYPE: Inprocess Inspection
7f19346b-b559-5492-9c24-4804d5f729fa | note | RECORDS: Linemarking Records
db882b6c-680e-5ae7-96b4-7403c09d1889 | note | ONSITE RESPONSIBILITY: Project Engineer
a7801a17-6121-4f94-833e-91c9d912f463 | section | APPROVALS
d7114ecc-db3a-4f28-b4e1-7758cc5dff95 | checkpoint | Approvals
9e375855-5fb4-5b9a-96e2-cf95a1275506 | textbox | Approved by Project Engineer:
3dfa362c-e2d7-53bd-b1f8-11b0981f157e | textbox | Approved by Contract Manager:
f9155381-a583-5944-b825-ead99af6e1fc | textbox | Approved by Client Rep:
| checklist | Weymouth Construction - Weymouth East - ITP - Ducting | itp | ITP - Ducting | 9db362c6-2ff9-40b7-bf89-e3a99e56aef5
| section | Ducting
| checkpoint | 1 - Permits
9b807ea2-71d8-5a65-9a1a-43780a0dd313 | note | ACTION (Hold, Monitor, Witness): H
6d0eee13-7c66-5bc4-9160-707c45e0c304 | note | DETAIL: Obtain Permits
c5c89645-f32b-5355-965c-3cb9da63a109 | note | FREQUENCY: As required
16e14ab9-3a8c-50b5-b6e0-2458d721ba23 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
e9e8b52f-3624-5c9b-bb8f-945eea0e81fb | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
1009f135-6507-5696-9a16-5b0477b685cf | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
ac4e755e-7408-59b0-a8cf-efb36893d335 | note | ACTION (Hold, Monitor, Witness): H
4df5ae24-02e8-531e-8451-f858f67f8d4d | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
fdf3a2e6-d7ec-55cf-834a-5ceff82a93ff | note | FREQUENCY: Prior to commencement
a1071c44-093c-5a5d-9f4d-5247c7456ae5 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
e26d652b-38f9-5bdb-a0d0-5b8306b06f3a | note | CONFORMANCE CRITERIA:
ac4cf49d-ac2b-5b59-a860-02101f71b078 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
7bfd2893-e908-5ffa-bf7e-84943ed90400 | note | ACTION (Hold, Monitor, Witness): H
3bc6bee7-9e4d-57cd-bf39-e2e7f48be370 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
575c68db-a39b-5782-ae75-719888cba936 | note | FREQUENCY: Prior to commencement
7e448c11-35cb-5356-950f-d1c8dabe9539 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
bd5b8dcb-27e2-5902-9d17-d2f98c2ce954 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
54125066-6a6f-5829-8ca5-ff2256a8ddfc | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
87d69396-0d82-5e32-b4d0-fe4857293fc4 | note | ACTION (Hold, Monitor, Witness): H
b6d2a170-10e7-59b1-b9c5-bf664f7ccc0c | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
9686a1df-07f9-5a15-83cd-b9e383e06994 | note | FREQUENCY: Prior to commencement
39cdb821-2993-5fee-bf30-59d865080c3a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
07994887-073d-5aae-af64-4669b264dc38 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
c74d4aef-2e19-556d-9024-674c27b06ae1 | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
eed985a2-ce41-5b2b-aeaa-46a9f3cc8ed3 | note | ACTION (Hold, Monitor, Witness): W
7080eb20-6117-5805-bf07-f9cd007c3d3b | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
c6d09318-9b99-5454-a100-06c345928d3a | note | FREQUENCY: Prior to Installation
f78de4f2-c230-56d8-b5a2-80ad11bdef0a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
603d02ac-c575-5bc5-9dd0-3eb543020797 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
a6e87ad5-4811-587c-8f93-f7be89388d79 | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
f239d5a3-5385-530a-9753-3305d94758b2 | note | ACTION (Hold, Monitor, Witness): H
ae1a60bc-824d-5cab-9d13-2fa8d2725275 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
1cc2ca67-39a9-5c43-a2f6-a9875f029cba | note | FREQUENCY: Upon delivery to site
911db722-a943-5692-b64d-71d60097605b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
c2015ea2-5314-5b87-a026-a169b2bb71eb | note | CONFORMANCE CRITERIA: 50mm Ducts
977a2b3d-1434-5a9d-a539-c389a9501cb9 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
e3a8cee6-0170-5bbb-942a-57f05d95ebec | note | ACTION (Hold, Monitor, Witness): H
6eb8b300-e2ed-5a5d-bb7e-c3334ac92144 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
80dfdbaf-3a93-576e-9390-f16dae3516eb | note | FREQUENCY: 10m Intervals
74b06afa-ff7e-5f52-8276-efa4ff6acda9 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
4ca2027d-419a-5715-842a-5f14124dcf7e | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
40bcb3d3-8996-53fc-abd8-c75c31997d6e | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
91ff3f7d-7c26-56ba-afb1-8a9294b35c33 | note | ACTION (Hold, Monitor, Witness): H
cf9bdf8e-d7a0-5176-8627-371d269259ab | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
dd2650a2-efad-5795-82cb-c6c2f42ccc28 | note | FREQUENCY: 10m Intervals
28e1cf6a-8d94-5656-a984-a2ea6ee4b3e2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
ff39eb06-1922-5d35-a929-eabfc7817c46 | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
40113de4-7606-5e70-ae74-e1a4f6a02e6d | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
7d670fdc-765e-5ba9-a5b3-06d59167cc47 | note | ACTION (Hold, Monitor, Witness): W
41d8aeb2-6d0e-5972-82c2-51c9889701a2 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
5b05feed-dfb5-58b2-b66e-1342133f06ac | note | FREQUENCY: Prior to Installation
b43732ec-0cd4-5399-a4de-2e5181448ef8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
ebd090c5-547c-528a-bc92-9e3f9621eb7b | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
68847a10-cf56-5e9d-a3ce-cda9d4413d57 | note | RECORDS: Photos
| checkpoint | 7.2 -
0206b909-ff8b-5013-b1ee-2c923d225c9c | note | ACTION (Hold, Monitor, Witness): H
6cbe10ce-6d41-57d1-bb3d-5856023f0c63 | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
b628a70a-4dcb-50e7-9770-5502fd4fc914 | note | FREQUENCY: 10m Intervals
ac81c0df-d192-5e46-9756-fd057c5850d2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
b7658e76-4b44-58cc-9c8f-3558713e9317 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
3283431d-340b-5152-81e2-dc1bbeddeecc | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
d9c778ea-05bd-5bbb-ae90-9eb4cc311159 | note | ACTION (Hold, Monitor, Witness): H
20261377-560e-58a5-9a4d-fbe4146c35a4 | note | DETAIL: Asbuilt Survey
eb221943-f4c2-50e9-89b8-23572d392154 | note | FREQUENCY: 20m Intervals
99696d74-bc38-5aff-86d7-8956ad619084 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
1dd247f5-211b-5a8d-b922-b428a6d72b88 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
3386ba66-d25b-5c45-95a1-d8d60d45f54b | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
cda1dbe3-5335-5627-b8e1-051fb1ab2d0b | note | ACTION (Hold, Monitor, Witness): H
b5e5a0c3-1e66-5a75-bbd2-42bb89925046 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
fd477d12-5b09-568d-b220-345fd83b72f7 | note | FREQUENCY: 10m Intervals
5c7dff9c-2f9b-5aae-bb63-4c0c18dca589 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
c416f9fa-9096-5658-add1-b42e80a653d7 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
403e3488-cc9d-5896-a162-8edf3e1f4b1f | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
33c6a9a1-8c49-59e3-9171-d088bff08860 | note | ACTION (Hold, Monitor, Witness): H
5c6ae00c-09b0-5db8-babc-189e7267750f | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
3fe1bff0-812d-57d3-bad6-b030039f5d0e | note | FREQUENCY: 10m Intervals
46f40fab-3228-5d6a-8060-35af7c46452a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d2a73287-d36f-5856-a499-a6cabdbf872f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
c8563e19-552a-5def-8694-61f29e5af09b | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
515a691d-4d58-50ae-bd40-991ae29a0323 | note | ACTION (Hold, Monitor, Witness): H
5c4bb835-9a18-576c-9984-3245b76f4b3b | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
258ebbd8-1670-5cea-a117-11367b37f529 | note | FREQUENCY: Eash Site
7fbcf8c5-7532-577c-8bd8-e10d276c3c8d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
1c5e4bfc-1567-58e1-8876-416d7dff7fae | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
df3ee9bd-70b2-51b1-a25b-3afd950e3e01 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
719a5bf4-2d4e-5741-a3a4-7fcdf0f15085 | textbox | QA Compiled By:
eebc3237-f64b-5707-8d41-cbb0b8cfbe25 | textbox | QA checked By Project manager:
b9d7fb39-79d5-50f5-b190-4ef8dcd83339 | textbox | QA checked By Contract Manager:
24e7dfe1-62d3-5015-8342-870aabfe1d48 | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Weymouth East - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 628aadbd-9df4-41b9-bbbd-d1c274422efc
| section | Site Set Out
| checkpoint | 1 - Site Set out
a94bc035-b09a-5ea7-b283-5c2679066de4 | note | VERIFICATION ACTIVITY: Surveyor
c6c7b602-d45b-5e5a-9e2d-8f06722b10d9 | note | METHODS OR REFERENCE: Surveyor
f121836e-f925-5f79-8178-b47c6f3ffc9d | note | FREQUENCY: Everysite
3aa57f08-a7a4-5b72-b1e8-13729e67145b | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
015e60af-108a-5351-bc95-82f9c24a6acb | note | HOLD POINT: Mandatory HOLD POINT -
baa004e0-6da6-5b3e-927c-4cf35d6d10d8 | note | RECORDS: Onsite records/photos
d2f4f5e4-38f7-504f-b298-5e08401d74a7 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
032e1c21-21ae-5090-ad79-a9276118b823 | note | VERIFICATION ACTIVITY: QA FORM
b27a031b-68d9-5224-a9a1-435cec941881 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
84f6b402-bbd2-5edd-8ab9-9ebe11fa4017 | note | FREQUENCY: Everysite
cb5b5085-3c44-563e-8db1-a5e464968660 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
c777481c-9723-5266-97b7-3ef95b55c48a | note | HOLD POINT: Inprocess Inspection
e78b6fcf-52f6-5387-aa81-9b5ec6dc46f1 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
2b79d070-8357-59b9-8a6b-e8ab220a7818 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
26f3626e-2530-5c78-b66b-d65e94dd1785 | note | VERIFICATION ACTIVITY: QA FORM
b0dbfa9c-ff55-5b65-908a-e8ce9fd213c2 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
9bea2d40-7680-5431-b212-f3e471be6e4d | note | FREQUENCY: Everysite
c4edcb6b-5d42-57e1-9338-c3a9f6c5a30e | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
506a9b8d-7fb2-55a3-96ad-633459fa0ca0 | note | HOLD POINT: Inprocess Inspection
db402f3f-52bd-5782-8bb1-d391588d8bff | note | RECORDS: FH concrete QA sheet
c427a503-028a-5839-a66a-d1e26575bf10 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
f5cb94ab-9aee-5132-b107-44e82e2d3897 | note | VERIFICATION ACTIVITY: QA FORM
b0a832a0-37cf-5d45-a792-a093e24e0469 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
47ac6833-c759-5862-827d-3fb3874014f4 | note | FREQUENCY: 10m Intervals
d347a46c-5b12-5bed-acbb-2b2f119f0c70 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
fe1987d5-98b6-5232-966d-d6fc6ebf5aeb | note | ○ Basecourse - 100mm min. thickness
f2f07ca4-b600-5b35-a777-c01e851efeb3 | note | ○ Clegg CIV > 12
e5d58e90-42c2-54ac-8696-b84c38154327 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
f0e31569-7507-56ad-92a4-6a54d57d0e90 | note | HOLD POINT: Inprocess Inspection
1685148e-207b-5680-89a5-814268b2d16e | note | HOLD POINT: Prepour inspection
9100ddc4-71cb-5937-a401-a38fa3e6b634 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
d2663a29-531a-5246-8055-26122993adee | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Shared Path Pavement
6c4894bc-6613-59b1-a205-8dfe01665ce1 | note | VERIFICATION ACTIVITY: QA FORM
3a78134e-b513-5f45-ac17-5214dfaaffb8 | note | METHODS OR REFERENCE: IFC
ba4e0185-9490-5656-9938-0f76ad6e1142 | note | FREQUENCY: 10m Intervals
15971630-325a-5e71-9000-8460767fe9c2 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
dbc15019-fe42-500d-b9ad-292d80aea1c2 | note | ○ Basecourse - 100mm min. thickness
6cc63b98-5435-5da3-9d6a-f18eb8915f83 | note | ○ Clegg CIV > 12
552fea38-0d21-58bc-afec-b02de25b6589 | note | ○ Surfacing - Concrete 150mm with single layer of 665 mesh(50mm cover) and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
a9e701ea-f70c-5cc8-8c2e-28a9b851e83b | note | HOLD POINT: Inprocess Inspection
08c4ee3d-d3d4-5fd4-8a40-aabe4e6df512 | note | HOLD POINT: Prepour inspection
9446736d-1b63-5ada-9294-8eca5a7057d5 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
0a9e0fb4-8f45-570f-9453-d609ea1b132e | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
d66e8b15-f719-5b99-880e-a629dff6b89a | note | VERIFICATION ACTIVITY: Visual
f398da86-a711-5abc-b1b1-bd20465492ec | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
0237a66c-fed4-52f6-8d6e-03b09a2c2f40 | note | FREQUENCY: Everysite
c0ba60a3-9764-5484-b2f1-0bb1e748081e | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
5d67d8d8-d030-5a2d-aa1f-502f5f375020 | note | HOLD POINT: Inprocess Inspection
38ece486-0460-5350-9f3c-72a5571d60bd | note | RECORDS: Photos
6fccfec6-cc2a-596f-b20d-fe2047de6296 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
0ad5f189-c9b5-5d50-881e-be0833399143 | note | VERIFICATION ACTIVITY: Visual
f148a2d2-07c7-5dc8-ab00-f4ace0f533a2 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
3243b5cc-9f5f-5502-9fbe-635c31e33720 | note | FREQUENCY: Everysite
f2c6e28c-157d-500c-9eee-c627f8f4dc2b | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
e7106fa5-d93d-5b00-b3a1-95e708c7ad1c | note | HOLD POINT: Pre-pour inspection
2452db04-f382-58e8-b2f5-305ffadf73cc | note | RECORDS: Photos
ceac15d9-9981-59da-a83c-e9ed1214af5d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
a5744ce0-1821-5152-b3db-da0cbb4fa7c4 | note | VERIFICATION ACTIVITY: Visual
d50ffb1d-10c8-519d-b4d4-08c9bc510e2b | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
f17e7dc5-18e1-5887-a2c9-4edb834396d7 | note | FREQUENCY: 10m Intervals
0ef0eb42-0c02-5322-9d6e-a85b44cba127 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
0d60d001-0bf7-5500-9dbc-bbdb4eb00f75 | note | HOLD POINT: Inprocess Inspection
9448cff0-6064-5f74-b1ef-4d7518b3e403 | note | RECORDS: Photos
cce440c2-ae0c-55af-8364-42c855107113 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
f01f5b16-f18a-54bb-9607-145ca62f64a6 | note | VERIFICATION ACTIVITY: Visual
b857e7de-1fe0-5b9c-ac97-41243a3f498d | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
a8c2e6b9-526a-5f8c-a1b8-a87b92fe7e9a | note | FREQUENCY: Each PX
4a0fa73f-1c24-515a-a01c-f60358f4e0f2 | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
064079e3-4ebe-5b75-96f5-fdfb3ae9647b | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
7fde4fac-f7ef-53e4-bf87-e830801b8790 | note | HOLD POINT: Inprocess Inspection, Measurement
6751e40c-6421-51ff-9f56-0426144709f2 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
89e63ab3-747a-53ad-bb29-b6cdba12db55 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
dc7f6b02-4616-5660-9683-1f6022b041d3 | note | VERIFICATION ACTIVITY: Visual
700f3224-6ed6-55cd-be81-e8cd9b205ee0 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
f4d5dce0-bfdf-586e-8d47-88ae109cfe4f | note | FREQUENCY: Everysite
b30df0c6-b84c-50a9-a555-b20c25b8b1d7 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
4de5b7aa-cc85-53ad-a6f9-b08ebc61ed72 | note | HOLD POINT: Inprocess Inspection
609dbf3e-b4ba-50c2-986a-36fd278341ea | note | RECORDS: Photos
78d94d85-0c02-5957-8d39-e7f877b1731f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
af0ede81-0b65-5100-8ad8-a771233d851b | note | VERIFICATION ACTIVITY: Visual
fe52156c-a09f-57c9-91e9-c65f728688cd | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
a19119e7-ffb7-5fbb-ae62-5fb008bd056e | note | FREQUENCY: Everysite
2d084ddb-bd0a-5383-8b73-6897357c67f4 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
07318148-f63e-52b0-97b4-c3e451e4f9f0 | note | HOLD POINT: Inprocess Inspection
634c0c28-99d5-5a2b-aff9-4d34561bb0d8 | note | RECORDS: Photos
57d53bf9-1cfb-5f60-a63b-52eef1a5d7bf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
39e23c6f-98a5-5596-ad47-085eb64bde3a | note | VERIFICATION ACTIVITY: Visual
a3ebddb6-37b7-5ab8-a961-dc3a144e4bde | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
fb125a4c-424c-5e51-b19f-c0ed45bfe45c | note | FREQUENCY: Everysite
31eb8248-30f6-5853-9b0a-df27fe424f49 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
4d720514-a4ee-55cb-900d-0f26701ea29b | note | HOLD POINT: Inprocess Inspection
7ab4d1fc-5761-5deb-9f17-9b57b664c6d4 | note | RECORDS: Materials Dockets
e0ffa713-bda0-5fbc-8f0c-b07c2946c249 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
9cdbaafd-e34e-5fdb-8c2d-4cf3f490d26a | note | VERIFICATION ACTIVITY: QA FORM
4c054007-326d-5e67-8e02-a5b65e5fa71a | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
f0d1eafc-8e8b-5fcc-a97c-ee2b04beba37 | note | FREQUENCY: Each Crossing
08f56218-5714-53a5-877b-1a99cb63c25a | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
86b651b4-9963-5081-857f-3d99524b87d1 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
8791efdb-867e-5ed5-b87e-439686eeb7ae | note | ○ Slope no greater than 1:12 where practicably possible
cb8edaec-c829-592a-a813-d31706232e4d | note | ○ Clegg CIV > 12
6ee6c2e2-67d6-5694-8dbb-c659d050a4f8 | note | HOLD POINT: Inprocess Inspection
f5974dea-618f-5109-807c-0004f113468c | note | RECORDS: Photos
f77301d5-3e45-5d72-8ecd-c5d5bea70d4c | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 10 - Timber Retaining Wall
04ec1e1b-1925-5f51-929a-5b57ecf1610b | note | VERIFICATION ACTIVITY: Visual
12756a54-38c5-5335-bf25-10a91c80b4ed | note | METHODS OR REFERENCE: TDM ST0004 - Version A, Timber Retaining Wall Detail
21f1fd1d-d34a-5acd-8550-f9f01b9a421a | note | FREQUENCY: Everysite
3e122755-5b2a-52d6-959d-60f20b6cd86d | note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
3b62563d-4d9d-58b1-8fdc-6e0bef15434d | note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
ae1d3178-0837-54bf-8e2e-ebfcefa79c69 | note | ○ Retaining wall slope to be 10:1 grade.
8d6e007d-451b-50a3-a8f1-a4e56a4ffb9c | note | ○ Maximum height of wall = 1499mm.
2afe07ab-a39b-54f6-ad9d-53a75a1e07f1 | note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
32664cc1-0a66-5425-8149-1689e9cfabaf | note | ○ Subsoil pipe to be lay as per TDM and connected to the nearest CP
f40927f6-7e9a-50bd-a3a7-572569b78605 | note | HOLD POINT: Inprocess Inspection
ad060678-cee8-5aa4-85b7-50d382352335 | note | RECORDS: Photos, Material Dockets, Dimension checks
814aa5db-9301-5998-9bf3-8d47330a881f | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
8396548d-2ee0-524a-b049-10226fe032f5 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
95db9887-e4a4-5bfd-a7e7-026d3350d23c | note | METHODS OR REFERENCE:
8f31f604-6c9a-57e4-8bb1-89508998e8df | note | FREQUENCY: Every Site
4529fc5a-f08e-5f06-a75e-1ff8e75bf0d3 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
1629156d-dcba-527e-b796-f1ee12bbe07d | note | HOLD POINT: In Process Inspection
bedaef92-d251-562e-b9d3-543b867c9d06 | note | RECORDS: Asbuilt records
9518fc34-9c00-5b85-9a6b-ef90a529fe16 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
21292868-239f-5d0c-a169-d1bcdc343cc7 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
28276547-cc74-5410-8afc-6e742e6ad824 | note | METHODS OR REFERENCE:
ef094016-5a8b-5654-a835-c34a560ae99f | note | FREQUENCY: Every Site
53ddeabc-060a-5a12-b9e2-354949d2ac2d | note | ACCEPTANCE CRITERIA: RAMM SHEET
07e0c822-24f1-5c20-968d-75fc99bd36b0 | note | HOLD POINT: In Process Inspection
e87a190c-7d67-5b24-af0f-a0140f471357 | note | RECORDS: RAMM Sheet
4d4bafce-a08c-5e34-8114-24b71496c046 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
854c9b17-b232-5637-8144-db80ee06611c | note | Prepared by: Ajithkumar Ayyanar
2809910b-fb6f-5c1e-b2d0-03244cb3884e | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth East - ITP - Signage | itp | ITP - Signage | 66ae37c5-8c94-4a28-b0f2-da1a10c97edb
| section | Site Set Out
| checkpoint | 1 - Site Set out
e5f6ac79-3181-565e-a639-cb2878372c0e | note | VERIFICATION ACTIVITY: Surveyor
dc99f033-6793-572f-8557-2b8cd098c0a7 | note | METHODS OR REFERENCE: Surveyor
40e554c4-6e1d-5cda-8f20-6d0930e82aee | note | FREQUENCY: Everysite
d90c5f6a-794d-5526-82c8-b9ed598bf8b0 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
b21ede61-554f-50b8-a590-c8a1d22085f2 | note | ○ Alternatively like for like
2071508e-f479-53d4-a7d4-ff72de0c0708 | note | HOLD POINT: Mandatory HOLD POINT -
1fd25641-4708-5446-8a28-2277c2247c34 | note | RECORDS: Survey Receipt
c9be92bf-4315-5e69-a9b7-44fd462c5b04 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
98a76ffa-f08c-5784-a4b9-f5b1b7f347a8 | note | VERIFICATION ACTIVITY: QA FORM
7360ec93-4da8-5550-83f0-b7f8961128de | note | METHODS OR REFERENCE: TDM Technical Standards
eb49850c-06b6-5f87-bf04-088490f86661 | note | FREQUENCY: Every site
7c400452-94f7-57a0-b3f2-b47c31d5e714 | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
ab494d3f-229c-587c-b6a3-1fe576b6b95b | note | HOLD POINT: Inprocess Inspection
0d7d628a-22b9-5072-9965-f1989b5f8451 | note | RECORDS: Dockets/Photos
42a1571c-4ccb-5641-b943-d992615055c5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
73408980-e1a7-54d9-a3d8-7bd2c3d6a291 | note | VERIFICATION ACTIVITY: QA FORM
9dd4186f-d6ad-5b41-a87b-f909bb0f0795 | note | METHODS OR REFERENCE: TDM Technical Standards
86da8450-4fac-564f-9ccb-56650c69cf3f | note | FREQUENCY: Every site
0d9ea1e4-4372-51fd-9c1c-64b354a7407f | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
8a0aceb8-edcb-55a7-b8a8-4290dbd5aab2 | note | HOLD POINT: Inprocess Inspection
466ca0b3-965b-5123-aeeb-0508beef92ac | note | RECORDS: Dockets/Photos
df29ef60-e927-5580-8674-3e89987796d0 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
a4f2ad25-ea8a-5fd7-8017-6c63504fb6fc | note | VERIFICATION ACTIVITY: QA FORM
26cff03b-2010-599f-831c-ebb51484605d | note | METHODS OR REFERENCE: TDM Technical Standards
54cc56b9-7a32-5a52-b5d7-e29e2f1e35de | note | FREQUENCY: Each Socket
2677dd8d-32e7-5102-8c4b-b75ea96949bd | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
43abe010-35a4-5264-b36b-590ff2a0d948 | note | HOLD POINT: Inprocess Inspection
a52407c6-a1df-5b69-ad18-6962495c316b | note | RECORDS: Dockets/Photos with tape measurement
3ce7b0a0-dd11-5d5c-af2a-47f8908e1103 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
603a59bd-a5ae-5af0-817f-ded6a0d08d6e | note | VERIFICATION ACTIVITY: QA FORM
180db986-177e-5860-aeb8-4b0a139c080d | note | METHODS OR REFERENCE: TDM Technical Standards
64501ea9-1f5f-530f-9929-f874c7b5df1f | note | FREQUENCY: Each Post or pole
3ce5e804-e662-5bc0-9d9e-d785c95ac315 | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
a5cea427-9ce2-5472-8b62-d4c115b1df85 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
1c8b22e5-a028-5061-936e-414ee77d287f | note | HOLD POINT: Inprocess Inspection
e0e44798-f682-58da-bd89-30489fd149b7 | note | RECORDS: Dockets/Photos
20ae47f3-203a-51fa-ae16-353f5a3b5754 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
c74db19e-c0d9-5664-b016-1f051ae33a15 | note | VERIFICATION ACTIVITY: QA FORM
d79e77ac-4195-570f-9491-41b324ac347c | note | METHODS OR REFERENCE: TDM Technical Standards
9e01c9ab-c3c4-5571-8b01-1ec5ee623896 | note | FREQUENCY: Each Sign
e64c5003-7b95-55e1-94a6-f71f0c390407 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
b9351626-45e7-5057-9150-4c6a0e2d2842 | note | HOLD POINT: Inprocess Inspection
45460aa0-b592-5581-99bd-1c877aa53332 | note | RECORDS: Dockets/Photos
30e72ebf-d9c4-51a4-8812-8596402b4224 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
e8ecb998-daa3-5f4a-827b-00131fcdcb87 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
7358e8a4-a6da-5403-9a97-5ecf5fc5aa72 | note | METHODS OR REFERENCE:
5fbc199e-f26f-5a6e-9b65-a16ca3d27063 | note | FREQUENCY: Every Site
b3d44311-9817-5c4f-bcd7-cbc6755e0582 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
cf79c8dd-e167-57b0-aa6c-857bd61b6d2c | note | HOLD POINT: In Process Inspection
b83e17dd-321e-5498-9d52-2d75cb877af7 | note | RECORDS: Asbuilt records
002330fc-bd33-5775-8072-eee287a7c302 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
c19bde38-e5ac-53f9-b6de-88e378534ac8 | note | Prepared by: Ajithkumar Ayyanar
c3cf0019-0817-58ec-94d1-d6e9ef1710e9 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth East - ITP - Traffic Islands | itp | ITP - Traffic Islands | 7a3b007d-8b94-4f8a-9dd0-1d9b60b9ae5a
| section | Materials
| checkpoint | 1 - Mountable Kerb
86333c33-b12b-5580-9f55-9c9571429a97 | note | VERIFICATION ACTIVITY: QA FORM
096bed7c-4b79-57e5-920e-87d1006c4541 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
8d63a8f0-b137-5601-af32-8eda4bff5fd1 | note | FREQUENCY: Everysite
358e43b4-3384-5a5e-bded-272acfd560e0 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
add294b5-8ccb-5115-8e4c-a7dcc766a113 | note | HOLD POINT: Inprocess Inspection
a4dec873-cab1-50c0-b7eb-2a5f33dac1ae | note | RECORDS: FH concrete QA sheet, photos.
26ac3195-9cfa-5182-812c-159ae91a9156 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
86d33652-706c-5dc7-bc2b-890d38104abc | note | VERIFICATION ACTIVITY: Survey
1776878a-f034-5f49-9f60-fcfbc25f8c27 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
b8b01a24-24be-5ebe-8d91-cc750f105d8d | note | FREQUENCY: Prior to commencement.
917020de-becd-50d2-aae2-fb2a4f1b0e84 | note | ACCEPTANCE CRITERIA: Survey
e01bda92-b0d6-5d08-be66-833909af7bc1 | note | HOLD POINT: As per Construction Drawings
bc61fe24-ea2c-5169-a838-167e8bce5673 | note | RECORDS: Survey Receipt.
828333b6-5ea6-514f-8cd8-130c07e50e23 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
408b8571-88b5-5f61-824d-0d62edf3bead | note | VERIFICATION ACTIVITY: QA FORM
2053b9ca-fa0d-501a-9b0e-9efa40cad169 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
d1575aab-77e5-5b7c-ad39-4b1c4453186c | note | FREQUENCY: Each Site
0eab1648-38dd-5353-b077-0ff771280269 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
2a2be2a9-5ee3-58ee-8c41-9381c61cb1a5 | note | HOLD POINT: Inprocess Inspection
1de8c30b-d02e-5e39-8029-a27304a045a9 | note | RECORDS: Photos
1bd3caf1-2f0c-5401-b5c5-5d934cbe9ca5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
5b46629f-5de1-586c-965d-518fcd7c7931 | note | VERIFICATION ACTIVITY: QA FORM
69b308e7-7d55-5ffb-9070-e2afb9ce781a | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
db67df97-6f7e-547f-a85c-c25e5bf56382 | note | FREQUENCY: Each Site
3dcb4a3b-d5ff-59f3-a365-838dc4f30704 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
fc7fbd43-7c10-5c10-8bea-9cd2e81935ba | note | HOLD POINT: Inprocess Inspection
3da26340-f4a7-55f8-82ec-c596bfe0c48e | note | RECORDS: Photos
42d28032-60a7-501d-9f24-46eaae7a6c02 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
3f188c96-4a47-52cd-b83d-4b98d25ac532 | note | VERIFICATION ACTIVITY: QA FORM
faf48686-4d5a-5d45-9a5c-ec05af8629f4 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
82e97a20-c69d-56c4-abd6-e1cc7f475fe9 | note | FREQUENCY: Each Site
7853691f-2c55-5c35-b3d1-616ad6170d72 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
168a77f6-20e6-5446-ae0e-fb5df20c5d79 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
a8a0faf6-4a38-5216-97de-198e9d8dbc90 | note | HOLD POINT: Inprocess Inspection
bce17100-6980-5774-ae4a-90fe8e258c69 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
2999edde-8329-5093-ad0d-d6a8d34271e8 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
e75f0b14-24b2-56c6-9011-76fd50c5f8ca | note | VERIFICATION ACTIVITY: Drawings
026ea312-86f0-5e31-8110-83a388aff236 | note | METHODS OR REFERENCE:
a4b7e16d-00e4-5c3a-98ce-ce95534da794 | note | FREQUENCY: Every Site
733a74d6-6479-552b-868c-c82138e81dc1 | note | ACCEPTANCE CRITERIA: As built drawings
6c34abfa-214a-5913-a23b-ecb115651382 | note | HOLD POINT: In Process Inspection
67251e32-f723-5a95-92a4-03b6e0e6e799 | note | RECORDS: Asbuilt records
c00f0d34-3c53-5daf-8880-1a8f1299e6c9 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
b09f4cd7-19ce-5377-a48f-2258161721c3 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
aab49d85-f563-57d4-b82b-d342ed9eac3e | note | METHODS OR REFERENCE:
7722a918-ce42-5162-a6f3-dd6e633a0d9a | note | FREQUENCY: Every Site
6eeefda4-9f71-59b4-b8f2-2a54a1f9e317 | note | ACCEPTANCE CRITERIA: RAMM SHEET
55097bbd-6d8c-55b0-ad68-806c0a4aab08 | note | HOLD POINT: In Process Inspection
ce2bf05c-d46c-5e53-b39c-15a9e546d89c | note | RECORDS: Asbuilt records
cf902edf-09ed-519a-8a4e-143cb748952b | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
f1555a79-7fe7-5d4d-b85c-dd2c70f9a651 | note | Prepared by: Ajithkumar Ayyanar
1536909a-99a7-58ef-97d2-609e3d8fefa5 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth South - ITP - Ducting | itp | ITP - Ducting | 686445e1-39d1-4fdf-8c80-bea280db15c2
| section | Ducting
| checkpoint | 1 - Permits
5aabf0c3-cca6-5522-94d3-b73be0137251 | note | ACTION (Hold, Monitor, Witness): H
0647d631-840d-5e5f-99fa-12b897837fc7 | note | DETAIL: Obtain Permits
2716b0ed-8823-58b6-a779-396152d684e2 | note | FREQUENCY: As required
22b1addd-baca-532c-8175-b393116b5cb3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
8730b573-e3a2-5aea-9f9c-19ab319ddc32 | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
6e18668d-ba74-5bce-8d94-a4b68d09ff64 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
26295997-5211-51ab-b7b3-67f84bf5a30c | note | ACTION (Hold, Monitor, Witness): H
b20f71f4-cdfe-5669-9da2-e0ae2aedbb87 | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
0808dc61-1742-537e-86bc-75de09f5a130 | note | FREQUENCY: Prior to commencement
5dca8ad6-3e39-54ed-8d8a-d1fb4af9e979 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9b9947b6-b2e1-5166-8b14-f3c080a2bc80 | note | CONFORMANCE CRITERIA:
2f071623-0d42-5806-b30e-bf030c517316 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
d03c4f1d-12bd-5ea9-b4af-9bfa4ab2a952 | note | ACTION (Hold, Monitor, Witness): H
c5427c09-373d-56ad-acf0-e4c3ff70e582 | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
33ffc2b9-3eed-50ca-a467-dbd9a3c991c7 | note | FREQUENCY: Prior to commencement
2e71b4e6-b94f-5dff-ad18-26bcd2da7c58 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
796d2938-5a65-5b38-a8b1-be3ccc646174 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
cdad5664-6102-567b-be4a-0b679d83770c | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
86ac315c-270b-5206-a319-3fff71813fad | note | ACTION (Hold, Monitor, Witness): H
25623ce3-3b9e-579f-825a-e3964cfdbfe4 | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
320d9dd4-55e6-5ae6-b221-79751d0f68e9 | note | FREQUENCY: Prior to commencement
c0fcecb6-df80-58c9-a2ec-233a8ed90a28 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
cc633d51-2b30-5244-8597-62dcd48bcf15 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
728fc16d-2e5f-5d30-8985-bae7184acb06 | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
7c457df1-c3ea-58a3-ac28-bfd6695e0da9 | note | ACTION (Hold, Monitor, Witness): W
cb2053d4-0d2c-5d21-b78e-8d896975236c | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
3bcf42f4-723a-5173-baa7-100ee08224c5 | note | FREQUENCY: Prior to Installation
618dc871-896f-5e33-945f-d114919e6d98 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
176a078d-0de3-5c4e-9578-54bebf13b0c9 | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
e38ff649-5247-5e07-bdd1-9379826582ed | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5.1 - Material Compliance
058adc2b-b3c1-5323-be43-36514a0b358c | note | ACTION (Hold, Monitor, Witness): H
bf44ebd9-a658-592d-980e-8256d5d33006 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
05f4b565-e4e5-50f0-aedb-ae3e14e81ea2 | note | FREQUENCY: Upon delivery to site
9d46bce3-cf13-5557-8315-53890bfee5d4 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
8455480d-882d-5bd9-a854-e8ba5a25600d | note | CONFORMANCE CRITERIA: 50mm Ducts
0160eab4-687e-5243-8dc2-7ac61f96af64 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
6758cc27-db28-58d4-b43a-0739f0240ccf | note | ACTION (Hold, Monitor, Witness): H
6136aa38-65d2-5305-9545-bb019cb7c104 | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway
c5ad7d70-f3b0-5d01-8486-9ba7334ac4e3 | note | FREQUENCY: 10m Intervals
9fee4cce-33d7-513a-bf4e-6e46fce8232b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
0ca57976-7dcc-5689-8ea7-9766814482ab | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
ccb596e7-5921-5ba2-8545-3fe9910e2537 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
8ba84b78-6dd9-5d25-94d3-47b64158e333 | note | ACTION (Hold, Monitor, Witness): H
f7f7180b-21a4-5830-808d-2a6d6f11a8f0 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
92cfa6b7-4640-5914-a5e1-3ef61fbd367d | note | FREQUENCY: 10m Intervals
16cda0ec-b2e3-568c-98b7-61bb44842446 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
6df28d6c-e051-5468-8c3f-c6db365b4bd0 | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
e594adf7-1412-5724-93ee-f7f4684e0450 | note | RECORDS: Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
44224d1d-ac27-5b09-8e16-0f3497776d8a | note | ACTION (Hold, Monitor, Witness): W
be600061-fade-56b9-842b-4467699e9ea8 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
6b9d40f3-78e6-5ac3-9236-634d672043a8 | note | FREQUENCY: Prior to Installation
1fcdfdd7-3d1f-5fbe-b9d3-c449bfaf4a21 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
c15cf689-fb90-5afb-94b0-0b264233a2a2 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
f712b3dc-b216-5ddc-b8b4-4570649941ae | note | RECORDS: Photos
| checkpoint | 7.2 -
4d28f053-beb2-5a78-9099-3b61cd612785 | note | ACTION (Hold, Monitor, Witness): H
6801448c-28c6-569e-a6f5-aa060677f4ce | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
fd0404e8-10de-5ac4-ae27-521f77fc9c57 | note | FREQUENCY: 10m Intervals
25c5ef22-92f7-5b85-bb2b-2d3ff36bec3b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
66b471d4-94d8-5810-bb0b-5e72f66dc48a | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
383fc081-fe42-5e40-8159-99d4ea64b5f0 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
410381ac-f14b-5ed5-9f37-b78ad886f93a | note | ACTION (Hold, Monitor, Witness): H
dd7dd7cf-cf4a-5fe0-b14d-98c998a1efdb | note | DETAIL: Asbuilt Survey
c3596b90-6990-53ce-bafa-cbe1f6aaab1d | note | FREQUENCY: 20m Intervals
22eb4d83-88fd-575d-9c2c-507dcd264f88 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
7008f6fc-4a20-5c89-a346-900ac5ebe472 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
0c6f5587-9ac9-5b0b-9ce0-94d45720be12 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
0c57e2b6-3461-5a3a-a812-ea0476b7405d | note | ACTION (Hold, Monitor, Witness): H
475310c2-08d8-5267-9838-f894f6565ce3 | note | DETAIL: Lay min. 100mm gap20 or finer for bedding and haunching
94068669-325d-5a6c-95f0-13c161eb19ee | note | FREQUENCY: 10m Intervals
7e56833e-752c-5cad-b659-4d5b9c29b85c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
d4139e50-3039-53ca-a0f6-04685c2cd2a8 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
4aa05c95-c915-5656-b11b-2942fa62da69 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
3917cdcb-659b-5f4c-a44a-97fa954ac23a | note | ACTION (Hold, Monitor, Witness): H
e93b872a-3b9b-50bd-b4ce-deb54fb02e30 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
98145071-a085-57c4-9505-e51327cef56c | note | FREQUENCY: 10m Intervals
b7d83f42-2750-5741-88b7-b4485ab57571 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
5c6601ab-8f3d-581d-a386-159e05ff4933 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
0949d168-4f67-5f4b-810e-ec0f5b1e07f0 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Reninstatment
4097a72d-3937-5dd6-b25c-71fcea60c59c | note | ACTION (Hold, Monitor, Witness): H
c0eef33c-10e6-557e-bc94-f7bd215caef1 | note | DETAIL: Ducts under berm reinstated with topsoil at the surface. Ducts running under any concrete structrues are carriageway need to be reinstated back to the same
d40a0af8-6861-55fd-91ef-8f5c970a4ff9 | note | FREQUENCY: Eash Site
2ee65bac-f407-5c34-acf6-d67e1cb60e44 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure/Docket
cce9bd30-022e-55ca-8b3c-7367a775f158 | note | CONFORMANCE CRITERIA: Reinstatement as per designer acceptance
3b0e7671-abdb-5f14-b05c-6eb492b073d3 | note | RECORDS:
| signoff | AUTHORITY HOLDPOINT
| section | ITP APPROVAL
| checkpoint | ITP Approval
79d183e0-f9f4-5a02-9bd3-a0ca99a7e74f | textbox | QA Compiled By:
f4215fc5-cc67-52bf-89ad-f45d2c32111d | textbox | QA checked By Project manager:
7d8c5e3f-4f90-548d-ae2a-943de722f453 | textbox | QA checked By Contract Manager:
5d5d29d4-298b-5d65-ba5f-326e2661871f | textbox | Accepted By Design/AT Engineer:
| checklist | Weymouth Construction - Weymouth South - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | 1d1c9176-2e73-4a98-9933-88fbf752575d
| section | Site Set Out
| checkpoint | 1 - Site Set out
0d4842d9-f011-54a3-b349-49975f6bdf9f | note | VERIFICATION ACTIVITY: Surveyor
748d30b9-3848-503b-b94e-b331b5e50dd2 | note | METHODS OR REFERENCE: Surveyor
23685882-e87b-5043-b82a-2b2407083033 | note | FREQUENCY: Everysite
ce069b12-1954-57b9-aebc-de80464fc138 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
00910858-59db-5d1b-b8b7-868764ad655f | note | HOLD POINT: Mandatory HOLD POINT -
930fd935-4d8c-5102-9f33-6ccee2ab61a2 | note | RECORDS: Onsite records/photos
8089c1bd-edc5-5641-b3d4-5715d0a5eaa2 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
07403f31-3697-59f5-95c9-0b8fcca9188e | note | VERIFICATION ACTIVITY: QA FORM
6904de3c-3d94-56c2-b62b-4a247e20aaca | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
9631aae8-a821-51ce-a6d5-ac98f7337e1d | note | FREQUENCY: Everysite
d31a36ef-c0fa-5728-8de8-b1d5fb549fa7 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (CBR>5).Concrete 20MPa @28 Days
4332df30-0f4e-5e27-a2dc-4def604d6ee4 | note | HOLD POINT: Inprocess Inspection
c971ef88-a93a-5326-8704-86c01bf6005e | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
8e054c6a-a855-5a27-be58-d9121acfafda | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
31da5293-3a93-5880-9aa9-0f14ee2028be | note | VERIFICATION ACTIVITY: QA FORM
74c7e08e-1078-5b5f-b16d-2daedaa6b957 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
d406a762-6e89-5b23-ad20-e14725eca4e4 | note | FREQUENCY: Everysite
cf81901f-ab31-5496-86b1-f5669b64d774 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
b12350fa-ece0-5fe1-98c4-b1eb6dd931a6 | note | HOLD POINT: Inprocess Inspection
279aaf67-959c-5e49-8c7b-65ace7d176f4 | note | RECORDS: FH concrete QA sheet
86f1cad0-aaa5-5bf3-9f92-ec1ec5bd007c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
987692b4-aff5-5397-9ae9-0a7ad65a688f | note | VERIFICATION ACTIVITY: QA FORM
6a4cb816-ccba-5ed4-9f8b-e4666ff389e9 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
1b93c64a-fe7f-56bc-8c92-15761e3fa6c4 | note | FREQUENCY: 10m Intervals
c9a30815-a782-576b-9ad7-666fe38ee83d | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
9b73456f-5c7b-527e-b3ce-b04c00f0eb47 | note | ○ Basecourse - 100mm min. thickness
85210446-e398-5234-87ad-12bb9688b150 | note | ○ Clegg CIV > 12
b30146c0-14c2-580f-8351-ca2c797c0dcc | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
d910e8a5-6d54-5f32-802e-a26bd3d216cf | note | HOLD POINT: Inprocess Inspection
47ac82e5-69e6-58c9-ae79-d17d9e847c65 | note | HOLD POINT: Prepour inspection
ec76aeb3-0d2c-53e8-af51-5b22b0aa48d6 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
11a65969-84d2-59d0-8590-e3874243479b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Shared Path Pavement
5c942633-5929-5c2a-9e98-27b8544625d9 | note | VERIFICATION ACTIVITY: QA FORM
59d99243-2aa5-5cfc-92cf-93aaa1cfda8a | note | METHODS OR REFERENCE: IFC
677ef081-5ea7-5859-83be-a69748885c09 | note | FREQUENCY: 10m Intervals
9e66d1af-a761-578d-b95b-291329317e43 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
b63b1f3a-c406-56f8-9ff1-b1a5aa4e5885 | note | ○ Basecourse - 100mm min. thickness
84e9239e-7885-58c4-82a5-f868156db9c2 | note | ○ Clegg CIV > 12
34aac1e3-59c5-5466-88e7-ba16768901a4 | note | ○ Surfacing - Concrete 150mm with single layer of 665 mesh(50mm cover) and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
119b20e5-376f-5a91-aa3e-a46c3550e834 | note | HOLD POINT: Inprocess Inspection
c845e232-27e5-5798-a454-20f4fdf4f839 | note | HOLD POINT: Prepour inspection
06aaa21b-70ac-5d3d-9d34-2112e9e9ad7d | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
848ce040-9175-5b0e-b19e-6e7d6262fea0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Construction Joints
4a3d9e50-d5d8-5caf-8717-6df818bc28dc | note | VERIFICATION ACTIVITY: Visual
f2a9a077-a2f1-5839-bcf0-cd17890fb797 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0002
31001c10-0027-587a-b299-30949bbd3762 | note | FREQUENCY: Everysite
85181def-7748-5237-83bb-2333d7456588 | note | ACCEPTANCE CRITERIA: All the sawcuts to be aligned to the Kerb joints. Dowel bar 6mm thickness to be used for the construction joints on the shared path
ba247323-72eb-5e4a-963c-2c6c6f5b663b | note | HOLD POINT: Inprocess Inspection
e2c90e41-ea68-55ad-95c7-8747b2956a04 | note | RECORDS: Photos
338dc1cd-01bb-5388-bf3b-05731c9a1ec7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Fall Gradients
d2ab389e-87ae-5618-bc14-d74a3e138e59 | note | VERIFICATION ACTIVITY: Visual
c84e3876-d5ca-5bb5-b24c-fef4d5337f72 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
6409bf64-fa7f-5a96-8bb9-4f4df0699c54 | note | FREQUENCY: Everysite
cbe4fedb-5346-5875-a225-25c076dc52ce | note | ACCEPTANCE CRITERIA: 2% preferred (Min 1% and Max 3%)
20c69df8-5667-5f61-811a-d73cb0c0a366 | note | HOLD POINT: Pre-pour inspection
d6463c72-0000-52b8-baf4-df4c86b72a1e | note | RECORDS: Photos
345b7c98-8352-5c25-a4b4-6a9795816cbf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 7 - Grass Berms
da926d37-ed1d-5bc4-aa81-7eef3ae872d3 | note | VERIFICATION ACTIVITY: Visual
17fd003e-5227-50a2-96f5-a4303fa71b1f | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
9badac76-5481-5c4c-b668-e0b3e4606e3c | note | FREQUENCY: 10m Intervals
f9a7ef60-fb74-52a5-a01a-1b2c60fd57ae | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
6b56fa0e-f0b8-51dd-a72e-c0b1fbd42eea | note | HOLD POINT: Inprocess Inspection
0751b942-b589-5269-a237-addd9e56c1ad | note | RECORDS: Photos
bb2b97c4-8e35-5481-bc76-4842b720dff3 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (1)
c2b673ef-4371-5fb2-bd27-7d0a07a2cb0b | note | VERIFICATION ACTIVITY: Visual
017262f9-5b02-5159-a57a-3adb16cd9c47 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
6ec1dc76-4bf6-568c-ac4e-3fbcd09ac6a5 | note | FREQUENCY: Each PX
edb25951-7a8a-5e69-aa5e-f32e57a5da04 | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer.
a493f0d9-afe1-5960-8362-aa010e360cb4 | note | ○ Warning TGSI tiles should have 100mm concrete haunching underneath
6f18d20c-40d5-549c-9f10-17e6069d2f28 | note | HOLD POINT: Inprocess Inspection, Measurement
6ffd6f50-f0b2-5769-b7b4-c9f05f79dcad | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
29036952-3b40-5380-9c47-fc6964743976 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (2)
59a354ed-c2bb-5bc1-a2f9-3863d1386ff7 | note | VERIFICATION ACTIVITY: Visual
488e31fd-36b9-5ebe-93be-aed58029c371 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
b9a99f05-030b-5ed6-a780-17457824e296 | note | FREQUENCY: Everysite
2afc965c-7508-5852-9946-ca2d4e9c023a | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
3c8d4fd4-ee2c-590d-a8cd-c95607cc0422 | note | HOLD POINT: Inprocess Inspection
251c7435-b521-5669-8a25-e6d999bf58a5 | note | RECORDS: Photos
f2762284-bac9-576e-a437-2359c0f8bd7d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (3)
c14ad57d-2b61-5965-9e8c-663a76e7326e | note | VERIFICATION ACTIVITY: Visual
e9e78e45-081e-5626-8ee5-1e43afa89e5a | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
5408a905-2214-5bed-9c45-7dace03491a4 | note | FREQUENCY: Everysite
37645a48-ef77-5e02-8d06-350582203895 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
ef86a2bf-c6d1-5613-a538-c9bfc9afaf2b | note | HOLD POINT: Inprocess Inspection
01dd7b86-706f-51e6-8b28-358025f3d5da | note | RECORDS: Photos
c42e3a2f-7a2b-5ee4-bf92-ea53e85621dc | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles (4)
3e52f43d-08d5-5784-a3ed-cb0dff83a064 | note | VERIFICATION ACTIVITY: Visual
688915a4-6280-550b-b689-229c0916d5ff | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
1597507f-e359-5062-a50b-3ed927fd4f9f | note | FREQUENCY: Everysite
d2f5a04d-894f-5930-be5c-b02e152e8ddc | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
6bc6f10a-3243-5c45-96f8-7083ace2a434 | note | HOLD POINT: Inprocess Inspection
03f64a7a-9fe5-55fb-95ab-6239b2829f81 | note | RECORDS: Materials Dockets
20185da8-07c2-5b62-bc44-36fcd1b5bbb6 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Pram Crossing
1332103b-d2cf-5b90-80fc-76e973eed319 | note | VERIFICATION ACTIVITY: QA FORM
fb4854c0-0f9c-5bea-aed3-b4ab218819ca | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
539be584-f1e1-51fc-bd75-3ee73e74684e | note | FREQUENCY: Each Crossing
478355bd-0eaa-5b2f-a722-e9418bd358ca | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
9c69eafb-e59d-53ca-af51-60360df9d772 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
ca23747c-ddad-562d-9fdb-31f1dc578ec8 | note | ○ Slope no greater than 1:12 where practicably possible
d507b680-8153-51d7-8cf7-117d092bb4ae | note | ○ Clegg CIV > 12
7b79050b-d5d4-5a39-bbc8-1d0c4c8ab131 | note | HOLD POINT: Inprocess Inspection
ace8b7e2-ab95-55d3-b305-4aafb6bd5fe6 | note | RECORDS: Photos
afe45e05-e7f9-5b97-a753-778165034a7f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 10 - Timber Retaining Wall
059e68e8-7c76-5486-806e-8a58fbe348ab | note | VERIFICATION ACTIVITY: Visual
af8e2100-6f74-5751-a956-dfc9b75bf6d9 | note | METHODS OR REFERENCE: TDM ST0004 - Version A, Timber Retaining Wall Detail
495e2cef-e2d5-5922-9ee9-2db378412d81 | note | FREQUENCY: Everysite
67dab360-b190-5fb3-a4b1-49c2fed771fe | note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
0dc5f0a8-0085-54de-982d-d102fcc00299 | note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
b05438cd-723c-5b9a-971f-05721b4b510e | note | ○ Retaining wall slope to be 10:1 grade.
07f3a4fe-0a92-51a1-a4d1-d973591871f2 | note | ○ Maximum height of wall = 1499mm.
ed32b94e-09f1-5200-a482-5610330be5f6 | note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
c37a4a68-c021-5a73-984b-b8f0a9fd1a25 | note | ○ Subsoil pipe to be lay as per TDM and connected to the nearest CP
e690eec2-dea6-50c1-8a29-5492166915fe | note | HOLD POINT: Inprocess Inspection
441c6f52-7157-50aa-9473-5d5caafb211a | note | RECORDS: Photos, Material Dockets, Dimension checks
d3563640-65fb-53f0-a636-b52e81b98462 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 10 - As built information
cb3c0cab-058e-57d2-b306-6d0cbdd0f320 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
f5386829-9e8d-5829-a06d-206ba9a85328 | note | METHODS OR REFERENCE:
80dd6c5e-f38c-594f-8465-e876c0d898b1 | note | FREQUENCY: Every Site
90c14987-8ce3-51a2-a437-a5d43379f7b4 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
a751012b-64be-5574-ae9a-fcee26965303 | note | HOLD POINT: In Process Inspection
d658f976-2ccd-584e-a72e-13755f6fa07d | note | RECORDS: Asbuilt records
7f53c330-b4bb-5e7c-8213-e97c742d5c56 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 11 - RAMM DATA
da124138-dee8-5b3d-b8c0-819d376c81ad | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
22004979-a0f5-5aae-a060-0c23c8557133 | note | METHODS OR REFERENCE:
c0e5e726-4b0d-5705-8faf-6d44a792166a | note | FREQUENCY: Every Site
94d523ac-9ae8-5283-80fc-d312b17d09e1 | note | ACCEPTANCE CRITERIA: RAMM SHEET
9ae0abbe-add7-5c69-8df0-950151a2623a | note | HOLD POINT: In Process Inspection
bfebc8cc-6742-5b12-927f-3e7531263a83 | note | RECORDS: RAMM Sheet
adb6962c-dfbe-5529-bd84-eb391983fbce | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
29fadf26-f928-5a34-9416-35d123801a4a | note | Prepared by: Ajithkumar Ayyanar
b61ae10b-5126-5ed8-9764-794f9910f7aa | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth South - ITP - Signage | itp | ITP - Signage | bf1c1504-f859-43ad-bba2-ffc07462371d
| section | Site Set Out
| checkpoint | 1 - Site Set out
04d96e71-19d1-5785-80e4-3f3a23a94f03 | note | VERIFICATION ACTIVITY: Surveyor
82b989d3-1845-5b9a-b92c-99099b6c67b2 | note | METHODS OR REFERENCE: Surveyor
1dfc32cf-13cb-5d9e-af14-1cb6c9d1a055 | note | FREQUENCY: Everysite
7eaad833-41c7-52ac-9a8c-d3c490519cc3 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
8912b0f6-a191-591b-8d8e-e489e662f6c9 | note | ○ Alternatively like for like
308afdf5-4d06-5499-b177-3d0bf2ed5daa | note | HOLD POINT: Mandatory HOLD POINT -
fcd7a17d-6bc1-565f-a37a-bf7900968d08 | note | RECORDS: Survey Receipt
623014a1-9b03-52bc-b611-f79bbf2b53e6 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
05175e83-56ca-5135-89b7-76fb65fd2f7b | note | VERIFICATION ACTIVITY: QA FORM
39092f94-14dd-5df4-bb01-7b0fea599e39 | note | METHODS OR REFERENCE: TDM Technical Standards
04183389-9321-5770-aaf4-12cfaa17050c | note | FREQUENCY: Every site
7af39b0b-dfa0-5328-8ce3-dfd621a97d85 | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
057ca105-fb14-56e7-964f-9c57cb84c3b6 | note | HOLD POINT: Inprocess Inspection
b4da26d9-5ed6-53bd-8d89-28488133a60a | note | RECORDS: Dockets/Photos
cf9daa99-b100-5bde-ab82-6d8457dcd380 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
c169f8f0-99b3-58b9-a771-d9db3e1a9d08 | note | VERIFICATION ACTIVITY: QA FORM
6a12091e-107c-5f09-86aa-da442710a5f1 | note | METHODS OR REFERENCE: TDM Technical Standards
7baede81-4bdd-5893-aacb-76460b73b939 | note | FREQUENCY: Every site
937d1881-6b39-5d37-8050-409af99879b6 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
27044d4b-7138-5f04-8288-4f9b986af073 | note | HOLD POINT: Inprocess Inspection
98e44e59-2651-5a69-9d48-1fe9a1a174b8 | note | RECORDS: Dockets/Photos
305b9a98-6e11-5973-b77a-2b12e3f176f9 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
ac77fd9e-7742-52b0-83ce-e2dce6c63648 | note | VERIFICATION ACTIVITY: QA FORM
fa8fa943-7439-5042-bbfa-ccc2af074dbd | note | METHODS OR REFERENCE: TDM Technical Standards
84da4a26-2daf-56ad-8a19-18f1043ce2c4 | note | FREQUENCY: Each Socket
1203ec35-8f97-527f-958f-e889707d2529 | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
ca5191e0-0e32-5408-b156-068f011697d1 | note | HOLD POINT: Inprocess Inspection
617f5932-ba58-5efe-9cd8-61b5670f300a | note | RECORDS: Dockets/Photos with tape measurement
5a8e5d9d-1ce3-5864-aa5c-81d9f2b68a52 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
0975dfde-a8e1-52c5-9bd2-13fc00852cc8 | note | VERIFICATION ACTIVITY: QA FORM
5ee648b8-d270-5753-a849-2a57efc08535 | note | METHODS OR REFERENCE: TDM Technical Standards
91fa60b9-7ab8-5659-81f9-652482fac6f4 | note | FREQUENCY: Each Post or pole
29bbafd3-b21f-5bc0-acac-bd1f989ca967 | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
12daad83-c69a-535e-b99c-5684697d3713 | note | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
6bcb213c-3a70-5d4b-a5a0-747e8d6b2a11 | note | HOLD POINT: Inprocess Inspection
f6293e92-9c4e-5c86-a03f-e0921f181316 | note | RECORDS: Dockets/Photos
794b1e76-8c1a-5c80-86f5-0ded649cafa2 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
aec55d4f-4ba5-529f-aa91-e6cd28dc807e | note | VERIFICATION ACTIVITY: QA FORM
0969fa17-1180-512e-8b02-bb624d5b199f | note | METHODS OR REFERENCE: TDM Technical Standards
f8f7ad4b-3f6b-5dae-8dda-f4ec6f255dce | note | FREQUENCY: Each Sign
29a10319-235b-5452-9be6-14b71521fb7c | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
fe13e9cc-e906-5dd3-ab01-c06d768d5277 | note | HOLD POINT: Inprocess Inspection
1362a4f3-80b7-5491-ba31-d5dd2854b18e | note | RECORDS: Dockets/Photos
adf6dd15-746a-5af2-a8f8-94c3d079b866 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
747dba81-6217-5331-9a65-fa7764609e2b | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
83dc5f45-241f-58b3-a1ce-796015303625 | note | METHODS OR REFERENCE:
b345d2c8-955f-5598-a11b-5b5295f0fa30 | note | FREQUENCY: Every Site
44b23300-0317-5cd4-9db2-b549817c8637 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
9a1db382-d430-5424-8cf4-9f5df6823046 | note | HOLD POINT: In Process Inspection
79dce571-7e3e-5293-965b-a367c258c0bd | note | RECORDS: Asbuilt records
e5824c87-82ec-5e9c-bf19-da1a3a7359ff | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
2662f4a9-ec32-55c9-a759-76660bb9cbc3 | note | Prepared by: Ajithkumar Ayyanar
edef619d-b297-51bc-a480-465dd7cdc793 | note | Approving Delegate: Sumesh Sharma
| checklist | Weymouth Construction - Weymouth South - ITP - Traffic Islands | itp | ITP - Traffic Islands | 98d89019-31d5-4012-a4d4-6d26600fbc1c
| section | Materials
| checkpoint | 1 - Mountable Kerb
f4310728-6289-5f61-b8fb-74a8212ea5c6 | note | VERIFICATION ACTIVITY: QA FORM
f84430ed-3a1e-5917-a049-2b6bef355ea1 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
0c9e4bf3-0058-5d1e-8922-f58891ce2e27 | note | FREQUENCY: Everysite
73f964a1-1b5f-5ad1-a9a4-52b8b96ffa4f | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
a353a48f-d697-542b-b338-95b6ad84fb3b | note | HOLD POINT: Inprocess Inspection
34184c54-db29-5921-b15b-9dd464bed4cd | note | RECORDS: FH concrete QA sheet, photos.
41a69fa8-964f-52d7-99c7-22a5f516d290 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
b1d857a3-3fb7-5852-b4a5-7cb0ab3ecebd | note | VERIFICATION ACTIVITY: Survey
fc5b6e9f-cd1b-5def-ad65-b58ebc981352 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
519279ad-31a7-5945-a593-a3b72a5a8b45 | note | FREQUENCY: Prior to commencement.
ac1ffda1-18a0-5880-a551-6ab24ba6830c | note | ACCEPTANCE CRITERIA: Survey
724e7953-9f4b-5d69-8be8-a3a9de78fd51 | note | HOLD POINT: As per Construction Drawings
b1e1fd92-758f-5393-a885-76eedff1e7d4 | note | RECORDS: Survey Receipt.
2ab0492d-8bd7-55cc-865a-264a332ecad8 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
64de5567-5ca7-5725-afdf-e66b4f6a1f88 | note | VERIFICATION ACTIVITY: QA FORM
d0fbb1e9-c3ec-5288-84eb-f433e659e3d9 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
acce7681-bed5-5066-b8d7-d0050dc54881 | note | FREQUENCY: Each Site
cee491c1-e3d6-5186-bd2d-1552539ae483 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
310d0283-41c1-5cd8-9f44-24ca6f90686d | note | HOLD POINT: Inprocess Inspection
a327090d-f500-559e-94af-1bc231826cf3 | note | RECORDS: Photos
0c3381a9-613b-5dd5-84ac-99f11729bd63 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
6f9e63a3-6759-59f9-8b99-4c86bdfde873 | note | VERIFICATION ACTIVITY: QA FORM
79988d9f-6561-5577-ba79-a352e9d0991c | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
bbaefa3f-64ec-542e-b94a-131b2e809eb7 | note | FREQUENCY: Each Site
439a7658-99c6-5373-b30f-f7bb972aef8b | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
2c0c9ac4-e5ec-568e-9e7b-a81620888910 | note | HOLD POINT: Inprocess Inspection
ac406a47-c4c6-55ce-bbb0-7c6d2a599dc6 | note | RECORDS: Photos
a773be43-1ae6-54f8-a222-063cd7cb4f03 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
28ed9cb7-04f2-5cc9-9e37-9d0bf6ef20e9 | note | VERIFICATION ACTIVITY: QA FORM
d5b96304-a992-571e-bbb9-245a28b23604 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
17be5442-7b4f-54b5-8ae2-47cea48cea8b | note | FREQUENCY: Each Site
4cff1460-5919-5c3e-95af-4a24b5b40b41 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide
d79a3918-80bc-5ab6-bca1-95939d24dcf5 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
dcf057dc-4909-511d-92d5-14d99935c63b | note | HOLD POINT: Inprocess Inspection
195f65b6-5406-5720-a170-60ab4bdc5f70 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
74f8dbe2-4bd3-5bb6-9295-a877935d2c37 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
aac2a09f-da04-5fb9-b3f0-b4cfdd1fbba7 | note | VERIFICATION ACTIVITY: Drawings
614a0b90-fc0c-5745-8029-3ed1214b7430 | note | METHODS OR REFERENCE:
a308d870-9c3e-5ac6-aac5-c9285752fb27 | note | FREQUENCY: Every Site
6352c9b6-4807-5599-a7bf-4ab15808b183 | note | ACCEPTANCE CRITERIA: As built drawings
ce2960de-aca8-54f3-ba61-40a1cb274804 | note | HOLD POINT: In Process Inspection
3f91a999-7872-5969-93be-190be25d7754 | note | RECORDS: Asbuilt records
38f55436-9b25-53ca-a5bb-dadc974c971d | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
d8b46ebb-85e8-5e86-b3c2-65983ae4cff9 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
6f51fe80-8c40-5341-ac77-9c8f4b9fbc2b | note | METHODS OR REFERENCE:
ad8907f3-71e9-5adf-b023-f1ecc97c524d | note | FREQUENCY: Every Site
90ff0c1a-3a61-526b-94b7-6c060d036cf3 | note | ACCEPTANCE CRITERIA: RAMM SHEET
f49c2aec-b38a-51d6-a623-ee776a6e26c6 | note | HOLD POINT: In Process Inspection
897511bb-9b4e-5e74-afef-f79bb81206af | note | RECORDS: Asbuilt records
fa93818f-d1b5-5006-9d84-ac531fbda0e1 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
586bf40a-2856-54f0-8ec9-7bf5ca126013 | note | Prepared by: Ajithkumar Ayyanar
0ad1fe3d-37b4-56dd-bf02-a88d9a0b5653 | note | Approving Delegate: Sumesh Sharma