## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Enabling Works - Footpath, Kerb and channel, Vehicle Crossing, Pram Crossing | itp |  |  |  |  | ITP - Opaheke/Chapel St - Enabling Works - Footpath, Kerb and channel, Vehicle Crossing, Pram Crossing
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Kerb & Channel
checkpoint | 2 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (Subgrade CBR>5). Concrete 20MPa @28 Days
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Channel Level
label | VERIFICATION ACTIVITY: Visual inspection
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
label | ○ All tie in levels are to be agreed with MSQA engineer on site.
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Visual inspection
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Footpath
checkpoint | 4 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
label | ○ Basecourse Gap40- 100mm min. thickness
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish.
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Fall Gradients
label | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Cross falll = 2% preferred (Min 1% and Max 3%)
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Photos of smart level
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Pram Crossing
checkpoint | 6 - Tactiles (1)
label | VERIFICATION ACTIVITY: QA Documentation / Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0010
label | FREQUENCY: Every PX
label | ACCEPTANCE CRITERIA: Tactile Pavers set out position to be agreed with MSQA
label | ○ Warning and Directional TGSI tiles should have 100mm concrete haunching underneath
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos, Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Tactiles (2)
label | VERIFICATION ACTIVITY: QA Documentation / Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every PX
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back minimum 300mm and maximum 1000mm from the face of the kerb
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Tactiles (3)
label | VERIFICATION ACTIVITY: QA Documentation / Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every PX
label | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete paver slab type B in footpath and pedestrian crossing.Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Materials Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 7 - Pram Crossing
label | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
label | METHODS OR REFERENCE: TDM Technical Standards - FP006
label | FREQUENCY: Each Crossing
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | ○ Tactiles Directional & warning - 60mm thick; 600mm flares;width as per design;
label | ○ Slope no greater than 1:12 where practicably possible
label | ○ Clegg CIV > 12
label | ○ 20MPA concrete
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Photos, Photos of smart level, Clegg Test Sheet, Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Vehicle Crossing
checkpoint | 8 - Vehicle Crossing
label | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
label | METHODS OR REFERENCE: TDM Technical Standards - VX0103
label | FREQUENCY: Each VX
label | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
label | ○ Base course - 100mm min. thickness GAP40
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide
label | ○ Broom Finish
label | ○ The grade of vehicle crossings must be maintained at 2-3% to match the crossfall for the footpath area over the crossing.
label | ○ Vehicle Crossing Ramp 900mm wide at max 15% with total 40mm lip (20mm chamfer, 20mm vertical) above channel invert.
label | ○ Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level.
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Photos, Photos of smart level, Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Refuge Island centre footpath
checkpoint | 9 - Refuge Island centre footpath
label | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: Each location
label | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
label | ○ Basecourse ATAP40 - 100mm min. thickness
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish.
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Photos, Scalar Test Sheet, Clegg Test Sheet, Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Fall Gradients
label | VERIFICATION ACTIVITY: QA Documentation / Pre-pour inspection
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Fall Gradients to follow shape of the final asphalt surfacing.
label | ○ The grade may need to be adjusted to ensure no ponding within the footpath area.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Visual inspection
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Grass Berm
checkpoint | 11 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 12 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 13 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: RAMM Sheet
label | ONSITE RESPONSIBILITY: Site Engineer & PM
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Ajithkumar Ayyanar
textbox | Approving Delegate:
checklist | ITP - Stormwater Drainage | itp |  |  |  |  | ITP - Opaheke/Chapel St - Stormwater Drainage
section | Stormwater Drainage
checkpoint | 1 - Permits & Services (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | FREQUENCY: Prior to any construction commencing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
label | ○ AT Access Authority approved and signed by RCA Authority
label | RECORDS: Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Locate and mark out all existing services
label | FREQUENCY: Prior to any construction commencing
label | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
label | RECORDS: B4u dig plans & GPR report attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (3)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Consents/Arborist report for trenching near Tree location
label | FREQUENCY: Working under tree drip line and working in the tree root zone
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Consent Review
label | CONFORMANCE CRITERIA: The Consents condition or Arborist instruction onsite to be followed
label | RECORDS: TOA, Consents and arborist instruction and Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Sub-Contract and Supplier Agreements
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Design is approved and Drawings are of the latest revision.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | ○ HOLD POINT if not issued to IFC.
label | RECORDS: Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
label | RECORDS: Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipe and Manhole Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
label | CONFORMANCE CRITERIA: Pipe shall be
label | ○ Check for freshly formed pipes and return if required
label | 1). Class 4 RCRRJ pipes AS/NZS 4058 or PVC SN16 Pipe(alternative material)
label | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | ○ Prefabricated concrete Manhole, Standard Catchpit and Street catchpit be in accordance with TDM Standards
label | RECORDS: Manufacturers Data Sheets, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
label | RECORDS: As-built Drawings. Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Excavation methodology
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
label | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
label | RECORDS: Prestart RCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (2)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Profile - Width
label | FREQUENCY: Daily / as trenching takes place. Different depth methodology
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
label | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | RECORDS: Construction Photos
checkpoint | 7 - Trenching & Excavation (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Trench Profile - Depth
label | FREQUENCY: Daily / as trenching takes place.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
label | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 7 - Trenching & Excavation (4)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Base
label | FREQUENCY: Every 10m
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
label | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
label | RECORDS: Test reports / Construction Photos
checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Placing and compaction of Bedding Material.
label | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 9 - Pipe Position Tolerance
label | ACTION (Hold, Monitor, Witness): M
label | FREQUENCY: At any point of pipe
label | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
label | RECORDS: FH Drainage Line Record, Survey Data.
checkpoint | 10 - Trench Backfill - Placing & Compacting
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Placing and compacting of Trench Backfill Material
label | FREQUENCY: Throughout Trench Backfilling operation.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick.
label | ○ Compacted backfill material to be free of Lumps > 150mm
label | ○ ATAP40 for subbase/basecourse.
label | RECORDS: Construction Photos
section | Subsoil Construction
checkpoint | 11 - Subsoil Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
label | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Subsoil Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Trenching (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Trenching (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Bedding, pipe installation and Backfill (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
label | RECORDS: Photo / subsoil log
checkpoint | 13 - Bedding, pipe installation and Backfill (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 13 - Bedding, pipe installation and Backfill (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure good coverage
label | RECORDS: Photos
checkpoint | 14 - Catchpit Connection (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photo
checkpoint | 14 - Catchpit Connection (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 15 - As-Built Drawings
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
label | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
label | CONFORMANCE CRITERIA: As Built and GIS Data
label | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
section | APPROVALS
checkpoint | ITP Approval
label | QA checked By Quality Manager: Denny Jeong
textbox | Accepted By Engineers Rep:
checklist | ITP - Pavement | itp |  |  |  |  | ITP - Opaheke/Chapel St - Pavement
section | Excavation/Milling - Widening Area, Structural AC on Concrete and Structural AC
checkpoint | 1 - Identification and location of shallow services
label | VERIFICATION ACTIVITY: Measure depth of cover to utility services
label | METHODS OR REFERENCE: Trained contractor staff
label | FREQUENCY: Two measures per service (each side of the road)
label | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage.
label | ○ Otherwise consider relocation or concrete cap
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Marked up sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling / Cut to Waste
label | Type O = 210mm
label | Type C = 305mm
label | Type W = 500mm
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm to design level
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Existing subgrade / subbase
label | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: Sitewide
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
section | Contingency Undercut Areas
checkpoint | 4 - Type O = Contingency weak / soft spot
label | VERIFICATION ACTIVITY: Benkelman Beam Test
label | METHODS OR REFERENCE: BB Test on exisitng Subbase
label | FREQUENCY: 10m interval alternative wheelpath
label | ACCEPTANCE CRITERIA: If BB Deflection >2.1mm and <3.5mm, Mill Further 70mm & replace with AC20 asphalt
label | ○ If BB Deflection > 3.5mm - Designer to review and advise
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): BB test results
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Type C & W = Contingency weak / soft spot
label | VERIFICATION ACTIVITY: Scalar Testing
label | METHODS OR REFERENCE: Scalar Testing on existing subgrade/subbase
label | FREQUENCY: 5m grid
label | ACCEPTANCE CRITERIA: Ensure exposed subgrade CBR ≥ 2.
label | ○ If CBR between 2 and 1 undercut 300mm and replace with woodhill sand wrapped in bidim A29 geotextile
label | ○ If CBR < 1 - designer to review and advise
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): BB test results
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - All Areas Contingency Weak / Soft Spot
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Existing subgrade / subbase
label | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
section | Subbase
checkpoint | 8 - AT AP65 = Pavement Type W
label | VERIFICATION ACTIVITY: No non-compliant results
label | METHODS OR REFERENCE: Material test results.
label | ○ The material requirements of AT AP65 are to be in accordance with Auckland Transport Series 0800
label | FREQUENCY: Once
label | ACCEPTANCE CRITERIA: Construction layer shall be Compliance with TNZ B/2
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - AT AP65 = Pavement Type W
label | VERIFICATION ACTIVITY: Compaction Testing
label | METHODS OR REFERENCE: Clegg Testing - where there are plant restrictions.
label | ○ NZTA B/2 testing requirements need to be satisfied where there are no such plant restrictions.
label | FREQUENCY: 5m grids
label | ACCEPTANCE CRITERIA: CIV > 35. to be compacted in 150mm layers for the Plant Restricted areas.
label | ○ For NZTA B/2, unbound granular subbase shall be undertaken in 150 to 200mm lifts.
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - AT AP65 = Pavement Type W
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - AT AP65 = Pavement Type W
label | VERIFICATION ACTIVITY: Surface finish
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: All area
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Concrete Subbase = Pavement Type W & C
label | VERIFICATION ACTIVITY: Strength and slump
label | METHODS OR REFERENCE: Concrete dockets & Lab Testing
label | FREQUENCY: each pour
label | ACCEPTANCE CRITERIA: Strength = 20MPa
label | ○ Slump = 130mm pump mix
label | ○ Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Concrete Dockets, Slump Testing Report, Cylinder Testing Report
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 13 - Concrete Subbase = Pavement Type W & C
label | VERIFICATION ACTIVITY: Levels / thickness
label | METHODS OR REFERENCE: Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour)
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ Target thickness = 150mm
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Stringline Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Concrete Subbase = Pavement Type W & C
label | VERIFICATION ACTIVITY: Rough trowel or Broom surface finish
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: All area
label | ACCEPTANCE CRITERIA: Rough surface verified over 100% of surface area
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Production Recurs
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
section | Sealing & Hatelit XP Grid
checkpoint | 15 - Type W & Type C
label | VERIFICATION ACTIVITY: Blinding/CAT60
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: ON CONCRETE SUBBASE
label | ○ Hand spray heavy tack coat emulsion (residual bitumen 1L/m2)
label | ○ Blinding sufficient to protect emsulsion from construction movement
label | ○ Manufacturer's guidelines for Hatelit XP installation and subsequent bitumen application on the concrete subbase in accordance with Hatelit XP installation guidelines.
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 16 - Type O = Contingency weak / soft spot
label | VERIFICATION ACTIVITY: Grade 4 Membrane
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: ON EXISTING PAVEMENT
label | ○ Hand spray Heavy tack coat emulsion (residual bitumen 1L/m2)
label | ○ Grade 4 chip
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 17 - Hatelit XP Grid
label | VERIFICATION ACTIVITY: Photos
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Type W &C = required over concrete subbase
label | ○ Extend 500mm into existing pavement (with <20mm asphalt blinding)
label | ○ Extend 1m into Type O
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 18 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Mix Design
label | METHODS OR REFERENCE: Sign-off by Designer
label | FREQUENCY: Prior to starting
label | ACCEPTANCE CRITERIA: Sign-off by Designer
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Mix Design Report
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Check weather reports
label | METHODS OR REFERENCE: Check weather reports
label | FREQUENCY: Daily
label | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): AC check sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 20 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
label | METHODS OR REFERENCE: Visual
label | FREQUENCY: Prior to starting
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): AC check sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 21 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Production tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Lab test
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 22 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Surface finish inspection
label | METHODS OR REFERENCE: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Inspection sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 23 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 10m each lane staggerd
label | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Inspection sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
checkpoint | 24 - AC14HF (Type O)
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: Thickness no less than 55mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 25 - AC20 (All three types)
label | VERIFICATION ACTIVITY: Survey As-built / Stringline
label | METHODS OR REFERENCE: Survey As-built / Stringline
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: Thickness no less than 100mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Survey As-built / Stringline sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 26 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: Cores air voids
label | FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
label | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
label | ○ Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot.
label | ○ 3 joint cores where possible/practicable
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): RFI response
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 27 - AC14HF & AC20
label | VERIFICATION ACTIVITY: Thickness
label | METHODS OR REFERENCE: Cores depth
label | FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
label | ACCEPTANCE CRITERIA: Target thickness 155mm (no less than 155mm thickness for AC14HF and AC20 combined)
label | ○ Target thickness 100mm (no less than 100mm thickness for AC20)
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): Core test report
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Asphalt Surfacing - 55mm AC14 (PG64V)
checkpoint | 28 - AC14
label | VERIFICATION ACTIVITY: Mix Design
label | METHODS OR REFERENCE: Sign-off by Designer
label | FREQUENCY: Prior to starting
label | ACCEPTANCE CRITERIA: Sign-off by Designer
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Mix Design Report
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 29 - Shape of road
label | VERIFICATION ACTIVITY: 3m straight edge
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: At joints and any other areas of concern
label | ACCEPTANCE CRITERIA: Irregularities < 5mm under straight edge
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Check sheet
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 30 - Temperature Limitations
label | VERIFICATION ACTIVITY: Temperature
label | METHODS OR REFERENCE: Contract Spec / M10 Spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Asphalt QA
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 31 - Surface Preparation
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Visual
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 32 - Asphalt Production Tests for AC14
label | VERIFICATION ACTIVITY: Production Tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Laboratory Testing
label | RECORDS (Responsibility): IANZ Lab
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 33 - AC14 - Layer thickness - 55mm compacted depth
label | VERIFICATION ACTIVITY: Insitu
label | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
label | FREQUENCY: Continuous
label | ACCEPTANCE CRITERIA: 55 mm minimum and 60 mm maximum compacted depth
label | ○ Final asphalt level to be 5mm proud of lip of channel
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): Asphalt QA
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 34 - AC14
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 10m each lane staggerd
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): RFI response
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Reinstatement
checkpoint | 35 - Reinstatement of Linemarking and RRPM's & Apply Joint sealing
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Visual inspection
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF:
section | As-builts
checkpoint | 36 - As-built information
label | VERIFICATION ACTIVITY: Documentation
label | METHODS OR REFERENCE: As-built drawings and ramm sheets completed
label | ACCEPTANCE CRITERIA: As-built records
label | TYPE: Inprocess Inspection
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
checkpoint | 37 - RAMM DATA
label | VERIFICATION ACTIVITY: Documentation
label | METHODS OR REFERENCE: RAMM Sheet
label | ACCEPTANCE CRITERIA: RAMM Sheet
label | TYPE: Inprocess Inspection
label | ONSITE RESPONSIBILITY: Site Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
section | APPROVALS
checkpoint | ITP Approval
label | Approved by Project Engineer: Ajithkumar Ayyanar
label | Approved by Contract Manager: Daeyoung Jeong
textbox | Approved by Client Rep:
checklist | ITP - Traffic Islands | itp |  |  |  |  | ITP - Opaheke/Chapel St - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001
label | FREQUENCY: Each Island
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid (Stick-on with epoxy mortar on structral AC20)
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct as per design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Infill
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 6 kg/m3 Red oxide.
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos, Concrete dockets
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 4 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 5 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Ajithkumar Ayyanar
textbox | Approving Delegate:
checklist | ITP - Roundabout and Apron | itp |  |  |  |  | ITP - Opaheke/Chapel St - Roundabout and Apron
section | Survey - Set Out
checkpoint | 1 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout for Roundabout and Apron as per the drawings issued for construction
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Survey Set-out on site
label | ONSITE RESPONSIBILITY: Site Engineer
section | Roundabout construction
checkpoint | 2.1 - Kerb
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: Type 2B Mountable Kerb as per TDM Technical Standards - KC0001
label | FREQUENCY: Circumfrence centre island
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base or Structural AC20. Laid 100mm high from finish level of apron. Concrete 20MPa @28 Days
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2.2 - Infill
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: As per Drawings
label | FREQUENCY: Roundabout infill
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish reinforced(1 row of 663 Mesh with 60mm cover) Concrete with 6 kg/m3 Red oxide.
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Apron Construction
checkpoint | 3.1 - Concrete Apron
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: As per Drawings
label | FREQUENCY: Apron Infill
label | ACCEPTANCE CRITERIA: 250mm thick reinforced with two layer of 663 Mesh with 50mm cover of 40MPa Concrete with 4kg/m3 Black oxide-Broom finish, on 100mm AP40 with 0.25mm polythene layer.
label | ○ Total reveal from road level = 50mm
label | ○ Chamfer - 25mm
label | ○ Upstand - 25mm
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | ○ Construction joint detail to be jointly agreed.
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Asbuilts
checkpoint | 4.1 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 4.2 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Ajithkumar Ayyanar
textbox | Approving Delegate:
checklist | ITP - Signage | itp |  |  |  |  | ITP - Opaheke/Chapel St - Signage
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Signs
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: All signs to be in good condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
label | ○ Any custom-made signs, approval of a proof design copy is required prior to manufacturing of the sign.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Pole, Impact recovery post and Ground Socket
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be in good conditon with end caps.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 4 - Ground Socket
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Socket
label | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos with tape measurement
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Pole and Impact recovery post
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Post or pole
label | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation.
label | ○ The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Signs
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: All the sign to be fixed to the pole or post with ARC brackets and tightened adequately.
label | ○ Ensure good visibility to road users & secured to prevent rotation around pole/post.
label | ○ Ensure sufficient offset from road & pedestrians/cyclists - as practicable as per existing environment/surroundings
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 7 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Ajithkumar Ayyanar
textbox | Approving Delegate: