## Master List Templates
Id | Type | Name | Values | Prompting Name
71311430-12af-4de5-b2e1-320343a3d7c5 | checklist | ITP-002 - Watermain Construction Stage 2 - Rev A | itp | ITP-002 - Watermain Construction Stage 2
20380797-825e-43d5-b636-1e28953acadd | section | Preliminary Works
107e3d9c-f945-48ad-a893-382139576ad3 | checkpoint | 3.1 Pre-construction Photos
955645e1-125c-52ac-a36d-9f7aaf64fd68 | note | Inspection Point: Quality Control Activity - Photos of worksite including vehicle access points.
de815be8-ff5b-5bbf-8fcf-b6a74f875d15 | note | ○ Photos of any existing defects/damage.
f629ba35-c6c9-5e84-afb6-f12afe19ba50 | note | Acceptance Criteria - Coverage of whole site
b343e756-6236-534e-a04c-adde741f9cf9 | note | Verifying Document - Photos saved
487d2c77-26c6-574d-9f8c-69197b900e60 | note | Reference: Contract Specs/Standards - D1.4
aa7dcc23-975c-5d3e-90f1-e46ecef13a8e | note | Inspection Point/Signature & Date - PM
441f8f47-9e59-4e93-af48-52ea9db74b4f | checkpoint | 3.2 Verify Construction Drawings
5979cb19-48d2-5a0f-8a4a-18a2495e019b | note | Inspection Point: Quality Control Activity - Verify Construction Drawings that are in the site folder are the latest revision.
77adfc3c-637c-5532-a2de-de99b4eb0801 | note | Acceptance Criteria - Latest drawings approved
2e7272cf-1b67-5992-8aea-1c720473b1e1 | note | Verifying Document - Drawings Register
91384230-7de8-55b8-b9f0-cf3094b4e632 | note | Reference: Contract Specs/Standards -
53f92b21-b0f6-50b0-9a66-65c339b74caa | note | Inspection Point/Signature & Date - PM
92a4d361-6a90-4261-aacc-b17a70c5ba02 | checkpoint | 3.3 Road Authority Notifications
a5905a4b-3c67-5ea9-9f5c-3f49ad93a559 | note | Inspection Point: Quality Control Activity - Corridor access Permit.
0158a33e-7ce3-58a8-babd-2c00a85ada9b | note | ○ Block by block Temporary Traffic Management Plans.
c980e384-1324-5a31-ad80-c5f42c7f2909 | note | Acceptance Criteria - Permit & Traffic Plan approved
670802ca-5daf-518d-ba40-b11f61b8bba8 | note | Verifying Document - Work Access Permit & TMP
ae04fd1d-8285-5e71-9dc0-6c451b22a24a | note | Reference: Contract Specs/Standards - C1.09, D1.4
afbe1801-0461-5ff9-9968-d71d709c4667 | note | Inspection Point/Signature & Date - PM
d39f31d1-9f41-49b3-8e2e-f1d32ae48a60 | checkpoint | 3.4 Management Plan
dacc70c9-2410-5db2-bd45-66d975547e52 | note | Inspection Point: Quality Control Activity - H&S Plan
c98cf114-7fba-5cd7-9f75-05f14d1dc0c4 | note | ○ Environmental Plan
ff8ca60d-7b07-570e-837e-2ea6f5924d22 | note | ○ Quality Assurances
6ad36c2d-187f-596a-87f1-b024ccfeeffd | note | Acceptance Criteria - Plans & Safety Measures in place
d5f70aa4-3aed-5da0-b07e-f5410907778d | note | Verifying Document - H&S Plan, Method Statement
79d6f9d4-a271-5202-907c-58e7835bcb83 | note | Reference: Contract Specs/Standards - D1.3
7f636cf1-81e6-5b8d-8b3a-e415c151f5d7 | note | Inspection Point/Signature & Date - PM, CR
5d595464-2779-423b-add8-0d8127f9cada | checkpoint | 3.5 Public Notification
3a84e0b1-0335-5dc4-bb53-a8236469f1e8 | note | Inspection Point: Quality Control Activity - Notice of works to properties in the construction zone in each block
111ac031-f06c-52e2-8d36-657040eef63d | note | ○ Notification to Rubbish collection contractor.
6425c7b3-a4a7-5fc9-b4d2-348fb03ae6aa | note | ○ Project Signage
1fb132d3-92db-5038-aa91-124209dd7f89 | note | Acceptance Criteria - 48 hours prior notification
6a28c857-a4f5-59ec-8a55-c083caf0c3a7 | note | Verifying Document - Letter to residents
c926fb82-add6-5d96-9893-e1996f955a14 | note | Reference: Contract Specs/Standards - D1.10
bdbcb526-3a1e-5e5d-86ef-0a808ab8369e | note | Inspection Point/Signature & Date - PM
83d17dff-2396-439e-955c-8f1f727f65ed | checkpoint | 3.6 Shutdown/Isolation
6ea865c2-ca78-5854-8fa3-2264bf699993 | note | Inspection Point: Quality Control Activity - Shutdown/Isolation process verified in each block closure
1555c1d5-29de-5a42-a7d4-8b3739287984 | note | Acceptance Criteria - Shutdown process verified
cd7f89f3-8fdf-5085-8c83-7bb9094c8b0a | note | Verifying Document - Notification letters
ef26b893-83e8-5557-854d-c80eb7263938 | note | Reference: Contract Specs/Standards - C1.16, D2.7.8
28d7be85-39af-58e3-9302-9376a974da67 | note | Inspection Point/Signature & Date - PS
d167c212-b415-420c-a15c-45c677294de6 | checkpoint | 3.7 Construction Set Out
742868c8-23f0-5452-9b92-ba186649d8d7 | note | Inspection Point: Quality Control Activity - Correctly mark out the position of the new pipelines for construction.
9e97b2cc-ba1a-5815-b8f9-fbfc1eb1d305 | note | Acceptance Criteria - Construction Plans checked
5b2e22e1-e5ff-5dc0-99bf-61f23b16df05 | note | Verifying Document - Construction Plans
62386f7d-45bf-5fb2-8ee5-5645b5fb6848 | note | Reference: Contract Specs/Standards - D2.7.1
d58502cb-242d-55dc-b860-3551207f6eba | note | Inspection Point/Signature & Date - PS, CR
a5600e25-383f-46d4-8512-0c264c1e449f | checkpoint | 3.8 Pre-Excavation Permits
dae1eccc-c23e-53c5-a82d-0efd94bccfeb | note | Inspection Point: Quality Control Activity - Permit to excavate for the location has been endorsed by an authorised person.
4086823b-a3b0-5514-bed4-f7f9e3b60915 | note | ○ Existing service plans & locates
c1e5fd2a-aef6-51bf-8cd0-bb993a96c4c9 | note | ○ Close approach permits
e9ebe2eb-6bb3-5920-af4f-3e5f51dc6ced | note | ○ Notifiable works
c0184131-3963-58e5-89ee-4c85ee5a746b | note | Acceptance Criteria - Permit to excavate endorsed
ef5bff12-f195-5b6f-aa81-cb8850c90580 | note | Verifying Document - Ground Disturbance Permit
64acb508-1d91-553b-8bd2-2bec3032ca97 | note | Reference: Contract Specs/Standards - D1.7
7835cccc-5334-5c60-a2d5-886aa9e0b519 | note | Inspection Point/Signature & Date - PS
abbb431d-e004-44ec-b738-fab1868140b8 | section | Incoming Goods Inspections
2aa07f2e-4aed-4158-88a0-e6abf1872ee1 | checkpoint | 4.1 Pipe & Fitting Inspections
335e2b85-3765-5d7c-823f-1a30f4f4c2cd | note | Inspection Point: Quality Control Activity - Visual check of materials delivered:
3c2f6b16-25d4-518b-a78c-50cd0381e2b9 | note | ○ Correct Material & dimensions
38ce9bbf-d35b-56d0-9094-6888dbbe0772 | note | ○ Condition & Quantity
e0aca729-1137-5fa6-a9c4-e65d8d4be14e | note | ○ Free of defects – surface abrasion, ovality, not kinked or crushed
c7813b84-576f-505d-b003-53fb30070daf | note | ○ Batch/serial numbers present
e60eb730-8b8d-5bbe-9001-2c575dd38607 | note | Acceptance Criteria - Correct material & no defects
775a2f60-1a0d-5a61-a840-33859f5f5380 | note | Verifying Document - Packing Slips
5523d66d-7eb8-57b7-8130-17f63b83eb86 | note | Reference: Contract Specs/Standards - D2.4,D3.3, D4.3, D5.3, D8.3
4815886f-d85b-584d-a8bf-54bb43596b4d | note | Inspection Point/Signature & Date - PS
18a89c7a-07fc-4278-9ab2-46bbdeed02f3 | checkpoint | 4.2 Pipe & Fitting Storage
736fc6ca-0587-58a7-aa66-1e6006900b05 | note | Inspection Point: Quality Control Activity - Stored as per manufacturers specifications including maximum height limits and safely chocked in place.
88679b02-09b0-5f6d-85d2-86abe8c910f1 | note | ○ All pipes are end capped.
ace5e548-9b68-55f8-acb6-13682245a6d3 | note | ○ No scoring of pipe more than 10% of thickness.
0f1df64d-4495-5578-a941-f201cb9bd702 | note | ○ No damage to epoxy coating on Ductile fittings.
1dbf0fff-4157-5283-af1b-f1fa245cb0fd | note | Acceptance Criteria - Stored as per manufacturer
c2c2afc7-5301-5e5c-ba67-ba552d116bc1 | note | Verifying Document - Manufacturer’s Storage Instructions
99bbba7a-beec-5223-939d-15034191d36d | note | Reference: Contract Specs/Standards -
1dbd7e86-bf3c-5e32-8b08-073e38069992 | note | Inspection Point/Signature & Date - PS, CR
1f6a3545-531a-431b-8950-db0056c6a96e | section | Construction Inspections
5b9fc0f7-1004-4407-be8c-24b464b7f09e | checkpoint | 5.1 Trench Excavation
02e391fc-3a18-522d-9c19-e2a03e270cfb | note | Inspection Point: Quality Control Activity - Trench width to be sufficient to safely lay the pipe (including shoring if required) and compact the side support of the new pipe. Bedding details below;
a6f490ee-48df-5ce7-ad7c-e1ea3aa3e379 | note | ○ Sufficient room to enable the pipe, joint, bed, haunch or surround shown in the drawings to be accommodated.
eec54b15-5ecd-5436-96af-7f3f1ec2feb7 | note | ○ Trench depth to enable pipe to be laid with the designed cover as shown on construction plans.
8fd021a9-e8d2-5b4c-8b4b-5843892fc6d1 | note | ○ If trench bottom to be suitable to compact pipe bedding as support pipe.
fc3f41ae-94b6-572c-ac89-2a9ef6fb22bf | note | Acceptance Criteria - Trench dimensions correct
e3b19d68-be79-52b1-b552-b4069f08f057 | note | Verifying Document - Daily Site Diary
84a404dc-63b4-5583-b4db-f3add2e91694 | note | Reference: Contract Specs/Standards - D2.6, D2.7
5aa888e2-14d6-582f-9a52-d9c849c2397e | note | Inspection Point/Signature & Date - PS
27edf7a6-5c6f-40e4-b0c0-9ab61a806878 | checkpoint | 5.2 Encountered Services
da1255de-facf-5b78-9de0-40b88d5693d6 | note | Inspection Point: Quality Control Activity - Block by block ensure existing live services are not unnecessarily damaged by works.
5fc0b366-4852-5bfe-a581-cba57122ba03 | note | ○ Repair any services that are temporarily removed during construction.
c6c5167f-c5f2-5998-b8d3-01f5f3e9341c | note | ○ Record any services found.
0631e0d3-22a9-5d7c-8b37-c6cbd46c7c91 | note | Acceptance Criteria - Existing services not damaged
81f412b2-a38d-50f2-a598-84775c34f384 | note | Verifying Document - Encountered Services Record
90c9acea-6aa9-5d0a-b22b-e74a722eebd8 | note | Reference: Contract Specs/Standards - D1.7, D2.7.7
7d0df532-6775-5e02-87ef-5933b5113c19 | note | Inspection Point/Signature & Date - PS
0bb6eb81-7e4a-451f-830e-1b4ed2ca3ea2 | checkpoint | 5.3 Pipe Installation
e9a5264d-e34d-57c2-b251-70577ea28002 | note | Inspection Point: Quality Control Activity - Interior of each pipe visually inspected to ensure free of debris.
4de7eba6-7a52-508a-8f6f-3da7ba17c6ad | note | ○ Re-cap end of pipe after installation.
9fcd0740-534d-500d-8189-e0970be0fe0f | note | ○ Check pipe installed at correct depth.
97372ff6-7a61-5b54-b317-dc368cef403b | note | ○ Ensure all collars are free from contamination in McDougall St berm
d141a6e9-ce08-571e-8cfd-8a4080f2f31b | note | Acceptance Criteria - Pipes free of debris & correctly installed
6c48859f-43ee-519f-b185-e2757b35f5ef | note | Verifying Document - Daily Site Diary
d6e34e20-3287-5bb8-accf-914843f1e5ed | note | Reference: Contract Specs/Standards - D2.5, D2.7, D8.4.2
c344ad27-9a7c-5088-8578-ce9de1f06115 | note | Inspection Point/Signature & Date - PS
315ca360-db4e-4b0f-b047-bcd13a88803d | checkpoint | 5.4 Concrete Pre-Pour Inspection
a0c3ca9d-7c53-5f00-a910-1efc9d53070f | note | Inspection Point: Quality Control Activity - Check dimensions of formwork match details in the Construction Drawings.
63a3685f-631f-50f2-b45b-5b550dd42985 | note | ○ Check pipe fitting joints are clear of concrete pour.
23788df5-5f26-5f32-a93c-2b6f87bf050f | note | ○ Thrust blocks to be poured against good solid natural ground.
2e389bbc-ca69-56cc-991e-0c7ae5298cfb | note | Acceptance Criteria - Thrust blocks against solid ground
4630ea02-6452-5ef8-9df0-b7baf484a9ae | note | Verifying Document - Daily Site Diary & Photos
2a52135d-b44a-5d64-8c2f-594fcb8d9444 | note | Reference: Contract Specs/Standards - D5.1, D5.3.2, D5.7
270f8374-94d2-5ff4-afe3-a9f4d98bb457 | note | Inspection Point/Signature & Date - PS, CR
02e5fe15-a3d0-4117-9c59-df286de87b71 | checkpoint | 5.5 Hydrant Depth
c166f8ac-68a4-56d5-a714-45a77c232876 | note | Inspection Point: Quality Control Activity - Confirm depth requirements have been met;
2f2ace55-1dbf-557c-880b-7b6a3dd25264 | note | ○ Hydrant outlet: 200mm min. to 400mm max.
285e10aa-95d7-51d9-ab64-3b2072cdb2d5 | note | Acceptance Criteria - Hydrant depth verified
9803aeb2-9d90-54ba-9e49-df36b5629658 | note | Verifying Document - Daily Site Diary
f8c94654-15c9-51e9-8452-342e59ecae6e | note | Reference: Contract Specs/Standards - D5.5
cc256614-c42e-5f6e-a39f-f68a89b87155 | note | Inspection Point/Signature & Date - PS
a0e3fce6-d131-4d47-b2fa-1afd64dedf22 | checkpoint | 5.6 Compaction Testing
ba0f25db-c515-54bf-af10-241ef05a2184 | note | Inspection Point: Quality Control Activity - Confirm trenches in paved areas are compacted to standard block by block.
49e7f8fd-7c6b-5d23-b61b-854926d2d227 | note | Acceptance Criteria - Compaction confirmed
22f4308c-0c3d-5079-b554-738af731d09f | note | Verifying Document - Clegg Record Sheet
ea3ff20d-d289-5332-88c3-7d7ac37a937a | note | Reference: Contract Specs/Standards - D2.7.10
bb591b35-fe0b-530a-8cb7-36e77516390e | note | Inspection Point/Signature & Date - PS
cdecfdb6-ad87-453e-b692-8fb65eb5cbe7 | checkpoint | 5.7 Watermain Pressure Testing
1da5f833-284a-5b18-99a9-331354fad608 | note | Inspection Point: Quality Control Activity - Hydrostatic pressure test on new pipeline and fittings block by block.
2f9a2668-68c2-5f33-8c5e-ec33a157d16e | note | Acceptance Criteria - Pressure test passed
36849462-809a-58b1-a71f-40568e648c95 | note | Verifying Document - Pressure Test Record Sheet
a57df2e3-9168-58b3-8e23-04a24658c806 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
2d130f10-37f0-55a1-8d72-a460b1f28c32 | note | Inspection Point/Signature & Date - PS, CR
a1e1175c-838a-44d4-97e2-105d86a88295 | checkpoint | 5.8 Watermain Sterilization
ce10429c-a3e0-5c3c-b478-43bc65ee371b | note | Inspection Point: Quality Control Activity - Flushing and sterilizing full length of new pipeline and fittings block by block.
14828d25-390c-5376-8cc6-48d3ee750694 | note | Acceptance Criteria - Sterilization completed
72845af4-3a77-57b0-bfd3-8c8b00ad194a | note | Verifying Document - Sterilization Record Sheet
c67f69b9-5827-576d-aa4b-e05ef53cf735 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
99631707-3d31-5b31-aff4-efb8e8c21979 | note | Inspection Point/Signature & Date - PS, CR
ddf7462a-b76e-41eb-a36d-0de8b8dd2a87 | checkpoint | 5.9 As-built Information
517e67db-4033-58c1-a6ca-d3362f98ca30 | note | Inspection Point: Quality Control Activity - Capture data for all new construction work.
ba450391-5c8a-5c55-b1c4-c22f0833b96c | note | Acceptance Criteria - Redline mark-up plan submitted
3eb797e2-7275-5590-8fac-676aa04c793f | note | Verifying Document - Redline Mark-up Plan
b2cc15a1-1e88-5f06-9c50-d2d2827d97a5 | note | Reference: Contract Specs/Standards - C1.22
3c06f156-3b4e-51b2-91ab-48d5a7624304 | note | Inspection Point/Signature & Date - PM
8b2fb51e-3dea-4864-85cf-ea6c1f2099ae | section | Final Inspection and Handover
e1185f06-97ee-41c3-ba68-9fa87ec8f197 | checkpoint | 6.1 Final Inspection of Works
937e6486-743d-5157-8e7e-d97207a69798 | note | Inspection Point: Quality Control Activity - Work is inspected by the authorised person and complies with the nominated specification/standards
17149ea4-e39d-5a08-9b34-a5a55b8544b8 | note | Acceptance Criteria - Work inspected & complies with standards
69020570-efe6-5843-a2ad-9a102698555a | note | Verifying Document - Practical Completion Certificate
b28f2ad8-0f63-5340-9f55-310a0e29c35a | note | Reference: Contract Specs/Standards -
5422ff6f-c5f8-5de4-8a22-f168bf4f557c | note | Inspection Point/Signature & Date - PM

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b06f12f9-df3d-4721-95e1-713877156dcd | checklist | TEST | itp | TEST
553802ab-4c97-4862-8d9c-2a7dcbabb1c1 | section | Preliminary Works
fbe5868a-689f-4a72-99ab-e38f386d7e81 | checkpoint | 3.1 Pre-construction Photos
88ff4964-334c-55dd-97ba-f465fd23f6a9 | note | Inspection Point: Quality Control Activity - Photos of worksite including vehicle access points.
3d26e6d5-37b6-5e3b-9287-367c8796ce5a | note | ○ Photos of any existing defects/damage.
df89ba38-62c4-5b05-815c-d4cf7fb29046 | note | Acceptance Criteria - Coverage of whole site
1c72c8a7-ed92-5df3-8d05-23b185e94cb7 | note | Verifying Document - Photos saved
bdebb0f5-3cd4-5825-b08d-b835066a0e0d | note | Reference: Contract Specs/Standards - D1.4
71408a1f-6731-546f-8450-6da9a6c6693e | note | Inspection Point/Signature & Date - PM
809cf54a-ae3a-4aa6-ab21-9a4f4173267a | signoff | ICC Signoff Required
7079e51a-08bc-4f6e-bf99-d51988786d58 | checkpoint | 3.2 Verify Construction Drawings
36ad6b3c-7485-5648-941e-9e79aa58123c | note | Inspection Point: Quality Control Activity - Verify Construction Drawings that are in the site folder are the latest revision.
9dbc405d-1902-500c-9e5d-735a1fa5e1cc | note | Acceptance Criteria - Latest drawings approved
84e66652-4f98-5fa1-b329-3e1e286aeb2e | note | Verifying Document - Drawings Register
c20fa82e-4237-5ebb-8abf-d49aff1f27f1 | note | Reference: Contract Specs/Standards -
9a03ac5a-9d76-5297-9b58-32e67d3ca007 | note | Inspection Point/Signature & Date - PM
b13521f5-c20c-4bc0-b45a-afa3f3e7acf2 | checkpoint | 3.3 Road Authority Notifications
d9134f68-be68-5e97-9d01-71f2ac5f478f | note | Inspection Point: Quality Control Activity - Corridor access Permit.
1e3e8227-08ba-5286-a0fa-e002380e9cc5 | note | ○ Block by block Temporary Traffic Management Plans.
c9687b51-53b2-5b9d-b224-7dc261949664 | note | Acceptance Criteria - Permit & Traffic Plan approved
f1160503-0611-5a3a-9298-64850bffedf9 | note | Verifying Document - Work Access Permit & TMP
6554479b-71a1-5afa-bb5d-09a4b7a1a5b3 | note | Reference: Contract Specs/Standards - C1.09, D1.4
4d9a60e9-387f-5fa2-9465-5507a93f40e7 | note | Inspection Point/Signature & Date - PM
042b6728-a6be-49a0-80bf-488769d57aaa | checkpoint | 3.4 Management Plan
fdb25380-79a5-5d8d-bca0-4d91717ff2f1 | note | Inspection Point: Quality Control Activity - H&S Plan
b586a639-ff07-50e5-bb85-40c67124ce8c | note | ○ Environmental Plan
e10d0069-abb9-5f19-add0-2351fe53cc28 | note | ○ Quality Assurances
9b74471d-86a1-5665-8455-aa2cf67f4de0 | note | Acceptance Criteria - Plans & Safety Measures in place
d14292ba-7a19-5cd0-9401-ec6c849cdad6 | note | Verifying Document - H&S Plan, Method Statement
e60d57c3-59ab-5458-a9ff-beb4f176d9c7 | note | Reference: Contract Specs/Standards - D1.3
70cae9e4-2d52-5402-ac00-ab4feaacebda | note | Inspection Point/Signature & Date - PM, CR
9834b300-0313-42ad-8bd8-9b35c1669cce | checkpoint | 3.5 Public Notification
794a0915-aee6-51ab-a475-8b0d67faf7c4 | note | Inspection Point: Quality Control Activity - Notice of works to properties in the construction zone in each block
50b22445-0c34-56cd-aff3-a53528832a98 | note | ○ Notification to Rubbish collection contractor.
73e0014c-746e-5869-a235-5044289a79d0 | note | ○ Project Signage
d4626174-dafd-51ec-9547-91d8e9f16a10 | note | Acceptance Criteria - 48 hours prior notification
d65c30c4-9c91-5f27-a604-748906723ef2 | note | Verifying Document - Letter to residents
72d27d32-17c9-5bb6-bb97-1fb6102de1e7 | note | Reference: Contract Specs/Standards - D1.10
23974a90-a4f0-5cc1-8a51-982f5baeb639 | note | Inspection Point/Signature & Date - PM
b3769d48-43fe-48b0-9950-4f0a2347d587 | checkpoint | 3.6 Shutdown/Isolation
46b0538e-7882-5b4a-aec1-6fd0dc5a4def | note | Inspection Point: Quality Control Activity - Shutdown/Isolation process verified in each block closure
2596bae8-39e5-51af-9695-5c9ef384b9b7 | note | Acceptance Criteria - Shutdown process verified
a016aeb9-6a51-5ac0-b43c-9b357c3e3c49 | note | Verifying Document - Notification letters
678c1634-70fe-57b3-80ac-05000e2f3c53 | note | Reference: Contract Specs/Standards - C1.16, D2.7.8
297c1a50-dac6-5d41-8a32-b1418b36ced0 | note | Inspection Point/Signature & Date - PS
47acac1a-b67d-4d50-9f9c-839449412fe7 | checkpoint | 3.7 Construction Set Out
8d25711c-343a-5311-95e0-82edfe522ddd | note | Inspection Point: Quality Control Activity - Correctly mark out the position of the new pipelines for construction.
e4e063e0-5172-5f53-99c7-7333c65705bb | note | Acceptance Criteria - Construction Plans checked
6024d9de-ab63-5083-aca2-e48a3a76d587 | note | Verifying Document - Construction Plans
14434d14-00ed-56b1-825e-493600220727 | note | Reference: Contract Specs/Standards - D2.7.1
6b19ca4c-130a-5c3b-b7f2-d20d670e78b6 | note | Inspection Point/Signature & Date - PS, CR
53e9a3ca-f6c6-43b1-9a12-b8263be11317 | checkpoint | 3.8 Pre-Excavation Permits
fca57436-1cd1-57e5-a16f-57227d13bdfb | note | Inspection Point: Quality Control Activity - Permit to excavate for the location has been endorsed by an authorised person.
bf9785de-2d2a-5846-a7b2-77a30c45db3a | note | ○ Existing service plans & locates
dc169852-6d2e-5737-b49d-b04399d4b83c | note | ○ Close approach permits
4b97e2fd-9d6a-5c16-bdd7-3088e9f0c548 | note | ○ Notifiable works
b0ce18f2-2eab-589e-ac3b-c46e03636ba9 | note | Acceptance Criteria - Permit to excavate endorsed
08a6055d-c9b9-5f38-8e94-73d96170c967 | note | Verifying Document - Ground Disturbance Permit
ae9387a9-acd5-5481-8cc2-6ffc07067eec | note | Reference: Contract Specs/Standards - D1.7
7abe4a36-e673-5822-9f99-8f72f552385f | note | Inspection Point/Signature & Date - PS
a253600c-ef0f-43e3-8660-cdddbbef8456 | section | Incoming Goods Inspections
a8a6af5e-c758-4dc8-b6f9-ae44e4840b1e | checkpoint | 4.1 Pipe & Fitting Inspections
fec85241-6be5-5b11-8217-78347b1e2907 | note | Inspection Point: Quality Control Activity - Visual check of materials delivered:
faed8055-cf83-5a70-8d37-96a8ffda0edb | note | ○ Correct Material & dimensions
18a0bb79-a99b-501e-80c9-ec9a3c8141b9 | note | ○ Condition & Quantity
a5e38ae8-4070-586b-b1f3-dedf99d1db25 | note | ○ Free of defects – surface abrasion, ovality, not kinked or crushed
283e2421-5c3e-5887-ab2e-f37977c4e915 | note | ○ Batch/serial numbers present
055e4553-5961-5a63-85d7-cbedf5762766 | note | Acceptance Criteria - Correct material & no defects
c3c7d23b-c08b-560e-aebc-08a908f67c2f | note | Verifying Document - Packing Slips
6aa038e5-4542-5050-92cf-a7d796ed1b25 | note | Reference: Contract Specs/Standards - D2.4,D3.3, D4.3, D5.3, D8.3
41712592-c1a9-56e5-84d4-e12c7450e55c | note | Inspection Point/Signature & Date - PS
a404bbcc-5be7-4472-97e9-a9243228d3ef | checkpoint | 4.2 Pipe & Fitting Storage
6ca24bb9-1793-5dbc-9287-4250c6422cb7 | note | Inspection Point: Quality Control Activity - Stored as per manufacturers specifications including maximum height limits and safely chocked in place.
35cef3c6-fc15-5eb1-bed9-d795c46a4e49 | note | ○ All pipes are end capped.
170b1977-a70c-5a3c-a3e5-342f4ccea8ff | note | ○ No scoring of pipe more than 10% of thickness.
30d30c50-eb98-5066-aa1c-a5bbdd8d5c72 | note | ○ No damage to epoxy coating on Ductile fittings.
3a67f244-f92d-5798-8e3d-f152cbeb899f | note | Acceptance Criteria - Stored as per manufacturer
ace33fd2-a393-5bfa-b6c5-8e61d3b1c35f | note | Verifying Document - Manufacturer’s Storage Instructions
f4290dd0-9b4d-56e9-aa4f-481e5fa71804 | note | Reference: Contract Specs/Standards -
df57d03e-6c02-5d40-ab7b-3c56f6f56f0b | note | Inspection Point/Signature & Date - PS, CR
b644d256-b2f7-4909-be81-e11636af6d4c | section | Construction Inspections
743e2563-35a1-49a4-8c29-f075890688a0 | checkpoint | 5.1 Trench Excavation
d9a14a93-9ca7-5ab8-9ee9-ef69d4fffc75 | note | Inspection Point: Quality Control Activity - Trench width to be sufficient to safely lay the pipe (including shoring if required) and compact the side support of the new pipe. Bedding details below;
e8a3d893-faf1-51ff-b384-23e63588935a | note | ○ Sufficient room to enable the pipe, joint, bed, haunch or surround shown in the drawings to be accommodated.
7199ecda-851a-515e-ae0e-4ac33b7dac08 | note | ○ Trench depth to enable pipe to be laid with the designed cover as shown on construction plans.
4daeb7d4-18a9-5ad7-8e4b-eb41968ce075 | note | ○ If trench bottom to be suitable to compact pipe bedding as support pipe.
75a06e11-11c5-53a2-b19b-2e2bdbed48ae | note | Acceptance Criteria - Trench dimensions correct
24504de6-2c96-51b5-8e72-2db2f039c707 | note | Verifying Document - Daily Site Diary
fe731f37-7e7f-5930-8b16-89a04bee26c3 | note | Reference: Contract Specs/Standards - D2.6, D2.7
a301b3b0-239f-5380-8195-be2d13875586 | note | Inspection Point/Signature & Date - PS
4a905c34-b47a-455c-8dc4-f96168b99e5e | checkpoint | 5.2 Encountered Services
21eb32b4-123d-5540-a0c7-94aad882cbe1 | note | Inspection Point: Quality Control Activity - Block by block ensure existing live services are not unnecessarily damaged by works.
1f59bef1-5b16-5acb-a1d6-146ecfbdddec | note | ○ Repair any services that are temporarily removed during construction.
2e07c5a5-ab9f-576b-9588-1602fbeee473 | note | ○ Record any services found.
13cdd9aa-9ace-5d10-b76e-62a521316288 | note | Acceptance Criteria - Existing services not damaged
582cb48e-beda-51c9-b6ac-7335e7a65484 | note | Verifying Document - Encountered Services Record
cad95127-501c-5c08-b606-e91bc1fea14a | note | Reference: Contract Specs/Standards - D1.7, D2.7.7
74bd3add-f4a7-5aa9-814c-3ae696c6f182 | note | Inspection Point/Signature & Date - PS
81353f1f-15be-49d3-838a-1ed56736b1c9 | checkpoint | 5.3 Pipe Installation
01923060-cdf3-5517-8e33-6b160c49fd6a | note | Inspection Point: Quality Control Activity - Interior of each pipe visually inspected to ensure free of debris.
952e516f-4bcb-52da-ae8e-4f73c9ee97ed | note | ○ Re-cap end of pipe after installation.
1cceb9a4-b12b-5633-87ad-d5c96c458186 | note | ○ Check pipe installed at correct depth.
a0b6b577-691d-5ad9-9f7d-5fa59c2b7847 | note | ○ Ensure all collars are free from contamination in McDougall St berm
eb416320-bed3-5ab2-b781-a5b0027db9af | note | Acceptance Criteria - Pipes free of debris & correctly installed
d7d27d26-e487-55fe-8620-8fa7fa21fff3 | note | Verifying Document - Daily Site Diary
a5cf8d98-7cd0-50bb-80b2-ed848c9f6287 | note | Reference: Contract Specs/Standards - D2.5, D2.7, D8.4.2
36450cbd-3427-542e-822e-d405d8cde5e1 | note | Inspection Point/Signature & Date - PS
2879712e-b560-43a7-9aad-1c57ab73e41f | checkpoint | 5.4 Concrete Pre-Pour Inspection
33c1c759-9c1b-5c04-bdba-892a74f223dc | note | Inspection Point: Quality Control Activity - Check dimensions of formwork match details in the Construction Drawings.
a2133ac9-5b72-5c48-b9d2-a72d49e7590f | note | ○ Check pipe fitting joints are clear of concrete pour.
7ffe38f3-51d4-54bd-8613-dde9232ded88 | note | ○ Thrust blocks to be poured against good solid natural ground.
b96b3d74-b9fe-5814-8703-47cb41118d40 | note | Acceptance Criteria - Thrust blocks against solid ground
76f656b2-f2f9-5d6e-9f8f-aa60d158a4a1 | note | Verifying Document - Daily Site Diary & Photos
a1c08dfb-1042-5833-9504-bada69b57bde | note | Reference: Contract Specs/Standards - D5.1, D5.3.2, D5.7
0ed845c3-c423-5340-b147-0944b926cb37 | note | Inspection Point/Signature & Date - PS, CR
2475a03f-7110-4365-83dc-96204d129ab1 | checkpoint | 5.5 Hydrant Depth
f17003a8-e013-5feb-b987-d171fbe595e2 | note | Inspection Point: Quality Control Activity - Confirm depth requirements have been met;
e17b1d05-684f-5fa3-9f9a-98575c0523cf | note | ○ Hydrant outlet: 200mm min. to 400mm max.
3f9b9414-3dca-52ec-a3f1-8ab12051fb9f | note | Acceptance Criteria - Hydrant depth verified
1bc6a7be-c09f-55f4-8439-f6b093b21a85 | note | Verifying Document - Daily Site Diary
3d1b6e9c-71d8-5fa1-ba89-da9cc1679c4e | note | Reference: Contract Specs/Standards - D5.5
1caeee8f-f9c0-5263-addd-395471bf4dd0 | note | Inspection Point/Signature & Date - PS
bb5aad7b-5480-42df-b460-52594d64a389 | checkpoint | 5.6 Compaction Testing
6936c653-790f-56c4-9d95-9b3b4451276a | note | Inspection Point: Quality Control Activity - Confirm trenches in paved areas are compacted to standard block by block.
a202b68f-0858-538b-9dab-bfcd10f9cb57 | note | Acceptance Criteria - Compaction confirmed
1c33312f-d3f6-5385-b3db-5b0e485102e0 | note | Verifying Document - Clegg Record Sheet
27d2a4bb-a60a-5250-a8a8-ea763d21d013 | note | Reference: Contract Specs/Standards - D2.7.10
01fb4b7c-7382-5d85-9052-b6648f08cff1 | note | Inspection Point/Signature & Date - PS
156bb1b8-a9ef-4689-885b-93695edaa74e | checkpoint | 5.7 Watermain Pressure Testing
0fa4cc67-2a3d-515e-bdef-cdeacb9dd544 | note | Inspection Point: Quality Control Activity - Hydrostatic pressure test on new pipeline and fittings block by block.
24ce6bd9-ff94-5701-a9c5-96e4c5f8e644 | note | Acceptance Criteria - Pressure test passed
1b68010b-dac8-53cc-a309-b15a475c61c9 | note | Verifying Document - Pressure Test Record Sheet
d652349c-b622-550c-9eda-9cbe8a0ebb5b | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
f3deb528-4ba1-5555-9dba-b373abacf58b | note | Inspection Point/Signature & Date - PS, CR
8bd362e5-3437-486a-a748-389f9a9f1be4 | checkpoint | 5.8 Watermain Sterilization
2cf95087-b098-524b-a0b6-d6bdc318a73d | note | Inspection Point: Quality Control Activity - Flushing and sterilizing full length of new pipeline and fittings block by block.
4c1a00ff-d112-526f-a96e-34ef28a68c76 | note | Acceptance Criteria - Sterilization completed
dd228508-aede-5af8-99a9-8b1c6d9f39de | note | Verifying Document - Sterilization Record Sheet
e1726fee-9df5-5a15-ad13-289c0a25c336 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
1cc88747-7e3c-582a-8bf3-4efa27301a61 | note | Inspection Point/Signature & Date - PS, CR
9143c635-a68a-45b3-9b26-c686e7954e2d | checkpoint | 5.9 As-built Information
50720e42-4bcd-5446-9119-2bbaed6d8901 | note | Inspection Point: Quality Control Activity - Capture data for all new construction work.
2dd5fe4f-94b3-58a4-a2be-59f661687482 | note | Acceptance Criteria - Redline mark-up plan submitted
b40d9ad2-14c4-583c-9890-085562792db1 | note | Verifying Document - Redline Mark-up Plan
8411e982-aa75-597d-9237-d8a058c28829 | note | Reference: Contract Specs/Standards - C1.22
eb3dce69-6c87-5070-bb05-54cea76f8280 | note | Inspection Point/Signature & Date - PM
f05395b3-f4f3-4bad-b1c5-dbf32ae35e1b | section | Final Inspection and Handover
5b9e8c0c-2be1-4a81-a4d2-d33d539ec710 | checkpoint | 6.1 Final Inspection of Works
658751f6-7383-5749-8303-5f323bb5b3c6 | note | Inspection Point: Quality Control Activity - Work is inspected by the authorised person and complies with the nominated specification/standards
275b2652-ccbd-5bba-bccf-8b20581d4f3b | note | Acceptance Criteria - Work inspected & complies with standards
d41dc86b-a1d0-5deb-85ce-023b6a87a3dc | note | Verifying Document - Practical Completion Certificate
b0928a1a-9ece-52c0-b413-14a1abfab8e4 | note | Reference: Contract Specs/Standards -
f1831583-edd5-53c6-9d06-133c10a16298 | note | Inspection Point/Signature & Date - PM