## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | itp | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | 8c38b3d9-1a95-4dd7-ac87-81f5ab58d84c
| checkpoint-no-value | 1. Referenced Documentation
4863d89d-2432-516a-80f8-bc42564f3e1c | note | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
8f112f11-ff99-5b96-807c-c8b3961380a0 | note | ITP Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
29604f05-026b-5891-8b9b-b18da7030ddc | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
425a501e-928e-5702-9cc9-7f397970f350 | note | Discipline (e.g. CIV/STR/RAIL): CIV
8874f323-7910-5115-b28e-72d172d7e026 | note | Revision Number: 1
146813df-1f02-5fdd-bc06-f5632d3f58c4 | note | Revision Date: 09/02/2024
244b1d5c-a9dc-5f47-9590-2a006c499134 | note | ITP created by: Pradeep Talasila
16365b3a-b7cd-50ff-9a70-3db1f1848207 | note | ITP approved for use by: Aldrin Guinchoma
| checkpoint | 1 - Materials - Fabrication
d89340cc-e55d-50d7-8d49-a7533a0e1c4f | note | Reference / ITP Reference - IFC Drawings Section 620, Section 701
b1a938a0-cf06-5fed-81ba-5e01966daa8c | note | Acceptance Criteria - (1) Precast items manufactured in accordnace with IFC Drawings
f2817ca3-e700-52a9-a7e8-45be407be0d6 | textbox | Drawing Ref No.
d625d82c-10da-5790-b184-b1b89bd87cd0 | note | Method - Visual Inspection
ad33bf28-f997-57f6-9225-601ed5a565d8 | note | Frequency - Each Lot
7cbcba4b-0032-585b-a309-3394acfbe877 | note | Category - IP
e118cafc-abe3-550e-9d31-2d661a370d31 | note | Responsibility - SE
75ee2393-de91-5064-9312-611034e28662 | note | Verifying Documents - Material Delivery Docket
c59d0631-b223-5359-a8d2-ce157afd4972 | date | Date Completed:
| checkpoint | 2 - Materials - Delivery
94622dcd-f54f-5511-bc8a-31a9897eb4fa | note | Reference / ITP Reference - IFC Drawings Section 620, Section 701
a219cb9c-763f-51b3-bc3b-96611c06879d | note | Acceptance Criteria - (1) Purchase Order and Material Description and Qtys matches
95cd4511-f396-57d2-9ef4-d126b5b94f2e | note | (2) Ensure precast concrete elements are as per IFC Drawings upon delivery and no damage evident.
abf8cf38-f7a6-552b-b1c7-019b4656d34a | note | (3) Lifting and Manufacture compliance certification provided
ce39861c-1118-502c-bacf-31d61d29ea53 | textbox | Purchase Order No.
31ed9309-5a56-5c3a-a391-c56ec8eaee5e | note | Method - Visual Inspection
f8858f48-1f17-55b5-8487-f18fdf947347 | note | Frequency - Each Lot
9ef7ffd4-4929-5817-8c2e-c39fc38d01a7 | note | Category - IP
04e6edb2-dcba-5306-853c-bb032d8c44e7 | note | Responsibility - SE
d98b872c-1d3c-5447-a360-0075844642f8 | note | Verifying Documents - Material Delivery Docket, Purchase Order
dcd0657f-6960-5db8-9c75-e764d38f7bb9 | date | Date Completed:
| checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
325cf1f0-1ade-5392-8e7b-6e71dee1e214 | note | Reference / ITP Reference - IFC Drawings Section 620, Section 701
8fe319df-8b49-5a4f-9564-88da65f973f6 | note | Acceptance Criteria - (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
3da76667-adb6-5b07-922e-b18b15d08471 | note | Method - Visual Inspection
86daa13c-5fc9-5601-83fe-e01ad253fcf2 | note | Frequency - Each Lot
c6423fc7-0c88-5632-813a-326026d62779 | note | Category - IP
8aa995d2-2f3e-5646-b388-79670e5b3738 | note | Responsibility - SE
34c4b2f7-607e-53a1-82d5-2e96aea401c7 | note | Verifying Documents - Material Delivery Docket, Compliance Certificate
b7569ee7-a388-51ad-b156-92a3bcfd313c | date | Date Completed:
| checkpoint | 4 - Materials - Delivery to site
35fcda50-ac0f-5ec9-9bb3-9812a7122cfa | note | Reference / ITP Reference - IFC Drawings Section 620, Section 701
3fe3c94f-cc3d-5ee2-aeb5-1cdb2fce244d | note | Acceptance Criteria - (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
0880c3a6-9905-56f1-9ef6-cbe43f96f3ea | note | Method - Visual Inspection
c7874e36-d0bd-55bb-9926-8da6ec016bfd | note | Frequency - Each Lot
4fad4770-6f03-5edb-9833-314e90cfb6a7 | note | Category - IP
578f93e7-9be2-5714-8d2f-5513b4d66966 | note | Responsibility - SE
69c4f1c0-0c36-50bc-9f33-1888541e0815 | note | Verifying Documents - Material Delivery Docket
b30e0e44-c964-5880-95c7-8ae7886b5cb4 | date | Date Completed:
| checkpoint | 5 - Materials - Others
76c68062-14cc-5bea-aa75-8e4e97c997c6 | note | Reference / ITP Reference - IFC Drawings Section 620, Section 701
dd15a4bf-e371-5173-815e-2e0e0ee2c3bd | note | Acceptance Criteria -
057f937c-84bc-52e8-a014-8b6667279f2a | textbox | (For Additional Comments)
42a3bcdf-efc8-5ed2-ae9c-12f8f49de78e | note | Method - Visual Inspection
bc894dae-d572-5f37-b22a-42952d651c55 | note | Frequency - Each Lot
7e894603-9f3a-5ea9-aa11-4280baf4929b | note | Category - IP
1f3973b7-a661-554a-bfcd-b96f3437e6c4 | note | Responsibility - SE
bde23f74-18a5-5cdb-a2b1-a4ad07b797bb | note | Verifying Documents - Material Delivery Docket
ca177b1b-8dbb-5b42-b805-8809acf64172 | date | Date Completed:
| checkpoint | Final Inspection
a3080b63-219e-50d7-b763-e914b23abbc9 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
69697743-71fe-5de3-bf20-d5ef876d653d | textbox | Name:
442acf96-0e4f-59f6-9265-3e7cb297bf66 | textbox | Position:
33394c6a-d9dc-58fc-a93c-50ee0a6e8be8 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | itp | CHK-006-STR&CIV-Material Inspection-Precast Panel | 5b7df678-e46c-4437-a67a-50283502bd28
| checkpoint-no-value | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
bce219b7-b6fa-509a-89b5-80ff6d021552 | note | Document Title: CHK-006-STR/CIV-Material Inspection-Precast
62961c05-6e52-5a63-b493-048af47a0ceb | note | ITP Description: Material Inspection-Precast
1ce143f2-b648-518a-a1db-efc1c77eb957 | note | Discipline (e.g. CIV/STR/RAIL): STR/CIV
950d4f02-af4d-5973-8fd3-59ffecf085a5 | note | Revision Number: 0
9764aeab-0311-54b9-84e6-b971cd585867 | note | Revision Date: 10/01/2023
1ded3da7-3f02-5fbc-9bc2-21a0425b650f | note | ITP created by: Ethan Caruana-Smith
e2410e60-86e2-54b8-925a-ccfc60b3f660 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1 - Delivery Details
344ce80b-5753-5523-99ce-a6912c3581d2 | note | Acceptance Criteria:
a629c0de-2f33-5d5b-9801-eef0646c48e9 | textbox | Enter: Delivery Docket Number:
ed7ab148-de7b-54b3-b413-51c9c9dce335 | textbox | Enter: Delivery Date:
ddedbcb2-125b-5b85-81e2-ec3c935c43df | textbox | Enter: Element ID (s):
911be025-2d1e-53c1-8338-e99cd948bf6b | note | Attach: Delivery Docket and packaging Slip
0abd2359-95c6-5244-b6de-bc4255069a93 | note | Method: Document Review, Visual
5579b877-be7b-53ef-9bec-0c58b7f9e63c | note | Frequency: Each Delivery
629ea501-4efe-56f3-9aff-dd2395b02250 | note | Category: IP
9307766b-5bb3-5a46-9bbe-d1950bfcefb5 | note | Responsibility: PE/SE
71260619-b205-5ca3-b0fb-7c403992e3e8 | note | Verifying Documents: This Checklist
e641c54a-db88-5a91-b836-ff6697681389 | textbox | Date Completed:
| checkpoint | 2 - Packaging Inspection-Quantity
76bf541e-3bfb-549d-9e9b-a9b1fcd55d29 | note | Acceptance Criteria: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
88a4e3e5-040b-5011-a92b-395c8276f2aa | note | Method: Visual
bcc67610-b032-5fa3-9471-d264cd7ea468 | note | Frequency: Each Delivery
e557bc2f-fdfa-5169-a109-7ca26a5b001a | note | Category: IP
73c1b1ed-5ec6-50fc-8072-c59d35d829da | note | Responsibility: PE/SE
fd0d2c3f-cf93-5fce-a58c-d760a84fc116 | note | Verifying Documents: This Checklist
140fa2d4-5566-520f-a50c-02b817f55816 | textbox | Date Completed:
| checkpoint | 3 - Packaging Inspection-Delivery Contents
718f4e51-e2b5-52ab-bf55-0233fdd7bd68 | note | Acceptance Criteria: Do the contents of the delivery match the freight list/packaging slip?
23f60db6-3ee5-5b2d-ab6c-fd7bffb8a9b2 | note | Method: Document Review, Visual
8e04e7cb-e915-5601-9abe-816ead3a9461 | note | Frequency: Each Delivery
cc95b07b-7874-5dbc-aad4-a218ec958020 | note | Category: IP
cce42478-14e2-5252-adc0-705f2506bf9b | note | Responsibility: PE/SE
5bca7a69-a2d7-5106-9e2a-72a8ea0c2b85 | note | Verifying Documents: This Checklist
2bf60b37-269f-541d-be21-67294c071223 | textbox | Date Completed:
| checkpoint | 4 - Packaging Inspection-Birth Certificate
35276d7d-24e2-5302-8605-48974734332f | note | Acceptance Criteria: Is the delivery accompanied by Precast items Birth Certificates?
3c50eace-c753-54a6-8660-e9ab5f91cc31 | note | ○ Precast components are to be marked on the birth certificate.
3f02192b-5489-5330-9035-2bc61686b8e2 | note | ○ Cast date and lot are to be marked on the birth certificate.
6c87b04e-a44a-5f8a-80b1-48ee2c1b6b6b | note | Method: Document Review
71133996-3eb3-5aed-bd0d-8473062cc67a | note | Frequency: Each Precast item
e347bacc-d21b-554d-a5eb-63c78e225738 | note | Category: IP
a458bbf2-2456-544d-815e-4a116ce3fcf7 | note | Responsibility: PE/SE
f454f1c5-4c26-5b5c-b7e2-7e726824dac6 | note | Verifying Documents: This Checklist
a8077aba-0b0f-5c84-9b5b-0a2020cb087d | textbox | Date Completed:
| checkpoint | 5 - Packaging Inspection-Transport
208f2510-4016-5f4c-841f-c52ca7b1c3bb | note | Acceptance Criteria: Is the condition of packaging acceptable.
fc0a0845-30af-564b-ab57-b6a1815f2676 | note | ○ Precast items are protected from damage during the transport
4a5e3b29-eee2-5e84-85c0-054fbacaf1c3 | note | Method: Visual
d3a33d85-a83d-53e9-9b70-e491657a3295 | note | Frequency: Each Precast item
4eecb52b-2993-522e-9bfe-aa789a6b9534 | note | Category: IP
805c2a14-74b4-533a-ae3c-2a408f40b3e3 | note | Responsibility: PE/SE
c20d38ea-0fcc-5cff-badf-4eeab1b27ab2 | note | Verifying Documents: This Checklist
b42deda3-3aaa-59a9-8819-0bb96f1ae887 | textbox | Date Completed:
| checkpoint | 6 - Fault IDs:
af9bf072-4f51-521f-94a1-83f10f055a9a | note | Acceptance Criteria: For each precast type delivered, check for the following:
8541fd75-648b-55c4-afaa-ef964e5ff77a | note | 1 - Identification markings match the element type
c316d1fe-42e7-5560-ab05-b043d1ca8cf5 | note | 2 - Element fabricated as per drawings
82259ea4-a5a5-59a9-8a2a-0616685da0f7 | note | 3 - Cracks
851b6e38-d72c-541e-b19b-799c7d6b0ab1 | note | 4 - Spalling/Damage to concrete surface
826a8a98-4894-558b-a698-aa0c9e299923 | note | 5 - Exposed Reinforcement
d78fc058-a6a2-5d28-a4a9-509d269f2086 | note | 6 - Damage to Anti-Graffiti coating
d1970c36-8287-543c-9c5d-d9c365cfee96 | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
262ffce6-2486-5b9d-b791-74d50d690fa8 | textbox | Date Completed:
| checkpoint | 7 - Check for Faults - 1
37482a30-1ad4-560e-8366-0ec4902552f2 | note | Reference: Item 6 on this Checklist
a65fdb1d-405a-5dc2-8fc2-375fe1f58e75 | note | Acceptance Criteria: For Each Precast type delivered:
32800972-51f6-548e-9949-1f21a90503fd | textbox | Enter: Panel Identification:
1bb34d5f-0a39-5091-9332-cf51e2cf6299 | textbox | Enter: Quantity:
c0b0aa8b-f59a-5943-b388-2dc4539679cd | textbox | Enter: Fault ID if any:
e7dbac52-3713-5b16-8ccc-0f6a360c87b5 | note | Method: Visual, Measure
fdbb5875-a28c-51aa-83f8-5763c3c8a6fb | note | Frequency: Each precast type delivered
e75086b1-a267-5767-a15c-d07a2118f337 | note | Category: IP
f930b2e1-c860-512b-80f7-89c775e2caa1 | note | Responsibility: PE/SE
a56cfd6a-d90c-56b1-86cd-4a9b472fdb5f | note | Verifying Documents: This Checklist
98e84f62-b5d5-5e6f-87a6-b459537b992d | textbox | Date Completed:
| checkpoint | 7 - Check for Faults - 2
dd3718ae-8a31-5703-bac3-58a624e8c7c8 | note | Reference: Item 6 on this Checklist
a511ad41-f344-538e-9ab7-597f812f962e | note | Acceptance Criteria: For Each Precast type delivered:
0550e532-2b50-54a3-ad43-daa88b8ecd56 | textbox | Enter: Panel Identification:
4d792993-ce62-5455-904a-40089d3bb480 | textbox | Enter: Quantity:
66d327e0-5346-5fee-885f-4d4c074c33b9 | textbox | Enter: Fault ID if any:
14125e41-4a60-52d7-b020-9ba921fba05b | note | Method: Visual, Measure
e8062087-ac7b-5c23-956c-211db93a9bf1 | note | Frequency: Each precast type delivered
8e0f2283-293b-501a-906d-8d31b5cfb5ab | note | Category: IP
6ba7b633-d848-5a01-9f5b-68d5b5515d5b | note | Responsibility: PE/SE
acbd4257-5087-5db4-85b2-d05d2c8a618a | note | Verifying Documents: This Checklist
25d8f4b2-9d6e-59aa-8e6f-8927df7f9e21 | textbox | Date Completed:
| checkpoint | 7 - Check for Faults - 3
335bf7cb-77dd-565b-ac96-d07bafaf09be | note | Reference: Item 6 on this Checklist
e42fad3a-7a16-5e73-99a8-ae631da951a1 | note | Acceptance Criteria: For Each Precast type delivered:
fa43809a-d1a3-59cf-9517-28d0d61431ed | textbox | Enter: Panel Identification:
0d0e22cf-8cf1-5325-aed6-4594fe24eb82 | textbox | Enter: Quantity:
83dd9ba2-8bda-5467-ad0e-0731b8785de9 | textbox | Enter: Fault ID if any:
4edd7b19-5fc0-5466-baa8-d8cec5e4feb0 | note | Method: Visual, Measure
d4ce2b9b-4c0b-56e5-97b6-a7a41d948ac1 | note | Frequency: Each precast type delivered
688102aa-fe76-543f-b031-56e3e0ace731 | note | Category: IP
d9ceb319-3444-523b-a41a-cf92b3bfe3bf | note | Responsibility: PE/SE
3109b6ba-21c0-5356-8bbf-fea3086df10f | note | Verifying Documents: This Checklist
87c2f0ee-2ad9-52d8-95d4-ec5cc9283fc5 | textbox | Date Completed:
| checkpoint | 7 - Check for Faults - 4
0d302f9d-fbf9-532d-9af0-e11652c024d5 | note | Reference: Item 6 on this Checklist
06df5cff-6cb5-526c-ae61-8d74a1bc003d | note | Acceptance Criteria: For Each Precast type delivered:
147f2266-9a23-5470-8f93-39abf8296e05 | textbox | Enter: Panel Identification:
26223c47-0c3d-566e-969c-d937ddeb75b5 | textbox | Enter: Quantity:
1a730ba1-1f74-5103-84c6-9cc1cf71ae43 | textbox | Enter: Fault ID if any:
3f54e94b-763e-5f68-ab61-bef25e849b27 | note | Method: Visual, Measure
4233fa42-2ed0-504f-b5b9-78b3fd5d7214 | note | Frequency: Each precast type delivered
546e4603-0b33-5b75-816c-5bd8d1d66f17 | note | Category: IP
4eaf04c8-1dfe-5073-9a20-5cfaba5aead9 | note | Responsibility: PE/SE
ec2151c7-b2e7-5e62-9da8-4e5fe60437ff | note | Verifying Documents: This Checklist
f9aca46b-b30d-5027-8165-b291842bd845 | textbox | Date Completed:
| checkpoint | 7 - Check for Faults - 5
849d9e62-b59a-53c0-84c1-97ee3f200dc8 | note | Reference: Item 6 on this Checklist
c98474e7-58ce-506c-b9cb-5a55bcec9e6d | note | Acceptance Criteria: For Each Precast type delivered:
78352b2b-44b5-5ace-9f97-3af61f839659 | textbox | Enter: Panel Identification:
dce07498-f44f-5b95-aba0-51daf463fe2e | textbox | Enter: Quantity:
dde847dc-9ef9-5a83-b463-c1ea08bf8887 | textbox | Enter: Fault ID if any:
7c0b39d2-b830-5219-8000-3e13af81b9e7 | note | Method: Visual, Measure
61812628-a897-5161-8c0e-d00f22b6819e | note | Frequency: Each precast type delivered
49b629f6-453e-5b61-851f-32f2ebac15de | note | Category: IP
0565b5a9-e2f9-5a0d-af6c-0019e6f3beb6 | note | Responsibility: PE/SE
93cc506e-37fc-51ad-9936-80129e34717a | note | Verifying Documents: This Checklist
9499e010-7f54-5b56-ad3a-6fdc667b1797 | textbox | Date Completed:
| checkpoint | Final Inspection
a83172ee-8ad7-5893-bc6f-92943ea5b3d0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c19cd29a-ae10-5504-8728-2f3c5f66ebc4 | textbox | Name:
fb7803d9-b823-5eb4-a4ff-cc4ffe6ae410 | textbox | Position:
a3c967d9-8366-56f9-b8b5-c56c995b9989 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-007-STR-Material Inspection-Precast Barrier Kerb Rev 0 | itp | CHK-007-STR-Material Inspection-Precast Barrier Kerb | dcd269e2-52fc-4e4e-9293-64d08944e7a2
| section | Details
| checkpoint-no-value | CHK-007-STR-Material Inspection-Precast Barrier Kerb
e469640e-3c01-5ed7-9fc3-eeb71270911e | note | Document Title: CHK-001-STR-CPD-Material Inspection-Precat Barriers & Kerbs
fae92e32-3bb4-57dd-ad1d-ade7635cf64b | note | ITP Description: CPD-Material Inspection-Precat Barriers & Kerbs
1f5c1b7f-6b2b-5ce5-bb1a-9539e5e93e99 | note | Discipline (e.g. CIV/STR/RAIL): STR
11a794b9-a787-5911-aa0e-95fd5afd65c8 | note | Revision Number: 0
216bca35-8d09-5ad8-a1f1-65aa8b9cbbaa | note | Revision Date: 14/11/2024
8d87d9a0-7d15-598b-affe-675e7189c4ae | note | ITP created by: Ahmed Abdelsalam
90e2e9a0-a505-5c44-b985-768dad6329d7 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1 - Delivery Details
5afe63df-1959-55e0-9c02-18348a624c95 | note | Acceptance Criteria -
432a6b00-8939-57b9-aee2-bd11fcce45e1 | textbox | Enter: Delivery Docket Number:
3b3e115e-eac9-507e-a24c-0b54eda8740e | textbox | Enter: Delivery Date:
ba2f1975-2484-5138-9e07-7afb8bbb0ac4 | textbox | Enter: Element ID (s):
616c1f8a-7c02-5b8f-bacb-8f0e20e24619 | note | ○ Attach: Delivery Docket and packaging Slip
e7d5fb1a-8168-57c9-ac75-2956bd9d979e | note | Method - Document Review, Visual
59550ca9-5b3c-5389-8acc-49fa34123e95 | note | Frequency - Each Delivery
75288f34-99b3-5803-a85a-808373fdbc56 | note | Category - IP
efe2a752-9e61-5094-9c8e-0814ebc5913f | note | Responsibility - PE/SE
35240e98-fa09-5c91-b10a-8247c3a181bb | note | Verifying Documents - This Checklist
65a9f303-805f-5d09-abb3-838c10299453 | date | Date Completed:
| checkpoint | 2 - Packaging Inspection-Quantity
2d781e84-61db-5aaa-a7d1-16818c6f8ba1 | note | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
369b570a-818d-5bfd-8630-c5b01930b41e | note | Method - Visual
30b9c5db-acb4-544a-8f24-e39fcd53f468 | note | Frequency - Each Delivery
568bb209-33ef-5188-b43f-4066f060cf3d | note | Category - IP
a30982b9-800c-5fdd-bbb2-a6d19b3e2022 | note | Responsibility - PE/SE
2963adf6-24e8-594e-b680-5d6cd6ff019d | note | Verifying Documents - This Checklist
086531de-f20c-5de3-b99d-e810583198b6 | date | Date Completed:
| checkpoint | 3 - Packaging Inspection-Delivery Contents
6194e9a0-c606-58f2-be84-f2f05fd21d88 | note | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
ff183877-0a32-52f1-a5fa-2f3c4413d460 | note | Method - Document Review, Visual
264c4f04-99b2-52af-a49f-537fd015bbf6 | note | Frequency - Each Delivery
fe7de8c6-a226-59c7-8a84-d14687db7342 | note | Category - IP
49852d9d-7902-5b9f-9ef0-3ca9a0061d07 | note | Responsibility - PE/SE
5e8c51d1-9ba1-5e11-a234-25b94a9df41d | note | Verifying Documents - This Checklist
b72702ed-eebe-5772-a770-64cb7fe96432 | date | Date Completed:
| checkpoint | 4 - Packaging Inspection-Birth Certificate
eefdac6e-56af-5b6d-8518-155569e47ddd | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
f679be31-e1e6-5213-aab5-4c10aca50cd0 | note | ○ Precast components are to be marked on the birth certificate.
887e9375-055a-5521-9c53-591430cd8bfd | note | ○ Cast date and lot are to be marked on the birth certificate.
72253f60-4e80-5651-a4bb-407b96b1cf8b | note | Method - Document Review
6bb19e26-7c40-52bc-bd22-63101d22f498 | note | Frequency - Each Precast item
a5e942ea-5e38-5c53-8804-ba2de20f3e59 | note | Category - IP
1e05cbb6-f07a-5a4f-9a8e-2f64ac8ac87b | note | Responsibility - PE/SE
aa91501e-3bba-5c14-b675-d0f6ebf71c3e | note | Verifying Documents - This Checklist
1a060393-24ac-5d0d-8c5d-64bcd3b338bb | date | Date Completed:
| checkpoint | 5 - Packaging Inspection-Transport
56fbdfb3-c2c0-59a1-929c-a06192a8a98d | note | Acceptance Criteria - Is the condition of packaging acceptable.
4482d5e9-7cca-5c08-a4af-f7e911839251 | note | ○ Precast items are protected from damage during the transport
04e39873-534f-544e-8017-8ebea06586a3 | note | Method - Visual
b2523e62-c3fc-516c-a88e-493ad0db5231 | note | Frequency - Each Precast item
68a94509-5f89-5eea-a49e-93e60c29f075 | note | Category - IP
0d5550ce-b517-54e8-8c25-18d07b339c9c | note | Responsibility - PE/SE
a4cbe996-6671-5f52-b005-3b51f285cc80 | note | Verifying Documents - This Checklist
bf411180-4897-5cfd-abb6-d269644dc22a | date | Date Completed:
| checkpoint | 6 - Fault IDs:
939f8944-e534-5133-a686-e578a873fed7 | note | Acceptance Criteria - For each precast type delivered, check for the following:
7982b518-a35f-5873-8dcf-15d84ca6690b | note | 1 - Identification markings match the panel type
c89d62dd-3ffe-547a-8f51-c25286374195 | note | 2 - Panels fabricated as per drawings
f43542f0-0730-5204-8573-176803e51c7f | note | 3 - Cracks
78763097-2d5f-525e-a919-597ea0212bc5 | note | 4 - Spalling/Damage to concrete surface
8a72dff5-ac8b-5add-93c3-7986094a1ae3 | note | 5 - Exposed Reinforcement
6b512374-128d-5df2-943b-ea6972d0a48c | note | 6 - Damage to Anti-Graffiti coating
39bc54ef-643f-55ea-8542-f39da5f27522 | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
ce71e41b-61f1-5a42-a771-362da0a42150 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 1
cb2e5740-f2ae-5e2f-9756-a57f1e167821 | note | Reference - Item 6 on this Checklist
74081c42-f939-5bec-8fe7-5416275335f8 | note | Acceptance Criteria - For Each Precast type delivered:
eebfd5e7-7812-5bbd-9f40-2fed1c7f6d71 | textbox | Enter: Panel Identification:
6f76945f-6d8c-585f-8edc-73f03c9c36ef | textbox | Enter: Quantity:
ce5aec17-5de1-53ab-82e1-b04b13163cbb | textbox | Enter: Fault ID if any:
9ef251d7-aa28-5077-9268-9e0f6428ef4d | note | Method - Visual, Measure
0234c31e-d84a-59a5-8f78-ab6e615c1b8c | note | Frequency - Each precast type delivered
84199d18-ef68-5be8-84fc-46a3a0230183 | note | Category - IP
78d17ee3-e0ac-5644-9dc0-3aa7791ff0dd | note | Responsibility - PE/SE
822695b1-2c68-531f-aaef-0aa8a90a996a | note | Verifying Documents - This Checklist
8e19a4aa-cc5b-5826-827d-815e31121474 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 2
6d9eddd5-4fb9-5ffe-a990-60c80c6863bd | note | Reference - Item 6 on this Checklist
bdfce283-101b-5d96-89a0-43d1fba73ab5 | note | Acceptance Criteria - For Each Precast type delivered:
f2ae48df-969e-5709-97de-a72050ba9242 | textbox | Enter: Panel Identification:
504eb1dc-ea42-55b1-bfba-7a6340da04a9 | textbox | Enter: Quantity:
8846ec9f-06fb-514f-b6c2-895021b4492b | textbox | Enter: Fault ID if any:
0d75ca2b-fda8-5d0b-9af1-0ad28286631e | note | Method - Visual, Measure
09672778-da8b-502f-ae0b-7ede357a9202 | note | Frequency - Each precast type delivered
611e8a2f-3aab-5022-a490-b954cc42db68 | note | Category - IP
80793d0c-b70e-554e-a524-566722badd54 | note | Responsibility - PE/SE
2b47d4e7-2caa-59c3-80b3-2203262b9641 | note | Verifying Documents - This Checklist
47dc582f-0786-52dc-b73f-125095fb2126 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 3
22256d15-28c1-54dd-b072-1a85566dc108 | note | Reference - Item 6 on this Checklist
e7402e77-bcd3-57c9-bd8f-baa8feff9c22 | note | Acceptance Criteria - For Each Precast type delivered:
5af4e06d-6e9a-5518-bec4-79daf72dd593 | textbox | Enter: Panel Identification:
eeab3a8e-6c67-59a8-9f65-2e9cd5f1d123 | textbox | Enter: Quantity:
612008cb-80ec-5674-b931-160fc982215f | textbox | Enter: Fault ID if any:
0cbdc9ea-2789-560f-a379-ffd3ae25d6cc | note | Method - Visual, Measure
bfebb9c9-2184-5db9-9e6b-cac1df1760f0 | note | Frequency - Each precast type delivered
f209954c-c4ab-5237-ab6d-f0f8b007246f | note | Category - IP
e1c4a3fd-2135-5c6a-a20b-40a3c0234781 | note | Responsibility - PE/SE
8c7a252c-72df-5081-bd4e-67c93ec3acc7 | note | Verifying Documents - This Checklist
a5e50592-ab52-5f03-8734-4a75ebdd5520 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 4
69db7343-da9e-5b21-84cf-2634ec2922ef | note | Reference - Item 6 on this Checklist
b6ad2bc8-42a2-51d6-8e65-6b542773f42f | note | Acceptance Criteria - For Each Precast type delivered:
15a23a9d-a71a-5af1-9b6e-ee964692dae8 | textbox | Enter: Panel Identification:
b2a08a7f-fc40-5ff1-b021-1f745974eba4 | textbox | Enter: Quantity:
f4bf8ca7-769a-50fd-84d3-d640442f2eb8 | textbox | Enter: Fault ID if any:
c70502d9-c3e0-5886-be51-bc22912ba809 | note | Method - Visual, Measure
7017341d-2cd7-5208-93a2-b6932ddeefb4 | note | Frequency - Each precast type delivered
134184ca-2190-5905-80a1-07804d33541e | note | Category - IP
3b9e7bf8-eac0-5c9a-8570-d28e8f57ad33 | note | Responsibility - PE/SE
93600b47-ed92-52ea-95a6-92acaa92da77 | note | Verifying Documents - This Checklist
fdccf58d-ae7f-5ea0-89fa-d7fe3415ad07 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 5
a29e2cb8-72b8-5950-9e2c-8b26f121ff14 | note | Reference - Item 6 on this Checklist
a0343fad-141a-554e-9149-e73c399b672c | note | Acceptance Criteria - For Each Precast type delivered:
48158eae-2f23-5c6b-8e43-90089bb22cc9 | textbox | Enter: Panel Identification:
cb04520a-e075-5ac2-8d83-c884ace45ee8 | textbox | Enter: Quantity:
53e1ab9f-9013-58d5-b33e-7b1e56a7391c | textbox | Enter: Fault ID if any:
78443e11-aeed-5707-8a19-f44d0c905a48 | note | Method - Visual, Measure
d994f362-05e5-5c8c-b2c7-a1cca7c54169 | note | Frequency - Each precast type delivered
90d05006-4584-518b-ab08-a61dd0f01b60 | note | Category - IP
0724f2b5-b4ce-561e-af92-c50f29ec82a7 | note | Responsibility - PE/SE
fcab2355-995c-5b47-94fd-7c412942559b | note | Verifying Documents - This Checklist
6f8a9585-328e-53ce-9522-ed57a42565ec | date | Date Completed:
| checkpoint | Final Inspection
8722ffbc-3472-504b-b794-4062e309ec0d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
97ace8a3-8753-5403-b01c-278f4bce7ce9 | textbox | Name:
8b205473-e432-5081-8751-e9d03fda011c | textbox | Position:
b866d173-fbc3-56f2-be80-889991cffb9c | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | itp | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation | b070ead5-3321-4740-9077-afccf5184d85
| checkpoint-no-value | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
60628a10-36c3-5717-a94e-cba0e4963c02 | note | Document Title: CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
7f185b64-4be8-53f9-ba49-19249c95a3cc | note | ITP Description: RSS Walls - Panel Installation
a57300cb-ac92-5703-a886-542912e0d281 | note | Discipline (e.g. CIV/STR/RAIL): CIV
a4ebe98e-b2ba-57a7-923b-97f01270e155 | note | Revision Number: 0
841a0393-beab-5097-b02b-e7f212bad102 | note | Revision Date: 06/11/2023
c46adb0f-d479-54e7-85f1-7be0a8b501c8 | note | ITP created by: Matthew Dib/Jason Quan
fb1c9a3f-e81c-5ec0-9789-5d4689fa09a0 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1 - Panels-survey set out-Tolerance
ec5c0bf7-11f8-5abb-a3cf-72663c7a9a97 | note | Reference: VR 682.20 IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1001 and 1202 to 1205
98312932-a44d-5ffb-a9eb-538b01bcf311 | note | Acceptance Criteria: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
135cc316-6a97-5e2b-a404-dde9f038be6c | note | Method: Measure
522488ac-c6bd-5d26-a467-ca8e217afce6 | note | Frequency: Base course panels
91d06444-0ff3-52f9-9612-38b2dc1578ea | note | Category: IP
6d5b175c-ed52-5d4c-ad93-4328bb8616cc | note | Responsibility: Surveyor/PE
58b763c9-0f26-5de3-972a-0a28e146ec78 | note | Verifying Documents: This Checklist Signed-off
740f46ec-6adb-560c-8e71-6b80f6ddabec | date | Date Completed:
| checkpoint | 2 - Mark-up panel for construction team
fc30ab54-9bc1-5ef8-89e4-a3da88e46ac2 | note | Reference: Construction Manual
647c88ae-771b-5b2c-9fbf-124036b85870 | note | Acceptance Criteria: Mark number of strips per row on the back of each panel. Mark design location (Wall number, row and column) as per elevation drawings on the back of each panel
7c9b37cf-4f51-5ef0-9d6f-508986b738a6 | note | Method: Visual
2ef95ede-fe73-5675-ba20-57d5e5c9d35b | note | Frequency: Each panel
5702c218-3d46-5990-b1fe-febcd5f47cb2 | note | Category: IP
90a89d60-0ab6-5de2-b8fb-be8f8ada4604 | note | Responsibility: SE
ec306520-4e89-54e5-8b1b-eee571f9be03 | note | Verifying Documents: This Checklist Signed-off
4689fe11-c498-5a4e-b62c-76dc673f33e8 | date | Date Completed:
| checkpoint | 3 - Panel installation
078b4f66-2ce3-5cfa-a4b7-402931178a61 | note | Reference: IFC Drawing:
27559ff0-7bfb-545e-a0df-23ca6cff4992 | note | ○ Instructions: MRP-080-C-RFL-DRG-33-CPV-CSW-2003
57e65f2b-d31d-5882-bc78-e6137256042f | note | ○ Weephole Locations: MRP-080-C-RFL-DRG-33-CPV-CSW-1401, 1402, 1501, 1601 and 1701
1d1e5660-7a5a-509f-8c70-ea5d27df247a | note | ○ Archtectural pattern drawings: MRP-080-C-RFL-DRG-33-CPV-CSW-1404 ,1503, 1603 and 1703
f00e53e3-d374-5126-8e8d-c48dc3bc512e | note | Acceptance Criteria: RSS Panels are to be installed as per IFC Drawings and specified schedule.
ee535164-40b9-50d9-8f16-704c908bd0fe | note | – Check for correct architectural pattern
f464d46b-746c-54e6-ab63-cf08e31d26a1 | note | – Check for Weephole Locations
895dec39-4a52-5663-a82c-f280c528f466 | note | – Check the 1 in 40 slope is to be maintained
693c030e-7c10-53eb-81d3-defd6ad133e9 | note | Method: Visual, Measure
1f19cc13-4b35-5e41-bfe6-89a47ed50062 | note | Frequency: Each panel
bb2265da-d911-5ca4-b18e-238e266fa647 | note | Category: WP
dbaff399-13ad-550c-8e4e-6cf95a23036d | note | Responsibility: SE
aed3e718-9a41-535a-a79d-78b1bac3e92c | note | Verifying Documents: This Checklist Signed-off
17899be1-1760-551e-b17f-dc1a815d2489 | date | Date Completed:
| checkpoint | 4 - Bearing Pad Installation
21d82eeb-ce61-5b61-bc45-535fbeaee529 | note | Reference: IFC Drawing: Instructions: MRP-080-C-RFL-DRG-33-CPV-CSW-2003
8a485805-caee-517c-8f42-8d5eff7aaaab | note | Acceptance Criteria: 3X19mm bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
eac3dcdb-de26-587d-9842-339dc55466b6 | note | – Check the 19mm nominal gap to be maintained
dd417a53-0ec7-5aa1-9013-2d247072893d | note | – Install 3 Bearing Pads at rear on top of panels
585dd8a9-54db-51c7-b7a0-c9ddca90e580 | note | – Above must be checked with Surveyor prior to backfill
3fd97cfd-7cd4-5b45-a6bb-ac4b8323a265 | note | – Note bearing pads shall not be installed under base row panels
579f0991-0306-5447-a29c-e06df963e058 | note | Method: Visual
6abf0b61-c07d-53fb-979d-209987467ca9 | note | Frequency: Each panel
fa828318-1cef-5bc5-aa51-e8aa6cb93b9f | note | Category: WP
e8a5bc05-9d34-532b-99a8-a76d89e33d9b | note | Responsibility: SE
7d9a643a-e8f1-569c-bc29-d700157b7743 | note | Verifying Documents: This Checklist Signed-off
6604db6a-03b9-5b55-81e7-87fa03d494d7 | date | Date Completed:
| checkpoint | 5 - Panel installation-Abutment interfaces
352e800a-bafc-54a1-85ab-ecc0c5f1a877 | note | Reference: IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1106, MRP-080-C-SME-DRG-34-CPV-CSF-3023 and 3024
898bf9c8-b7a0-5543-b3da-30688ba7c931 | note | Acceptance Criteria: Panel installation and abutment interfaces
5116b153-d451-57d2-9c41-3768e167ef4b | note | – 20mm nominal gap between panels and Abutment wall is to be mainatined
a8ee7baf-d9ff-5316-b007-11061af970a8 | note | – 150mm wide x 6mm Folded Galvanized plates (Grade 250) drill and fix to as per IFC drawings with Galvanized M12x75 Long Excalibur screwbolts at 500 CTRS Typical each wall.
95f986c0-c7a2-5466-ae2a-cbf69a031947 | note | – 600mm wide BITAC tape installed
c7f53298-83f0-5795-942c-6aae7ee00f7a | note | Method: Measure
cefa7bda-1a64-51e0-aa91-99a7a4f7aa24 | note | Frequency: Where applicable
d696292e-67e2-5cc2-8b0d-aa5f93d910bb | note | Category: IP
45879306-2b62-5096-82c3-506d328b9704 | note | Responsibility: SE/PE
27e852c2-c95a-5773-8f62-b5a80be7b1d8 | note | Verifying Documents: This Checklist Signed-off
d4749aa2-1e9e-598e-93e5-0acf8a55b665 | date | Date Completed:
| checkpoint | 6 - Filter fabric -Installation
95298764-d327-5a7e-bb49-ab8bf3427380 | note | Reference: IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-2003 VR682.11
1b6bad61-be78-5a54-95bf-dad7600b0f91 | note | Acceptance Criteria: Install Filter Fabric against all vertical and horizontal joints
b378caaa-e060-58a0-8693-64f8f1c44ba7 | note | Method: Visual
0c7283fb-b5b9-5a88-be7a-96ad1e995168 | note | Frequency: Each course of panel installation
c756ea8e-5ea4-58a6-8095-d7f23d96e046 | note | Category: IP
29f142e4-9cc4-560a-be13-a72017ac11f2 | note | Responsibility: SE
032371b1-9c07-5b53-88ec-2523b4bc3018 | note | Verifying Documents: This Checklist Signed-off
b82f27e8-0515-58bb-b65f-622be40e5390 | date | Date Completed:
| checkpoint | 7 - Drainage-Strip Drain
23bb4b91-c964-57ac-b0ef-30122d75fcb8 | note | Reference: VR682.11
6bd07f17-9cb3-537a-98ec-3a2117a0e2c2 | note | Acceptance Criteria: Install 300mm wide strip drain between precast wall panel vertical joints. Strip drain to be encapsulated by nonwoven geotextile in accordance with section 682.11 At every vertival joint between panels in RSS wall, ensure no gap is formed bewteen strip drian and RSS panels
9e980d20-e04e-5d08-801a-d0c113b1f52d | note | Method: Visual
3a8f8069-a4a1-51d1-9e22-162ef850c459 | note | Frequency: Each course of panel installation
a3165bcd-f7bd-59a2-8473-9dcc977bc89a | note | Category: IP
03a2a280-f041-5474-a18f-fd63515e7947 | note | Responsibility: SE
feda960a-8da4-578a-a6d0-75e1cfc7847f | note | Verifying Documents: This Checklist Signed-off
3060fa38-6c0b-5c2e-b572-2694c5142730 | date | Date Completed:
| checkpoint | 8 - Panel installation-Survey reference points
53886d03-d73a-5828-b167-8b345b1785ef | note | Reference: VR 682.20
8c127dd4-0f74-5c5f-9338-b01d9466e451 | note | Acceptance Criteria: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
d816a4de-f706-5d24-be67-0f6b2630235a | note | Method: Visual
bdf2aa53-e9ce-5e3c-83da-2ebb429921d5 | note | Frequency: Each course of panel installation
d35d7dac-3b40-5c29-99c9-fc5c04e2d372 | note | Category: IP
cffbaac6-20d2-5f1d-93c7-aa8ebc6a31b4 | note | Responsibility: Surveyor/SE
f7566f1a-7219-555b-a337-70dafe1c1226 | note | Verifying Documents: This Checklist Signed-off
28263e3c-d788-5060-a8ca-900b5d446b0c | date | Date Completed:
| checkpoint | 9 - Traceability of precast units and records
ea6b0bd5-675e-5dbb-8c33-e02f7c318101 | note | Reference: VR 620.09
a91b153a-a759-5ee4-a1f8-ae77f445e67b | note | Acceptance Criteria: Unique ID of precast panel is recorded.
4cb7f5f0-c032-5163-941f-71c92e77c12c | note | – ATTACH: marked-up elevation drawings or installation record with reference to panel ID
3250e66d-a540-592c-a273-06f283d50974 | note | Method: Visual
f6d0eb82-ba6b-55d0-a508-a7e9e7b4472c | note | Frequency: Each panel
35a0b050-7db2-5834-957d-21b1021c69e8 | note | Category: IP
1e3e97dc-4304-5ed9-bfb7-21fd43c1fea1 | note | Responsibility: SE/PE
22a11466-433b-5a59-bac2-e50260f231d4 | note | Verifying Documents: This Checklist Signed-off
d826f113-5181-51e5-9482-3400ea09ef02 | date | Date Completed:
| checkpoint | 10 - Panels installation-Conformance Survey
86f30299-8e16-5b5d-935e-4421f835f930 | note | Reference: IFC Drawings VR 682.06, VR 682.17, VR 682.20
73990e87-4333-54d0-ae26-e4e6b0bba436 | note | Acceptance Criteria: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
b8d95246-73ed-50b9-9d0f-c84e77146467 | note | ○ Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
f2314fc1-dc19-52fc-915f-7a7d37a026cf | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
dab41d19-6f5a-5207-a4c9-4e50f29fe9a8 | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
b72296e8-876c-535f-9f49-f37c138105c5 | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full length of the gap
b45fb8cc-95e2-5be7-824c-4b4aa3860980 | note | – The wall level shall not deviate from the specified level by more than ±20mm
b530976d-bb05-556b-bf61-37634ec04971 | note | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
7227af2d-81cf-5599-bbba-44efbf56dbef | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
143ebc3a-72d5-53cb-9f32-2f461791ec27 | note | Attach: Survey Report
fc9614ce-63c1-535e-82ee-dbee154fcdfc | note | Method: Survey, Measure
c16636c5-efce-5f85-9509-a3ac2aaf4acb | note | Frequency: Each course of panel installation
18cbf1ba-714d-5333-a8bc-d798c1309f8b | note | Category: HP*
75db4a07-8779-558c-9f84-a77000e72e59 | note | Responsibility: Surveyor/PE
43c77cf1-fa06-505f-afdb-70ff2bf7faa8 | note | Verifying Documents: This Checklist Signed-off
bfd2fe17-04e8-54bf-8cd1-7bfe747adc3e | date | Date Completed:
| checkpoint | Final Inspection
5b1c94c4-0404-5fb3-8a7e-5850e9b448d2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
333def9c-7604-5831-b57d-c3a7dac23ff0 | textbox | Name:
fb32f7be-7bf5-51d2-9196-12f9bbc2b61d | textbox | Position:
583928f4-3d30-5bbf-ae8f-4395acba1a69 | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | itp | CHK-009-CIV-CPD-RSS Walls-Fill Placement | 993c9fc6-174a-4a27-9b6e-1ab1d06b864d
| checkpoint-no-value | CHK-009-CIV-CPD-RSS Walls-Fill Placement
6128f4a3-3107-522a-a68e-c4a22df59cce | note | Document Title: CHK-009-CIV-CPD-RSS Walls-Fill Placement
6dba2edf-05ee-58aa-87b7-414470589d6c | note | ITP Description: RSS Walls-Fill Placement
36ad6b0f-fd9c-523e-bcd0-ead7a2b1dce0 | note | Discipline (e.g. CIV/STR/RAIL): CIV
e7909d05-ea40-5202-bf76-77004b896022 | note | Revision Number: 1
7362251c-9954-597c-b25a-9aea862c72d2 | note | Revision Date: 14/12/2023
c19d2176-023b-59b6-b5c0-8805fcc6e4d0 | note | ITP created by: Matthew Dib
7a6b3ddd-aef9-5a46-8f16-60b1ff9ef102 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1 - Soil reinforcement-Straps
d60805f8-a405-5cc9-b4ec-a315a232b02c | note | Reference - VR682.08, VR682.17 IFC Drawings
73271751-92ca-5fdf-a1f6-19a256df29c3 | note | Acceptance Criteria - Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
0c470ae9-30d9-588d-90fe-0bad01488f8c | note | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
ff291c56-0dce-52f4-ad24-547fc2a54f9d | note | Method - Visual
d198d0b3-123f-5284-8462-30139c5d56b1 | note | Frequency - Each strap
4e42d951-8098-5339-a32c-38c566536cc0 | note | Category - IP
c84ba2ed-be4d-51f1-9d88-fcd71716b8b2 | note | Responsibility - SE/PE
0a69a04c-5974-5af5-a75b-9795c9daedbf | note | Verifying Documents - This Checklist
178b72f4-5655-5ec7-9832-07309096f21c | date | Date Completed:
| checkpoint | 2 - Soil reinforcement-Straps
ad48b446-877e-57dd-8210-9c1c7c6b8593 | note | Reference - Installation manual
9f978d62-5d35-5a33-af84-70291df38868 | note | Acceptance Criteria - Correct number of reinforcing element shall be attached to each panel/wire facing units
bd9a335a-26ba-511e-ba1d-2969d6ffb571 | note | Method - Visual
c5a0d7f0-bb3e-59de-9941-d5c631a032ad | note | Frequency - Each panel/wire facing unit
f10102c1-3726-5188-b88e-13d1a95726ac | note | Category - IP
9cdc77a8-72ab-5588-a42b-1b7c15e2b556 | note | Responsibility - SE/PE
dc27f563-1d9b-5842-8e6b-da474ad15aee | note | Verifying Documents - This Checklist
6e9bba0b-4374-59f5-9b7a-4e0f343c3b9f | date | Date Completed:
| checkpoint | 3 - Pre-cast Panel Soil reinforcements-Bolts Connections
249a1359-c368-5599-8c3d-7d84dbd3eda2 | note | Reference - IFC Drawings
7390482d-8928-5e11-9db6-b368325d8271 | note | Schedule of lenghts:
23d25e56-69f2-5982-9882-8e9e03b1314a | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1403, 1502, 1602, 1702, 1803.
cd7be197-2495-5c9c-9c8f-70ac11fa7cc1 | note | Connections arrangement:
612d52bd-0050-5b65-b646-1702c7fa29af | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-2101
b1c535b1-2dd6-5528-ae07-01fe89f7ddf0 | note | Acceptance Criteria - Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
fe73e879-b8f7-5471-8832-1ce320feb9a0 | note | ○ Finger tight nut or use a wrench so thread emerges from top of nut
0ed778ce-7964-50f0-adb6-358f0f3da33d | note | Method - Visual
e29aeefb-88aa-5c48-a2fa-e5126b3b838b | note | Frequency - Each Fill Layer
1816ff78-c827-5edd-aaf6-1fe064e0ff67 | note | Category - IP
4503002e-98a8-518b-bd6c-6318830f38c1 | note | Responsibility - SE/PE
1654bd29-7401-596e-a7a6-967c88191ea9 | note | Verifying Documents - This Checklist
ffb122ea-e330-507d-bb1a-5cfcc445f3e6 | date | Date Completed:
| checkpoint | 4 - Wire Wall Soil reinforcements-Connections
ae02d538-801d-5536-83e5-22c001674688 | note | Reference - IFC Drawings
da2ac41b-8106-5882-bdeb-1874ee77ad41 | note | Schedule of lengths:
1512097a-f5cc-5046-a24c-cadc0a74dc7f | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1301, 1302, 1303, 1801,2802
aa53b998-c915-547b-81de-0181c78a7619 | note | Connections arrangement:
f40a33d5-e3f8-5011-a77a-3c2d48ecd6e8 | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1956
d6cc7480-186d-574f-a021-f3367a258427 | note | Acceptance Criteria - Grid Strips are to be installed to the wire facing units in correct length and to the correct locations based on the number of grid-strips.
16261944-b73a-5ff1-90c5-1b643239ec81 | note | – The first layer of grid-strips are to be ziptied or connected via hog rings to the facing units.
bf78e160-f0e5-5ab6-b13d-84fedf97607f | note | Method - Visual
ff507bc2-fdf5-5347-a1ab-db858ae698ba | note | Frequency - Each Fill Layer
fd23094b-1b9a-5b9b-9017-4da30e901502 | note | Category - IP
9e5bd7d6-9494-5c09-b174-02e7653c8be3 | note | Responsibility - SE/PE
bf174fe5-f75c-50b9-be9b-e38a97891276 | note | Verifying Documents - This Checklist
c19c7d90-c0e8-5629-8d0e-7d0db78604f7 | date | Date Completed:
| checkpoint | 5 - Soil reinforcements-Plan arrangement
a9242f7a-5dbe-5f17-b536-d12e7b6668f6 | note | Reference - IFC Drawings
6239cfcc-04d4-5eb8-9f61-a825daf3a627 | note | Arrangements:
78f118d9-e0be-5383-bff1-4ad8c8a58649 | note | ○ MRP-080-C-RFL-DRG-33-CPV-CSW-1101 to 1105 VR682.06
34e7e53a-d1bb-53c1-b8e5-5b7a3dad0baa | note | Acceptance Criteria - Plan positions of Grid Strips are to be as IFC Drawings.
47ae5370-8e3c-545c-ad98-9a42e04c2eb7 | note | – Grid Strips to be placed perpendicular to back of panel where possible.
e388c0d2-b118-58e7-89e4-2cd14ea5b2e0 | note | – Grid strips shall not overlap
aaf9549d-88dd-508f-9132-afd761374dd7 | note | Method - Visual
48e339f8-f315-5cdf-a18b-951e00856685 | note | Frequency - Where applicable
7475d940-d07b-525a-b793-14b035894031 | note | Category - IP
dd4147ad-0eb8-5f2d-b4fb-de145cd52d6c | note | Responsibility - SE/PE
4ee9b0da-1fb9-580f-8170-6ce722b30649 | note | Verifying Documents - This Checklist
b20afd70-bc10-5582-bd0a-aa4f99ca8e89 | date | Date Completed:
| checkpoint | 6 - Soil reinforcements-vertical/horizontal deviation
bd6bfa2a-bf95-5bd0-b13d-1d2040f18194 | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1101, 1901 and 1904
a38b324c-80c3-5aff-845d-92019781aea3 | note | Acceptance Criteria - Skew grid strips as required to achieve 100mm clearence from pile sleeves
871fd89f-e1d7-5820-a0d2-b85244a0b93b | note | ○ Where grid strips are in the same horizontal plane, ensure 75mm Min horizontal clearance between grid strips
70c56a87-94c7-5eea-ae3a-1c56f7315fc2 | note | Method - Measure, Survey
a6335da9-8bb9-5690-91c5-9094c7524c5f | note | Frequency - Each fill Layer
7d8933b8-f49d-548e-b1f8-9d8fe402a884 | note | Category - IP
55381383-bfe3-5575-84ff-fabb97918b4f | note | Responsibility - Surveyor/SE
69133933-a711-5956-b2ef-fb8067a5c1e9 | note | Verifying Documents - This Checklist
c72defd8-1804-5a38-8261-d2a249fc6941 | date | Date Completed:
| checkpoint | 7 - Soil reinforcements-clash with drainage
4f69f8a2-386c-5408-9571-7fcb1bf9cfa2 | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1109, 1901 and 1904
132f5f24-dd6d-5dd4-ab94-cc06c0097d2f | note | Acceptance Criteria - Avoid clash with stormawater pipe as per IFC drawings
8ffcc24f-0631-531a-a188-2f2afb7fbcbc | note | – RW02 column 1-27 and 30-41: Top layer of grid strips to pass over stormwater pipe. Other locations to pass underneath.
cbd65d2a-0ab0-50bc-b21b-ef312f3e5634 | note | – RW03 column 1-23 Deflect top layers of grid-strips below stormwater pipe at maxmum 1:3 slope, column 24 pass over stormwater pipe.
3875e196-6d6d-5e67-bb76-6e449a493115 | note | – Set Out invert levels of stormwater pipe before commencing straps and fill placement for RW02 and RW03.
fe05194c-4836-5f55-9446-4a2dd335fa23 | note | Method - Visual
612fc2ab-8236-5a11-ab38-b64a1fd99edc | note | Frequency - RW02 and RW03 stormwater and grid-strip interface
f23dfbe0-ef6e-5d5a-a618-5afca5e7307a | note | Category - IP
0508d2c8-9c52-5794-9e7b-c697a861ca01 | note | Responsibility - SE/PE
8906d973-dfb9-5c7b-bc86-1d011ea057de | note | Verifying Documents - This Checklist
c30a3bbc-b21d-526f-8f40-8d529d0cacac | date | Date Completed:
| checkpoint | 8 - Cobble-Placement
d130864b-f0a9-5685-9421-2f54b2d6babb | note | Reference - MRP-080-C-RFL-DRG-33-CPV-CSW-1955
48366bd2-a4d1-5c09-b829-510d3fad2ac2 | note | Acceptance Criteria - Cobble to be placed a minum of 300mm from face of wire basket
ce95bb0d-bd67-55ec-8e16-c3ea844d2cb1 | note | Method - Measure, Visual
9e358e6f-e6aa-51fb-83ca-48d1b3e47bce | note | Frequency - Each fill layer
85f3a64b-a862-5c46-93d1-c84e123cdba7 | note | Category - IP
3f8efc8f-23f7-5a57-8897-e9ba1efdc517 | note | Responsibility - PE/SE
a432700c-673d-5f4a-b144-44dfbf39f93b | note | Verifying Documents - This Checklist
ce050bd3-b30b-5da3-a7bc-c97fc5ab90d7 | date | Date Completed:
| checkpoint | 9 - Geotextile-Placement
f33b881c-2c55-51b3-b494-2ac23cad0376 | note | Reference - MRP-080-C-RFL-DRG-33-CPV-CSW-1955
b6dac1f1-0684-5ae2-bd78-dee06e52eded | note | Acceptance Criteria - Lay geotextile between cobble and select fill for full length of wall.
032b9fa7-32b7-5283-b708-80b8f2783d7a | note | Method - Measure, Visual
d2d2e750-6ea0-557a-a9bc-f06e98177424 | note | Frequency - Each fill layer
476981a4-2610-5ab4-bd58-032ad2dad45b | note | Category - IP
cf7a5c3f-2e6e-519b-8a25-b191fbac0b25 | note | Responsibility - PE/SE
7df2834b-b72d-5703-8628-54c8f89eab39 | note | Verifying Documents - This Checklist
585eb0c2-907a-53d0-9cb8-d173bd4cd167 | date | Date Completed:
| checkpoint | 10 - Fill-Placement
471b2c37-7c37-5544-9841-d8088539ddfe | note | Reference - VR204.10
0f09e942-23a2-5d8b-8cb5-b5a91088fe96 | note | Acceptance Criteria - Select backfill shall be placed in accordance with Vicroads section 204.
b567547c-eb3d-53a3-891c-22371361d944 | note | ○ Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
5354f0be-adc7-545b-9c65-2697c632a7c8 | note | ○ Fill dispensation to be granted by superintendent to increase thickness layers.
1b05b719-5726-54a2-a18b-aeed9adc5075 | note | ○ All RSS fill layers to be spread from face of panel to tail of soil reinforcing straps.
4766305d-fe1e-53aa-9d0c-b046df69e5cf | note | Method - Measure, Visual
7d45538f-da57-50cd-aeaf-8fc41f61639e | note | Frequency - Each fill layer
7209ead3-dadb-503f-924b-3d9cff0df53d | note | Category - IP
a5484e94-c6f4-5be5-9d9e-e4d42897386e | note | Responsibility - SE/PE
96be064e-d4b8-54fb-bc98-387e66b280af | note | Verifying Documents - This Checklist
534a3e6c-7bb7-5853-9b64-cf3dbcdbf6eb | date | Date Completed:
| checkpoint | 11 - Fill-Placement compaction
95e818d5-c4e3-529f-a3cc-9911463bc3ef | note | Reference - 204.111
fd364887-67be-5614-888a-429774bdff4a | note | Acceptance Criteria - 0 - 0.15 m Light weight hand operated DPU
47ad0faf-41c3-5794-a7d1-a7d289ecef62 | note | ○ 0.15 - 0.30 m Less than 5T Roller
7be34670-926c-5c11-be75-65860a33106f | note | ○ 0.3 - 1.2 m Less than 10T Roller
5a98d96c-914d-5e4f-91e3-6795b91d19e9 | note | ○ >1.2 m Less than 35T Roller
0aa3f36b-49f8-50b1-b190-d9a42288b12d | note | Method - Visual
26e19376-08ac-5af1-88f1-fc6b07b8e43d | note | Frequency - Each fill layer
baea6dd6-2f59-5cdf-8484-6a361e9a9f4f | note | Category - IP
ed113193-c55e-54ca-919d-5d0b3e572057 | note | Responsibility - SE/PE
265a7e41-7bc5-5d3f-9d66-f37daa4a005d | note | Verifying Documents - This Checklist
f0c967e2-572e-5c62-91b5-ed0767183116 | date | Date Completed:
| checkpoint | 12 - Fill Test roll
011fe456-bdd0-559f-a7e8-f748c1a28b06 | note | Reference - VR 204.12
082ed73f-d00d-5c11-8a92-0f1100b6da5c | note | Acceptance Criteria - All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
f1ceaa4a-09c4-54c5-be62-22f1a19c127c | note | ○ Static Smooth drum roller with a mass >12T; or
2a30f1bf-d0b5-57fa-8426-b1bba4f58154 | note | ○ Tandem truck or water cart with a mass >20T.
7b8a2758-d036-5d54-b609-f82ed26a2b75 | note | ○ No visible deformation or springing during test roll.
55e28608-5364-5408-97d8-3e1badeca676 | note | ○ Unstable areas rectified as per agreed method.
f2649f78-ae11-5dbf-b777-859228b8a552 | note | Method - Visual
46db0bc7-3913-56c8-a60f-9ea1dc4f448b | note | Frequency - Every Fill Layer
778ca5a3-d109-535c-aa39-695a1cd0a16e | note | Category - HP
f8e2bad6-3b67-5277-a524-66a4ae92de0e | note | Responsibility - Nominated Authority
bb0cb5fb-eb82-58fd-a740-5c92dceb1621 | note | Verifying Documents - This Checklist
d62caf52-98bd-56dd-95f0-6cd20e6927a9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Select back fill-Compaction Testing
3bbd2159-d374-53b7-b602-f198b12fd06d | note | Reference - IFC Drawings VR 204.14, VR 682.16
95cb8874-4f05-5117-917f-c20e8e1ae734 | note | Acceptance Criteria - Testing frequency shall be in accordance with Vicroad Specification section 204.14
b5ea2ff9-aaac-5ec3-8bfe-ca6f2142b477 | note | ○ Moisture content shall achieve minimum characteristic value of density ratio: 98%
ceb9f121-cb15-5bba-b1b8-2d66c1e0e7fc | note | ○ Moisture content of backfill shall be maintained evenly at all times. Moisture content shall be +0%/-2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content must be allowed to dry.
19acfb2e-e00f-5357-8983-76a46208e150 | note | Attach: Compaction test results
870fa792-e1b6-5423-b14a-537b5d8c35da | note | Method - Document review
6af77cbe-b281-54e1-94e6-92db214bb08a | note | Frequency - Each Fill Layer or every second layer as agreed
64a80d5b-fc90-5025-bd63-8424fea6fe0d | note | Category - IP
81d13e27-9ebe-50d3-8bce-9d3574831205 | note | Responsibility - Nominated Authority/PE
b91a40eb-f90b-5faa-9bd3-e2e032a94470 | note | Verifying Documents - Attached Test Results
9b40d4b6-62af-5520-ba03-e814bfee8ed9 | date | Date Completed:
| checkpoint | 14 - Select back fill-Test frequency
d271d5b8-b2cc-5561-89d1-30058465d0b9 | note | Reference - IFC Drawings VR 204.14, VR 682.16
d04e6c7a-0139-5860-86b6-fb9133944053 | note | Acceptance Criteria - After three consecutive lots of like material have achieved the specified requirement, reduce frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
5e7169ec-7654-5c5b-93fb-74c40727cade | note | Method - Document review
eea5eef2-66e0-5f80-a84a-10fa3cb5e273 | note | Frequency - Each Fill Layer or every second layer as agreed
af9a6bc8-2582-549a-9721-fd2971a6562a | note | Category - IP
1abee40c-62c4-5798-8fde-cf0481b813a1 | note | Responsibility - Nominated Authority/PE
04c938de-8deb-52c1-8b50-e18f51fb7e2a | note | Verifying Documents - Referenced Lots in This Checklist
b605e041-c5cb-587b-8a3c-ad0fec0e1bd2 | date | Date Completed:
| checkpoint | 15 - Survey Conformance Asbuilt
1e027606-a4df-5fe0-b108-efa459bcd56e | note | Reference - MRPA Quality Management Plan
e0bc5b00-8a0f-5bad-96c1-5c94cfaf9189 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
4a50c9a7-72e3-5c29-9796-8c7bb3db70e1 | note | Method - Document review
fe66ba3b-3e55-5164-a559-d7ffd528a29b | note | Frequency - Each Fill Layer
ebcf7edc-fa10-5ebc-af9e-98d803080b80 | note | Category - IP
b05ef320-b1b3-5610-8f81-f636f80d97f0 | note | Responsibility - SE/PE
4fea5c88-2792-506d-bd65-3b42a285ba50 | note | Verifying Documents - Attach: Survey Conformance As Built
af89178e-08da-5a57-983f-17a91c7c2e6e | date | Date Completed:
| checkpoint | Final Inspection
a3a59414-d8bf-5eab-98c5-136b2bf13b5f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
72473e6a-d86f-51db-aab5-ee7ed0f7b596 | textbox | Name:
f183d421-b4c1-5d76-818e-cfb6111f09fc | textbox | Position:
1fdfdcc1-e2bb-5ee5-b38b-45469fe422aa | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | itp | CHK-010-CIV-CPD-Wire faced wall Installation | 7b8afe80-1608-43c5-8a6e-b6353d90782f
| checkpoint-no-value | Referenced Documentation
fdd374af-847a-5f33-b017-e4483e5d7aa3 | note | Document Title: CHK-010-CIV-CPD-Wire faced wall Installation
1057eb5e-31d7-5a09-beb3-01bcd50101e1 | note | ITP Description: CPD - Wire Faced Wall Installation
f8ead154-fb53-5746-aad4-91427d843f75 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
220a7ed1-35a2-5f8e-9b55-40b30ebf2ccd | note | Discipline (e.g. CIV/STR/RAIL): CIV
11c08af7-8314-53c7-98a3-959b0de8f1ee | note | Revision Number: 0
b0f7bf73-c5cb-5755-9387-2f8c6abb48c5 | note | Revision Date: 1/12/2023
5958646a-cab0-5910-acbd-4d0cdbd190f6 | note | ITP created by: Matthew Dib
7bec2bca-798e-5ea3-afe7-8b87e42b10ce | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1 - Wire Facing Units-survey set out-Tolerance
1b752fad-8cb2-5d55-af6f-8a4d5b05f580 | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1201, MRP-DPK-080-00-CSW-0033-0-1206 VR 682.20
68982d74-a860-5fc3-8d3d-9742aef53968 | note | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
46317428-c782-5d63-9a7c-0d0dc811f7c9 | note | Method - Measure
3d45eb0e-ea66-566e-bd0e-08d1050521a9 | note | Frequency - Base course units
565e0fda-3b51-5883-8d8b-f9c115f88874 | note | Category - IP
c3752e6d-5fcb-5c92-a060-087b7bf7d7d3 | note | Responsibility - Surveyor/PE
881d800a-c1b7-5d7d-b23b-a5ef0cbb0550 | note | Verifying Documents - This Checklist
bef1d5b6-a514-5674-8a3f-371f0848c876 | date | Date Completed:
| checkpoint | 2 - Wire facing installation
aed0dcb6-b869-5b3e-821e-ea0a9d4c03c2 | note | Acceptance Criteria Wire facing units are to be installed as per IFC Drawings and specified schedule.
a0e439e6-7da4-5018-9b13-ced43fe0b084 | note | – Connect adjacent wire facing units with stainless steel zip ties
3534ffa6-c3b0-5088-bb61-4cc122d6bd92 | note | – Attach grid-strips at locations shown in Drawing 1957 for appropriate quantity given in elevations. Bottom layer of grid-strips to be attached with stainless steel zip tie shown in Drawing 1955
a6717d77-d9c9-5959-a181-f9401e838601 | note | – Cut the half-height panels at top of wall to correct height (refer Drawing MRP-DPK-080-00-CSW-0033-0-1953)
ca600287-a9c6-5937-90d2-a7a9024fae50 | note | Method - Visual, Measure
aba8e130-c8c8-513c-9f8b-32c643fafc5d | note | Frequency - Each wire facing unit
8b8941bd-1d79-5b91-a0d8-a0b9ea6378ab | note | Category - WP
1c1a6c28-9d11-531c-8ebc-e771ce544c3d | note | Responsibility - SE
2d407d1b-29a5-5517-8615-67b28ee0b0ff | note | Verifying Documents - This Checklist
289f1b67-9f75-57fc-83b7-416227854f45 | date | Date Completed:
| checkpoint | 3 - Wire facing installation-Abutment interfaces
b7b18c69-98da-59ee-823a-20451a13ae4e | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1106
d186c03c-0309-50bd-bedd-cda1d9e61471 | note | Acceptance Criteria - Cut any transverse wires as required for bends at abutments and wingwalls (refer Drawing 1955).
8808b7ba-2b6c-541c-8e7f-62c8979eb08c | note | – Wire facing unit to be in contact with rear of panel (RW01) and side of wingwall (RW06).
d3a8c469-4a52-5fbb-a5b7-7cac30e4a1f1 | note | – Geofabric to extend along abutment as shown in Drawing 1106.
96c819ba-6583-52e4-b718-646882d3fab1 | note | Method - Measure
e5a2f0ed-66d9-5191-a385-006df302b277 | note | Frequency - Where applicable
766a1370-ebbd-5e0f-a7ce-966a0d786d66 | note | Category - IP
0b850fa1-d911-5394-892d-c4c84b03de23 | note | Responsibility - SE/PE
8101c466-4f5f-55ac-a225-08cbdb3a0c8b | note | Verifying Documents - This Checklist
170cb56a-c5e8-5a7e-9fa1-4af5330302da | date | Date Completed:
| checkpoint | 4 - Geotextile - Installation
dcb48184-e5a0-521a-a23f-edce0e2ca93f | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1955
bebb6fbd-f2ff-5184-aeaf-1c13d259dbdd | note | Acceptance Criteria - Install geotextile between cobble and select fill for all panels
18b4fbe6-22e7-590e-95a7-459269d5870b | note | Method - Visual
e814c9cf-ad1a-5343-9b84-fab885468a92 | note | Frequency - Each wire facing unit
56218383-32a8-58af-9e92-12a83001c56c | note | Category - IP
36b6e610-b35d-5190-9af5-499009e2346c | note | Responsibility - SE
dc7303ab-68c1-5619-a7cf-db2634b3283c | note | Verifying Documents - This Checklist
6a55a9a7-7479-5c4d-9358-61a1f492b0c5 | date | Date Completed:
| checkpoint | 5 - Wire facing installation-Survey reference points
c2e20c05-49c3-5306-9234-3c585ccf0c30 | note | Reference - VR 682.21
12f406ff-24b5-5cad-abc6-25d821ed3e24 | note | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
8c2859f4-818e-5146-b379-fb8803854d67 | note | Method - Visual
7294b8de-8dbf-5bf1-a752-f4af36861589 | note | Frequency - Each course of wire facing installation
0cc5ccf9-adec-57a0-abfa-83e9a25f21db | note | Category - IP
5b73fefc-8dc4-5ac4-80e6-0f86f5071003 | note | Responsibility - Surveyor/SE
7c414f4d-c7f3-5394-8b1b-211a14043c77 | note | Verifying Documents - This Checklist
10339e29-68d5-5eb6-8428-cf904c4af324 | date | Date Completed:
| checkpoint | 7 - Panels installation-Conformance Survey
5dfd4f02-59fd-55e0-930a-c94d9e02664c | note | Reference - IFC Drawings VR 682.06, VR 682.17, VR 682.20
f15c3a06-472c-5f8a-a583-5ded4e2a9024 | note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
75851f61-8154-5f71-8226-548b19ae8bdf | note | – Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
0f9c6e11-224c-564c-b647-feded3678f46 | note | ○ Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
7c47e8c1-3781-5d4d-a72c-6cb7cdfba77b | note | ○ Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
66facd51-f982-52c6-89d7-8ac691c5e741 | note | ○ the wall level shall not deviate from the specified level by more than ±20mm
7b18faf9-d6a1-56c8-88c6-12718b75b6bf | note | ○ the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
63e6d3ee-1955-5c06-b4c0-a8d83c1e56c5 | note | ○ The wire facing walls shall be vertical when measured at the corresponding point for each row of wire facing units.
eeea2d85-6939-525a-937e-ab5f4f5911c3 | note | Attach: Survey Report
1ee148f2-f150-5e24-93b3-30775fbc153a | note | Method - Survey, Measure
8b6de733-36b0-5727-8624-3119ad22972b | note | Frequency - Each course of panel installation
ed4a0d08-201f-589d-94f6-371fd840f3df | note | Category - HP*
775d7948-11c5-5c6e-91a3-2dc9c9fe38ad | note | Responsibility - Surveyor/PE
1ab680d5-0b9d-5d0e-b467-fbb2b7117eae | note | Verifying Documents - Survey Report
37993514-6637-5985-8845-a4156a48dcb8 | date | Date Completed:
| checkpoint | Final Inspection
14f481db-ed7d-5c6c-aa54-454d61efb091 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
92f87b57-45b7-53a2-99da-6aac87fb1a0b | textbox | Name:
53d99209-d921-5bd4-9926-2ec6a807d604 | textbox | Position:
880fc71a-1b50-5262-ae16-30a96f01d413 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-009-STR-Bored Piling - Rev 0 |  | ITP-009-STR-Bored Piling | f3d066a9-d57e-4e39-94c6-6e609efce0b3
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
70deff00-e4c2-5484-ae92-ce89f855f706 | note | Document Title: ITP-009-STR-Bored Piling
6ef3d51e-9fe2-556a-8294-ab785c5c5ef3 | note | ITP Description: Bored Piling
bef5ddca-cda4-5034-803c-f21f973ef84f | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
639ee6a9-c63f-59c1-952b-9d135eea4666 | note | Discipline (e.g. CIV/STR/RAIL): 009-STR
860a3bb4-6b87-5525-8dc7-bf3d68f15b2b | note | Revision Number: 0
4f49a0fb-0218-59fd-afc2-d3df71a80909 | note | Revision Date: 11/10/2022
| checkpoint | 1.1 - Non Dependent
641b35d4-14be-5196-9ff2-697557431081 | note | Reference - VicRoads Section 606 July 2017
| checkpoint | 1.2 - Non Dependent
688df7bb-a8eb-5248-b79c-433c1ac166e0 | note | Reference - VicRoads Section 610 Feb 2020
| checkpoint | 1.3 - Non Dependent
d844f97e-6b2e-50a4-953b-79581650df4b | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
6d361911-ccfb-5caf-b282-9738c4ec2344 | note | Reference - AS2159-2009
| checkpoint | 1.5 - Non Dependent
7e8c2ef8-8d3b-537e-a808-9adb584b8ff2 | note | Reference - AS3810.1 2018
| checkpoint | 1.6 - Non Dependent
2825e1fd-2eda-5103-8318-b27132c0dddf | note | Reference - AS5100.3-2017
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
c46bd9d7-05b0-508e-96b1-9ca3e995e7fe | note | Reference - 610.07 Table 610.071
185f114c-5b6b-5bec-a0c6-061dd78339c6 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
164ddf8d-41d1-5961-a707-c3fab2c53837 | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
afb43345-92dc-580d-a184-6db0f897bbc2 | note | Enter: Teambinder Material Approval number
933742c4-77c8-5fef-bd7e-90a47db67028 | note | Method - Document Review
9db5dc46-e510-5161-b166-23ce1253f146 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
c3f17396-fa57-5f6f-b603-aaf766e16b57 | note | Category - HP
c96a2fc7-df6c-56e8-959f-144173db2238 | note | Responsibility - Nominated Authority
9695e915-0047-5bb2-9a8a-7c18f9f9e0d5 | note | Verifying Documents - ConQA Hold Point Release
a89b79c4-9756-5dda-9a87-cdef5f74787e | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
4cc5f199-c03a-5e72-a8ef-352c00bd512d | note | Reference - 611.05 (a)
94a8981b-4bf9-50e2-bae6-ff07e803187d | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
011d8146-4fb6-51cc-bad2-d2ff81f2e864 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
0fb27cfd-0607-51b7-a607-b0ef4e127d85 | textbox | Enter: Teambinder Material Approval number
938994a9-054f-5094-8726-6bbe98201695 | note | Method - Document Review
1c31a660-6966-5344-9c4f-cba319bb014c | note | Frequency - Once for each supplier, 14 days of award of contract
0e570fdd-4672-52d3-b407-3cb16acd2439 | note | Category - HP
a738ab58-d089-542d-b6fe-7fa8022305d8 | note | Responsibility - Nominated Authority
61990dc4-580e-5172-b067-b1caf9b21a39 | note | Verifying Documents - This ITP
7e53f986-a668-5c08-8c75-3939f230d273 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
4b4e101f-dd88-57f3-bf25-ba9a0a8b81b7 | note | Reference - 610.26 (a)
a9dab2f2-d03f-5aa4-9b65-29a5c206ca08 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
6f95c768-3e5b-5478-aa66-85c452a3f9a4 | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
015cc1d4-2424-5230-80b5-430111a6f273 | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
a8c2ac94-488c-5531-9527-da44b2d85ca0 | textbox | Enter: Teambinder Material Approval number
5204e8ac-9d63-5dbb-bdf1-0fcb4a741237 | note | Method - Document Review
4c038cca-5d51-595c-ab2e-78f821ee5ae2 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
5a1ae7af-5cad-5a6e-96cd-cd827393de5d | note | Category - HP
6ce6ae7f-b307-5cf3-a6d7-8303a3d595ae | note | Responsibility - Nominated Authority
ac2a7554-1ed5-5e09-98f1-94e293d0cc98 | note | Verifying Documents - This ITP
2108ce6f-1d9f-50e1-93ce-7d78dba01652 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Working Platform certification
5e9eb1b0-511b-5d80-8e64-0ec00e5e4658 | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement
494d1fa2-fa0b-5ca1-88f0-9c935222cedf | note | Method - Document Review
4f5c9553-289e-57a1-b8b7-3706ec7110bc | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
22895676-31fe-5d9f-bf96-ec9c72c87330 | note | Category - HP
33372c2a-3842-5baf-95a2-11de3bc87e1f | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
5a0f0ff1-d1c5-5510-ace5-94e24fc6ffcd | note | Verifying Documents - This ITP
a6b9ef00-968d-5a0f-8e19-43b7423f9eaf | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Piling Operations Work Procedure
19a55fbc-dd2b-5e43-aad5-cb8286214c24 | note | Reference - 606.03 (a)
5d33d674-711f-5b46-9fca-cdb73ff2f722 | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
4a84677a-2aeb-53a5-a9c4-fdc51470e70b | textbox | Enter: Teambinder Approval number
866b9f2e-c337-5de2-857f-7dd9705b6c9f | note | Method - Document Review
a08d7c62-0f9c-5982-95f9-b7a5ceffd854 | note | Frequency - Once, 4 weeks prior to the commencement of piling
f2861df1-b38a-55f2-bc3e-d3e3128ae5fe | note | Category - HP
fdbbcb31-8dc9-521a-9eb8-3261bbbfdf2e | note | Responsibility - Nominated Authority
ceecfde2-b5c4-5f57-8128-74741d275694 | note | Verifying Documents - ConQA Hold Point Release
baf340be-13c1-50e6-b49b-fb6eddf4f679 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Temporary Steel Casings
77d2711e-9d3e-5192-af59-d6179c19e73a | note | Reference - 606.03 (b)
6440ac1a-e921-534d-abdc-a2146d66fc61 | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
dbdfafff-e0dd-5d58-939e-01d242b467b3 | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
22a2dc1d-4ddb-5a6f-9ae9-a137410c89d8 | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
5fb88094-f5f8-5c32-a09d-5fa5167aed40 | textbox | Enter: Teambinder Approval number
577d364d-c460-5819-94f2-8910f8732b25 | note | Method - Document Review
e299dbae-04ee-5664-9bf9-2c5b887ed961 | note | Frequency - Where applicable, once, prior to use
5d0ac6da-bc19-512b-9089-c92ed9e09e89 | note | Category - HP
f9edf96a-0573-5651-8270-ee8513307f77 | note | Responsibility - Nominated Authority
ab9dc98c-4c75-5a4e-b937-606cede89cbe | note | Verifying Documents - This ITP
cfc155bc-89f9-54db-8532-9f758223ce3d | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Casting Under Water Procedure
852e7a91-dea2-5743-9462-418af568d3e8 | note | Reference - 606.06 (a)
29bbb10c-7542-5463-9cea-0407c6bfcc54 | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
050db3af-735e-55f5-be20-908bf53978cf | textbox | Enter: Teambinder Approval number
4edc7f83-d45d-55f1-a78c-3265d6768512 | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
2c872037-2fe0-5ffb-b145-182ee38a55b4 | note | Method - Document Review
bc553972-ecfa-55d0-8ae9-0ff524eb9605 | note | Frequency - Where applicable, once, prior to placement of concrete
5161391c-98fb-5ed3-bac7-8c5103153287 | note | Category - HP
d80a3d1d-c769-5a30-bdac-84b2651b044a | note | Responsibility - Nominated Authority
0094db76-fda0-56a6-877d-be25ec9fd212 | note | Verifying Documents - This ITP
a08ad46a-8b0e-553d-9edf-bda6a50edae7 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
5393e021-cd75-583e-a782-6b15e121a60f | note | Reference - 606.03 (c)
fc93b65d-002b-574d-93fa-3136837fdb7e | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
bff898b9-ed74-5381-843f-8159e1fe39a1 | textbox | Enter: Teambinder Approval number
82b07a35-6b70-5477-9b5f-358a870b4edb | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
78dd738f-5ef3-5da5-9d27-0e6878ec613b | note | Method - Document Review
55eaf5ad-5db1-5bbe-8f1a-3b44437a67e9 | note | Frequency - Where applicable, once, prior to commencement of boring
6467ca66-604d-58f8-bbcc-7496147a68b3 | note | Category - HP
b4a7ffdb-062a-50b3-a365-5f8aaec24f8f | note | Responsibility - Nominated Authority
8bad09d6-6992-5793-a403-f6a01179f00e | note | Verifying Documents - This ITP
1ee2689d-c5b2-53e9-8eea-287ecc10a9c2 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Dynamic Pile Testing Procedure
47d0d2dd-f141-50e9-893a-486d315f573e | note | Reference - 606.07 (c)
86c4e241-a19d-5754-a1bc-8b727c439f1b | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
2e9891f3-0500-5ccc-94c3-77ff34e4ea2e | textbox | Enter: Teambinder Approval number
e5c65b1b-c547-5fe1-8dd8-c0cbb9e9a8ae | note | Method - Document Review
d48a7568-8dd1-51d0-9091-eadc43c55bff | note | Frequency - Once, prior to testing
206b1981-f9f1-5a8b-b255-36de0579ecd9 | note | Category - HP
d41faa86-651c-5914-8d47-4a90819b78c1 | note | Responsibility - Nominated Authority
634a2276-807a-5e49-972b-1d9aa9d59853 | note | Verifying Documents - This ITP
c9e65f2f-caee-59df-b466-d261f8c584d0 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
41e19f97-beb6-56cf-8439-02cfa696181e | note | Reference - 606.07
50586dc0-a8c8-5aae-8351-6ee554fc903a | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
f30dee24-1fc1-55a6-960e-298b00715a59 | note | • Details of the consultant to be submitted for review to the Nominated Authority.
d3365d35-913c-572b-82ac-ee3f0b0c1696 | textbox | Enter: Teambinder Approval number
3d253a86-0f84-53bb-9f2f-379e4c212136 | note | Method - Document Review
41e0f3d7-f5f9-5824-85f3-c7dd51e1e355 | note | Frequency - Once, two weeks prior to testing
5c1e1f2e-6674-5bb4-90b9-a67124d3149c | note | Category - HP
394fa4c9-64c5-5880-a11f-cb15eaa8f22c | note | Responsibility - Nominated Authority
895ba038-c9aa-575a-912e-6feebeebc3c4 | note | Verifying Documents - ConQA Hold Point Release
29565947-b1d9-5ab1-a932-52f289942255 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
cb2c9e3b-1700-58be-a0f8-ceda08077c88 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
94182149-cf10-5286-a001-a167a2871ae2 | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
ee91287b-88ea-5930-80d8-6eb5b764913f | textbox | Enter: Teambinder Approval number
c2ea2cc6-15f9-5c16-8ba7-5f204921e47e | note | Method - Document Review
5979b1b9-0f14-5ffe-b3fb-507b72c2d038 | note | Frequency - Where applicable, once, prior to welding
65b844cc-1d90-59e3-a6b6-1e1aefdf02a9 | note | Category - HP
6c593126-2fd9-537b-ac35-0ce3bc981105 | note | Responsibility - Nominated Authority
3154af69-03c7-5e1e-af72-d4cf823a8fd2 | note | Verifying Documents - ConQA Hold Point Release
6674978b-4b73-5efb-96d6-bec603d11782 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
5bddffc5-0d1f-5633-935f-483d48084536 | note | Reference - MRPA Quality Management Plan
e57f53bb-dba1-5cb9-a8fd-94cb03369afe | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
183688c3-b5e2-51b5-a1b1-9848113ceb91 | note | Method - Document Review
29a7dbbc-0394-509b-b062-c10ab9b8f751 | note | Frequency - Prior to starting Works and at regular intervals
1a8d4338-2622-5605-a6ec-b22b41159907 | note | Category - HP*
679f47db-c605-599b-8063-7160b387eaa9 | note | Responsibility - All
c1f7601f-22d5-5f99-9427-6dfed845c4a7 | note | Verifying Documents - This ITP
7dd0fa56-209a-5b32-972a-74dfc35403ae | textbox | Date Completed:
| checkpoint | 4.2 - Survey Set-out
dd1b7f7f-26fc-5034-b4db-cef8fc49d576 | note | Reference - IFC Drawings 606.08 (a - c)
b4a06923-68a5-5301-adbd-04ed86486c0c | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
ab482f12-f23a-5e36-9701-cfe4ea38fdbe | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
90842512-57ca-5ee2-a8e5-506301e115a1 | note | Method - Measure, Visual
7822bc61-0ca1-5efc-9f1a-1ac0daec2a91 | note | Frequency - Each pile
0815d47a-3087-585e-9ed6-c4fcebced536 | note | Category - IP
83edb9a1-d6c3-5744-993f-5593f684c40f | note | Responsibility - Surveyor, SE
68aec104-2401-5567-af27-6fd7bac18ec6 | note | Verifying Documents - This ITP
665d69ce-ba28-5078-82cc-c3a0a0ae7798 | textbox | Date Completed:
| checkpoint | 4.3 - Protection of Adjacent Piles
787cfeaf-2ba3-5868-af07-83837ca91f1e | note | Reference - 606.04
168813c7-0d42-51e5-af7c-a9530cd5b6df | note | Acceptance Criteria - Pile construction shall not:
e814fc41-5f5c-50ad-ab08-ce60988e6e8e | note | i. result in damage to adjacent newly cast piles due to ground vibration.
09e24af0-9a2d-510b-92ef-82f8fc3c93bf | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
702f700d-8128-59a6-81be-070636581710 | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
4c777e02-8960-5f31-a13b-407c4a89ec01 | note | Method - Measure, Visual
6d96d74f-777d-503e-960f-178e94bcbe8a | note | Frequency - Each pile
7d6589a7-1981-5f76-ae41-99e2700b7230 | note | Category - HP*
e35a8016-ea0f-5b6b-83c8-08df39f3cbab | note | Responsibility - SPE/PE
24bcb744-d085-5b84-aae6-38c61a371d77 | note | Verifying Documents - This ITP
4e2e5597-d0b3-5506-b107-5c1efb7a0f8c | textbox | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Boring Operations
2e0e66ae-c32c-50a2-9260-637225c508f1 | note | Reference - IFC Drawings 606.03 (a)
19e7bed7-f446-5330-8abb-c97c6e810bd1 | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
b52cd620-5e74-5166-b404-cd3297d5d3de | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
3999ddb6-e160-5ed2-ac55-0fdee1019f58 | note | • Excavation clean and de-watered (where applicable) for inspection.
869cc012-f33f-57b2-ba30-ad6b0b9792bc | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
2e2646fe-8a7d-52e7-a31a-eb3089acf99c | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
ff74b51f-39bf-52dc-b89c-ff990d2bd686 | note | Method - Measure, Visual
f4e9d4c3-6bfb-5f0d-83ca-5a4cdee92bc3 | note | Frequency - Each pile
ecd4d15f-a7ce-5d6b-8905-60951373b4b6 | note | Category - IP
ad9ce876-6f2c-5960-a267-f3edcdc416f8 | note | Responsibility - Surveyor, SE/PE/SPE
4ecc093a-56a1-51e0-9911-5208d694b2a7 | note | Verifying Documents - This ITP
4ccce1e1-f277-57d3-9f68-042ba7140e83 | textbox | Date Completed:
| checkpoint | 5.2 - Formwork Extension
8bc3c99f-a4be-58bc-825a-d30f52db1633 | note | Reference - IFC Drawings
5a2444e8-9cff-50c8-8e13-e9d2f94b43a1 | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
56843e52-2052-58eb-807f-3a3a2e546788 | note | Method - Measure, Visual
671aa1a0-9623-5ee6-b3e5-a882f5e63a3c | note | Frequency - Where applicable, each pile
6923fc64-35a9-5109-9a64-8f1aa261e634 | note | Category - IP
995e5b4d-09e8-5410-9972-87d31c5719ac | note | Responsibility - Surveyor, SE/PE/SPE
27027c48-f2b0-5454-965a-1dcfef2e3b1e | note | Verifying Documents - This ITP
c1724e1c-1ee9-55bc-9809-fec4a5ebbfb4 | textbox | Date Completed:
| checkpoint | 5.3 - Inspection of Pile Excavation
6c86c6e8-85a8-5a5a-95b3-982af1ff16e5 | note | Reference - 606.05
92bc4419-fef2-5e48-a1ef-5b7fffd3524c | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
50beec26-9707-5195-b9d7-918807941c84 | note | Attach: Geotechnical Field Sheet or Report
dc445c7c-26bb-53a0-aff0-549cd7a08960 | note | Method - Measure, Visual
5e4d8257-be18-5544-ac47-4a6af400b582 | note | Frequency - Each pile
ee751d8b-4777-52df-b2dd-01b7436fc707 | note | Category - HP
6b17c0a0-2bb0-53e4-84d9-3acbc92c9687 | note | Responsibility - Geotechnical Engineer
a7f1be9f-b758-5fa3-bdf0-1579c5ed739d | note | Verifying Documents - ConQA Hold Point Release
fddf5e1f-50dd-5dee-a133-2ec2d4fe7992 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Reinforcement - Placement
c0d5509f-4c0e-531a-a927-98dbb33d5f89 | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
2b6f02f2-d59d-5539-9783-b265089ed39a | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
0c77b42d-05a8-51d4-a265-bc7b3883b143 | note | • Projecting reinforcement is the correct length and location.
383015dc-0157-5ded-bfdd-39307502e1e1 | note | • Splice lengths achieve the minimum length and are in contact for this length.
cb8f452b-8007-5249-9ee6-caa3d548a142 | note | • The reinforcement surface condition is free from dirt, debris and damage.
8f0409b7-c1b2-5840-92e1-e305cc640c5c | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
a637e21a-5b15-5414-aad3-ae9fcc1ea38a | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
4a1ce2f2-a6f5-5f51-9ea0-bfa1f238cc49 | note | Method - Measure, Visual
b9d48af2-cde8-58b0-90b8-949778b26041 | note | Frequency - Each pile
edc011a1-da90-5f57-9fda-4152e220188c | note | Category - IP
d7686d48-67b7-54eb-8b92-fa70c8999f15 | note | Responsibility - Foreman, SE/PE/SPE
7ab39a4c-15e9-510c-b9ce-5e2f3e01ce09 | note | Verifying Documents - This ITP
23814118-bfbc-5b8d-937f-58ad6e70f9b8 | textbox | Date Completed:
| checkpoint | 5.5 - Reinforcement - Electrical Continuity
8f5e0c62-f8f8-5f5a-8ae8-6e023530a64d | note | Reference - IFC Drawings 610.29 (d), 610.43
b8773b64-bab6-5f8e-a7fa-2539cc80e44c | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
ce190e68-f8c7-5648-bc21-64be9ede9d75 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
45cde450-090f-5728-885b-c36a56742954 | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
d18e43c8-dceb-5512-8dd1-d5d9f70160f7 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
4d6d29e3-aa8e-57c4-8d40-5bb2cac575c6 | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
56ef2b2d-13dc-57ff-9827-96b3bd1c06e5 | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
11652ba8-4ccc-5fd7-a877-520b19693dfc | note | Method - Measure, Visual
14167044-8b7c-59df-9635-a3041ceeff18 | note | Frequency - Where applicable, each pile
e76a2cf0-6667-54df-bcaa-460875c24d3a | note | Category - IP
1ec6c1fa-5f1f-505a-af05-7bb51d3c509d | note | Responsibility - Earthing Engineer, SE/PE/SPE
989b82f4-eae5-5a1a-9dfe-a93e01b6f259 | note | Verifying Documents - This ITP
5f41aa10-3720-5cfb-94d2-8a69676507a0 | textbox | Date Completed:
| checkpoint | 5.6 - Cast-in Items
19f8fcde-a882-5eaf-b154-5a430baac213 | note | Reference - IFC Drawings 610.46 (a), Table 610.462 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
5b735a64-8d4e-5786-af63-168b596f6655 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
21f9ca48-9872-5124-a6fb-2d368a4c856b | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
dcd7de38-1ba1-5b65-8ffc-da15a16d1b66 | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
f67d5f75-a150-5602-8fb1-3eb71cd54e37 | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
7d264d81-7d6d-5157-b6be-7ea9f59952bc | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
2d205eaa-e326-51e5-b6c8-2a65aebf73d6 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
fb88f485-72c6-5f5c-9f8a-8904948b9f15 | note | ii. Running dimensions of a group of the above = ±6mm
8e26a7f8-8e77-5389-94f3-06cb41fae72c | note | iii. Ducts and conduit location = ±12mm
e472e455-b7f2-54ef-a3ec-504f10280c21 | note | iv. Diameter of ducts and conduits = ±3mm
8efb410c-2531-5ec6-a9b8-2c988fc93014 | note | Method - Measure, Visual
403cda94-2204-5db9-b482-94f481400f40 | note | Frequency - Where applicable, each pile
513dbd4a-fef4-5d4f-8c58-931b67fbff50 | note | Category - IP
a1dcdd77-54f4-5636-8987-d7b37b89eef9 | note | Responsibility - Foreman, SE/PE/SPE
f8d710ed-8097-516d-9a21-7f3bdc51bd62 | note | Verifying Documents - This ITP
d26079d0-d158-5b26-b1eb-7e50c346cbf9 | textbox | Date Completed:
| checkpoint | 5.7 - Pre-pour Inspection
26a05ffb-c0d1-59a5-8234-ec521a909376 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
b31d5516-867e-57f1-9e0e-a0619547e9ee | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
154049df-8f96-5e80-b398-68576561b0b8 | note | • All foreign material has been completely removed from the excavation.
ad23c896-9c1a-5c4b-a984-897e77d4d922 | note | Method - Measure, Visual
d13d6261-fcfc-5954-b4ae-e6f6781fcbaa | note | Frequency - Each pile
b2a6f744-3450-5403-9a2e-e969a9247d84 | note | Category - HP
ac8fd46f-5541-583d-ac63-46d9f7013710 | note | Responsibility - Nominated Authority
7afe085d-1a52-56ff-9fef-5f6c40e3fd52 | note | Verifying Documents - ConQA Hold Point Release
64d68c03-43eb-50f2-87cf-81af218a0c68 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Weather Conditions & Evaporation Limits
01c37bf8-1a5a-5ac1-8b77-0bd744e0e3c4 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
d455a339-9141-579b-95ba-029c5a5a11cc | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
7df65bd9-783a-5200-9181-2cacc8b19310 | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
841b0326-ba53-5167-a1ca-8489ac2871e6 | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
0d8c9813-1b1a-5f21-a70c-147aae31ac32 | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
57eabf29-3c98-5d7a-9bc8-4b3a2665db69 | note | Record: Required information on the Concrete Pour Record.
b0182d67-8a7e-5b27-aa05-49c40d409a3e | note | Method - Measure, Visual
3af144a4-d2b7-5d75-8941-0ca826dfbe19 | note | Frequency - Each pile
addb3a1f-970b-5a4e-8801-cec383bf9347 | note | Category - IP
2a572dfb-41f1-53be-b5c5-14e8fe2ad5d7 | note | Responsibility - Foreman, SE/PE/SPE
be616ec0-b313-5b9e-82f1-7e021247037b | note | Verifying Documents - This ITP
5736ff18-b456-5dd8-a998-cf60bf5f83e0 | textbox | Date Completed:
| checkpoint | 5.9 - Concrete Testing - Sampling Frequency
a8ac749e-48eb-5176-b330-80d8cfbaba0f | note | Reference - Site Sampling & Testing Procedure 610.16 (b) Table 610.161
a428b53c-a748-56ab-97da-8e710c088066 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
01f9ecb5-16cd-57d9-bbbe-3652617482e3 | note | • 0m³ to 10m³ = 1 sample
97489ab9-c01a-5629-8517-f1b6c27fc659 | note | • 10m³ to 25m³ = 2 samples
40293a3c-ec10-52b1-8137-080e66348e8f | note | • 25m³ to 50m³ = 3 samples
0c797d15-bb8b-5650-95ae-7898de01b38c | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
ae5a7495-ac36-5427-bd47-ae625bca663d | note | ○ For each additional 50m³ and additional sample shall be taken.
41c629b4-658b-5ebd-a19e-95d208d178bd | note | ○ where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
3186641b-5786-5247-9f88-ec278a0eb7b3 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
0d507ecc-5efb-5682-8c5e-de25d351f8c1 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
5ab32254-0f39-5a55-b936-924da5a63a4b | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
224d93ee-e6a8-5d6f-84eb-8f5186430cb7 | note | Record: Required information on the Concrete Pour Record.
1cc8f27b-8ce2-59f5-8e6d-80f15969bd59 | note | Method - Test
564d1b74-88b4-5104-8105-4b00708d7727 | note | Frequency - Each pile
a0de3e8c-6078-5cf5-bb5d-221adf0f7899 | note | Category - IP
dc7ddb89-6456-56c9-bb4f-2729533af90a | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
259aec42-9d3b-5f9e-9783-8a08079be40f | note | Verifying Documents - This ITP
e61c9fb5-3de0-5af6-bfe2-3d78396f4c37 | textbox | Date Completed:
| checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
c50304c0-a508-58ea-8ae1-3e9bbc15a952 | note | Reference - 610.13 (b)
cea33701-f9cc-5a83-a318-f6b6319fbad5 | note | Acceptance Criteria - Spread range = 550mm to 750mm
2395d27f-fdf2-59aa-b7f0-268cdc489bdc | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
a010b04c-6d28-53a8-aedd-732d9456fee7 | note | • Passability = ≤10mm (aggregate height differential)
d1d80c52-2a39-5002-adf6-b1b8552f7d21 | note | Record: Required information on the Concrete Pour Record.
95f31521-72d0-5dfc-8642-746ede2eece3 | note | Method - Test
72ce3045-7603-5aff-9d67-994c50c72e14 | note | Frequency - Each sample of Self-compacting Concrete
cd7d726c-512e-595a-aa99-397dadcadce5 | note | Category - IP
e8961b09-00ce-595c-b138-5b43aea05c27 | note | Responsibility - Concrete Tester
19d7f9a1-792b-5736-b438-6349f70ca4d6 | note | Verifying Documents - This ITP
91262c33-ef3c-5369-a36e-011909452a57 | textbox | Date Completed:
| checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
498bf912-5031-56db-9f30-84b3e8aa9159 | note | Reference - Site Sampling & Testing Procedure 610.16
77f92e38-7eb0-5f43-827c-8a64fe154fa4 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
e8329f3c-2bdd-5df0-bd19-abe22904d7f4 | note | Record: Required information on the Concrete Pour Record.
0c161da9-e06f-5820-ab19-58bb496af78f | note | Method - Test
82114fe6-f2a6-52af-be59-246ff5f6bdd5 | note | Frequency - Each sample
a015c77e-120d-564e-8e69-6681ad252438 | note | Category - IP
beb8dbad-5c5e-5627-a0ca-39204eff4827 | note | Responsibility - Concrete Tester
01f8c5e5-1441-5901-a779-a136b6a9fa90 | note | Verifying Documents - This ITP
7d61cedb-3b32-5327-bce9-fc1c839fc7ea | textbox | Date Completed:
| checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
50f5461d-d33b-5b71-a034-93ddc144cf84 | note | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
3495ec75-4557-5fff-899e-ae6c6b9975e5 | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
077d25b6-87f8-59eb-9795-0307f81f603c | note | • All concrete batches are traceable.
392ca1c8-34d8-5133-9bbc-11fcadfbcf28 | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
65a996e5-de5d-5ad6-b57e-c8c6d402d304 | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
58906133-50e4-5599-9105-57012729efee | note | • the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
0f2e4f18-7f1b-535f-9e99-2bc59fbe65b5 | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
789e32d2-2d4c-543b-802e-7981f162bf40 | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
74f80b59-d3c0-5628-99ec-9cd4409060b0 | note | Record: Required information on the Concrete Pour Record.
7f7bcfc0-5bca-5a70-80be-04bc3359df98 | note | Attach: Concrete Pour Record
94cb4a78-3ef7-5875-804b-223b5738c198 | note | Attach: Concrete Dockets
6856b66b-72c6-5a5f-8711-102abef51f5d | note | Method - Visual
3467b85d-0218-54b8-bb71-c75933af15eb | note | Frequency - Each load
7b632bab-0c58-517d-9900-b84c79e379a1 | note | Category - SP
10e86cc3-6161-5a18-aa25-8b06ef280317 | note | Responsibility - Foreman, SE/PE/SPE
65b00a6d-3526-5536-b70e-d0ed6d55825b | textbox | Date Completed:
| checkpoint | 5.13 - Surface Finishes
8ab540c6-0549-5637-b0f7-5682b00e5430 | note | Reference - IFC Drawings 610.31, 610.20
2a0fbe2e-f68f-5dfe-a548-9c915c1c9544 | note | Acceptance Criteria - Surface finish as per IFC drawings.
34a068a4-827e-52c6-929f-b56877992595 | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
c5b3d4ce-f8fb-5652-b688-5632839514ed | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
524c2986-849e-5168-9399-edbc4f36399e | note | Method - Visual
6dd14904-d372-50f7-8873-d7a51e762e3f | note | Frequency - Each pile
2653eeaa-84e9-506a-96c5-2d6779fe4404 | note | Category - IP
d19c9d3a-4a35-5ced-9493-c4fc72011c96 | note | Responsibility - Foreman, SE/PE/SPE
65370567-7b84-50ba-8951-eb08e6b9cb79 | note | Verifying Documents - This ITP
82112d01-7b66-565d-a3c4-e3c8f780e2c5 | textbox | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Pile Trimming
4af8e301-96f4-5c22-a06a-3597c3db0871 | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
57462bbf-fffd-548a-9080-e98f36b8f046 | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
513230ec-c76a-56f9-81c4-b9c6ab93800a | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
6b35115c-5a41-5f63-9515-531a28e130fe | note | • Any weak or damaged concrete shall be removed back to sound concrete.
8ad4fbd8-1819-5493-8bcb-ebaffaf5d8f6 | note | Method - Measure, Visual
94a38309-3711-5b5a-a12f-d8b6e25eab1b | note | Frequency - Where applicable, each pile
9eb4f118-a4a1-5146-845d-36d88458ab69 | note | Category - IP
40b67f49-0dd2-54e8-aaee-2613484e895d | note | Responsibility - SE/PE/SPE
21e3755c-36e4-5258-8565-78b009b927a2 | note | Verifying Documents - This ITP
ed0ed1b7-34c0-5bd3-a9cb-058ca5dfe7d9 | textbox | Date Completed:
| checkpoint | 6.2 - Compressive Strength Test Results
00800f81-04d1-5b0e-a49c-f2fcb758883b | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
d9671c21-3380-5453-9498-d443acb6ae02 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
e67d52e4-c612-5724-9af8-84b9fa246105 | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
1fd1bcb1-d2d8-504c-8044-b426f3364ee8 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
a4197524-ccd9-5064-8984-3bc408c19eb6 | note | Attach: Compressive Strength Test Results
05802d91-48c8-5c04-9f8a-e0f05aa3ed7c | note | Method - Document Review
131061ef-7b2e-5daf-b124-556df8f9cc89 | note | Frequency - Each cylinder
ef05b7f2-fe31-5745-b417-572f3a373606 | note | Category - IP
89aea3b0-671e-5748-bc4e-76ca2381886f | note | Responsibility - SE/PE/SPE
5b3700f9-cd24-52be-b3f3-bcb5585ef23f | note | Verifying Documents - This ITP
27019cad-7c8d-5ab8-850b-72b9905f445b | textbox | Date Completed:
| checkpoint | 6.3 - Pile Integrity Testing
d08293cb-c9f7-5e84-8ca9-176a7c3037cd | note | Reference - 606.07 (a, d & e) AS2159 Clause 8.8
2502d88e-6e25-5f40-b2ff-3a3594b95fef | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
eed571e4-dc37-5ca4-a3b5-661746583a0d | note | • Cross-sectional area = ≥95%
e7b5bf39-1546-56b7-b662-386351fe4949 | note | • If any test fails, all piles shall be tested.
b32bf22b-8cb7-5389-94f3-d820ec4e6d2e | note | Attach: Pile Integrity Test Report
481224b3-970b-5205-8cc6-54b151088e74 | note | Method - Document Review
ebc1ef1a-39b3-50fc-adb7-ec835c4e00f9 | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
bd57d94f-25ab-5bbb-b98e-6f412261de56 | note | Category - IP
43c5efe2-6a68-525e-a8b7-fbe061f111bb | note | Responsibility - Testing Consultant, SE/PE/SPE
51b75e46-79dd-5184-80e9-1cd5b9cc8c65 | note | Verifying Documents - This ITP
0b5e482d-a0dc-5582-b750-caf8c25bc14d | textbox | Date Completed:
| checkpoint | 6.4 - Static Load Testing
bb3e1383-3fc9-5bf2-801a-8e8e8273f23f | note | Reference - IFC Drawings 606.07 (b, d & e) AS2159 Clause 8.4
c7ebcbc3-949d-50d7-a1b4-b7d58fd43b81 | note | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
eb1655fe-e3b9-543a-8e87-c0422fad802d | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
57dffeb7-c639-5b57-9603-5143dd28a2fb | note | ii. Creep rate = <2mm / log cycle of time at the test load
6e615506-14e1-58f7-99d5-23d996442b2c | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
2a02f7b3-2393-5efa-bf5f-6579a2179907 | note | Attach: Static Load Test Report
582f95eb-89f6-52ed-a42c-359ee650c629 | note | Method - Document Review
5bc9f1a0-de25-5ec5-8f2d-1499a692278a | note | Frequency - Where applicable, as shown on the IFC Drawings
6131c4c6-6d58-5b75-ae28-caf3b8a90d3b | note | Category - IP
53fcf8ee-5a0b-5a3e-af6a-2f62ad575f31 | note | Responsibility - Testing Consultant, SE/PE/SPE
0955070d-08ab-5025-b845-25e3fc6d4175 | note | Verifying Documents - This ITP
81883927-3da1-5755-aa7c-2ad8faf168b1 | textbox | Date Completed:
| checkpoint | 6.5 - Dynamic Pile Testing
6e7800f9-ec5d-518b-afc4-e51dceb1b554 | note | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
e7ee23fe-366b-58af-bc60-3c5054b05dd8 | note | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
f2a32143-d929-5f9a-9eee-64619d12624f | note | • Measured Ultimate capacity = ≥ values on IFC drawings
f993cc28-a30a-52c6-ba17-83dfcf5068bd | note | Attach: Dynamic Pile Test Report
4ca71fe8-6361-5cf0-9782-02f6a3a34c8a | note | Method - Document Review
26c93876-4132-5aac-97ea-81474c292fe0 | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
75cf3c85-4cbc-5a1b-9e26-c8e779e4316f | note | Category - IP
1c5e918c-b0fd-58b4-a3cf-47f58edf26d6 | note | Responsibility - Testing Consultant, SE/PE/SPE
ad7a6b35-e228-5d59-981b-de9c4b4e90f3 | note | Verifying Documents - This ITP
0bf1011f-b840-5f23-b9f9-3a9bfe9a1b37 | textbox | Date Completed:
| checkpoint | 6.6 - As-built Survey
e210b520-0d29-5adb-9bba-ed0ff3ffe4b6 | note | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
d9cc5fa4-2e41-5d59-ad78-59a2af6f192f | note | Acceptance Criteria - The following tolerances apply to piles:
11b9fcf9-ddaf-5e07-a95c-40edfe180db3 | note | i. Pile head plan location = ±75mm
13c164b7-9184-5afc-a4f2-796ef4186f11 | note | ii. Variance from vertical or rake = 1:100
927d25e5-7fa6-5f41-ad37-37c8c5172536 | note | iii. Irregularities in straightness = 1:100
881c4620-ba37-5b61-aa82-1b7735a81455 | note | iv. RL = ±25mm
5c0ae95e-dda1-543e-94ac-f930da1e58c8 | note | Attach: Survey As-builts / Survey Report
fb9bd508-5768-5edd-ae9a-2de3bd11c7cc | note | Method - Document Review
2025aadb-9b87-5af1-b424-f9a720d97c2d | note | Frequency - Each pile
25839e40-57b8-5b79-9192-fd744cbdf541 | note | Category - IP
e4e0712d-66b9-5234-830e-d4eb3b55a3d8 | note | Responsibility - Surveyor, SE/PE/SPE
5234d5b7-0bdf-52dd-af6e-bb5d7d0fe9b2 | note | Verifying Documents - This ITP
bb115e70-f532-5135-aaf4-2212c5170e81 | textbox | Date Completed:
| checkpoint | 6.7 - Non-conformance Report (NCR) Closure
15bb5809-c770-53ae-a21d-6d42d1ec0132 | note | Reference - MRPA Quality Management Plan
3634dacd-dee7-5df4-bccb-9b857df9b3c5 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
3748ef3c-af8d-5033-925f-7fe9fca118ee | note | Method - Document Review
66a34beb-791f-5600-96e0-7a27cebe2f1f | note | Frequency - Once, prior to closure of this lot / element / Work area
0cd02d17-19bf-5562-bb81-efc65d17b789 | note | Category - HP*
d9039f95-6d2f-5ea5-9fd7-adea2711689d | note | Responsibility - SE/PE/SPE
abadb37b-ae2a-5d72-be92-561b79eb911c | note | Verifying Documents - This ITP
4edb2188-9c84-5248-bfa5-ef7ec6ee42fd | textbox | Date Completed:
| checkpoint | Final Inspection
4b9eb61b-e649-5927-a92b-6f76a54f79cc | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9501bf7f-0768-5dec-8503-7e148a57b4c2 | textbox | Name:
a1806edd-8307-58fa-bf09-403bfef965dc | textbox | Position:
aed64315-ebdd-59b6-b933-4e4a7140e9fe | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-013-STR-Pile Cap Construction Rev 0 | itp | ITP-013-STR-Pile Cap Construction | 9de8b40d-9d90-49d5-852b-38b3d9c5d155
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
b76f9ee3-6550-570c-88e2-b5e9e34f72cd | note | Document Title: ITP-013-STR-Pile Cap Construction
d29037fe-84bb-5299-8a2c-f75cb7226076 | note | ITP Description: Pile Cap Construction
78986eca-a3df-51d1-935b-28675262f3ea | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
1d299b58-4271-52d6-8a4b-b80dae86c8f2 | note | Discipline (e.g. CIV/STR/RAIL): STR
edccbb10-a0b4-54bb-8951-64b46ebb7194 | note | Revision Number: 0
a38ee1eb-73c8-54ef-8656-a21060eb378a | note | Revision Date: 01/12/22
5a7009d5-182d-5789-90f1-6373a6253935 | note | ITP created by: Victor Mira
20dfea2c-7100-5ecc-af75-cd27d13841bd | note | ITP approved for use by: Victor Mira
| checkpoint | 1.1 - Non Dependent
0f5741f7-e7ab-50f1-ac27-fb94c3246fcb | note | Reference - VicRoads Section 602 October 2007
| checkpoint | 1.2 - Non Dependent
7fb2f478-d6fc-51c6-80bc-7b453ad8e7cc | note | Reference - VicRoads Section 610 February 2020
| checkpoint | 1.3 - Non Dependent
a271af53-4f1d-5300-a24e-c7f1bb4be358 | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
b97a3ea1-7284-5d18-8c1c-6924c5a66d58 | note | Reference - VicRoads Section 614 June 2017
| checkpoint | 1.5 - Non Dependent
7e01e8ec-6dbc-5d73-9dec-8c055c4cb047 | note | Reference - AS3810.1 2018
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
3cf2244c-d220-5722-acdc-dc8b7819cc96 | note | Reference - 610.07 Table 610.071 IFC Drawings
2580ab94-90ed-5777-b0ed-8e925256dd21 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
cb680efb-7b83-56bf-9ca3-be897acce3d2 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
accebecf-c99c-5cd2-a432-8395c5db0a5b | textbox | Enter: Teambinder Material Approval number
4629a1dc-dcdd-537f-8248-bfae61ea8b85 | note | Method - Document Review
fa725204-c7bd-574a-b1f7-a252c5be2a83 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
32596c90-5acd-5d30-bd91-bc37e46282d2 | note | Category - HP
59630ed5-16a1-51c8-aeff-d66499189d47 | note | Responsibility - Nominated Authority
c7a20219-6170-58a6-aaf0-b56b25845a1e | note | Verifying Documents - ConQA Hold Point Release
1b66efa6-a1c9-5267-86a7-f92b7d5b007b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
6cc984d7-15cf-5e89-9ab2-59e7dbec0a4f | note | Reference - 611.05 (a)
b0f0897a-cb3b-5816-8e1a-610e0b7955bf | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
c028a1a1-7245-5137-a7de-cd5d8c76025f | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
d5efe286-a4f2-52eb-ac8c-4b1286ab8817 | textbox | Enter: Teambinder Material Approval number
d2d146ca-5e86-569b-aa4b-eb4df2d41f20 | note | Method - Document Review
efa0f029-c0be-5125-ab34-f2bc6d7b781c | note | Frequency - Once for each supplier, 14 days of award of contract
7517f28f-bb98-50e9-b17c-f54483f5343f | note | Category - HP
a67468eb-05f0-55d9-8892-e0d604cb79d5 | note | Responsibility - Nominated Authority
4b6b05b3-05f3-548c-a0bc-b6a12854a227 | note | Verifying Documents - This ITP
d25a5e16-5aba-58c2-9a7c-0b9ec6f6757b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
70809ac3-0957-5818-863d-05b17fb635f7 | note | Reference - 610.26 (a)
3fc9448b-f331-554f-b0fe-cd97912bed0c | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
69019490-7bf4-5cc4-81af-70dd19675f41 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
682350b9-ce7c-5279-a02e-0638eab95411 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
ec5322fd-6ab7-5646-849e-2beb63163757 | textbox | Enter: Teambinder Material Approval number
a33b4369-9444-5847-b06a-2c8da099a983 | note | Method - Document Review
d10234b7-4db6-5979-b537-b5d200905e67 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
6449c61e-fc4d-5f8c-ae69-61860d44197a | note | Category - HP
0990a72b-4550-5192-8262-eda3c8720edf | note | Responsibility - Nominated Authority
2fcac8eb-ad7c-5324-b3da-29397a67f705 | note | Verifying Documents - This ITP
18046d2d-b053-55f1-b9f8-9888e11ebe0c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative
9074f8f9-e096-5887-a3ba-b3c888c0a32e | note | Reference - 610.17 (f)
59ba2c3d-fc99-54a9-af27-ffa6ac46a8e2 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
eb5e2d52-40f2-5e72-8a5e-d988f40591e2 | textbox | Enter: Teambinder Material Approval number
0c42f92a-e0d1-5aab-abb8-cf3edf20fbd4 | note | Method - Document Review
c01a3c6e-7d65-54f0-aa83-b3e78a62d533 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
55a16ca7-6c8e-556e-b604-eeca98ae5d8d | note | Category - HP
07368ecc-c017-5847-950e-faffa4e80b2c | note | Responsibility - Nominated Authority
80fe0c20-7b4a-53e3-bc6e-46c60234e5a6 | note | Verifying Documents - This ITP
18571657-f2f8-5c3b-8070-d0fdf2628b8b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
6af0458c-e8f7-5c71-ae26-de8fda22de90 | note | Reference - 610.23 (d)
296c096d-bf2a-5ab4-b7b1-3fa8301f02e2 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
9306bb59-96ce-52f9-8147-bafb0049920c | textbox | Enter: Teambinder Material Approval number
5f166212-c2b6-58ad-837d-f152f85887de | note | Method - Document Review
e0f89fe1-a8f8-539b-8ccf-4504d49bfe30 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
8ac8ad10-eef1-5019-9b6f-5e808030dd84 | note | Category - HP
764b6ded-af58-5685-a67c-b2d43e9fb259 | note | Responsibility - Nominated Authority
a3f6028b-5de3-586b-b384-aa81d530e294 | note | Verifying Documents - This ITP
fe7894e0-7266-54a1-a3fc-5ac6d6fb1728 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
2bd834ed-545a-597d-9427-87e15422fad7 | note | Reference - 610.18 (a) (i)
4b7e03a6-a7aa-5b7a-a6bd-58c660d082e2 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
b352c7be-2a07-5561-b7e5-72001087c825 | textbox | Enter: Teambinder Approval number
0b980fcc-e178-5a49-96c8-cd0bb900f4bc | note | Method - Document Review
a6edfbe2-be13-5531-a684-10504a4e620e | note | Frequency - Once, 4 weeks prior to placement of concrete
0132bef7-49a1-5bf2-8b8b-f3f0007591d3 | note | Category - HP
1874cf6e-9165-5f32-93ff-a39e79ff187d | note | Responsibility - Nominated Authority
584c6ffc-f7e1-5f23-a4dc-28215667f24e | note | Verifying Documents - ConQA Hold Point Release
4cfede23-c845-5899-8acf-15f889db3051 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
b4f3e60c-479d-5346-80df-1509b7a12346 | note | Reference - 610.18 (a) (v)
e39b8ab5-e531-5fab-866b-dec2846a0187 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
b0529034-af9e-53ee-a7ce-3596333b3730 | textbox | Enter: Teambinder Approval number
10ee9594-e491-5742-8a1e-ec4e087ab578 | note | Method - Document Review
c2633d02-6a68-57df-bb61-20b737f5466c | note | Frequency - Once, 4 weeks prior to placement of concrete
194ca65c-9fe7-539f-8abf-f6aaec6c4460 | note | Category - HP
b9a6b667-062f-5d48-9fc8-95285f4e4254 | note | Responsibility - Nominated Authority
32060d29-9a30-54f9-9fe7-f4fd80ee02e7 | note | Verifying Documents - ConQA Hold Point Release
fc1475fd-9e93-534e-b1c4-a72c7c0f8d85 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
7380a063-6226-5302-84b9-8d1897d7108e | note | Reference - 610.18 (a) (iv)
baa00dd5-1761-5af0-9d77-e3107aa3ca94 | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
320097d9-b6da-538a-81a1-4a5a4bcb6c58 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
d9cccf81-4031-55e5-8b3f-fb941feec5b1 | textbox | Enter: Teambinder Approval number
2d5980c7-998c-5544-8d8f-36c0d3166347 | note | Method - Document Review
ab7a88e5-42d1-51db-8554-9feee6b8e722 | note | Frequency - Once, 4 weeks prior to placement of concrete
48c60485-5969-5a06-89ed-57b4463f9997 | note | Category - HP
846bfe9a-7509-5249-80ca-45171eb9214e | note | Responsibility - Nominated Authority
7d687890-caf4-53b4-828a-2ddefe4aefa8 | note | Verifying Documents - ConQA Hold Point Release
549bfe1d-cea6-50a5-807f-d598fe8b8230 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
0d501701-05a3-5a64-b681-c859efd1c04d | note | Reference - 610.17 (a)
699fab8f-23a3-548e-8bef-f0d41ba99a38 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
59ec0686-4c0c-52bf-842f-441d46ab34f3 | textbox | Enter: Teambinder Approval number
77e9c4ed-6472-5e3d-b78c-a72b31677c3b | note | Method - Document Review
081c4e59-470b-57f8-8115-e52211dec9f7 | note | Frequency - Once, 2 weeks prior to placement of concrete
fc85752e-c3ab-5ac3-bded-1b65021ddc13 | note | Category - HP
b00f614d-20b4-516e-a008-32a713e64616 | note | Responsibility - Nominated Authority
b917221e-15e5-5f97-a426-3028c875a3a4 | note | Verifying Documents - This ITP
51eb5497-de31-5f7a-bab6-01abe62608c4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
94d73e3b-b00f-5442-a9b8-789b6abd3c58 | note | Reference - 610.23 (a)
6323a75e-668b-543c-8e85-d7d51d620348 | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
2fb5cb9c-60e7-5162-a9fc-6379c723ebbf | textbox | Enter: Teambinder Approval number
43904c1f-d932-52e7-80e5-c3b6a0a1c95b | note | Method - Document Review
86c7e5fd-3fc1-5d53-9a0d-6ff7f92a65c8 | note | Frequency - Once, 4 weeks prior to placement of concrete
be5598f5-351c-5351-9552-46ab4228a783 | note | Category - HP
43f9ecd5-9cf5-511a-9374-e4dc26ddff0c | note | Responsibility - Nominated Authority
b57375de-51a8-51d1-a62b-365ef3d1cc84 | note | Verifying Documents - ConQA Hold Point Release
51b34793-0bec-5439-9283-c90e9c7def6f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Concrete Drilling Procedure
89e55657-778f-5da0-af96-1ffd33bc026e | note | Reference - 610.46
715fc275-8630-50a9-9422-332b7d44df0b | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
5217868f-d2ed-54cb-9bbc-da530f17fbe2 | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
a5d7fefb-045e-55c0-99d0-c4e584601cd4 | textbox | Enter: Teambinder Approval number
d0e1d2ad-0173-5a8e-90a4-228da9f33c5a | note | Method - Document Review
1695843a-4434-5bbc-86db-95e7d135c97f | note | Frequency - Where applicable, once, 2 days prior to drilling
6ab3ff0d-5ba1-58f2-8036-e595f1a750bc | note | Category - HP
f6197e72-424e-5b0f-bba8-69e615873d95 | note | Responsibility - Nominated Authority
19ab114c-c6d3-525f-8acc-d1637ceb47fd | note | Verifying Documents - ConQA Hold Point Release
cf181aef-6019-5ae2-8b72-a67b2711b87e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Temprature difference measuring-Calibration
646e3eaf-758d-586b-b1f4-a79a9ed928f9 | note | Reference - MRPA Quality Management Plan
d96c29c2-4cb6-511e-8a9f-4aac577eab1c | note | Acceptance Criteria - Calibration records are valid and up to date.
a08eddb9-08bf-5cb7-814e-5a6be59c72c1 | note | Attach: Calibration certificate
ee1a809f-ddd6-5103-b24c-1e504aebfe36 | note | Method - Document review
6a056a8f-30a1-5f3b-bf9b-c9c175e0058f | note | Frequency - Where applicable
dffa94ff-9545-52cb-ab0a-06ecfd371780 | note | Category - HP*
5d5c7574-6a5a-563a-91df-f1db124d2dfc | note | Responsibility - PE
62590a6a-547f-5e6b-84c5-9062e2fd1a73 | note | Verifying Documents - This ITP, Attached calibration certificate
dccbda64-41cd-5c48-8c40-6596d3c3aefb | date | Date Completed:
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
1540b0c7-cd8a-58a5-9755-76f2cbccb7fb | note | Reference - MRPA Quality Management Plan
80745837-3583-5072-bb00-22743b6e4933 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
091f6b0c-1cac-5070-96ef-a14af4ab4abf | note | Method - Document Review
129df37b-109b-5c42-9e5f-7563ab0a561e | note | Frequency - Prior to starting Works and at regular intervals
41494368-88c9-51be-971b-364238a0ff69 | note | Category - HP*
e2fe1d61-0979-5cfe-97d4-992336e73603 | note | Responsibility - All
7af73bb1-972b-599d-8aa8-2e514893266e | note | Verifying Documents - This ITP
8280f773-82ec-5687-bdcc-d6c2c578e4a5 | date | Date Completed:
| checkpoint | 4.2 - Survey Set-out
b7aca6d8-365c-52c1-a56f-063d4fb586ba | note | Reference - IFC Drawings 610.47 (a) Table 610.472
5ff7306c-b73f-52ef-a5d3-adea4cd04996 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
3ec72587-1ffb-50b7-a2eb-1d981a14fe4e | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
ee79a0b4-1683-5536-8cd1-1bc56fc9c44a | note | Method - Measure, Visual
98af64ea-20ba-53c5-8fa5-0aaf076ba63d | note | Frequency - Each element
5d238f95-2c1a-5b62-b8c9-ef63c690fa66 | note | Category - IP
962f6639-8402-558f-8bf3-a272c5274ab1 | note | Responsibility - Surveyor, SE/PE
5eb0b3d1-6fad-5b84-b57c-74ea2dc3ae1e | note | Verifying Documents - This ITP
2f373f45-d385-5ef0-803e-b028dbe50931 | date | Date Completed:
| checkpoint | Piles
ce56de83-348d-5c5a-8972-982fa3c07113 | note | Reference - IFC Drawing
bff61097-843d-57d3-878b-6d31f5a3a42f | note | Acceptance Criteria - Related piling Lots are closed.
31a854e7-0822-5729-8119-3a265a9abc6a | note | – Pile design strength is achieved.
7901a989-c897-5430-84fa-3e0e0665c9c4 | note | – Integrity and Dynamic tests performed and interpreted.
42f94a00-ff80-5387-80a4-77f344a9728a | note | – Pile is broken back to the design level.
87aa9c76-e7d7-543b-948b-d0439d46bd69 | note | – As-Built Survey performed.
3b93f889-05d5-5cba-8efc-86770c7013ea | note | – Related piling NCMs are closed.
2fc96764-ff04-5809-ab5d-2e5a301de077 | textbox | Enter: piling Lot numbers:
6de37380-7587-5b84-ab1b-6af4974ccde0 | note | Method - Document Check
2dffbd70-a31f-5d56-956e-da0a11dd858f | note | Frequency - Each Element
6323edcc-20df-581e-8f13-66f24a1e1e5e | note | Category - HP*
c260e47a-1be5-5820-85a2-f7ed1779e67a | note | Responsibility - PE
6230556d-36de-5cae-9924-cf02febfc012 | note | Verifying Documents - Piling Lots
d1a039f2-fdf3-5b3c-949d-64198d575fab | date | Date Completed:
| checkpoint | 4.3 - Excavation support
473a62bf-cb27-5d1b-bd9e-0031e2a84179 | note | Reference - 602.02
fffebd69-fe33-5a74-b41d-22c4955a998f | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
3f2ea74e-00be-55d9-9b34-31997dc46740 | textbox | Enter: Teambinder Approval number
81672a6e-54f1-5332-a6f6-ff261cc97b6c | note | Method - Document Review
2a4fb53a-baf5-5253-b51a-b0223350bb5a | note | Frequency - Where applicable, not less than 10 business days prior to excavation
571d866d-ea61-54b0-a049-6556e2094a31 | note | Category - WP
9e466b8b-ed41-55c1-a8c2-37aee3e458b5 | note | Responsibility - SE/PE/SPE
ce94c0ed-3797-5a37-baf8-89cd9193d8b7 | note | Verifying Documents - ConQA Hold Point Release
6b23ebed-6c51-537b-b7c6-03622c29446e | date | Date Completed:
| checkpoint | 4.4 - Excavation Inspection
e52058a6-6406-54f4-afc8-4a2c52eefb24 | note | Reference - 602.03
73d273cd-591b-549c-91d7-a1a668a3e76f | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
2e632299-657c-5082-9c51-d160396aaff6 | note | Method - Visual
2cdcba21-cff4-5793-8122-104b233977b9 | note | Frequency - Where applicable, prior to placing blinding concrete
1748932c-6489-5fbd-86d3-0a918ed53b10 | note | Category - HP
bfa7c08f-a66b-551b-824b-89b727667ae6 | note | Responsibility - Nominated Authority
d6dd5d2b-c766-5edf-af8f-2d5d8b0fc303 | note | Verifying Documents - ConQA Hold Point Release
f6c1d094-088a-59c6-acf4-a101da1cee45 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
ee14acdd-abb8-5cb5-9e8a-a5e90c1a25ab | note | Reference - IFC Drawings 614.04, 614.05, 614.06
7bb0d6b6-4a81-512c-8a32-91da2b29b112 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
4869a5b9-23ac-5b93-9d5d-65fbc8e9e1ad | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
92caecbe-5839-5dc0-972a-986e6baf712b | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
abcb44fc-16fa-5d71-9bf7-0744fc75cdd1 | note | Method - Document Review, Visual, Measure
e58fddec-506d-5d47-8c35-c75c3474d88d | note | Frequency - Each type of element
f7aef27d-c581-5219-a191-2f1539e6fe58 | note | Category - IP
8469ce25-204c-551f-9310-93e033da5604 | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
60a2b6f9-6a06-518a-8a9f-5c02af1e2177 | note | Verifying Documents - This ITP
85a751d8-6ab5-5526-ab45-95b7bb17b615 | date | Date Completed:
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
b75d1d6f-4e50-54c4-bc36-61113a185ff2 | note | Reference - 614.08
0d3da601-40f0-5d7c-b626-eabf17cec194 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
a8bff38d-8908-56c6-a597-ab09e670abea | note | ○ Pile caps with heights greater than 2.0 metres
b02f211d-7465-5a63-8ff5-879900be13e6 | note | ○ Any member for which self-compacting concrete is proposed.
0fb06854-ee09-5042-b6ed-1d30be919732 | note | Attach: Attachment A
0d94b082-0262-5556-8b5f-9465939c310f | note | Attach: Attachment B
38e7fb90-8a79-554f-9956-f9a1ecefd889 | note | Method - Document Review, Visual, Measure
15a4c63c-c27c-506d-b463-c85b5a2228a3 | note | Frequency - Each element (where greater than 2m)
584e3447-16da-52e7-89dd-1ce8a9f5aa71 | note | Category - HP
8e9e9df8-70b8-5fb3-b11a-6f4338f1d78a | note | Responsibility - Temporary Works Designer, Proof Engineer
104d6fd5-b639-5755-9e73-f62cb2bdfc91 | note | Verifying Documents - ConQA Hold Point Release
f4d7c82f-40fb-5423-8f3d-9536013995a7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
f64dd90f-71f8-5a00-9eb4-8f795e0af5c3 | note | Reference - 614.08
5053e5d4-a0a1-55fe-8380-b15c0b783f4e | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
74605a5c-0c54-5877-8f0f-b02394db3b00 | note | ○ Pile caps with heights less than 2.0 metres
bfd3fe0d-b98d-559a-b139-571cea655454 | note | Attach: Attachment C
28e62420-d110-5811-be0b-f5e848cb07c5 | note | Method - Document Review, Visual, Measure
e5033dc9-9230-59f9-83b8-37da58c3a58d | note | Frequency - Each element (where 2m or less)
8c770cab-9741-5194-a7c0-09eb5e298ba1 | note | Category - HP
166de3eb-0dd4-56d7-b7e8-bc793a5826f7 | note | Responsibility - Temporary Works Designer, Proof Engineer
f7a1360d-db88-5548-b8ee-5d01f5708d58 | note | Verifying Documents - ConQA Hold Point Release
06d84021-d002-5fc6-bbb7-86beef5d9ac9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
a99407d0-a94f-5929-91d0-72359c3406b6 | note | Reference - 610.47 (a) Table 610.472
d872d2a6-40b7-5f73-9ae6-3208f10ae758 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
d06676c9-e69f-5712-93a5-e7009ffddc21 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
9632e181-a44c-5fb6-9a5c-a1172970db3e | note | Method - Measure, Visual
7799b699-d162-5250-a672-aa5ac1bb7039 | note | Frequency - Each element
e904b780-bff2-5603-ab1e-2131a5925781 | note | Category - HP*
dbbde62a-3384-5625-86b1-5cf906e0004f | note | Responsibility - Surveyor, SE/PE/SPE
c84b2609-5ad3-5b41-9a77-563d7c7268cf | note | Verifying Documents - This ITP
4c910ed9-3477-5709-ab94-96d09c9ecc97 | date | Date Completed:
| checkpoint | 5.5 - Reinforcement Placement
4378e09c-8945-59b0-a868-ee2eab31b6ff | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
01a64174-dc6d-5939-ab01-d8dc61cc3acf | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
f84d1f21-0a2f-53e1-9a0a-1077bbcedb29 | note | ○ Projecting reinforcement is the correct length and location.
f87ef64f-6437-509b-aaae-3196451c8ef1 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
5c6e745c-6f8e-57ea-87d0-cd7c0df966b1 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
2f444baf-4bb3-5e31-8ff3-2dab581e2033 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
6bbc5e65-29dc-5540-aabd-74f3c4248283 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
b110b408-1a96-5b31-bc80-1c2b45278b9b | note | Method - Measure, Visual
9192e9ea-fa61-53f7-b942-f969543f77a3 | note | Frequency - Each element
c819da1f-735a-5dfb-be3e-d6e88b7f83d2 | note | Category - IP
e1412ba7-7dad-5716-a4cc-6a9884b8bfff | note | Responsibility - Foreman, SE/PE/SPE
9a662646-c7e1-5d35-baad-76bd38bb9280 | note | Verifying Documents - This ITP
89a5a293-ae17-5477-bf77-6c9ae6dc3d2d | date | Date Completed:
| checkpoint | 5.7 - Cast-in Items
b69ee3e8-e948-5cfb-a0e5-df0ef6cb0cfc | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
23a74c39-1dcf-52c5-a09d-e4e5cbe6eb05 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
15cd577c-e882-54df-92e2-1da60dbe07d0 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
ddec8060-91f5-5e9c-b433-f47779fb7982 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
f9568cbd-3024-54df-8c16-e3ba2bb8e403 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
608b2af3-cc1e-5cc7-9d06-a163931179c6 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
896a5e35-0e0d-5961-ba5d-f49884fe0519 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
2da04cb0-f3db-5def-b0f2-251b4646f5e0 | note | ii. Running dimensions of a group of the above = ±6mm
4ea0805b-6c1f-57d5-b671-e013ea8396d0 | note | iii. Ducts and conduit location = ±12mm
88340149-aa34-5a8f-843e-69d94a5fa9d6 | note | iv. Diameter of ducts and conduits = ±3mm
2e3549ee-8120-5e19-9dcf-9e148e9a4cf0 | note | Method - Measure, Visual
c1782abb-ee0f-5455-9704-8e62b03eed95 | note | Frequency - Where applicable, each element
5dbe7fc8-e0ce-580a-ba7a-409c390427c8 | note | Category - IP
7e5317af-ab6c-509f-b668-73116e5e4fc9 | note | Responsibility - Foreman, SE/PE/SPE
6e7d220f-99b9-50f8-b69a-eea079eb86fa | note | Verifying Documents - This ITP
ab622eec-8e22-5e2d-8e7c-0e9c3c8df5ed | date | Date Completed:
| checkpoint | 5.8 - Thermal Differential Monitoring
f4890f00-2642-5e54-b6ba-e69bd11be12b | note | Reference - 610.22
cd2062e9-3c36-5954-a746-64f715bbf2ae | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
fde46802-fe87-52c0-8e8d-7e43bc0814ef | note | ○ Only applicable if the element has:
e7b5af4a-5f9d-5291-b185-d49c36e1d094 | note | i. the smallest sectional dimension exceeding 500mm
d7ffb95f-ea2e-537b-a377-6500cb5d1453 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
6f2126a7-c3ef-5744-b988-bd6818e1d9fa | note | Method - Measure
118e6066-08fb-52f6-b87f-f9ef85faf567 | note | Frequency - Where applicable, each element
300e3467-f35c-596e-88e0-b664d303a71d | note | Category - IP
d6c105e7-0f93-5e16-adc7-2836c9e5be02 | note | Responsibility - Foreman, SE/PE/SPE
35eacf51-0940-5d49-b6e9-73c356f440c3 | note | Verifying Documents - This ITP
211b1577-fe3e-518c-84b2-b5c53e1d1173 | date | Date Completed:
| checkpoint | 5.9 - Pre-pour Inspection
41d29ca3-45cd-5c70-a029-8de4b6fa6a1f | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
c8a99d00-2216-53a0-bdc5-ad542030bdc1 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
535c439e-08c1-5535-9b37-5e39f7dd2956 | note | ○ All foreign material has been completely removed from the forms.
ecbb3f3f-3906-5af5-8cc0-16377829cade | note | ATTACH: Pre-Pour Checklist
fb36b252-9d6f-54da-9672-fb12856024b1 | note | Method - Measure, Visual
17e03bf8-af0a-5f12-b95c-103b59091e24 | note | Frequency - Each element
4b0cb181-6c8f-592f-a935-0667b0ab5d32 | note | Category - HP
1ef8a458-92c6-56db-84a5-3faa667b3ca3 | note | Responsibility - Nominated Authority
67993e98-ea77-5778-8e1b-4eaeceed87db | note | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
b918298d-e4c5-5527-8e33-d7cf90cd567a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.10 - Weather Conditions & Evaporation Limits
a8c40b62-0976-5c45-9f03-4779d3701f15 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
82183335-c96a-5e0e-89a9-ba2678951b15 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
8acf73fe-94ce-54c5-80b6-249d3ae4e521 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
2f6d7f9c-2872-5e50-aa48-c74bfa27f379 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
7b8ce12a-516f-563f-9a12-03b3cb86092f | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
5143b7ab-c1d7-53cd-b02c-01734b577225 | note | Record: Required information on the Concrete Pour Record.
b59ce63f-242a-54cf-bf1e-e542997f23ce | note | Method - Measure, Visual
5321d005-9796-5ce3-920e-94a9662cd57b | note | Frequency - Each element
09dc37f6-df12-59d9-b327-24f35652d8b2 | note | Category - IP
4c82f5bc-ed26-54cb-a89f-6b32612f5cbf | note | Responsibility - Foreman, SE/PE/SPE
67d2519a-9055-5d74-b422-f0ec9ac68132 | note | Verifying Documents - This ITP, Concrete Pour Record
a6b4641b-ebb7-53b4-8f83-5ff6d4267483 | date | Date Completed:
| checkpoint | 5.11 - Concrete Testing - Sampling Frequency
3034a109-0638-570b-ad2d-c825d1f4320d | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
71afce13-1f63-5887-b685-56a7a80eb5a0 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
48db1ef0-276f-54fe-8315-b5d5141d66f1 | note | 0m³ to 10m³ = 1 sample
08e7e0e3-5db4-5140-9b52-4f8039b5fbef | note | 10m³ to 25m³ = 2 samples
d8ccc0ef-4b60-5b43-b3a1-4731090fd64f | note | 25m³ to 50m³ = 3 samples
7f5a0c5c-3f52-5627-8c4e-744c3fdf73b1 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
16b84793-f55a-5265-85c2-520cf49e5041 | note | ○ For each additional 50m³ and additional sample shall be taken.
871a3f71-3868-58a2-9fed-259d6879e52a | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
e0a2c5d1-1641-5d45-b609-cd3ff31e6842 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
29d9d342-9374-59ad-be4e-9d7245115443 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
e77ead74-a759-5cee-b4e2-377b55602fcd | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
936828e2-f8ae-55a6-8179-c9520c66d7ee | note | Record: Required information on the Concrete Pour Record.
629c2ec8-7c4e-559a-8021-6e2c62cf995c | note | Method - Test
56c668bb-8fd2-5252-b930-4148d0706ca4 | note | Frequency - Each element
e48bc97f-c416-52c7-bfaa-eccdfbd3ab88 | note | Category - IP
fcfbfab6-ca11-5973-b3a2-90f3031383a7 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
fb8f56ae-df30-52b8-948a-a7b5b12a4c91 | note | Verifying Documents - This ITP, Concrete Pour Record
d5e87554-2fc1-5f61-a560-fd83af2b728c | date | Date Completed:
| checkpoint | 5.12 - Concrete Testing - Slump
a2fa0aa9-c4cb-502b-89c5-f29661ac0507 | note | Reference - 610.16 (c)
84d15b00-1a8b-5b82-86c0-359cf884f2c2 | note | Acceptance Criteria - Slump testing tolerances =
401655b8-8852-5005-ab04-6c15ed311bfd | note | <60mm = ±10mm
0d78a74a-10d0-5f1e-9dca-28e752af56de | note | ≥60mm to ≤80mm = ±15mm
85f5b767-595c-5adf-a116-4e93269f6c06 | note | >80mm to ≤110mm = ±20mm
6cdb05c5-e20d-54f4-ac37-3b8318a6b9b2 | note | >110mm to ≤150mm = ±30mm
208289b2-7156-5d58-8ca0-c911fbe544c2 | note | >150mm = ±40mm
8a0e710a-0166-5d5b-9791-d936526ff554 | note | Record: Required information on the Concrete Pour Record.
b73144f1-b0d8-5c04-b073-3303632cd1b0 | note | Method - Test
5f55b06f-1130-5982-99e8-d70db83ef0a7 | note | Frequency - Each sample of Standard or Superplasticised Concrete
fa4b836c-6960-57e6-9b5a-ce8366a46785 | note | Category - IP
1811fa8c-189b-5d71-80d0-3eda99de3cd7 | note | Responsibility - Concrete Tester
91c74100-e02a-50dd-931a-472ea84bf93e | note | Verifying Documents - This ITP, Concrete Pour Record
4ce4bcfb-8beb-5c83-95fb-5fc880e02cc4 | date | Date Completed:
| checkpoint | 5.13 - Concrete Testing - Spread, Passability & Viscosity
c0e12a74-9a00-593b-8b87-86d6bd06014b | note | Reference - 610.13 (b)
3ed50975-59b5-51c4-81cc-f296f5471f66 | note | Acceptance Criteria - Spread range = 550mm to 750mm
9506dafb-8a83-5925-9ad9-15f4183d9ea8 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
4126827b-0f1b-5a35-8a3d-70f0faae4385 | note | ○ Passability = ≤10mm (aggregate height differential)
dd550d0d-ace2-5850-814a-a9622182be5e | note | Record: Required information on the Concrete Pour Record.
1e8b7d91-fefc-52df-885e-2dd859818aa1 | note | Method - Test
01231750-6566-5f00-a6fa-34f0ce5bbc39 | note | Frequency - Each sample of Self-compacting Concrete
4ab981ee-373a-5833-8b9f-6bcf618a48a7 | note | Category - IP
16eeb615-b682-51c2-b07c-2126ea7d3028 | note | Responsibility - Concrete Tester
7f117fe6-ffd0-5de8-8630-e195cbc13ae1 | note | Verifying Documents - This ITP, Concrete Pour Record
b2b05077-753f-5ba6-aa12-161275a12f26 | date | Date Completed:
| checkpoint | 5.14 - Concrete Testing - Compressive Strength Cylinders
45355b5e-dfa1-5ec1-a5b1-5e3a7d74fc09 | note | Reference - Site Sampling & Testing Procedure
19d6e2c2-559e-5743-9242-16b2711b7626 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
13d8b997-04a7-5c8a-bbcd-fb216041327c | note | Record: Required information on the Concrete Pour Record.
0c6735a0-a0a5-5075-80ae-dda5988e6773 | note | Method - Test
45eddb79-843a-5e6a-a232-c8609a1ed665 | note | Frequency - Each sample
1d8f0875-a4ac-53dc-b3f8-69a5557dc4f2 | note | Category - IP
66a01360-f414-5245-8931-ed5e0f83ba68 | note | Responsibility - Concrete Tester
6daddfdd-42ac-5b3b-bcc8-a1806dd3eb32 | note | Verifying Documents - This ITP
514a107f-bf4f-5868-8646-2ef0e9758528 | date | Date Completed:
| checkpoint | 5.15 - Supply & Discharge Rates
0582a8b7-437f-580e-9ac0-7c086cba4ece | note | Reference - 610.13 (a) & (f)
2219f57a-c71d-588b-9966-c409e2bb75a0 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
cc362360-0f48-54bc-97b9-e202e1d24fb8 | note | ○ No water is to be added once discharge commences.
435603f0-db94-5b0d-8d8d-00ac8d92a80f | note | ○ Maximum time between batching trucks is 25 minutes.
7b9e402b-2151-5938-8969-6c6344cddb91 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
fa28731b-3f8d-5777-a38f-b4b6424f1f79 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
2a405657-5f61-5d73-9d7c-128472c062ae | note | Record: Required information on the Concrete Pour Record.
7bdcbd4a-3955-5b89-9d22-899ef69eb9ac | note | Method - Measure, Visual
35d6e0ac-16f4-5dab-a36a-7fa49ed86678 | note | Frequency - Each load
d6946aa6-3c17-5c38-9f54-dd8969ae6860 | note | Category - IP
0d62d52b-069e-59ba-9e83-474409430edd | note | Responsibility - Foreman, SE/PE/SPE
33a1d9f4-7a79-51a5-b45d-0e7cb84f1745 | note | Verifying Documents - This ITP, Concrete Pour Record
b2d0297e-27ed-515f-8175-9d0f7f0050bd | date | Date Completed:
| checkpoint | 5.16 - Placement & Compaction
b5648c58-b171-521e-a82b-03ebd8604112 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
1b630365-0be0-5ebe-bdbf-4b994f4640fd | note | Acceptance Criteria - All concrete batches are traceable.
379993a3-1dac-5f00-9470-486904171265 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
6bcf79cd-9bed-5b70-b7f3-a108758ef8c3 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
2858e83c-dfc4-5a59-992f-c6209a373ad2 | note | ○ Concrete is not moved horizontally by use of vibrators.
4b1e1f85-5d95-5a7c-b72b-4b061b58c960 | note | ○ Adequate compaction is ensured
4c45567a-8990-598f-921e-6c660be27765 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
777c7603-0e9b-5482-b252-15b9f1730c9f | note | ○ Concrete layers are not more than 350mm
accf71f2-1915-56c7-86a9-2f25b7501a25 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
20683ca7-cfce-516f-adc8-644400562f6f | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
9162c6fb-f850-5233-bdb5-08f985165851 | note | Record: Required information on the Concrete Pour Record.
625da546-2d1b-5ef7-845a-f5065d7a9bba | note | Attach: Concrete Pour Record
78f85f75-0609-5801-8dff-bc8c5ec9aefe | note | Attach: Concrete Dockets
37d3d183-8354-54be-8405-a727b31da6b0 | note | Method - Visual
eb37767e-b227-5d6a-8b95-d0006c777629 | note | Frequency - Each load
deaeb97b-ba1a-5181-85f8-06393f0684ec | note | Category - SP
401d20c5-b00c-5ca7-9855-31a39957642d | note | Responsibility - Foreman, SE/PE/SPE
00ee48b7-6469-54bb-8395-269657525742 | note | Verifying Documents - This ITP, Concrete Pour Record
fadaf0c1-3216-58ea-b5a7-c829f4e010db | date | Date Completed:
| checkpoint | 5.17 - Surface Finishes
6355f7dc-7bc2-5bb7-9bc1-6f40542900a1 | note | Reference - IFC Drawings 610.31, 610.20
7479f192-fbb0-501f-afd6-964cb495a127 | note | Acceptance Criteria - Surface finish as per IFC drawings.
5d64487b-dcdb-5431-ad7e-ca466d391ea7 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
15e2b136-d745-566b-8180-fc347df70c21 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
97202b55-616f-5810-9b7d-da0393b51e19 | note | Method - Visual
eb184f26-4225-59b6-b8bf-5f2be711d64e | note | Frequency - Each element
86ea79b3-7bc3-557f-bb39-bee9a45c27c4 | note | Category - IP
2d3c8c66-12d9-53cc-a647-fcf79becada0 | note | Responsibility - Foreman, SE/PE/SPE
2d0e9fa1-5620-5891-9b72-11c93df4ca67 | note | Verifying Documents - This ITP
a687575f-20b0-5ef7-9d0f-8f45752cdc6c | date | Date Completed:
| checkpoint | Curing-Top Surface
13be2619-659f-5bb1-9f9a-946c29cb05eb | note | Reference - IFC Drawings
76d3daa5-9b7f-5c8d-941b-38468b204c7b | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
243e0bc4-e912-5f3a-8eff-470ecf4c8259 | note | Method - Visual
af3a782b-b20e-5e9b-a6bf-e7dd7770ba82 | note | Frequency - Each element
4883a6ec-2bb1-51cf-b3c8-b927dc48f354 | note | Category - IP
c6ad498a-22e1-5e3a-a35d-758d3b77d7f4 | note | Responsibility - Foreman, SE/PE/SPE
5fd42851-a595-5107-abe6-c803254ac45e | note | Verifying Documents - This ITP
a94b1557-cf1a-5e6c-bf9c-252dad34e183 | date | Date Completed:
| checkpoint | Curing after formwork removal
21d6d226-092c-51fd-acac-fb6943748897 | note | Reference - IFC Drawings
05c67cb6-2cef-526c-8cee-63ddbecba166 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
24222837-3dcb-5c0b-9444-91bc44ead9df | note | Method - Visual
2ae02e88-a45d-5c4b-824f-c67775185831 | note | Frequency - Each element
c24035c5-5922-57f5-8bfd-9fd73e906edc | note | Category - IP
cd00b31d-5b9e-5093-a425-e01026354624 | note | Responsibility - SE
d47cafe5-4e50-54cf-8cc9-fd11c480c8b2 | note | Verifying Documents - Thip ITP
846bd7df-d78d-52b6-b08f-9b385b9913e5 | date | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
49a4f569-6426-5052-8215-a7a550524361 | note | Reference - 610.22
6803119b-0c04-5102-941b-34c0b38027fb | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
d3447717-f45c-5cf4-a97d-da21a706defd | note | ○ Only applicable if the element has:
f564492b-d806-53a7-9eb5-f11bcf2cf43b | note | i. the smallest sectional dimension exceeding 500mm
7c2acd5f-aab4-5b18-a1d5-39e53a396bad | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
84656e60-59e4-55fc-9216-e22137928495 | note | Attach: Thermal Monitoring Report
642152e6-acfe-58a6-9143-b348db3a1ba7 | note | Method - Document Review
5e0e5ab1-03c4-5ce1-80ed-bad27bed295a | note | Frequency - Where applicable, each element
181e16c9-9e6d-5404-a617-b3fd98aea1b7 | note | Category - IP
e19c64d5-9841-58a8-b25c-309e45f37ac0 | note | Responsibility - Foreman, SE/PE/SPE
eddee7ae-c807-5625-91c4-bb48f5980c07 | note | Verifying Documents - This ITP
7c546729-dfbc-5d93-9106-cef23b00e01c | date | Date Completed:
| checkpoint | 6.3 - Early Age Compressive Strength Test Results - Removal of Formwork
b1839de0-aad7-5c89-b5af-5cdd56a8e527 | note | Reference - IFC Drawings
31235bad-4746-56fa-8d6c-c5f61e1d818b | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
27b10b27-4630-5312-a2c1-49ee06c71126 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
041194e9-805e-5534-b21a-56ee623ec9a0 | note | Method - Document Review
b7c1ab59-90e9-5a51-ae94-288af35acd5e | note | Frequency - Where applicable, each element
7d449959-c7f4-5995-9309-250e63cffd4c | note | Category - IP
da781b6b-865f-5025-a16d-18fdad3c7ffe | note | Responsibility - Foreman, SE/PE/SPE
f5bf6538-7141-5161-9021-971aa326c3ee | note | Verifying Documents - This ITP
4e45d1a1-9783-55f1-b719-dd9ed470cb51 | date | Date Completed:
| checkpoint | 6.4 - Surface Inspection - Cracks
219a59bb-5f28-551a-a3c4-a3c82f6597d4 | note | Reference - 610.24
20c7baea-12a0-5ce7-ab0a-eefc8f99a48c | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
238e9255-24a6-547f-b879-feb3d9f0932c | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
04336ac8-d272-55ad-a73e-50fb3e128a77 | note | Method - Visual, Measure
2fdf18be-c1ab-5192-8ee6-b250c60168af | note | Frequency - Each element
570b678d-aa9c-5b98-abe7-9e6dac53373e | note | Category - IP
a6c1b2e2-a1d6-5fa5-89af-47fd40e3bb43 | note | Responsibility - SE/PE/SPE
6be41d90-2cf6-5519-827c-3cc1c78cc47b | note | Verifying Documents - This ITP
936d1bd9-0eff-50e6-a829-9137fcdbb5c4 | date | Date Completed:
| checkpoint | 6.5 - Surface Inspection - Surface Finish
31f17bff-3ea9-582b-a919-41adaa52a305 | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
883b3ca3-a4f5-52e6-943b-dd5991381288 | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
78cc79a9-92e1-50f9-aa81-0d7df020ac58 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
2ab94267-f210-5c68-9f89-734c487ba7dc | note | Method - Visual
c6a82e19-0d4e-52dc-b8e1-401a83f05928 | note | Frequency - Each element
4ab9aba0-9ce1-58d4-ab5f-7c78efa6f8b6 | note | Category - IP
8fc72889-f2bb-5355-b5ff-76d7b2727a45 | note | Responsibility - SE/PE/SPE
090c23b2-95c5-591b-b2a7-2743971545e1 | note | Verifying Documents - This ITP
a2a82405-f652-512c-b44c-ae01e39fb348 | date | Date Completed:
| checkpoint | 6.6 - Measurement of Concrete Cover
e969d2f5-6fe3-50af-941c-a3f4fab62921 | note | Reference - 610.34
e10d4206-134e-54f7-b2ad-24453d106c33 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
f079e596-f63e-5dba-bedc-20d97d4c39de | note | ○ Minimum 10 no. measurements recorded in each area.
7d62d88a-6506-542e-8958-e688a0630aa9 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
3c795a0b-4aa4-5934-8bdc-3f3fcc9d5b03 | note | Attach: Covermeter Check Record
4bfc4b40-8c7f-5c9c-b2d8-84605e9058e4 | note | Method - Measure
05a723bb-1748-52bf-9601-435f763f6a4f | note | Frequency - Each element
8967682f-9155-5aa7-b533-ebffc838dad0 | note | Category - IP
c927b98e-98ae-5b5c-91d9-ce1af02fe628 | note | Responsibility - SE/PE/SPE
196c16fd-bdd2-5530-ac92-92df3f681c89 | note | Verifying Documents - This ITP
88a89b35-84c8-56ce-ae45-6583631cc3f9 | date | Date Completed:
| checkpoint | 6.7 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
bda1604d-9bc3-5f9f-b991-eab0cc41b4fe | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
e44b34b5-0e2e-5f9e-972a-810de2d6bf5a | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
04c038b2-ad7d-5acd-b853-91348b1f9854 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
cb87583c-6d80-5ea0-b9be-d1aaf29a8ca2 | note | Attach: Concrete Test Results or Maturity Test Results
bfde790e-60a5-5ba8-83a8-87f4f498ae79 | note | Method - Document Review
dbd9dcf0-3b6d-5ca4-8844-08e9d7514742 | note | Frequency - Where applicable, each substructure element
94fa8a84-dd8e-5964-bd99-ab274a1f77a1 | note | Category - SP
7aba84ea-bcb6-546c-9bd4-594a7cd90c76 | note | Responsibility - Foreman, SE/PE/SPE
8f00e205-b5b5-5c58-8d04-e259eff27f93 | note | Verifying Documents - This ITP
a51068c1-2ff9-5470-9a8b-21ee195988dd | date | Date Completed:
| checkpoint | 6.9 - Compressive Strength Test Results
3c3208e1-fc32-5e28-9549-759e35270b12 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
d4716329-02c0-5d9e-99d1-200312fd2c58 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
ace3186e-cd35-525f-8855-d85f6223ec1f | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
7eef129c-355b-5eab-8425-c17f38486946 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
cb683cae-4f89-5887-8574-cc6ff4788a53 | note | Attach: Compressive Strength Test Results
35009282-4848-565e-8a3c-570387c83f61 | note | Method - Document Review
e0aba5ff-3f8c-5eac-a1db-2f54236db636 | note | Frequency - Each cylinder
0634216f-d8f3-5eea-acb8-e08d1a2f40e2 | note | Category - IP
990ca89c-1c82-56b1-b0eb-7a3fe54e8572 | note | Responsibility - SE/PE/SPE
e138a501-8905-5a6b-bc82-f06a30e91d5c | note | Verifying Documents - This ITP
bbda4e90-f6a9-532e-85c6-a74b559c00f8 | date | Date Completed:
| checkpoint | 6.10 - As-built Survey
5244eb9f-7ef5-55e7-9541-07b150ef2983 | note | Reference - IFC Drawings 610.47 Table 610.472
ba11d60c-7545-5c81-8157-20f1ef5453f7 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
a1e86ece-acb0-5e78-a4a8-5caecbe3d8ed | note | Attach: Survey As-builts / Survey Report
6261e3db-48a8-594d-91e1-7e57a7311bcd | note | Method - Document Review
81ebc053-a218-59d6-87cf-e36fa6f812f7 | note | Frequency - Each element
aaa07c9e-42c0-5547-8647-4a0e74a9b524 | note | Category - IP
0a13c4af-3419-537c-8784-03a234edde56 | note | Responsibility - Surveyor, SE/PE/SPE
d0a950bb-9306-590a-a985-dac8c6906c47 | note | Verifying Documents - This ITP
57114000-394e-5750-a33b-be29a41769f5 | date | Date Completed:
| checkpoint | 6.11 - Non-conformance Report (NCR) Closure
0040cc55-1b3a-55e5-90cb-2a0702932c55 | note | Reference - MRPA Quality Management Plan
e4915ef0-4f05-50f1-b3f6-ddf21086b1a8 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f6bbc6c7-7dd2-589e-82d3-c0e0a12a3475 | note | Method - Document Review
00abf5d7-6adf-59b1-97d1-dfa29940d39a | note | Frequency - Once, prior to closure of this lot / element / Work area
fb389238-485f-5b73-9d32-7d0647236add | note | Category - HP*
d112b900-a84a-5b9d-9dfb-774367ea479f | note | Responsibility - SE/PE/SPE
a748f516-002c-5747-9546-7d4582b279de | note | Verifying Documents - This ITP
61ac4572-49db-5bd6-ad28-f9a8f80ecc78 | date | Date Completed:
| checkpoint | Final Inspection
191365ff-d1c0-5fe6-9306-9d98a37c9d76 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2a7b588d-8d08-51b1-9572-48235c78d9b4 | textbox | Name:
1bb15fe2-3362-5ac6-9b9a-d0f52035fb5d | textbox | Position:
1d08114d-b49d-51ed-b1bd-e65401bce7c7 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-017-STR-Structural concrete Rev 0 | itp | ITP-017-STR-Structural concrete | 2a70391f-9ded-4f5d-ab83-2ef16dd16621
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
bd2f342b-2be8-5aba-9837-122d3d938d35 | note | Document Title: ITP-017-STR-Structural concrete
18ba4e21-4f7a-56bd-b21f-649a5cc6ea8e | note | ITP Description: Structural concrete
03bd451d-59ca-571e-b698-366dc73e3e3a | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
7562d660-4a1b-55da-b44e-d89f81c18e92 | note | Discipline (e.g. CIV/STR/RAIL): STR
8a8eabe3-8819-585b-b4ff-c137687235b9 | note | Revision Number: 0
8c4da1d5-4bdb-5381-93c6-2a034cf69134 | note | Revision Date: 01/12/22
aceac5f1-98b6-526b-9a97-bf0680adaa03 | note | ITP created by: Victor Mira
dbf9186d-ca8d-5993-97c2-86665d1d9fbc | note | ITP approved for use by: Victor Mira
| checkpoint | 1.1 - Non Dependent
a33417e6-0864-5f4a-b996-7c8b2116b784 | note | Reference - VicRoads Section 602 October 2007
| checkpoint | 1.2 - Non Dependent
6726a6ee-d123-5efc-bd95-8fb217e75f18 | note | Reference - VicRoads Section 610 February 2020
| checkpoint | 1.3 - Non Dependent
a2be94c9-1730-553a-9d50-3864c01bff6c | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
211a0d04-0b40-5a16-9512-8867837574f6 | note | Reference - VicRoads Section 614 June 2017
| checkpoint | 1.5 - Non Dependent
d6b3b71d-b93a-5b9b-a887-901f97d53eb0 | note | Reference - AS3810.1 2018
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
af792a71-d68b-5c03-8c49-31792bcac9d8 | note | Reference - 610.07 Table 610.071 IFC Drawings
39e8755f-8b8a-5422-98c2-d6228b95faf9 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
f4e5337a-81bf-57b0-a7cc-5fa684604457 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
4e96c0ea-1bb9-5fb6-98fa-cdc5aadefde9 | textbox | Enter: Teambinder Material Approval number
62ff8715-b665-5541-b9d1-2ef8bedbfbf7 | note | Method - Document Review
cda4958b-83d7-54cc-85f9-f2384103dc2b | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
7ffefa04-1a9f-553b-8360-33406abbc467 | note | Category - HP
81946e21-0d37-503f-900c-d1d1861e4a40 | note | Responsibility - Nominated Authority
355b529f-ac42-5f88-aa36-8daf43830bb2 | note | Verifying Documents - ConQA Hold Point Release
77fae47c-c9d1-5808-8251-4604ee94704f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
72768f61-777d-5ea0-a394-621888cebf9f | note | Reference - 611.05 (a)
e1a6fef2-8fcf-5ce4-89da-4991328f203e | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
09d3cdc8-fb72-5519-a7ca-24e34744e9a6 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
8b2d496e-2598-5b43-9e88-177f504e21ac | textbox | Enter: Teambinder Material Approval number
e3a8a0bf-bf38-51f0-89dc-337b39d0f9df | note | Method - Document Review
bd956417-ea07-556d-899f-e782d4d5704d | note | Frequency - Once for each supplier, 14 days of award of contract
ee813f9b-f6b7-5f1e-ad3f-8c3706f3c9b5 | note | Category - HP
15214f2b-9fb8-5258-a438-2de5d09f7a72 | note | Responsibility - Nominated Authority
1dcb3acf-817a-5b75-a97f-d2b63ae19692 | note | Verifying Documents - This ITP
3813b8df-8aa9-55d3-9d6c-26c19e4f1c69 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
96ffcb57-b13f-58dd-8d31-4bca6ab76ef3 | note | Reference - 610.26 (a)
c84467f9-10a3-54fd-afb2-ca7f4c2d05cf | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
2a9cd5b1-0b60-5165-ae86-a958412673dc | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
048b6ba5-2de1-5815-b287-006f0d2407a4 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
176d1058-5c86-5a25-a03a-2625d5c3a96c | textbox | Enter: Teambinder Material Approval number
10c9a689-32ca-562a-8ee7-005085339104 | note | Method - Document Review
9d4b1e3c-3b58-5f0c-a2b8-6b26489f44b9 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
25614107-9de5-5ba6-88d4-033e60b3289d | note | Category - HP
40fb5f17-ed0b-5305-b93a-45d206d5045e | note | Responsibility - Nominated Authority
23da94e2-0a0d-558f-a75d-d24ce99a4df4 | note | Verifying Documents - This ITP
438fde43-95d9-53b2-a805-38e05fc6f864 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
06726874-9d7b-5d86-b1af-38e5ea938382 | note | Reference - 610.17 (f)
171a7547-9956-53a6-9f90-a80f1d5ba929 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
68731a50-7b6c-5aed-872a-ce6801075ba7 | textbox | Enter: Teambinder Material Approval number
352c0bb5-ec52-5249-a13c-a2e79c2caa8d | note | Method - Document Review
94f47226-c5e7-5706-814f-a4d0c3e88b4f | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
6c22f27a-2022-53fd-b616-54861a9c6d9f | note | Category - HP
93a9b5b3-fa07-592d-96a9-46720bad301d | note | Responsibility - Nominated Authority
19792e76-310c-5cfb-b9ef-84a64f59b25e | note | Verifying Documents - This ITP
236c96d9-ad3c-5808-be3f-49c4899ec9d7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
ec132ec9-3357-5fb9-9cb3-b520c73c9233 | note | Reference - 610.23 (d)
b0517335-80a4-5e92-8586-57c5f4325e7c | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
23d39d3f-2c06-5cfa-b7a0-c141b822ce29 | textbox | Enter: Teambinder Material Approval number
66d1f230-00ec-5ce5-a5b3-1ac1455d5b5c | note | Method - Document Review
0844324a-2720-5454-a529-de33f300035c | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
f1f9e1d5-adea-5aba-acf5-bb99f674eded | note | Category - HP
d7b64b1b-69b7-50cc-9ad8-a09396b658d4 | note | Responsibility - Nominated Authority
e28cc53a-39af-5a1d-9ff9-8a23881ede44 | note | Verifying Documents - This ITP
aa3ede60-1046-5f14-aba2-9b36132d2fce | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
6f0dee6f-c325-595e-8668-74cd7a78947f | note | Reference - 610.18 (a) (i)
8fa2facd-1f9c-5b54-8122-a90384232d74 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
72974378-f9d5-5a67-a6bf-08a29f853e84 | textbox | Enter: Teambinder Approval number
ee1e022a-1bcb-572a-9f56-1aafda43a17d | note | Method - Document Review
d99c0510-42d9-5cb4-a928-577c8c619216 | note | Frequency - Once, 4 weeks prior to placement of concrete
7d6baefa-f631-5cf8-a338-4059830482be | note | Category - HP
8848b448-2835-5bf5-9bf6-b3756d3d1466 | note | Responsibility - Nominated Authority
7cb37875-225a-5d65-b803-02a435515a05 | note | Verifying Documents - ConQA Hold Point Release
1910cb2b-3de9-5def-9888-8dd01dd88b24 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
2b8831b1-77cc-535a-8d71-ddd3b0801a83 | note | Reference - 610.18 (a) (v)
43543c6f-e549-5430-aab2-c6aa05f60cd4 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
12b26039-afe6-5ec2-8ea1-940e73f74e28 | textbox | Enter: Teambinder Approval number
0ea987db-fed6-5d93-80d0-e3a2d8d54d9a | note | Method - Document Review
87eef7cb-3dfa-5b6e-9e78-fa2b804922b3 | note | Frequency - Once, 4 weeks prior to placement of concrete
495afd3d-3374-5d42-a4ac-b05213ad2451 | note | Category - HP
5c14e1c2-8951-53be-a4fa-80fd665553b1 | note | Responsibility - Nominated Authority
a81c876f-c1a7-5073-8a8f-794e20e7fdc7 | note | Verifying Documents - ConQA Hold Point Release
6b9d5f0b-438b-59f3-aead-ecf3023c88b8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
a7ad7e3d-2612-57e7-949c-f61750406a08 | note | Reference - 610.18 (a) (iv)
799675f9-e35e-5f72-a154-e07d9f7754a9 | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
f6107bd6-5b86-5bdd-97f2-b0a8dd0917ea | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
7850de00-2428-5bb5-8018-342969936bb1 | textbox | Enter: Teambinder Approval number
25ee5c32-a41d-5212-b09c-d8197850b019 | note | Method - Document Review
88ee11c1-10a7-58aa-90fc-5b7fd00bead5 | note | Frequency - Once, 4 weeks prior to placement of concrete
1e010b08-8c18-5849-9e7b-77bcf386cccb | note | Category - HP
38221f17-2f48-5626-8352-e11a5b468f1d | note | Responsibility - Nominated Authority
f55b6d97-2142-5444-9477-be8233999bcf | note | Verifying Documents - ConQA Hold Point Release
c617e6bd-89b7-50e4-9ebd-6b93839c4273 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
13f63b4e-20b5-517f-82d4-04e10b38c424 | note | Reference - 610.17 (a)
70cef88f-0e31-5dd7-bd71-192f9ea7d67b | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
13b6bd3b-64dd-540d-b6cb-aa4aa0551425 | textbox | Enter: Teambinder Approval number
ce145703-2f39-5d35-a764-be367d5ca49c | note | Method - Document Review
ad6946e1-f83f-5b04-b25c-3f16a658915f | note | Frequency - Once, 2 weeks prior to placement of concrete
3d208da1-5435-5716-8318-efbaaf461b4a | note | Category - HP
4ae7970a-6167-5fbe-9d17-fbe63791eed3 | note | Responsibility - Nominated Authority
cdd171d8-03dc-5a20-9899-c9718510cabf | note | Verifying Documents - This ITP
a5aede70-0d8d-58ae-83de-0b6f6b6695fb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
934109d3-a2c4-55a5-8ba0-f1e631c1d148 | note | Reference - 610.23 (a)
78b7b89e-253e-504b-a195-c3d5a25ee8aa | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
2e951641-d335-5613-a83c-40a4127d6a15 | textbox | Enter: Teambinder Approval number
3b55396b-82c1-55f0-bd82-30a80cb2cf77 | note | Method - Document Review
a1153721-646a-54ad-8928-474f89f50a38 | note | Frequency - Once, 4 weeks prior to placement of concrete
4dccc7b0-3949-5f9d-a3e2-75ac4aa7fffb | note | Category - HP
7b0b46c4-0a56-5e97-8aaa-6a3c7b74f870 | note | Responsibility - Nominated Authority
aa733904-62c6-5e9e-8b39-a222d19722e8 | note | Verifying Documents - ConQA Hold Point Release
515e6cab-9be9-5328-bf10-cab0f7bb7bc8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Concrete Drilling Procedure
b0124a09-4156-5edd-aa12-9643ea5629cc | note | Reference - 610.46
aac9e1e3-b0f9-5d63-bc9d-0dde4813efb4 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
3fc774ca-7b70-56f5-9f93-8d1333b9593d | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
220f4370-3447-5f5a-8927-857d857cf168 | textbox | Enter: Teambinder Approval number
6a1934c0-7a07-54b6-a483-79aa6a43fb9a | note | Method - Document Review
da65ad6d-2e84-56c3-aa31-7d0d77c7e6f2 | note | Frequency - Where applicable, once, 2 days prior to drilling
809095fd-2f4e-52c9-9b46-50830182d739 | note | Category - HP
bb1fe959-9574-56ca-adbf-d386ff08e56c | note | Responsibility - Nominated Authority
4ac8bb90-0624-503a-a927-cff682fd5808 | note | Verifying Documents - ConQA Hold Point Release
c1c90ab1-f924-5be3-8c01-8dbaa6417f75 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Temprature difference measuring-Calibration
ca8007da-5bc2-58ac-9fd3-2dbac012e938 | note | Reference - MRPA Quality Management Plan
db2fff19-2231-5727-a30b-b79c0f2d000e | note | Acceptance Criteria - Calibration records are valid and up to date.
f0e85fc2-0ee6-5f3d-8b07-e32f343033ef | note | Attach: Calibration certificate
4ee0ce6d-6e3e-56c9-900b-8aa83c67d252 | note | Method - Document review
95791d7d-56f0-52e6-8953-08a083f4c497 | note | Frequency - Where applicable
2f1446a3-f86a-5833-8415-7e6ce03b686b | note | Category - HP*
fdb2e59f-0732-590f-b1aa-42b6c519cf9f | note | Responsibility - PE
69cf74cd-9d7b-5b7a-805e-44e1ecdbc923 | note | Verifying Documents - This ITP, Attached calibration certificate
a112c65d-25bf-5a56-9126-8d634c2de457 | date | Date Completed:
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
08985e92-41e8-5590-acbf-ccc138f0e75b | note | Reference - MRPA Quality Management Plan
cdcebd6d-6a43-544e-b3d0-4d6ea3429b95 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
77afa9cc-2f69-57ee-9941-ac8b4cf1309d | note | Method - Document Review
1d46c227-e343-53ee-87db-b9741734abd8 | note | Frequency - Prior to starting Works and at regular intervals
6004b695-26ef-50a0-93d3-21edeb5b5b14 | note | Category - HP*
60dfd7bd-e3fd-58fb-9866-6b852c90247c | note | Responsibility - All
b6bc1b2a-860e-505b-acba-ea4ff0434ac9 | note | Verifying Documents - This ITP
da7b5284-837f-50c8-9b9e-793b94daf882 | date | Date Completed:
| checkpoint | 4.2 - Survey Set-out
c8eeed26-e399-51d4-9899-ff6258f17eff | note | Reference - IFC Drawings 610.47 (a) Table 610.472
ca9d9bb5-8846-5deb-88c9-a6a2e1d9fbd2 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
d00fba9a-d7c7-5e4b-a141-0a23d08e2d58 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
b51b0d18-7ec9-5aef-9bbb-835fcfb05541 | note | Method - Measure, Visual
c1a55da6-eca0-5908-8120-2b72dac9117c | note | Frequency - Each element
a7e7b5e4-7966-5d28-8ea3-8670c9591d33 | note | Category - IP
e7f5a275-74df-51b7-bc8f-1c950a6d0134 | note | Responsibility - Surveyor, SE/PE
987d7d15-df2d-57f0-9244-6329b38ebd2e | note | Verifying Documents - This ITP
4a61840a-4b4d-5b9f-b93c-3a647961368f | date | Date Completed:
| checkpoint | 4.3 - Excavation support
69255910-e8b2-50dc-825b-d0f8767315a4 | note | Reference - 602.02
a5d28ae2-3dfe-553a-b524-b954428ec64f | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
5ad4d986-adc9-5e8e-90fb-5d507f3b4a41 | textbox | Enter: Teambinder Approval number
1b26676d-8f15-5cd2-a241-8a6ec8d1f2a9 | note | Method - Document Review
f6cd4ed3-289d-56d3-866e-a0d7ca16eb55 | note | Frequency - Where applicable, not less than 10 business days prior to excavation
2e7e5cc6-dfb2-57b5-9eea-c4a98b4aa8c6 | note | Category - WP
a504382b-5e07-5d39-b131-1196fb122d78 | note | Responsibility - SE/PE/SPE
697577d2-f191-5978-b81b-49229f84a4e1 | note | Verifying Documents - ConQA Hold Point Release
b1449a57-6df5-504b-8528-9b19b9f3cb80 | date | Date Completed:
| checkpoint | 4.4 - Excavation Inspection
782e87e4-e521-5e6f-9a81-3470e31fb56d | note | Reference - 602.03
fd8902f2-623a-5049-bd59-2116b1e7fd5f | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
3d1b5ae5-e441-5597-ad85-2cb9ae18f8df | note | Method - Visual
c9a04a34-b27b-5ee4-a272-dd393045812e | note | Frequency - Where applicable, prior to placing blinding concrete
bb8d47ba-53d0-59ad-a9d8-2feada695639 | note | Category - HP
ccc3c39f-6351-5c4a-8779-c6ed18b814a3 | note | Responsibility - Nominated Authority
b10a50b6-9e57-5e71-9be1-c2c06a9a93c1 | note | Verifying Documents - ConQA Hold Point Release
3d202c56-c644-527c-9f4e-d5eb00295886 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
6992fab6-91d1-5920-88ee-fe71a370fcf8 | note | Reference - IFC Drawings 614.04, 614.05, 614.06
dc50f857-58c7-5b58-bd67-9fdd994f2736 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
1cae2217-9e6f-5bd6-8b94-9ac62cb1419a | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
2fa71bc5-f741-5e4b-b802-6547ef100770 | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
32eea5ab-9cb2-5f02-b2a3-9ecf708e64fa | note | Method - Document Review, Visual, Measure
4c212454-4e45-5022-a5ca-e5f800f99b08 | note | Frequency - Each type of element
0a364115-461f-5c9a-bb93-d9541b18966a | note | Category - IP
b1764228-e6da-5ec7-b622-200fe7775b6c | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
df8fc66d-d343-555a-ab21-42c70601923b | note | Verifying Documents - This ITP
acf821dc-99bd-595f-a097-f4b764583bac | date | Date Completed:
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
e1151143-12d0-5f0f-8b4b-83471f13c246 | note | Reference - 614.08
3bc86840-b2c7-5ce0-8aa7-6a61bf691dd6 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
e50801f7-300d-5181-bc0c-72ea905bfff6 | note | ○ Walls with heights greater than 2.0 metres
0cbde7c5-9442-50f0-97ef-b2ddae304fba | note | ○ Any member for which self-compacting concrete is proposed.
9d840773-ca73-51f0-bf57-6f3579c4111e | note | Attach: Attachment A
df7cb9cf-a712-5fdd-8332-4a786e2bc334 | note | Attach: Attachment B
45970928-51c7-53a3-a999-ac84cb277443 | note | Method - Document Review, Visual, Measure
8bf9982a-2f49-547f-8226-ca6a2f3f50d0 | note | Frequency - Each element (where greater than 2m)
e9a52113-cab1-5616-a61a-e85ad1cfd10a | note | Category - HP
405e5502-e915-50cc-8b32-ea426f3fa2ff | note | Responsibility - Temporary Works Designer, Proof Engineer
7f6440d5-0110-57d4-b52b-51bc5def21c0 | note | Verifying Documents - ConQA Hold Point Release
8e1ad566-dce0-5418-a67d-942b8b7a83ac | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
7fc846b8-83f0-535d-a458-9717630993b9 | note | Reference - 614.08
343eb449-d7c2-5dec-bce5-fbabcd3d9ac8 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
70bc9941-ba5f-5432-8b4d-776ac67fd013 | note | ○ Walls with heights less than 2.0 metres
01d8e9cc-7535-5501-af10-feaf5e659b6b | note | Attach: Attachment C
f33eb1f1-39ba-5c58-99ef-153c7f65f931 | note | Method - Document Review, Visual, Measure
d260fc5d-fee3-59f3-8981-d7d711d27764 | note | Frequency - Each element (where 2m or less)
5f4edf48-b916-5799-b884-ab2beedda29a | note | Category - HP
02fc7e83-4813-5e0b-865d-8e2e49d9131b | note | Responsibility - Temporary Works Designer, Proof Engineer
cb29eb19-fbb1-5b18-b032-fbb8705d34da | note | Verifying Documents - ConQA Hold Point Release
1af32547-6d7e-5648-849f-32d7b88402d4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
82ca1b88-6124-50bc-bc89-9bf2baff9e79 | note | Reference - 610.47 (a) Table 610.472
35dc7ea2-ba90-5560-b8c7-16252c71fa03 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
cd1a441c-c9ae-519d-88cd-410479ab2722 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
de95a010-e6a4-510b-84a4-55d3afa69b7f | note | Method - Measure, Visual
a86d4634-67f0-54f7-8baf-b2ae3a014671 | note | Frequency - Each element
2d82a8e1-d072-5d5d-b909-d990769db065 | note | Category - HP*
9d674c77-fe39-5ace-be87-2b71c6c2cf2c | note | Responsibility - Surveyor, SE/PE/SPE
e48e0187-7e0f-525a-a4e5-064f4a52dae6 | note | Verifying Documents - This ITP
695cf60b-766c-5f46-be3c-b24b70de8274 | date | Date Completed:
| checkpoint | 5.5 - Reinforcement Placement
deb12f6a-7611-5653-8150-1d09167a414d | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
b9e008f2-adb0-597b-ae2f-3392b4f814ec | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
f0f0a982-18bb-57ab-b5f5-9507d8645d3f | note | ○ Projecting reinforcement is the correct length and location.
26065dcc-57ac-5aca-b0f4-c63c1dbed064 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
99c7009a-e59e-5e8f-9c50-4969adbc7adf | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
565d1e09-369a-5ff6-bf87-bc6501516c56 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
0d4ead09-bad7-5781-b1e3-c6e7b92bfe35 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
677af706-807a-5e99-be85-8f7d35a1ef30 | note | Method - Measure, Visual
774bff88-b2c1-54f2-9f5e-84cb2e2c0739 | note | Frequency - Each element
6f446826-98a3-5b23-a4fe-63aef42a1735 | note | Category - IP
780cdf86-a958-5f1b-aeb2-c5856fc52a1a | note | Responsibility - Foreman, SE/PE/SPE
e0076e08-9e7a-53c0-a8a1-79b3086a1191 | note | Verifying Documents - This ITP
47f6e7fc-7dbd-544e-8159-0c1e72273cad | date | Date Completed:
| checkpoint | 5.6 - Cast-in Items
a4d7cf9e-9de1-5917-b256-589917818501 | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
de0da661-529d-58c8-a4f9-24e164b3ec8e | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
086eaaa1-b6ed-5283-9ee4-4ecd9d47c117 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
27d14032-5c08-582d-bf2e-f1d1109490bb | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
22934175-cca8-5bdf-ad32-3f8628dd813f | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
2c186d2c-d61d-5cf8-9571-566e23cbe6ef | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
50af0a90-4e70-55d9-b429-50b8f442ec3f | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
6d8b7121-7f89-5030-bfa8-26c5d2470166 | note | ii. Running dimensions of a group of the above = ±6mm
387e02be-109c-50d4-9c56-ab7d8667235a | note | iii. Ducts and conduit location = ±12mm
c0e2ba68-b1e1-5dd8-baac-b41d9c919de4 | note | iv. Diameter of ducts and conduits = ±3mm
ff1d88b8-006e-57f4-8ed4-dea959cfa19c | note | Method - Measure, Visual
1e0128cb-047c-567e-b220-e5b46a06abf7 | note | Frequency - Where applicable, each element
fffe0ba9-50a9-5ed4-8138-2973b9c0d3a3 | note | Category - IP
9d986076-e3ce-5c4f-8b84-7506c32b13c6 | note | Responsibility - Foreman, SE/PE/SPE
f5f63297-6ba8-5598-9c78-bf3184f4698b | note | Verifying Documents - This ITP
275c07bd-c852-5234-9b91-77e023db73d9 | date | Date Completed:
| checkpoint | 5.7 - Thermal Differential Monitoring
397735ac-941d-5b40-82aa-c7968ceed093 | note | Reference - 610.22
910bde99-0cb0-51b0-80b4-d1939c97f24a | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
f4685eff-d330-5ac0-b872-4924d1f55d67 | note | Only applicable if the element has:
bf230c6e-b9ee-59c6-be4c-c9297890a64a | note | i. the smallest sectional dimension exceeding 500mm
635a1951-6bbf-5ed2-be96-c2d77bf1730f | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
2b69b6c0-0769-568e-914c-35c8280c2729 | note | Method - Measure
76e67f84-591d-5d88-a630-f7af27b8b880 | note | Frequency - Where applicable, each element
b780ff0d-6f4f-574a-b854-63fa92181f39 | note | Category - IP
7ab19ff9-4bad-5ddf-bb48-f1709aaad098 | note | Responsibility - Foreman, SE/PE/SPE
150bd8eb-7c56-5b13-97a7-39e69a42242d | note | Verifying Documents - This ITP
b4b43339-fae3-5681-a569-e0e2f2cd9bbf | date | Date Completed:
| checkpoint | 5.8 - Pre-pour Inspection
d06ab918-50f1-5e75-9176-43f07b153979 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
3bfa1b03-a7ca-5bc6-b77a-9b56603b345a | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
25a3af25-2f5c-5b2c-9a2f-d12a648b05b3 | note | ○ All foreign material has been completely removed from the forms.
a0415887-23ee-5026-952e-5f25dd20cd4d | note | ATTACH: Pre-Pour Checklist
8b1df1ce-4c47-5a2f-a15e-6897aa90327d | note | Method - Measure, Visual
e2894fde-6936-52ef-b6c4-10f5c47d7b87 | note | Frequency - Each element
59f31472-618e-5a5d-aad8-5f819f60986f | note | Category - HP
fa14fadc-5063-539f-9292-c6e5c54fa337 | note | Responsibility - Nominated Authority
09aa7ab0-2888-580d-8dda-257d113a0d26 | note | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
5f8440eb-74f5-51ce-80af-7e28659f4afc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Weather Conditions & Evaporation Limits
cb3be6fe-0efb-5bb4-b5b3-25a9791b2a08 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
08060fb9-e746-5068-998b-4474d18fee38 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
ff9ba82f-7ecc-53f9-8aa7-c57e8ad2e6bd | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
f71b56d7-ae8e-5302-a92e-c2fd79089907 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
50cf4f19-659b-591b-92bf-cf1be29a0138 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
819b53d1-d113-5b6a-8e04-263c5975e50b | note | Record: Required information on the Concrete Pour Record.
8e3ff3c9-6a6b-58a0-ba12-e9a20820dd82 | note | Method - Measure, Visual
a68c298b-2d4e-5ef2-aa9c-a15b06bc43d9 | note | Frequency - Each element
863f5644-0fd5-5cf5-8fe9-c0c897edf891 | note | Category - IP
c5ac1501-d470-5b53-a879-ce7081c13693 | note | Responsibility - Foreman, SE/PE/SPE
d2b2a2f8-380d-59f0-bdcd-64d0e32a448d | note | Verifying Documents - This ITP, Concrete Pour Record
be085f5e-c691-562b-9ab0-574e81097714 | date | Date Completed:
| checkpoint | 5.10 - Concrete Testing - Sampling Frequency
4ad2afdd-1f90-5b3a-9d86-f0aa25ccd1d0 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
c962228a-40e4-5d14-a24d-e24c5e3ffcc0 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
02a00e98-0feb-56bd-b008-207b3713f4f4 | note | 0m³ to 10m³ = 1 sample
92af27fe-36c4-5f08-a77f-a1a3f43d9b86 | note | 10m³ to 25m³ = 2 samples
5ca6740e-d399-566a-a8dc-f823c626ac19 | note | 25m³ to 50m³ = 3 samples
20d0c58f-3c65-5be1-92e2-87303eda064d | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
aebe5f9f-fc03-56ec-90e1-db4186d27fcc | note | ○ For each additional 50m³ and additional sample shall be taken.
c2c359ba-781e-5f33-9496-b84b66a12356 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
0682f843-6fad-5dab-8f53-614616fcb8ed | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
6de72ba8-822a-5c10-a96c-9368407b94fb | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
94197f89-6929-5a19-b036-ca5306922f3f | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
e696e884-27de-5951-817f-30c45ae6ac66 | note | Record: Required information on the Concrete Pour Record.
7b132439-ebf7-52aa-9b2e-28e81af49494 | note | Method - Test
7fab640e-e381-52ca-b692-543d8defd33e | note | Frequency - Each element
84d7372e-839c-5d28-8624-222adfdfeb50 | note | Category - IP
665e0fed-6445-5835-9194-0302b4c89681 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
07ad0d22-9ee7-5624-8ade-684fc69f60c8 | note | Verifying Documents - This ITP, Concrete Pour Record
0213828d-8336-55e6-9113-ed217596084b | date | Date Completed:
| checkpoint | 5.11 - Concrete Testing - Slump
fb24c2fb-c477-5774-8b70-13fe4366957d | note | Reference - 610.16 (c)
948bffd2-6986-5fa0-a668-086b7523d200 | note | Acceptance Criteria - Slump testing tolerances =
5c5d4cf4-77d4-5cc2-8155-d237cb8a825d | note | <60mm = ±10mm
357be78f-14c6-5039-a5ec-eeecff4eb5b4 | note | ≥60mm to ≤80mm = ±15mm
9db45a0e-7582-5dae-ae4b-a1d02708065d | note | >80mm to ≤110mm = ±20mm
85941b4e-2640-5d0c-bf29-8224d358343e | note | >110mm to ≤150mm = ±30mm
d83eeb38-aa4b-501a-b8e2-a82bd81663d9 | note | >150mm = ±40mm
99901afc-b24a-57d0-a54c-1dc897f1ae56 | note | Record: Required information on the Concrete Pour Record.
8942ac95-5e16-5bfa-a650-a5ff640f8d2a | note | Method - Test
fc87e65a-0270-5915-b745-181f1e50de6d | note | Frequency - Each sample of Standard or Superplasticised Concrete
0010d650-9bfd-5a0f-8994-41810f5a1ad4 | note | Category - IP
8df1c006-5799-587c-b5ba-00b6e4e081b7 | note | Responsibility - Concrete Tester
368dc4bd-158f-568d-95a0-d4c7eb23c9a4 | note | Verifying Documents - This ITP, Concrete Pour Record
96fee3a2-f6d2-54fe-85a0-bfc060f4909c | date | Date Completed:
| checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
9bda63d0-8ade-5e9a-add3-f71514472598 | note | Reference - 610.13 (b)
318237df-1f37-5bde-8b19-76a9f23a352c | note | Acceptance Criteria - Spread range = 550mm to 750mm
ea60c3bc-0812-5036-aadf-41d89bb63fb1 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
6dcece7b-eb6c-566c-b83b-4f986ed1ff7d | note | ○ Passability = ≤10mm (aggregate height differential)
5e8ce836-41cc-5591-8341-21e5d9f5d2ad | note | Record: Required information on the Concrete Pour Record.
bc201295-5c10-5032-8f59-6aaeab0ded37 | note | Method - Test
a80b0f59-1852-5c8f-87cb-1948ec25647f | note | Frequency - Each sample of Self-compacting Concrete
558cd712-7d5b-53a5-adc3-22604cba7c7e | note | Category - IP
8f241bed-8f22-5058-a6be-3e74726b6de6 | note | Responsibility - Concrete Tester
f1214410-0e2a-55c0-b69f-24246da0ed16 | note | Verifying Documents - This ITP, Concrete Pour Record
9c5abe86-563c-5691-a8af-1ba32eef4590 | date | Date Completed:
| checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
063de718-2cda-54d2-9820-9a0ff689bac8 | note | Reference - Site Sampling & Testing Procedure
863d64eb-9444-5271-a746-cf4acc85b3a3 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
78eb0c1d-98d5-5fc2-bf27-3b153fe017d5 | note | Record: Required information on the Concrete Pour Record.
a371f7a1-6334-51f5-bb35-73ac4be1a66c | note | Method - Test
42f7d305-3201-5ac6-8a43-3b5f0cf0af1f | note | Frequency - Each sample
4e6f79f2-1430-5186-b3b5-325fd0094776 | note | Category - IP
54e1ad28-32ff-50ee-bb51-3fd2f3abd2e5 | note | Responsibility - Concrete Tester
9547cb4d-2067-5fde-b911-86f9e2bf9664 | note | Verifying Documents - This ITP
80f31e03-672e-50e2-819e-ecf9f4ca4bdd | date | Date Completed:
| checkpoint | 5.14 - Supply & Discharge Rates
7335262d-8603-5d64-87a9-8006e1bbb4ab | note | Reference - 610.13 (a) & (f)
4d674a14-ca76-58e4-bea8-515dd92ac63f | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
ebd153f9-3a47-52e2-a2f4-9a6222ff8e86 | note | ○ No water is to be added once discharge commences.
e55b380e-5e8f-535d-a8d6-eeddcec20879 | note | ○ Maximum time between batching trucks is 25 minutes.
453ccce0-d4a8-543e-a8e2-9348a19bfc69 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
ec1fd5e7-6d6d-57e7-84d2-32cbca3c89da | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
c8a3ff8d-10d6-50f5-bdd6-11fe3696bbd3 | note | Record: Required information on the Concrete Pour Record.
b6154554-e649-5987-a2b1-2b0fbf7545e6 | note | Method - Measure, Visual
5554939c-abf0-5d32-bf63-16fe689a52fd | note | Frequency - Each load
0d129dea-9024-52de-ac63-415e4c65ff6e | note | Category - IP
1ee61008-7499-56fb-b8e5-6e419af92686 | note | Responsibility - Foreman, SE/PE/SPE
94dd52ac-12df-5410-aac7-642feddb55c7 | note | Verifying Documents - This ITP, Concrete Pour Record
283e92e5-bbe5-52b4-8c79-b156db9c44ce | date | Date Completed:
| checkpoint | 5.15 - Placement & Compaction
8e1e9b65-83c9-57b4-a3d6-2765d295fd9c | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
d99fd762-3e51-527f-bfdf-60cc4962cd87 | note | Acceptance Criteria - All concrete batches are traceable.
d8993057-103c-5d49-8b49-414aeeadfd7f | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
e5abd859-b5e3-59e2-b1a4-bd8a81d23922 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
10ff67d6-2735-50bc-bd1e-701901d11d49 | note | ○ Concrete is not moved horizontally by use of vibrators.
3d320554-2deb-5d09-80de-bf3219d4a6a1 | note | ○ Adequate compaction is ensured
3f51e5c2-0e63-5803-be64-dd825c533387 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
5254aa8a-25db-5f3a-bba2-32d8ac476bbb | note | ○ Concrete layers are not more than 350mm
003f75ec-dc00-5cb5-a616-3b21ee32f9f9 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
91870db5-6acb-5c63-bb5c-0214a8973069 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
d3a667ba-944a-58f5-9f86-c5fb83b45160 | note | Record: Required information on the Concrete Pour Record.
15b90f95-9259-5adf-bdd9-0bc11fea00d0 | note | Attach: Concrete Pour Record
f3e54e65-b9e3-51fb-8af1-9b7e31570e44 | note | Attach: Concrete Dockets
f21ddfca-5292-5352-87b3-06476ac3cc4d | note | Method - Visual
90bf0f99-fe51-5948-8009-5e6c73b5333b | note | Frequency - Each load
9ac93b9f-ee5d-59d7-a62f-d8c3933dc9d7 | note | Category - SP
a0827916-e68f-58ab-84ee-d75c64407f17 | note | Responsibility - Foreman, SE/PE/SPE
7bc9cf34-fe19-5295-9cb6-11c2eb4a0531 | note | Verifying Documents - This ITP, Concrete Pour Record
bf73b4ce-bf10-52f9-ae4f-45302bedad55 | date | Date Completed:
| checkpoint | 5.16 - Surface Finishes
c2f4f34a-01c1-526c-9729-430a9cb6d329 | note | Reference - IFC Drawings 610.31, 610.20
a5130cd2-c6d7-5958-83eb-de9d1145bff1 | note | Acceptance Criteria - Surface finish as per IFC drawings.
29cd02fc-8c56-5a12-8249-a0b65b7e575f | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
24fce402-2638-5243-ae1b-1328ba040ed3 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
707bd167-02dd-50b8-b741-8e4f39787cf2 | note | Method - Visual
ef2261d4-c6a3-5540-a341-6f0525da5b9d | note | Frequency - Each element
cee6fc5b-b6d9-591a-b6e0-b91ff32a6f79 | note | Category - IP
7aa5369a-bfaf-5b59-bb22-76720c8c7e8f | note | Responsibility - Foreman, SE/PE/SPE
d4098df4-5092-5003-b494-19d59f20523e | note | Verifying Documents - This ITP
6c95a393-a515-5d37-814a-11195890b97e | date | Date Completed:
| checkpoint | 5.17 - Curing-Top Surface
8d0a0cc0-55a5-508c-8ada-c15d12dd8940 | note | Reference - IFC Drawings
bad83a98-5d8c-5015-b463-3f1ef75c57bc | note | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
eefac5ca-e123-50fe-b81d-fbb873196d32 | note | Method - Visual
c686c905-d612-5d99-bde5-eef1736fc035 | note | Frequency - Each element
d3674589-e6c2-5980-a854-595cd4926269 | note | Category - IP
74261da2-4dde-5e88-b798-07209b84a1c9 | note | Responsibility - Foreman, SE/PE/SPE
6182e521-d5f3-56c5-8e3f-101d56efb4bc | note | Verifying Documents - This ITP
ecc7bee0-daaa-52f7-b889-e759082f1d27 | date | Date Completed:
| checkpoint | 5.18 - Curing after formwork removal
f69680aa-6d4a-51c5-a1bf-b9da4976a09a | note | Reference - IFC Drawings
e9c727d1-9627-55c0-adf9-feb295082aa5 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
c4b02c50-9770-5279-994e-339e517ed6c7 | note | Method - Visual
8d75b0c0-7bc9-5f2f-b752-4e82aa99d228 | note | Frequency - Each element
97025ec5-fcfc-5622-892e-f0f80c88d6c8 | note | Category - IP
abd1775e-b613-5c14-bbf0-ddb96d16f282 | note | Responsibility - SE
8c266d3c-5201-58e8-b658-6fb1361bda1d | note | Verifying Documents - Thip ITP
8a88867e-aafe-5b1f-8184-140e0c4f7f5b | date | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
80eebdb7-43ca-5a9c-a2c9-1668ff3fb56d | note | Reference - 610.22
8165a423-0566-56f0-a581-0bff214f729a | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
4810ae44-5637-55b6-afba-91bfa71f70ae | note | Only applicable if the element has:
ff6d7f73-ed5e-58b7-ba55-35826ef27c21 | note | i. the smallest sectional dimension exceeding 500mm
ae5798a8-b4d2-5d04-8bf0-9b59ff50875a | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
bab713ff-1c25-5879-8b10-f05be62ad4df | note | Attach: Thermal Monitoring Report
2e805cd2-d14b-5ac8-9e44-c721f4956890 | note | Method - Document Review
208d0c2a-2ea2-5db2-bf41-639a344d3e16 | note | Frequency - Where applicable, each element
95f2572a-5abb-586d-abae-416c73ac5111 | note | Category - IP
2679f548-e358-55f0-b601-e75cbaf1d212 | note | Responsibility - Foreman, SE/PE/SPE
2a7d40b0-1fb3-502d-bd51-aa9aefbd91f3 | note | Verifying Documents - This ITP
d43d66e2-4e91-5976-8192-de94b9649440 | date | Date Completed:
| checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
82297998-d225-5be6-9d08-bde36dfdde70 | note | Reference - IFC Drawings
1232cf2b-36ed-5382-9e8b-dec9367a1634 | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
172242ac-03f0-5774-a31c-215af8fb6bd4 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
cd3a09e8-cd6c-5380-88e7-7485cd301f46 | note | Method - Document Review
5b4b6084-3e12-5805-b2ed-cf6f3182a247 | note | Frequency - Where applicable, each element
5f3efa09-70d0-5b95-ba01-760dde92c6f4 | note | Category - IP
f7164271-a7c5-5bcb-b927-a1393eb927a7 | note | Responsibility - Foreman, SE/PE/SPE
93f702cb-2e01-5c2d-b8f8-51cda0499ccd | note | Verifying Documents - This ITP
87fdff22-0d6a-516c-a383-b03c15d80c09 | date | Date Completed:
| checkpoint | 6.3 - Surface Inspection - Cracks
f60a97bf-c945-5151-8967-63c068e16538 | note | Reference - 610.24
47bc89ca-8557-5808-95bd-c71e90d13950 | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
0fc8188b-b98d-5445-8208-463ab143782a | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
e1d9fe28-2d8e-5ecf-bf2e-61bdbbdcd64d | note | Method - Visual, Measure
ec4d7096-b630-5ee7-8c78-ccf8fbac598e | note | Frequency - Each element
0bf06c9b-746b-55be-9d93-3021d4cd3e51 | note | Category - IP
d1a46fe3-96ac-537f-88c2-3e68d48d3fe8 | note | Responsibility - SE/PE/SPE
3bb14dfa-9c82-5d6e-ad93-69ef41d4dabb | note | Verifying Documents - This ITP
41c81185-9838-5345-b6fc-9b6482b7a233 | date | Date Completed:
| checkpoint | 6.4 - Surface Inspection - Surface Finish
4da581e9-cfb0-5375-a097-84362cbb8b7f | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
78997794-01d3-570f-8960-49d1e9370ead | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
f5082051-b67f-5a7c-bb07-6284ab5179c0 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
780b9b73-a5b7-50b6-8f2d-34e43170306b | note | Method - Visual
ba0ddd49-ac6b-50db-802e-8b9cb6544029 | note | Frequency - Each element
f6195762-893f-5b43-867b-9c722786cdb3 | note | Category - IP
ecd5548d-9ba8-5e52-8ff8-293ad12c9337 | note | Responsibility - SE/PE/SPE
57618440-3400-5466-becb-2326706510e5 | note | Verifying Documents - This ITP
9f91df0d-5e0a-520d-9f65-33dbb3cf76ee | date | Date Completed:
| checkpoint | 6.5 - Measurement of Concrete Cover
5541add6-8343-55da-80c9-84bdf2645d32 | note | Reference - 610.34
9e27ad70-4418-5ff8-8cf1-b431da9e91bd | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
683d06d4-b072-570f-bf80-79f0493a0b00 | note | ○ Minimum 10 no. measurements recorded in each area.
7074cae0-c04c-5aef-b162-d95c9c045b35 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
63b703fc-d1d4-5d07-bac8-82c82b6d6e5c | note | Attach: Covermeter Check Record
dbe34793-6ca2-50b7-a25c-178f25552b8e | note | Method - Measure
c4ae64c5-4b60-5f70-90d1-0eeef70e41ee | note | Frequency - Each element
d3da17db-e652-5a4d-88b8-5a0eeaf88434 | note | Category - IP
daba4809-869e-5c42-84c5-ce1856a4a541 | note | Responsibility - SE/PE/SPE
e0e65985-aa6b-5b8e-8c23-f3cf50419a95 | note | Verifying Documents - This ITP
2969845c-f5c2-59f3-8055-15ef47270ee9 | date | Date Completed:
| checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
2f8306f9-d9df-5dc3-9cfa-0cc6cf767d74 | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
2960618a-c208-5c6c-b67a-26b358cc1366 | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
0202a066-cdb3-53d9-81c7-0af7bd394218 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
9f921509-b1e3-5f15-9cba-4321d69751eb | note | Attach: Concrete Test Results or Maturity Test Results
8413bf00-512c-594e-a447-39ec5ebab5b1 | note | Method - Document Review
e86794a7-5fbb-57c0-9d71-65814fc6691b | note | Frequency - Where applicable, each substructure element
282f84f9-a6ab-5809-bb70-3946de3b5fd1 | note | Category - SP
bdca7e56-433b-5f98-a763-11e3b74fda41 | note | Responsibility - Foreman, SE/PE/SPE
6579b3a5-71d6-5f2f-b6a6-61131bd3cbea | note | Verifying Documents - This ITP
90cb266e-d217-5e9a-889b-e960755399a9 | date | Date Completed:
| checkpoint | 6.7 - Compressive Strength Test Results
e0f4bc45-292e-5dbe-be28-7f5f5a997eb2 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
3f64b684-fe4e-533e-b0c8-657f86a13768 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
f63c5b92-43d5-50de-8c0d-3aa1f14ad48a | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
a0876829-e1c4-5029-ac8b-6e731939d8b5 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
da4f064c-422f-52c3-9325-f39452faea91 | note | Attach: Compressive Strength Test Results
f383909c-919e-5774-bda9-1a90c516ce8c | note | Method - Document Review
05d394d4-c2ef-55e8-917d-bcc5f18ea216 | note | Frequency - Each cylinder
d33ab4b3-2261-5451-8914-23558a93450d | note | Category - IP
edf9b540-a936-5511-b7de-b32ac3a64dd3 | note | Responsibility - SE/PE/SPE
8aa98d85-f73b-5987-848a-b78ca35980ba | note | Verifying Documents - This ITP
75ca58b6-3aa3-5fa7-bd85-4f835de93271 | date | Date Completed:
| checkpoint | 6.8 - As-built Survey
9db57ddc-f047-508a-82a4-ff4231cd12b1 | note | Reference - IFC Drawings 610.47 Table 610.472
26d62b63-9eda-5b17-808a-cf5f39a91d1f | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
f84701b1-c18b-51e3-9d4f-084f24367d14 | note | Attach: Survey As-builts / Survey Report
a7b81fff-e6e4-5db4-ac1e-aedfbe3e5fbf | note | Method - Document Review
af40485f-35b7-5636-a991-4a7dc3c36e26 | note | Frequency - Each element
0dec67f9-b1a3-5317-b3ba-d63f80ebba6c | note | Category - IP
3761847d-9c0a-55a9-a8d0-1e0fccab30f9 | note | Responsibility - Surveyor, SE/PE/SPE
61be9adb-a3f3-50c1-b0af-11bc06d772cd | note | Verifying Documents - This ITP
695a3189-96db-5a8b-9c91-aa90a30597da | date | Date Completed:
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
d8452e65-edf5-5d82-97fc-84c366a3fce0 | note | Reference - MRPA Quality Management Plan
a782ab54-e1b5-5f4e-b0f7-053f8dcc23b0 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
8121c4f7-0b55-51f3-b70a-5471c061b0c3 | note | Method - Document Review
c9d3b1ee-f639-5af0-adff-38fc9546f689 | note | Frequency - Once, prior to closure of this lot / element / Work area
7c4740ce-f2b3-5b9e-968f-30aaf0987623 | note | Category - HP*
ee704a48-08b2-521b-a9f0-2b294a564801 | note | Responsibility - SE/PE/SPE
7083280b-6284-5d5f-9ede-632b2764194b | note | Verifying Documents - This ITP
6645cbec-7345-55ce-ad58-042479e64d01 | date | Date Completed:
| checkpoint | Final Inspection
f36e5999-b796-5e9e-88e9-0ddc5b2fdc33 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
15277e10-5889-53b3-90f5-fe4922615102 | textbox | Name:
6c88b4e4-c408-56dd-b217-65f693ea5198 | textbox | Position:
285d6882-d8fd-5434-b76f-8f7c75cb31b5 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | itp | ITP-045-CIV-CPD-Subgrade Preparation - Road | 9430c0e8-7582-45cd-bdc8-07b023f65665
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
7528f190-4343-5025-8b1e-528d2d9de0f6 | note | Document Title: ITP-CIV-CPD-Subgrade Preparation - Road
aaa761ab-3732-580d-9648-a5cd54f95c3b | note | ITP Description: Subgrade Preparation - Road
aab28051-4d93-54b3-b9ab-33ceaa561a9d | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
5c1d458b-4804-521b-9d62-ba7b625d9a5d | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
437a1dda-629e-52a0-a8b0-041f8633de3c | note | Revision Number: 0
60823dcb-b438-5709-8bc9-c8433430c392 | note | Revision Date: 12/07/2023
a034d993-29b4-56be-ad05-f59c38b94c9c | note | ITP created by: Matthew Dib
1ec0b0cc-c1f5-56ae-8819-961862550527 | note | ITP approved for use by:
| checkpoint | 1.1 - Non Dependent
8001842c-e8f6-57fb-b222-6919b0f65418 | note | Reference - VicRoads Section 204
| checkpoint | 1.2 - Non Dependent
0b420d85-5188-58ba-ac75-13e88ef529d3 | note | Reference - VicRoads Section 173
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Non Dependent
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - Non Dependent
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-Out
92b8bc7c-0f24-5f3f-8d04-19e7fafeb1cd | note | Reference - IFC Drawings
69784157-e96d-5af0-a8c3-23c13af41a7d | note | Acceptance Criteria - Area has been set out in accordance with the drawings
ff167d6c-9f9e-5592-83a3-fdff8f3589db | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
3d41f110-1874-5e5b-9fc0-17cb21b10254 | note | Method - Verify
f5973371-b5eb-5762-bbc6-fb5d33154ed3 | note | Frequency - Prior to commencement of excavation
c8bfbfd9-1af2-56f2-bb39-627c5e221c96 | note | Category - IP
a9f9025a-de76-5f2b-b26a-50fd2d30869a | note | Responsibility - SE/Surveyor
013ee332-2057-5223-a622-210662cf1ab3 | note | Verifying Documents - This ITP
4e8b7852-b687-5215-a0c4-da98a49cf4f6 | textbox | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
2bdd789a-590b-550e-9877-560dadc46cd6 | note | Reference - Section 204.06 (c) Section 204.06 (e) IFC Drawings
ae0922c9-49c6-59c7-836d-69f6aacee5d7 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
592e1378-f6da-5917-b7c5-f14a0fc5ea75 | note | • Assigned CBR ≥ 2.0%
753d4573-6990-5138-9b66-4f45131492e4 | note | • Assigned Swell less than 2.5%
8bddbe8c-736c-579f-9c5a-00ffd80d1a99 | note | • If parameters are met, rip and re compact to a depth of 150mm.
78fc6b54-23d9-51c4-b940-c7fc22f262c2 | note | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
3badb9dd-e517-528a-9b45-d84c6c65f2c0 | note | • If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type A/B Fill - Road is to be utilised.
ecf92566-2511-5e3c-bb1c-2333101b8f72 | note | Attach: Laboratory testing Verification:
9e84f50b-1a6b-52a6-936f-53c051b760cf | textbox | Enter: Type A/B fill Lot Number:
55d72201-f997-533f-9d5e-23be8434b22c | note | Method - Verify-Document Review
b38f8eba-0704-5b66-8017-2847545f72b7 | note | Frequency - Each lot
5f14b3dc-576a-55fe-9a2c-ecdcc7fee1d9 | note | Category - HP
52ee2822-4898-58a8-a671-054db7a9d298 | note | Responsibility - PE/Nominated Authority
8792767d-86cb-5c6c-9322-56454fb74e15 | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
ef8771b3-be1f-532d-b8ec-1311e5e3b26b | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Material classified as silt
47c295e5-d53c-5a3d-a69c-d45140037f47 | note | Reference - Section 204.04 b)
9f071f05-e20a-54e7-a056-6f89f7791b07 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
70e04e18-557a-558c-8d71-cfbd719636e1 | note | Method - Document Review
61dec7c8-c92d-5362-a773-10b7b0a7999a | note | Frequency - Prior to commencing
ba41a107-e41f-5fcb-96a7-c3cdb6951451 | note | Category - HP
42a3433c-dfa3-542f-aacb-e1822486378c | note | Responsibility - SE/Nominated Authority
e0ad02b7-e98e-56bd-a674-652e4b9c2789 | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
642aac42-4690-574d-8057-d68303bb2756 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
76b47cd4-cc3b-5c7e-8d87-f08bcf9d4089 | note | Reference - Section 204.06 f)
64fc65df-f123-5d91-88dc-0572cd2ea923 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
a6015c38-efbf-59e0-a517-764dff1cac5d | note | • Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
c38d6e61-adb1-5559-9d5e-62bce7fb5db4 | note | Method - Site Inspection/ Document Review
b31b64af-b876-5e40-9dd1-9751636574e6 | note | Frequency - Prior construction of the regulating layer
77763d8a-60ce-5aaa-8330-e248b24ae92b | note | Category - HP
6c53df8b-354d-5e58-8d6f-531e41aede24 | note | Responsibility - SE/Nominated Authority
b7aeb5ac-2283-560d-95d3-52cdc0f6a486 | note | Verifying Documents - This ITP
0f1c4a40-bf8d-5e15-92eb-cfb1e25f2ce7 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Unsuitable Material
28637f27-eaf7-5be4-88da-777592a2daf8 | note | Reference - Section 204.07 d)
4ee12dad-2e21-58a0-b273-0c7dbb8c729a | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
6a657f8e-ae64-5f69-99a7-7e1e1b9866dd | note | Method - Visual inspection
ab393f88-697d-547c-891a-6d7e78973f03 | note | Frequency - Each lot
77bad8b5-45a8-5f90-9c35-d663e4f73afc | note | Category - HP
79f88cef-cac3-5aec-985f-506b9bbcf11a | note | Responsibility - SE/Nominated Authority
341c15c8-e2e0-5dd3-b553-1cd4cc68d14e | note | Verifying Documents - This ITP
25d2ce05-845f-5da8-89be-97ff1260146e | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Groundwater
ef343f13-e50b-5da7-8a84-e093c4d5a21c | note | Reference - Section 204.06 h)
553a028e-a3f3-5266-bba5-6377136eed5f | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
4224f83f-f9cb-5cff-89fe-b1c8fae0c323 | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
c5fcd095-4929-5abc-97ab-e5fe82d60455 | note | Method - Visual inspection
cb35badf-1863-5735-b1c1-ae4e765516b4 | note | Frequency - Each lot
a6f3a1bb-a48f-56d2-b31a-07b7f663ae6c | note | Category - HP
e8ec8778-934e-5ac4-b845-7d428923cdc7 | note | Responsibility - SE/Nominated Authority
321c9b77-559f-5c77-8850-2e0d0029e0b2 | note | Verifying Documents - This ITP
5cc29c93-d7de-5004-bc70-edbf8bd26523 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Cut to Fill Zones
ef28fff6-7581-5a5c-ab8f-4b05185198c4 | note | Reference - Section 204.06 g)
3740c484-3c6b-54eb-8dab-33ba06d58700 | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A/B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A/B material.
d2067d64-9d70-5c10-a702-ce2fda4178e0 | note | Method - Site Inspection
271825e0-9032-5c98-9acf-c4eaae8913d0 | note | Frequency - Each lot
d7fa463f-ff5d-555e-9341-fcaa58cf3328 | note | Category - IP
62bf0744-cfab-555e-8ea4-d9958fe4b7e2 | note | Responsibility - SE/Site Supervisor
d21ae106-4872-528c-9664-04246baf6f04 | note | Verifying Documents - Sign ITP
b7853a3f-89bc-5801-a22c-68fc8e9429d2 | textbox | Date Completed:
| checkpoint | 5.7 - Proof Roll
5f3b3b00-da79-5f70-bc4b-e313b36e579d | note | Reference - Section 173
c4e504ad-695b-522c-b17a-cdcad9f2b836 | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
508d3ee8-213d-5ad1-92a6-28c55123ebb8 | note | Method - Visual inspection
d5ffe7ed-e254-53b0-8069-3c6fcdcc8987 | note | Frequency - Each lot
145e8b0f-9872-570e-b580-d47b7bda2c4e | note | Category - HP
c1ee7c7f-c73e-5f50-9a3b-a4dbb871bdf7 | note | Responsibility - Site Engineer/Superintendent
f8adeb94-f708-594a-9294-8b10a7ce524d | note | Verifying Documents - This ITP
e8841163-2d3a-5df2-8ae8-8b18e8c3f3dc | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Compaction Testing
d57adf16-9421-572e-b4b8-dbd82f284b34 | note | Reference - Table 204.131
e3dbf970-9030-5587-b14e-b74169b5bc7a | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
b4804177-9c95-573b-a756-31886a0486b0 | note | • Ripped and re-compacted material below Cut Floor Level
db61d721-c6bc-5d4f-a6a5-55b15a87f3cd | note | • Scale B: Characteristic Density Ratio 98%.
b1e2ed62-9bb6-5bb2-b4b5-7ed16ddf8a4b | note | Attach: Compaction Test Result:
ddc47195-8f0c-5643-bbef-4e37faa0410c | note | Method - Document Review
69930ca9-0e1d-55ff-a6f9-30d727e58333 | note | Frequency - Each lot
d3d77cbc-48e6-56f9-a13e-105eff55b590 | note | Category - IP
b9a7605a-22a6-58d9-a440-590963cc44a0 | note | Responsibility - PE/SE
89aa4ba2-bf69-581e-881f-28a966fd5d40 | note | Verifying Documents - Test Records, Lot Register
6f29cbb8-4dd8-5399-beff-85aa39d1a2c5 | textbox | Date Completed:
| checkpoint | 5.9 - Post Compaction Material Property Testing
4ae9b3e7-8a12-54d1-99bd-faa1cdf30a9b | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
f5710c54-1e84-5b92-a5f7-830085788686 | note | Acceptance Criteria - Material Properties:
ad89f386-e9d4-5372-a868-7501995be6f4 | note | • CBR ≥ 2% and Swell ≤ 1.5%
c2117359-31fd-5765-889a-e7bee849a3f2 | note | • Max Permeability = 5X10-9 m/s
f24e6698-1386-5684-8536-ba05524ad8e4 | note | ○ Grading:
c58faac6-e896-525c-a11d-55fd4d1a335d | note | • 75.0mm 100%
db326a2f-d598-5bfe-b546-f5ef655ae1e6 | note | • 4.75mm 40-80%
b0499f27-fb8b-5ad8-85de-454ec66c0d61 | note | • 0.075mm 10-40%
7c059b4b-9219-5f86-96dd-eff2cc5ae94f | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
38d1faac-8ac9-5314-adde-4296e4e314e8 | note | ○ Scale B:
8afa9151-0146-5863-8d72-841d801468c2 | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
7c34bbba-08e2-5054-a1b8-c61bbc2bb70d | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
b7a7f372-b7b6-5ae6-a786-987a3bd8efa5 | note | Attach: Post compaction test results:
062f77fc-d78d-5c47-accd-8dace84592d7 | note | Method - Review Document
51f8bee4-78a0-5201-ac8e-2233a55008ff | note | Frequency - Refer to Section 204
2cd4ef93-85d9-5248-a4a6-539e9e5531c9 | note | Category - IP
c9482379-d5c9-5c2d-8d50-965324b74aca | note | Responsibility - PE/SE
fc808f2e-1cdb-557e-b086-3b82c92e0284 | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
eff53af4-12f9-5149-be92-f8bd6bcd573e | textbox | Date Completed:
| section | 6. Post Construction Activities
| checkpoint | 6.1 - Survey Conformance
20060779-5a77-5092-a6e5-776a091596b1 | note | Reference - VicRoads 204.03f,g and h
7eed938e-9995-501a-8e5e-5519c55c9e4d | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
1387e5f0-f68f-5c45-b871-376cc627e08e | note | ○ Level tolerances (Scale B):
35e26a69-1726-587b-809c-4f2b298e5382 | note | • Range x = +5, -25mm
6bcc3e01-eab6-54a4-bf72-89385e157d83 | note | • Max S = 15 mm
38ee0337-3c92-5ac5-aae1-6f4b2e1c27e9 | note | • 40 measurements per lot
bb92d6a5-2093-59f1-9499-c35b6b5307ca | note | Method - Review Document
a828d010-5c8f-5e91-8047-93f965d5abf3 | note | Frequency - Each lot
f3c686bf-6e0b-5acc-b9a5-848b18ffb438 | note | Category - SCP
3d276712-2c98-546e-8762-4841d5a5806f | note | Responsibility - SE/Surveyor
574bf915-86aa-51a6-8b38-61942295620c | note | Verifying Documents - Sign ITP, Attach Survey Report
a448b87e-fc1e-5e41-bf7d-a0b4996be48f | textbox | Date Completed:
| checkpoint | Final Inspection
25c9af64-aa07-5448-8829-5645b0a39ac1 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
490ce730-3f19-599e-8aee-2917414efb0e | textbox | Name:
496d3e96-9853-5840-8843-b9f1cabca955 | textbox | Position:
f9b058e4-08e6-54d4-b8bb-1fc719ff9336 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | itp | ITP-046-CIV-CPD-Type A Fill - Road | 5619ea3c-44b4-4e95-b2c1-4e01cb32eab8
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
04dff166-9dd8-5bc0-a59a-6d9dfeab4b8a | note | Document Title: ITP-CIV-CPD- Type A Fill - Road (Supply and Install)
2e328150-ad80-516e-90ef-cfa5581b235b | note | ITP Description: Type A Fill - Road (Supply and Install)
618d6363-7516-56a8-bc30-f93990bc1cb0 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c6fc5f5e-87ab-5ed9-9037-9a2da1063ac2 | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
9d8abf76-5441-508f-b4ab-ff9c7bf139bd | note | Revision Number: 0
47651862-5031-5637-9ace-f624191e10e5 | note | Revision Date: 12/07/2023
1dc6e926-8224-5b5f-98bc-351e3c12570b | note | ITP created by: Matthew Dib
1b7a676d-c1ab-5969-ab57-fc41ae66b9c7 | note | ITP approved for use by:
| checkpoint | 1.1 - Non Dependent
76b0e669-abb6-57da-93a9-d2f32151a410 | note | Reference - IFC Drawings
17f45917-1af6-5194-8ce2-c7eb44b5d63e | note | • VicRoads Standard Section 176 (Sept 2008)
45139a27-a71a-59d0-8b16-e6cb4d8e27c3 | note | • VicRoads Section 204 (Dec 2015)
9792e7d1-e930-5283-a6bc-3abe30abbce2 | note | • Code of Practice RC500.20
034472c1-2d1e-5515-b42a-6e878b689075 | note | • Code of Practice RC500.5
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
425d55c8-ac7a-5e3c-80a0-5a62732e1bb3 | note | Reference - Section 204.04 b) Table 204.041
12bc2454-34ed-533c-903a-799dc417c27c | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
8b2ead9f-fbbd-57c1-ad67-49349d13ca4b | note | • Assigned CBR≥6%
44a7512a-e04c-59a8-8f07-c3a5f3cfa629 | note | • Swell ≤ 1.5%
e7cedf62-c5d0-5880-9958-7cd69517a655 | note | • Permeability ≤ 5X10-9 m/s
5b61e4c9-7631-5c03-8df6-c276a4bf0594 | note | ○ Grading:
ced8d0d9-6123-5eeb-a7a9-b008fd82c536 | note | • 75.0mm 100%
7fe02200-0009-5e62-ba49-ad35ec2a67d2 | note | • 4.75mm 40-80%
542a4241-58d6-5ff8-b8c1-ce46563063c8 | note | • 0.075mm 10-40%
645f5910-ebe2-5f3e-bba0-aca3bde3739d | textbox | Reference: Material approval in Teambinder:
262ef993-9f76-5abe-bc43-69c339a4526c | note | Method - Document Review
b15c6888-c8dc-554a-a7b3-b54199b8d25d | note | Frequency - Once, for each material type
3e70129f-1de4-5578-84f7-25616b289e6a | note | Category - HP
d83b16af-9fee-5b03-992c-bcaadfd21eb1 | note | Responsibility - SE/Nominated Authority
36dbf726-fae6-51be-8cbb-75c96e139482 | note | Verifying Documents - Supplier Material Conformance Certificate
f10e62c9-3d93-585e-99e9-23ab1a25c3d6 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - Pre-Commencement of Fill Works
b7c34647-c4b8-5264-b632-643e8b90fe78 | note | Reference - Section 204.10 (b)
83cec521-af0a-5bf2-8ac8-9d3d7c3774c4 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
dc9ce301-7dc7-5746-b571-f1848c0bb5ba | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
34e9a4d4-1068-5b00-8e19-607ce8381364 | note | • No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
cb38de53-c079-589b-a94a-edff130e8c5b | textbox | Reference: Fill foundation Preparation Lot Number:
6dda44b0-7bb0-5bed-abcf-ab16a75ca024 | note | Method - Visual Inspection
34151bf9-2f53-5ba6-bf60-cec811a9f0d3 | note | Frequency - Prior to commencement of fill works
e4fce539-17cb-587d-be43-2286b784a8f9 | note | Category - HP
48a92bbd-9539-549e-be85-560f16c08a9d | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
e5ebfe17-8862-5c5f-a8a4-18a59590cf51 | note | Reference - Design Drawings
87f58417-3fbf-587c-b476-4c591f6869f7 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
8ff901ff-a5e3-565c-8f67-35d13ab31e01 | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
a6a95aba-ee65-5d8f-8cfd-49e14ec1dd08 | note | Method - Visual Inspection
a7c46065-950b-5a4e-9ec0-e40ab55b67a6 | note | Frequency - Each lot prior to commencement
b1bcb0f0-33d6-5450-adb8-b842858a8243 | note | Category - HP*
6bb44688-09a3-5e41-913c-78a76f2d5dc3 | note | Responsibility - PE
99750622-1290-5176-bca3-ab3e16be00a3 | note | Verifying Documents - Signed ITP Lot Map
e6f517fe-6fd6-51b1-aa95-41757524b20f | textbox | Date Completed:
| section | 5. Type A Fill/Verge Activities
| checkpoint | 5.1 - Placing of Fill
1daa79f5-f303-59e0-b236-475956a18fcc | note | Reference - Section 204.10
f67b7119-aa2e-5ad1-91e9-e3bb89aac3db | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted from superintendent.
24a89339-3559-5662-bb67-6c574010486c | note | Method - Visual
5d5a3776-69f9-50fa-80a0-ab756f9973ce | note | Frequency - Each Lot
ab05be17-4baf-56cf-b638-c38289087017 | note | Category - WP
ee424c06-5c39-5370-a601-9bee8d4afdf6 | note | Responsibility - SE/Site Supervisor
d080f5fd-2fc8-5584-8b91-5aad8ad54dab | note | Verifying Documents - Sign ITP
8aaba3a5-1d61-5166-900f-113b3023cc3c | textbox | Date Completed:
| checkpoint | 5.2 - Test Roll
d9ee110f-b472-56b7-b77f-125fb67633a6 | note | Reference - Section 173.03 Section 204.12
3244da56-85d2-5017-93b6-ee8b6b7a15c6 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
4ed78b09-a3f7-519f-8c54-47b8a50c6088 | note | Method - Test Roll as per 173.03
a138b451-7031-5529-96fd-3d301e729252 | note | Frequency - Each Lot/Layer
e89a4c19-1c76-5077-af45-5e27c9c23033 | note | Category - HP
d38ec773-74f1-55d9-b9a2-9cd5db202597 | note | Responsibility - SE/Nominated Authority
02981694-87c2-5256-a20c-8e49c5c786ee | note | Verifying Documents - Sign ITP
5ce69613-8788-57ef-96d9-3662c9721deb | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Compaction Testing
2345172b-c4dc-5fc0-b677-86c1770cc283 | note | Reference - Table 204.131 Section 204.14 c) Table 204.142
efdc2cf0-ac0f-5777-a2c0-3797e550db0c | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
dc464198-3c8d-525a-83c1-23cd01bcf2cb | note | ○ Standard Compactive Effort
5d77e4ed-762f-5225-887d-5e901b3d85a4 | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
3e931e7c-7501-52db-87cd-3557f35faf15 | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
f68ca55f-d106-59ab-bc60-0e4104f87a4c | note | ○ Compaction and Moisture content
0a4fbbda-42df-5b44-a819-f1b90582b889 | note | • Scale A: Characteristic Density Ratio 99%.
246b59c3-8506-54d3-8b45-eea82a6debc8 | note | • Scale B: Characteristic Density Ratio 98%.
98efe837-3fdd-5f78-9647-31295b0d6c7f | note | • Scale C: Mean Value of Density Ratio: 100%
e1c3675a-45b0-5a5e-8bb9-38e2771004a4 | note | • Lot size - the leser of one day's production or 5,000sqm
f2210a02-c083-5746-b46f-95aed580c343 | note | • Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to every second lot of like material and work.
08382353-c5fc-5872-9c71-070d54672054 | note | ATTACH: COMPACTION TEST RESULTS
3bbbe73a-e118-5eb1-b8d7-dd31ac7607e6 | note | Method - Review Document
70d3700f-88ef-5b56-bd3b-957b1bdcb693 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
08a3226f-b143-5885-9c8d-2e331a76ea1e | note | Category - IP
c921312c-d068-589c-bd92-701fb5c52a6b | note | Responsibility - SE/Site Supervisor
a6e81cf5-5b8a-58bc-8b44-14e84b9f13ab | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
ab47b4c7-fac8-5ba2-9bc4-23109f0e52ba | textbox | Date Completed:
| checkpoint | 5.4 - Preparation of final surface
9b24c781-0301-52f6-ab67-e82459f83e53 | note | Reference - Section 204.15, 204.03 (g)
d9b583c2-9cc2-5001-b028-5c0e42ac694a | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
e3862c83-ee01-5b3f-b68b-7542e6c9df6f | note | Method - Measure
ed4f6255-30b0-5f65-a6a2-8962ba80f072 | note | Frequency - Top layer
8e9aadf0-3e0f-5adf-ac0c-832a23cadccb | note | Category - IP
30467f77-3fb7-5cb7-962c-19975dfb9ced | note | Verifying Documents - Signed ITP
04698542-b2f2-5ed2-bd23-77bde2230d16 | textbox | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Post Compaction Material Property Testing
360219e7-8bcc-589b-bf63-614e39f7cd68 | note | Reference - Table 204,041 Table 204.141 Section 204.14 a) or b)
c5851ff8-f55e-5ff4-8560-417a2be0e0e7 | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
d92164c7-d89d-587f-86da-e5e329550b1d | note | • CBR ≥ 6% and Swell ≤ 1.5%
97818fc0-114a-535d-9fb6-993420c0fc26 | note | • Max Permeability = 5X10-9 m/s
2b096aa2-ef1a-56dd-aa12-65a76eab51e1 | note | ○ Grading:
96800a91-c8a3-58c7-884b-de2bd9442ebb | note | • 75.0mm 100%
afb008c9-0036-516e-b8cf-9c4861a3c406 | note | • 4.75mm 40-80%
9c590be7-6107-5620-8381-a9436bbbede2 | note | • 0.075mm 10-40%
7f6e35a9-9a2b-5143-ac14-0a4dac96d6bd | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
ffadd300-21a0-5226-a4c1-7e0bbabc0ff4 | note | ○ Scale B:
40489fb7-1139-5dd5-a504-6fb97d8a396c | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
a7c3fa0a-ac3b-5b31-ae34-a32cb9fc650a | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
576fd385-bcd2-5b04-9904-40894963473f | note | Attach: Post compaction test results:
1045710d-9dd8-56e0-990d-aeec79925c14 | note | Method - Review Document
b7948c2e-3816-5d25-b402-62acc2fb9b9b | note | Frequency - Refer to Section 204
ff151421-d598-5dec-9c60-a8d5fe8bdfca | note | Category - IP
f9cc41c8-e8e0-546a-90db-cb38e4a7fcf2 | note | Responsibility - SE/Site Supervisor
9faa9b84-20a6-50fe-a579-9c01ba4ddff1 | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
10a98b07-9aa8-55e9-bd5e-e3d392607aaa | textbox | Date Completed:
| checkpoint | 6.2 - Survey Conformance
be92c2fb-eb93-510d-ad19-d3aed14f3092 | note | Reference - VicRoads 204.03f,g and h
5f6f6e39-fec8-5bac-8c43-0d16dc135843 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
127f48d8-796d-5558-8212-47324ccbf5a0 | note | ○ Level tolerances Scale A:
4f6d068e-bd29-5623-9272-2ac784007c7a | note | • Range x = +5, -15mm
a90325d6-4ea5-5351-8008-7ab3ae0b1e48 | note | • Max S = 12 mm
50e2cc4d-ccb9-5215-988d-37906fe414ad | note | • 80 measurements per lot
b5784200-319f-5d39-9358-fdbc4472de9f | note | ○ Level tolerances Scale B:
1e48be07-2ece-59d0-a181-865f69f8893e | note | • Range x = +5, -25mm
6bf99577-f270-5b07-be2b-6e781f5d3a49 | note | • Max S = 15 mm
78e5e603-bcd8-5b88-9c2c-c59ba999fc93 | note | • 40 measurements per lot
6be9b64d-98f4-5ca9-8e9f-8b6dae2b0327 | note | ○ Level tolerances Scale C:
831a17ba-ddee-558a-82c1-ad599c8374ec | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
7ee7365c-1cea-5223-b01a-771287295a7d | note | Method - Document Review
764939f0-487d-5636-b284-ba7d78a18c19 | note | Frequency - Top of Type A/Verge
3ec689ef-8188-5e9b-bbd1-584980ac0572 | note | Category - IP
306d8828-0fd1-5736-a4b1-146ccef0a809 | note | Responsibility - Surveyor, SE/PE/SPE
0f69f592-453b-5ba1-b218-17af3155d40d | note | Verifying Documents - This ITP, Survey Conformance Report
144a076e-6143-5229-9c59-99f9713efa54 | textbox | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
2a4e9695-02e3-5f4e-955c-f1cedfae2ddb | note | Reference - MRPA Quality Management Plan
0ac6cd56-1ef4-51e4-88c4-29eb5eed1866 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
f1071e79-8b53-52ee-8683-6eec9fb98b76 | note | Method - Document Review
c2bc63fb-e42b-5ff0-a010-8fcf91dafb47 | note | Frequency - Once, prior to closure of this lot / element / Work area
1ae8b622-83df-5c63-9ec3-331070490178 | note | Category - HP*
7679b883-4ef0-5bf0-b1f7-f2a5f757dcf3 | note | Responsibility - SE/PE/SPE
12643d86-9f7a-5016-b432-f3636c1a94af | note | Verifying Documents - This ITP
97088407-c4b8-555b-b8e1-74b7a73d71ab | textbox | Date Completed:
| checkpoint | Final Inspection
0ae9d3e5-fa94-57b3-9ab4-9dd60cdd2481 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c34cd726-4ca4-55d1-86af-c46580d04874 | textbox | Name:
ebc653a5-e87e-5d4d-8970-33127db15e24 | textbox | Position:
360777e6-6e81-5d3a-96a4-efae52176481 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | itp | ITP-047-CIV-CPD-Type B FIll - Road | 51c5fee6-4576-467f-8804-773232db449e
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
238556f2-d3ed-5e38-8819-595bae5bb9ac | note | Document Title: ITP-CIV-CPD-Type B Fill - Road (Supply and Install)
81e5da89-722d-5bee-b7dc-d250fba7279d | note | ITP Description: Type B Fill - Road (Supply and Install)
5cdb59e4-d014-50a1-bf0e-1336da646ba5 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
d3f3e526-429c-566f-bbd5-34cdf01a9821 | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
abd8a9d9-f56a-5b5b-a672-295fda6b7aaa | note | Revision Number: 1
40222268-4f3d-5113-b7a4-14074b27f432 | note | Revision Date: 25/10/2023
493eec9b-49c6-5401-87f9-d957f9f1f1df | note | ITP created by: Matthew Dib
ab42a86f-254d-55d4-a7ff-6a2f1ae0fbcd | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
edc683c8-f320-55b9-834f-c07f3134b756 | note | Reference - Reference Documents:
6e638777-99c5-5d30-a075-9b8b0b9b8ad1 | note | • IFC Drawings
40837480-245a-5b56-a9ee-e3f3ce03cc5b | note | • VicRoads Standard Section 176 (10/9/2008)
a5a69f99-ae40-5245-a663-a3712ee6d651 | note | • VicRoads Standard Section 204 (29/12/2015)
| section | 2. Preliminaries
| checkpoint | 2.1 - Material Supply
5bca1668-9f42-5837-9e42-e66adb23a36e | note | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
22c27b38-db86-5311-81f6-88d111d60441 | note | Acceptance Criteria - Free of topsoil, deleterious &/or perishable matter and maximum particle size ≤ 150mm. Swell < 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
0692d139-f06f-516b-ab89-b5f24a72010a | note | Method - Doc. Review
2f3e0c7f-bf6d-5ca2-a4fd-9cdf93388967 | note | Frequency - Prior to Commencement
008aa88b-46f1-5fd6-989b-081ab234573d | note | Category - HP
d0dbadd4-555c-57ff-a969-8a6f9667cf92 | note | Verifying Documents - NATA Test Certificate
084d9e2e-edc3-5058-996d-51ebddc9adf1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Pre-construction / Pre-installation Activities
| checkpoint | 3.1 - Survey Set Out
b66f58f6-cef8-5082-acff-4b9298880e99 | note | Reference - Design Drawings
0ebadef1-db0c-5bf3-84c0-c1ea3251b301 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
c10f054b-d450-5ce8-af36-eb7d7d391067 | note | Method - Visual Inspection
0847cf5d-2649-566f-ba96-fde0e4c6fdbd | note | Frequency - Each lot prior to commencement
098f8d9b-9b7f-5591-96c3-390b459c6dba | note | Verifying Documents - Signed ITP
ef60b33b-f6be-577f-bf69-2d1483de5bb8 | date | Date Completed:
| checkpoint | 3.2 - Pre-Commencement of Fill Works
e3039a71-713c-53f1-9af6-05562d6272d1 | note | Reference - Section 204.10 (b)
d3bfd620-fa0d-5cc6-b51f-c285af4dbfe8 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
ec640253-d01b-5781-94da-a82eecd2ea37 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
4e4ea450-8446-5edb-ad83-a54974b78c11 | note | Method - Visual Inspection
d0150e17-9256-547f-ab34-41c47529f16c | note | Frequency - Prior to commencement of fill works
a386c6c4-5ec2-51ed-b113-07002385d512 | note | Category - HP
e6572f72-131f-55e2-aa3e-2105bbc3f657 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Placing of Fill
7d9fdeda-899d-51e9-aec9-dbfe8f115cb9 | note | Reference - Section 204.10 (d) (iii)
f92d7b5d-bc50-5dbd-9ec7-32f4d64f6346 | note | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
86f976d1-155c-55a7-9c2d-57ed4afdcca2 | note | Method - Monitor
971e86c9-19b0-524e-a66b-c41cc36d39bc | note | Frequency - Each layer
f56628d8-dd7d-5216-82b4-2836d290a22e | note | Verifying Documents - Signed ITP
3b1c324f-a7d7-558b-8cab-cc99d716052a | date | Date Completed:
| checkpoint | 4.2 - Keying of Layers
f0afdd0c-e977-5331-9ae1-56af5e71f307 | note | Reference - Section 204.10(d)(i)
d54e699d-8a3f-5542-8ea9-a182bf0d121e | note | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
5a91d9fb-6c7f-506b-9770-0e88fd10b298 | note | Method - Monitor
4b942366-bc01-5f26-a4a1-5aebff614754 | note | Frequency - Each layer
e2bb6d05-4def-5368-bca7-8edf66877833 | note | Verifying Documents - Signed ITP
c9d555b7-6f4b-589d-a84a-3e4117a1d401 | date | Date Completed:
| checkpoint | 4.3 - Test Rolling
f493f69c-e8ca-5361-900e-ccc72642aef3 | note | Reference - Section 204.12, 173.03
53a9c0bd-81fe-54da-aa45-9dc31c1aa494 | note | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
d7a90d11-1fdb-5d79-b83f-fd0143bb4001 | note | Method - Measure
5ddb319f-a801-50c9-b315-756e65662db4 | note | Frequency - Each layer
302117d3-3235-53fe-b064-b2475393ff1a | note | Category - HP
ece8beec-e611-5cc0-abc0-74473f4b54dc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Post Compaction Testing
3bc8ac1d-5a0a-5de8-843d-a9722f7278c3 | note | Reference - Section Table 204.131, 204.13, 204.14
2013c772-f4a3-5ce2-8498-ec3c87bd33ad | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
310298ae-e1e8-5a2c-b0e2-75a06ad3d1a2 | note | Scale B: Characteristic Density Ratio 98%.
0258f297-895e-5171-9ab7-cb0df3d61d76 | note | Attach: Compaction Test Result:
00a4815c-97b7-5700-85ed-74fe92c0cd72 | note | Method - Doc. Review
3e1f624a-12e2-5188-9d1c-738367d55eb4 | note | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142:
ca5cab5b-f876-512b-b59d-7d55994c3b2e | note | ○ Placed within 400 mm of top of Type B: Test every second lot of like material and work
f9e2c15e-51d3-582d-bb5e-c7a535e5dabb | note | ○ Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
5b666f8c-ead5-5dd8-809f-0423141ee744 | note | Verifying Documents - NATA Test Certificate
0004700b-db54-5d70-a993-3ea51a41cca5 | date | Date Completed:
| checkpoint | 4.5 - Preparation of final surface
922f2e93-472d-5bcb-bb03-e6af5ce713c6 | note | Reference - Section 204.15, 204.03 (g)
cdb7532a-2d15-5c1c-b11f-eb4a454f43d0 | note | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
4ed21aac-3691-52b8-9035-782109d3f6d8 | note | Method - Measure
ff9e752b-a906-59f0-a4c2-4428f536f81e | note | Frequency - Top layer
8280b1da-7862-51dd-99ce-9c66983d3ac7 | note | Verifying Documents - Signed ITP
2846b091-b387-5b2b-bc3b-5a4a483e0c7b | date | Date Completed:
| section | 5. Post-construction / Post-installation Activities
| checkpoint | 5.1 - Survey Conformance As Built
51a6e5c6-33f2-5461-85cc-a34d4d4e8ba3 | note | Reference - Section 204.10(h)
5bc82fd6-fe59-5fde-93a3-e737b5ffde31 | note | Acceptance Criteria - The Contractor shall establish a procedure to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
2d739730-aaf9-5c24-8b49-82fcbfc48fcb | note | Method - Review
14dada8c-29a9-5bd2-a31e-a5a0c16aedfc | note | Frequency - Every 3 layers
62fbedcf-dee2-58b6-8460-f416461b8ed8 | note | Verifying Documents - Survey Thickness Conformance
b209403a-1809-561e-a38e-a01e7c751ee7 | date | Date Completed:
| checkpoint | Final Inspection
6a73f30b-f38b-5841-81cb-d23808f59b39 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
7a6529d3-4dbf-5e67-9db7-dde56f98c9d7 | textbox | Name:
4e6cd2a3-baed-5525-8d19-28adc8275395 | textbox | Position:
b16e5600-a36b-524c-b0d3-76c612120908 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | itp | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation | 1c13b79f-05b4-4abd-b61f-9be7a4ee36b9
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
54cbbd25-0217-5f93-8c04-32ab25705d02 | note | Document Title: ITP-048-CIV-Calder - Stormwater Drainage Supply & Installation
42c73e1f-b4fe-5e17-a4e6-fe786d9930e6 | note | ITP Description: Stormwater Drainage Supply & Installation
1072443b-4ce6-5d29-99dd-1e5558e3eec9 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
97538d00-08c4-5a58-9b5e-371d88c3ab2b | note | Discipline (e.g. CIV/STR/RAIL): CIV
0b1049cc-c86a-56cf-a523-601b79eabb9d | note | Revision Number: 0
c5684dc8-88cd-5f91-a657-01aa964aac1f | note | Revision Date: 19/07/2023
2c42a650-f171-5637-9c8a-f3c8221f848a | note | ITP created by: Ethan Caruana Smith
3a4fd5a2-f344-530b-8cff-3ad6650804a5 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
049d257f-d67a-5254-9e87-432b7942d94f | note | Reference - VicRoads Section 701 (May 2020)
| checkpoint | 1.2 - Non Dependent
1373b251-3ace-5e65-b601-89dd12746253 | note | Reference - VicRoads Section 705 (June 2021)
| checkpoint | 1.3 - Non Dependent
290abb78-b920-58d1-882c-07f26b057f92 | note | Reference - IFC Drawings - package 13
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
5133ef34-9f0e-5f1c-a55a-73ea66b52c6f | note | Reference - Section 701.04, Section 701.05, Section 701.09
60fa969a-ef98-52e5-badc-796c6863f8f3 | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
1d9b6d4d-27f2-5f39-b007-284f3632a292 | note | • Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
04545dc0-1ab0-591f-8f08-70a29a845bb5 | note | • Rubber ring joints shall comply with the requirements of AS 1646
38bbd1f4-2d65-5143-a9b1-6247293e3f6f | textbox | Enter: Teambinder Material Approval number
93b9fe18-2b6f-5666-a865-555cefa2e92c | note | Method - Document Review
d79391aa-d611-5d18-aaa6-c67571466739 | note | Frequency - Each lot
594117ee-77f5-5ab2-bb85-e26d59148d12 | note | Category - HP
bf3f0b6e-d05d-5464-8cf9-3c441e8eaa6e | note | Responsibility - Nominated Authority
4878f0ce-de8f-51a7-82a5-2415a004563d | note | Verifying Documents - Teambinder Material Approval
769d6910-4e6b-5e3d-a923-aa280010a925 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Drainage Flexible Pipes
2719ec57-48eb-52f2-bf32-78fbf41e4fec | note | Reference - Section 701.08
54afc51d-7959-5eca-a6ca-cee0aada02ec | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
1893723f-e63d-5060-b679-921de47f50ee | textbox | Enter: Teambinder Material Approval number
5ad4e039-2896-55b3-8b69-ba5ce5ccb4d8 | note | Method - Document Review
28c02fcd-976e-5151-b77e-bc0f9325dffb | note | Frequency - Each lot
a488a7ae-65cf-59ac-aa33-b0dcf57394c9 | note | Category - HP
cf212d1a-bc40-53da-b07b-9a464ca7db40 | note | Responsibility - Nominated Authority
50a55385-8b8e-5017-90fc-cc6b36b4393b | note | Verifying Documents - Teambinder Material Approval
dfe786c1-a388-5026-97c3-63068e294d77 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Precast Drainage Pit
f0d33795-6cf4-5e2c-89b2-cb962804e517 | note | Reference - Section 705.07, Section 705.04, Section 705.09
4259a9fd-ffa0-506a-b45d-85fb802bb345 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
0fbdbc27-1134-5b87-83d7-3d91964e65f6 | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
5ff9ae96-528a-53c9-8c59-720be22cbb93 | textbox | Enter: Teambinder Material Approval number
83dae22d-3dd4-539c-8ad9-b87f915e213b | note | Method - Document Review
b05605b5-c370-548e-a9bd-8a5b67ae4d42 | note | Frequency - Each lot
9862f83a-a3a7-5540-ad14-a1b7d1b9ce5b | note | Category - HP
ce3276fb-1124-57dc-973d-69937c3ceade | note | Responsibility - Nominated Authority
254f27fc-ce7e-51b3-b351-efb9371d71a8 | note | Verifying Documents - Teambinder Material Approval
6deee45d-38ca-55a0-9dd0-bafda30155c6 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Cast in Place Drainage Pit
b0c6263a-4906-5eeb-bed0-6a05159afefb | note | Reference - Section 705.06 IFC Drawings
4c574fbf-66de-5d27-adc5-9762d785a5ce | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
7356e754-fcfb-5158-b07d-ab82d4f69446 | note | Method - Document Review
c8012b05-25d5-55fc-a331-524090c05bca | note | Frequency - Each lot
2cd6f092-3b20-573f-8a36-6f31eb417ee7 | note | Category - HP
1552e327-2f0f-5c95-8180-dd0104a1610f | note | Responsibility - Nominated Authority
8583b9f9-0559-5e0c-9103-743cc4278ea2 | note | Verifying Documents - Teambinder Material Approval
adb3fb5f-7143-5e51-a951-971fe87f493f | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Drainage Pit - Step Irons
de1765f1-a411-599f-ab5a-14b9678c3e3a | note | Reference - Section 705.04, Section 705.12
3e26662e-84bf-510e-b3f6-d42424d71596 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
bee12f83-908c-5b48-82cd-93c14abc4787 | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
ba8abbd4-9dc4-55f9-80ee-e47b2f3f5d49 | textbox | Enter: Teambinder Material Approval number
99b5df9e-9c16-547b-8db6-0e7acb88655f | note | Method - Document Review
6272a703-8f4d-5f92-a46f-463b35b49417 | note | Frequency - Each lot
df43af24-e5f9-578b-a8d3-ea92460ea8a4 | note | Category - HP
022e485b-8cd8-5a48-bfcd-facc399c0a54 | note | Responsibility - Nominated Authority
0177011a-dcb4-5593-9ecf-79e631c2132f | note | Verifying Documents - Teambinder Material Approval
e7f9e350-cb0a-507b-870f-3d7359d1e940 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Drainage Bedding Material
92e4115c-4958-5781-b554-bf6a0f20ebc2 | note | Reference - Section 701.09
424a6ae9-cf56-542a-a746-425541df9ac4 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
b7242711-1be5-5a69-a5ac-d51aae795379 | textbox | Enter: Teambinder Material Approval number
8d2e688d-6ca9-52a8-88f4-53fe73f2d64f | note | Method - Document Review
a0500e5d-b26a-544a-99ad-58f9d349ad7c | note | Frequency - Each lot
a2331930-1dea-5021-a18b-54000a2ea669 | note | Category - HP
8d52516d-7bc1-5423-9d05-8301e55b1d82 | note | Responsibility - Nominated Authority
66026fc8-7e6c-56ba-be5c-c1ebfc74f4e0 | note | Verifying Documents - Teambinder Material Approval
df192745-9d6d-55fc-a48f-006c81689cff | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Drainage Backfill Material
a5660455-5648-51f1-b7fb-301f2a5deba1 | note | Reference - Section 701.09, Section 701.19
eb8c7bb1-a2ea-5db9-a7ec-0c8b9eaecb67 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
e757e716-dab5-5cd7-895a-67df1ae343c8 | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
61bf1fb8-75bd-5da6-8e72-349d8471ce1d | textbox | Enter: Teambinder Material Approval number
864c98a8-82bb-565f-a93e-7b180f524d1c | note | Method - Document Review
22480f11-8375-57bb-852a-5c1c1528c943 | note | Frequency - Each lot
7b9585be-690d-5fb7-b91a-397f553be0af | note | Category - HP
5f601394-7c21-52f9-8574-5e16fd000b39 | note | Responsibility - Nominated Authority
16fe453e-e1eb-55ec-b9b6-45254763d6a4 | note | Verifying Documents - Teambinder Material Approval
8eba1970-91ea-5481-8588-8c186a8afb48 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documents
| checkpoint | 3.1 - Subcontractor ITP (where required)
0362af02-66ae-56aa-b8e3-143176e6cebc | note | Reference - Subcontractor ITP
74fe2701-1e67-5a33-a25f-d5999fd059bf | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
f4da3484-f959-5392-9bc5-df6fa0c81d53 | note | Method - Document Review
e4b52356-3e31-5a47-80de-822155694525 | note | Frequency - Each Lot
741383f5-65b6-5f2e-b248-01222b681a81 | note | Category - HP*
9d7642fa-522e-5a59-95a5-399135116f82 | note | Responsibility - PE
e0f5210b-b100-5b1c-825c-947dbf860573 | note | Verifying Documents - Refer to ITP
4587736f-0ffe-544c-8863-dc96ee2c1506 | textbox | Date Completed:
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set Out - Pits & Pipes
70d94c64-0326-55f9-aed8-1e9443ff6694 | note | Reference - IFC Drawings Section 701.10
dd704398-4feb-5fd9-b7de-203238535d62 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
64d2893b-b9d5-5492-9634-59836d22c7a4 | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
4d466f72-d787-5032-9238-749becd181fb | note | Method - Survey
9756bab9-b149-5172-baf5-acee85f08548 | note | Frequency - Each Lot
7d36971f-7c74-5382-98c2-bc8555c48b17 | note | Category - HP*
8fc73ffc-44c2-519d-b384-d4c9b16b960b | note | Responsibility - PE
a721a0a8-2053-5220-8bf4-ddb3321ce645 | note | Verifying Documents - IFC drawings - package 13
1af63d70-f385-5962-b8f5-e5fcb3ce30b0 | textbox | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Pits - Excavation
caa95059-ace6-5199-9990-4ad82c896447 | note | Reference - IFC Drawings Section 705.05
0df875a6-d97e-58ed-abce-9e62aba8665f | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
005a2253-2af7-535b-b65c-d6f3aac7dcf4 | note | Method - Visual inspection, Measure
f0847ad8-fdc3-539b-9b13-d8141a2ac768 | note | Frequency - Each Lot
c320091e-83a4-50b1-960e-e9b2d0dc85ce | note | Category - IP
fba45ade-d691-57f9-b739-4c15f3139464 | note | Responsibility - SE
0a3be269-25d8-5ce4-961b-34baa0fee62b | note | Verifying Documents - IFC drawings - package 13
3f0fbeb9-cbf6-56bd-b405-b218c9fb5303 | textbox | Date Completed:
| checkpoint | 5.2 - Pits - Placement of Bedding Material
609fab17-84d4-5385-b21c-c8c916a554e2 | note | Reference - IFC Drawings Section 705.05
f3e827c5-5f0a-5493-89aa-233561c74707 | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
e9d78fb0-ba1d-5577-8796-a215571d5375 | note | • > 80mm for clay foundations
8a7ca185-d9f1-571e-8179-dcfdbff540a0 | note | • > 150mm for rock foundations
e2ca7365-89fc-5740-88bb-0a1fe4cbb501 | note | Method - Visual inspection, Measure
9b82bc28-c862-5f94-93af-31ff125b58b6 | note | Frequency - Each Lot
c3b42d33-2e82-5270-b05c-286292481427 | note | Category - IP
bda556e7-9678-564a-af54-601482fe6436 | note | Responsibility - SE
f466157f-630c-563e-b50f-0bf19e6e8284 | note | Verifying Documents - IFC drawings - package 13
4011c2ae-7d9f-50c9-b6a9-a9c1e6354ce3 | textbox | Date Completed:
| checkpoint | 5.3 - Pits - Bedding Testting
30c88298-f054-5a0e-9947-59bb39746955 | note | Reference - IFC Drawings Section 701.20
efbe308c-b7fd-5388-9e83-ef80f4c80a3f | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
d8170177-29fc-5785-9e23-84c3c2dafca8 | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
29cc3f78-d7a9-56f9-89f3-a7e26d461c1c | note | Method - Compaction Test
71aa1913-9300-510d-8913-56147226a8fb | note | Frequency - Each Lot
7d473651-ab4c-56ab-86a1-2838bfdb5322 | note | Category - IP
e253adbc-c019-509f-9768-640f74766ada | note | Responsibility - SE
00cc67cf-1598-58e7-b016-820aa2cb6e15 | note | Verifying Documents - Compaction test results
181ec86c-9008-519a-8cfd-3f9fc4eb1ff1 | textbox | Date Completed:
| checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
8445a6b9-8a3d-514e-8157-37f9148cb128 | note | Reference - IFC Drawings Section 701.10
c6fb90dd-63b7-5bc1-a6bf-1c2728b8b0fb | note | Acceptance Criteria - Survey pick-up to verify:
ccfdefae-6536-5657-9d8b-dcd0e4f4e530 | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
0bc0715d-666a-5418-93bd-ab4ddbc06334 | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
42ae0187-5739-5608-b095-b759dd7ba63c | note | Method - Visual inspection, Measure
3d954ba7-3fca-5eeb-bdfb-8de74a14d406 | note | Frequency - Each Lot
c6f71124-5932-5f7e-a29c-414e6a2fc497 | note | Category - IP
4fa75a0f-ad76-5d98-bb8f-4493b007fd6f | note | Responsibility - SE
e3910c1c-1b87-513a-873b-512a664cf162 | note | Verifying Documents - IFC drawings - package 13
173c371a-c9c3-5cdc-b815-cce2a719bfc8 | textbox | Date Completed:
| checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
11b9adce-0de9-5265-981f-52b43044d990 | note | Reference - IFC Drawings Section 705.06, Section 610, Section 611
66eb6791-a02b-5420-a903-48a950aef3e5 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
602e3814-ca47-5c16-9e5b-6384a1a445b4 | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
1842684d-4e3f-5baa-b3a7-6face97eea13 | note | Method - Survey, Measure
6a0db754-2204-5b87-b445-f024a2c0ebb7 | note | Frequency - Each Lot
fb5c4c5a-ebe5-5a27-be94-7fb7c2f09259 | note | Category - IP
11db52ba-3dd5-5b3c-82db-c3e00b0c96d3 | note | Responsibility - SE
d2bd30c4-1f9f-52fe-ab8f-97a31689a72a | note | Verifying Documents - IFC drawings - package 13
18e8b6c4-67ec-563b-816d-88c9c5d15c75 | textbox | Date Completed:
| checkpoint | 5.6 - Pits - Jointing & Drainage Connections
aef13145-6a72-51e8-a6c1-a49a24fa9dd2 | note | Reference - Section 705.11
26eee097-7ab9-533a-bb3e-15befbbf2076 | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
a6d44c82-1458-5642-91dd-3f7239a9abe1 | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
a97984fa-5060-54a3-9cca-10a4c5b9f7ab | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
4aa122b2-4eb3-5fbf-b6c1-3d502ab6295d | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
85ebb87e-6876-54ab-a791-198b255482c0 | note | Method - Visual inspection, Measure
2c0242e6-09e0-5907-9326-7f28423d5aa4 | note | Frequency - Each Lot
12165db4-9657-537a-89fa-762c3e28be9e | note | Category - IP
776ac49f-e001-513f-8e2b-e2e218704adf | note | Responsibility - SE
a68b4be4-f8fa-5ace-9228-c4a1650de199 | note | Verifying Documents - IFC drawings - package 13
90747576-042a-5739-a315-5d5c7ba662eb | textbox | Date Completed:
| checkpoint | 5.7 - Pits - Shaping of Floor
11a21eee-7f8d-5091-8e87-a3fe26b4dcb0 | note | Reference - Section 705.13
c3844a26-6931-5129-85bd-f4947853cc6f | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
5fbcb750-2786-58ba-8e35-42be64ef7263 | note | Method - Visual inspection, Measure
2f1c57e7-accf-5775-bcb9-21bdb4d2a645 | note | Frequency - Each Lot
012e16f5-31dc-5eed-8a04-7e6e01bdd01c | note | Category - IP
5279eeef-cf53-5055-a392-30e38e8e1431 | note | Responsibility - SE
771a23d8-b310-5318-8cd3-28c3c1246ca3 | note | Verifying Documents - IFC drawings - package 13
b5efdb44-349e-5ed2-8fea-848691c36cd7 | textbox | Date Completed:
| checkpoint | 5.8 - Pits - Step Irons
40a287a2-a3d8-56ec-ade2-04c5881fbb4e | note | Reference - IFC Drawings Section 705.12
20ceb859-c1dc-5169-aec8-a34318bd7296 | note | • Brimbank City Council Engineering Detail 275
724e50b7-ddaa-5fdf-b350-a980cb98fb73 | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
01ab8bb9-deea-5046-bafa-1bcd43095040 | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
98f31534-53ac-502c-92ef-e19653b495cc | note | Method - Visual inspection, Measure
169e9152-ac78-5188-8233-9a9bcd1bd1f3 | note | Frequency - Each Lot
64427089-cd42-5da3-8cf0-83a58241e5d2 | note | Category - IP
9b336f7f-c7b9-573e-bc89-19582b1842cd | note | Responsibility - SE
ad0afc5b-c6c1-5289-8523-68eb0d7aaa29 | note | Verifying Documents - IFC drawings - package 13
3fea7099-4584-58e1-b04c-6222185ca8cc | textbox | Date Completed:
| checkpoint | 5.9 - Pits - Fitting of Covers
c974319c-a80a-55a8-90df-55f9cbf46fd6 | note | Reference - IFC Drawings Section 705.17
fa4568e0-8706-57b9-8ea3-66e2b131097e | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
7e734e95-8d50-516c-b6c2-0d4f5d0d3ad0 | note | • Height shall be within 10mm of the design level.
8cac3de9-c7b1-558e-9c08-87c7c76f56ca | note | Method - Visual inspection, Measure
1bd06876-0670-5640-bc1e-97a7286bd1f2 | note | Frequency - Each Lot
e5b15a2b-280c-5f2f-8a8d-87edfee396e3 | note | Category - IP
fe506aea-af53-5eb5-9e98-071f3f1ebfc1 | note | Responsibility - SE
e2be20f2-4046-54c3-b10b-b0045cef53f5 | note | Verifying Documents - IFC drawings - package 13
6a2b9740-d520-5755-bbcc-ac7a97bb5da0 | textbox | Date Completed:
| checkpoint | 5.10 - Pits - Pit Lids
0c45472c-5923-5b1c-86cd-21d85703da0a | note | Reference - IFC Drawings
fbc0a655-d3d6-501a-8f7c-d9bb2e23d3b7 | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
87cac1bf-cfc6-5b7f-b83e-af51beb10ab6 | note | Method - Visual inspection
c8be6773-b101-516a-8195-b8d4743f95f8 | note | Frequency - Each Lot
12853f30-dfc1-521a-af48-b297d4951952 | note | Category - IP
0003b34d-d6c8-5bd7-8814-0f49cbb1aa69 | note | Responsibility - SE
10e02d3c-da54-5add-9402-954722e52bde | note | Verifying Documents - IFC drawings - package 13
36a30aad-afd0-5ecc-b140-9b244fb9e3b7 | textbox | Date Completed:
| checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
178e5b87-8106-5221-99a2-27e38afb9038 | note | Reference - Section 705.18
b131c02f-261d-57dc-b77a-974334f5c1f4 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
cf2f2e73-08ae-50a3-9747-02ccf0ee94e8 | note | Method - Visual inspection, Measure
6f61a433-63f9-55f9-867b-f61365bd85b5 | note | Frequency - Each Lot
8ddcaab2-879c-5d47-b0d3-3f8344c33171 | note | Category - IP
990993e6-7ca6-5e0c-b636-2ede6d5f79dd | note | Responsibility - SE
58ed6474-63ee-503a-8879-c22329a96c36 | note | Verifying Documents - IFC drawings - package 13
c24005f5-35c8-5c2a-a895-2c956031df36 | textbox | Date Completed:
| checkpoint | 5.12 - Pipes - Trench Excavation
70f598f8-8a81-51da-ba68-7e612d466779 | note | Reference - IFC Drawings Section 701.15
3e383ca7-800f-530d-889d-6edad882bd3f | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
da5cd7e0-3e89-54a4-b0a0-849a087fc333 | note | • > 300mm, < 600mm for RCP
35dcaf5f-7278-551a-aef4-1ef908d3cfb7 | note | • > 150mm for Flexible Pipe
939af018-0859-54ad-8d35-62179dd2f936 | note | • The base of the trench shall be compacted to refusal using mechanical plant.
afae5658-0092-52f5-9523-dd40c21b40ff | note | Method - Visual inspection, Measure
6fe0ddd4-9fff-5ff9-a084-181a9f1bae48 | note | Frequency - Each Lot
517bd21e-590a-57a8-a514-212e98cfb3c1 | note | Category - IP
cd68f300-3f13-5e97-a37d-f1d9e118998d | note | Responsibility - SE
30de6eda-2a4b-53a4-bd58-e87c077dab9d | note | Verifying Documents - IFC drawings - package 13
84b39d09-9072-509e-8217-361460d00cd1 | textbox | Date Completed:
| checkpoint | 5.13 - Pipes - Bedding Placement
39b60e51-97dd-55a5-9364-7ca2537d65df | note | Reference - IFC Drawings Section 701.16
c4a65476-e603-538b-84f6-fd22522a704f | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
cd28d9ca-ab30-5164-8c8f-ebe9298a09dd | note | • > 100mm where D<1500mm
af9f4397-ef7a-59fc-8e41-e9dadf561ca0 | note | • > 200mmwhwere D≥1500mm
73d173e5-cf31-5f96-841c-ba95e5df225f | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
5f7b10ac-fad9-5b93-a873-db644544b6c8 | note | Method - Visual inspection, Measure
a57efc41-4bc3-5d88-b84e-04b49aceed04 | note | Frequency - Each Lot
07897e3a-db62-5748-935c-407b60db9a71 | note | Category - IP
c706220d-d9f2-5fb6-9eeb-d061b57cc91b | note | Responsibility - SE
ea9b5601-a046-5122-9ee9-c8bd1c3e7a20 | note | Verifying Documents - IFC drawings - package 13
df3c6be1-a4d0-50c3-824a-93e0069aa5d9 | textbox | Date Completed:
| checkpoint | 5.14 - Pipes - Bedding Testting
fd0dd52e-857a-58e2-8649-bd8cfc704be3 | note | Reference - IFC Drawings Section 701.20
2b30d468-d416-594a-a02a-335673a91ec8 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
0333d10c-86fe-53d3-9d6c-5a23e873a324 | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
71405129-e773-5876-bd01-f48f9913bf23 | note | Method - Compaction Test
fe6f172a-98a1-50d8-8c3b-e4a8518cab43 | note | Frequency - Each Lot
d35efc8a-9dbe-5f16-81b4-484747d42ba4 | note | Category - IP
972fd341-9d18-5f52-9ecb-53a24adf158a | note | Responsibility - SE
6b8ca982-9103-56b3-9bf0-48fcf9a024d5 | note | Verifying Documents - IFC drawings - package 13
b2c83092-6cc7-569c-af07-f30299d1c5d7 | textbox | Date Completed:
| checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
79d8d38a-8c0b-570f-b2c0-0dcc098127d6 | note | Reference - IFC Drawings Section 701.17, Section 701.20
bae2843e-abe2-5339-a10c-aaa431adfbc1 | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
8bfb2d50-bc59-504b-ac94-4444a189b866 | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
d5cfe77b-5ea8-5053-8c24-6936ab3955a4 | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
32855b46-f922-5c71-bc08-3dc9943694e9 | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
cb9033b3-5d19-563c-af50-19ac6dad9df9 | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
b25b3778-9de8-5ec8-92f2-098c4b9a581c | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
4a7b9c53-4688-5330-9298-59628ac15ded | note | Method - Visual inspection, Measure
71644f2e-28ba-5aa0-9925-174ea148acf1 | note | Frequency - Each Lot
8b2f2ee0-b87a-52cc-baee-41b1509db581 | note | Category - IP
10359d91-0351-586c-bd3e-9e290ab0ea9e | note | Responsibility - SE
70a78be1-2032-529a-abc6-448e838bc2fb | note | Verifying Documents - IFC drawings - package 13
e4ddb5ec-2cde-5844-aa05-b29ba0066518 | textbox | Date Completed:
| checkpoint | 5.16 - Pipes-Placement of Pipe - Flexible Pipe
b0c2ab9d-57ef-5ded-bd87-5d462dd85064 | note | Reference - IFC Drawings Section 701.17, Section 701.22
e5938a38-d81a-5eb0-b450-73409eaabd4a | note | Acceptance Criteria - All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
f768b84b-7c54-5236-889f-b1e3b4476fab | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
3a05e9d5-9e77-5e8e-b599-40d900b42864 | note | Method - Visual inspection
a8adff73-e9f9-59fe-817d-d5fe06bfd66e | note | Frequency - Each Lot
0c4031c2-804b-5b2d-ab33-78dd4d74afd3 | note | Category - IP
5ee5fd6a-571c-5017-bbc8-e7e41cbc80d2 | note | Responsibility - SE
35add517-2564-5d1c-8c5b-598fd9a4982a | note | Verifying Documents - IFC drawings - package 13
6bd024ef-bd3f-526e-ac5f-13faab451d91 | textbox | Date Completed:
| checkpoint | 5.17 - Pipes - Lifting Holes
9f8fea2c-7e03-5cb7-b418-e0678490dce8 | note | Reference - Section 701.18
9441d552-ba94-5e23-8e17-a4e17b05e6c0 | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
18c2728b-2318-5b6f-8a38-ed0c0966679c | note | Method - Visual inspection
4a7e31f8-4d8f-5369-be55-ebe430fb3c3b | note | Frequency - Each Lot
97a30247-b025-5c03-ba08-c60ab50b72eb | note | Category - IP
62dad747-3607-5570-9953-4f90c2f600a7 | note | Responsibility - SE
73edc9ce-b190-59b3-96d5-7a2a7f4bfe68 | note | Verifying Documents - IFC drawings - package 13
7f98c8f4-ed28-5bd9-85c2-1d7a63cd6758 | textbox | Date Completed:
| checkpoint | 5.18 - Pipes - As-built survey pick-up
65fdd3d3-74b9-5c3d-ac92-a9b001b83678 | note | Reference - IFC Drawings Section 710.10
4618d72f-c6c3-5b83-a951-b278234fa0ed | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
f45f9038-e968-52e2-9528-597f2c8c9ece | note | – Offset pits to kerb +/- 20mm
69c4d7c0-316d-51b2-85cb-7691b8f5d11a | note | – Plan location pits not adjacent to kerb +/- 100mm
a0ef3f04-dcc0-59a9-aa86-aab81cccb5d3 | note | – Invert level of pipes at pits +/- 50mm
9fa74f1a-7edc-5d7f-a50f-4764f6e59cb7 | note | – Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
15298798-008a-5250-8001-f19077b40ae3 | note | Method - Survey
cc50fb2d-9898-5685-9469-49c0814208f0 | note | Frequency - Each Lot
04be207a-fdc3-5150-8148-4758b722583a | note | Category - IP
b886bd9e-2a22-5165-8ab8-8116b0a6d842 | note | Responsibility - SE
69b97f1a-6cd7-5db9-b3b9-ff441fb04c83 | note | Verifying Documents - IFC drawings - package 13
86c1c59a-15f4-5a3d-93db-c181d3d47b0a | textbox | Date Completed:
| checkpoint | 5.19 - Pipes - Backfill Placement
96c3e9ad-2cf2-5da0-bc7e-b2c75dec5bcc | note | Reference - IFC Drawings Section 701.16
f5f8ae20-1eab-5d73-9a60-08db62f9a929 | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
1dcca698-0276-51bf-9c7f-904510874eec | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
52a13dd8-f804-5253-a677-74458ba968eb | note | Method - Visual inspection, Measure
a5a123bf-c02c-5a61-8fa4-d5b8329843ac | note | Frequency - Each Lot
620523bb-cb8a-5503-921f-ba0c1b50f821 | note | Category - IP
21a28aab-c82e-5f7f-9a55-473cf9814576 | note | Responsibility - SE
d78ec0b4-ea00-5a74-b460-10451afce3a6 | note | Verifying Documents - IFC drawings - package 13
b9786838-80ea-5cf2-9292-e42323a83b22 | textbox | Date Completed:
| checkpoint | 5.20 - Pipes - Backfill Testing
8811f545-8abb-5afe-88ce-e518460342bb | note | Reference - IFC Drawings Section 701.20, Section 701.29
dd8b82cb-edc1-51c2-8e40-5358f688259b | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
5d9fc6f0-26a4-5fe1-9f56-27a0df218c6d | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
e956664b-a745-58b3-ac97-e575abf8c622 | note | Method - Visual inspection
83d8a346-7eff-5697-b8be-515e585d7c0b | note | Frequency - Each Lot
79333351-1ce3-5a6e-bc64-51c117c2376a | note | Category - HP*
a0ac511d-0776-5f38-aba3-ddf6079c7af2 | note | Responsibility - PE
a4d07d83-1238-553e-96be-e6d1e7055b4d | note | Verifying Documents - Test Report
9e7bc270-69ba-507c-9581-2692faef88cd | textbox | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Flushing & CCTV
17cf6dc4-ffd9-58f3-8caa-43599bf28176 | note | Reference - Section 701.28, Section 701.30
7a2e3fc4-2ec3-5d1f-9de3-f1c2d3f09c11 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
0196d779-71f3-5cb1-96fc-6489ea45a624 | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
1bb3880f-6316-5a42-86f3-06eed6286cf8 | note | Method - Record Review
3a614928-5cf0-5b09-8fd2-5980501e453a | note | Frequency - Each lot
2ae0775d-f109-56e2-8b17-4477a4d707e5 | note | Category - HP
8107d998-7373-5889-a53d-f261c7e3375c | note | Responsibility - Nominated Authority
6b5144ec-2e05-589c-884a-15b88d90b78e | note | Verifying Documents - This ITP, CCTV Reports
018228e7-c6cc-5d84-a54c-2a9283fbd8b2 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - As Built Survey
5ae75aaf-1fc7-55ef-8422-197163abcd43 | note | Reference - Section 701.10
eb0c283b-efc6-50fd-b6fd-e44f5ca7a3f3 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
0daf43af-98e3-513e-9b61-8c5691b72d87 | note | Method - Document Review
aef88904-4655-56cd-9810-656ff45a04ea | note | Frequency - Each lot
226820df-c873-550b-8a08-e0160c39bd54 | note | Category - IP
eac9f31f-3456-5e13-b090-746d8ad12d4a | note | Responsibility - SE
44f70784-c4e8-5fcb-b1c0-ff5d37e03d7c | note | Verifying Documents - This ITP, As Built Survey Report
fd5647ac-8aaa-53c5-b3b1-9c7146501133 | textbox | Date Completed:
| checkpoint | 6.3 - Repairs to Damaged Pipes
5c826723-4332-59bb-9928-c29a9ae8d1f8 | note | Reference - Section 701.31
ac6f870a-0c4e-5988-99d9-f52cb15564c7 | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
bc855816-e88d-5e84-b6dd-1c24e3b48324 | note | • cracks wider than 0.5 mm
8b6ec901-b873-59bd-a22d-c069b359394f | note | • spalling of concrete
ee7a57f0-f606-5fb8-b3a3-27a20a7fcc4d | note | • exposed reinforcement
9ff6ace4-128e-58d6-bc9e-dad75573ee49 | note | • joints that are not fully engaged.
3433a168-f529-522d-9b6d-665d1f2f9877 | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
e9759370-b10d-56d8-8795-8cc307a6b86e | note | • longitudinal cracks greater than 2 mm
06dbd597-5fb9-5295-b0aa-779fed4bfd60 | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
175fd7da-d28f-549c-9b99-d0081892e58b | note | • circumferential cracks around part of the circumference with width greater than 4 mm
5d0f3aef-6020-5939-a10d-e17701662b55 | note | • penetrations with area greater than 400 mm2
e10ab73e-53a4-5d2e-bae1-3b6de360d7bc | note | • pipe joints that are separated.
59be98db-ed65-556e-8cf6-dbb1a2061371 | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
d88d4f68-1c3f-56b2-8991-66bd8b000fae | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
88f9cc79-2105-5f81-bbe9-95e6f077588e | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
e6e48f47-bb14-5765-bea0-b4226013acbd | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
86306aea-5613-5599-936d-9057b2570dc9 | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
e5ec0a41-5042-515d-9654-20ca187032e8 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
6c1c8195-eb9a-50c0-a326-17a106e6d995 | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
5605e607-91ad-5733-bd00-f14e7e0b3534 | note | Method - Document Review for Repair Procedure
137d3468-82d7-5237-b61f-da1ab4ecadaa | note | • CCTV Report Review
547350de-2c03-5f8a-84e3-101ac965cad2 | note | • Visual Inspection
4b666407-894c-52c9-a93c-952380abc867 | note | Frequency - Each lot
d2f08c4f-eddc-55ca-a910-080b21951b32 | note | Category - HP
db8ddab2-4209-5b17-b27a-77a46540bede | note | Responsibility - Nominated Authority
cafa6c1c-4aae-5ee3-9a3f-42ae8f8509ee | note | Verifying Documents - This ITP
e2e61f29-fb84-5a37-a460-a408025f1528 | note | • Approved Repair Procedure
509ccef0-d07c-5800-9610-be976114bee3 | note | • Post Repair CCTV Report
d443fb15-0d16-550f-83f0-bd8026e838f1 | note | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
c7d5bb2b-f955-580a-a40a-08c3a1b4a4fc | note | Reference - MRPA Quality Management Plan
c8117e65-da6f-5d0c-b479-bca64f7a29b4 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
b4f7b8ec-2715-5aa0-918c-c35edcb1eb64 | note | Method - Document Review
2c361a9d-44dd-5fd9-9279-71b9efba6107 | note | Frequency - Once, prior to closure of this lot / element / Work area
af3425ee-b8f6-52bd-9bdd-48c0763597f0 | note | Category - HP*
8bd8b407-dd98-50f3-af31-9b68a7f6e7c2 | note | Responsibility - PE
c028964f-9a00-5716-86a3-cc4329510172 | note | Verifying Documents - This ITP
6c0773a2-4df4-5eae-9cdc-b6c2bd9bc598 | textbox | Date Completed:
| checkpoint | Final Inspection
07c78d4d-dac2-5838-aa89-0901f8469d86 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
01cb9db2-ff5c-5467-8414-8baf551cf698 | textbox | Name:
2a3c7cfe-f7cb-5b59-98e2-1fc8d6afb192 | textbox | Position:
0948c33f-18de-5c78-830f-2a6705494b3a | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading - Rev 1 | itp | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading | 7efa8c2e-b70e-48d9-bb2d-4b498511bc9a
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
a32b4918-940b-59df-b037-fa678be9004c | note | Document Title: OHLE-ITP-MRPA-Calder Park-OHLE Wire Regrading
b24f3662-d736-5c6d-8c24-1d295100b84e | note | ITP Description: OHLE
25492ccc-2582-53b0-8943-12fa0f2c38ee | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ad3f5baa-9994-5773-8391-035c461cc5bb | note | Discipline (e.g. CIV/STR/RAIL): OHLE
2ff6095e-5e05-59bc-8c1a-3f3a106d120f | note | Revision Number: 1
7b1e0a27-d0fd-585b-ab34-32628600583d | note | Revision Date: 24/07/2023
76f350fc-106a-58a1-9353-3bfa21a11786 | note | ITP created by: Kevin Liang
| checkpoint | 1.1 - Overhead Line Electrification
b0e71249-5732-5839-8aa7-204459f9897d | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
| checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
7779b8a7-1e6b-53c9-8f90-7b8dbcb2306a | note | Reference - VRIOGS 001 AS 4100
| checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
030b68d1-71cd-5c0e-9f23-0387c5c47313 | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1)
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Procurement Materials delivered/collected to stores/Site.
54441720-fbb6-54e2-8cc1-9ca4f15bccfe | note | Reference - Contractor - Site Material Control procedure.
c0bce270-39db-5290-9909-bc2c47a7b758 | note | • Cat5 Material received -Calder Park Tracking sheet
3b6ef55b-9201-5c65-a128-3585c4986c4e | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
f4ee23b4-670b-593e-a89a-961727b3bc66 | note | • Certificates of Conformity provided by MRPA
bd78a38b-586f-5ad2-9406-72a4423dad64 | note | Method - Document Review
caab6fb3-90b0-5893-a66d-d122f9b1eee7 | note | Frequency - Once for each supplier, prior to works start
f955e49b-709c-51b7-bd0c-72cb3503037e | note | Category - IP
30a7aad7-fe4b-5159-b948-7cb08e009544 | note | Responsibility - MRPA Issue, CAT5 Receive
bb90ef3a-5489-539e-a3ec-461a9040c153 | note | Responsible person - MRPA
3ad1ec87-e13a-5674-9029-aa29982fd44b | note | Verifying Documents - This ITP Signed Off
df87d913-b5da-5e87-8523-c5a62b89408c | textbox | Date Completed:
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Produce Work Package Plan
647875d4-ab8c-5fa6-8e49-391202f8d49d | note | Reference - Work Package Plan
b7610fde-5ea1-56cc-a47e-805de3163062 | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
def1689c-a197-56e6-aa61-18cc255c16bc | note | Method - Document Review
e2870b42-77a5-5e1b-84d1-5d9ad90f550d | note | Frequency - Prior to Works Start
47a18377-211b-5f96-9465-1915acc64675 | note | • TBC in accordance with MTM Standards
c9c74a07-8335-5d37-b59c-c4950b67d386 | note | Category - HP
c95f874b-9c52-57d4-a123-382c705256e6 | note | Responsibility - MRPA/CAT5
6358471a-4c1a-5c3b-b892-558e74d1ce70 | note | Responsible person - MRPA/CAT5 Engineer
2860e522-3ee5-5c5e-a9f2-a0971b13b4ad | note | Verifying Documents - This ITP Signed Off
a0b619fa-dc12-5c02-b0dc-232aa45ee6a2 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
25dbfc00-e399-5ca6-abde-bdd51077fc7f | note | Reference - Contractor Design Management procedure. MRP-DPK-060-00-ETN
c269feec-0bfd-5bcd-a7ae-31831e3339eb | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
404e5e9a-64ee-5f13-af6d-60a00acf2835 | note | Method - Document/Drawings Review
d9b6a5e5-4e8f-5d34-8329-36b075237912 | note | Frequency - Prior to Works and at regular intervals.
158fd854-05e8-5929-b1ff-e8ff8acf739c | note | • TBC in accordance with MTM Standards
f782056f-48db-56be-b252-bb05cab118de | note | Category - HP
c870d3db-8fde-5b4b-951d-4fdb1182d6c6 | note | Responsibility - MRPA/CAT5
bef60c99-85cf-5472-8b1c-1100aa422779 | note | Responsible person - MRPA/CAT5 Engineer
a50307b9-ad1f-5342-8248-d328ef67cd0f | note | Verifying Documents - This ITP Signed Off
4699bce0-8eec-568f-8233-df558510a9b4 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Task Specific Permits
f5693ae4-51d0-5bdc-b68c-01197ecbde09 | note | Reference - Working at height permit. OHLE SWMS
be6a0bfa-dd26-5850-a84b-e6a0ccba74dc | note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
3eac8767-508d-59f4-9ee7-be71a87a6bbd | note | • Task Permits to be generated and signed off by appointed person.
2547ba90-72b5-58a6-8515-04a29f67b073 | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
ec1b4d5c-2480-5ec2-9cd1-e3f9b8b800c8 | note | Method - Visual, Document Review
bd3bdf82-9a9d-5848-a0c7-3c9a5b8d5558 | note | Frequency - Each Task prior to works start.
6620f226-5971-5a24-af39-b497cb6a2c99 | note | • TBC in accordance with MTM Standards
40a14e7f-b66b-5731-91c6-ab61c1901611 | note | Category - IP
6e65d00b-e6e7-5885-93fc-6577fc136f31 | note | Responsibility - CAT5/MRPA
69bdd03a-23f7-564d-bf66-f14fd2b487f5 | note | Responsible person - MRPA/CAT5 Engineer
4bdad0fd-9bed-5fd3-b8ba-3d3c30b28a64 | note | Verifying Documents - This ITP Signed Off
561ca558-88d3-5449-8222-081dd03ace9c | textbox | Date Completed:
| checkpoint | 4.3 - Cantilever assembled.
c6f514ff-5b85-5b76-ae5f-db71e1a92cc2 | note | Reference - Cantilever assembled as per IFC design.
54410576-e071-54ff-b894-47642dcfb53c | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
7f70a447-3296-5b97-8bd5-2048bdd1bbe2 | note | Method - Visual, Document Review
a7662440-4f59-5384-9cc0-c18322251eed | note | Frequency - Each Task prior to works start.
1717de01-4438-5896-9e4a-6cc21c133f83 | note | • TBC in accordance with MTM Standards
66fb8fcd-5d20-5803-947d-2c01af582821 | note | Category - IP
49523014-be97-58e2-8c29-29682e00ef57 | note | Responsibility - CAT5/MRPA
ec8d59bc-7c66-5544-9eef-38c773955d85 | note | Responsible person - MRPA/CAT5 Engineer
81932f57-0373-533d-bf5d-69ce22f26c5c | note | Verifying Documents - This ITP Signed Off
63e8aec9-4f7f-5b12-b365-f2664527ba8e | textbox | Date Completed:
| checkpoint | 4.4 - Pre-Installation check
a91c08d8-6384-5fa7-8087-08a9303875c0 | note | Reference - IFC wiring layouts, IFC cross sections and BOQ.
e3b8e6f6-0331-5c47-9aa5-1c9618f488c3 | note | • Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
4d69206f-9f12-5690-97ef-16cb37c70214 | note | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
2679c460-2750-5b67-aaf7-ceb62daf332b | note | Method - Visual, Document Review
0e3016a0-62c0-5177-949f-8ce5a19f84d5 | note | Frequency - Each Task prior to works start.
5e5f481c-b1ff-5c60-af3d-4f1b54ea2fee | note | • TBC in accordance with MTM Standards
27998cf5-0dc6-5138-847c-2ae77523d8fe | note | Category - IP
7ba89816-325d-5da0-b30c-b8a1dd8c3559 | note | Responsibility - CAT5/MRPA
04ebf7e0-da85-5683-8f77-13716a65ffc9 | note | Responsible person - MRPA/CAT5 Engineer
61814104-be95-57a7-b96d-314684428da6 | note | Verifying Documents - This ITP Signed Off
88c96d68-69d4-520d-8f87-9c05a72db722 | textbox | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Cantilever installed.
46babaf0-d542-598d-b243-d16c8d31c5af | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
a0e36c4d-6bf9-510d-b641-fbdd9f666b6a | note | Acceptance Criteria - Work instructions in accordance to IFC design
f1dda229-c289-5dc6-b5bc-bc493e5eb90b | note | Method - Measure, Visual
4b902408-c214-568f-833f-f2ffe38b040e | note | Frequency - Each OHLE Structure
f0dce753-f7e9-5016-ac82-1dcf63e778ea | note | Category - IP
87b88d2d-ef3f-55d8-a17d-484bec024cf9 | note | Responsibility - CAT5/MRPA
dc03a787-ba63-5fe8-a9cc-39c40e54c438 | note | Responsible person - MRPA/CAT5 Engineer
8c039af6-eaec-53fe-8fae-14f26be2a424 | note | Verifying Documents - This ITP Signed Off
cbdf85a3-28cc-5a29-a0f1-c6d557a5142f | textbox | Date Completed:
| checkpoint | 5.2 - Install SPS to correct height / position relative to track
3f49ec51-9932-514f-9d17-d8b2047e4e26 | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
dcbc225e-93bf-5ae4-91a4-f1431fdef5ff | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
e995ab48-9f4a-5fdc-a87c-8c29d0047dbc | note | Method - Measure, Visual
c5ee7828-1c17-5ea1-ae0a-201fc80dd52f | note | Frequency - Each OHLE Structure
bab6a7d8-c23b-504b-9816-35f7129d979e | note | Category - IP
53bc6145-954b-5c67-91c5-7df31f70320e | note | Responsibility - CAT5/MRPA
82b42f6e-d39a-53e6-ad04-6eaf22c66661 | note | Responsible person - MRPA/CAT5 Engineer
908bbc34-b7b1-568a-8f29-656ca5be4740 | note | Verifying Documents - This ITP Signed Off
05777c99-1d8c-5e24-a52d-0175c6596b40 | textbox | Date Completed:
| checkpoint | 5.3 - Cantilever checked once installed.
acf75bd7-67eb-5787-a3e7-c23d8f3be8ab | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
10373dc7-d52e-5cb4-8e0c-a2eeba8b1597 | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
3e19309a-fb3a-5912-9c71-1862aa63d414 | note | Method - Measure, Visual
9a8f3773-f711-5484-935f-a0025e4efe38 | note | Frequency - Each OHLE Structure
3eef33ed-d060-5161-818a-67b77e065384 | note | Category - IP
80e4972f-c054-579d-a4ec-64409289227d | note | Responsibility - CAT5/MRPA
59773a61-49cc-5c46-8218-8c175358af61 | note | Responsible person - MRPA/CAT5 Engineer
262efde4-d01c-5504-a1b4-d422bb6fc0a4 | note | Verifying Documents - This ITP Signed Off
fd70e711-a0cf-5756-b39e-9479e50515b7 | textbox | Date Completed:
| checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
0cfcd28f-03ee-56d3-9c6e-12b45a52ecf5 | note | Reference - Install as per design drawings.
e4efe236-000d-534c-8644-905b6ae8c1e6 | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
5bcca83a-6398-53fc-9a89-0f11b0d4e902 | note | Method - Visual
03b9fe89-920c-5c59-bd3d-3194104e6528 | note | Frequency - Each OHLE BWA structure
bb3c2c82-e2a7-5e35-9c20-b9cad02f8ec2 | note | Category - IP
1c77a65b-a7b8-5fa5-b9e5-f764a2da5b8e | note | Responsibility - CAT5/MRPA
9fab31a5-26b9-5f93-ba2c-af1437e999c1 | note | Responsible person - MRPA/CAT5 Engineer
3a6c2ea2-2def-5657-81c8-767ff34c380a | note | Verifying Documents - This ITP Signed Off
a15d33f4-22a2-5f9b-b57d-1f8b9ba971b2 | textbox | Date Completed:
| checkpoint | 5.5 - Installation of small parts
01a6bf55-fe0e-5dae-8cea-a806ac0f6a33 | note | Reference - Install as per design, use span/ambient temp. tension charts.
ff75c1b3-9a05-5327-a803-83a409b6f2a3 | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
5fe3c8d8-b4c5-538e-b3c6-70bd9f1b32e4 | note | Method - Measure, Visual
bae12386-ad01-5f14-ae96-021dd9689cda | note | Frequency - Prior termination
049e82bc-b4c4-5efc-9ffc-ea355c0bd9a1 | note | Category - IP
300b6b3a-112f-5c8b-a643-8f261499ad9b | note | Responsibility - CAT5/MRPA
3d3a7935-ef13-5990-8128-3867d448141c | note | Responsible person - MRPA/CAT5 Engineer
bac1c9f5-f9e6-5bc6-b914-80fc885e216c | note | Verifying Documents - This ITP Signed Off
8adb4494-5bf8-5d89-8fc3-a087a0ae59cd | textbox | Date Completed:
| checkpoint | 5.6 - Complete Clearance Checks
96e12612-ca9c-5885-b9ac-ea845f610e0b | note | Reference - Install as per design, use span/ambient temp. tension charts.
8d8dd6ad-0c7c-5279-bfd3-9e5298846e68 | note | Acceptance Criteria - Visual inspection for clearance and wire staging from Hirail EWP
d4940203-2538-59aa-acc6-f58d35656e06 | note | Method - Measure, Visual
e87512dc-8f7d-55cd-9cb9-9f8a70d2416c | note | Frequency - Prior termination
e0f6ce63-5600-59a5-a195-1c99018bf51a | note | Category - IP
15a4daf7-81fd-56af-91a2-8b51fd545ce5 | note | Responsibility - CAT5/MRPA
0ecd002e-102c-5c4e-b7f6-d82cd9dcabf7 | note | Responsible person - MRPA/CAT5 Engineer
28ff49eb-cb96-5369-a071-2264c7ce497a | note | Verifying Documents - This ITP Signed Off
2a42cc65-30bf-5c9d-a604-923a29fc6dc1 | textbox | Date Completed:
| checkpoint | 5.7 - Complete Pan Run Test
81a48cdb-b208-58b7-8f97-d9992f0d3c0c | note | Reference - Install as per design, use span/ambient temp. tension charts.
65116da3-f7c2-5698-bea3-4cd747d22d13 | note | Acceptance Criteria - Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
04e8a10e-15e7-50a2-8ec0-2506a6f4ba73 | note | Method - Measure, Visual
27fc42ac-2c22-5399-b825-773b5a6d4b00 | note | Frequency - Prior termination
3b7fe085-bbd2-50df-b813-7e8473721916 | note | Category - IP
596278d9-8f1c-58bc-8afc-d3eff7febff7 | note | Responsibility - CAT5/MRPA
cc9798b7-c56e-5b0b-9612-51270f42fbbd | note | Responsible person - MRPA/CAT5 Engineer
9b901689-cef1-59e9-9587-5de88a4d0297 | note | Verifying Documents - This ITP Signed Off
bd832821-46fb-53de-bc27-03938d98398e | textbox | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Defects/Temporary Works
eec8f481-2a40-502f-bc3b-44b3db3ac3b3 | note | Reference - IFC wiring layouts, cross sections and design drawings.
98ef030a-e015-59fc-861a-d66f37749259 | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
e6cb15dd-ea29-5e22-94d3-6602589e7e20 | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
640fe297-343f-55d0-9da0-a273f1af8169 | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
4de6b930-d150-57d4-adf4-34d54d0e6d5d | note | Method - Document Review, Visual
d9f9dedd-c24d-53bf-b0dc-cb2364dce366 | note | Frequency - Each OHLE Structure
3c96d655-8276-5b16-8eb8-982d5b411e5a | note | Category - IP
90f688aa-dd5a-5007-86f8-604832b8845a | note | Responsibility - CAT5/MRPA
f2cf3eaa-589b-5e8c-8be7-7d4c955441bb | note | Responsible person - MRPA/CAT5 Engineer
e76874d9-3dcf-5f2e-9e56-653fda0eab08 | note | Verifying Documents - This ITP Signed Off
52c032e1-d094-5125-9a04-2b491f96d651 | textbox | Date Completed:
| checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
73fd6133-97c5-5748-b0e1-5c77ae4044cc | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
90fca279-7bd9-5a24-ae89-1645d315c920 | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
8f162cbd-862c-53e5-ba1f-e5836b38d5d9 | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
26fe2918-5922-5ca0-966c-04d0b2be1918 | note | Method - Document Review, Visual
9adac229-0d5e-5586-bb68-e2e8fc5630f2 | note | Frequency - Each OHLE Structure
298e6225-2bdf-51e5-9c2a-5fe7706f7151 | note | Category - IP
5f7262c5-45a7-5c09-9b34-c6efe70a3d5f | note | Responsibility - CAT5/MRPA
2a95a4ec-feb4-53a3-8be8-9d26485dda4f | note | Responsible person - MRPA/CAT5 Engineer
de63686d-8807-57c4-a5ce-245df97f28d9 | note | Verifying Documents - This ITP Signed Off
8ac3918d-1b09-5b6e-9c72-ddc29fd4ca8d | textbox | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
34ef5da5-0fd8-5c77-a52f-1f90a7f17d3d | note | Reference - MTM Quality Management Plan
e30c34da-27c4-5d0d-8323-6e6871e15db0 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
20fdd725-2040-5c87-814d-52fc7256a97a | note | Method - Document Review
50b5cab6-21ae-5c0a-8081-ab21758dac42 | note | Frequency - Once, prior to closure of this lot / element / Work area
3e43dfd8-96ac-552e-b248-e9fb750b7f5a | note | Category - HP
d6071b4b-2cfb-5ef2-abe4-cadbdf8a2a75 | note | Responsibility - CAT5/MRPA
57deea1c-4c99-5837-83d7-970e1b715070 | note | Responsible person - MRPA/CAT5 Engineer
121d5590-2517-53cb-bbc6-6938e940adc5 | note | Verifying Documents - This ITP Signed Off
687d1eb8-2574-5c17-a9df-7c2123e8bf5d | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
9b47ebcf-8d0c-5760-aaac-2b4d451d3fac | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6819ad12-5e86-5f4f-a24e-08239dab2609 | textbox | Name:
7b5045be-d17f-5b25-b8da-95c5214d527c | textbox | Position:
49fce55a-18dc-5059-9808-a61c0ae69067 | textbox | Date Completed:
| signoff | Sign ITP
16d8d230-3116-4fd3-b652-1d76c20d968f | checklist | ITP-050-CPD-RAIL-Calder Park-OHLE Installation Rev 1 | itp | ITP-050-CPD-RAIL-Calder Park-OHLE Installation | 330cd3ac-9297-45d6-a4c4-fb62d684d8da
12da3871-0f0e-4e61-9a69-c8e0296b7c1f | section | 1. Referenced Documentation
c949bcd6-0ea6-49c4-a7b9-b0f9b9394a38 | checkpoint-no-value | Referenced Documentation
79e67654-9deb-596b-9e43-f41e56541d06 | note | Document Title: ITP-CPD-RAIL-Calder Park-OHLE Installation
aa1df8f9-e051-556f-80b6-27fe3074d576 | note | ITP Description: OHLE Installation
61939789-0706-581f-a222-9d50f0be1b21 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
a66c3517-ef63-5476-90a7-625123e8d4bc | note | Revision Number: 1
8703b134-eb8f-554a-9791-00bd15c49117 | note | Revision Date: 24/07/2023
607c0702-efbf-50e1-8ede-8aed62fe79b9 | note | ITP created by: Kevin Liang
97061c8c-73c8-5449-aff6-ad189371d099 | note | 1.1 - Overhead Line Electrification
d2c2bba9-5410-5f02-81d8-baf7fd9d8051 | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
f86364c6-3a46-53b1-b5af-1b9a38a59618 | note | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
2798caaf-fa3b-5de6-8574-87c9177ebe76 | note | Reference - VRIOGS 001 AS 4100
c0aa1d71-be06-5c51-a724-faba619d8464 | note | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
f5a57c06-c68e-57c6-be4d-ebe4a07e56bb | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
6e8c46ab-9339-562b-b1a8-4ab87e6d9424 | note | 1.4 - Fabrication of Steelwork
48a406f0-2c84-5d1d-b9af-fcfbc5f71f96 | note | Reference - VicRoads Section 630 January 2023
02fe8ea4-e756-5c0e-9fbb-43bb7719783a | note | 1.5 - Electrical Networks Standard Electrical Networks Principles and Performance
69302164-9732-56a9-8cd1-b2cd0ae7275f | note | Reference - Structural Steel Work - Fabrication and Erection
af204715-ad9e-4ba9-8ae6-634a78a0fef8 | section | 2. Preliminaries - Materials
68fda354-c256-4d32-861f-9c1680522c4d | checkpoint | 2.1 - Structural Steel Components and Fasteners
c4ad86b0-5d28-5385-9136-f17f6a930fff | note | Reference - IFC Drawings
1bbc0be6-5d08-524a-a87a-c82bfd87bfed | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
aebc28d9-91ce-59fa-81da-424945d6583f | note | ○ Typically this consists of but not limited to:
c1457d73-aeae-5cbd-8464-7ba786c4d96b | note | i. Completed fabrication ITP
9670042a-97b4-5e9c-8fdb-426c17abb5f7 | note | ii. Weld Procedure Specifications
a10d27d7-c56c-59f1-aa94-b61bf5d79258 | note | iii. Weld Procedure Qualifications
dc581a4c-3c97-5a8b-8e88-d353b2f243a1 | note | iv. Welder Qualifications
ef701064-bb41-5d08-a475-efb8eddf46bd | note | v. Material Certificates
65220b57-4710-5008-a447-774394b13872 | note | vi. Coating certificate(s)
326fbc68-a2b5-5252-8047-fb62b5ec7b6d | note | vii. Non-destructive Testing (NDT) Reports (if any)
c23a44d9-e03d-5785-a75f-b2bc725bd856 | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
23948e39-f747-5c3a-be7c-7eb69c99e6fe | note | ○ Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
f1a625f3-4d08-5a12-b149-b4c79103a415 | note | ○ Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
388aa28d-6dee-5316-bb1d-1e2331246444 | note | ○ All bolts nuts and washers are hot-dipped galvanized.
e6655abe-148e-57e4-a67f-0a4c8129faac | note | ○ Collate: Structural Steel Quality Assurance Documentation.
3b5b4d21-3fb6-5ccd-afb1-a6d0c4a87761 | note | ○ Attach: Collated QA documents in ConQA
45ba3a00-5154-58ee-b46f-2cb9387390ce | note | Method - Document review
3c789553-2780-560a-8e8f-eeac0500413a | note | Frequency - Where applicable/ Each element
ac22e4eb-1707-5440-8011-89a05ab9f534 | note | Category - HP
e1fa8944-c83c-5fb8-b2ea-30f09c867be0 | note | Responsibility - PE
deee5bec-b420-51b5-b727-37b458dcbc2b | note | Responsible person - MRPA Engineer
5d1e4baa-09b7-50ad-9976-c8f8adb3cf49 | note | Verifying Documents - This ITP Signed Off
acc15b40-8f6e-58c7-8942-cf50f0b09e03 | date | Date Completed:
cdc2fd9c-8e3c-4cb5-90bc-c6f2bdc552a6 | signoff | AUTHORITY HOLDPOINT
26f2d230-674f-4695-9638-c371dd22fa6a | checkpoint | 2.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
2470affd-ff95-59c1-aa2a-da432678e37a | note | Reference - AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
58d5ed29-45fd-595d-829c-1ed22c5ea2f3 | note | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
b53e9bc4-5da0-55a8-b68b-612d46ad0312 | note | i. technical data sheet or information on the product
aa7949b1-46f5-5d5c-8c53-b5a13a74ad6c | note | Method - Document Review
555eddcf-6f2d-5106-94ad-56420cbe4d59 | note | Frequency - Where applicable/ Each element
e51229b6-cfdb-5d6a-ae74-1aaf600b7198 | note | Category - HP
b3832077-d65a-5563-82c8-dcffeee49582 | note | Responsibility - PE
8976f400-500a-54cb-a432-6d40c2796d53 | note | Responsible person - MRPA Engineer
124753e2-24ea-5bab-ad56-3d2ce1fca46f | note | Verifying Documents - This ITP Signed Off
f0486c6e-a834-503d-a6af-0f779f45ec6c | date | Date Completed:
beadfc5e-a850-4225-928a-49b0e986a232 | signoff | AUTHORITY HOLDPOINT
3431b6f9-56e0-4b71-9659-20642a0d92a1 | checkpoint | 2.3 - Overhead Wiring Small Parts Steel and conductor wires
dfe7b3e8-09cc-51b7-9af0-a728eac1a9f8 | note | Reference - Relevant MTM Standard Drawings
6152a3cc-fedb-5d96-adea-2ba122add6f0 | note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
fa6b40ff-78f7-5372-abdb-6464a3a94dd5 | note | ○ Deliveries are to be inspected to match the purchase order
052bf5eb-7170-5dc9-9e3b-e6203977591b | note | ○ Attach: Purchase order/Delivery dockets/Certificate of conformity
9f12a9a6-a203-5413-9566-c45d7d6ad7a7 | note | Method - Visual Insoection and measurement
2bd8fe9b-7791-5907-a545-fd88448860d0 | note | Frequency - Upon delivery
b7ebcf02-c8ed-5866-8de1-31f04c748520 | note | Category - IP
12a16bfd-7677-5b59-989b-383a61fc45a6 | note | Responsibility - PE
d46d57d5-e97f-5d09-b2ff-247baacb043c | note | Responsible person - MRPA
95a35096-a8c7-5369-96d8-a863cd783051 | note | Verifying Documents - This ITP Signed Off
13e5e3f9-5e96-5c9f-8c28-c5c7229c08a9 | date | Date Completed:
67ca3cba-279f-4e91-8944-bd500053680f | checkpoint | 2.4 - Grout
c61f72b1-f96f-5117-9f49-9047f554d250 | note | Reference - IFC drawings
8007a1d7-da90-5c94-aab0-1d09ad688f1f | note | Acceptance Criteria - All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
aa7c0472-700a-5e5e-b523-56016bac1d1e | textbox | Enter: Teambinder Material Approval number
f4bb11d7-2c73-5ed2-9114-0e27d9379ee4 | note | Method - Document Review
4a0b7f5a-9d82-520f-b13f-683c54a58409 | note | Frequency - Where applicable/ Each element
cce6345b-8524-5f1b-882c-d2621dc92f8c | note | Category - HP
acefe402-0932-5252-ba82-58d03fed4daa | note | Responsibility - PE
4cd2d792-9f5f-51c6-8f80-4cf237efbbb0 | note | Responsible person - MRPA
063714fb-571d-51c2-901e-76cd152df8ac | note | Verifying Documents - This ITP/ Material Approval
fe050b2c-7953-556e-bf27-da472fb34c82 | date | Date Completed:
bd04067f-e131-48d3-9a7c-20719b5b6e85 | signoff | AUTHORITY HOLDPOINT
a45e277e-2deb-4e16-8c7a-d7b014e27e49 | section | 3. Preliminaries - Procedures & Documentation
4ee6e64a-624c-4118-99ca-e2a5cee3baac | checkpoint | 3.1 - Installation Methodology & Works Method Statement
261772b1-47de-5e60-9035-eb5b1751c8d6 | note | Reference - AS5131 Clause 11.2.3
bf1b81c0-5817-5b99-ad92-ffd84af1373e | note | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
d7cb104e-4802-59f2-9783-e6b4bb8f33f9 | note | – Transported to site;
c880cdfe-06b1-5291-acb5-b007b5aad9fd | note | – Handled on site;
57ee6c28-3c3e-51d8-9d95-a0be57f3f8cc | note | – Installation Procedure (subcontracor ITP's);
9144274e-b615-5db2-8a06-00c97ac6fe08 | note | ○ Submission of Work Package Plan and MRPA approval and acceptance.
46129c9a-991b-5db4-89c1-8dec76351d8d | textbox | Enter: WAP number
b768900b-c1cc-594a-ac60-c94d96d5d5fb | note | Method - Document Review
40ab9ea7-2082-5ffc-9ff4-bd7aac3dacf1 | note | Frequency - Prior to Works Start
1301d7f8-9702-5c4d-8674-ee559bbd4a6e | note | Category - HP
cc044e41-3570-5a94-aaf3-8bb57e127d02 | note | Responsibility - MRPA/CAT5
23ded55e-85f6-5398-9dbb-d63f914cec23 | note | Responsible person - MRPA/CAT5 Engineer
bc21ce7d-34b5-5298-b116-f33d90a645fc | note | Verifying Documents - This ITP Signed Off
760fb29e-a906-507a-8f85-63137322e26d | date | Date Completed:
b4c8cdd1-170b-49db-8b77-2686e3214c4f | signoff | AUTHORITY HOLDPOINT
3ccea34d-1009-48a6-bd26-e5d69d2ed285 | section | 4. Pre-construction Activities
111bc94a-1fcf-42b1-9449-a3d4911eaf21 | checkpoint | 4.1 - Approval of IFC drawings
3cf6623a-76c7-5260-9084-d773ab19efba | note | Reference - Contractor Design Management procedure.
d2f5f049-dbeb-5bfc-8fca-efd4d3f4db7b | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
b386678a-384c-539b-a41e-6ac870f0df29 | note | Method - Document/Drawings Review
cc548a9c-4c97-5297-b3fa-c2ae37935bf4 | note | Frequency - Prior to Works and at regular intervals.
508fae2a-2970-57fe-8b5f-750d48153581 | note | Category - HP
c3c9a3b3-e999-596c-8176-1751f0510f68 | note | Responsibility - MRPA/CAT5
5e68f72f-a4ad-5d1a-bfb2-4f98fff7b5e2 | note | Responsible person - MRPA/CAT5 Engineer
98868494-b76e-5696-bb63-c8df0f847fdb | note | Verifying Documents - This ITP Signed Off
6db2ec5f-d57b-5f6b-a350-0bc47740b86c | date | Date Completed:
e0e36286-8902-4a13-9a68-5b89a0073fab | signoff | AUTHORITY HOLDPOINT
d6f0205a-b472-454a-bb95-6835db6e2953 | checkpoint | 4.2 - Cantilever assembled.
b4dbf94e-b057-50fd-ad41-6f4b0d45c320 | note | Reference - Cantilever assembled as per IFC design.
d980be09-00e2-5e73-9d1c-e22f8a2e8081 | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
2837b1a9-d5d8-549d-844e-2af415d6000f | note | Method - Visual, Document Review
3f981cd6-ca47-5bfe-b1f6-134e84a10215 | note | Frequency - Each Task prior to works start.
4255748e-6589-5b95-b0f5-7092ee97d5d5 | note | Category - IP
8fabe298-6758-5dd9-8a98-b77e5a346e72 | note | Responsibility - CAT5/MRPA
89b9d826-980b-5775-ae16-4cf62df92113 | note | Responsible person - MRPA/CAT5 Engineer
b7aa4c6c-94a1-5b89-9d51-7cdb2af38b0d | note | Verifying Documents - This ITP Signed Off
e0d3f352-114c-563e-94ae-0221ae92c28e | date | Date Completed:
0e3d25b0-632b-4d9e-84ec-16da4aed0843 | section | 5. Construction Activities
4c0ac3ec-f37f-4691-986d-8288dfbf3c68 | checkpoint | 5.1 - Mast Installation
40eb4ba5-476b-5d65-832d-6189d9443f84 | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
d3c62e43-5e70-5b2e-a194-07db90d454d1 | note | Acceptance Criteria - Work instructions in accordance to IFC design
d5e78fe0-26ec-5841-8502-8e6a3d104b30 | note | Method - Measure, Visual
31c3068d-6bb3-542b-be1f-2770ace905a2 | note | Frequency - Each OHLE Structure
67f661e0-80e1-56c0-aacc-5c436415881a | note | Category - IP
bd7e7358-d953-5c53-83de-648c36d9fe2d | note | Responsibility - CAT5/MRPA
f9692a5a-4e7f-52b5-810b-dc8981d01685 | note | Responsible person - MRPA/CAT5 Engineer
d61f2436-10f1-558c-9ad0-1b4cd5598406 | note | Verifying Documents - This ITP Signed Off
503f2be4-2482-5ebf-a716-40ef4b04195a | date | Date Completed:
c2618bea-b0f0-442f-bfa8-bdafe293b623 | checkpoint | 5.2 - Cantilever installed.
4632056d-4212-51d0-b8e7-3b1716c30dea | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
916ec3b3-e4ab-5fcb-8630-d98ce9a63584 | note | Acceptance Criteria - Work instructions in accordance to IFC design
1662ac48-3825-56d6-9d18-89691d8ae33e | note | Method - Measure, Visual
39564a54-b5e4-547e-96fc-2c840ce43e2b | note | Frequency - Each OHLE Structure
3349cc50-cda5-5dd6-bd21-aef0804ce2ad | note | Category - IP
d3fd4dff-0b4a-5a9e-bbdb-886e7e87c54a | note | Responsibility - CAT5/MRPA
63c64613-8a54-504a-ad50-ba5aad41a894 | note | Responsible person - MRPA/CAT5 Engineer
0d24ef5b-fb83-5354-ac8e-b11e5d1c500e | note | Verifying Documents - This ITP Signed Off
727c9396-55c6-59da-be83-9113a16d5763 | date | Date Completed:
f59b9c52-0891-41f4-ae54-9c508d7ef1c7 | checkpoint | 5.3 - Bearing type Joints TB Friction type joints TF
7be90eda-0e45-58fa-8481-e20baa1530f3 | note | Reference - IFC Drawings
6cdd31d3-1654-5660-ab1f-4c93a2729d59 | note | Acceptance Criteria - BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
c6cabad3-6b43-5521-8fad-c98392c94729 | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
f3dc75be-55f3-5262-8b3f-489a4c555a71 | note | – DTI squirts are to be visible for inspection
5bf7651e-e2a6-5a1a-b513-034e170c3b61 | note | Method - Visual
2c0fbf98-7426-546d-b98a-6f8a17d17a43 | note | Frequency - Where applicable/ Each element
2547b9f8-332c-52b0-a3fc-a69ec4dfd4be | note | Category - IP
22cfc949-6aef-5a9b-a552-9a0845db9eab | note | Responsibility - PE
9534dd42-95e7-5edc-81ff-796cd8af7113 | note | Responsible person - MRPA/CAT5 Engineer
77de140c-a8d9-5409-8fb3-4ec08c7854d9 | note | Verifying Documents - This ITP Signed Off
436fe59f-91d6-54d8-ae47-58488b700aba | date | Date Completed:
392b5bc8-a6c9-4319-ab79-3692a5731ea4 | checkpoint | 5.4 - Install SPS to correct height / position relative to track
6ae251d6-a322-5a8c-b906-ba14884a8c06 | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
20583cf0-750d-57a0-ae15-805be75955a1 | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
5ba3b75e-caa3-5774-a7d4-76d75a6b4dc9 | note | Method - Measure, Visual
b7bca8f4-ad6d-5487-a833-9a3e83c11622 | note | Frequency - Each OHLE Structure
346c97c6-ca7a-5cef-b419-68dcb6df5944 | note | Category - IP
67e98495-61aa-54fc-9daf-f8c6b2471e00 | note | Responsibility - CAT5/MRPA
595f0570-e788-5211-858f-95c770f0a87d | note | Responsible person - MRPA/CAT5 Engineer
511f4596-3510-5ba5-926a-fc6c2f706268 | note | Verifying Documents - This ITP Signed Off
1460f470-64c6-5737-a3ca-478eea26f274 | date | Date Completed:
d4bec270-3395-424d-be29-51e3384505e3 | checkpoint | 5.5 - Cantilever checked once installed.
132f5d1c-cc83-5da2-a0e4-820123472f7a | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
f79b7898-3aac-5290-a4b6-1c611c10134d | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
c5dcd14f-0172-5b5e-bf31-2fca2324fa2b | note | Method - Measure, Visual
9e5fdb56-7e02-5c1b-aca2-ea13dc0a847f | note | Frequency - Each OHLE Structure
369e66b1-0e92-52ba-a602-f1d4b73b3510 | note | Category - IP
11818f84-b158-532b-8b98-37e3e0f91d82 | note | Responsibility - CAT5/MRPA
261a2743-2d2b-5763-afc9-a340d58a7b58 | note | Responsible person - MRPA/CAT5 Engineer
d72bc56b-6bc4-5781-8917-cdbbb019b64e | note | Verifying Documents - This ITP Signed Off
1278fe6c-d376-5e1e-9a3e-80b91491dc14 | date | Date Completed:
2642b924-668c-4e6f-bcc4-fdac4723d5a2 | checkpoint | 5.6 - Base Plate Grout
9ae8e95e-24e2-584c-bbe1-794e3ef0a610 | note | Reference - IFC Drawings
3204f66a-6409-5131-888d-b0e8d3a3abc9 | note | Acceptance Criteria - Grout to be mixed as per manufacturer TDS.
4d385912-4344-5ee4-b8cb-5b5b58826676 | note | ○ Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
2f5c7923-49f5-55be-a523-ba5586de71ee | note | Method - Visual
8c766b37-ca7e-5c36-bcc4-2fe67c0323d3 | note | Frequency - Where applicable/ Each element
75170efb-536b-541b-8a32-eaa4f8a567b9 | note | Category - IP
94807e99-6d20-536b-8ca4-bf0aeb6d9bb6 | note | Responsibility - PE
e0c43532-dddf-55b8-a1c6-4dda983a8ebd | note | Responsible person - MRPA/CAT5 Engineer
a823d687-aa62-586d-a83d-cda001e67dde | note | Verifying Documents - This ITP Signed Off
0cf243e7-c6ab-518a-8ea6-69a9d7ff05c7 | date | Date Completed:
ee5832b8-8b65-4752-830f-97935eb97578 | checkpoint | 5.7 - Installation of wire supports at the correct height and stagger
adb0b4d3-caf8-5a71-bd7e-63be2141684e | note | Reference - Install as per design
cb232168-f5ae-5bcf-a598-d57884aab603 | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
cd8163dd-f59d-5c85-ae38-b9d7dfc8d207 | note | Method - Visual
4a141889-88fa-5257-83b2-740901c0037e | note | Frequency - Each OHLE BWA Structure
995c8d0b-4dfa-5fe6-8bb5-09c0dc476a4b | note | Category - IP
96d0b2bf-5698-5284-a7bb-f2ad2a989c51 | note | Responsibility - CAT5/MRPA
2753b265-3755-50c7-8ff0-e2335efa1ce5 | note | Responsible person - MRPA/CAT5 Engineer
1699ae87-3a3a-52ac-ae32-efbc8f1b123b | note | Verifying Documents - This ITP Signed Off
f6e76db0-100d-57ee-ad66-37e500123873 | date | Date Completed:
9a8a64df-3e8c-4300-b7f9-4c4b500226ee | checkpoint | 5.8 - Install to correct tension
ad66be0a-bfcd-537f-88a3-921253d0e3e6 | note | Reference - Install as per design
683ed970-4c85-541f-99f5-1b2ee1bca766 | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
553a2483-ce45-5be0-9e59-80d457bcbb4e | note | Method - Visual
102f8ca3-6aac-5ba8-8dbc-41ba8d1d2e58 | note | Frequency - Prioir termination
b123d88a-eb98-53cb-93fe-31ae1d2e4106 | note | Category - IP
1bf1b426-f9a7-5b3f-8b84-5b53fe453311 | note | Responsibility - CAT5/MRPA
6098fcd5-a754-5685-9844-7ffd647de62b | note | Responsible person - MRPA/CAT5 Engineer
15ff8ee9-8ba7-5280-88ea-84805212a5b6 | note | Verifying Documents - This ITP Signed Off
3752483f-c3f5-58e0-9b9e-4016c95f92a0 | date | Date Completed:
8e41aaf1-5d9d-48b8-a508-88daf96b8aa9 | section | 6. Post-construction Activities
a1179d2e-f678-4a2f-bfdb-f4a94be024c2 | checkpoint | 6.1 - Defects/Temporary Works
bdceabcc-6c3e-5288-b509-c6f5cd107877 | note | Reference - IFC wiring layouts, cross sections and design drawings.
bf36a478-72a2-5864-b16c-fc001552af1a | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
073e835f-8217-5311-b51a-fc11690ee0d7 | note | ○ Defect list to be provided at the end of Occo identifying planned work to rectify
6d65789e-f56a-5192-9b9e-4ba03b825af2 | note | ○ Attach Design mark up, Defect list, temporary bond register, and approved TW design
065e0182-7c97-52a3-9827-64b72af4c1c2 | note | Method - Document Review, Visual
d388c9e5-4f3c-52b8-8eae-865f322d08b1 | note | Frequency - Each OHLE Structure
7da1193a-df91-5720-9bdd-84fe58d9a4c2 | note | Category - IP
10f4ce3b-169b-5dfd-b3c6-7903252ffa58 | note | Responsibility - CAT5/MRPA
3a674f8b-3665-5d4e-ade6-35916a88cdd6 | note | Responsible person - MRPA/CAT5 Engineer
ae176c28-21c8-5dd0-9b26-f99f1204c452 | note | Verifying Documents - This ITP Signed Off
4d6171da-a109-58ad-b7b5-eb610cb785c0 | date | Date Completed:
e9c6f680-f323-4967-953d-cecce35e9948 | checkpoint | 6.2 - Relevant documentation readily available (As-built Survey)
c3d2069c-9b97-5b50-98ad-44dd8f7e75cd | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
f2e1c1a7-487d-5087-bedb-f5cf659647a6 | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
94e17c3b-1913-50e6-936e-97d7475bf11d | note | ○ As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
eaa888b5-b5ab-51b4-97f7-59739518d116 | note | Method - Document Review, Visual
05858365-a6ef-539a-a074-66338ab334db | note | Frequency - Each OHLE Structure
aed3f654-eab8-55c9-bc53-55c9eba1a842 | note | Category - IP
57183670-d866-5788-a98e-b22a203280ec | note | Responsibility - CAT5/MRPA
573f6b17-52ad-57ab-8091-c8661f17a03c | note | Responsible person - MRPA/CAT5 Engineer
158e1db5-1d0c-5cfa-946d-36eb005f40c4 | note | Verifying Documents - This ITP Signed Off
559c8225-0c27-5916-812f-9d88ee50e833 | date | Date Completed:
2bc240aa-b38b-4a32-b99f-61c12141de7e | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
61a5332b-1be3-579c-8d33-0615fda685eb | note | Reference - MTM Quality Management Plan
d85d0853-8902-51af-87f3-9c2361b523e7 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
9c0365b3-533c-52a2-9d7d-145c7c5688d2 | note | Method - Document Review
5282bdc7-51b9-5f35-8f25-d2f1e610db1c | note | Frequency - Once, prior to closure of this lot / element / Work area
caf639f8-357e-5cd0-8735-a65f3de59d20 | note | Category - HP
186189fe-342b-550d-8e0a-7f7f6af8d77c | note | Responsibility - CAT5/MRPA
5abd5571-8dfe-5375-bd71-7561b2e14697 | note | Responsible person - MRPA/CAT5 Engineer
b34fc949-5b81-5d7f-a498-525b147327c4 | note | Verifying Documents - This ITP Signed Off
f5b85ffd-9fd1-5539-beeb-40ab77a83bd9 | date | Date Completed:
04cdf893-d8dd-483e-bd1c-e997257f5e0e | signoff | AUTHORITY HOLDPOINT
22e96813-d9b9-454f-ae25-0ed5d8fe4f2d | checkpoint | Final Inspection
ed844901-527f-5e0b-a7fa-38252aa3592e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
226e1d5d-22d5-5cb3-8e71-e87bdd247bbf | textbox | Name:
1cc9891d-bb22-5e5e-b11c-4b24ae855c3f | textbox | Position:
112391af-b7d4-56a2-8959-308d4f2fafe1 | textbox | Date Completed:
3e706ac6-7196-4606-8b32-36ff62c0828e | signoff | Sign ITP
| checklist | ITP-054-CPD-Subsurface Drainage (Supply and Install) - Rev 0 | itp | ITP-054-CPD-Subsurface Drainage (Supply and Install) | a8308ae8-b213-4b0a-8084-93b1ace135c7
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
5e756c66-1426-56ad-bf7f-1753be386bc2 | note | Document Title: ITP-CIV-CPD - Subsurface Drainage (Supply and Install)
73872110-eeed-568c-904c-9ee0962d7bf2 | note | ITP Description: CPD - Subsurface Drainage (Supply and Install)
7fadb68e-8521-588f-bd62-ea9b74570bdf | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
9b621f6c-1c7a-5cf1-914d-42a5b9ddaaba | note | Discipline (e.g. CIV/STR/RAIL): CIV
67320dad-d3c2-56b5-8786-0005fbe7f61c | note | Revision Number: 0
c4bd4f24-ab79-5d8b-b974-2ef4aac0c609 | note | Revision Date: 27/07/2023
b30ab790-24ed-503a-b68b-c2c2fde9a83b | note | ITP created by: William McCuskey
ec15eb94-ec94-5b28-ac8b-9ee20565fcca | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
78b41507-92ed-5564-bfd9-55c03a69c0c5 | note | Reference - VicRoads Section 702 (May 2019)
| checkpoint | 1.2 - Non Dependent
b210e6dd-638b-545b-a55a-77e6ef489c0f | note | Reference - VicRoads Section 204 (Dec 2015)
| checkpoint | 1.3 - Non Dependent
c66b22bf-ea71-5a53-b2df-34ee787eb1ac | note | Reference - VicRoads SD1611
| checkpoint | 1.4 - Non Dependent
c648f746-be2f-5579-b820-f820befa2368 | note | Reference - VicRoads SD1051
| checkpoint | 1.5 - Non Dependent
c705426b-171e-5974-80ad-5540e80d5731 | note | Reference - VicRoads SD1631
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Drainage Pipes
b5796c7a-541f-5723-9f2d-215166b00127 | note | Reference - IFC Drawings Section 702.04
b59b964d-521a-59e4-9fba-8c40dc4e1df2 | note | Acceptance Criteria - Subsurface drainage pipes:
5bf33e40-132d-57c1-8ad1-f08f630c4473 | note | • Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe - with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
6fe38e57-e807-5ac4-bf19-21b4adc60b77 | note | • Attach: Material Approval Ref Nos
be3b896d-f3c6-50b6-a212-c6c75d13b7b2 | note | Method - Verify, Document Review
ab29a124-7cf2-5af0-80d0-ec1615c7fea7 | note | Frequency - Each Lot prior to work start
e0a2a39a-e518-5e4e-9997-9ca32b6c200e | note | Category - HP
0b05d7b5-87de-5d95-8771-0e3865fb76ca | note | Responsibility - Nominated Authority
8df53096-0a8f-5576-aa62-3a60a7305861 | note | Verifying Documents - Conqa HP Release
f558844e-4de4-541c-8734-37d18c21271b | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Granular Filter Material
6779b815-7d29-5755-a92e-c96f3784728c | note | Reference - IFC Drawings Section 702.05 Table 702.051
dad02bcd-59a4-5e88-9b37-ce100f6c57e0 | note | Acceptance Criteria - Granular filter material:
5b88e3b0-5c50-5ae3-b27e-fd7b1eda594e | note | • Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
d593be4c-2e48-56b9-b702-4c0f5b45efb6 | note | • Attach: Material Approval Ref Nos
1e2016a8-85e4-5f7f-b748-5d420fd01a6f | note | Method - Verify, Document Review
8ea1b184-d0d4-558a-ba31-80173c07d358 | note | Frequency - Each Lot prior to work start
5dedc4f4-3633-57d2-82a0-a00432f60603 | note | Category - HP
dcbf3c06-0aac-5896-b0b3-88a90a5b4c89 | note | Responsibility - Nominated Authority
a371b996-a5f2-5d58-ba51-d11d5b68e904 | note | Verifying Documents - Conqa HP Release
4e16d30d-4ab9-503d-bf2a-6cf8608c36ff | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - No Fines Concrete
46b59dd1-10ec-512e-92e6-4cb8142855b5 | note | Reference - IFC Drawings Section 702.05
984fa64e-635d-5c1e-84cb-956ca8cddcca | note | Acceptance Criteria - No Fines Concrete:
bea200ad-41ea-5d1c-90d3-def04ad1f310 | note | • Shall comply with 702.05 (e)
0c1d1023-3442-588c-a5f0-946ec6e83b67 | note | • Attach: Material Approval Ref Nos
20db4eed-3d07-5d5d-8c37-80cf5fa0f39d | note | Method - Verify, Document Review
be96de49-b1af-56fa-bbfa-c34228cdf7f9 | note | Frequency - Each Lot prior to work start
00d61619-bd12-59d1-b1c9-e6d44cbbd858 | note | Category - HP
1e334a40-5ed7-5d87-be37-1f4f44ee2d3c | note | Responsibility - Nominated Authority
75ef8396-3798-58e8-83c5-81a00e143355 | note | Verifying Documents - Conqa HP Release
1e2f92c6-a897-5c63-82cd-9cb3a010e5af | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Geotextile Filter
6975b730-6514-574a-847f-c07265b61c08 | note | Reference - IFC Drawings Section 702.06 Table 702.061
e1dab299-9d25-5c3b-9514-a9ea410354c8 | note | Acceptance Criteria - Geotextiles:
b81b089c-1d18-5e17-ae36-3af162afbc38 | note | • Shall comply with 702.06
c41b3eb6-c018-519b-993b-9b3b9b8dc359 | note | • Attach: Material Approval Ref Nos
8bfb0f32-0505-568a-8690-62fbb2046471 | note | Method - Verify, Document Review
966e471d-df32-5d4e-a83c-1122b2ef1022 | note | Frequency - Each Lot prior to work start
f4824265-b9a1-5d20-abc7-ff9b44526a5d | note | Category - HP
36750d5c-b5df-567e-8413-7aac74f38d75 | note | Responsibility - Nominated Authority
9a3434a4-ee45-5b34-8ade-c75e4a715500 | note | Verifying Documents - Conqa HP Release
12efcc18-34f6-50c9-92bb-9596ceabd1e9 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
5c6b4fc4-4d62-5dea-8df9-da2c691fc597 | note | Reference - IFC Drawings SD-1051 SD-1611 SD-1631
5b389cc5-140b-5d97-8ce9-856b0e6907a6 | note | Acceptance Criteria - Subsurface drain pits: shall be Type S1 (as per SD 1611).
1c2f7ac6-ec6b-5b2a-a3b0-55b4ccaf9fbe | note | • Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
fa557a01-170a-594d-864d-bc00b8cf478b | note | • Flushout risers: As per SD 1631
6019bf60-d1f3-56ee-ae61-85c769e9ff96 | note | • Attach: Material Approval Ref Nos
4a6d949e-972c-53d7-b435-d4411b183324 | note | Method - Verify, Document Review
52c285b4-ecd9-5fa1-9884-df41f4a40ce2 | note | Frequency - Each Lot prior to work start
867df89c-512e-5d3d-9d34-60e57b063665 | note | Category - HP
c0a20f3f-6a6d-5c95-a5e0-931049ee4b54 | note | Responsibility - Nominated Authority
8d1bb047-85db-5bf9-a3e4-5af829ba59ee | note | Verifying Documents - Conqa HP Release
d3e2311a-4415-51ac-a4b4-d0a0bec6641d | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documentations
| checkpoint | 3.1 - Check for correct documentation
2fd21618-982d-5eb3-a309-4854d0b4bb90 | note | Reference - IFC Drawings
934924aa-1824-59e4-b2c8-1fd9bb5f90d7 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
27b65153-7293-5189-bc5f-a3fe349e9804 | note | – using the correct and complete set of drawings
9cf63416-89b3-513c-a9dd-baca03312615 | note | – all drawings are the latest revision
13f4817e-20fa-5c01-a9b8-136cc4e8437f | note | Method - Visual inspection
a6d9adf8-d0e4-55a9-a441-8f39c43fb9c1 | note | Frequency - Prior to commencing any activity
7d80d9f9-abf4-531d-aba3-a5f7c124ffbe | note | Category - WP
ae54de58-32a0-5554-a4ae-f1059be70202 | note | Responsibility - SE/Site Supervisor
9a6da605-2cf7-5923-b8ad-1107cee1c93e | note | Verifying Documents - This ITP Signed-off
25148f33-f8c7-55da-9d6a-2ec3343457ce | textbox | Date Completed:
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
d888693a-661e-56b1-951e-7c66537b9931 | note | Reference - IFC Drawings Section 702.03
83035189-e0e3-5b71-a892-4596c5fae006 | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
153f7e79-367a-545a-aeb1-6b4e8d58c87c | note | Method - Visual inspection
bc1869bf-402c-56c5-97be-a667477b3970 | note | Frequency - Each Lot
14e3dbda-a02f-5154-93fa-4c52479cfa5f | note | Category - IP
3110ac88-9619-5fcc-b1e7-92121e2eeb2e | note | Responsibility - SE/Site Supervisor Surveyor
41f41eaf-e3f7-5812-9782-8e0a505634e1 | note | Verifying Documents - This ITP Signed-off
6c5d890b-5b97-51e6-a663-db355449eed3 | textbox | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Trench Excavation
a70f40e5-c83c-5092-af9b-687336db85c2 | note | Reference - Section 702.08
c1972e48-14a2-5347-a70a-f8efa7b71d62 | note | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
1f8c4e72-ae3e-51a8-a24e-f09f72ce93d4 | note | • There shall be no departures from the grade of the base of the trench that would allow ponding of water.
a7594d55-9149-536c-a372-5c39d05e9ce0 | note | • Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
3e680e9d-54ed-594a-a285-c9578648464e | note | • The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
bf24e9e5-2f4f-55d4-b834-378b9bf2d314 | note | Method - Visual Inspection
71f94bb1-ab95-5798-ae7a-760e6fa2e3ba | note | Frequency - Each lot
113f10ca-be7c-5ba9-b72c-cfaf36aa5b2a | note | Category - HP
ac4291d0-514c-5c55-87b2-1a340f68746b | note | Responsibility - SE, NA (Nominated Authority)
e2cd5145-e123-546c-a217-d743c0be25cb | note | Verifying Documents - Conqa HP Release
50b66fa8-2394-5832-8011-24d090010baa | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Placement of bedding
b705b011-c4c7-566a-bfe3-88f4f70d48b9 | note | Reference - Section 702.09 (c)
640a8ee6-9ed2-5220-9725-d461f324b59c | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
89c4c992-717e-58f9-9a9a-9ecf7fa7e5da | note | • Attach bedding material delivery dockets
67f5b9d7-ac2f-58c0-9806-f5bf16ca17de | note | Method - Visual inspection
a2cf62e6-3529-55a4-af59-43bdfb7c4c20 | note | Frequency - Each lot
bec0046c-b2d9-5e19-8c71-eae115a3eca8 | note | Category - IP
1a2791c7-5180-5028-9e80-9fa5a3f5366d | note | Responsibility - SE/Site Supervisor
bef3cdfb-41fa-5a3d-be76-d2b0fc53db1a | note | Verifying Documents - This ITP Signed-off
dde6bb55-f4fb-568a-bbbb-bfa81a73a63b | textbox | Date Completed:
| checkpoint | 5.3 - Pipe and Geotextile Installation (if required)
033d5c9d-d831-5a78-91a9-3ec4ce74268c | note | Reference - Section 702.03, Section 702.09
fd373f6e-6746-54bc-8906-673a59283596 | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
aea4b5bd-5941-5867-bf1f-3fa36768f8cd | note | Attach Suburface pipe and geotextile delievery dockets (if applicable)
f28fbfe0-cd9b-5c39-932a-606cc405e543 | note | Method - Visual inspection
e5663bc4-61f3-50a7-bc21-d7c6ca51513c | note | Frequency - Each lot
7519a3c7-9cab-5059-9d88-547e9951e09d | note | Category - IP
6e3ad5b5-4d75-5c5f-b14d-a3ab4ff75622 | note | Responsibility - SE/Site Supervisor
4b15a022-df71-5e5c-b7fa-d355262c2eac | note | Verifying Documents - This ITP Signed-off
89544609-bb53-5633-b9d9-818a589bf8f8 | textbox | Date Completed:
| checkpoint | 5.4 - Backfill Installation (Granular Filter Material)
a63ccf80-1165-5629-a90a-756a1962ceb8 | note | Reference - Section 702.09 (g)
2d981ce4-a03b-5246-89b5-12dc73f81e94 | note | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
8de61911-e80c-5d78-940a-d87043b46a70 | note | • The method of compaction shall be in accordance with the procedures and reviewed by the NA.
78e06ee3-78bf-54c0-9f96-8288788fbc29 | note | • Attach Backfill Delivery Dockets
653253c0-fb8d-532b-ae11-e5d2f8a49dac | note | Method - Visual
ebfbd0ef-a68c-5eb7-964c-8eb30e4689fa | note | Frequency - Each lot
69191e75-fad4-5cf8-9472-af01739c487d | note | Category - HP*
1c932b2d-a6b7-5b1b-bb56-f22ac93114d1 | note | Responsibility - SE, NA
86c676dd-4534-5203-8b6f-6149d9264544 | note | Verifying Documents - This ITP Signed-off
423a13d0-ca67-5727-9392-ebc99af2295f | textbox | Date Completed:
| checkpoint | 5.5 - Backfill Installation (No Fines)
74acda89-7936-5a8c-8fc4-23c756fc8add | note | Reference - Section 702.09 (g)
f6085be0-f146-54a6-af4e-54417cc92429 | note | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
cea87425-1c26-544f-b900-673131d0b962 | note | • Attach Backfill Delivery Dockets
2359108a-063c-5d17-924c-fd29799c5c52 | note | Method - Visual
83759285-96ac-586c-85e2-4abd1b459878 | note | Frequency - Each lot
4c972846-af50-55df-99e3-c358c9d69b0c | note | Category - HP*
c3624f7e-616a-590d-93c0-573c4789f896 | note | Responsibility - SE, NA
cc7dc6ec-a691-5c59-a28b-dfb78094c16a | note | Verifying Documents - This ITP Signed-off
3b319340-47c3-5043-a165-aeacec418bed | textbox | Date Completed:
| checkpoint | 5.6 - Install Pits and Flushouts
eb52c2d6-8ac5-5746-a0ec-2ee48969ea31 | note | Reference - Section 702.10
6e148972-a161-5be8-814a-77252d24f099 | note | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run.
f746ce8b-a7dc-5da9-9d4d-d63708011f3d | note | • Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
5e596683-69fc-5fe1-b6ff-7e90f625dac9 | note | • Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
c6075ac1-ca70-51e1-9431-63fedb0ec56e | note | • Attach Pit and Flushout Delivery Dockets
8047eb38-f5d9-5478-bf18-0b8b6094aee6 | note | Method - Visual
c540bead-2874-56c5-af4d-a235c932ca24 | note | Frequency - Each lot
2ecc4d8d-6ca7-55df-afa6-01d776bbc20d | note | Category - WP
cc5351f2-b788-5e44-a7cf-e2cb752ebde8 | note | Responsibility - SE/Site Supervisor
a7517441-2bc1-5a16-9109-1600758d17d5 | note | Verifying Documents - This ITP Signed-off
de5d8165-62c3-5c35-af53-ad38fdb95981 | textbox | Date Completed:
| checkpoint | 5.7 - Marker Points
e047c081-f1dd-5f9e-8f7c-bb7934ed2ab3 | note | Reference - Section 702.11
3d0cbebe-6d20-56d0-9acd-93af052b2166 | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
d575821b-c29b-53dc-a2c1-a687e0205b76 | note | • Attach Marker Post Delivery Dockets
502e7323-e708-5d20-b9ae-acbe1d09cef1 | note | Method - Visual
187abe52-5a65-5c5f-b084-69762e84edf5 | note | Frequency - Each outlet
70f4068d-661a-50d0-82a5-74c852be709f | note | Category - IP
3329a9cf-c213-5e6a-b4b4-f27156365c76 | note | Responsibility - SE/Site Supervisor
cbac4167-5bfb-51c6-8557-2d520df43e35 | note | Verifying Documents - This ITP Signed-off
715a474e-b1eb-5b53-be00-39cbf91a97f6 | textbox | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As Built Information
85c26b24-727b-50ee-8de6-3c6d8317d8c7 | note | Reference - Section 702.03
a786e809-50ea-55be-ad4c-319cc1c94348 | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
1f33915d-3d9a-5387-8ab4-5dd9ae08bff2 | note | • Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
206579b8-6554-50d6-aa36-0d1531fac5b8 | note | • Attach Survey Conformance Report
7a7793bb-6400-5b5f-86a9-fdcb46dd7e8d | note | Method - Document Review
f76e61d9-05f6-5af7-9e6b-ed385a2adf17 | note | Frequency - Each lot
db6f68f1-2e48-580a-8ddf-c81c515fee94 | note | Category - IP
789dc594-c779-5589-ac3e-dc8f2b636c75 | note | Responsibility - Surveyor, SE/PE/SPE
3df17ede-d5e5-5ebd-a7d2-b728465e1124 | note | Verifying Documents - This ITP Signed-off
31cbdff4-8b28-5c4a-9967-4249661eb4e5 | textbox | Date Completed:
| checkpoint | 6.2 - Flushing
7fac7770-1824-5d53-9f6e-f6d169c0802b | note | Reference - Section 702.09 (h)
89c741b8-2d9f-562b-9c3f-b3a545855ff0 | note | Acceptance Criteria - Flushing test shall be witnessed by the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
f77cf290-b9fc-57b0-ac44-d76ac248f0c6 | note | • Attach Flushing Tests Records
ad869ed9-8b52-58fb-b5e4-d5a42ad95a5f | note | Method - Document Review
b6510b1b-92d9-56dd-a004-f8aebec2c06e | note | Frequency - Each lot
51b61388-5855-5f13-b92b-1688d13232e2 | note | Category - HP
c190dbdc-f065-58d9-bb39-b3590d45b102 | note | Responsibility - SE, NA
9b4da817-4475-5425-b940-40e09253dbb8 | note | Verifying Documents - Conqa HP Release
76cf8b12-05be-5cb8-8bc4-9f96688e2b8f | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Inspection of Subsurface Drainage - CCTV
50f09ae0-1760-54f4-ab9e-3833c970dbbd | note | Reference - Section 702.09 (i)
15e991a3-07af-5e10-b6aa-9c6c6230535d | note | Acceptance Criteria - All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
7cef991c-1b5a-5b41-ad05-5bcfeb64979d | note | • Attach CCTV Inspection Record
72847521-4d11-5acd-aaf1-e224600441f8 | note | Method - Document Review
23ca1eb0-1c8f-5155-bf22-43cbc5a3cda8 | note | Frequency - Each lot
d3998dc4-6389-5d01-b944-4c263846f273 | note | Category - HP
ff23ec9e-9d32-5c58-83f4-7afd16bada64 | note | Responsibility - SE, NA
ccf4b25b-7b8e-55b0-a858-6e14888220fd | note | Verifying Documents - Conqa HP Release
b4011a66-7aa9-5513-ae59-84f65eebad8f | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
35fa8fb7-10d6-5a7c-9a8a-30f5f24da95a | note | Reference - MRPA Quality Management Plan
8f6ffcdd-295d-5834-bc64-bc8fc44b9856 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
e47a01ba-0c65-5d72-bd15-72c8a055a60b | note | Method - Document Review
5ad6364a-8853-5592-a982-cd4ccb6ee130 | note | Frequency - Once, prior to closure of this lot / element / Work area
40ecc591-f9fb-59a4-8dec-eb011bc621a3 | note | Category - HP*
1b33d991-0b38-5b86-b47e-e8932df24bc2 | note | Responsibility - SE/PE/SPE
45a4651e-2ddc-5cbb-8c88-1da11aa260cb | note | Verifying Documents - This ITP Signed-off
39cee6ae-fb96-55d5-93d4-5dd3033dbd3b | textbox | Date Completed:
| checkpoint | Final Inspection
1906eb47-6ddd-522d-8aac-61c67e65097e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
edd5b7dd-7068-53aa-9fa5-c796b85993d3 | textbox | Name:
288f74df-e006-5904-846f-15d1971cee2b | textbox | Position:
1942fac1-7484-583c-bf81-e53d5cdf2c73 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) - Rev 0 | itp | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) | ee98f55a-f499-409c-a25c-ac3c6a9d17f9
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
d574efd4-ae65-577c-8f36-b253727c2e98 | note | Document Title: ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install)
0e346702-12a7-5fff-b8e1-8446c0b3b1c5 | note | ITP Description: Conduit & Pits - Rail (Supply and Install)
d215155f-81ff-52e8-b169-f142c50ba78a | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
3939086a-5226-54e2-95bb-ce728f55cc4f | note | Discipline (e.g. CIV/STR/RAIL): CIV
3ce57144-ec29-57e5-ad0d-b28455374f10 | note | Revision Number: 0
15de89f3-76c2-5184-87af-10d6a7b23638 | note | Revision Date: 4/08/2023
db21fc11-ca47-5c1f-8eb3-963ae41db11b | note | ITP created by: Andrew Carlini
17e349c7-4521-52a7-a0cf-ec6a4974126e | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
700c534b-d66c-5720-b337-23bd8e85c2ee | note | Reference - IFC Drawings L1-CHE-STD-043 (VRIOGS 012.2.1) L1-CHE-SPE-070 Australian Standards MRPA Standards
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Conduits
adda807a-ac2c-5131-95df-260c5add916c | note | Reference - HV Conduit: AS 2053, HV Conduit (boring): AS 4130, Comms Conduit: AS/ACIF S008:2006, LV Conduit: AS/NZS 3000 - 2000. L1-CHE-STD-043, L1-CHE-SPE-070
641e28d3-a4a6-5fa1-b3de-129b42980852 | note | Acceptance Criteria - LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
2ad198a9-daf3-57a3-b6e7-94848db131f2 | note | ○ LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
fd55a62f-8c2b-5cc6-9f61-e59c79bf4925 | note | ○ Inspect materials upon delivery and attached delivery dockets.
a414aed1-ee27-5902-8fe3-c955e274455d | note | Method - Visual, Document Review
2dc4ce3b-6496-5123-a6cf-528a1feafce2 | note | Frequency - Each Material Type, Each Delivery
b1e6392e-0a69-5f54-911d-d68df12eec36 | note | Category - IP
f9fbfead-bc3e-50b2-8248-b531e1569ffb | note | Responsibility - SE/PE
ac4286c5-11cb-5c11-97dc-a3e2ff9c8035 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
8ae9671f-ecfb-52d6-936e-6c6629e382f1 | textbox | Date Completed:
| checkpoint | 2.2 - Pits and Pit Lids
5a2b71e2-aeb4-5842-836d-e5c22f3db003 | note | Reference - IFC Drawings VRIOGS 012.2.1 Section 6.15-16, VRIOGS 012.2.1 Section 6.9, VRIOGS 012.2.1 Cl.6.7 (c) L1-CHE-SPE-070 Cl.10 AS1289
8e0c8c84-808e-521d-b47b-20baa8abb5d8 | note | Acceptance Criteria - Pits:
2ba34af4-eae6-5e7f-8564-fc1360054418 | note | ○ Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
00d89f1f-ff61-5d12-a523-dcf5c908bee1 | note | ○ Pits 900x900mm or greater, multipart pits lids to be used.
397b2ab5-52ac-52d0-a02a-99f1091d4004 | note | Pit Lids:
6a7cb99d-b793-5063-8d62-b9fa3a16bbc5 | note | ○ Pit Covers shall comply with AS3996-2006
5dfe8848-8465-5782-bf1b-9a17f5bd312e | note | ○ Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
01ea0439-4a0c-5f4e-90de-51a1d95c6d9d | note | ○ LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
228eb118-fe5b-5679-ab30-dfb17a518fa1 | note | ○ Inspect materials upon delivery and attached delivery dockets.
3e1cdd0f-f6ba-51bf-b195-5730b4e1b780 | note | Method - Visual, Document Review
22003fba-5c13-5142-8fd2-e2d56322f224 | note | Frequency - Each Material Type, Each Delivery
0ea1de73-44ad-5115-bf3c-e1463d998309 | note | Category - IP
f9b48deb-5708-593b-841e-471a76a1a888 | note | Responsibility - SE/PE
9e49cac3-6eb9-52d6-9933-8c04b786a9c2 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
23d54b23-4ef6-50e0-a002-63795f327098 | textbox | Date Completed:
| checkpoint | 2.3 - Warning/Marker Tape
81322cb4-fb9b-566d-a1a5-23b2cc751a0d | note | Reference - IFC Drawings AS/NZ 2648.1 TS-SP-013 L1-CHE-STD-043 6.4
177bcef4-9d12-5df8-ac98-952330e76d8c | note | Acceptance Criteria - Warning/Marker Tape:
e7a554ba-76fa-58b6-af2d-9fb5ceff60af | note | Above LV:
068f767f-0fc1-5e8d-9e52-154ca2294b5d | note | ○ 150mm minimum wide orange coloured PVC
e5423953-b56c-538e-8cda-30cc2f27b69b | note | ○ ‘DANGER RAILWAY SIGNALLING CONDUITS’
62c87c4d-caea-5e44-97a6-e2cc8696b950 | note | Above Comms:
1aaa33f0-1ddb-50c8-ba9e-0cd1dc43a833 | note | ○ 75mm minimum wide white coloured PVC
90bb46ae-0a50-537b-b900-481bf0a0e297 | note | ○ ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
e18c2a58-1b69-5405-bc5b-e02400443ea6 | note | Above HV:
667b80b6-2b57-5bae-8d69-43d1a4a5f5d1 | note | ○ 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
a13d5dad-11ed-5423-8d90-523db7729ffb | note | ○ Inspect materials upon delivery and attached delivery dockets.
8246514c-c6c3-5dc9-a6c1-1247a06e69f5 | note | Method - Visual, Document Review
92e2f927-3749-52f8-b351-3e46f711ed51 | note | Frequency - Each Material Type, Each Delivery
0b44d18b-032e-534c-991e-73089137eccf | note | Category - IP
51b3c154-84a3-5557-98b4-1b5c2ef8185c | note | Responsibility - SE/PE
e3b7bf58-1770-5e93-ac66-73fe45488051 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
dbc7ad92-4ef6-5dbf-9fa7-b0bda4d41cb2 | textbox | Date Completed:
| checkpoint | 2.4 - Protection Barriers
f3168ab3-1588-585c-b331-cca86a14873a | note | Reference - IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
088bdbf5-25fe-5f73-b445-3f9d03c21013 | note | Acceptance Criteria - Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
95c43c6d-d061-53ea-99f6-97138cc812bd | note | ○ Inspect materials upon delivery and attached delivery dockets.
f3b9df6e-5228-501c-8e4c-5e52f7cf1cc3 | note | Method - Visual, Document Review
3f526150-ac73-5840-b772-2a10433adc3e | note | Frequency - Each Material Type, Each Delivery
5800ab40-e139-503c-8eba-7ce86b1ecae3 | note | Category - IP
bbbfbaba-abc0-5063-b81f-f96d843d495d | note | Responsibility - SE/PE
f0db990e-5907-5adb-8395-916e0f2fbeaf | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
17516c59-4539-58b5-81f8-3c16e72e22b4 | textbox | Date Completed:
| checkpoint | 2.5 - Backfill Material (stabilised sand)
a4095bee-1b38-5faa-8d65-3bab95828070 | note | Reference - IFC Drawings, L1-CHE-STD-043 Section 2 Table 1
3d88d363-a112-5329-8d68-c20519686407 | note | Acceptance Criteria - Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
d40f9be1-1cb4-5efb-a5ed-b39e07a2410e | note | ○ Inspect backfill material.
8990036b-a781-5223-b5f4-36e607b82d94 | note | ○ Attached delivery dockets (if applicable).
288a02cd-f330-5062-b692-0088c2786dd6 | note | Method - Visual, Document Review
d567bd72-ac03-55ad-b563-90de126f2fc6 | note | Frequency - Each Material Type, Each Delivery
436df35b-a50b-51d8-8944-0e4b9ea1660a | note | Category - IP
4d8576a0-3d27-59a6-a8c6-23192ebee22a | note | Responsibility - SE/PE
ad07a356-62cf-5142-9db0-40e1be211b10 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
62919031-e79c-5d11-a056-7a28a0a50896 | textbox | Date Completed:
| checkpoint | 2.6 - Bedding Sand
5d2d8ad6-0283-5e6b-bf72-fe94f760e0c7 | note | Reference - IFC Drawings AS2758.1
2b1dd650-d6e2-5e6a-829d-96eb9cdea7f8 | note | Acceptance Criteria - Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
1dcd8f0f-d9be-5339-88cc-8457094006dc | note | Method - Visual, Document Review
dad097f9-26a7-5c45-a254-30c811dab74e | note | Frequency - Each Material Type, Each Delivery
facdc3db-7b75-55a7-9fc1-c0ab9f341c92 | note | Category - IP
fb3f4156-cb40-5483-bc4d-729c3bde7653 | note | Responsibility - SE/PE
2f252b55-8443-5185-99dd-9d1bbab1fb23 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
8cdae23a-759f-5eec-b077-d5be044d8a65 | textbox | Date Completed:
| checkpoint | 2.7 - Draw Wires
0f61742f-2d8a-5ff6-acd3-13d9feadf38c | note | Reference - TS-SP-013 AS 4142
1732fa4e-2f8d-5120-8527-23dad8a2018f | note | Acceptance Criteria - 6 mm diameter polypropylene blue/yellow
d11d5b4a-e8a8-5727-b13c-141fbf112420 | note | Method - Document Review
9985d47c-af0a-5ac1-aa94-ab13f61536e2 | note | Frequency - Each Material Type, Each Delivery
a2b44d4a-b56d-555e-9e76-f3b32e1010f2 | note | Category - IP
309035bd-6091-5495-9a26-2a9988b9a287 | note | Responsibility - SE/PE
e4fd4868-6b84-5fb5-b632-bafbe11e82c9 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
ae06fbdd-2580-5ce9-8ab9-4edf2a99c372 | textbox | Date Completed:
| checkpoint | 2.8 - Concrete Mix - Trench
f09cb20e-9e0c-5d09-a71c-8f616caac142 | note | Reference - L1-CHE-STD-043
c1758b37-f8f5-5579-bd5b-3f266fd70f48 | note | Acceptance Criteria - N/A
352fc044-65f9-52c7-bd44-5e54040a3f4a | note | Method - N/A
b2e9fd7a-7a4d-5a01-8f62-32826ba23586 | note | Frequency - N/A
249e00d4-2d5c-56b9-8518-8d9ee519afda | note | Category - N/A
3939c5ea-1736-5823-9346-d7f9693172b9 | note | Responsibility - N/A
120ece0a-ecf5-5d6a-ba78-1f28512e149c | note | Verifying Documents - N/A
cdd8c11f-2684-52b7-a3fe-8b8abbab728e | textbox | Date Completed:
| section | 3. Prelimnaries - Procedures & Documentation
| checkpoint | 3.1 - Services
10592b48-0888-51f1-a807-1bfed85b1143 | note | Reference - Services CAD file
f04260c8-f036-5644-8316-05a0bcaa61d6 | note | Acceptance Criteria - All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
1f91c915-cc1a-5226-932b-d2b31a10364d | note | ○ Survey to mark out existing services.
cbfb6c8b-a507-596c-bdc3-be7e784474f2 | note | Method - Visual
d4decad2-ca0d-54ea-a5f9-86b56725c039 | note | Frequency - Prior to commencement of works
474aa9e9-30a6-5af3-aeb9-2e1eb12b9107 | note | Category - IP
7160db47-3e2d-560c-a8e8-de0d193dd936 | note | Responsibility - SE/Site Supervisor
cc293ac5-9031-5254-bc62-36d93bce4e40 | note | Verifying Documents - This ITP
6c4dff34-fc15-5b53-a688-5c461423c08c | textbox | Date Completed:
| checkpoint | 3.2 - CSR Works Procedure
3f780eb8-3bad-5bff-ac91-94761f1afc29 | note | Reference - WAP_CPD_254
18db5f7f-3efe-5bd7-9713-fa52735f82f0 | note | Acceptance Criteria - WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
e145eee5-a827-5eac-8d1b-61c81743a18e | note | Method - Document Review
ef997b0c-9663-5265-957f-1855c48a13bf | note | Frequency - Prior to commencement of works
8861eb41-a5b3-5bb1-aba8-2305181d43e7 | note | Category - HP*
cf353dbf-e1f6-53c8-a293-5356b683923e | note | Responsibility - SE/Site Supervisor
08937bdd-eb45-50aa-a3e8-d9f9a6c94a81 | note | Verifying Documents - This ITP
7bdef42d-8851-595d-a36b-edeaff63d926 | textbox | Date Completed:
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set-out
280f7842-2107-557a-9099-3c8f7688f5b8 | note | Reference - IFC Drawings
1ab1d630-2ff1-5297-8965-6c018fbeddc5 | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level).
97420f9c-eac0-53e4-b078-4a02e0c551fc | note | Method - Measure, Visual
c8fba9b8-1004-5af3-b25f-76131d46159d | note | Frequency - Each element
c9c95446-196f-5396-b79e-38461fe7afe8 | note | Category - IP
af43c15d-4ce3-583d-b328-9e8388647c93 | note | Responsibility - Surveyor, SE/Site Supervisor
d5ac35ad-87e6-5192-bb2b-62a74cb22731 | note | Verifying Documents - This ITP
1aa5020d-3efb-5ccf-afef-dd10f3a19f24 | textbox | Date Completed:
| checkpoint | 4.2 - IFC Drawings
c4f6c505-b815-57d1-8a80-e185aa0b0754 | note | Reference - IFC Drawings
d1263639-8a8c-56d9-a54b-302fa6a40597 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
24835c94-aa10-5192-9caf-4cc4aef3770b | note | Method - Document Review
9d29eb8d-5e17-5760-8d8b-b0da9ebf1610 | note | Frequency - Prior to commencement of works and at regualr intervals
a4dfc6d9-6b14-513d-bcb8-fcdcf2889d45 | note | Category - IP
f461ecaf-c155-50a9-bdcd-d6cac30a22c0 | note | Responsibility - SE/Site Supervisor
c8ed7922-a6ff-5152-918d-6c33c3e4de27 | note | Verifying Documents - This ITP
6456aa3a-ec76-57e5-9ca8-54757e1e8a10 | textbox | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Trench Excavation
eafe2cec-edd8-5851-baaa-65984714dd1f | note | Reference - IFC Drawings L1-CHE-SPE-070 7.3 Table 2 L1-CHE-STD-043 L1-CHE-STD-070 7.1c
49da775b-5a2c-54da-93e9-f5fe9e473888 | note | Acceptance Criteria - Trench profile and depth as per IFC drawings.
26b6a76b-ce11-5280-b227-4172134cb1ef | note | ○ Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
a0d4c894-6777-5133-90c5-d2d13161acb9 | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
e6acfa55-b7ec-5408-97b6-938162db8efc | note | ○ The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
1d4e5e63-53be-5e06-b29c-c427696e1c85 | note | Method - Measure, Visual
70443a86-d9ca-5db1-ac8f-c88e8fa21e34 | note | Frequency - Each lot
02f91683-dcea-588f-a18a-c693fd031530 | note | Category - IP
6f553e96-fdbc-521e-b453-7fb0e7bc4919 | note | Responsibility - SE/Site Supervisor
f426a83e-7956-5c83-b990-7b15e1cb3998 | note | Verifying Documents - This ITP
707266e4-30d8-59ab-b6c1-0ed87694b3a2 | textbox | Date Completed:
| checkpoint | 5.2 - Trench Stability
7af6e120-bf32-5a2d-86dd-dc524cc3e33b | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings MRPA Standards
3ed4fb2b-7dea-578f-aac2-e86d84841634 | note | Acceptance Criteria - Trench stability check:
64119b42-f251-5901-8c1e-72c25702b036 | note | – Shoring,
973cb3e1-5f45-5c93-916f-e22f04f6ac1a | note | – benching
2f45c57b-32e4-5bee-96a7-07d6afc08643 | note | – geotech signoff
5e019d02-7665-5a1e-ab68-68fd6cab0276 | note | ○ Attached Geotech Report
0cad6040-798f-589e-8838-1a402002776b | note | Method - Visual, Document Review
ccbe28d7-2884-55ee-b5ea-ce2b92010380 | note | Frequency - Each lot
ab0fbaf2-e89a-5d5b-9995-dbe823b51196 | note | Category - IP
6b7d5873-8b4b-549b-8aff-95670b773cf9 | note | Responsibility - SE/Site Supervisor
be4bd7df-2cf8-5fea-9d77-247259a15f60 | note | Verifying Documents - This ITP
c46005aa-52c8-5052-9409-e076baebd2a6 | textbox | Date Completed:
| checkpoint | 5.3 - Placement of Bedding Sand for Conduits
58215e33-3c32-5291-a656-975b486d8139 | note | Reference - IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070
3303d0ca-532c-5f38-96dc-1bd669541f42 | note | Acceptance Criteria - 100mm of bedding sand/crusher dust to be places at the base of trench.
de3b34a7-0c7d-56fb-bfb2-773517287700 | note | Method - Measure, Visual
c21dab29-fb23-559d-83b1-3c497b8f81e0 | note | Frequency - Each lot
e8249845-e3c1-5c6e-947b-0762469a6e22 | note | Category - IP
3f65e296-0bfa-5261-8679-f5d44764cd29 | note | Responsibility - SE/Site Supervisor
2a3cb03e-ea87-5798-87ff-19b15aa016c1 | note | Verifying Documents - This ITP
8e674989-908a-5d29-8bc4-baeb9831bbb5 | textbox | Date Completed:
| checkpoint | 5.4 - Conduit Placement & Configuration
12f01c77-9dd5-5b2b-8d0a-e9e5c47b8b60 | note | Reference - IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077
7d5bb706-effe-5738-bee8-3a6d399bfa5d | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
6eaf6216-fbbb-53f2-99af-b88244e2f5df | note | Min Cover
c30331cc-26fd-509c-a1cb-70fbe221c371 | note | – HV: 1000mm
694951ad-c1a0-5f74-a6f8-28db36e53f24 | note | – VicTrack: 650mm
645642a8-f0f8-5b63-a991-8a3918f01464 | note | – Signalling: 800mm
75429d5d-c8fc-5a75-a370-13540c127f0e | note | – LV: 800mm
c344a6bc-47ef-5f98-9639-d2f3805d6122 | note | – Electrolysis: 800mm
c34c4e1a-d20f-5054-a38e-8c3db6f2503e | note | – SCADA: 800mm
d3f76d18-d174-5a20-9bd6-0df0538854ba | note | – MTM Comms: 600mm
28d37a54-6f77-5481-9d47-acec5f1492a3 | note | – 800mm below water coarses (stab sand encasement)
52a236c1-6022-537f-a81d-d965c6ad98fe | note | – 1200mm Under VicRoads Roads & top of Rail
354b1e05-9ecc-593f-bf73-5b0fdcb367c3 | note | – 900mm below council roads
e6076fdb-e220-567f-ac03-1abd806be704 | note | Method - Measure, Visual
11370d73-1af8-5b8b-9510-8f6c0a0eb185 | note | Frequency - Each lot
38681cc7-f1b1-5a70-966f-1030c61c16b2 | note | Category - IP
f9daada6-2b74-5cf8-b562-5ed416a9eec3 | note | Responsibility - SE/Site Supervisor
8f377df5-6e8b-5008-b2aa-03b258c0063f | note | Verifying Documents - This ITP
cdce26f5-31aa-58e9-8ca1-c3b2b6b302a9 | textbox | Date Completed:
| checkpoint | 5.5 - Separation of Services
074698bf-7bca-54dd-82c2-5f8e735081a0 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077 IFC Drawings
9c630784-ff45-5859-8d9d-a661d1df465f | note | Acceptance Criteria - Separation of services
7a350678-4383-5844-8498-27ea4448964d | note | – HV: Min. seperation distance between HV conduits at least 50mm
0a5c0bbf-4844-5247-8205-c25f8d57b397 | note | – VicTrack: fiber 300mm from HV
f155bdc6-dc87-5ccf-a29a-b3d739a9e47d | note | – Utility: 300mm to utilities
b91f18e7-77a4-56df-8037-16cf4f034a8f | note | – Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
8bb70b9a-71cd-5411-93b2-382c4a3d5eef | note | Method - Measure, Visual
c9ea7a7e-5892-59a2-888b-bd389eec7989 | note | Frequency - Each lot
c3716912-4c25-56cf-8258-16e8b1b504aa | note | Category - IP
a0a4d3c9-eb34-5104-be42-b0236146890d | note | Responsibility - SE/Site Supervisor
898f7551-f6b5-5ef6-878d-f2ace6eadce4 | note | Verifying Documents - This ITP
fc57cdbe-62ee-56c8-b0b9-eee946127b24 | textbox | Date Completed:
| checkpoint | 5.6 - Joints
3db65550-8b92-5c38-8cdf-068f02046324 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
db7abc2e-2f5c-5463-96a4-b8265ad52c6c | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends.
2fa5f6eb-df66-5d14-8eca-bbcf04875a26 | note | ○ Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
076de0a0-d42e-54de-a842-2147d22fed78 | note | ○ The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
3b3ff1a3-0c07-598a-b338-3fbd09fb722c | note | ○ Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
3a6dcc2a-de49-503b-a855-dcc587b4fe32 | note | Method - Visual
f74c4c14-e29f-5621-ab09-6165e3d001f9 | note | Frequency - Each Joint in each trench
c670e2d4-9e7e-583e-aecd-35b462a9c783 | note | Category - IP
96a5a622-7fba-586f-bed7-c20a37f53cfc | note | Responsibility - SE/Site Supervisor
b7d64d44-2120-5744-aeac-ea1693042f60 | note | Verifying Documents - This ITP
420e5be8-0f38-56f2-9ded-8d22f9a43850 | textbox | Date Completed:
| checkpoint | 5.7 - Conduit Inspection
58a8c196-2d73-5ff6-8911-4c142cd69418 | note | Reference - L1-CHE-STD-070 16
3c6837d8-c79c-58ff-b652-f1489a88348f | note | Acceptance Criteria - Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
39c9a83d-05dd-5c80-b502-cee0596e7fec | note | Method - Visual
0cf29286-ad39-513d-bfbc-905329a628cc | note | Frequency - Each lot
29b22df1-8f70-5c70-9bc5-540085ce9469 | note | Category - HP*
aaa8ec4f-5d95-54af-b904-cc67a8374a43 | note | Responsibility - SE/PE MTM / VicTrack Rep.
1e896922-7d20-532f-9ad0-447705ead382 | note | Verifying Documents - This Itp
32f728f1-699a-5828-9135-fa7d7cd37e8d | textbox | Date Completed:
| checkpoint | 5.8 - Bedding Sand Installation
ef9e6720-6fc3-5332-8862-41f1e4895814 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 CL13.1 IFC Drawings
9076c4f9-845e-5ead-8887-fabc81fe88b2 | note | Acceptance Criteria - Bedding sand/crusher dust extends 50mm past edge of conduits.
c4d2992f-115d-507b-a1e4-c9014f805f25 | note | ○ Bedding sand/crusher dust extends 100mm above conduits.
cf0df211-2f73-524f-8667-b7c1a8073e55 | note | ○ Attach Delivery Dockets
84a51892-c323-5cef-83e8-f056e128ef9c | note | Method - Visual
bca1b862-bf5a-5dbe-887b-46ccbf70b24c | note | Frequency - Each lot
63804100-df35-5244-a25a-06f3df7bd53f | note | Category - IP
1f41e38e-038f-5569-baab-6f720ca0eefe | note | Responsibility - SE/Site Supervisor
cf561779-1a21-52c5-8417-80c8c4c667ed | note | Verifying Documents - This ITP
44f53d78-5ea3-5d15-aea2-87a864af9a6a | textbox | Date Completed:
| checkpoint | 5.9 - Marker Tape
cd41623d-2523-588e-a4fe-b90c9213011f | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-SPE-070 Cl10.3.3
5cd38453-ca09-59bf-9fc7-cf1b21117ac9 | note | Acceptance Criteria - Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers.
09f494b4-a20b-587b-913f-36540c08526d | note | ○ Tape to be one continuous length.
8a285ce1-fbea-55f1-8ce1-b200855b781c | note | ○ VicTrack to inspect the Marker Tape placement..
85b211cd-0ef6-5449-861c-500aed2dbce0 | note | Method - Visual
7c78e7fb-eed2-5280-92af-8d6bd1797b57 | note | Frequency - Each lot
e4a8e826-4f5b-52c3-bce3-7dabf858dd95 | note | Category - HP*
4a9ef731-ac03-55f5-bac9-a0ddf2f39f8c | note | Responsibility - SE/PE, MTM / VicTrack Rep
5120c505-f768-5844-ade4-ff7531728474 | note | Verifying Documents - This ITP
e17ee366-ce0f-54bb-b6be-117cab6ddf43 | textbox | Date Completed:
| checkpoint | 5.10 - Backfill Installation for Conduits
309229fb-1770-511d-9d02-d1e4fe30c714 | note | Reference - IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
fa39071b-07aa-52bf-b872-154f9b0bb4e3 | note | Acceptance Criteria - Backfill per trench profile
9b6e5712-8d68-52c5-bf7f-bcf65a7558b4 | note | – 150mm layers of 3% stabe sand
38885896-f690-5a06-9198-ae87018dbc2f | note | – conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
4535510d-1ad1-5c6c-b1f4-7169bdfac958 | note | ○ The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
9948f318-7ebe-5092-a08b-07690e522eae | note | ○ Trenches under road pavement - backfill to be same material as the road formation material.
42a9ea04-373b-5aa6-baba-d9257c33676c | note | ○ Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
ac8e80a6-1d6a-52ca-9e4d-aa1046b29db5 | note | ○ When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
21f0ae9e-1b44-5347-9a58-fefbd261fda3 | note | ○ VicTrack to be notified and witness the first layer of backfilling.
2650814c-a180-5ae0-98cf-4dcec2d79619 | note | ○ Attached Delivery Dockets
85bb2de2-e23a-5781-90b9-94df0ac25668 | note | Method - Visual
d8812673-1803-5f52-9e15-c1020001d7b2 | note | Frequency - Each lot
4c6f81a3-3039-513c-9343-143e79c91960 | note | Category - HP*
321d3578-d78c-5754-ad69-9c98e2d2ca52 | note | Responsibility - SE/PE, MTM / VicTrack Rep
5e158dca-a361-5545-b04f-7585263be18a | note | Verifying Documents - This ITP
29c721d9-d35d-5437-beb3-99c340ab58c0 | textbox | Date Completed:
| checkpoint | 5.11 - Signalling Pits, LV Pits, Electrolysis Pits, SCADA Pits, MTM Comms Pits
e5a8adc3-c03b-5f2b-850a-8251b9fb8bd8 | note | Reference - L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
0b84102d-2880-518e-b673-f514e1509d83 | note | Acceptance Criteria - intervals no greater than 400m (electrolysis 190m)
9755bc0f-988a-5c61-a508-492bdba1cca4 | note | – 3m from rail
702ad092-ff4b-536e-b232-1d65d55e51b1 | note | – Access Roads, Class D lids
b1f33314-a101-5636-bfb2-41de0398d1fc | note | – Footpaths and non traffiacl areas, Class C Lids
7ac5c2a1-c0e1-570c-b3e8-ef1b5d83c0ce | note | Method - Visual, Measure
2b4e2c64-4b51-5257-9a47-5985ff87efde | note | Frequency - Each Pit
99417a6c-a826-58e1-a193-055512ba4037 | note | Category - IP
0f25147b-6957-57da-ac57-fee24b77d4c4 | note | Responsibility - SE/Site Supervisor
927b5fb9-22ac-5527-b140-9a67c343157e | note | Verifying Documents - This ITP
c07001d1-40a3-5781-879a-d452edfd60be | textbox | Date Completed:
| checkpoint | 5.12 - Additional Considerations
f6aaaa5f-309a-5d3f-8e6d-709ff5b0eb9c | note | Reference - IFC Drawings
af47d0a8-79c1-5689-bf5b-cebba95fb597 | note | Acceptance Criteria - Access tracks to pits
fd5888b6-4114-56a9-ac01-4e044623674c | note | ○ Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
917c4c9a-fe1d-555d-99da-01cc3636a20e | note | ○ Hand rail & retaining wall installed as required
abd696f1-43b3-575d-96f5-cb201c2d6737 | note | Method - Visual
7eba5134-a139-5c4e-9c49-28714126a6e5 | note | Frequency - Each Pit
a932b828-c904-549e-9c6f-859a9cf0e852 | note | Category - IP
e426eb48-4028-5a26-b0bd-482b701c223a | note | Responsibility - SE/Site Supervisor
21e28740-15c5-5e53-9ded-77f3b811d434 | note | Verifying Documents - This ITP
4a89f8d3-e9f0-5084-8cc6-04cf1d51c348 | textbox | Date Completed:
| checkpoint | 5.13 - Bedding for Pit Installation
e6c529e8-c553-550f-ae53-317a76a425f8 | note | Reference - L1-CHE-STD-070 Cl 7.21.u L1-CHE-STD-043
38a14659-045d-5455-b1f2-0ee310c02bd4 | note | Acceptance Criteria - 150mm of crushed rock under pit extending 500mm past the pit
2d84c477-ede4-5b53-84d1-dd088d15bdd6 | note | ○ Drainage arrangements shall be provided at the base of each pit.
83c6375c-11f3-56ce-865f-e931179c37ad | note | ○ Attach Delivery Dockets
02a0ea38-aeeb-5fb6-a7bf-17d1888eed82 | note | Method - Visual, Measure
76f70624-88ba-56f7-b201-8eabd84f7d94 | note | Frequency - Each Pit
871556c0-dce9-5950-af1d-97d8153e5acb | note | Category - IP
d6a1118d-e36f-5f8a-a9cd-0a0d10906f14 | note | Responsibility - SE/Site Supervisor
1f3e0a81-00ca-5b32-b7ea-fa173f58ce63 | note | Verifying Documents - This ITP
45687674-a8c0-5d6e-abc3-ab731c923cea | textbox | Date Completed:
| checkpoint | 5.14 - Pit Orientation
4095909a-a01d-5d75-a411-0dd9c1bc4143 | note | Reference - IFC Drawings
0e800dc5-6ccd-5dc8-88ec-296957475509 | note | Acceptance Criteria - Pit to be parallel to track and parallel to conduit route.
6e6295a5-cabc-5df2-be14-7b01d6156613 | note | Method - Visual
255d3569-1447-5776-a29f-0732352aa9f6 | note | Frequency - Each Pit
1a32b1d5-bca4-5760-9b73-79907ee0cbd7 | note | Category - IP
26af59a4-1fe8-5c72-8c4d-648a7d21482d | note | Responsibility - SE/Site Supervisor
f1521a62-99c2-5c0a-8379-ec62b37d2cb8 | note | Verifying Documents - This ITP
fbd14b9f-58bf-5693-b72a-69c91f163126 | textbox | Date Completed:
| checkpoint | 5.15 - Pit Installation
767baceb-d5f4-5c84-a7a6-665fa6353fb9 | note | Reference - IFC Drawings
2fea99fa-570d-528d-946f-14963f7808bf | note | Acceptance Criteria - Pit installed to design specifications. Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
40b6d2b6-1dbd-53da-b432-a5e65a433505 | note | Method - Visual
7aae198c-7f3b-5043-aa17-894d9e8089dd | note | Frequency - Each Pit
743825cb-bd78-5b9a-ae5e-44e2e4dd6bd2 | note | Category - IP
716681d5-38eb-5699-ab54-cf3804c90a91 | note | Responsibility - SE/Site Supervisor
bc2acf09-1d65-511e-a4dd-b85110ab4ec1 | note | Verifying Documents - This ITP
088089ab-ac40-5a91-a9e5-fc96f9cdca90 | textbox | Date Completed:
| checkpoint | 5.16 - Conduit Entry onto Pits
ea4af1eb-01c7-5c1d-84c0-146b23bf77e2 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
b717a97f-4229-59ac-9e88-ffed48553ec5 | note | Acceptance Criteria - Lowest conduit 100mm from the pit chamber floor.
bc8d57c4-b2c7-5ade-8b50-b9aeaa31eb0d | note | Method - Visual, Measure
f612fe6c-ad8f-5ef8-bf42-ad08e7166ca2 | note | Frequency - Each Pit
1e3126be-4798-5253-9bdb-1dad82a58be8 | note | Category - IP
c18330d4-0a04-5086-8df4-f0cad540a016 | note | Responsibility - SE/Site Supervisor
679d6c1e-6767-5c35-9f6e-1e12dbeed974 | note | Verifying Documents - This ITP
b75ba114-400d-5cb1-8f10-0411b6e7b1a5 | textbox | Date Completed:
| checkpoint | 5.17 - Tracer Wire
fa991a31-8af9-5351-b2f6-342b564d3ce8 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
f279d04f-fc97-56d2-8494-e282a6339468 | note | Acceptance Criteria - Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off. If tracer wire broken needs to Crimped
bb4729e0-a0d3-5038-b9fb-7311e37177d1 | note | Method - Visual
3e1b70cc-450b-51fb-9b5c-02c0938f86b6 | note | Frequency - Each VicTrack Pit
3dd1a31a-4882-56c4-aabf-7f76f5c16cc3 | note | Category - HP*
767cf503-623c-5c2c-afa8-ad41d9c37731 | note | Responsibility - SE/PE, MTM / Vic Track Rep
5ba3acab-e38c-5549-8894-3aab6f5e6d36 | note | Verifying Documents - This ITP
84567fe8-f43e-5462-9925-059c6a7d4200 | textbox | Date Completed:
| checkpoint | 5.18 - Spigots and Bell Mouths
6c9ba6b0-40bd-5f4f-9863-8c9b8550b09c | note | Reference - L1-CHE-SPE-070_9.3.4
c40254c0-8726-5f68-a59a-6a8c86a26f1c | note | Acceptance Criteria - All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
047871a9-496d-5bf2-832c-a0c3d3e0a5c1 | note | ○ HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
5631a1f9-24a1-575d-9e07-f8ef4e417384 | note | Method - Visual, Measure
0812f447-08c4-582f-b275-445e2cd3e71a | note | Frequency - Each Pit
ad7a28c6-d64d-5e5a-9b63-36cd1adca824 | note | Category - IP
7565d39b-fdde-588a-984f-8e229a176803 | note | Responsibility - SE/Site Supervisor
1b804370-3a92-553c-a790-a0a3a3cec32d | note | Verifying Documents - This ITP
49211a3f-4b6a-53e3-90b9-623874e0daaf | textbox | Date Completed:
| checkpoint | 5.19 - Draw Ropes
fbdca9ef-7c41-59ab-af02-b06b4fe182bc | note | Reference - VRIOGS 012.2.1
0096efee-b8b9-5474-ba62-bce62a249561 | note | Acceptance Criteria - The draw wire shall be continuous for the complete length of the conduit run.
d3afb3d3-05f9-59d0-8c6e-99bf73ae7490 | note | ○ The draw wire shall have a minimum of 2 metres of slack within every pit.
24a72e33-0a42-5e4e-a125-1dbdb5b4c2fe | note | Method - Visual
647079a6-7a33-59a6-a9cd-4caca6f63731 | note | Frequency - Each Pit
3ddb0e2e-d185-55e6-9383-ea9aa5c3d23f | note | Category - IP
5f059c2f-024f-5473-94bb-0ce5ae8f7da1 | note | Responsibility - SE/Site Supervisor
10bfb173-f04f-5f5b-bd1b-75751d2e2f22 | note | Verifying Documents - This ITP
d883517e-2efc-5fc6-8d0a-6346372b79b1 | textbox | Date Completed:
| checkpoint | 5.20 - Backfill and Compaction Testing (if applicable) arouns Pits
d3dc11e4-fb0f-5b39-9c60-b3e43b4f8cb6 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
c10eecfb-8f64-5872-9009-67f96676270f | note | Acceptance Criteria - Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
c0b42b7d-43d3-5d6e-96bc-41979ac8f9fb | note | ○ Sand within sand pits to be compacted in layers no more than 250mm layers
e3fd918a-8917-5ba0-aca0-6f2626e53be0 | note | ○ Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
6c5da9c4-0f32-5938-a3aa-ebc3f9b44301 | note | ○ Attach Test Report
27af2d9b-f078-5ade-9066-a2610c3732d1 | note | Method - Document Review, Visual
99fcb32d-c3a2-5564-bb26-405bc5fbb413 | note | Frequency - Each Pit
d3bfb12e-96c7-5f3d-8383-ae37b607bc9a | note | Category - IP
31d880ab-318e-5f93-8324-5948b6ead153 | note | Responsibility - SE/Site Supervisor
00678977-c135-5e41-87c4-4127b3f3d9ef | note | Verifying Documents - This ITP
461944d6-dbb3-5917-aaab-04cfe24b14a5 | textbox | Date Completed:
| checkpoint | 5.21 - Spare Conduits
7198f4db-5b7b-570b-a1f1-3fb56104cb02 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
f9e07ac0-4542-55b4-a8a4-b34267630601 | note | Acceptance Criteria - Spare conduits to be sealed and to be included on survey report.
17ac863b-f4e8-5e2a-938c-ee715ea69d9b | note | Method - Visual
ab8ff0b7-e019-5192-a5bd-0d3837f0da91 | note | Frequency - Each Pit
e9383298-dd2f-5452-86e3-2fbf54e2011b | note | Category - IP
d38579e2-5c7a-5ec4-901f-9374d988bdbc | note | Responsibility - SE/Site Supervisor
70ab70a9-793d-5329-91b7-0fe8684388f0 | note | Verifying Documents - This ITP
84d3e9cf-635e-5c8b-863b-25b610b60306 | textbox | Date Completed:
| checkpoint | 5.22 - Pit Lables
8b2469d8-609e-5f00-b0fa-5088ab86608b | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
5b15e083-257f-50fa-b595-758ec9ab2eb2 | note | Acceptance Criteria - Pit labels Brass Label (30mm x 150mm)
ff2c4770-d874-5461-83bc-fdce2cc6e4c4 | note | – HV: DANGER - Railway High Voltage
ce7bdc95-7fd3-53b3-8d54-0bc8db360a0a | note | – VicTrack: Victrack Comms
65763f92-69f7-58bc-9fec-38b76ccfeb60 | note | – Signalling: Rail Sign Comms
5e2edce3-a88d-53d0-bf62-01d6910270ab | note | – LV Pits: Electrical
06ec0057-9e77-55c6-8d5d-d82c652a1f33 | note | – Electrolysis: Electrolysis
98363d14-5df3-5bbb-80c3-5789a0de2289 | note | – SCADA: Rail Sign Comms
199a783b-d4a3-55b2-9163-c50c0162fe51 | note | – MTM Comms: Rail Sign Comms
38085be2-d7e4-57fa-9e1c-60c4dfa68df6 | note | Method - Visual
aff0a11d-f6e2-5892-bd78-6c8ffb652972 | note | Frequency - Each Pit Lid
823c27cc-93e7-5eb5-a615-bd098be7eecc | note | Category - IP
19b42533-ee3b-5017-9b8b-cdb9de7e191d | note | Responsibility - SE/Site Supervisor
00882f4f-1703-51e3-a2e1-33c47b43665f | note | Verifying Documents - This ITP
6f66be85-0084-5e78-9ee8-76d26f5b1a98 | textbox | Date Completed:
| checkpoint | 5.23 - Pit Numbers
57ef8401-2bef-58e4-95f8-e546a9032d3a | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
2a33ed09-48aa-54e5-a160-57cbc29eb625 | note | Acceptance Criteria - Pit Number Brass Label (30mm x 150mm)
63690212-9fad-5d38-87c1-f4707d2a35ef | note | – HV (22kVV Feeders): ###HV
c0f2a534-82a8-598e-a35d-88814d5eea8e | note | – DC (HV Feeders for OHLE): ###DC
218ea3fd-3708-5225-a2c4-291ff3d93fe3 | note | – VicTrack: ###C
538569ad-7b93-5cf6-9279-e3dd5c06d950 | note | – MTM Comms: ###M
cbe824e2-7099-53dd-9dd1-92c9c050defc | note | – Signalling LV: ###SL
07be26a5-329a-5bb8-a4cb-3bda1612cdcd | note | – Signalling HV (2.2 or 3.3kv): ###SH
528dee8d-a4e1-5a24-bc20-5316099c9679 | note | – LV Pits: ###L
8a24c374-843e-522b-a204-313fa5bf95bf | note | – Electrolysis: ###E
0b5c6c83-c7ac-5b6f-9f64-fc18611bad71 | note | – SCADA: ###MS
6a31ff1a-cf87-5e1c-a51e-c0562438c5e1 | note | Method - Visual
6aaa054c-563f-56c4-b8a9-027445a94742 | note | Frequency - Each Pit Lid
25ac117d-b851-5d0f-b96d-b5662fa889b4 | note | Category - IP
33a8480d-b169-5976-bda0-46a55412dc09 | note | Responsibility - SE/Site Supervisor
38099c11-dc29-5088-8f09-f33d88d5da5a | note | Verifying Documents - This ITP
8f8a93b9-56f1-58f3-96fc-09154eeedf1e | textbox | Date Completed:
| checkpoint | 5.24 - Cable Route Markers
1c316756-406a-576d-a4ef-fa15cdd852d7 | note | Reference - L1-CHE-SPE-070_13.2, STD_E0169 and STD_E0170, AS 4799, STD G0003 and STD G0004
ef3cc1bc-cfc0-502a-aa8a-8fd4f7b2dd32 | note | Acceptance Criteria - Cable Route Markers
3a02f06b-1422-5cb0-b0ee-db8042e2badd | note | – points entering & leaving the rail corridor
edca459c-117b-5ca5-b23b-ab70b9e441ce | note | – no greater than 100m spacing
f80540f6-b852-581e-b636-eff54eb60409 | note | – Change of direction (more than 5 degrees)
06fa92c2-025a-5e50-ae37-facacc42e258 | note | – White posts with marker plates for conduit runs
b7d09e33-fda0-56e7-8e49-584662f57331 | note | Method - Visual
38b3656d-8e2f-515e-9d01-58337029eb14 | note | Frequency - Per Cable Route
00bd0f77-8335-5221-8ab7-3403377ab11c | note | Category - IP
ad2815d8-db44-5225-be92-184b82028378 | note | Responsibility - SE/Site Supervisor
2f94395e-c145-5fe8-9ed3-6ffa6f8e3aa7 | note | Verifying Documents - This ITP
415afb5e-0fac-5ed3-8e8e-7f988ea60088 | textbox | Date Completed:
| checkpoint | 5.25 - Cable Pulling
e0740c34-d166-58e8-ab4c-b0c4292a3158 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
f12da0cf-59a4-5134-be7b-54a48bf69d93 | note | Acceptance Criteria - Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
8732c8b5-fa53-53f3-84ec-8cebed44ab64 | note | Method - Visual
87c219c2-6112-5985-b033-ebbb52dc7630 | note | Frequency - Per Cable
b4e85ddd-b085-5915-a90d-c9df148007cf | note | Category - HP*
1119c78b-fbae-5ca4-8ea9-6ced38748868 | note | Responsibility - PE, MTM/VicTrack Rep
f45a34d3-f75f-51c9-80d7-43f4ed019697 | note | Verifying Documents - This ITP
d3827269-fe2d-5dd5-b2c4-d29cfff946ae | textbox | Date Completed:
| checkpoint | 5.26 - Cable Labels
bd18e5a6-f38f-57c6-b402-7c25863f6a36 | note | Reference - L1-CHE-SPE-070 Section 13.3
2c09ddcd-9084-55bb-8bb9-e99937d4a8d9 | note | Acceptance Criteria - All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
93e2e7e8-682d-5fc1-807b-b8c8c6f1184e | note | ○ The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
4314af9b-6159-53e7-ba7b-590e8072d39c | note | Method - Visual
bef2445f-605f-5913-8bc5-f48db783ec5a | note | Frequency - Per Cable
897034a6-3750-518e-821b-b8226f3951a4 | note | Category - HP*
e107edca-571b-5f46-97b9-c7b74793cfc9 | note | Responsibility - PE, MTM/VicTrack Rep
f200d832-f329-53f8-80b4-a720f6da7a12 | note | Verifying Documents - This ITP
1ef0e06a-a75f-5be5-b2ad-859e4607142a | textbox | Date Completed:
| checkpoint | 5.27 - Cable Joints
27358873-bc05-5137-9d81-7f04d3d273b6 | note | Reference - L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
6d3afe82-ce73-579e-be9b-84f22854d7c6 | note | Acceptance Criteria - Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
61587ece-4611-5c14-8ed7-cd33e7c769f2 | note | Method - Visual
00810287-ae5f-501f-b19e-3e849ac3f6d1 | note | Frequency - Per Joint / Termination
f7280edd-2119-5d72-8337-8ad007fecd77 | note | Category - HP*
e4488101-8738-5daa-b94e-9702177a8668 | note | Responsibility - PE, MTM/VicTrack Rep
e93aa4f1-4c92-58b9-af3e-41828e2bc68f | note | Verifying Documents - This ITP
16e2445a-77e6-5156-ac41-9e9a80ebbe98 | textbox | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
5010c438-01ea-5916-a091-e7cff0c23133 | note | Reference - IFC Drawings L1-CHE-SPE-070 Section 13.1
8f70877c-a2e2-5ad1-9479-baf43f33fb89 | note | Acceptance Criteria - Survey report to include but not limited to:
07581f97-bc09-5cf6-8009-85695454ac8f | note | – Cable joint locations.
5e6eee6c-b335-52b3-a148-59e98b4330a1 | note | – Cable pit locations (Corners)
574d1ccf-2992-563f-977c-dc2797c1fe26 | note | – Pit dimensions & pit lid type
41802733-43a4-5950-b8ce-e0d3684c58c9 | note | – Under line crossings
8bbbf653-2927-5476-93f6-0325a8fbcc49 | note | – Under road crossings
17b441e3-f462-5a00-8401-af5258c8841a | note | – Changes of direction
c86c2ca3-576c-55ea-be4a-6af3ce98ec5e | note | – Spare Conduits
5fb45484-975b-59bb-a1a0-6bcac21ccd1a | note | – Conduits labelled as per trench profile
69d1f8ec-011f-5c2a-b3da-b073813b89c9 | note | – every 10m
fda627e0-f0c9-5a6a-93e0-b20391b251b9 | note | – Other significant points of the cable route
d6d03b8e-a0ed-55cf-9c52-8a13506b53ad | note | ○ Attached Survey Report
20e9cb1c-b5f9-5b0c-888e-a4ebe4eb4140 | note | Method - Document Review
ff1245a2-1acb-52ae-8081-6dea999155a1 | note | Frequency - Each Lot
8ef73a25-2dee-5a63-805a-4564f330f04b | note | Category - IP
1932aaf6-2a6c-5f47-9d93-38b7b4ba8a8a | note | Responsibility - SE/PE
c7a7d7f1-517c-585b-88d0-567837b51bbc | note | Verifying Documents - This ITP
b6b38845-7056-54b6-9209-c99adc186c46 | textbox | Date Completed:
| checkpoint | 6.2 - Handover Check
1d488719-bd0f-5139-b906-c79d2b181adf | note | Reference - IFC Drawings
09883a1f-dfb8-5107-b3e5-a64b0140d14d | note | Acceptance Criteria - Handover check completed for Testing and Commisioning.
a81d3e37-c1a1-535e-ba67-3189a2355801 | note | ○ Attach MTM/Vic Track Check Sheet (Signed-off)
e4ba4984-868f-5a65-83e4-1f84bb96d5bd | note | Method - Document Review
5e2ca7fe-cd7e-5584-8708-b112b132c65a | note | Frequency - Each Lot
dd429740-1468-5cdf-ad56-629ba69a00f1 | note | Category - HP*
4a4b687b-0975-5e4c-b6d0-e33ea794463e | note | Responsibility - PE, MTM/VicTrack Rep
6ccd5f93-d08c-598a-9cd1-44a869b7c514 | note | Verifying Documents - This ITP
5a9b9141-e1e4-582e-9ac3-80d4a3cb71b6 | textbox | Date Completed:
| checkpoint | 6.3 - Testing and Commissioning
af019a27-52af-5329-85fd-6e4b55746cd9 | note | Reference - IFC Drawings
de0abc0e-f493-561a-a05b-faa3f82092f9 | note | Acceptance Criteria - Testing and Comminsiong to be completed
af79657f-efb8-5799-8224-c99300cab46d | note | ○ Attach Testing and Comminsiong Report
c41cc4e9-0c9d-5898-ac6a-3296182059a2 | note | Method - Document Review
0997c5c0-19b3-5fa2-999d-53754efd1875 | note | Frequency - Each Lot
cab6c9b5-d8df-5c42-90a1-3057d19def65 | note | Category - HP*
73783d45-9e70-5d68-adaa-68467df20161 | note | Responsibility - PE, MTM/VicTrack Rep
4b591755-52d2-5db2-8e4f-eb54b233c200 | note | Verifying Documents - This ITP
eefa444b-c58e-5a09-a6f4-5713e806bd9a | textbox | Date Completed:
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
f5319cb6-11f7-5b30-ab23-af85159a1eb2 | note | Reference - MRPA Quality Management Plan
3c4084dc-0e77-515f-a2f0-5e4e4f76efc6 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
1ce62661-6684-58f1-99ff-d42b77acd1a0 | note | Method - Document Review
28db623d-fe29-5557-aa70-2855e4f3c3a0 | note | Frequency - Once, prior to closure of this lot / element / Work area
e25f0eaf-e438-5072-9525-39ebecab4401 | note | Category - HP*
a54ae390-f890-536b-8023-ebe7c9ba4a1f | note | Responsibility - SE/PE/SPE
3cd77f36-2b38-573b-8121-83de76430ec7 | note | Verifying Documents - This ITP
27213cda-753a-5f6e-9846-bf2c68ba8972 | textbox | Date Completed:
| checkpoint | Final Inspection
ac07e7f9-467b-5be0-9d99-69a508a34d63 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
691b314f-2aa8-5cab-af7e-908f31fc9297 | textbox | Name:
745b76df-e074-5503-bb42-33bff019e066 | textbox | Position:
362b811d-0e4f-5d48-9a08-842ed50ade40 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | itp | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction | b6ddc7f6-b6bd-404a-a002-1afc2d27a009
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
ef2320af-26dc-5cdb-8440-e1e8c78c3b3c | note | Document Title: ITP-CIV-CPD Unbound Flexible Pavement
2cbeac5b-2b48-5450-8ea9-c52c6d8b1210 | note | ITP Description: Unbound Flexible Pavement
afdd6abf-7f1e-597f-a368-ed0ab3ce8453 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
3b6e9a75-fea6-52fc-806f-54e714466ffb | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
7875f11f-5110-5baf-857b-b5ef577d07a6 | note | Revision Number: 0
2038d4b2-271f-5dc3-9790-e406677c4285 | note | Revision Date: 14/08/2023
63cb63d5-a56c-508c-a594-2fc0447af96c | note | ITP created by: Ethan Caruana-Smith
35a8ba9b-bfeb-5080-ad7c-924698de66e3 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
9255c4c4-eae7-5f64-92e9-4b5440837f47 | note | Reference - IFC Drawings
| checkpoint | 1.2
abc6407d-b876-57e2-bb82-867378991163 | note | Reference - VicRoads Section 173 (10/9/2008)
| checkpoint | 1.3
929e635c-bb1a-5fb4-9ee0-0f45b42d8276 | note | Reference - VicRoads Section 304 (13/8/13)
| checkpoint | 1.4
3b425cbc-612c-5694-8139-63d59b27156d | note | Reference - VicRoads Section 801 (19/07/18)
| checkpoint | 1.5
dd274434-1e79-59a4-973a-e498e860c203 | note | Reference - VicRoads Section 812 (13/07/16)
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Crushed Rock Mix Design
cb7270e0-3687-537c-8e0b-c2089f472990 | note | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
74f060ed-0c21-5058-aab6-21142e27edc3 | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
1e8b38d9-00d5-5fc6-b622-5623d2e8145f | textbox | Enter: Teambinder Material Approval number
6421c17c-5f15-5ac8-9493-043e99e8de75 | note | Method - Document Review
9423e754-7887-5b0d-8b91-d9f7677e2e19 | note | Frequency - Material conformance as per Table 812.121
8c9bea69-1e3e-5e8a-840a-65b9ebf6d012 | note | Category - HP
4c9a7e25-f2f2-5c2b-a001-0c81d51b9c31 | note | Responsibility - NA
7719a719-dde4-50bc-99ae-3731de8b907c | note | Verifying Documents - TeamBinder Material Approval Number
971649c9-92d1-53a7-a2b4-19c122ec4da1 | textbox | Date Completed:
| section | 3. Preliminaries-Documentation
| checkpoint | 3.1 - Subgrade Preparation
64302fc0-0c83-5f0b-95ef-02bfc2562a1c | note | Reference - 304.04
a5dc12f6-8494-503a-9d6c-071b45eacdc3 | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
6cc7dfda-a294-530e-8a3a-d9fffd21c03f | note | Reference: Subgrade Preparation/Type fill Lot Number:
ce02167f-bbbf-5702-bd74-694ca167ae60 | note | Method - Document Review
91b67b0f-8c05-56e1-a25c-75b88bf22d44 | note | Frequency - Each Lot
fddca177-850a-52ed-9fe4-12e7fb7e6910 | note | Category - HP*
9fbd03f2-9838-53b5-a895-97caf6f82257 | note | Responsibility - PE
e242e0d6-b395-5eef-bbaa-e4f5d4d6fb46 | note | Verifying Documents - Underlying layer Lot number
9b8f20d9-215e-5ed5-b438-99239b0c5d57 | textbox | Date Completed:
| checkpoint | 3.2 - Select Scale
3fde8bc7-22bd-5946-a6aa-ef71e7133ce8 | note | Reference - Project Requirement Specifications IFC Drawings
d86a0587-ab72-5981-93db-b14ab9f556e0 | note | Acceptance Criteria - Specify site specific scale:
8c782be8-d468-5003-be22-aa573e784814 | textbox | Enter: Site Specific Scale (A, B or C)
1641f9e6-e798-5ffe-809e-1ca2a87987f8 | note | Method - Document Review
b577eba2-ad0e-51ef-b8bb-b08055150d0f | note | Frequency - Prior to Commencement Each lot
5a32cc8f-41e1-5a94-8fbe-9bda50302ff0 | note | Category - HP*
08f9b94e-282b-5ee6-95da-9553d8c25671 | note | Responsibility - PE
d625fedd-7b73-5b0f-bf0c-3ef8b85b6088 | note | Verifying Documents - Sign ITP
30200f34-0a82-5dd1-be6a-20af53b1c63b | textbox | Date Completed:
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-out and Lot size
ed8f00ef-e837-5f41-b1ab-fc26f3daa444 | note | Reference - IFC Drawings Section 304.06
8f8c696f-79dd-5b2f-b1a2-5c7295a51b83 | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
b31d0dd0-a009-5fe1-99a0-8ef3115b7a87 | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
37ffdf15-a490-5bfd-bcb7-3d307bd041a0 | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
2b744394-5f69-524e-a441-f64e2ab007b0 | note | Method - Survey, Document Review, Measure
d45237eb-ad3d-567c-99f8-39409e602e41 | note | Frequency - Each lot
4c4dbb3a-e436-5edf-be56-ea23d178efa4 | note | Category - IP
ceeaae3e-1daa-506e-8e92-aef482aed839 | note | Responsibility - Surveyor, SE
63a9f3cb-0c9d-52c9-8cb2-6d5286b14270 | note | Verifying Documents - Sign ITP
36fc3025-54a7-57a8-9415-41c21f87e568 | textbox | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Crushed Rock Delivery Dockets
12718882-db02-5606-a571-0666b70984cf | note | Reference - 304.04
c6fd7c0e-2dab-5ae3-a795-02d2e6ae82dc | note | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
b6149cc5-d08d-5ed4-8bf7-969dfe54af95 | note | ATTACH: Delivery Docket(s)
5adf6d2b-a0c9-5aba-ae31-64f268429cab | note | Method - Document Review
40b60401-c4f3-5e1c-87af-9e948b3b65af | note | Frequency - Each Lot
6847a6a1-3e62-5027-bb94-059d50afb645 | note | Category - IP
9cd4855e-c5f1-5cd4-bc12-4ed167abcd16 | note | Responsibility - SE
8796dfd3-112d-5e6a-9efa-f462e56c164b | note | Verifying Documents - Attached Docket, Sign ITP
cf1cf749-a11c-5cdb-a47b-a39c5dddd61d | textbox | Date Completed:
| checkpoint | 5.2 - Placement of Material
bcb1ba30-363f-5857-bd1d-a1ecd0c586e9 | note | Reference - Section 304.03, Section 304.06, Section 304.08
2c66ba9a-a9d3-5c80-be73-0a397ae01705 | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
7f395a4f-604f-5a76-9403-c5d8998abd12 | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
7c0b8a25-01f3-5dd3-b72e-022a807503d0 | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
72266e1e-1033-583f-bcf4-5818a317c007 | note | ○ At no location shall water pond on the surface of any pavement layer.
3a035549-0e3c-5170-9f6e-cb3327aa9a1e | note | Method - Visual and Measure
1c6fb702-1fe2-5ac8-8a5e-40e5def1affa | note | Frequency - Each lot
432f659d-933b-588e-8ee4-900cbbe02782 | note | Category - IP
c4fbee85-77e1-5034-a521-f2cd7c1340ef | note | Responsibility - SE/Site Supervisor
636045f5-15fe-57e0-8cfa-7cdecc87e65e | note | Verifying Documents - Sign ITP
bbae402b-e9d6-530e-b742-8cefe5ed130c | textbox | Date Completed:
| checkpoint | 5.3 - Construction - Jointing
8f728c6d-963b-5e34-8f97-2aca6616e75e | note | Reference - Section 304.07
acf792a6-fd49-5145-bb5b-59a2490daf52 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
7f65d51f-78ba-528a-a922-a374d0a8cdf2 | note | (a)material shall be spread in such a manner as to minimize the number of joints;
6792e001-5f31-54f7-8f6a-d08697f60c72 | note | (b)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
a655c747-815d-5a27-8f85-09528ababcc2 | note | (c)transverse joints shall be offset from one layer to the next by not less than 2 m;
89d2f63d-2602-524c-a9a7-a83e7a1bf470 | note | (d)longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
a2208e64-d1e8-5345-94f2-ba9119ba8221 | note | (e)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
d27a486e-bf12-51d3-83d9-9b9df3cfd012 | note | Method - Visual and Measure
49977efe-6632-52e0-944c-7f4a03d22663 | note | Frequency - Each lot
11a3c6cd-23ec-5827-9843-707129b0a921 | note | Category - IP
e0a10294-38d8-57d0-acfb-4ad558dddcd4 | note | Responsibility - SE/Site Supervisor
ae052435-06ae-5297-9e0b-b240a0c2e4e9 | note | Verifying Documents - Sign ITP
f9e22e9d-6b78-52bb-b8a0-712758eed998 | textbox | Date Completed:
| checkpoint | 5.4 - Compaction test (Frequency)
e5c1edb7-bed6-5983-ab57-d2a5f9be2e36 | note | Reference - 304 .11 (b)
3a5c72e8-fbd9-5646-aa27-20290a21afe7 | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
ba85afe3-76e8-56e9-a84d-2e6217681447 | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
015d310c-0b1b-5a36-9590-adc818b57617 | note | ○ Scales A and B: 6 samples
34f81167-ed4b-5172-8822-f430f7e2b8d3 | note | ○ Scale C: 3 Samples
2f542fc9-ba3a-5027-a797-a3c4bcca31e1 | note | ○ Pass: Tested
9d5e4c6a-f243-5ad9-b803-54f994846b2e | note | ○ NA: Not Tested
9266e1fd-c224-5914-9886-f72d84d2fd8e | note | Method - Visual
f105a76f-1891-5063-8277-018b508f804d | note | Frequency - Each Lot Where applicxable
55375623-073a-52b7-b5d3-04e7106bd588 | note | Category - IP
3774f41d-c8ac-5881-8241-fafeb21e9622 | note | Responsibility - SE
c3391b2a-c9aa-5433-94e5-33c7bc86901e | note | Verifying Documents - Sign ITP
40645c17-0428-56fa-8d44-7c143e802a40 | textbox | Date Completed:
| checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
06d5a86f-2801-55b5-b77c-dc0b0a612f6f | note | Reference - 304.11 (c)
8275823d-28c5-581c-91b3-48e320f8e898 | note | Acceptance Criteria - SCALE A:
df0a5516-796f-504f-bc54-5490228590f5 | note | ○ The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
49e8bfb4-738b-5948-886c-b512c3b78ade | note | Compaction:
845d3c40-9358-584f-a50d-95a9b3ad899d | note | ○ Lower Subbase: none
721796a4-dc91-5cbe-8398-0ed5a83679f6 | note | ○ Upper Subbase: 1 in 4
b86ebbde-90f4-5539-9c91-1434778902ff | note | ○ Base: 1 in 2
43fadb60-bb38-5f6b-bc70-7e9252c6779b | note | PI:
9ec6b3bb-5cde-54dd-8bb0-ed1d1e5f79b7 | note | ○ Upper Subbase and Lower Base: 1 (two samples) in 8
3a4aa8ef-f061-5535-a230-f348eae3de32 | note | ○ Upper Base: 1 (two samples) in 4
cf2dad95-d715-508b-a689-06d01a09e871 | note | SCALE B:
df249b67-9751-5f27-94e8-95fb90e714bb | note | ○ the first lot of each pavement course shall be tested for post-compaction grading and PI.
163ed4b1-6d6f-5ab4-a69a-4b2ca5b4cb14 | note | SCALE C:
495e157a-7355-57a7-a09e-c620d3cd7bce | note | ○ Post compaction grading and PI testing is not required (CHOOSE NA)
074437bf-5ccf-5c1f-b6de-f59ebcb15784 | note | Method - Visual
577df030-3595-5854-989d-4b4ac33eaa8e | note | Frequency - Each Lot Where applicxable
7e75f971-a2e1-5c4f-9484-ce3a556eb707 | note | Category - IP
f646a15c-161a-5145-9c30-5fa1a49865f3 | note | Responsibility - SE
2b030299-c6b9-5ef5-8065-66eea984e9d9 | note | Verifying Documents - Sign ITP
aa03fa7f-55e1-587c-91d2-090471f1e949 | textbox | Date Completed:
| checkpoint | 5.6 - Proof Roll
4c670494-f690-5b50-810e-b494570a6bb1 | note | Reference - Section 304.08
4fd0a818-401e-5e3e-aeb7-406ef6b362eb | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
8c320614-1cce-5fcd-9686-b21ce9ad32f1 | note | Method - Visual
9562dd5a-f4ec-5eba-8de4-2bde4a837d12 | note | Frequency - Each lot
a3592546-ce81-5d32-8c05-77f347e488d5 | note | Category - HP
50451aa1-f26c-5901-bdd2-6facbe8a04a9 | note | Responsibility - Nominated Authority
cd5ec3b1-837d-545b-a085-b6d24852b0a3 | note | Verifying Documents - Sign ITP
234bdd0f-6ce6-5392-ad0d-4789896643f6 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 - Protection of compacted layer
9de1387d-da9e-5443-8866-d2cf11176d33 | note | Reference - Section 304.09
adcd9f68-6b46-536c-85bf-7ad429565437 | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
1465141b-6e46-5801-96b2-6679fa90e68a | note | Method - Visual
44f84631-9610-5022-96fa-789f1ee4da19 | note | Frequency - Each lot
ec0860e5-2b42-5f33-bccb-8c17271d442e | note | Category - IP
57a07243-aa6d-5bf1-a019-6cc45bbb11a3 | note | Responsibility - SE/Site Supervisor
27dfa74d-3c27-5935-bb06-661942abc55c | note | Verifying Documents - Sign ITP
494d0f6e-c5ed-548f-bce6-34476297cec1 | textbox | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Compaction Testing (results)
2242548d-40ec-5a75-a1c2-5ce801574c92 | note | Reference - Section 173, Section 304.08 Table 304.081
b20d74d0-e862-525d-8587-87cfeb821dfb | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
9d04de45-b2ec-5050-8536-04ede1937e2b | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
5f56cb8b-14d7-587f-8cf9-75dbe6ad5d3b | note | Scale A:
20835722-b854-5339-8cb4-ef3e51a79c00 | note | ○ Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
b27f285d-161f-581a-9ac2-ff1da6e298a8 | note | ○ Base Layer CDR ≥ 100%
eb177e72-a221-53db-8be1-5601cc512574 | note | Scale B:
2c10a9d8-c7a0-53bc-b762-f36863dff1d5 | note | ○ Subbase Layer CDR ≥ 97%
4bfd70ed-b4ec-5fa3-a291-c3335ce0fbbc | note | ○ Base Layer CDR ≥ 98%
63042eec-cb6a-5b54-99e2-056b2996e1b2 | note | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
9e7a3c9b-e687-5b20-bcaf-56f0d6665a21 | note | Scale C:
cc214577-2622-5d6e-ba15-94702ad8d3fa | note | ○ Mean Value of Density Ratio (3 tests):
4cb065f7-a97e-5366-9ef8-552d0580d99a | note | ○ Subbase Layers >98%
b0e6fa51-0c88-51c1-9c21-82f03d00efc5 | note | ○ Base Layers >100%
56c80dc4-1d4b-586c-988b-9afff67683a6 | note | ATTACH: Compaction Test Results
63af89d5-6d7b-5107-b85d-95a4a45b09da | note | Method - Document Review
561d7d45-92d8-5d24-8ce0-8782ea1dd555 | note | Frequency - Each Lot Where applicable
a0f3545d-4bde-53ab-95b9-1492b090b9ec | note | Category - IP
276995be-006e-54f0-86eb-990c537d6548 | note | Responsibility - PE
f6477e74-934c-5ed4-b1b0-159de42d7881 | note | Verifying Documents - Compaction Test Rersults
4239c8d9-0e22-5550-b373-b321fa78c676 | textbox | Date Completed:
| checkpoint | 6.2 - Post Compaction Materials Testing (Results)
731d3ff7-2559-54c0-aad4-be2b0b89a328 | note | Reference - Section 304.10, Section 304.11 RC 500.02
27189b99-b814-5755-aa37-e802bd3f6d3f | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
edd68a6c-32fe-5d26-9ea7-50f8aa9e12b6 | note | 20mm Class 3:
124262fd-5324-5bd1-879d-1a16f2fc246b | note | Grading
0572fd0a-e62c-5d55-a135-c4701c683fa1 | note | ○ 26.5mm 100%
f6bea2c8-ec7e-54ea-b429-e7ffefe672f6 | note | ○ 19.0mm 95-100%
399f3b38-5f14-51c0-813f-11c7d0e46e57 | note | ○ 13.2mm 75-95%
491496be-136e-58d2-8302-aa0e4c21c0df | note | ○ 9.5mm 60-90%
5780aad9-b3d1-58a7-a4fc-2030f778f9b2 | note | ○ 4.75mm 42-76%
0b37b07a-c016-544b-9b4c-18f078808bd2 | note | ○ 2.36mm 28-61%
b78f1cf6-3527-5bba-870c-9ffed8683269 | note | ○ 0.425mm 14-29%
7cf7dce7-d45d-5913-92a2-9c9e388b6655 | note | ○ 0.075mm 6-14%
e32a840b-9f12-516c-a624-a87791820b02 | note | ○ PI between 0 to 10
dad2a5fe-0af1-5d1b-9272-2e91f1f2d937 | note | 20mm Class 4:
9753c4d7-b0d9-53e7-89f6-c5e8286e4fe9 | note | Grading
b6081ed9-499d-53b0-ae9c-3999cf4df452 | note | ○ 26.5mm 100%
1c23d409-7a0a-5977-88bf-64ed8fc6b327 | note | ○ 4.75mm 42-76%
c2c8b3f6-63d8-5717-8468-10134b9d8d57 | note | ○ 0.425mm 10-28%
aabc78da-ed56-5718-855a-c7ef432490a0 | note | ○ 0.075mm 2-14%
20d3958b-5a3c-5b71-a5ce-fbc1190bb98d | note | ○ PI between 0 to 20
6dd20bde-d680-59b8-807d-448f861263c8 | note | ○ PI x % passing 0.425 mm sieve (max) 450
d0f04ea2-b903-59ae-a19c-1b2274dc3f74 | note | Scale C: Post compaction material testing is not required (Choose NA)
56c0b8df-a95c-59b2-8320-7156be335e23 | note | Method - Document Review
9b0694cd-569d-598c-b1ab-8048e9f9b41c | note | Frequency - Each Lot Where applicable
bdefee9c-c7a6-51d9-9ad0-2350efe46d90 | note | Category - IP
b2a3c4a2-70ba-53ad-a7f3-94ed4d9e57be | note | Responsibility - PE
f307566d-a017-56dd-819a-f8e6d484163a | note | Verifying Documents - Compaction Test Rersults
91ae96d0-ab72-5b3a-986b-252f7dcbf82e | textbox | Date Completed:
| checkpoint | 6.3 - Survey As-Built - Surface Level
2f177bd5-09e5-5cc2-9f73-a9b4944a6a28 | note | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
daac33a4-2505-5dc2-bac2-215948de096a | note | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
f713b0ed-011b-5dcc-91db-3aaef1714c1a | note | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
0c9f80a3-e46e-5888-a959-3ca7ca48eb42 | note | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
9e30fc32-4606-5db2-9198-52170d3b71ca | note | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
98a82767-7f60-52ca-a42c-5fa125ce0be5 | note | Scale A: A minimum of 80 measurements per lot
73192754-d30e-54c2-bb01-2c9c6f256c11 | note | ○ Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
1ad6d947-d6d2-5e85-9f9d-693d8ac8eb72 | note | ○ Base: mean range ±5mm, maximum Standard Deviation of 8mm
01a0161b-df65-515d-8d32-ac84bc31439d | note | Scale B: A minimum of 40 measurements per lot
fae784a6-f3a1-5266-83d6-391aebc9ab07 | note | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
62fcef04-af3a-5f58-a603-7911a85c6ac0 | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
fc7113e9-698c-5381-a95b-98ca9320402e | note | Scale C:
80fd02b2-a566-5015-8441-ea674e409f53 | note | ○ Lower Subbase (mm) +15/ -25
677164f0-04c0-55fd-9e53-12cd8b1805a1 | note | ○ Upper Subbase (mm) +10/ -25
fd437000-87e0-5439-ad1b-089e245f1458 | note | ○ Base (mm) +/-15
628a2dd0-6740-5b9e-8ec5-a2aa0bc33e87 | note | Method - Document Review
c39b8114-4091-5992-ac73-3aba3cbf351e | note | Frequency - Each lot
16cdada0-abd7-57d3-a1ef-1b40206f7670 | note | Category - IP
afaef9cd-b082-5e2b-bf21-5b9cc91e940f | note | Responsibility - PE/Surveyor
4888d8cd-d316-5b22-8d69-c5e60bc43a02 | note | Verifying Documents - Survey Conformance Report
19522a1d-657a-5f6f-89b6-8b9945570eb9 | textbox | Date Completed:
| checkpoint | Final Inspection
97701c0f-330d-56ba-a590-f042cb2a259c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
71328de3-80bb-5389-8ad2-f8e82e3425ac | textbox | Name:
e565f738-e0ef-5bf5-8937-eae0ef2cad8c | textbox | Position:
2fc62b8c-0047-57b0-a093-084902d943a3 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | itp | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) | 06ec5267-866b-4c86-9506-97de52634e90
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
18459930-d8bf-5a9f-837c-d390b2aafc2f | note | Document Title: ITP-CIV-CPD-Hot Mix Asphalt (Supply and Install)
96144a59-7228-52d2-97d3-3ef13efc2eba | note | ITP Description: Hot Mix Asphalt (Supply and Install)
e37c4508-a1c3-54d5-8fd7-1924114dc8f2 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
bdaa64c8-ad1c-5707-96b6-6065068d358e | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
c5ffb4aa-5811-5392-8892-37094ef19397 | note | Revision Number: 0
55760bfc-5a1e-58c6-ad99-e74343d9714b | note | Revision Date: 22/08/2023
ab4fc8b6-7d69-57f1-b44a-c71a535cbf14 | note | ITP created by: Ahmed ABDELSALAM
b2297ecc-bdfc-5a14-a8ef-66431f2d0473 | note | ITP approved for use by: Pradeep TALASILA
| checkpoint | 1.1 - Non Dependent
7dc8f174-bddf-5942-9923-024abf4936c0 | note | Reference - IFC Drawings Vic Roads 407, Vic Roads 404, Vic Roads 417 AS2150
| section | 2. Preliminary Works
| checkpoint | 2.1 - Mix Design & Trackless Tack Coat Approval
061e3e14-c08a-5a80-bb7c-51f60aa2c1a0 | note | Reference - 407.09, 407.08(d) Mix Design Registration
60958fc8-0679-5380-b4ee-a3fe58a383e5 | note | Acceptance Criteria - Mix design and trackless tack coat to be used has been approved by project superintendent, prior to use
9319eba8-f24e-502a-ae42-f2cf6036ec12 | note | Method - Approval Correspondance
9fc74144-8674-557b-bd08-35cfb7281eae | note | Frequency - Prior to commencing paving
f19e3ece-1353-54d0-99ba-e6974d3c1668 | note | Category - HP
ab8a4d71-01e5-515e-a3fc-e410e5e8c8fa | note | Responsibility - Project Engineer/ Supervisor
bcc249ef-9117-57d4-abe8-71d8311ac98d | note | Verifying Documents - Completed ITP
fd1d053b-8aed-5fe4-b2a5-f477ef3c5d4b | date | Date Completed:
5870ca28-5bb4-53e6-a8f1-fdba3ec9a203 | textbox | Team Binder Approval Number
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Asphalt Placement and Lot Plan
fade3785-aa28-5455-bf46-4f60b26424a5 | note | Reference - Section 407.17
e281b48d-1316-519a-9c91-cb4e2bde76f7 | note | Acceptance Criteria - Asphalt placement and Lot plan to be created prior to commencement of works.
e388acf8-47a9-57e3-bf10-05c45ddc4e2d | note | ○ The location of all joints shall be planned before work commences to achieve the specified offsets between layers and the final position of joints in the wearing course.
0e36a93e-1f67-59b9-b720-542a04914e3c | note | ○ Plan to specify start/end chainage, offset/lane and layer.
bfea3d18-69d9-5ac1-bab8-f72f6438d120 | note | Method - Verify
963bb98b-d955-5956-8ec4-5b80ed598710 | note | Frequency - Each lot
dc52dc4a-094e-5ceb-8801-49639aeeade7 | note | Category - IP
6b9ea933-b49e-5b22-bc0c-48421364a5f5 | note | Responsibility - Site Engineer/ Asphalt Supervisor
7de782b9-4b69-5512-bc8e-28d76024f30b | note | Verifying Documents - Daily Lot Record
815b8ee1-dacf-509e-a975-cf131cf65945 | date | Date Completed:
| checkpoint | 2.3 - Site Inspection and Base Condition
c63305a1-2b28-52c0-b77e-31a6c59279ec | note | Reference - 407.17 AS2150 10.1 AS2150 10.3
35b682d0-36eb-5910-a673-17611be69fd2 | note | Acceptance Criteria - Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
ccfb2874-e413-575f-9e41-3ac191b15f3a | note | Method - Visual Inspection
a9dbcca0-d203-5698-8f74-00a96423713c | note | Frequency - Prior to commencing paving
27854199-91c6-588c-aced-23422e9df2e8 | note | Category - WP
5c9df642-9fd6-56e5-ad17-c7f10fb0d8aa | note | Responsibility - Asphalt Supervisor
c3a4bc9c-7990-5fa2-8280-799f3cc0ff6a | note | Verifying Documents - Completed ITP
d82a9faf-e7dc-5397-91f8-a11181b5c4c3 | date | Date Completed:
032848f2-d8b8-5f4b-bab0-07091f56d2b7 | textbox | Team Binder Approval Number
| checkpoint | 2.4 - Ambient Conditions for Placing
39362b2b-f86b-5079-80e5-e71ed0935db3 | note | Reference - 407.17
dc7184e2-3e25-5f69-b9ce-818edceb8173 | note | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following:
7fe3ea1d-c760-54c1-a861-5ab99623d180 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
3355e62f-17c7-5a97-983f-178261c76866 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
04001dae-9180-53d9-b886-a92c606ffbdd | note | ○ Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
fffbf003-3d0e-5bbe-af37-7ac049df9ab3 | note | Method - Infrared Thermometer
43d02c54-8036-5e52-8701-59b495c41ffe | note | Frequency - Prior to commencing Paving
3bf07dd4-46c0-5bfc-8677-bd96c927587f | note | Category - IP
8476cdb2-7934-561b-99ae-3731ccd14cf6 | note | Responsibility - Asphalt Supervisor
e8d08644-1b0d-51e9-b3b8-d80e1dfd9ddf | note | Verifying Documents - Completed ITP
c035702a-42c4-567b-858a-b5bc5d2f4ea3 | date | Date Completed:
ae289b21-2a24-58e4-8ef6-2940ff11881d | textbox | Team Binder Approval Number
| checkpoint | 2.5 - Planning of Joints
ebfc0b11-6cb8-55fa-b182-f9ec952001aa | note | Reference - 407.21
8c6f8ca2-7b6c-500e-a8b5-e27e1b3378e3 | note | Acceptance Criteria - Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines
71618320-5455-5d0d-b720-ec2567a09bbb | note | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines.Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
b3ae3744-5ca8-5114-9416-54d5a785f245 | note | ○ At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
1cbbb87b-9b16-547f-a72d-cde8469606e7 | note | Method - Measure and mark out runs by tape measure or survey
ec630a31-6343-548e-bd5e-b210156620e0 | note | Frequency - Prior to commencing paving
79da9765-c3f2-5cbf-aa39-8c9865ea3149 | note | Category - WP
ea46f3f3-f50f-5a2b-88a4-ceb1d2561cd1 | note | Responsibility - PE FHC
876aa49b-309d-5518-9b0a-cfb15938b2e7 | note | Verifying Documents - Completed ITP
8e54b79e-94ed-59a5-a07d-428cc1c9ec9a | date | Date Completed:
| checkpoint | 2.6 - Tack Coat
4ca7e6e2-959b-59a3-8464-98c2f0060f47 | note | Reference - 407.19 AS2150 11
937eb937-22b4-558d-a0ae-e89d96d2a5c0 | note | Acceptance Criteria - Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2. This rate is to be doubled on joints and chases.
356f90e5-b9c4-5699-ae2e-20fa5262379e | note | ○ Tack coat must be allowed to fully cure.
98ab737f-96ca-5687-a5c6-edc51691e1c8 | note | NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces Photographical evidence must be obtained (with an identifiable landmark)
bfb41f3f-8bb0-575c-a3b6-b05da709cc22 | note | *from 1st July 2023, "trackless Tack Coat" must be used
4bbb6c28-2641-57b6-a901-049d3eb6f369 | note | Method - Spray area and inspect
038b1833-043e-5ae5-8f0c-8e1a2eb0a9e4 | note | Frequency - Prior to Commencing paving
44910c3c-0a8e-52e2-9a42-91efeb570f9e | note | Category - IP
7284b695-e885-59fa-bb09-782380fa74f4 | note | Responsibility - Asphalt Foreman
cea1b5cb-3762-5540-8037-6cab4dbca074 | note | Verifying Documents - Completed ITP
ba775944-c994-5600-b83b-02a6d9b650c5 | date | Date Completed:
| checkpoint | 2.7 - Submission of Primer Material documents (if applicable)
374a07ee-be35-5c82-8422-ce5d2d46cb3a | note | Reference - 408.08 c, e
db59a6cf-0fac-5f7f-bf16-5b982de27058 | note | Acceptance Criteria - The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.
6d78d335-6732-5fb2-8529-28a55aec18cd | note | Method - Document Review
dc7822ff-acd7-5cb6-bb70-ad7ec7a587b2 | note | Frequency - Prior to commencing works
34a34b7a-4d7d-57e5-9386-4cad2bb2aee0 | note | Category - HP*
9a8e6213-0866-5c9c-afe4-f26beb78ad68 | note | Responsibility - Site Engineer/Project Engineer
be36a2fa-73c0-5703-b99c-6f74065d2d4b | note | Verifying Documents - Conformance Certificate uploaded to TeamBinder
40733b85-ce5d-599e-97d6-7522de9ee34b | date | Date Completed:
9e154799-623b-53d4-a37f-c1cdc8157a90 | textbox | Team Binder Approval Number
| checkpoint | 2.8 - Application Rates for Primer (if applicable)
2c1d0a4d-1d51-5fa0-bee3-b4afcfa53a6e | note | Reference - 408.13 a
21fda06a-4cf7-56a9-b2f0-7932193cf6cf | note | Acceptance Criteria - At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent
94652226-3a76-58aa-93ab-642788441e86 | note | Method - Document Review
1328907e-12d6-5c26-85b4-470f6ffe4d8f | note | Frequency - Prior to commencing works
c42956b7-f006-52c4-a2f6-45151ef13482 | note | Category - HP
a8fdc5ad-068b-58d8-907a-b512240c526b | note | Responsibility - Site Engineer, NA
2b7c30df-2ddd-5508-bf96-65ebe01700e1 | note | Verifying Documents - Application Rates uploaded to TeamBinder
a087b4f2-8df4-54ee-ab12-a800344d935e | date | Date Completed:
910fb660-2bb0-5305-be40-9be3187f5688 | textbox | Team Binder Approval Number
| signoff | AUTHORITY HOLDPOINT
| section | 3. Asphalt Placement Works
| checkpoint | 3.1 - Commencement of placing
25fa4f75-ee1d-5704-91a9-ca9786e9d489 | note | Reference - 407.23
9aea9c39-1dc2-537e-9e81-36b6c3644364 | note | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
8126cd56-6c63-5513-8012-5631bb514e79 | note | Method - Visual Inspection
e895648f-0452-5a3e-9124-5f4b4c8443a8 | note | Frequency - Prior to Commencing paving
029346a8-779a-546c-919d-313835fa8bd7 | note | Category - HP
3760abda-76ba-58b7-a7b2-c2870f9b4145 | note | Responsibility - Asphalt Supervisor / Superintendent
f8d434cd-d711-5f93-bddd-5a3027a99180 | note | Verifying Documents - Completed ITP
794b73c1-5a71-5e40-a8fa-e19ba6a16403 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Delivery of Mix
990ae318-9942-593b-8c2e-13a7a7aca897 | note | Reference - Pavement Design Details 407.20
59cbb45d-f919-59a7-8ef3-d706661311dc | note | Acceptance Criteria - The majority of the surface area to be paved has a temperature greater than or equal to the following:
65115537-a58a-5329-9822-8fefcee6ce1d | note | ○ Base & intermediate courses: 5ºC for conventional binders or 10ºC for PMBs & Class 600
46d1ec28-7631-50fa-a8de-d5f11d6c1456 | note | ○ Wearing Course: 10ºC for conventional binders or 15ºC for PMBs
7c405867-0f70-59cc-828d-8f2607c7be4d | note | ○ Where the above temperatures cannot be achieved , asphalt must be laid under the "Fulton Hogan Cold Weather Placement Management Plan"
2e048a61-6298-5535-bc94-a1f6e98ad9ab | note | Method - Check aspahlt delivery docket
9abd3a3e-37d4-5f95-b923-c7677141bbc3 | note | Frequency - Each lot
795c35e8-150f-588a-97d8-7801d764fe78 | note | Category - IP
b81f920a-b601-5108-b008-144d5124234b | note | Responsibility - Asphalt Foreman
a51c3068-357a-52f4-a0f7-cc9da29eac48 | note | Verifying Documents - Completed ITP
1e92119b-e45d-586d-b70c-8e8d98634e84 | date | Date Completed:
| checkpoint | 3.3 - Delivery of Mix
26d98e0e-9a2f-5467-b732-220670bc0823 | note | Reference - 407.11 Table 407.111
5c7aee8e-3eaa-53ad-8e9e-48a142076f93 | note | Acceptance Criteria - Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
74d7a728-e7e1-5c3f-b437-09edfce92fc2 | note | Method - Visual Inspection & Delivery Docket
806ec01d-84c1-54de-8ba7-5b0055ca4b5e | note | Frequency - Each load
c4c03733-4cdd-5a5e-a48e-0f152a31329a | note | Category - WP
8dbbbc70-9e94-516f-8000-3e8183c8b556 | note | Responsibility - Asphalt Foreman
e9b4bd6a-0069-5c78-8b7c-2567af0dc0a6 | note | Verifying Documents - Completed ITP
8c9dbb02-661a-5187-adcb-b847d87e5f59 | date | Date Completed:
| checkpoint | 3.4 - Traceability
43d66e52-8a8d-5201-b1e1-97432dff447b | note | Reference - Fulton Hogan Quality Plan
d3ec92cc-9346-5b5a-b150-1d76c95eccbc | note | Acceptance Criteria - Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
dc88a8e7-29cf-58e2-bc66-d2c1eabf104c | note | Method - Measure and Record on Daily Lot Record
71b1c173-bac2-5e41-88e8-87a5a7b7e65f | note | Frequency - Each lot
a259f9de-fc7e-568e-8b92-001e0c76feca | note | Category - IP
14440865-d54f-5bf6-8fe7-50ea83c69e74 | note | Responsibility - Fulton Hogan Foreman/ Engineer
307a6533-56f8-55e4-bb56-96368f86e70d | note | Verifying Documents - Completed ITP
0dc3764c-391b-5682-a486-f041867411e5 | date | Date Completed:
| checkpoint | 3.5 - Layer Thickness and Level Control
a7ba4f11-6eeb-5eef-a9fc-34eb8dfb29e9 | note | Reference - Pavement Design Details 407.25(a),(b)
9073055c-312b-5eca-a312-95fdb24b5bec | note | Acceptance Criteria - Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
a47fab5d-7b70-5e3c-bb1d-6db5f3434b0b | note | Method - Dips using ruler or dip stick
07d1e12d-ad7d-5fa1-a6a4-f9face8fb84c | note | Frequency - Regularly during paving
f17f3ed6-df65-5044-ad8e-37873aab050d | note | Category - WP
c1d244f4-1726-53a7-a032-68521de0a1e9 | note | Responsibility - Asphalt Foreman
253cce31-6e82-558b-8950-2cda2ffc9675 | note | Verifying Documents - Completed ITP
b1e151ec-c24b-5b42-94da-27a8927b0d6f | date | Date Completed:
| checkpoint | 3.6 - Spreading and Paver Stoppages
9d1b0baf-e837-517f-9f0d-cb309023978b | note | Reference - 407.25 (c)
5c2860c8-4fdf-5649-9e6e-8577aa1286eb | note | Acceptance Criteria - All asphalt shall be spread with a purpose designed asphalt paving machine to form a uniformly smooth asphalt mat complying with the requirements of Clause 407.29 without segregation, tearing or gouging. In areas that are not accessible by a paver placement of asphalt by other means is permitted.
a88f5768-fa6d-5853-a5a8-8df0f0f6774c | note | ○ The width of a single paving run shall not exceed 6 metres unless paving in echelon is proposed or procedures are in place to ensure that a uniform asphalt layer free of segregation can be achieved.
4a5105e6-3a3f-513a-a0fa-0b6eeba5a7fe | note | ○ The Contractor shall conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised.
c6d0de29-bbb9-510f-ba65-fb5e061385ef | note | ○ If the paver is required to stop and asphalt in front of the screed cools to below 120C, a transverse joint shall be constructed.
09e61437-3044-535c-8556-9f9b415cd292 | note | ○ For asphalt work carried out on a road to be opened for traffic at the completion of work each day, each layer of asphalt shall cover the full width of the trafficked area. The requirements of Clause 407.21(f) shall be followed in respect of the treatment required for exposed edges.
4b7391b7-ba04-5aa5-9b35-67678a3b5619 | note | Method - Thermometer
77dfb3e3-144f-5516-a2f3-a0377b5c90f4 | note | Frequency - If paver stops
59a56ec7-5853-5f27-82e8-da5e42483d95 | note | Category - WP
594b57f9-4d40-531c-b953-f261ad0ae945 | note | Responsibility - Asphalt Foreman
264c175a-7c2c-52c9-8594-7de2da269297 | note | Verifying Documents - Completed ITP
ee27abaa-e7db-50d0-a977-0de548efddd2 | date | Date Completed:
| checkpoint | 3.7 - Surface Finish of Wearing Course
9cebbd99-8954-5678-981d-967ac7fa48b8 | note | Reference - 407.29 (a) (i)
5ed443b1-4fa7-5a0c-b80c-c92409b5f7e0 | note | Acceptance Criteria - The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
a7c1250c-f23f-5eba-8c69-61fa4a636797 | note | Method - Visual Inspection
30746fc8-80db-54f8-a21b-2008070b8bd6 | note | Frequency - During paving and after final roll
6bc5fb0e-1f54-5325-8da5-8f86d298f0bb | note | Category - WP
692e4c85-7f94-5cb9-a206-2a33aea7c748 | note | Responsibility - Asphalt Foreman
3fb545e2-5312-5b39-8188-595e9e1e03d6 | note | Verifying Documents - Completed ITP
98617658-b722-5fac-8918-1d2b54b86177 | date | Date Completed:
| checkpoint | 3.8 - Kerb and Channel
b26fda89-5cee-56a1-97ff-f766f179859a | note | Reference - 407.29 (a)(ii)
b8a2c800-b013-587b-af79-2709bd77be0e | note | Acceptance Criteria - The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
5291621d-25ae-5f22-a270-15e403e4fedc | note | Method - Visual Inspection & Measurement
0229cbb3-eca5-59b4-8acc-d4cf97221502 | note | Frequency - During paving and after final roll
c98fdce4-9f94-5584-ab54-a14503cb6a9d | note | Category - WP
84cd81fb-4331-551b-8c01-5e00337afde5 | note | Responsibility - Asphalt Foreman
59a1081d-47bc-520a-9133-ec09db09a2c9 | note | Verifying Documents - Completed ITP
26a1238b-8da4-5ce8-8541-fb23f91e682f | date | Date Completed:
| checkpoint | 3.9 - Shape
c928f3ef-6786-5e5c-950d-ea8e8ab1a047 | note | Reference - 407.29 (a)(iii)
2d812b51-20ee-5bdb-bb02-f24a74d0f2b1 | note | Acceptance Criteria - No point on the finished surface of the wearing course shall lie more than 4 mm below a 3 m straight edge laid either parallel to the centreline of the pavement or, except on crowned sections, at right angles to the centreline. For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
892168bb-a599-5085-8cff-4b8b023d4412 | note | Method - Visual Inspection & Measurement
7eccdd91-c406-5b1c-a12e-7a68c19b6a56 | note | Frequency - During paving and after final roll
31eba65f-693c-52e0-969c-3446f66a0fff | note | Category - WP
7a7629b6-8e6e-5da3-896a-6ed1460addc8 | note | Responsibility - Asphalt Foreman
8cf1a468-0831-5459-8377-555e0fa27478 | note | Verifying Documents - Completed ITP
3f466315-054b-5d7f-ada0-1a2fcb276100 | date | Date Completed:
| checkpoint | 3.10 - Alignment
3aee018f-7e98-52d6-beb7-3ab1c50b1587 | note | Reference - 407.29 (a)(iv)
387a5726-b042-5680-9aad-010b768e6277 | note | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside, the designed offset from centreline or design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
76f5ec50-237b-5244-bcfb-f830d5a138dc | note | Method - Visual Inspection & Measurement
dced3035-988e-5531-9fdc-e8a800c54bfe | note | Frequency - During paving and after final roll
2612b300-de12-57d1-8a7e-4915cdfc6d60 | note | Category - WP
afe6ab5f-25a5-52a0-bf8c-6fab8b23ac54 | note | Responsibility - Asphalt Foreman
d5782e33-0657-5550-b98a-57da0a903e3e | note | Verifying Documents - Completed ITP
cb9de6a4-be0a-54cf-b2bf-52960a4bda58 | date | Date Completed:
| checkpoint | 3.11 - Width
33971501-8703-54fb-8247-f0fa435bb64b | note | Reference - 407.29 (a)(v)
21d52b1a-c8b2-5ed5-b688-3a18968aad0d | note | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm. The average width over any 300 m shall not be less than the design or specified width.
b2ca7e75-4ea5-59f4-b184-ffc792b0f657 | note | Method - Visual Inspection & Measurement
4e1c76c6-97d3-584f-970e-016f645223b2 | note | Frequency - During paving and after final roll
3ad6b409-aaee-5ff8-92a6-2b5c5f3937e0 | note | Category - WP
72443c3a-6787-5efe-835d-b1ac33bcae55 | note | Responsibility - Asphalt Foreman
7bb8048f-73ad-5419-93b0-baa6cb1a0a71 | note | Verifying Documents - Completed ITP
67c952df-bf70-547c-988f-924971ced937 | date | Date Completed:
| checkpoint | 3.12 - Trafficking pavement after placment
607d8302-73e4-5a75-9e50-335555f3c30d | note | Reference - 407.28, 404.14
0c6375ab-d0a1-5ce9-8a67-afda11054331 | note | Acceptance Criteria - Trafficking or placement of asphalt over previously constructed layers is not permitted unless the majority of the previously constructed asphalt has a surface temperature of 50°C or less and Falling.
fbf293fd-1e61-5bb7-af1b-cdc547da8650 | note | Method - Visual Inspection & Thermometert
13a51b54-19e1-56a9-b6ae-b5bbfa2944e3 | note | Frequency - After final Roll
ad3f53ac-4086-55f8-8a49-18260b99feaa | note | Category - HP
d644e9f5-3bde-5b83-a38b-2f5910da69ec | note | Responsibility - Asphalt Foreman
a9062faf-3342-53b5-83a4-8298fe1e4bb5 | note | Verifying Documents - Completed ITP
21324058-5454-5e26-ada5-36d6be0f6ded | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Testing
| checkpoint | 4.1 - Compaction Testing (Open Graded Apshalt)
018957ff-da81-566f-9903-a53327169c07 | note | Reference - 417.12
0eaee80d-0424-503c-9a64-f57540c2326e | note | Acceptance Criteria - Accpetance of compaction shall be on a procedural basis
81331193-a614-56df-bff3-27f7811336bf | note | Method - OGA/SMA Compaction Procedure
0d7c5aa2-dd5e-5482-8af5-8f93959dd881 | note | Frequency - Per lot
a5ac6dd8-ea1c-59b7-9474-8d94fbbb11b1 | note | Category - TP
c33bf95a-9868-5040-adf9-5b09664afb5c | note | Responsibility - Fulton Hogan Laboratory Technician
edc38704-45a0-5fd0-afbf-6ce82ff5d1ba | note | Verifying Documents - Completed ITP
05bd7020-6b5c-5af3-ab56-27c10415fae4 | date | Date Completed:
| checkpoint | 4.2 - Compaction Testing (Stone Mastic Apshalt)
25c5988a-b4c9-5dba-a888-37fc7c9ddcc1 | note | Reference - 404.15, 404.14 OGA/SMA Compaction Procedure
68c2f8e9-0686-5fa9-94c9-339eecae0afb | note | Acceptance Criteria - Per lot, the Characteristic Density Ratio must meet the minimum limit of 96.0%
8f08c36b-06f1-5054-ac29-bfb5b0b1a6ca | note | ○ For layers thinner than 25mm, accpetance may be on a procedural basis
c691c499-6b02-5ad8-abd4-a5856758ccff | note | Method - Nuclear Density Test, OGA/SMA Compaction Procedure
79e13529-fdbd-58df-b585-a1fd7099bd10 | note | Frequency - Per lot
cee05e20-5ac5-522e-99e7-25a65a679bf2 | note | Category - TP
755f8b19-4db7-5a0e-be30-2289eb4dd550 | note | Responsibility - Fulton Hogan Laboratory Technician
4c82f963-124d-5ad5-a529-a85d07329b42 | note | Verifying Documents - Completed ITP, Compaction reports
d2fbe671-e55c-5f69-a2ed-6f06d99974cf | date | Date Completed:
| checkpoint | 4.3 - Compaction Testing (Dense Graded Apshalt)
d52d9d4e-45b0-50ef-9e0a-350c6d3794c1 | note | Reference - Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
fcc9f695-95ff-5848-a4cb-3d31c32f04a6 | note | Acceptance Criteria - Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
33ec1528-387b-55b4-bc32-77aca66c8eeb | note | >50mm layer depth = 96.0%
82e1b2b7-5266-5455-8499-fea7cdb8113a | note | <50mm layer depth = 95.0%
8e17d602-6f86-54b4-9d58-6a0d043eea39 | note | ○ Additional Test must be undertaken on the longitudinal joints for wearing courses
633b5fc6-7539-5596-b158-1632c986f075 | note | ○ Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
8c5e38e7-d899-5bdf-8bec-af789bec93c6 | note | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
f8074350-1d1f-5dbb-bd72-17c5def92864 | note | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
fc53af78-5766-54f3-ba89-ef1f8e49d08f | note | Method - Nuclear Density Test, DGA Compaction Procedure
bf0aa345-10e2-50f7-87a8-245831188836 | note | Frequency - Per Lot
ec0fc5d5-7b6a-5e79-a45d-d719e9bb5182 | note | Category - TP
0d30aac3-5a38-50a2-b8d9-bd42fea18f7d | note | Responsibility - Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
584a2597-469f-5a54-ba41-10c72c26e986 | note | Verifying Documents - Completed ITP, Compaction rerports
a640eca4-7d6a-5c40-87d1-f1ffd52a72af | date | Date Completed:
| checkpoint | 4.4 - Level Conformance
60517cb3-4a14-55e4-9db5-41248989f7ad | note | Reference - 407.30, 407.29
375576b5-d90a-5e6c-b7f2-121ce8709209 | note | Acceptance Criteria - The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
3709b035-2468-5af1-99e0-114cad9e164e | note | Method - Survey Results
5acd3257-4c7b-50b4-a6de-9c8d7fa4af9d | note | Frequency - Each Lot
afb827c2-a597-5540-a926-97cdfadc5a53 | note | Category - WP
41dec22b-e843-59d0-bd6e-ffb73493d55d | note | Responsibility - Surveyor
7e8c4cce-39f0-5ce2-9986-ded67aaff9c5 | note | Verifying Documents - Completed ITP, Survey Conformance Results
00c1fdcd-28fd-59d7-b44a-48881e037c8e | date | Date Completed:
| checkpoint | Final Inspection
3e0531d0-bd35-5b0d-aa93-23e8bc015c1d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0888a47f-243b-53da-9838-ac81a86dbd1a | textbox | Name:
e37f6d89-abdc-5667-89ea-419fafb4e8db | textbox | Position:
564b6603-c18e-52c8-8639-bf5ac51c4988 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-075-CIV-CPD-General Concrete Melbourne Water Rev 0 | itp | ITP-075-CIV-CPD-General Concrete Melbourne Water | 74111725-680b-468e-ad41-fa0b1e69f627
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
4653338a-7c87-5de1-9e96-050800a934eb | note | Document Title: ITP-CIV-CPD-General Concrete_Melbourne Water
2c8ebae9-1631-5b4a-8390-e575f194791a | note | ITP Description: General Concrete_Melbourne Water
8c5635f0-b5b2-5dba-9335-d2c71c523617 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
96a735d9-ade2-593d-9e67-5c38492996d4 | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
9fd33d7d-c743-5be7-acf6-569a0a6ab542 | note | Revision Number: 0
e711c6a0-fe85-576e-a4d9-1a3a6b298d8f | note | Revision Date: 8/09/2023
93b81387-33b3-5eba-b8e3-b4af2d532fa8 | note | ITP created by: Ethan CARUANA-SMITH
97691837-5713-5d0d-8d89-a10b06b1ee46 | note | ITP approved for use by: Pradeep TALASILA
| checkpoint | 1.1 - Non Dependent
72745b8b-7131-5c73-8ce7-4bb15a65468b | note | Reference - VicRoads Section 703 June 2018
| checkpoint | 1.2 - Non Dependent
ed0f88e5-53e8-5e86-b792-97c373330e06 | note | Reference - VicRoads Section 812 July 2016
| checkpoint | 1.3 - Non Dependent
70cf5ff7-9404-5d5d-97ba-5137ecb7c2d2 | note | Reference - Melbourne Water 7251/08/420
| checkpoint | 1.4 - Non Dependent
119c0fe3-9dea-59e5-9ba8-2a3dbfbab6a1 | note | Reference - AS1379-2007
| checkpoint | 1.5 - Non Dependent
0fa8810a-d67f-5b7a-b2d8-cc1637518d1b | note | Reference - AS3610-2018
| checkpoint | 1.6 - Non Dependent
af529cd3-139f-5279-bb48-2c7ca12ff740 | note | Reference - AS4671-2019
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Bedding Material / Base Layer
000b2f2f-07fc-5547-adc3-f86538ed7475 | note | Reference - IFC Drawings 703.21 812.04
37723d0c-8cd2-5c53-9d2a-798a692d843e | note | Acceptance Criteria - 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
830fb834-790a-5501-8d63-29211a470663 | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
1aeec655-e4dd-511e-8c76-9f9616760ef7 | textbox | Enter: Teambinder Material Approval number
fef6f844-7b68-5b89-9a1c-061c0edbae90 | note | Method - Document Review
4c2212d6-66da-5e7d-9960-06bb16f9a24f | note | Frequency - Once, for each mix design, prior to placement of material
e27abaa2-b4e4-5a46-a110-bbb6f6b285df | note | Category - HP
80fd637d-05da-5ffb-9c9a-b59343e3bdac | note | Responsibility - Nominated Authority
efd081f5-a691-5ea5-a1c1-3320b9d134b9 | note | Verifying Documents - ConQA Hold Point Release
17c92423-a231-50d4-ae0c-8bc6cdc1cd58 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete Mix
3549c91a-6bfc-59a5-8c99-dbc21c880ccc | note | Reference - IFC Drawings 703.05 (a), 703.07 MRPA Quality Management Plan Melbourne Water 7251/08/420
147e4a36-a043-510b-978a-101c2dd405f3 | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
9fd2837b-b60a-5c07-a802-4f6e111dc17f | note | ○ Paving concrete mix conforms to AS1379.
26c36394-822d-5216-8bb0-045faab09950 | note | ○ SUP concrete mix is registered with VicRoads.
e0c5565d-187e-5749-820f-77a33dbebf17 | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
ed07b331-94a4-5247-9321-d194fb74c54c | textbox | Enter: Teambinder Material Approval number
44033910-9938-57b4-9d8a-540b5e9352fe | note | Method - Document Review
e6255a53-c78e-55d1-92a4-c604d2afc8a0 | note | Frequency - Once, for each mix design, prior to placement of concrete
c2d83749-8997-5ac0-a835-a9b14ca55307 | note | Category - IP
f14b06ff-3761-5e78-bbe5-d61553fa1df5 | note | Responsibility - Nominated Authority
6badb348-4ede-5591-a507-1c8942597e33 | note | Verifying Documents - ConQA Hold Point Release
1edc6470-d241-51f2-b955-76b3545a5686 | date | Date Completed:
| checkpoint | 2.3 - Reinforcement Certification (or ACRS Certification)
e665e891-8633-59d1-819a-f9b652aef5fb | note | Reference - 703.13 MRPA Quality Management Plan
a008af05-3b71-5d8c-9e95-c83c99731cfa | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
53eeb21c-ff0e-5113-900b-2182aa13b204 | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
97e788b6-b399-53bd-aa27-5103778be240 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
956f52f8-5eb6-5033-b9cc-e4d44659b096 | textbox | Enter: Teambinder Material Approval number
023fdb67-16e5-5dd3-a110-440775551479 | note | Method - Document Review
39fec9cd-23f0-55ed-9753-419f3ef722c9 | note | Frequency - Once for each supplier, prior to placement of order
f0dc7e99-d74e-56ad-bc10-108b5bedc4e0 | note | Category - IP
98d7a4b4-ddb1-5a16-bca3-0a0bb407f9f2 | note | Responsibility - Nominated Authority
2dbc8386-2826-5a09-80fb-c4adbd82f693 | note | Verifying Documents - This ITP
65eebc14-14b3-598b-b1e8-aff40358df74 | date | Date Completed:
| checkpoint | 2.4 - Evaporative Retardant
c24808b2-4dc1-5b39-951e-39154010778e | note | Reference - 703.09
2c90d8fd-e342-562c-bad4-0e7e89b042d7 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
f1aac25a-eb60-5c40-8b80-cbd7b5f7f567 | textbox | Enter: Teambinder Material Approval number
8946d981-e225-578d-8fcd-26cd79d77e2a | note | Method - Document Review
8b96c432-b018-5c6f-a7d4-b9030b76d20e | note | Frequency - Once, for each product, prior to placement of concrete
247034e3-4323-5cb4-829e-924d68f99e86 | note | Category - WP
8b4d24d4-8e78-5005-aed1-572d09c2e957 | note | Responsibility - Nominated Authority
c141e75b-9c41-5a7c-8940-10e843116eb4 | note | Verifying Documents - This ITP
e45414b9-bf15-5881-b63a-b17880b7b919 | date | Date Completed:
| checkpoint | 2.5 - Curing Compound
b30f00c3-a226-55f6-939e-21fad51b14ca | note | Reference - 703.10 (a)
e62feeac-b3c5-5c72-83b0-ccd4e8ff327f | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
b02faaea-7141-5cb4-b514-6f6527a51f37 | textbox | Enter: Teambinder Material Approval number
1b197ab3-65d1-5395-add4-5b82e95b84ee | note | Method - Document Review
e33c3bd5-a67f-50d0-8c6c-50c14f5b4be5 | note | Frequency - Once, for each product, prior to placement of concrete
bdd78c48-6a51-5194-830a-56722dfc41c3 | note | Category - IP
da489684-a85d-559a-afe9-62cce8821365 | note | Responsibility - Nominated Authority
06cadd2b-8fb7-53c9-84e4-d239247bc0c8 | note | Verifying Documents - This ITP
7aec5318-e7cc-5371-b74b-ca7cfbbaad94 | date | Date Completed:
| section | 3. Pre-construction Activities
| checkpoint | 3.1 - IFC Drawings
6426a222-bb73-5463-8f9f-b7150c566942 | note | Reference - MRPA Quality Management Plan
5f2f9d68-2b89-556a-9931-acc8ad30fb07 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
b6269227-a153-544d-8cc7-2645f996af9c | note | Method - Document Review
67aecb2e-7848-5192-b226-8212f2faba6d | note | Frequency - Prior to starting Works and at regular intervals
e299f28a-0b14-5c3e-989c-e84fb597a36c | note | Category - HP*
3d7f7aca-9d0f-5f64-a0d7-4c323448a6ba | note | Responsibility - All
ac4c7f16-a084-51d2-b15d-8a8ea74e00cb | note | Verifying Documents - This ITP
cb0d2c9b-56b8-5721-aa85-1efae77ccd87 | date | Date Completed:
| checkpoint | 3.2 - Survey Set-out
69cb26f0-6a7a-5b47-bfb1-148d5fc35ac6 | note | Reference - IFC Drawings 703.17
08d12c2c-d8a5-5f03-ba57-056b68b99a60 | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
d9d886a2-9f1e-5d6e-a583-98dbfcb01133 | note | ○ The Nominated Authority will review and confirm the set out.
6b90438e-d1ee-50dd-805a-766021c97909 | note | ○ Maximum deflection angle of 18 degrees
88018fd4-c958-540a-a810-f1b5c8727f60 | note | Attach: Survey Report
56765df2-1b26-5121-b6dc-9074eaa1b82b | note | Method - Document Review, Measure, Visual
7996c7e5-3c86-50ef-a0f0-26d21da70c35 | note | Frequency - Where applicable, each lot
6aef585e-ce2e-57e6-9ab3-65b1b2453349 | note | Category - HP
719c928f-0687-5695-982c-3125ab2f036d | note | Responsibility - Nominated Authority
fe0b739e-c78e-5076-9fb6-a0a203b6f5e1 | note | Verifying Documents - ConQA Hold Point Release
11a66558-217b-5df1-94a1-2c856d46250c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Construction Activities
| checkpoint | 4.1 - Excavation
88fed95d-3c22-5995-885c-6a46d88820c7 | note | Reference - 703.20 Melbourne Water 7251/08/420
048e5428-e37c-5658-bf0a-e5f3b3a3c0ff | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
9d9a2648-32d8-502a-b897-e0950228d75f | note | ○ Excavation to allow for a minimum of 50mm reinforcement cover on earth face and a minimum of 375mm from pipe joint.
a39f535f-391f-5604-a7ed-f675e697f1f1 | note | Method - Visual, Measure
b3071921-0cc9-5f8a-8726-098cf294f7d8 | note | Frequency - Where applicable, each lot
c6a2a243-ad38-5325-8429-fd28a37bc708 | note | Category - IP
3bd4d08a-0714-51d5-b683-bf876af50816 | note | Responsibility - SE/PE/SPE
dda87f13-9415-56f1-b248-e9c3b53a6a87 | note | Verifying Documents - This ITP
6ac3921b-e04d-5a7f-b15e-2a927e005b67 | date | Date Completed:
| checkpoint | 4.2 - Bedding Material Placement & Compaction
8371f887-92bd-568b-adda-1ce8934c5102 | note | Reference - 703.21
8580478f-2eea-5fe8-aa98-7359e8fffb92 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings).
00b6303d-518f-554e-af21-c379b0056f25 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
f2132e71-974a-520b-b7e2-bb7bd3d310bd | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
1737aa7d-579d-5319-a515-15f6f9e1e0c1 | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
d173d864-7990-5e9a-b63e-101fa4485f57 | note | Attach: Bedding Material Delivery Dockets
73ac1954-9cdd-5b72-ac05-9691e3922004 | note | Method - Visual, Measure
dffae503-2944-5ece-8fa3-090880e954b9 | note | Frequency - Where applicable, each lot
94a7661a-085e-54f9-b031-91644baea92f | note | Category - IP
481a9273-0620-5438-ae22-bcf0affc90f7 | note | Responsibility - SE/PE/SPE
6a3dc31f-c074-5bca-bea7-e09d16b3e7e9 | note | Verifying Documents - This ITP
35c4f32c-f1b0-5817-8419-250b4dc9ceb3 | date | Date Completed:
| checkpoint | 4.3 - Formwork Construction & Placement
8d7d287e-b762-564b-96fd-bf486e9044d8 | note | Reference - IFC Drawings 703.12
86253e6b-2590-5029-a152-eea93f28784c | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
be9f6c12-1f73-5d54-adb9-bfbb41e5732b | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional comformance.
ee35bfb9-f10a-5e2b-a906-757dba06d37b | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
872170fa-6ce8-5db3-91ff-fda55367a102 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
9e9998e9-e179-5cbd-b343-6fbca1c877a3 | note | Method - Visual, Measure
96c60c44-d739-581a-a239-75b34b996583 | note | Frequency - Each lot
f7de3048-1c93-5fec-8af9-178c9a1d02cb | note | Category - IP
f170cf69-34f3-500a-9243-22bf5a78421f | note | Responsibility - SE/PE/SPE
fd97d0fc-e41a-5d49-9909-f85ae5028f6b | note | Verifying Documents - This ITP
a3471baf-5305-5dc1-8e97-5e3764b6f033 | date | Date Completed:
| checkpoint | 4.4 - Construction Joints & Matching Exisiting Surfaces
aa44e527-4c7f-58d2-ba11-5320dbe921d8 | note | Reference - IFC Drawings 703.24
288f78d8-d194-557b-b3cf-d6e586bf486f | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
959e43f5-124e-5149-ae7e-b15b9f517e42 | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
c81b2168-2ff9-5672-a828-45dced7d9ece | note | i. Concrete cutting of a shear-key
b20a8be7-a71e-58d1-bcf9-f603a7c72c28 | note | ii. Surface roughening
ae2872ac-3c07-5c83-83c7-ad9a9b9e9442 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
3f918921-dedb-57f6-9fe7-a2ce3134a923 | note | iv. Cutting a groove for sealant
3a33104f-ed7c-5893-a0d2-9e7a991bf8c5 | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
b03ca746-b82e-5623-8459-e8551be9f76a | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
c6312b00-bd9e-5d61-a308-30a7884324a5 | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
1d245dc2-329b-505f-9135-09467e26cecb | note | Method - Visual, Measure
f97bf05a-530c-55bc-8a5f-bc07d141c466 | note | Frequency - Where applicable, each lot
e75c3338-6768-5b0d-b569-39298390ea13 | note | Category - IP
465a0a85-d5b3-53b2-908f-897f1bce0426 | note | Responsibility - SE/PE/SPE
4c298354-991a-5582-bddb-5303a0833a65 | note | Verifying Documents - This ITP
1c78c08a-204e-5c30-8ad5-2f985e8b30a1 | date | Date Completed:
| checkpoint | 4.5 - Isolation Joints
d85f4770-8333-5195-991c-b99ef3d200c5 | note | Reference - IFC Drawings 703.26 (c)
c49034ad-231c-5711-a4e5-ad9f121c37de | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
ed655f84-3bef-5ff5-802b-df3fa6274fda | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
816763fe-8d67-5739-b450-b097534f2a74 | note | ii. at any location marked on the drawings
556e00dc-b395-5b57-a6a6-2912ba01078a | note | ○ The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
db77ad3c-4d18-5f45-b6b9-497b53f2e8e8 | note | Method - Visual, Measure
f0549619-c033-5529-9324-2c9d40fbc1c0 | note | Frequency - Where applicable, each lot
34dbe71a-b52c-58ce-8d85-71d5f66b1b5f | note | Category - IP
b77bbf58-4758-5103-bbee-297e04fb9af7 | note | Responsibility - SE/PE/SPE
102cfa30-7fc0-59be-becf-9c66ae7e8c60 | note | Verifying Documents - This ITP
ef1b48e6-d303-5161-8f7b-94979808d2ee | date | Date Completed:
| checkpoint | 4.6 - Reinforcement Placement
8308e378-01ae-5694-8920-4c5584db78fc | note | Reference - IFC Drawings 703.13 Melbourne Water 7251/08/420
d68b1e85-1012-5191-8519-ce64b12ebe9c | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
2101b24b-b8f0-54a5-b663-5e71bdc9574c | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
a4ed0c8c-3e5d-5466-9e37-19549c617229 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
9ad68f9a-dd1c-5664-adfd-786865cc47a7 | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
d9cadece-a5e9-5787-a559-5fc80e2638ea | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
4071fb6d-2c4c-5916-a531-1bc107208b98 | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
aada9b25-0a60-5a90-b5b0-8ada5b3c8eaf | note | Method - Measure, Visual
962b5467-8790-5045-bf64-0bff9724741b | note | Frequency - Each element
043f19fe-c3e6-5d3c-b40e-9f6c8e9395c1 | note | Category - IP
3feb5d1b-f8f4-5385-98f1-0afe0739c75b | note | Responsibility - Foreman, SE/PE/SPE
f3d4073e-215d-5829-ba13-9acfd0365362 | note | Verifying Documents - This ITP
a6087e27-d0eb-5ac8-a36b-ff4de91a9aec | date | Date Completed:
| checkpoint | 4.7 - Pre-pour Inspection
a244640a-fb13-5bdd-8a5e-11fdc618ab07 | note | Reference - IFC Drawings 703.15, 703.21 Melbourne Water 7251/08/420
ca104637-bcf4-52f6-a618-cdef96323376 | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
0c7d075a-2a1b-5596-8306-234ff6301a5a | note | Method - Measure, Visual
043f2d96-4791-5ff8-bdb6-bc8d51777598 | note | Frequency - Each lot
26457566-8a53-5f6e-8392-e52ff8523e9c | note | Category - IP
e1b09f05-8858-55b5-8b08-052359e59820 | note | Responsibility - SE/PE/SPE
879202db-fff5-5206-b247-b13a64554175 | note | Verifying Documents - This ITP
395b1cf6-e685-5db6-b6fc-0f4f5dc51d1c | date | Date Completed:
| checkpoint | 4.8 - Weather Conditions & Evaporation Limits
19ca0386-37fa-5419-bce5-718cc8a9b9ac | note | Reference - 703.09
7e184674-74b7-5b97-a840-8f88e01796aa | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
3d6ce1cf-06a3-515c-bd3d-83c7fe978852 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
889ed53c-3a15-5a0d-92ac-a35d7abd74d0 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
a61203d8-38bb-554a-b4f6-087312bc6786 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
7b689208-c841-5b60-923f-7cdcf6b2172d | note | Record: Required information on the Concrete Pour Record.
62fbc996-9d37-5248-bc11-870f24382907 | note | Method - Measure, Visual
14bea358-8c47-5e55-b394-490bef268424 | note | Frequency - Each lot
60aa04d7-b2cf-5814-a143-67a45bad6101 | note | Category - IP
66c0b56e-f58d-5a2d-bbb5-893dcda751e7 | note | Responsibility - Foreman, SE/PE/SPE
ef9efe39-f788-5d7a-8528-0e170bbf0101 | note | Verifying Documents - This ITP
2f44cbe0-4a3a-5acb-afbd-4f930cf098f6 | date | Date Completed:
| checkpoint | 4.9 - Concrete Testing - Sampling Frequencies
d98ce424-59fe-5925-820b-79284d6efe56 | note | Reference - 703.11 Melbourne Water 7251/08/420
f0bee053-69ec-5c15-bb3b-0640d14560fd | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
1f5402d6-5742-55a4-a089-15cfc2f06122 | note | ○ 0m³ to 50m³ = 1 sample
446cbb7c-f234-5b85-828a-8c6b4f7089d3 | note | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
ce83dcae-45db-537b-9305-f0b8e1cf907d | note | ○ Compressive strength cylinders = 2 no. 28 day strength.
72917c0c-1f26-5335-b5d2-e1c1d65a71cf | note | Record: Required information on the Concrete Pour Record.
d280b638-70e3-5bf5-9df6-594fe023e94e | note | Method - Test
d960cea9-9ffe-54ab-b4f9-338f7d171ad6 | note | Frequency - Each lot
67288153-515d-51ad-9c14-370d5a76ee44 | note | Category - IP
8389a154-0b81-5650-9adb-0a8a913810a5 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
590d7036-5595-5244-b503-445906639905 | note | Verifying Documents - This ITP
8768c1b5-5630-5cb6-9da5-b23c47be2be6 | date | Date Completed:
| checkpoint | 4.10 - Concrete Testing - Slump
528124a4-5dc5-5aa6-8b14-c892e5e595bd | note | Reference - 703.11 Melbourne Water 7251/08/420
d423b738-a635-5cb5-9823-c8a2f6138b1d | note | Acceptance Criteria - Slump testing tolerances =
ae97dee9-a785-5d58-ae34-c30842045627 | note | <60mm = ±10mm
4331b4a6-e9f4-5d1f-9861-88a091c44b2d | note | ≥60mm to ≤80mm = ±15mm
c28eb7d5-e77b-5759-80c1-73a4c112a61f | note | >80mm to ≤110mm = ±20mm
0de3aa26-0a08-54ce-a053-495fef32d1ce | note | >110mm to ≤150mm = ±30mm
66621cdd-166d-5332-90f0-80f5351098bf | note | >150mm = ±40mm
aa738e69-d42c-597f-9eaa-c9d67023661e | note | Record: Required information on the Concrete Pour Record.
73adfe84-de97-55f9-bc2b-ebc8e8e46553 | note | Method - Test
603868d1-e59e-52a5-a820-cbc4c1015194 | note | Frequency - Each sample
5bf9762c-542b-5d2e-9431-3464cb98f6a3 | note | Category - IP
482372f1-b8bc-5677-9ba9-c9b075dd2bf5 | note | Responsibility - Concrete Tester
c929f9f5-6a7d-56f1-b423-083b550f808e | note | Verifying Documents - This ITP
0a82b0cd-cadd-52c2-a934-410c5f6d1ab6 | date | Date Completed:
| checkpoint | 4.11 - Concrete Testing - Compressive Strength Cylinders
c7ef0792-b734-5b82-92b5-a3860ddb3d93 | note | Reference - 703.11
d6e185d2-2fae-58a1-a97a-0008bdb8a69e | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
1bb5da0a-d100-5fa8-9da3-4d40e80c8589 | note | Record: Required information on the Concrete Pour Record.
8cd0bd27-870b-509b-9bd5-398e8c17bbe9 | note | Method - Test
3fb3f7bb-0b3f-5815-992e-4d202e52da83 | note | Frequency - Each sample
dc76acdd-f211-5c45-9c72-415d7f37554d | note | Category - IP
01e9c024-4d5c-5bff-93f4-59dc95ae0d39 | note | Responsibility - Concrete Tester
3b4c6965-543b-51dc-abfa-82e401ab8365 | note | Verifying Documents - This ITP
93087e4f-51c8-5891-a0bb-ad43802471aa | date | Date Completed:
| checkpoint | 4.12 - Supply & Discharge Rates
6fb3abab-a840-5754-8d04-348f737be34a | note | Reference - 703.08, AS1379 Clause 4.4.1, AS1379 Clause 4.2.3, AS1379 Clause 4.2.5
36509d34-09c7-5a82-8e8c-b397ef25dbc3 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
98aeae15-a5fa-5ff8-b091-29dc302b1dd1 | note | ○ Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
4c69807b-765d-5d8d-9265-a37526ae916b | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
6b0edb11-f3f1-523d-99d2-c87794d0d46c | note | ○ If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
6c6dbaf8-6eba-5cf2-bca4-8f2e881eb282 | note | Record: Required information on the Concrete Pour Record.
9eada15b-fedd-528b-8c52-7f427289459a | note | Method - Measure, Visual
4691718a-b21d-5afb-9b5d-eee2d82460ef | note | Frequency - Each load
c5cd3177-4560-544c-884b-c66e1755f694 | note | Category - IP
48f288f4-9b26-5926-8e3b-9b6bc4fd069b | note | Responsibility - Foreman, SE/PE/SPE
53d2e5cb-d21e-5a1f-acdd-531c6468cfb3 | note | Verifying Documents - This ITP
7daf97e5-9ba3-57c1-ad54-d32fb0a99742 | date | Date Completed:
| checkpoint | 4.13 - Placement & Compaction
b27dd459-89ef-58b0-8a82-fe5cf2063a72 | note | Reference - 703.08 Melbourne Water 7251/08/420
19b55af9-38e4-53bd-b243-07b79741c69d | note | Acceptance Criteria - All concrete batches are traceable.
7015a62c-16cc-52a0-9c6e-26b2716ca899 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
15161386-a02b-5c3f-b029-4fa966a30012 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
066766a7-cfdc-59eb-acca-5a0caa074d0e | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
92165207-171e-52dd-a9d0-274d4e4cb075 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
d410a271-e5f4-562f-8870-c184a556f7fd | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
473a5b13-44d5-5c9f-a728-f7777967efe1 | note | Record: Required information on the Concrete Pour Record.
4e150ffc-54da-549b-b679-39d8361ba6f7 | note | Attach: Concrete Pour Record
66b3af8d-e511-58cd-8f89-2fe6587a06f8 | note | Attach: Concrete Dockets
3ca341bb-3165-57e8-9d7f-dd591c06f8c0 | note | Method - Visual
2f54d2af-0eef-5ea7-8bc6-2554f3acf1e2 | note | Frequency - Each load
393d0cf6-cd84-59e1-9459-5e2a9c8351bb | note | Category - SP
5c82ce43-b46e-53be-94ed-cab8e98708b0 | note | Responsibility - Foreman, SE/PE/SPE
4fcaeb62-0176-51e3-ac14-954d3c169129 | date | Date Completed:
| checkpoint | 4.14 - Surface Finishes
c921b68a-d071-537a-9050-2635be562d23 | note | Reference - IFC Drawings Melbourne Water 7251/08/420 703.25
23c4abbd-c5f0-5199-9ab4-0aabc533857f | note | Acceptance Criteria - Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
621219f2-c9d7-5759-8917-12576a59db7d | note | ○ All outside edges of slabs and all joints shall be finished with a suitable edging tool.
6aebeeae-df98-53c7-a2a2-93bf8a7ecf3c | note | Method - Visual
f6e1ad3d-498b-5788-adfa-316b3b22cdb1 | note | Frequency - Each lot
da599b8d-3df8-5b48-8a65-cca4012bbd15 | note | Category - IP
f5c91fd6-aa06-56d4-8917-0a1d70598808 | note | Responsibility - Foreman, SE/PE/SPE
5ad6836d-3d72-5300-a56e-9464ed1322ec | note | Verifying Documents - This ITP
51663458-9de4-5f04-8924-91a9e360dc86 | date | Date Completed:
| checkpoint | 4.15 - Marking of Conduit Locations
43d5e2d5-5782-595c-956f-02f755509060 | note | Reference - IFC Drawings Relevant Council Drawings 703.28
5ea2b454-847c-5801-9cb5-ae104e82254b | note | Acceptance Criteria - The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
799a9754-1635-553f-a72f-9a0b2a360de2 | note | Method - Visual
cd25786a-0f88-5e1c-b573-55adbb306467 | note | Frequency - Each lot
f6a7c4cb-d795-5750-b5c0-f5050468af68 | note | Category - IP
8b69f2d9-8df2-5000-a0bd-3afeb25831b4 | note | Responsibility - Foreman, SE/PE/SPE
63bf04b3-d8a8-5421-8484-4c873e7f448b | note | Verifying Documents - This ITP
ebca278e-7d6d-5a1e-bc9a-5308c60dcbbd | date | Date Completed:
| checkpoint | 4.16 - Crack-control Joints / Weaken Plane Joints
7f0bdf1e-0e5a-5f38-a923-7dc5006780b6 | note | Reference - IFC Drawings Relevant Council Drawings 703.26 (b) (ii)
c090ae0b-e7b6-5792-bb49-18baaf0028cb | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
db77e76a-b06c-5ea6-9cd7-ea52c4cada4d | note | Method - Visual
dca562b6-1a21-567e-9b84-7aab3b92954b | note | Frequency - Where applicable, each lot
182e0ea0-b7ae-593b-8be8-70b045a8dc2f | note | Category - IP
44be92cb-9edd-592f-9551-5ec5370e8833 | note | Responsibility - Foreman, SE/PE/SPE
c4ee80c7-cd7d-5f25-b8b4-bd46cbd9a4f5 | note | Verifying Documents - This ITP
a960470f-d947-5cae-9006-4b0d01e203d7 | date | Date Completed:
| checkpoint | 4.17 - Curing
5c270ddd-2f04-56ed-86b2-1572a26e0a05 | note | Reference - 703.10 Melbourne Water 7251/08/420
d4c0072c-c72e-5b3e-bffc-5d3e031ce5d9 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
d213cf11-213d-51b7-a599-a9cb11650045 | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
f969856f-3815-570b-9851-9b7fe1fcdac1 | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
4c109aad-8c84-5259-8742-0b2410e2bd84 | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
da8dcaa5-a5b9-5e21-93df-de3bca9ec82d | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
7cd5f37e-38f4-5d85-b3bd-25b16b58ee16 | note | Method - Visual
ca60aa9c-bb81-54a7-9f22-8abf3631193c | note | Frequency - Each lot
d955f8fb-a138-5267-84ff-6601923754ad | note | Category - IP
96f461f2-1988-574f-8f64-ebdd8d55afb1 | note | Responsibility - Foreman, SE/PE/SPE
5cf74e6c-a932-5a62-a691-d45df054b3ba | note | Verifying Documents - This ITP
4c5ab4f8-8dc4-539b-8723-02622188bdaf | date | Date Completed:
| section | 5. Post-construction Activities
| checkpoint | 5.1 - Protection of Newly Poured Concrete
10c0234b-1833-5f35-b4d5-56c104cd3265 | note | Reference - 703.27
bdd86b18-daa5-54f9-b731-751e20a99763 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
f87b4e7a-e2be-5cd5-9398-72a15f13807f | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
ecb23cb1-d0f0-5603-bf4f-21f9818a4b63 | note | Method - Visual
0e3108a0-c1b6-54ae-bdf6-70538cbda2f0 | note | Frequency - Where applicable, each lot
3a1b5ca1-12c7-56a1-a6db-692bc69380e2 | note | Category - IP
f6f3564f-d1b5-5270-aa1e-adc24f141231 | note | Responsibility - Foreman, SE/PE/SPE
5171a3f9-7c4c-5f47-a581-7b12a04ac20c | note | Verifying Documents - This ITP
57a474ab-1eef-51a7-bf4d-7332655ffc16 | date | Date Completed:
| checkpoint | 5.2 - Stripping Formwork
a1a8f5ea-6f91-5b3a-bbe4-fe38b6901808 | note | Reference - 703.12 AS3610
522c0bd0-0645-5930-a22d-f4a5d3489ae6 | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
6fbb5c6d-e115-5695-8a36-17f2f194da45 | note | i. 2 days for vertical formwork on external surfaces; and
4251cc87-90f5-5579-8b32-f1030f8d1e94 | note | ii. 1 day for vertical forms on permanently hidden surfaces
630bd564-2707-51bd-bd2d-4cff0a3fd5aa | note | Method - Visual
3f9f9a1a-efcd-5738-8890-ebad80708f31 | note | Frequency - Each lot
af83a91c-8ac1-5449-987f-7371f975bacb | note | Category - IP
6bd31d00-a7c7-51f4-861d-b2f98512b895 | note | Responsibility - Foreman, SE/PE/SPE
f62c063e-64b2-58e9-9bae-7ce2a26100ee | note | Verifying Documents - This ITP
36c6fba7-b60c-5a7b-a795-b9b6b7255d37 | date | Date Completed:
| checkpoint | 5.3 - Backfilling & Pavement Restoration
dd7ccb08-000a-57eb-9ffd-849c40c53364 | note | Reference - 703.29
897594b7-1773-5a40-97a7-1e1977508a88 | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
50f35e5d-7192-5353-995e-abb235d1ea12 | note | Method - Visual, Measure
b493dcda-ab59-5dbc-bebf-8cd4e7b9e686 | note | Frequency - Each lot
d1429f3f-23e5-5892-8ba5-c2146150cb1f | note | Category - IP
8f7f669b-d256-5b58-8029-22d2a5b6563c | note | Responsibility - Foreman, SE/PE/SPE
0963c900-b4f1-5ba9-8881-d276e7b79294 | note | Verifying Documents - This ITP
bec9c22f-9ea5-5101-9d75-fa4febb00f6b | date | Date Completed:
| checkpoint | 5.4 - Surface Inspection - Cracks
aca1e765-8336-53e9-bf20-34af0d1eaf61 | note | Reference - 703.3
87d7b69e-ae59-5021-b6aa-7f7883ab61eb | note | Acceptance Criteria - No cracks greater than 0.2mm. If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
c43eb3b5-f8d4-5a74-8765-5af2821d3efa | note | Method - Visual, Measure
a9d67844-258b-574c-acd0-07e5d06b5a4d | note | Frequency - Where applicable, each lot
00b75b23-5265-5774-bbeb-49b96fab25ca | note | Category - IP
ee6b867d-1929-5137-867c-0119ff861870 | note | Responsibility - SE/PE/SPE
cc3c2026-c5c6-53ff-b758-e104189cb4be | note | Verifying Documents - This ITP
d63741f2-69eb-50b3-b909-0c152bb297d3 | date | Date Completed:
| checkpoint | 5.5 - Surface Inspection - Surface Finish
a8b78811-9c2e-59e0-92c5-a1c315ce3952 | note | Reference - IFC Drawings Melbourne Water 7251/08/420 703.25, 703.10 (a) AS3610 Clause 3.2
0fecb972-94bf-5d45-a9f6-15fd9071ccdd | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
2dc522be-a23a-5c55-b874-d2959aa85058 | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
6c323a7f-a3cb-5423-a5e7-cfe135e0b1fc | note | Class of finish:
8633039f-567f-5763-b2aa-7152a03c1c81 | note | Permanently hidden surfaces = Class 4
3da6f88f-de9b-5c4c-b5c3-2b4db01ab231 | note | All other surfaces = Class 3
f8e551ab-bec2-526b-ae1e-554cd5d829b3 | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
b99c5a52-7ddd-5632-a609-4fcfc5cbe91d | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
8766675d-3f84-5f13-be10-a2f986ad2319 | note | Method - Visual
4df2cbd1-2bec-576c-b6ea-6cb93e26f8d3 | note | Frequency - Each lot
5f0536e0-60a7-5786-82bc-976dd4bcde7f | note | Category - IP
8be7b73e-4ad0-54ce-912b-66bdb0037b9d | note | Responsibility - SE/PE/SPE
cb827e1a-da58-5f09-ac2f-61823e19a26e | note | Verifying Documents - This ITP
a009e4e0-626e-5291-9b10-0c2f77f43cf5 | date | Date Completed:
| checkpoint | 5.6 - Compressive Strength Test Results
c1a62914-e43e-53aa-8a1c-f5515c8516e9 | note | Reference - IFC Drawings Melbourne Water 7251/08/420 703.11 Table 703.111
b4ac3812-9c66-5151-8827-d2b8d3bc7105 | note | Acceptance Criteria - 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
0ec09cc0-84c2-50f9-af94-561277e9cbd6 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
edde4d09-be4e-515b-a472-08c2bcecd3a0 | note | Attach: Compressive Strength Test Results
182e237b-79bd-55ae-b8f4-6040d025f67e | note | Method - Document Review
219135da-4469-534f-aed6-bc74b8e44fd0 | note | Frequency - Each cylinder
5322fe31-ca18-5cd2-9e90-5d1d8fabfda5 | note | Category - IP
04cf2143-f324-59c5-b9f2-191ccc116616 | note | Responsibility - SE/PE/SPE
2388493a-6eb6-5c78-878b-a709348e8992 | note | Verifying Documents - This ITP
13131217-957f-5b87-9bd8-c8dfa66541cc | date | Date Completed:
| checkpoint | 5.7 - As-built Survey
3c30e129-fd9c-5089-ac9d-c596c8e9153f | note | Reference - IFC Drawings 703.15
8b416ff7-1d58-5659-a760-d6db554616c2 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
e951980c-76ec-50b4-893f-70ef9243b734 | note | Departure from RL = ±10mm
780aaba6-762d-5d1d-b60b-c11deb6ce60b | note | Departure from alinment = ±10mm
e42b2f86-f6db-5651-8415-32c7fd09791b | note | Rate of change of deviation from RL or alignment = 10mm in 10m
509d7b98-012e-5b6d-8579-dd7bc2cac945 | note | Irregularities in alignment = 5mm in 3m
57866689-af7b-53e1-bb79-2a8f7bfeabb7 | note | Section dimensions = ±5mm
7f0996dc-2efa-5810-a25d-555e499a4586 | note | Section dimensions (less than 25mm) = ±3mm
bb54b6ce-d5a6-54a9-a728-719f9091c25c | note | Width of pavement = -5mm, +15mm
59fb6bc8-9bb8-5773-8c4e-1c4a7e7698aa | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
e6ae771b-744f-5a12-b093-23efc741cff1 | note | Attach: Survey As-builts / Survey Report
83688ee6-aa62-58fc-819f-b752284bcf20 | note | Method - Document Review
f18a4b6e-4111-5eb7-8db3-bc5ce1fcc69e | note | Frequency - Where applicable, each lot
38dba314-bd66-5f54-8a8e-572aef000f8e | note | Category - IP
06d5c049-3e81-5870-b18e-8b164f5c1ad6 | note | Responsibility - Surveyor, SE/PE/SPE
80faa364-a96f-5dfc-b519-39c56df243a7 | note | Verifying Documents - This ITP
723364f3-9ef7-57c0-a133-703005f6bbe3 | date | Date Completed:
| checkpoint | 5.8 - Non-conformance Report (NCR) Closure
ce0d933c-11a3-52f5-8731-f5c2cd66663f | note | Reference - MRPA Quality Management Plan
44e2b881-d6f9-5b9a-9568-d0a40a4af45a | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
6820194a-614b-5438-a5e5-81126d806673 | note | Method - Document Review
1c52f84f-18fa-5870-acc6-01289750d702 | note | Frequency - Once, prior to closure of this lot / element / Work area
3348193c-6c6d-5ee3-98d6-76ccf2ebc590 | note | Category - HP*
2df30883-7872-578d-b288-89e422cdc93e | note | Responsibility - SE/PE/SPE
697f27df-2170-5b5f-b752-11ac5bc6f795 | note | Verifying Documents - This ITP
ca7b9721-1489-52c1-9fb5-a9e57506a612 | date | Date Completed:
| checkpoint | Final Inspection
8217accb-e5b9-5c67-8adf-84f47a8d9d24 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1b8e50b8-4942-5883-872c-8522a9e1850d | textbox | Name:
5077af21-7b71-5b9b-a8f9-dc425c1d7b34 | textbox | Position:
12a7bc41-a47c-574f-b3e0-43b812c9ffa3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-076-CIV-CPD-Pit 5.5 Installation Melbourne Water Rev 0 | itp | ITP-076-CIV-CPD-Pit 5.5 Installation Melbourne Water | 0a2725d8-24b0-4e13-8100-41f50f8188b1
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
e3c57628-6f1d-5176-8ae6-dc509954ac92 | note | Document Title: ITP-CIV- CPD - Melbourne Water - Stormwater Pit Suppy & Installation
2126c640-389c-5eb5-b9a3-b49d96de3f60 | note | ITP Description: Melbourne Water - Stormwater Pit Suppy & Installation
f21b8290-98d2-54ce-a429-18a093d5980b | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
aec547cc-661c-5036-a1a7-31d495cda8b6 | note | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
4fa0a860-883e-5797-b747-567c5d650977 | note | Revision Number: 0
a96f086f-a94f-5cbb-a527-db6d2a00ce0c | note | Revision Date: 19/09/2023
c7a3489d-d019-51d2-a876-9f2c756c8f78 | note | ITP created by: Ethan Caruana Smith
5cf49721-7927-57a2-b4b0-9edc6a02989c | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
b1c60354-e36e-516e-89e9-2367a6690213 | note | Reference - VicRoads Section 701 (May 2020)
| checkpoint | 1.2 - Non Dependent
c1582f87-eddb-56e5-a144-f9757517b8fd | note | Reference - VicRoads Section 705 (June 2021)
| checkpoint | 1.3 - Non Dependent
911c2c37-f545-500e-8f66-ca00898ad447 | note | Reference - Melbourne Water Standard Drawing 7251/08/416
| checkpoint | 1.4 - Non Dependent
e50b7765-f4c0-5d3a-b0a0-a760d0fcc615 | note | Reference - Melbourne Water Standard Drawing 7251/08/423
| checkpoint | 1.5 - Non Dependent
09f34d79-ebee-5ac0-92e6-bb8785ab9d0f | note | Reference - IFC Drawings - Package 36
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Precast Drainage Pit
916c2ad5-f67d-58bb-bea8-18945a1a5300 | note | Reference - IFC drawings - package 36, Gestalt Engineers pit L-4/5 & L-5/5 package
b89419fc-ddee-5e90-978f-7f9bb77b8e73 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
ec3635ea-f24b-59a7-afc7-2b7dc109eb73 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
955ac574-d421-5509-9eab-812f5ffbebbf | textbox | Enter: Teambinder Material Approval number
11ea8f81-15c9-5364-b015-38bfbe4ae685 | note | Method - Document Review
f8d01bb7-0b99-5f58-b98c-291e2513545b | note | Frequency - Each lot
105acc12-945f-5257-9d87-694951e9941f | note | Category - HP
bc0874ba-e0d4-528f-a067-bb9e77c93eeb | note | Responsibility - Nominated Authority
af01e4ce-85dc-5f69-b512-5d11cafb2b9f | note | Verifying Documents - Teambinder Material Approval
09e317a2-3c0c-5ee3-8a35-ef4b687e590b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Drainage Pit - Step Irons
f4262bd5-b71d-5ee4-bdad-976b141648eb | note | Reference - Melbourne Water Standard Drawing 7251/08/416
99c3c072-b306-59cb-bdd2-9ac1eab807c2 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
96f65e59-12a9-5f2b-8679-86af2b03b11d | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12 and Melbourne Water - 7251/08/416
2ebbc430-0582-525f-a469-d2543dcd2f2c | note | Method - Document Review
b12a083a-61b0-5c43-a25e-7a35daf967b5 | note | Frequency - Each lot
f2d297e1-0ef1-57ed-8b04-7156b71f7dac | note | Category - IP
2e9829fe-7db4-5dc1-a900-001b28095bb4 | note | Responsibility - Nominated Authority
6a0f24e5-8dcd-5b58-a015-151c2e7d3f5a | note | Verifying Documents - Teambinder Material Approval
05325922-87c1-5932-b5da-0f337c6907a3 | date | Date Completed:
| checkpoint | 2.3 - Drainage Bedding
d1028385-1953-58b9-8600-e85c72252549 | note | Reference - IFC drawings - package 36
84db88ac-cfdc-5419-bbcd-5535e751e1d6 | note | Acceptance Criteria - Pit shall be installed on nominal 50mm thick 200 Sq concrete packers. positioned at 1m centres around perimeter of pit. Underside of pit to be flood grouted with Min 25Mpa grout
8f707b6a-7810-56c9-be84-06ec8ed49e84 | textbox | Enter: Teambinder Material Approval number
e29664fe-e425-559d-8ffc-d7b42b7f7c62 | note | Method - Document Review
2703c418-8f5b-50af-ac66-e0a0140e3c7e | note | Frequency - Each lot
5412dd4c-7133-5377-b573-16982f5317db | note | Category - HP
06fc958e-d6eb-5008-b86f-214a8b75ad02 | note | Responsibility - Nominated Authority
3e703498-7bcf-5661-a15a-d25af367f904 | note | Verifying Documents - Teambinder Material Approval
f32e883d-835f-548e-be98-13000ab1816a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Drainage Backfill Material
077dfa6d-76e9-59a5-b57f-0c40b6115b46 | note | Reference - IFC drawings - package 36, Melbourne Water Backfilling the excavation - Backfilling materials 6.8.2
ee9112d2-991f-5657-a655-56c34e57835f | note | Acceptance Criteria - Approved Backfill as per Mebourne Water requirements
54aaa4ea-3197-5699-b279-428553320406 | textbox | Enter: Teambinder Material Approval number
64f06ca4-d169-552e-aff1-1fcc7ab54e83 | note | Method - Document Review
d1180ed7-ac16-5897-a4d8-37771efdfce9 | note | Frequency - Each lot
7a55992c-c732-5faf-8531-418e44d5ddeb | note | Category - HP
013f3336-3f99-57b5-91e7-df267bf2ca28 | note | Responsibility - Nominated Authority
abc5b962-894f-5644-8813-8bc2e7e4a8d7 | note | Verifying Documents - Teambinder Material Approval
8ea9b4d7-a9c4-5a59-b082-8f9429edee64 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set Out - Pits
44403e7d-36e7-518a-8673-a47aff5de138 | note | Reference - IFC Drawings
43ed44bf-2ead-5e38-bf40-6ca2e3e5bbd9 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
cf682cba-2cc7-5f35-84d9-d3ae42e89f19 | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
5e4bf08c-e956-5da3-8704-4312293585be | note | Method - Survey
f0ef9ae4-135f-546f-95d8-3ac68c503858 | note | Frequency - Each Lot
b1edd407-b7b2-5d13-938d-e54ecced551e | note | Category - HP*
129501e9-ae0f-5a37-a75f-42fff3869354 | note | Responsibility - PE
f3856a05-b8d2-5989-94ea-7774dd06ab80 | note | Verifying Documents - IFC drawings - Package 36
d491d712-c994-5b85-b9f0-bf6682acb8fd | date | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Pits - Excavation
0c2939ca-6110-5f57-9510-fa0ed08de4be | note | Reference - IFC Drawings
9e908f7f-9216-54cf-9599-e5037d6e3e5a | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
adcf51fa-4912-5ad2-9d23-573258405f8f | note | Method - Visual inspection, Measure
864f8843-2e7a-50a2-a6a0-e92fc26ea603 | note | Frequency - Each Lot
80b22fb7-6cfb-5d71-9aca-b495e05e5b26 | note | Category - IP
b59bd38f-fe0f-563f-98fb-4f7c9f0f97f3 | note | Responsibility - SE
c4ce5387-e055-5354-a4f8-fa70e84334ff | note | Verifying Documents - IFC drawings - Package 36
08b2b446-8770-57f5-b732-63ef49d15558 | date | Date Completed:
| checkpoint | 5.2 - Pits - Placement of Bedding Material
9d3fdfb1-ac2b-5155-a5a7-69a7d4dd67e3 | note | Reference - IFC Drawings
0a722592-efc2-5a1c-bfe1-0a8714045184 | note | Acceptance Criteria - Underside of pit to be flood grouted with Min 25Mpa grout - As per Design Drawings
2d06cbf4-1910-513b-b3d0-404122933261 | note | Method - Visual inspection, Measure
a3d9bb56-704a-5e7c-9f2d-a771de6fc91b | note | Frequency - Each Lot
c5469b6e-a959-5a82-8522-c79ac44b0e17 | note | Category - IP
29908fd4-1d7b-5b9c-bda9-e7c703d9a400 | note | Responsibility - SE
50e614fd-60ec-5dfe-8fbe-003c1b127616 | note | Verifying Documents - IFC drawings - Package 36
9f09e7a9-0499-583b-b778-9af0b17caa49 | date | Date Completed:
| checkpoint | 5.3 - Pits - Bedding Testing
edeb086a-cb9b-51a3-8fab-91de9a7ed353 | note | Reference - IFC Drawings Section 701.20
fdcb48a5-15ba-562f-b714-1c63d4ddffd3 | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
1e76e232-bf11-5aad-852c-96fca69f282b | note | ○ 28 day compressive strength per sample comply with the design strength.
fdcb5d1c-466c-5e7a-b096-9aa420d0941f | note | Method - Document Review
b2e12546-2bf8-52f8-83c9-49d76fee63b6 | note | Frequency - Each Cube
7307767f-a83b-5099-8d35-a9472667a1a5 | note | Category - IP
bb5ffe56-9f8d-50b0-adc9-c3f117ed329d | note | Responsibility - SE
0374d208-0ed4-5dcd-b982-77b08bc5db7e | note | Verifying Documents - Compaction test results
b606fb68-a8e2-50bf-a5a8-940ebef24a23 | date | Date Completed:
| checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
49265f6c-25d2-58de-9817-1dcf5b1012c7 | note | Reference - IFC Drawings Section 701.10
7c1d48f9-3342-5622-8b31-98980e0aecc0 | note | Acceptance Criteria - Survey pick-up to verify:
0c3d48a6-b7d8-590c-9103-da76d70d27ff | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm22
304f1a4a-fe44-52c8-a912-1ca92f8c6438 | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
aaaba0a9-dffb-5727-9e7a-69ba0a971d5b | note | Method - Visual inspection, Measure
4f69d39d-0ed2-5aee-a46d-d147532a8d7d | note | Frequency - Each Lot
6eed486a-0c24-59fb-af68-b037e5cb0427 | note | Category - IP
dc13d830-23e3-55e7-9995-4cf0343756a8 | note | Responsibility - SE
77360f2e-03b4-55f1-9ea8-908b27dae955 | note | Verifying Documents - IFC drawings - Package 36
e12d931f-52c9-517c-84ab-633468ccf3e1 | date | Date Completed:
| checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
a821cfd8-c682-59b2-92c6-8a0826f33ff0 | note | Reference - IFC Drawings Section 705.06, Section 610, Section 611
60bbfdbf-c830-540c-a37a-69ef4eb54be3 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
7e861a5e-0129-5a55-8204-953f34516f69 | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
2c6793b1-5449-5664-94ef-aa21c7f56e9c | note | Method - Survey, Measure
6a446d34-e813-5a30-921e-2c1dac2cba3c | note | Frequency - Each Lot
2736a058-1344-5baa-90d0-1400857e6c41 | note | Category - IP
654fd549-92ae-5c1a-9310-f5f8348e455b | note | Responsibility - SE
7eeae67a-9d8e-5abc-a916-664e915c5984 | note | Verifying Documents - IFC drawings - Package 36
d66f85bd-fab2-5da0-887e-cb1f0ced6c95 | date | Date Completed:
| checkpoint | 5.6 - Pits - Jointing & Drainage Connections
2dce674a-5fb9-5383-a8bb-86612e8c9c2f | note | Reference - Section 705.11 Package 36
b824a17b-09c5-5ff9-85ae-eb9de8ba9b09 | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
30101334-9fa0-566d-864a-0c8da24d2b60 | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
9ce3683e-f0fc-518c-aa0a-d4ef2bc15e12 | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
a1feba24-9afb-5d40-9b49-2b6cb40f1760 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
bebca184-6f42-5079-991c-96c6f1b2dbe3 | note | ○ Joints to be sealed with Hydrophilic seal around pipe as per design package 36.
4b0cf15a-ad84-5b24-92a8-e7ebce164a56 | note | Method - Visual inspection, Measure
792bf531-e8ee-504a-8275-dd5e554d8285 | note | Frequency - Each Lot
ebd64f91-ad03-5710-882e-9666080a0366 | note | Category - IP
003a1c47-86ff-57f5-87d8-f8ab9ac926ac | note | Responsibility - SE
0a821022-c612-5cb5-bc17-0f98284cae36 | note | Verifying Documents - IFC drawings - Package 36
f04c64af-91c5-5170-b9cb-03d8a8a5e9df | date | Date Completed:
| checkpoint | 5.7 - Pits - Shaping of Floor
7e72d152-c06f-5d38-b17d-b56e36020487 | note | Reference - Section 705.13
c6cd05d7-dc55-5bc4-9a96-b0e87032dae8 | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
d2ba10e1-ef92-5522-a325-7a87232bcdde | note | Method - Visual inspection, Measure
9b85105a-5d53-5aa0-a4e4-b33246bb398b | note | Frequency - Each Lot
0595f479-d14b-511e-b8b7-41820e44e4e6 | note | Category - IP
be0ec377-5f67-5c0b-b11d-ec2d7af17716 | note | Responsibility - SE
8ceceb39-97a6-5405-bdf7-8bcd556dab54 | note | Verifying Documents - IFC drawings - Package 36
f17c9e78-3f53-5c63-9e00-7dfbfd4092a8 | date | Date Completed:
| checkpoint | 5.8 - Pits - Step Irons
23e91028-0100-5051-94d0-8151989d2324 | note | Reference - Melbourne Water Standard Drawing 7251/08/416
5890e6ae-c811-5cb9-a285-a457550f233f | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with Melbourne Water 7251/08/416. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
344c7e26-8d5d-5567-b587-53c1ba6d3000 | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
c4506283-117e-55e2-976e-bb75448b85aa | note | Method - Visual inspection, Measure
792a3ef2-1d5b-5e3f-941a-8b22529ad790 | note | Frequency - Each Lot
6e0b096d-c919-542d-b62b-78dcf167741c | note | Category - IP
c3eeff11-96b4-5bda-8a29-7a3e77339a75 | note | Responsibility - SE
592b35cf-5310-5c79-bd99-bad19663b876 | note | Verifying Documents - IFC drawings - Package 36
db577629-f8b5-53c0-9352-b20d232ff757 | date | Date Completed:
| checkpoint | 5.9 - Pits - Fitting of Covers
b93ac3ff-7ec5-50fc-8d2b-ed08458cbffd | note | Reference - IFC Drawings Section 705.17
527ae9d1-8a2c-51f0-9b02-2edc35d8fc17 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh shrinkage compensated grout with a minimum of 40MPa.
fe1f6e96-ae34-513c-a3f4-bc2dfbd50fe8 | note | ○ Height shall be within 10mm of the design level.
63202a48-5697-5839-a2f1-4e615bbd6121 | note | Method - Visual inspection, Measure
7e10e9d7-4ae1-5ec7-9513-08b9be286ea7 | note | Frequency - Each Lot
0f41a642-6146-56c0-b159-c0428a9faeb4 | note | Category - IP
3ff2b377-423e-5886-bb01-6594d97beac0 | note | Responsibility - SE
59609a6f-eb1c-5f02-8d83-c5d1f40fd2bc | note | Verifying Documents - IFC drawings - Package 36
971584e4-f788-5b0d-ac08-5d558d374cdf | date | Date Completed:
| checkpoint | 5.10 - Pits - Pit Lids
ccab593c-085e-53ba-909c-1277188d5d55 | note | Reference - IFC Drawings
c9da3677-6f87-57d6-90dc-215335a14054 | note | Acceptance Criteria - Precast steel reinforced concrete drainage lid shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
215ef3c7-4404-52ce-8684-01064ae61caf | note | ○ Stitch pour concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
7e7164b0-7040-5b58-9fa6-9072a98dae4f | textbox | Enter: Teambinder Material Approval number
dbbd58be-9b7e-57d1-9271-c611d5cdce07 | note | Method - Visual inspection
6d3d43ce-0a23-5c70-b128-318a09c0e1eb | note | Frequency - Each Lot
f2d2a92a-837a-5131-9a55-8ed19fd70564 | note | Category - IP
2e2ab60e-6f4b-56fd-8554-e06e7234efbb | note | Responsibility - SE
ff4aba42-6003-5371-8b34-80639c8be7c3 | note | Verifying Documents - IFC drawings - Package 36
e95b3511-6858-5c8e-a03d-87570cd32326 | date | Date Completed:
| checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
3849641d-55c9-5533-b6ce-c773309f351f | note | Reference - Section 705.18
cbc770d7-7fad-5e19-acc4-70b362fa0af5 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
e5ebce4a-4bf1-5b61-9cd4-233e12d39967 | note | Method - Visual inspection, Measure
74da5057-2526-544d-b0f5-a8ba8d377f00 | note | Frequency - Each Lot
f627b31f-60b8-5858-8649-855056204491 | note | Category - IP
b575ce71-1bc6-5cca-9f2d-32cd4bd95fe6 | note | Responsibility - SE
5e053d9e-924b-571d-bfb5-f485c2c755f4 | note | Verifying Documents - IFC drawings - Package 36
aa4979a4-b2af-5dbf-a54b-d37026013fcd | date | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Flushing & CCTV
00fc293d-c1ea-5633-8433-ef4eec3f6fd5 | note | Reference - Section 701.28, Section 701.30
5dfbbb0b-0640-5524-a257-2927b5a48eaa | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
4f448fa6-dd25-5fc3-93a9-df7788916945 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
7bef5cec-511c-5ff0-8b2a-93c520d49c9f | note | Method - Record Review
ff82b506-1571-5f3e-9d50-895ec5a71390 | note | Frequency - Each lot
eb6ad45b-4433-54b3-8576-c6f735536b42 | note | Category - HP
5357580b-c037-5e0f-9445-6dac4ddad293 | note | Responsibility - Nominated Authority
ea6a56c5-1534-570f-92e8-7ef56b011993 | note | Verifying Documents - This ITP, CCTV Reports
21768c77-37db-5fc0-8ad6-a9ec07e0592d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - As Built Survey
0d3a93da-4d59-50ef-a553-58a5d372bfe7 | note | Reference - Section 701.10
b6004005-e051-5701-88e8-c03ff278f20b | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
0c008f5b-0ed7-561a-a6a4-ed88b4130b28 | note | Method - Document Review
4e8b22d0-6beb-5f8f-b2cd-fe38659b8ab7 | note | Frequency - Each lot
4e14d7ba-5764-52c0-9223-25ee5c8d8668 | note | Category - IP
db84c2fe-bfd7-5c59-bbe6-0f09f41bc889 | note | Responsibility - SE
44741c84-6599-59ad-aa7c-10dd5d0bc144 | note | Verifying Documents - This ITP, As Built Survey Report
9b6fc855-0afa-5117-80c1-ee3b387bb112 | date | Date Completed:
| checkpoint | 6.3 - Repairs to Damaged Pipes
47e63eb7-a673-5d00-8340-904650116602 | note | Reference - Section 701.31
204eadd3-dbfa-59f7-8d06-046e33caa5ac | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
353ee942-97ad-5ce5-b8d6-039aba0d6c02 | note | ○ cracks wider than 0.5 mm
733c914a-5197-5d44-9abc-da3fd9f8eec5 | note | ○ spalling of concrete
e5127832-790f-5d19-b5dc-7782d3f97aa9 | note | ○ exposed reinforcement
68508e22-687d-51d7-b5cf-8b1d85a991b0 | note | ○ joints that are not fully engaged.
5ce724aa-1930-50f7-bd09-12dd54787103 | note | Any pipes with defects greater than the following limits shall be removed and replaced:
718a06a9-63e3-5a24-98e2-d413cb3da936 | note | ○ longitudinal cracks greater than 2 mm
f28ea585-511d-5147-8e9f-a2f02b3ae403 | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
b4f0bbe8-4827-5f79-b63c-3e9ac1d7a28c | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
042c0268-deaa-5ecd-96d2-84f64b5c264c | note | ○ penetrations with area greater than 400 mm2
1680f01b-0606-5410-af2b-fff3fe955975 | note | ○ pipe joints that are separated.
85202bbb-cbdd-54fa-8c23-5815e0f5eecc | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
4320244c-d23e-5a2b-9dc4-da4ccb4f5030 | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
6fcd0fa0-9aa1-5efc-8a48-49ba15569a60 | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
7debf01f-fbbc-5fbb-a624-89c4965c490f | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
72848237-dd25-5c20-bea4-572f5490c11f | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
dba2ad52-16e3-5d05-a180-04fe36485fd9 | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
52a3042b-e040-5229-81cf-88ea6a8eec3b | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
79393559-fe44-50bc-a0f0-669d81d86dbe | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
5a2c58c8-d4b1-5f62-ad5e-517a03ea044d | note | Frequency - Each lot
2c5e6869-2a4c-567c-bb5b-f7d7b15d84dd | note | Category - HP
03e18a58-6221-555a-a5e0-7022ffec217c | note | Responsibility - Nominated Authority
a1908a99-f184-5705-b770-0ba9bbb2d365 | note | Verifying Documents - This ITP, Approved Repair Procedure, Post Repair CCTV Report
61a78237-f062-5551-a42d-46d4513bfffb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
6510898d-7156-5763-a7bd-cc18a4a8ef88 | note | Reference - MRPA Quality Management Plan
7246bc90-d17c-5a37-b3b9-3d7d8d0d6d92 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
b62856b6-f612-5c90-9e9a-747f6889d636 | note | Method - Document Review
db5ef82d-dcc4-553d-a499-ae1ad56808d8 | note | Frequency - Once, prior to closure of this lot / element / Work area
1cd2fada-45ac-519a-9d24-2f9641d77d81 | note | Category - HP*
c7b2066d-d46a-599a-8f75-d3c326c4db5f | note | Responsibility - PE
9d984508-5682-554d-837e-d7bc3ee4e041 | note | Verifying Documents - This ITP
6e66ac83-4a21-53a7-a2d3-be8585712d11 | date | Date Completed:
| checkpoint | Final Inspection
a00f6dde-44b4-54bf-9300-b9e9ab31af0d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c6e3909e-fa5c-58a3-b844-355e4dff5acf | textbox | Name:
668d9d76-dd00-5f70-ad8c-b5aaa6e7ff21 | textbox | Position:
b39d604f-5e64-5528-9a9f-9acf8bacb1cc | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-102-STR-RSS Wall Main Rev 0 | itp | ITP-102-STR-RSS Wall Main | da5eeacb-db22-4790-b6c8-27e706de65ff
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
f6416660-44c7-5779-b6ca-913cc18d8029 | note | Document Title: ITP-102-STR-CPD-RSS Wall Main
91c07c9a-c670-5f63-8269-75ddb5132189 | note | ITP Description: CPD-RSS Wall Main
ddc2e889-e5d9-5ed4-ae61-d1fca5036399 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ee9c28d7-05a2-5daa-84d0-9394778f3fdf | note | Discipline (e.g. CIV/STR/RAIL): STR
f2ee3417-c9f5-542c-b13f-fe1ce928afea | note | Revision Number: 0
a7a2c228-f1c9-5fc8-bb5d-1559f258a6c9 | note | Revision Date: 09/11/2023
b5578fa3-a3f1-5f2c-86e2-6c7ef654d73c | note | ITP created by: Matthew Dib/Jason Quan
c515b9b8-4f43-57f8-9d41-ec84fcfb420c | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
2def75d5-310e-5d44-83aa-26b0bedc8b7b | note | Reference - VicRoads Section 682 November 2018
| checkpoint | 1.2 - Non Dependent
31911aca-dac9-57c9-aa3e-939895d4f9df | note | Reference - VicRoads Section 204 December 2015
| checkpoint | 1.3 - Non Dependent
5d592d65-53f3-56ff-8691-3d441b3983ee | note | Reference - IFC drawings
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Concrete-Leveling Pad
8a0363bb-545e-5f9d-830e-a843736fc7f6 | note | Reference - IFC drawings
985767b3-9946-5ef0-9ecb-bd1a0320aacd | note | Acceptance Criteria - Concrete compressive strength grade must not be less than N25 for levelling course and backing blocks;
8eedd003-4cef-5797-b372-893488c4e7ea | textbox | Reference: Teambinder MA number:
d8434fcc-b9bd-51ad-a618-2390ea781b12 | note | Method - Document Review
beb745a5-5e09-51c2-a29a-950a73dbf176 | note | Frequency - Each element
3d6fbe01-aa97-5497-ba72-63db28462577 | note | Category - HP*
88d002f7-7121-54dd-aebf-f2e9c73b44ef | note | Responsibility - PE/Nominated Authority
55978f6d-9721-56a3-bb69-54859ca22fef | note | Verifying Documents - Material approval
4da07b9d-a629-5e49-b6e2-b9077aeb0be4 | date | Date Completed:
| checkpoint | 2.2 - Select fill
3ded5562-5a87-576a-90b7-dc63dcf5b35e | note | Reference - IFC Drawings VR 682
8b8ae7fe-27cf-5e24-9a19-9ec11646f527 | note | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
72270269-06d9-55a3-8f3d-66abb07c052c | note | ○ UNIT WEIGHT (Max): ≤ 16 kN/m³
c1e2666e-ba9e-5d10-a4d4-d36c492ccba4 | note | ○ COHESION (Min): ≥ 0 kPa
0472e86e-3a5b-5607-b02c-4522c8478e91 | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 36°
695c7f44-8a3a-5349-881b-f9c1cd16fdf8 | note | Gradation:
fff0eea0-6aaf-5cd4-b467-6882652254c0 | note | ○ 150mm : 100% PASSING
6cd73d49-9e6b-5110-94a8-2d241d0e976c | note | ○ 37.5mm : 60 TO 100% PASSING
28843e24-e9a2-5184-bed6-62da1e98bc34 | note | ○ 9.5mm : 25 TO 100% PASSING
5fd28a37-a11e-553a-bcd8-e4cf1e6d8a40 | note | ○ 2.36mm : 15 TO 100% PASSING
6dda1d4f-9b32-5c5e-a851-0d33c712e700 | note | ○ 0.6mm : 10 TO 100% PASSING
f1366295-5587-5f66-b712-afe4a7c3e281 | note | ○ 0.075mm : 0 TO 15% PASSING
032e8721-eb61-5ebb-ad9e-08d647ab3a00 | note | Electrochemical Properties:
4edd9d38-fc68-5de8-b375-234b6c1b4908 | note | ○ pH: 5 - 10
bcb194f6-c795-5e9d-9c10-0255ee3fed2f | note | ○ RESISTIVITY >1000 Ω-cm
cd2bf118-d3b4-5e09-81e6-601845540743 | note | ○ CHLORIDES <200 mg/kg
7c26dc2c-729d-524e-9d4b-0b0a145aab2e | note | ○ SULPHATES <200 mg/kg
98863680-2c15-584b-81c4-68a05bfe3ea5 | note | ○ ORGANIC CONTENT 0%
3149739d-66d8-50f0-9f5a-cd4427feb150 | note | Structural Properties:
c509e7bb-060b-505c-ba8d-889760462e4b | note | ○ COEFFICIENT OF UNIFORMITY ≥ 5
bb8bc0ae-5ea7-5955-b4d9-b7b102cfbbf8 | note | ○ LIQUID LIMIT ≤ 30%
bbaeaafa-3dae-5b4d-bd29-153f72d0649b | note | ○ PLASTICITY INDEX ≤ 12
b5d1774e-a1ed-5f72-9dbf-fbbab37f9a20 | note | ○ The select backfill must meet the minimum requirements of Vicroads Type A filling
cae1100c-2512-5fc4-840e-c0dfa10eae34 | note | Reference: Material approval in Teambinder
8d90fffc-23ef-52f8-8675-d4bf295c070e | note | Method - Document Review
44e3ba5e-cae9-5666-8623-2ada9be65902 | note | Frequency - Each material specification
0d390af3-3b5b-5580-b316-3d657525ad6d | note | Category - HP
4b78af60-c2a9-52d2-9050-fd965e5ab6a9 | note | Responsibility - Nominated Authority
dcf4753b-9f97-52a0-920e-9e5c0cc352cd | note | Verifying Documents - Material approval
e7df57bc-ff43-5962-b5ed-c7e60e26d4f8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - General fill
f52822f9-0ed3-5227-ba23-2404ad0ba99e | note | Reference - IFC Drawings VR 204
225a0a2d-4d33-5854-a6cc-074f17594d2d | note | Acceptance Criteria - Backfill behind the reinforced block shall be Vicroads Type B or better in accordance with Vicroads standard specification 204:
481894bf-bc43-5691-8c04-67cdc3c122c1 | note | ○ Select General fill shall comply with the requirements of the RSS designer (RW05-RW06):
b72605e7-26cf-5593-9800-7031ad01e164 | note | ○ UNIT WEIGHT: ≤ 19 kN/m³
95666c3b-eeab-5fa4-8dbe-52b5db960ef6 | note | ○ COHESION (MIN): ≤ 2 kPa
66fc399b-3dfd-5b42-9d2b-884f4ee14ecd | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 30°
b3831307-3dcf-5970-8995-7e175fc7a266 | note | Reference: Material approval in Teambinder
d88a87f0-77ea-51d8-a1b7-3874c0958c40 | note | Method - Document Review
8cd5de8e-aef6-57bd-9771-4d5e2bdd1eb7 | note | Frequency - Each material specification
664d4530-9266-58c6-8fbe-91324f04d008 | note | Category - HP
4e152af4-075a-5221-bec5-ddbf62220a73 | note | Responsibility - Nominated Authority
0fbbf8f1-fb1e-5e1e-ae0e-b32e796bf33a | note | Verifying Documents - Material approval
b05bca9e-c008-5b61-a40e-144e681880a4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Perforated Pipe-material
301ae42d-c64c-5e32-acd0-f59715ca2660 | note | Reference - IFC Drawings
5561e744-a5fc-5afe-b2e1-13e538df6ce4 | note | Acceptance Criteria - Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
b6a3dc0a-15aa-57e7-af8d-242809fd3168 | note | Reference: Teambinder MA number:
6c95df93-5d75-53d8-968e-7e07b86bc046 | note | Method - Document review Measure
de7646ba-e1e0-5465-adfc-3dfc973d77df | note | Frequency - Each wall
7bf5ef62-fc84-5634-8177-dbc3d0036258 | note | Category - HP
b0f83887-31b8-5f12-b61b-678e6204487f | note | Responsibility - Nominated Authority
5ddcb906-5eb3-5e06-bcd1-c565bbac8709 | note | Verifying Documents - Material approval
3bbe7983-fa5a-5023-8c31-0779067e082f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documents
| checkpoint | 3.1 - RSS Panels
02482ce7-24da-5402-8f81-7d3b5142ef03 | note | Reference - IFC drawings
739d670c-e6ce-5aad-9f20-cfdae2f72967 | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
5b2ab3c5-852d-50c3-ad58-dcd87da74bd7 | note | i. Certificate of Compliance / Birth Certificate
9cd1ce78-f519-592f-be14-f33db81cb26f | note | – 1. Concrete strength;
9739040d-3045-5b6c-9332-a89c8b8b0277 | note | – 2.Date of manufacture;
fdeae804-b199-5feb-92b7-21d9c7afccfe | note | – 3.Unique Identification number;
878059be-fe8a-5a21-a597-935fcfb4cae8 | note | – 4.Mass;
7ac6cedf-06fa-50ae-bcc6-b2cd67d1516d | note | – 5.Confirmation of number, type and capacity of lifting inserts;
77e7856e-a19d-5a0d-9998-829c4c259912 | note | – 6.Quality assurance sign-off.
0bc6dbc0-6973-5a93-b1be-39f36076c50c | note | ii. Compressive strength test results
554405d2-8808-5422-9a9c-eae07d6d1b1a | note | iii. Precast Lifting Design
bdddeab2-3386-5990-af69-723b44a99894 | note | iv. Pre-pour check sheet / ITP
52399325-3421-5750-9475-3983f5565339 | note | v. Post-pour check sheet / ITP
ee7b6ffc-be4d-5da6-bc5a-5216c48ed4db | note | vi. Covermeter check record
1f941374-83e8-5946-a0c1-c5ce2f661818 | note | vii. Record of dimensional measurements
c41cafed-bee2-52b8-8337-94b8c8662fdb | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
77674e63-24f0-53df-9f28-9868bd45e910 | textbox | Reference: Precast panels MDR Lot in TeamBinder:
ce14dd84-b1f1-5c71-a32b-754d00c95bb8 | note | Method - Document Review
407009a9-f554-52ae-a945-276158c59005 | note | Frequency - Once for each type of panels
8cb3594c-9a84-5b72-870c-d167eecf1615 | note | Category - HP
022a492e-40a5-5580-a703-ad7fd8abac5d | note | Responsibility - PE
c9ec7aa8-ab9e-57d6-a82c-f9e3e414844d | note | Verifying Documents - Precast panels Birth certificates and MDR Lot
56790282-28c8-577a-ab63-1b2d4d0c368d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Foundation
acb670cf-3fd5-5e14-a0ee-2bf50b19e738 | note | Reference - IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007, MRP-080-C-SME-DRG-34-CPV-CSF-3012, MRP-080-C-SME-DRG-34-CPV-CSF-3013
410e0616-1ab2-5829-84f9-e162915a72ea | note | Acceptance Criteria - Foundation material under RSS shall adhere with minimum design bearing capacity.
87a1ec6b-4412-52f5-8931-4831069d206d | note | ○ RW2: 150 kPa
a85f4dda-83f3-516b-9a92-54f481d59bd4 | note | ○ RW3: 200 kPa
cc2cad46-bec4-57c3-a91d-5f78066af540 | note | ○ RW4: 200 kPa
16902fb9-7516-5840-b7f6-250aa0001ce5 | note | ○ RW5: 250 kPa
4b4f0d2c-53fb-53ca-81eb-302419aee36c | note | Method - Test, Document Review, Visual
3c7d0e60-7398-5582-b2ee-8902c476489f | note | Frequency - Each retaining Wall
4da1cda0-a5ad-53a4-87e1-eff47361c08a | note | Category - HP*
6d97841b-276b-55e4-a450-ae703fd21bf3 | note | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
4b52cd11-bb1a-5e2b-a4b1-d96990706fae | note | Verifying Documents - This ITP Signed off, Test results
53339517-6403-5f12-8b79-1d6e4ae33a45 | date | Date Completed:
| checkpoint | 4.2 - Foundation
1d175881-2ff6-572f-8673-62c1ccba2b4f | note | Reference - VR 204.12, VR 204.11
f2b63a55-8346-5cd6-9a0d-59f782108a19 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173. No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
fcd5e6b0-68a2-53cd-9a05-c24412f7d9fa | note | Method - Visual
69661b69-68a6-54bb-af3c-fef858e9b711 | note | Frequency - Each retaining Wall
6d84f289-4e25-5fe9-8991-3408ef0c6a09 | note | Category - HP
38773d48-2b2b-5afe-8855-e37ec7485fe9 | note | Responsibility - PE/Nominated Authority
00374869-0578-5a21-a7a4-3a2f71ae9f8d | note | Verifying Documents - This ITP Signed off
8247d857-acfe-5565-a01b-d15f7a5f3102 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Levelling Pad-Survey Set out
8e04f549-681d-54f1-ae4c-dacd5ad0bead | note | Reference - IFC Drawings VR 682.20, MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205
7c7a221f-c077-59f4-b6e7-46d0444d9ac4 | note | Acceptance Criteria - Survey to set up and validate all works meets levels and locations with the right tolerances as per IFC Drawings and Vicroads Specification. Levelling course level shall not deviate from the specified level by more than +/- 3mm
066621d1-2e50-5a41-969e-243907b547ec | note | Method - Measure, Visual
76154bb0-a254-5d9e-ac52-3c2ca370504a | note | Frequency - Each retaining Wall
5c55c148-72fd-5395-8810-3f7fee3ebe85 | note | Category - IP
df6d9aee-248c-5be8-866d-a858f9ed6174 | note | Responsibility - Surveyor, SE/PE
b1563a43-002d-5f3c-bf04-3cadca848518 | note | Verifying Documents - This ITP Signed off
c7cb9c18-c4cd-556b-ac05-496de7165f42 | date | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Form Levelling pad
8b10c758-5970-5044-937d-c35759210845 | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205
47dd3a6c-5565-5a3a-8e85-949d61f943a2 | note | Acceptance Criteria - Form timber shutters or Earth form to edge of levelling pad
c4959613-2db5-537b-a353-2e094824a1a5 | note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
7d047857-c78b-5c3f-b099-125178a94bff | note | Method - Measure, Visual
134a063a-980f-5413-8757-0db9978bcb18 | note | Frequency - Each Lot
94bcc02c-c411-549e-b83f-f38699457814 | note | Category - IP
1f406090-a8cd-5847-b5f9-1aa7b1b67787 | note | Responsibility - SE/Site Supervisor
31a40388-c323-5690-b252-91bee2312bf0 | note | Verifying Documents - This ITP Signed off
e373f9ce-3f80-5ba7-86f4-68ceb9af0417 | date | Date Completed:
| checkpoint | 5.2 - Leveling Pad Concrete Pour
614a3988-40ff-50a2-8837-41af317b29ce | note | Reference - IFC Drawings VR610
b381b487-d2d8-5ffd-928d-f167d1902711 | note | Acceptance Criteria - Concrete to be placed in accordance with VR610.
bbd86c96-f9fa-5cce-9e5b-270d28bcbeac | note | Attach: Concrete Delivery Docket
707ba3ee-ccd9-5165-b617-6df234a784bf | note | Method - Visual
8445b6d8-410e-5635-afe1-3816b547657d | note | Frequency - Each Lot
12fb176c-5197-5b28-a9ed-21d03578f449 | note | Category - IP
8eecf2cb-80b5-5228-ad57-feec9a670d28 | note | Responsibility - SE/Site Supervisor
7aa20989-f933-5850-8491-a92ba3bb5936 | note | Verifying Documents - Concrete Pour record, Concrete Delivery Docket
b4b42449-a834-507a-bb44-1acc0c6f83b6 | date | Date Completed:
| checkpoint | 5.3 - Leveling Pad Concrete Testing
65d049fb-0d74-5ef3-a5f3-a4e054d35a1e | note | Reference - IFC Drawings VR Section 610.16 (b)
5341df0d-2628-5b15-81ab-db9e2504bc5b | note | Acceptance Criteria - Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
8fa3486a-d4dc-5c25-b52d-888458145384 | note | ○ Concrete strength (Min): N25 Mpa
80589885-c02c-55de-81fe-77c51f95238d | note | Attach: Concrete test report
76d74232-9178-5dc4-b30a-512265299d2e | note | Method - Document Review
2b79629b-e428-5b84-8bb8-7935d9bb4904 | note | Frequency - Each Lot
dadb7b20-1925-5bad-aa1a-c38a92a3f07f | note | Category - IP
3589530b-f0eb-54e1-ac83-24adcdc02337 | note | Responsibility - PE
73a32238-3b4f-5dea-b908-157a41f0c595 | note | Verifying Documents - Attach Concrete Test Report
7c0cb9be-1d43-5708-a704-00fd1cb8a888 | date | Date Completed:
| checkpoint | 5.4 - Levelling Pad-Post Pour Survey-Levelling Course
1788d0e9-ecaf-57e0-878c-ca07ba956970 | note | Reference - IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205
745b8f3e-ecdb-5fe6-853a-d284702d524f | note | Acceptance Criteria - Levelling course level shall not deviate from the specified level by more than ±3mm
5a403c9d-3e34-5af8-a801-62275639a190 | note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
4e1cb190-e451-5fc9-8b71-51a0d04cf5c4 | note | – Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
7b3eb44c-c639-5017-a72d-adca738576f8 | note | Method - Measure, Visual
41ea2075-c45d-5558-b605-f3fceb0aeeaa | note | Frequency - Each retaining Wall
85d85d78-46df-5b73-a75f-036581d42c94 | note | Category - IP
a4d42980-bb8d-5947-b387-c24672e1b603 | note | Responsibility - PE/Surveyor
5a86b060-ccab-5524-b247-60e6f1e79256 | note | Verifying Documents - Attach Survey Report
699c987b-831f-5ffd-a87c-b897fa9ef9c1 | date | Date Completed:
| checkpoint | 5.5 - Wall Panels Installation
e38ace6c-a84b-57a9-b1bb-c077b5644c3f | note | Reference - VR682.17
a843f47f-00ae-5b4a-ad3a-1962a2427e78 | note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
d9b80e58-ff32-5a86-a8ba-badc9cdc3b27 | note | ○ Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
745b30ae-298b-5944-8923-f4caa19833c4 | note | ○ Refer to checklist for each course of panels
2c838cb1-197c-5abd-abbf-e094f6d2025d | note | Attach: Lot map
1d1f42e0-712d-506d-9d0a-ae42f2490af4 | note | Method - Visual Measure
5f228282-3a72-5d42-bf58-6dd884022eb3 | note | Frequency - Each course of facing panel
464ac046-3212-5f2d-b385-afd9070230d1 | note | Category - HP*
82eadf45-12db-52f7-a291-4fd1d7eb7048 | note | Responsibility - SE/PE
fdbacf2e-e41a-5aee-9960-b81ab75420ab | note | Verifying Documents - Inspection record checklist: CHK-008-STR-CPD-RSS Walls-Precast Panel installation
1e05f5c6-a080-5a28-8839-b3612fc63849 | date | Date Completed:
| checkpoint | 5.6 - Drainage-base of the Wall
8fffbeaa-6797-5b5b-a607-2e2edb045734 | note | Reference - IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3031
f2bb8b91-d785-5994-ace9-96c3846cf3c9 | note | Acceptance Criteria - to install 300mmx300mmGranular backfill in Geotextile BIDIM A24 around 100mm Dia. Perforted plastic pipewith 0.5% min fall to weepholes in RSS panels.
1c83db86-93c7-5a8a-9f14-b0f4837c470b | note | – Geotextile BIDIM A24
06e95dfb-8d58-56dd-b8b4-b2f1934f9f18 | note | – 300mmx300mm Granular backfill
60a52c94-e505-57df-bf40-ac2d8d13e6c5 | note | – 100mm Dia. Perforted plastic pipe
7be5ba29-6063-5db7-80dd-f7e984116884 | note | – Perforated pipe to have 0.5% minimum fall
a42da700-ce33-5aa3-aa70-d0736181bcae | note | Method - Visual
94e8dc71-671f-5c85-83a7-511947d0e5a6 | note | Frequency - Each wall
13c82418-6a34-531e-815d-613e2179f6ed | note | Category - IP
405e8a44-5ba4-5de2-9256-8c17c66ee5b5 | note | Responsibility - SE/PE
1fa42912-8311-5ca8-ac53-8f9964482d8b | note | Verifying Documents - This ITP Signed off
3a65987a-f6aa-5838-a7b6-18184004f725 | date | Date Completed:
| checkpoint | 5.7 - Fill
4c39f14f-83ad-5668-a3ad-66287f7719c0 | note | Reference - VR682.16
be39dc12-7412-5de3-babb-50b0ab12902b | note | Acceptance Criteria - The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
79b871de-242e-5ac8-916e-6bba4093f658 | note | ○ Refer to checklist for each fill layer
d606adfe-54ac-5fd4-ae58-66ddda053020 | note | Attach: Lot map
e462a55f-1357-5fa5-94fe-ff2c1b6c2b2b | note | Method - Visual, Test, Measure
4b17adb7-27a3-5fde-9f2f-13509428243d | note | Frequency - Each layer of fill
99e6e588-29d5-59f9-b15e-0c463da4792b | note | Category - HP*
8e627a26-5e17-5aa0-a0f8-f8c286d5829d | note | Responsibility - SE/PE
02cd0653-492e-527e-9f58-1a4980453a02 | note | Verifying Documents - Inspection record checklist: CHK-009-STR-CPD-RSS Walls-Fill Placement
00a06841-3c52-572f-a060-faa15d91f6df | date | Date Completed:
| checkpoint | 5.8 - Settlement Monitoring horizontal inclinometer
2e1ea935-df0e-5482-b3bb-ba66d809c6a2 | note | Reference - IFC drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007 VR 682.15
10d0a8c3-50d5-5658-92ee-faac1bdb4e93 | note | Acceptance Criteria - Survey Pin and Inclinometer survey procedure us as follows:
c66e2329-8af2-5008-b1a6-f72adbbed9dc | note | ○ Inclinometers shall be installed prior ro placement of any fill
70b2dc8d-b2dc-583d-bfd0-6d7b8e8bbaaf | note | ○ RSS Wall and abutment wall survey pins shall be installed immediately following construction of the first level of RSS wall/Abutment wall and prior to any fill placement
6c7c99f3-d0fd-55dc-8185-736451c22ee8 | note | ○ Traffic barrier survey pins shall be installed following construction of pavement and barriers
770c0a8c-40f2-5fc5-b38f-fe524f6a1780 | note | ○ All survey pins shall have appopriate stick-up from finished surface level for continous settlement throughout construction/post construction
b9261bcd-c401-5f39-8cb1-05591767e950 | note | ○ Pavement construction shall not commence until monitoring from inclinometers and RSS wall/abutment wall survey pins indicate ground movements have reached at least 90% of construction settlements and confirmed by the geoechnical engineer
d498b2eb-f201-512f-accb-34e60c7c9789 | note | ○ Settlment Monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) unitl settlement stablisers or advised by the geotechnical engineer
84b6f22c-e774-5057-8f67-0f276d0e46b6 | note | ○ If at any stage prior ro the to the completion of the RSS placement, the total settlement exceeds 50mm, fill placement must be suspendedm and direction sought from the design engineer.
df77d2f8-a62c-5913-8aee-515960910b4a | note | ○ Survey pins and horizontal inclinometer shall be installed to monitor ground movement throughout and after the RSS wall construction.
dc90afc2-be1b-532a-a70d-b92ddbadb55e | note | ○ Only hand operated equipment shall be used within 1m distance from inclinometers
40d4c93a-cecb-5ab0-a312-cea03855000b | note | ○ Geotechnical instruments shall be preserved and protected for monitoring until the conclusion of post construction. Damaged or malfuctioning inclinometers shall be reported and replaced where possible.
81de2609-af80-5b7e-8537-3538b1f4d06e | note | Method - Document Review
9f8e254e-2ebf-52a9-891b-ca4ac48e37ae | note | Frequency - Each Inclinometer
4ac076d1-5749-5953-9b38-a90207cf5867 | note | Category - HP
f46ea647-3411-5f3b-95e5-366faf076d7c | note | Responsibility - SE/PE
24f82a38-0912-5de9-bd63-57b12d674b0f | note | Verifying Documents - Teambinder approval
e9f659a3-da02-58bc-aa96-e7e5985e210e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
7c362dfa-70c2-5ac5-a36f-2ba48388d0ff | note | Reference - MRPA Quality Management Plan, IFC Drawings
1bbad82a-2b7b-5f7a-8ccb-47a568286dcf | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings.
7bc5895d-b2bb-5c12-bb1a-2d25b206863c | note | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
abb45417-91b0-5c54-962e-8e41616c7bb9 | note | (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
acf4ac3b-f471-55be-9f8c-f47f85b9529e | note | (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm;
ece30a9f-b0c6-5118-b3de-30ad532d3525 | note | (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height;
e8d40f04-a621-5bf4-9f1e-7ffebac933d6 | note | (e) The wall level shall not deviate from the specified level by more than ±20mm;
f22f81c2-774d-5f4a-b38f-86e6c4a91bde | note | (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap.
b1739066-a03f-511e-98da-c32608acbe86 | note | (g) The levelling course level shall not deviate from the specified level by more than ±3 mm;
564abc57-5b98-5257-9e7c-e22ffe14cd33 | note | (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise
c7f2456c-37ad-5fb6-81b4-ef26a711f2f4 | note | Attach: Survey As-built / Survey Report
efe76cb0-840a-503c-bcc2-e4abe62a16cf | note | Method - Document Review
0c2447b0-2769-5cae-8600-34afc07e3622 | note | Frequency - Each element
10a980df-843f-5f61-897e-e7d571d38cea | note | Category - IP
b449445d-4188-537f-b2aa-d8b6654ac822 | note | Responsibility - Surveyor, SE/PE/SPE
1320a2b1-68e4-5765-958d-33203e7a624f | note | Verifying Documents - Survey Report
d9d4a5df-7485-5bda-8c7e-c210931c5cec | date | Date Completed:
| checkpoint | 6.2 - Wall Post construction monitoring
539b174b-0ee7-5424-bf2c-e16b65b7695e | note | Reference - IFC Drawings VR 682.20, VR 682.151
ad6917af-f2b1-5a52-b7ea-8f10ee46203d | note | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
e3bae21a-3934-5b79-a376-109bc7f9e526 | note | Method - Measure, Survey
c7e5be72-f95e-57dd-a497-986efc80bcb7 | note | Frequency - Each wall
62a8c277-0b9e-5570-bf73-d7773ee6ade9 | note | Category - IP
aea8bc91-8ec6-557d-8b8c-8f10bd2e0ecd | note | Responsibility - Surveyor, SE/PE/SPE
03231913-6223-52bf-a8d4-0de8ac6c3441 | note | Verifying Documents - Survey Report
74515ab0-9fae-5189-9bca-d94a9449cf9b | date | Date Completed:
| checkpoint | 6.3 - Settlement Monitoring
b8911b72-8218-5036-a046-f37017f8c2f7 | note | Reference - IFC Drawings VR 682.15, VR 682.20
4c952ec2-9cca-527d-a67a-1829c565fc36 | note | Acceptance Criteria - RSS wall base level:
3b4d0f97-5d83-5236-8866-55ce82ae2385 | note | – Start of wall construction to completion of wall construction (before pavement placement) Approx vertical settlement < 20mm
09a63d85-11fa-5f2d-af86-30aa7002160c | note | – Completion of pavement construction to end of defects liability period (2 years after practical completion) Approx vertical settlement < 15mm
fc5312aa-bffd-551f-adfb-250cd6ab95a6 | note | Pavement level (Top of RSS wall):
8224fda1-fc31-5b06-8a1a-31a2c9d24430 | note | – Start of Pavement construction to completion of pavement construction Approx vertical settlement < 20mm
aef4a9f2-ddef-5caf-92e2-fe3b6ba8887e | note | – 10 years following practical completion of payment < 50mm
7abd0441-1349-5a2b-b24b-691eaf351019 | note | ○ Settlement monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) until settlement stabilised or advised by the geotechnical engineer
8574507f-c4bc-5590-ad32-51749c9edcae | note | ○ If RSS fill placement total settlement >50mm, fill placement must be suspended, and the mitigation method reviewed by the superintendent and DTP before recommencing fill placement.
9310ee61-7d95-5171-9f2f-d826fa51a3ca | note | Method - Measure, Survey, Document Review
a2c24ba1-e220-586d-ac92-8e56e8099e29 | note | Frequency - 1m of fill
474a2c8c-da59-5df6-bb6c-d8fdd9eadb7d | note | Category - HP
ebaa1a6c-1d66-54a7-8084-62eae5990b33 | note | Responsibility - Surveyor, SE/PE/SPE
24cde826-7549-5027-b984-afa260e7d2d8 | note | Verifying Documents - Settlement monitoring results
e77032d4-d88f-5d10-8311-baa5dccca5d4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
3a8f8f5d-729a-5aed-968b-56507b806587 | note | Reference - MRPA Quality Management Plan
7903c01c-5d82-59ba-abab-33179c83496a | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
3854ebdf-58e8-526d-a0a6-cfae7034e29a | note | Method - Document Review
595004da-bcc1-52da-943e-6ed4f8c709ec | note | Frequency - Once, prior to closure of this lot / element / Work area
156538f3-d68a-589d-a720-d7431c60c4e9 | note | Category - HP*
77a91613-98d0-58e9-bdd1-23ae1c1eb819 | note | Responsibility - SE/PE/SPE
de66aa23-4612-5f14-9325-926a683bfb8c | note | Verifying Documents - This ITP Signed off
b0517ef2-cbf0-5ad9-8725-ce6088e141c8 | date | Date Completed:
| checkpoint | Final Inspection
8c6ba7ec-3387-50e0-84fb-70b09713a11d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
91c58319-dc15-5f4a-82b7-1f211ffcdcfe | textbox | Name:
a00407d3-93b5-568e-9869-046dd1289c5c | textbox | Position:
28ce3d48-6c98-50b1-a920-2ce4477ded28 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-112-STR Precast L-shape Wall Rev1 | itp | ITP-112-STR Precast L-shape Wall Rev1 | e5994219-ee26-4a50-8c5d-8685118d3ed1
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
5c2f115a-3b6b-5bd9-a9dc-def0dbda79df | note | Document Title: ITP-STR-Precast L-Shape Wall (Supply & Installation)
778d05de-8b0a-513b-bd6b-2ea23bd87281 | note | ITP Description: Precast L-Shape Wall (Supply & Installation)
551997e1-1215-51b0-a503-90be43e01791 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
f4e2d6d5-8767-5ca5-8cf5-4fb44537169a | note | Discipline (e.g. CIV/STR/RAIL): STR
11c40e23-eb08-5b21-a76a-261ccc5d3421 | note | Revision Number: 1
c108933d-9345-5cb8-b280-a68d70975981 | note | Revision Date: 4/12/2023
d2d918ec-faf0-5bee-86b7-c18a7b018338 | note | ITP created by: Matthew Dib/Jason Quan
5aa195f2-d45c-53af-a7c4-c67af7b20c94 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
2b6ed922-1c00-5a64-8e2e-7dfe068b852c | note | Reference - VicRoads Section 610
| checkpoint | 1.2 - Non Dependent
29518ce6-45cc-5f98-bfa8-1d2d59e5a6d4 | note | Reference - VicRoads Section 620
| checkpoint | 1.3 - Non Dependent
971e2381-6bc5-5f3a-9b17-801af1328f4b | note | Reference - IFC Drawings
| section | 2. Preliminaries
| checkpoint | 2.1 - Precast Elements
7e43c90f-fffe-5e01-ba0c-189d860631a0 | note | Reference - IFC Drawings 610.47 (a) Table 610.474
4513d817-6537-537b-a50b-9db5cd9015ef | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
cb430eb8-5103-57a0-9e11-822555044b82 | note | i. Certificate of Compliance / Birth Certificate
f217dfde-308e-573d-a170-d0959185e3a2 | note | ii. Compressive strength test results
59968e3c-1a56-530c-b65f-559f297d0f3b | note | iii. Precast Lifting Design
58a5be56-c275-58f6-b3e1-8179e537e44b | note | iv. Pre-pour check sheet / ITP
33cce3fc-8ae1-5bec-9278-f0dc529915e4 | note | v. Post-pour check sheet / ITP
e8a90ae5-abc8-5156-875e-10b58b1ac25c | note | vi. Covermeter check record
eb67e935-787e-526e-aaf0-8056dc9b2481 | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
219beefe-f283-567c-b4c8-f25d6ac9f416 | note | Note: Different revisions of 610 have different clause numbers
c15c11ec-30ca-5aeb-bae3-f87b18c64080 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
1b059c1b-30ad-5eed-bd77-d3924495f2b3 | note | Method - Document Review
fa812c37-0be1-5fcf-a210-acc2b62a9e86 | note | Frequency - Each element
4af7a4b4-6152-52dc-b8db-7eb73ccd9163 | note | Category - IP
0146191e-f88c-5551-ae7e-9f145e8e90e2 | note | Responsibility - PE/SE/SPE
1ce28ac0-563f-5c5d-a3b2-695b639b4fff | note | Verifying Documents - This ITP
9d23dcb2-9802-502b-9be2-2e075ed68f21 | date | Date Completed:
| checkpoint | 2.2 - Joint Sealant
76baec38-64ae-5835-b76e-b22b252fbefa | note | Reference - MRPA Quality Management Plan
b3e4b4aa-e0b9-50f5-b62e-a32ee4868aeb | note | Acceptance Criteria - Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
267e650c-8119-5b73-96a5-da3b795691cf | textbox | Enter: Teambinder Material Approval number
d8f7fbff-6846-58d7-b0bd-c33736ade3d0 | note | Method - Document Review
40a0c0ea-5332-54bf-b4ca-bea7165b9ebe | note | Frequency - Once, for each product
46924b02-c733-5b98-88be-7857076b5bc9 | note | Category - IP
2ffcf096-08ff-5a53-8b7c-0c87254d58a0 | note | Responsibility - Nominated Authority
383fc283-f1e1-5709-b1bf-e5b57a310963 | note | Verifying Documents - This ITP
47df4a6b-2835-5e2f-b5f1-741ca2c18156 | date | Date Completed:
| checkpoint | 2.3 - Foundation
73ba0b36-9d5a-5601-8fd4-49f1e494c2b7 | note | Reference - IFC Drawings
a008bb9e-025b-5e23-bac8-cbb74ab2a397 | note | Acceptance Criteria - Foundation material under L-shape wall base slab shall adhere with minimum design bearing capacity of 200kPa and shall exhibit a minimum unndrained shear strength of 80 kPa. L-Shape wall shall be founded on 0.5m of Type B Structural fill
d6edf79c-47d2-50a9-8289-a611330a9a76 | note | Method - Document Review
d1d02242-5e05-5a71-90cd-a6caccf471d2 | note | Category - IP
b606a5b4-6bcc-5f17-ac39-7635fab9d300 | note | Responsibility - Nominated Authority
3aacb8a4-924e-5aaa-a4d8-c8a166813cbc | note | Verifying Documents - This ITP
78b9d5cf-e599-5aee-87b5-dadc75546f55 | date | Date Completed:
| checkpoint | 2.4 - Architectural Finish
02a1ccf8-9852-5760-9dba-bce492c20fa9 | note | Reference - IFC Drawings
d77e2c39-e89d-5eb9-8c57-63464ee58126 | note | Acceptance Criteria - 50mm Thick Architectural finish. 20mm Thick Dummy Joint in Architectural finish.
41b0c114-5841-5129-ac2c-a7d622430d34 | note | Method - Visual
0df6e7a3-e0b1-5662-8fb1-8576e507d94f | note | Frequency - Each element
118246c2-5fc5-5fc9-9bc3-ff6db19eaa1b | note | Category - IP
9121ebb7-5bfb-5535-ae59-43f1c7371d6e | note | Responsibility - SE/PE/SPE
499a6aa4-6bfd-542b-a971-74feda7286b3 | note | Verifying Documents - This ITP
e243bbc8-0a7b-5df6-bda9-5738bc47bfed | date | Date Completed:
| checkpoint | 2.5 - Precast Traceability
cb14e508-c62b-5483-8efb-0190eb388972 | note | Reference - 620.09
e1610e8f-f9a3-59c6-adda-d4a5b0f101e0 | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
1a194a12-b971-523c-ac6f-350591ba1ed2 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
d83a12bb-09a9-5342-ac51-85ea7d01e56b | note | Method - Visual
d5718f86-c9be-5e74-830a-50cbb1d3d853 | note | Frequency - Each element
63aa8fc4-81a5-511a-9579-e181aff7ce3c | note | Category - IP
55a372fa-cd4e-5e4a-9f36-de16672031eb | note | Responsibility - SE/PE/SPE
ab57a5c1-cb66-556c-be86-248ee3f9d7fa | note | Verifying Documents - This ITP
0bb98fe4-763e-5fa7-b1c9-e64a9377a61b | date | Date Completed:
| section | 3. Pre-installation Activities
| checkpoint | 3.1 - Survey Set-out of Precast Elements
9581c9c6-4409-539c-af2d-6a99f65a4afb | note | Reference - IFC Drawings 610.47 (a) Table 610.474
e8a9ccfc-a1eb-53cf-8236-4015caa73f1f | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.474 as applicable to the element.
1e9a8d03-6cb3-5da3-9aa3-6ad04587256a | note | Method - Measure, Visual
72334d6a-bc35-5b82-93be-560b6c763253 | note | Frequency - Each element
5e5aebf4-7bd3-55d2-9c99-3659c190df12 | note | Category - IP
a060f8e8-4e6d-5e56-8de2-8bed733af010 | note | Responsibility - Surveyor, SE/PE/SPE
fbaac7b4-fc88-596c-9c38-2ebe6ed047a3 | note | Verifying Documents - This ITP
f0c13d93-9e89-53f2-9a81-9b53ec5a87a1 | date | Date Completed:
| checkpoint | 3.2 - Blinding Concrete
ffba990e-59c9-5190-a16d-4ffaa1a7c24c | note | Reference - IFC Drawings
f73d8c13-4aaf-5e32-b234-07e425ae35dd | note | Acceptance Criteria - Blinding concrete shall be placed, leveled and surveyed. Provide stiff broom finish or rougher, Minimum N15 Concrete 50mm thick
72b1296b-9c60-5ea1-8f16-0482203e3a33 | note | Method - Measure, Visual
4bffd5b2-47ed-5a0f-96c9-8bcb4c7e915a | note | Frequency - Each element
c13ca6f0-a8f9-5705-b04f-e221faef8324 | note | Category - IP
90703554-5836-57d2-81c9-30edbd99303d | note | Responsibility - SE/PE/SPE
d194ad2b-5a4c-54ce-b10f-4f6e61dd9304 | note | Verifying Documents - This ITP
312724c1-cc02-55f5-8d4c-9110c73d6215 | date | Date Completed:
| checkpoint | 3.3 - Packers
ec844503-5b8a-544b-bab2-fbce5303ea03 | note | Reference - IFC Drawings
dc99223f-a52d-51e6-a4c8-d9e3deff479a | note | Acceptance Criteria - 100x100 min non metallic packers shall be placed on blinding concrete
840765bd-53ce-5282-a9a6-756842d30ca1 | note | Method - Measure, Visual
7c86bb0a-4bd7-539f-9315-175b0e3edeac | note | Frequency - Each element
bd5d402d-4612-545e-9ef1-ce160b09f20d | note | Category - IP
3072606f-50a7-555a-a74e-e0101cb3621a | note | Responsibility - SE/PE/SPE
351c2feb-a6fd-5061-9794-9e867dea907c | note | Verifying Documents - This ITP
2957d0bc-e2ef-5675-aeab-141a61d55bd1 | date | Date Completed:
| checkpoint | 3.4 - Ferrules
e8d9d5b2-bbd8-55b8-b82d-10304b76aa6b | note | Reference - IFC Drawings
57f87267-79ba-58e6-9c90-a924f92ccd5d | note | Acceptance Criteria - Ferrules are installed as per IFC drawings
ef998869-579f-59fa-845c-019379c1d3b7 | note | Method - Visual
fe3edc8f-0b41-57ee-810d-c468ae249842 | note | Frequency - Each element
bb84192f-8150-55b6-8310-d6894402f166 | note | Category - IP
d1176d02-4505-553e-ac7f-85bd7cac6251 | note | Responsibility - SE/PE/SPE
d49f9e2b-1487-57c8-b1b4-99762ebf0401 | note | Verifying Documents - This ITP
55add579-81a4-5342-89a3-c193d6c69940 | date | Date Completed:
| checkpoint | 3.5 - Materials Inspection Checklist
5f515491-321e-555e-b937-a3ad83c3a9ce | note | Reference - 620.06, 620.07 MRPA Quality Management Plan
29274d99-0ef2-5866-b189-2b5eb36d567b | note | Acceptance Criteria - General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
e0904ab5-e14b-56c9-bace-3e4bcfb9df27 | note | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
307ada0d-d6bf-5670-bec6-0f8bc2c586ec | note | ○ Elements shall have unique identification and orientation marked (if applicable).
8b1f9cd3-5e37-52e0-a741-cf14615ecbc6 | note | Complete: Materials Inspection Checklist in ConQA
f8a43ae2-2be5-52da-a84f-d525401309ad | note | Method - Measure, Visual
0b692649-b48d-5ac1-8d1f-6e1cbbfde581 | note | Frequency - Each element
bfb4dc1a-bb16-5ef5-bb0e-f5b9352df542 | note | Category - IP
ea0d9616-5990-5c2d-bebc-b16aa7861fb2 | note | Responsibility - SE/PE/SPE
4d5e08e5-ec46-551f-81eb-ab25d9c89864 | note | Verifying Documents - Material Inspection Checklist
839a233c-3a64-5a6e-a43d-19a2e70d6a10 | date | Date Completed:
| section | 4. Installation Activities
| checkpoint | 4.1 - Precast Handling
e21777cf-abd5-5971-add6-c2c0f9c5d4a4 | note | Reference - 620.07 Crane Lift Study
556181e1-ac3b-512f-a1dd-1ea0595c1fe8 | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
6c9bf39f-74ce-5345-be65-cb858de0d518 | note | Method - Visual
07119e75-51f3-56ed-ab3b-8e0079493c17 | note | Frequency - Each element
d06e09cd-89ef-5ca2-9a60-e7f15b7cb3e9 | note | Category - IP
cc49a420-52a9-5566-b283-300421d337c7 | note | Responsibility - SE/PE/SPE
42cb4e10-4f6b-5a83-83d4-b0ee2694ac12 | note | Verifying Documents - This ITP
628d0df6-551b-58f4-a4f9-a867fb46967e | date | Date Completed:
| checkpoint | 4.2 - Precast Placement
af5a7017-3c8e-5f4b-b540-206121c86a02 | note | Reference - IFC Drawings 610.27
df23c2be-6d86-56b0-8684-afcea014def9 | note | Acceptance Criteria - Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance.
868cfbc1-54e0-52c9-80be-5e5f3bfdb3cc | note | ○ The nominal gap between elements is as per the IFC Drawings.
0d29c38c-c437-5d99-b2ef-c865b7576eae | note | Method - Visual
0c2d1071-dbff-52c2-b3c3-edd827a0db0e | note | Frequency - Each element
0f701b51-0f15-5760-b34d-e383dfca97cc | note | Category - IP
f9418b5a-2c4a-5427-8c85-f60a07b1bd31 | note | Responsibility - Surveyor, SE/PE/SPE
46d014ef-591f-5b2c-95f0-457ae133c4a8 | note | Verifying Documents - This ITP
827de890-4a9c-5019-a32f-16b639ef0264 | date | Date Completed:
| checkpoint | 4.3 - Flowable Grout
626b975f-fd36-500a-b346-181621f35a1f | note | Reference - IFC Drawings
23f40d6c-d9ba-5b41-8311-500996cabd16 | note | Acceptance Criteria - U.N.O All cementitous grout shall be a flowable type C class dual shrinkage compensated grout with a minimum compressive strength of 40 Mpa
46c5521a-5a3f-5252-83f7-d8b227a65f61 | note | ○ 50 NOM gap between precast wall base and blinding shall be flood grouted.
8c287916-8ef9-528f-857d-e47e75a3dfa7 | note | ○ Backfill and compaction may commence after Grout has achieved 10 MPa Min Strength
aa449747-d38e-5798-977f-3e67928e90aa | note | Method - Visual
23dca991-59fa-530c-9649-d36c5ffa0266 | note | Frequency - Where applicable, Attach Concrete Test Result
b5015452-d657-5fc3-9031-7ae56bbe9c66 | note | Category - IP
0d2de902-37d8-551c-89e4-efc2fe657ef5 | note | Responsibility - Surveyor, SE/PE/SPE
bda1a941-f839-5eaf-8dbd-6a75c10147ba | note | Verifying Documents - This ITP
36c0e3be-076c-5086-87d3-6a05137806a0 | date | Date Completed:
| checkpoint | 4.4 - Panel Joint - RSS and L-shape wall
828ea906-4d8a-57a3-8553-c77e5142c5e1 | note | Reference - IFC Drawings
54abe26c-d41b-528a-928d-1286f227fe3b | note | Acceptance Criteria - The gap between each precast element or at interfaces with other structures should be sealed with an the approved filler. Install compressible filler with backing rod both faces.
09e227ee-02f9-587a-abb7-07c4f73be0e9 | note | ○ 300 Wide Bitac Multi-laminate tape centrally over joint between RSS wall and L-Shape panel.
50a257dc-ff05-5c3d-805d-1719637f3488 | note | Method - Visual
9d040eb9-d5c7-53ba-95e6-bd56aa3d642f | note | Frequency - Each element
e555ed88-f2b5-5094-925d-a8a0a7243b2b | note | Category - IP
74cee11b-217a-527d-8bb6-5cbe908e2a40 | note | Responsibility - SE/PE/SPE
796ac34a-024d-5fba-a668-76973a4f755f | note | Verifying Documents - This ITP
449595f2-b9e0-5771-a225-e3a75c2fd6e2 | date | Date Completed:
| checkpoint | 4.5 - Drainage
2506ba36-6aa5-5c4a-bef1-339f7de76743 | note | Reference - IFC Drawings
eab2be06-9d05-5a5b-b883-165969b7b945 | note | Acceptance Criteria - Drainage Weepholes to be installed as per IFC Drawings
afffdd62-5fbc-57ea-8180-8ac4c42f32f4 | note | ○ Install 50 Diameter uPVC Pipe with 0.5% min fall.
54c36984-3d33-5bb9-833e-c8b0df82ad6d | note | ○ 300 Wide Strip vertical strip drain (Prodrain PD40) positioned centrally on back face of panel
dce3681a-2ac0-516d-8d60-87026d5ffa2d | note | Method - Measure, Visual
b415b154-58dc-5ae7-8266-ccf9b20f880a | note | Frequency - Each element
64f487fa-e8f8-51d4-9b12-91abc238501e | note | Category - IP
8e9f244d-edbc-5fcc-9fb9-1512f0ecc4b8 | note | Responsibility - SE/PE/SPE
01cbddfb-f7ed-5c8c-84cd-91cabf613c16 | note | Verifying Documents - This ITP
79dcc89c-d37e-5847-83cf-68888981d97b | date | Date Completed:
| section | 5. Post-installation Activities
| checkpoint | 5.1 - As-built Survey
1dd54b46-2021-52ba-812d-fef9dc829b16 | note | Reference - IFC Drawings 610.47 (a) Table 610.474 (Feb 2020)
4cbbb080-b1a1-5357-82a3-d48ff9f6672b | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.47
cab54a28-1a05-52b1-8b47-610fa4856af5 | note | Attach: Survey As-builts / Survey Report
bcd156b5-7499-551d-bf25-837bb61a6ff1 | note | Method - Document Review
b2b9329f-c2e3-58e2-afd6-7566ebbb8986 | note | Frequency - Each element
c72e4186-a76c-549d-96b4-af9715878e7c | note | Category - IP
8484fb0f-b358-5a1c-8a85-804cd468c972 | note | Responsibility - Surveyor, SE/PE/SPE
3540b731-5f8e-5678-b901-15563051ef21 | note | Verifying Documents - This ITP
bb46a365-2941-564a-8f72-5a833baedcf8 | date | Date Completed:
| checkpoint | 5.2 - Non-conformance Report (NCR) Closure
970e375f-621a-5ec9-a630-327a3f7406f8 | note | Reference - MRPA Quality Management Plan
db839d34-6ef5-5708-a8b9-ac2ce75639da | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
3371a286-5dc1-5131-9fd9-1cc20a6d0508 | note | Method - Document Review
2255eff1-a65b-506c-ab72-078ed26d926d | note | Frequency - Once, prior to closure of this lot / element / Work area
5208162c-9c58-526b-bca2-978c7747733e | note | Category - HP*
fcc1f980-6b98-5561-a0d2-371ff362c607 | note | Responsibility - SE/PE/SPE
9c32d3c3-b4b9-5a88-89f5-253b575ac562 | note | Verifying Documents - This ITP
b65ca038-7f91-5deb-988a-f6c2357b3052 | date | Date Completed:
| checkpoint | Final Inspection
b4aa91e2-aa05-54ad-bb8e-ff2972eee94e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fd7acf0f-cfcf-5b58-a4ab-ebc30da69b44 | textbox | Name:
0d29112d-75a0-5ee0-bea9-a5001ebcefd9 | textbox | Position:
eaaa6851-f6d4-54e7-b2c4-637c39a2baf3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-113-CIV-CPD- Jemena Conduit & Pits (Supply & Install) Rev1 | itp | ITP-113-CIV-CPD- Jemena Conduit & Pits (Supply & Install) Rev1 | 4937393f-35e8-4f5d-be6a-ac0667322b1d
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
53fe9999-79d4-5a51-a5a8-3bd2d49de341 | note | Document Title: ITP-113-CIV-CPD-Inspection & Test Plan - Conduit & Pits - Rail (Supply and Install)
66d6d135-9169-5833-86b1-4f5a180666f6 | note | ITP Description: Conduit & Pits - Jemena HV relocation
425e115b-9611-5c53-9a2c-be512e83db0d | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
275f2cd3-afa5-5e49-8521-497565a896a8 | note | Discipline (e.g. CIV/STR/RAIL): CIV
9996c7a4-5773-5508-bd31-dd0640c0f968 | note | Revision Number: 1
dff8a319-7e69-5f31-a8fd-819965ef06c4 | note | Revision Date: 8/12/2023
0a3d1610-38ac-5f66-8e33-95d9d863221d | note | ITP created by: Lachlan Morris/Pat Sabaruddin
4829db38-56fb-53bd-b72a-12e6716c5b3b | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - IFC Drawings
0aceb62a-1522-5afb-bbce-39d796bacba0 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
| checkpoint | 1.2 - VESI D&C Standard
0c8db75f-edcf-5be7-b06a-cdb3bb9fe5f8 | note | Reference - VESI_URD_003
| checkpoint | 1.3 - Plastic Industry Pipe Association - Industry Guidelines
f37d66e2-9cfb-5bad-ae1d-053cfc282a78 | note | Reference - PIPA POP 003
| checkpoint | 1.4 - Australian Standards
aab62cff-8294-5d4c-9d89-5d7abd3c02b5 | note | Reference - AS 2032, AS 2053, AS2648.1
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Conduits
f5f33d93-648c-56bf-8498-70e6270127d4 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003; cl4.4.2, cl5.8.2 AS2053
dd84aa1a-4142-514d-a2f6-ecbee434a3f1 | note | Acceptance Criteria - HV & Comms: Conduit sizes as per IFC and VESI 4.4.2 CONDUITS USED WITHIN THE VESI NETWORKS SHALL BE HEAVY DUTY SOLID WALL, ELECTRICAL CONDUIT TO AS2053.
2c77cc61-821e-59f3-b451-71b6b713b335 | note | ○ HV & COMMS CONDUITS TO HAVE A max BENDING RADIUS AS PER VESI_URD_003 - 5.8.2
46347979-2439-5cdb-a64f-ba57e0561b60 | note | ○ Inspect materials upon delivery and attached delivery dockets.
80b462a1-6c47-5f0a-a89e-6d762bb3d21d | note | Method - Visual, Document Review
9a2f3396-0f10-538f-9774-8231a167c433 | note | Frequency - Each Material Type, Each Delivery
99b5b451-0db3-55dc-acc3-2b68c9306188 | note | Category - IP
e3e033d8-3882-5806-97fc-7f196df2f093 | note | Responsibility - SE/PE
42d2c485-4f29-56c8-927c-db35ea8919c9 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
3f5e9be0-7e06-5ded-a971-18e9a1de396e | date | Date Completed:
| checkpoint | 2.2 - Pits and Pit Lids
a0211734-41ca-5348-a1a6-b62bd88c1ac5 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
0f4884f2-3661-51d1-a0ce-3543bb3b18a9 | note | Acceptance Criteria - Pits:
fac9277e-4066-5a95-92ca-4579933d2240 | note | ○ Pits to be used and installed as per IFC drawings and manafacturer requirements
a5624844-f73e-5973-99c6-23417286959c | note | ○ Inspect materials upon delivery and attached delivery dockets.
aa229adc-4a74-57bf-8ec0-3d4f568723c6 | note | Method - Visual, Document Review
0a774e07-6486-58a1-bdbb-8663a3c4683b | note | Frequency - Each Material Type, Each Delivery
c968b835-6aec-51ec-bff7-0ea05ab7abf1 | note | Category - IP
550f821f-2c51-5e23-a97b-33e3c33bb0c9 | note | Responsibility - SE/PE
628f80ac-6b3a-570c-a6c0-b47808434476 | note | Verifying Documents - Attach Material Conformnace Certs, Attach delivery dockets
e4a1c952-4f96-5d36-8d14-5c1f4d32ffab | date | Date Completed:
| checkpoint | 2.3 - Warning/Marker Tape
ef787d9d-ecb4-547e-9317-52fa61c753d8 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, AS/NZ 2648.1, VESI_URD_003 -5.5.2
9f3e70a9-7a69-537a-8db7-730fb864b100 | note | Acceptance Criteria - Warning/Marker Tape:
b84dfb06-1828-5f09-a2ad-385dd1e5eb33 | note | Above HV:
707c6847-a0a2-545a-8b9f-f365fdbee496 | note | ○ Orange 150 or 300mm width marker tape compliant with AS/NZS 2648.1 shall be used
6c3a2d8a-5026-5f1b-a94d-8acfa230e7ef | note | ○ Inspect materials upon delivery
c1536669-4242-5693-8613-765e3bc2206b | note | Method - Visual, Document Review
7694a862-262b-5a51-80b9-316b35c0a480 | note | Frequency - Each Material Type, Each Delivery
01e1c786-0b71-5314-9029-c7f04b087b6b | note | Category - IP
c7663192-47cc-5745-87d9-29245fb3c600 | note | Responsibility - SE/PE
a70cd9ea-77b3-5bae-b381-831590808cee | note | Verifying Documents - Attach Material Conformnace Certs
ee8ac25d-87e3-573a-9386-28a2cf5f2f9d | date | Date Completed:
| section | 3. Prelimnaries - Procedures & Documentation
| checkpoint | 3.1 - Services
d71fb84b-ea60-576b-a0e2-8238e822a1ff | note | Reference - VESI_URD_003 4.4.2, 5.10
d961c62a-4437-5806-9dbc-2052d0c6e899 | note | Acceptance Criteria - Clearances are requried between individual electrical assets and between assets of other authorities.
7d4029f1-bbd4-5c1f-8a7b-f9d7af21a59f | note | Method - Visual
219bedc4-3ce3-5604-887d-a4586425dc09 | note | Frequency - Prior to commencement of works
831d9e6f-5383-5be6-8aa2-ddfdcdba9d4f | note | Category - IP
4c96fbca-0d99-54cb-9628-392b6c5a2d90 | note | Responsibility - SE/Site Supervisor
876ba946-0b1c-5cf7-acde-13a1d6dae305 | note | Verifying Documents - This ITP
4b0d2633-266e-5c18-8fe1-8fac0b76143f | date | Date Completed:
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set-out
deb2444b-2860-5c2e-adaa-c2e076d8c26d | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
8c3cd768-a361-52f0-8f80-6059e9ac6b08 | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level). Survey to mark out existing services.
76dc6408-8b5d-548b-bf41-75b66391cb8d | note | Method - Measure, Visual
35d84cf9-2264-58eb-9925-d03676a3dcb9 | note | Frequency - Each element
4ae62148-28db-55b0-8b6e-514feb538040 | note | Category - IP
09365510-8805-5e39-8f71-b30c076a7fa8 | note | Responsibility - Surveyor, SE/Site Supervisor
8c6f11fa-55dc-5fac-b10a-35ac5f4643b1 | note | Verifying Documents - This ITP
c3fd09e6-6265-5c42-88ee-20a36de961c6 | date | Date Completed:
| checkpoint | 4.2 - IFC Drawings
64bfd49d-2c2c-501b-a8af-02eb00bb4b78 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
828e6179-1251-5093-a14b-8a45e2ccc078 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
cd37071f-0d28-5e69-b5fa-a0d60973a4d1 | note | Method - Document Review
5a57059d-123a-5e5d-91f8-ba08e3ed6445 | note | Frequency - Prior to commencement of works and at regualr intervals
292826d4-1800-5d15-8e33-887439cf0327 | note | Category - IP
61a7c5df-c836-5197-aa2d-3a94361eb7e7 | note | Responsibility - SE/Site Supervisor
28d9ae57-5b2b-5d50-b347-d344507a925e | note | Verifying Documents - This ITP
1ef87dc9-b95a-51d9-b588-ef53bff7da0b | date | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Trench Excavation
1705a4ca-3185-5b8a-b4a6-1360db33eec4 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
458a6cae-2dc6-51b6-8bd1-8812022c8c9b | note | Acceptance Criteria - Trench profile and depth as per IFC drawings.
5ccad464-5f30-5a7f-844c-654416e0a9c1 | note | ○ Depth of trench is to be sufficient to allow for the minimum cover as per IFC from the top of conduits.
845abd5c-871b-589f-8c02-9d077bf0f5a3 | note | ○ Cl5.3.2 Within the VESI networks, cabbles shall be buried up to a maximum depth of 1400mm (max trench depth of 1500mm).
d96bb569-5e61-5f6a-b896-92a1f634ec69 | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
0198e6c9-c61b-5f6f-891b-ac0fbdbd6068 | note | Method - Measure, Visual
fd800739-ae59-573b-b2c0-73f0b23fe1a3 | note | Frequency - Each lot
e9fadfb0-c7c0-5da8-b752-acb7132f911f | note | Category - IP
028de31d-7ea4-5f23-ad25-fed0e95f4970 | note | Responsibility - SE/Site Supervisor
f7e75c6a-ae00-5dc7-afe6-9331d1a8bc7b | note | Verifying Documents - This ITP
ebb7d2ff-cd54-5816-b2e2-25af3257358b | date | Date Completed:
| checkpoint | 5.2 - Placement of Bedding/Embedment and Backfill of conduits
40f9eb0d-b858-5e99-bd28-af2458002898 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003 - 5.7, VESI_URD_003 -5.4.2.2
4215b288-ee30-5a53-89f4-aabeff4763ac | note | Acceptance Criteria - Measure, Visual
9549ed48-f22d-5e49-aaa0-a673eae24a3a | note | Method - Measure, Visual
82b4dc85-31ba-5977-becd-3d9c45d13dcb | note | Frequency - Each lot
2e21899c-cc1a-5d3d-81e1-5917a0201b42 | note | Category - IP
5622f178-29d2-5001-a138-376e46842c11 | note | Responsibility - SE/Site Supervisor
7b8952c6-ccab-5594-8595-aecd587bce92 | note | Verifying Documents - This ITP
24958e79-725c-52cc-9b1d-5dafe63acb8c | date | Date Completed:
| checkpoint | 5.3 - Conduit Placement & Configuration
68bef158-7d09-5ae6-9368-d005efb75c1c | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
0578ace6-d5e1-53cd-8440-d7ab5134082a | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
818995a1-0a1e-5d22-8bb8-425b9c915efa | note | ○ VESI 5.10.1.3 Where shown on the approved plan or by prior written approval conduits may be stacked in vertical alignment.
8ab68478-fc99-53fc-a921-3e02581cf91d | note | ○ VESI 5.8.1 Conduits are to be provided with suitable non-perishable, watertight, endcaps or plugs. For any
e29afb79-9923-5c17-a62a-e1f37283b612 | note | Method - Measure, Visual
cb0a9069-f532-5075-9207-d7510a566236 | note | Frequency - Each lot
3cddc9d1-08fd-56a8-b090-8b4a552f4138 | note | Category - IP
389ed160-0e74-5a9e-9b3b-52bd3e24ce72 | note | Responsibility - SE/Site Supervisor
677c4513-34c8-5827-94b1-8342268ac5e3 | note | Verifying Documents - This ITP
c7bb86f0-6c61-5f6c-ae92-bd5fe6f95b4c | date | Date Completed:
| checkpoint | 5.4 - Joints
d80cd435-4e25-5e77-aaf6-25084a616c47 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003 -5.8, AS2032.
a1895306-938c-5774-b588-3d83b46118fd | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends.
0f9200fe-7a9d-55dc-b29d-b2ed8dffdd63 | note | ○ Conduits are to be joined using solvent cement and comply with AS2032.
c1ec70f4-063d-50c7-a8d1-704ac265b831 | note | ○ Socket ends to be placed firmly into the spigots prior to backfill.
f973d731-8735-5767-8483-21f154717368 | note | Method - Visual
73cc208e-4583-5ce0-b13b-6d6d939f31cc | note | Frequency - Each Joint in each trench
45a1a0e9-cf5d-55e1-88bf-744542f23527 | note | Category - IP
ce5d52b5-f736-525e-98ac-f5fbee4ad295 | note | Responsibility - SE/Site Supervisor
acc4cd62-e796-5a87-b9b6-f186031524a1 | note | Verifying Documents - This ITP
cb7a8939-cdd1-5ca7-a3d7-eaeeff531f90 | date | Date Completed:
| checkpoint | 5.5 - Conduit Inspection
f9598065-57f2-5c72-a320-09ae26442927 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
7177e53f-c0b9-53d8-be05-f1f345b883fd | note | Acceptance Criteria - Inspection of conduits undertaken by VEDN accredited contractor
8df668ec-95e7-5003-9e61-1eefe26ff8c9 | note | Method - Visual
978cc1b3-0e86-598b-a54a-3e10d586e18c | note | Frequency - Each lot
5ca33ec5-d29f-56f0-8c7b-14140bbddf6c | note | Category - HP*
c0e39564-3671-5c68-99ba-8242346b82d4 | note | Responsibility - SE/PE
26c80910-2c78-5749-b42b-5d6f93b266fb | note | Verifying Documents - This ITP
d22f3412-4dcc-5ef5-8976-2fe0baa24192 | date | Date Completed:
| checkpoint | 5.6 - Marker Tape
36ae0b47-b725-5d1a-9384-489a75ba690b | note | Reference - VESI_URD_003 -5.5.2.2
0a020f5f-c3e7-59f7-932f-b1dccb101bbe | note | Acceptance Criteria - Marker tape shall be installed no closer than 150mm to the cover slab or conduit and no closer to the final surface level than 250mm.
839ae883-23ef-5240-bcd1-0906e1c1c0bc | note | ○ Marker tape should be located no deeper than 600mm from FSL.
f014d2de-4331-5852-ba71-3e071cb15cd5 | note | ○ Tape to be one continuous length.
8ea540c6-817f-5ca5-81a5-40d5d77dd56c | note | Method - Visual
4b9d5669-efcf-5a2d-93bc-dd7e9eda45bc | note | Frequency - Each lot
486b97f8-6141-5e36-a9c8-723779140706 | note | Category - HP*
330e28ea-a1db-51d4-99bd-2993b8612e0e | note | Responsibility - SE/PE
607c10fe-1fe6-52c3-92e5-7f45ea72c754 | note | Verifying Documents - This ITP
ad38cb7c-67e2-5fd7-a171-4d85b8e1bad3 | date | Date Completed:
| checkpoint | 5.7 - Pit Installation
202123b5-f511-5dfb-91b4-144b15fe5c2e | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003; cl5.9
0f78317a-cb84-5427-9f3d-cda988431604 | note | Acceptance Criteria - Comms and electrical pits to be installed as per TC-2203
09c31809-a4b3-59b0-8136-eebdc84d521b | note | ○ Pit chamber floor to be 100mm lower than the underside of the lowest conduit. Entry conduits installed 75mm into pit.
76ca8c22-4e30-567a-b35a-40478b543045 | note | Bedding: 50mm crushed rock bedding
69560cf4-eb52-52c8-b442-e4490cb7e1a8 | note | Backfill: Crushed rock is to be compacted in 150 layers arround the pit to bring the surface back to existing levels.
cbbcae4d-0024-52e1-8e9d-e9dae19d7a6d | note | Method - Visual, Measure
c0ae4c46-71e5-50ad-a0e2-8216131a6817 | note | Frequency - Each Pit
f2e08056-7a78-5b76-b553-98de1a72b250 | note | Category - IP
acdd25ad-67ed-506a-a48f-daf6bcef5900 | note | Responsibility - SE/Site Supervisor
ca087882-fc44-5036-80a6-dee65337de21 | note | Verifying Documents - This ITP
bad39874-0be6-589d-a3f0-c2ba9fb2f95d | date | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
a33ba74c-c868-53fd-a695-2aecf70d4e1c | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
b2fc6b79-bcab-5ff8-b3c0-e2c3f151ee97 | note | Acceptance Criteria - Survey report to include but not limited to:
438b656b-7d86-588f-9ad0-c7ee1e3d25e0 | note | – Cable pit locations (Corners)
289ae640-91f2-52b3-b8f8-04703abe8f77 | note | – Pit dimensions & pit lid type
fba4294d-2433-59c7-80b5-ea680d51f7b5 | note | – Changes of direction
e56a2654-b19f-579b-8bdb-093879a7546a | note | – Spare Conduits
572ee01e-aaaa-5439-afe1-11dbe3bb31ca | note | – Conduits labelled as per trench profile
428c6f11-4888-5482-94eb-5eeb0630c0f0 | note | – every 10m
2e6bf8bf-2c09-52e0-9ad9-14fb7a5c72b5 | note | – Other significant points of the cable route
826bcfe7-18ed-5cdb-9d5d-783585ddf0b8 | note | ○ Attached Survey Report
0360bd15-a23f-5e47-851b-a3ca1d3f4238 | note | Method - Document Review
31fb8c82-0297-5259-a919-2de01518da09 | note | Frequency - Each Lot
ea708d54-3e53-5c7f-914f-fd14cc812ac8 | note | Category - IP
1db48b5b-877f-5143-b24f-d8e85f42d713 | note | Responsibility - SE/PE
fa890235-1c98-5704-a9e0-08ae167ff77a | note | Verifying Documents - This ITP
5e8d5221-cd60-591c-a210-140132032736 | date | Date Completed:
| checkpoint | 6.2 - Handover
ede0bd7b-fea8-5714-95f0-5546fe60302e | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
9a9ba09d-1a81-5b88-9b66-65914d20fadb | note | Acceptance Criteria - Jemena Audit form complete
94cc8b64-61b5-5ca7-b6f7-024f48c8e0dd | note | Method - Document Review
86cbaab9-6862-5122-9c65-7977fd30e8b6 | note | Frequency - Each Lot
ca439f3d-da9d-5865-b934-7bae68686d61 | note | Category - HP*
31aac4c9-e96c-53d4-abcf-a8e7da616dd4 | note | Responsibility - PE, Jemena
798f187f-e4d5-5bd8-9900-961e984f238e | note | Verifying Documents - This ITP
d006002c-b1cb-5804-8b36-077b2bb288b2 | date | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
8b72af64-8a93-5793-9757-2831469b7463 | note | Reference - MRPA Quality Management Plan
e4a40f2a-b838-5503-9be7-c77ef0b89e99 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
6a4ca620-a052-5ba7-9cc7-0cbcd035cc4c | note | Method - Document Review
044ee160-e9e6-5be3-8c80-1ded70ba3249 | note | Frequency - Once, prior to closure of this lot / element / Work area
90b7772f-b099-54db-911d-54801ca9dc5d | note | Category - HP*
7341df55-548f-5352-910a-a89bebbaa804 | note | Responsibility - SE/PE/SPE
2fe02882-fc04-52af-8f74-29f5735b01de | note | Verifying Documents - This ITP
3a34bb5f-8b39-5df4-9773-07cddcad6774 | date | Date Completed:
| checkpoint | Final Inspection
339c5638-ffb7-5747-bb49-2600f321a2ea | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f1add705-614a-5aee-96e8-a5c1cb52afe7 | textbox | Name:
8515a0db-c0b0-5e75-8031-b62535e86d98 | textbox | Position:
b796480f-38d4-5b8f-add2-daa37bdc4227 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1 | itp | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1 | ed0e2f56-d2df-4917-be48-3e6b6c25ffee
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
e99cf2d2-30c6-58c1-bef4-3c43b10a229c | note | Document Title: ITP-114-CIV-CPD-Inspection & Test Plan - Horizontal Directional Drilling
67f5be0f-97bd-5c3f-ad24-1ba14bb81308 | note | ITP Description: Jemena Conduit Bore
df085331-598c-5a61-b7c7-e5f42c8e2aaa | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
61d7e18d-1a16-555a-acaa-f8bca90748a1 | note | Discipline (e.g. CIV/STR/RAIL): CIV
6736d612-d6d4-512f-9b18-bce960cd9cd4 | note | Revision Number: 1
71f2a565-3225-5d1e-96a1-a3d4386618bd | note | Revision Date: 12/12/2023
4581dbf0-fbd3-5a7f-a61e-ff3cdbcfbc2a | note | ITP created by: Lachlan Morris/Pat Sabaruddin
fc634587-72f9-59d0-9330-b6102770b4a3 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - IFC Drawings
68903ee5-f6a1-5d06-bc44-f9789ad400f5 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
| checkpoint | 1.2 - VESI D&C Standard
8a4b3509-54ab-5326-9219-ce75c4d5bd31 | note | Reference - VESI_URD_003
| checkpoint | 1.3 - Plastic Industry Pipe Association - Industry Guidelines
db364956-70e0-5004-be28-0686111ecc57 | note | Reference - PIPA POP 003
| checkpoint | 1.4 - Australian Standards
6eae4cf9-ef8d-527a-a8ab-6ea25b5c422c | note | Reference - AS 2033, AS4142
| section | 2. Preliminary Works/ Materials
| checkpoint | 2.1 - Electrical Conduits
906afc69-f8a7-5d48-9682-ca57689aefa3 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
2acc479c-d45d-5ae1-b7fb-ba0002b47a2a | note | Acceptance Criteria - Conduit Grade PE100, SDR 13.6
44340154-40fd-5c51-b72f-ca905cedd0ed | note | Reference:TeamBinder Material Approval Number:
5474e9cc-baa9-54c6-9e6c-7d597e657ca8 | note | Method - Document Review
ae5d14dd-8324-582c-8138-0965a60bc2f1 | note | Frequency - Prior to commencement
17a59224-6ac1-5fac-8feb-dea03fc502f7 | note | Category - HP
b95ccf83-7f13-5428-bf7a-0ba32ead4b2f | note | Responsibility - PE/SE
59b47f2e-de72-5619-8f58-48788a16f282 | note | Verifying Documents - Teambinder approval number
0a0ae259-f9cb-5e48-86af-5535c2be972f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Grout
3e4ea3c6-b320-579c-a4e1-4196c854fd8d | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
d619d962-48a5-56d3-bedc-4360e8054d13 | note | Acceptance Criteria - N/A
c3911137-8046-5455-94a8-edd3b8f01b2a | note | Method - Document Review
7bbb0c3d-46dc-5408-8861-2dfb20a464d2 | note | Frequency - Prior to commencement
ea69a55c-bc20-52f3-8847-cb2307b629a2 | note | Category - HP
c5048fb7-fb20-5b64-bb1e-4992b098ab27 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminary Works/ Procedures
| checkpoint | 3.1 - Check that current revision drawings are being used
526500e9-582a-5230-95de-b785cd788e8a | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
e4ebf4ad-4cfc-5870-b506-351a62ba2edf | note | Acceptance Criteria - Drawing revison must be confirmed with the design manager
e86b54b6-cdf1-5b75-885a-b0a6980ac541 | note | Method - Document review
f372b4fb-5d00-5aeb-b963-b8d3e5e5a1e5 | note | Frequency - Prior to commencement
eb7ec909-bb18-5041-92ec-ff1f26285317 | note | Category - HP*
0753249b-30d8-5804-826a-2a5ebbfd5a5a | note | Responsibility - SE/PE/SPE
42d3bf9e-6746-5385-80c0-588b1f3b3bcc | note | Verifying Documents - Design drawings.
0b56e4b2-7795-5e60-9059-1e006a52341e | date | Date Completed:
| checkpoint | 3.2 - Auditor accreditation
f70c3f3b-f32c-538f-aa06-130d1e94a4d8 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
67d5d173-4e3b-5a00-97ec-de029562f4ef | note | Acceptance Criteria - Auditors are to be VESI accredited
32f74ca1-f4e5-5737-872f-2dbc0300abb8 | note | Method - Document review
dfc63961-d09d-5b6d-ba9b-d9e45bb53de2 | note | Frequency - Prior to commencement
8f593e91-1c95-5c89-854b-be595541b445 | note | Category - HP*
7887a15e-e703-561a-a3cb-a240c3fa6a02 | note | Responsibility - PE/SE
c6ebc7a7-93cd-58f8-a36b-f99c95b3f1fb | note | Verifying Documents - Teambinder approval number
3ade642d-e974-5804-99f2-ccc2a5cf4e3c | date | Date Completed:
| checkpoint | 3.3 - PE Welders Qualifications
c0a93a96-2802-5cb8-a972-4ae45a9b8633 | note | Reference - AS 2033, PIPA-POP-003
22f6b648-c64a-5595-b19a-dbda4934c334 | note | Acceptance Criteria - PE welders are to be qualified and regularly certified by a suitable RTO to PMBWELD301E
e1cb521a-8483-5c97-af1c-3fd97f786596 | note | Reference:Teambinder Hold point release number:
e55c3390-6106-58a9-9ee6-d2ede7b54777 | note | Method - Document review
849804fd-592b-57f5-adef-7b0d0b417fa4 | note | Frequency - Prior to commencement
c2e1f59d-cf47-5fc7-80f4-aa693d4e0ffe | note | Category - HP
faae7862-6e63-5ebb-b742-ef6e45ef70fc | note | Responsibility - SE/PE
9a1329ed-c99a-54d3-8c9a-07e5ef5cbe16 | note | Verifying Documents - Teambinder approval number
b076ef38-c4aa-508e-9a44-ea1528978473 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-out
ccd02d0b-1e2c-5c2a-92be-53729d1aff40 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003; cl5.10.13
7db81439-1769-52c5-a9d8-d489eebba60d | note | Acceptance Criteria - Set out line and level of drilling works.
86b562ab-6bff-575b-886d-4e9ca544cbe5 | note | Method - Set out line and level of drilling works.
2308aab4-2554-5e0d-89c4-5e734a9ab3dc | note | ○ Survey to mark out existing services.
c9381ae5-1ead-5cc1-8d54-4612bc78bbbc | note | ○ Must maintain a min. clearance as per VESI D&C 5.10.13.
c30b0bed-f157-5e2b-b870-03ed29d6710c | note | Frequency - Measure, Visual
cd392fe7-fcab-5fe6-bde1-d3db69026d25 | note | Category - Each element
fdc4b033-bc1a-5e59-b13b-fe64c84d0da6 | note | Responsibility - IP
709469a6-645a-5e34-9b16-022cbddd26ab | note | Verifying Documents - Surveyor, SE/PE/SPE
c05e1525-6646-5646-a268-7e0dd1ed902e | date | Date Completed:This ITP
| checkpoint | 4.2 - Draw ropes
afcf164e-21dd-58bf-a9a5-7dd620b1c908 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, AS4142
cd36b161-9117-5e59-a005-e8f512337bda | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
4bc42dab-37cb-5fd9-a54c-e6b8c2922b28 | note | Method - Document review/ Visual
21eefa28-cf19-5b12-80b5-9662131c8488 | note | Frequency - Prior to commencement
dbbc3444-5e63-5d68-aff3-59696ab7ce1f | note | Category - IP
21bcbc76-ff5e-5e2b-bdd5-884d2de57d53 | note | Responsibility - PE/SE
b23a1352-ee0a-515e-98a2-df24ca9c89e1 | note | Verifying Documents - Material compliance certificate
020410c0-cb55-5250-8822-aca504691d3e | date | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Conduit welding
4ce25c27-e154-5773-948c-0d1bf38ec272 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, PIPA-POP-003
fed80b2c-4994-5693-983f-73199e4cae9e | note | Acceptance Criteria - Joints are to be butt welded.
9faf490c-7455-5ff8-aa67-34cee2dd0a84 | note | ○ Weld map to be supplied and identify unique joint numbers.
0d4e6933-a8ca-561e-9569-73ac61afb929 | note | ○ Butt Welding records to be supplied.
647da021-29cd-5ea4-8767-0b0b02464fe1 | note | Method - Document review
78db6a44-7cbf-5797-aa10-6eb4fefffde0 | note | Frequency - All Joints
aa66a2c7-1164-5017-af0e-80f635d37cfe | note | Category - IP
15883d1f-31c5-5f8c-ba69-6b09c0a3fe51 | note | Responsibility - SE/Site Supervisor/Survey
3e88b158-b927-5a42-b397-d88956086e95 | note | Verifying Documents - Sign ITP, Butt Welding Records
775f27f6-8c93-5f70-840b-5211e1cee124 | date | Date Completed:
| checkpoint | 5.2 - Drill rig setout
4b2ef03f-f0ea-524b-8640-fce7489fd8c4 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
6d6b56c7-3cc2-57b7-bd40-cc044adc5ed6 | note | Acceptance Criteria - Location as per current Drill shot plans
e9045223-c39a-553c-9f64-39514c8ea575 | note | Method - Measure, Visual
5d73ba72-0da0-55bd-a8a7-9e37df5dfb49 | note | Frequency - Prior to commencement
ad654842-dc67-5d23-8983-d38048d5f163 | note | Category - IP
a5fdf361-b6e0-5520-b0a3-6437708215b7 | note | Responsibility - SE
68402971-158d-5935-a44a-30b23b7b0a17 | note | Verifying Documents - This ITP
98ff112b-abeb-56e9-8766-44fc9e02f5a9 | date | Date Completed:
| checkpoint | 5.3 - Installation of Pipeline (Trenchless method)
598f9a73-6093-5e34-9f87-84b7ebec0577 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03, VESI_URD_003
6ba82f20-47e6-5626-8556-6e92733c6dc8 | note | Acceptance Criteria - Drill to be installed as per the survey setout.
bf9b96fc-aaa4-5bfa-a43c-1ee6c0ed7e3d | note | ○ Bore logs to be supplied.
c02e1055-440f-56d0-a948-f817ed34fee1 | note | ○ When multiple conduits are installed into one bore hole care shall be taken to ensurethe conduits do not rotate during installation. Accurate detailing of conduit positions must be undertaken.
129d6e15-558b-55b9-9fec-981052286476 | note | Method - Document review, Visual inspection
cd66787c-3854-5411-ada5-824535138845 | note | Frequency - During pilot bore and conduit installation
efb091ef-011a-5ee9-8e08-0a3fe5d55beb | note | Category - WP
41c4ce52-10c0-5467-8cad-d2395c0569a8 | note | Responsibility - SE/Site Supervisor
241e41fb-5c13-5df4-9c23-b3c2aa672b14 | note | Verifying Documents - Bore logs
d0b33ab9-ce98-5760-ac2e-612b81f28532 | date | Date Completed:
| checkpoint | 5.4 - Plug pulling
e766b8fd-9cdd-5df0-916a-10e5a1219b00 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
6911bd1a-844e-58ce-ba01-40fe351993d0 | note | Acceptance Criteria - Mandrel with 90% of the pipe diameter to be pulled thrugh each conduit to ensure the conduit hasent been compressed.
7313b3c8-f1ff-5923-8fd5-48bbf81d3e41 | note | Method - Record and Review
602a9987-a96c-53a2-ae76-83734432dc97 | note | Frequency - All Pipe
e7430db4-d77f-502e-866f-294e67d94cbb | note | Category - HP*
33916ad1-c74c-560e-9c46-065b924f5c9f | note | Responsibility - SE/SPE
bbcf6bfd-c0eb-5ba0-b977-091785d0e99b | note | Verifying Documents - Sign ITP, Visual of pipe pull pictures. Subcontractor Test Record
d19a3f4b-7aa5-5a7c-a54b-e0d04614a75f | date | Date Completed:
| checkpoint | 5.5 - Draw rope
4bc12696-75cc-565e-b454-eeaecdad5a3b | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
b7288165-5256-563d-afc8-c74e37de3f94 | note | Acceptance Criteria - All draw ropes must be continious between shafts and have 2m slack in the shaft.
7c4bb466-d403-583d-8748-33d833b55330 | note | Method - Visual
9c113881-67fc-55c1-bb2f-85be3ccb3ac2 | note | Frequency - All Pipe
f35c0d98-ff94-576e-b4ee-a288374ca474 | note | Category - IP
3d68ca35-2809-50c3-868b-743cbd463586 | note | Responsibility - SE
6b413113-84f5-5a8f-8e7d-4b933fb4e39b | note | Verifying Documents - Sign ITP.
2e46d822-ea6f-544f-b984-d9482bc52afa | date | Date Completed:
| checkpoint | 5.6 - Auditing
77bca45c-0a78-57b7-9687-2fdc9255a922 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
116635f6-a946-5c86-a3f0-bfde470cc344 | note | Acceptance Criteria - Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
12939338-8c93-5eb7-940e-114d8d44abce | note | Method - Record and Review
ca234e3a-2a96-514b-8154-cd6a0b7a545e | note | Frequency - All Pipe
3bcf3ccd-47b7-513f-b65a-2529596a2db9 | note | Category - HP*
65739fc3-b013-582f-b31d-18447b0471e2 | note | Responsibility - SE
bc90cb0f-2e8a-5aa6-8110-9f76b460b055 | note | Verifying Documents - Sign ITP, Auditing Report
0eb2f303-b9d8-5e1a-b171-ade3cc815773 | date | Date Completed:
| checkpoint | 5.7 - Reinstatement
0675fd44-dd19-5c4a-bfcc-e80958bfaaa9 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
9d5542c7-7113-5bb8-8a21-5ca5fc071739 | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
8855e73b-7018-5fd7-8c25-f27a6aa61611 | note | Method - Visual
2c790064-5080-52e7-b002-0c43dbeb2400 | note | Frequency - Each shaft
23775305-ceb4-5ff1-bd7e-0096ab87c339 | note | Category - IP
7ec05128-ca93-5b37-98f3-297af6416371 | note | Responsibility - SE/Site Supervisor
0c99032b-d013-57df-8d36-10fe985bc752 | note | Verifying Documents - Sign ITP
9230cb13-abf9-59df-a5f9-d8de0e34a047 | date | Date Completed:
| checkpoint | 5.8 - Subcontractor ITP
f7054897-a74a-56be-a846-27a8ae6211e5 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
842e69c6-03c9-5b45-b074-3b11c6881beb | note | Acceptance Criteria - Acceptance and closeout of subcontractor ITP
7558f78d-225e-527e-af76-cd07e13ade3f | note | Method - Document review
881fd6d2-322d-5db7-a9eb-23dd10b7c2b5 | note | Frequency - Each element
d27fe65b-124b-5bf8-afab-c4352ec44802 | note | Category - IP
907385f4-ad58-5274-a3d7-371b03ead775 | note | Responsibility - SE/SPE
8bdd7c51-ec65-541e-825b-fbea17fb609b | note | Verifying Documents - Sign ITP Completed
ef6773d3-2daf-5887-9770-99ad9effc581 | date | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
4c3f0d0a-b7e1-5045-be52-e4ab917074f3 | note | Reference - JEMEE-DW-UG-10061100/01, JEMEE-DW-UG-10061100/02, JEMEE-DW-UG-10061100/03
168d00d2-5b51-5367-a274-b3539ededfff | note | Acceptance Criteria - Survey as built report to be compiled.
01603476-25a5-53a4-8089-0463446a60e7 | note | ○ Borelog obtained from subcontractor
8c6ed733-f5db-5c30-aba4-f2e5842047ce | note | ○ Autocad and PDF reports are to be supplied to:
d094d9ee-1068-524d-99b7-c45a55ff33d4 | note | Method - Document Review
fb1cfc7f-ab58-5e48-909a-739e3cab9baa | note | Frequency - Each element
c14af921-b599-5fda-a8d4-a54866a9400d | note | Category - IP
ffb53cfd-2c9f-5a9e-bd70-2e149bae0f9c | note | Responsibility - Surveyor, SE/PE/SPE
a422a380-4dac-545d-b38d-45da0dd7e7f0 | note | Verifying Documents - Survey As Report
b9a5d7bf-ad64-5314-9ed6-b25261b877a9 | date | Date Completed:
| checkpoint | 6.2 - Red-line / As-constructed IFC Drawings
d621ffbf-f4e6-562b-a177-504d31a12802 | note | Reference - MRPA Quality Management Plan
e676c5db-5014-547d-9e42-5a48eb0d27b8 | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
ea13b683-d49d-56c8-a72a-2ad6072fe852 | note | Method - Document Review
c0f5d327-c7da-59c8-82c9-57cc94f17e97 | note | Frequency - Once, after construction of the design package
6299a18a-0c4f-574b-b3dc-52b8bd742917 | note | Category - WP
488dff39-365d-5f11-8245-36a2b92fe1ca | note | Responsibility - SE/PE/SPE
f868facd-b069-542e-955b-163fed5845bd | note | Verifying Documents - This ITP
33fd4b8b-7e38-54d8-b7a0-e068194b1bea | date | Date Completed:
| checkpoint | Final Inspection
40ad701d-75f0-5791-bde1-1dca940a14a6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8ba6ec3b-7260-56cf-82bc-baedff33b8db | textbox | Name:
bfdd0459-cfe1-5068-8c40-27106bb3800f | textbox | Position:
59d384c8-4839-598c-8f17-e433b2600813 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-121-STR-CPD-Grout Pedestals & Bearings Rev 0 | itp | ITP-121-STR-CPD-Grout Pedestals & Bearings | 486706cb-0fd3-41ef-86bf-b4d28bcefea9
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
08814c56-325e-59fe-89a5-ffc4953e79f5 | note | Document Title: ITP-STR-CPD-Grout Pedestals & Bearings
b35788b6-d954-5fe8-8c65-bca83b54bd94 | note | ITP Description: CPD-Grout Pedestals & Bearings
b9621cde-10d0-5e91-8284-7a4bf7b4ac9c | note | ITP Number: 121
323d07ab-589f-5f84-a860-b5608d6c378e | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
b88f4b54-fb74-554b-8322-8ac43db86660 | note | Discipline (e.g. CIV/STR/RAIL): STR
60057c2c-8cc5-5078-894e-fc896f4bc1b4 | note | Revision Number: 0
11dcb7c3-c418-57bc-b52e-679a4a4913d9 | note | Revision Date: 19/01/2024
4e54fc55-4e8f-5c55-96c2-1ef04a36ca4e | note | ITP created by: Andrew Carlini
da2f3bda-7490-5fb0-a428-dc9579d6725b | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
47f28304-2040-5ec7-98e4-1f9e0eabd492 | note | Reference - VicRoads Section 610 Feb 2020
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Product Selection
5e9e32de-ecec-578f-8cc9-a8fa92363929 | note | Reference - IFC Drawings 610.28, 610.33
898a8e84-f212-58c0-bed4-140b95cac752 | note | Acceptance Criteria - Product to be selected based on the following criteria:
dc16ee35-bd61-51b3-8bb0-9dcba16c3a0e | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
c73518ce-20c7-50bd-8a71-e5ca0bb2daff | note | ii. have the required strength at 28 days as noted on the IFC drawings.
51148651-2f4f-57a1-8604-d239dd9264f9 | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
a3bd0b6f-80ec-544f-953a-bc9a62961074 | note | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
5155439a-4d9a-58b0-8ef9-e8548a679e63 | textbox | Enter: Teambinder Material Approval number
5bf9a5fe-43d1-5228-9a23-7f050e8ea776 | note | Method - Document Review
39d117c9-699c-5a02-9f00-9c57e44f2907 | note | Frequency - Once, for each product, prior to placement of product
58052465-d194-5e76-b894-490693124469 | note | Category - IP
41f72756-5fb1-5a08-93a1-5530e04c9c46 | note | Responsibility - Nominated Authority
fa14f771-94d6-5e21-962c-8172ec0705c5 | note | Verifying Documents - This ITP
cdd1926f-c1b9-50fe-9fbc-54a73ecd4696 | date | Date Completed:
| checkpoint | 2.2 - Curing Compound
b646eeae-9e6a-5d65-98ca-dc14a4f24c15 | note | Reference - 610.23 (d)
2db66a3c-bfb2-50d2-bce9-0758532bdff6 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
aeeec999-98ad-5e15-bf10-03cd85a9dfa4 | note | Note: This may be the same product used for the concrete curing
c76ae6c1-e866-5c6d-80c8-5c0b4af96c7b | textbox | Enter: Teambinder Material Approval number
318a9c61-aa48-5faa-9cd2-de167625834f | note | Method - Document Review
9c0f16f4-b630-5f29-878d-acb2cbb5c724 | note | Frequency - Once, for each product, prior to placement of product
07f1a7b0-840d-576d-ae00-151c6c876d88 | note | Category - IP
eb568ecf-cdc0-57e1-a13e-abb59ac15504 | note | Responsibility - Nominated Authority
a81774fc-9b02-54bb-906d-9594e758e66e | note | Verifying Documents - This ITP
1cbfc00a-614c-5b83-875a-c0da855544bd | date | Date Completed:
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Curing Methodology (for Concrete, Grout and Mortar)
8d23e36d-7e4e-5bfe-acad-490d83506a4c | note | Reference - 610.23 (a)
ea1caed0-f0ba-5fb1-b763-258a7c95da3a | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
f6004601-aa9e-5b9a-8556-751b7eaf73f5 | note | Note: This may be the same document used for the concrete curing.
d57f30a1-c3f6-50d4-93bc-24d242237b08 | textbox | Enter: Teambinder Correspondence Approval number
f5c5da43-dd49-5d8d-804e-2e0709e89169 | note | Method - Document Review
67a08bc2-baf2-5ebe-9287-71521ef07ef1 | note | Frequency - Once, 4 weeks prior to placement of product
f78fbbb2-a9e2-5466-b2cb-20ecf991c262 | note | Category - HP
0ddd3134-0e2f-5c3e-959f-ae010edce4a0 | note | Responsibility - Nominated Authority
d4353884-a8e1-5ed3-b540-38f1726abf28 | note | Verifying Documents - ConQA Hold Point Release
c2b04e3a-88eb-51a2-b9fd-47d8ce5f19f2 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
3bb92d15-6439-50d5-870d-6d1056d3a740 | note | Reference - MRPA Quality Management Plan
1d5155ae-3c28-51d6-b439-45e4bd4af72a | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
ce4d98a2-3fd3-59c8-b5c4-d9384b60c528 | note | Method - Document Review
88970b81-faa6-52b2-9197-42716c112850 | note | Frequency - Prior to starting Works and at regular intervals
a4f4912b-bef6-51ec-b2cb-50a89b08e35f | note | Category - HP*
bb1fc0e7-c5bd-5704-b1c0-a66ed04f2082 | note | Responsibility - All
a172a42c-f1ce-5248-8bfd-42ea12849a0d | note | Verifying Documents - This ITP
d9892098-d137-5836-9b56-066c76bf4a07 | date | Date Completed:
| checkpoint | 4.2 - Survey Set-out
3f2fddd4-a3c1-5e8a-a203-a1012775cacc | note | Reference - IFC Drawings 610.46 (a), Table 610.462 (Nov 2018), 610.47 (a) Table 610.472 (March/June 2019)
5b5b9cd7-bc1b-52df-8a91-6b910fcc4e4b | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
c2db3dfb-dab7-5373-9f95-e357e0b5ea2d | note | Note: Different revisions of 610 have different clause numbers
b0d9c523-6f2e-5ed6-b78e-ec448cab029c | note | Method - Measure, Visual
3256ca51-c9ed-5a45-bd59-cb2da384dd93 | note | Frequency - Each element
19fd1581-be84-5140-95d9-9354c7761916 | note | Category - IP
8ea849b5-c92f-5a2b-8254-bf581199dc79 | note | Responsibility - Surveyor, SE/PE/SPE
e5703f02-91ec-5b73-a6ab-592314cff871 | note | Verifying Documents - This ITP
8ec6aa2d-1e7d-5802-ba4b-20956eba984b | date | Date Completed:
| checkpoint | 4.3 - Construction Joint
ffdb4775-71af-5b0b-85be-55115bb467b9 | note | Reference - IFC Drawings 610.20 Fosroc Renderoc BB TDS
c8da7205-4de8-57dc-bef7-638c012ee07c | note | Acceptance Criteria - Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
899567fc-165e-59c6-babc-ecda361c5e9c | note | ○ Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
6b08134b-3a3e-5681-849b-8b33ecdbc677 | note | Method - Measure, Visual
07f02a97-2d26-5b3d-909b-6755a09df628 | note | Frequency - Each element
8ffc68fe-7d0e-547a-bee2-074fe91b30f3 | note | Category - IP
939f82c7-2e1d-5554-89c9-3387e4eefca5 | note | Responsibility - SE/PE/SPE
8d3c2b74-0fc7-5083-b861-afbb7e2a88a2 | note | Verifying Documents - This ITP
e5aff094-d94d-51d8-bfab-47e8b8f9c80d | date | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Construction & Placement
b04740d4-9114-5b56-a15b-868a0851200e | note | Reference - IFC Drawings
f3f7d09f-3358-51b0-8610-d4291d584acc | note | Acceptance Criteria - Dimensions in plan as per drawings (typically +50mm all around).
84b58138-bd9f-5760-8236-60493f15411d | note | ○ Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
d70800bd-3339-557a-8671-349dff358bb9 | note | ○ Any cast in componentry (ferrules, conduit etc.) secure.
dc7f82ba-1d6d-5a53-ae80-bb50fe552c30 | note | Method - Measure, Visual
5131f81d-ea47-5fd1-8564-3fb91762cebf | note | Frequency - Each element
d90445ca-3074-58ce-8c20-bfebe916a1fb | note | Category - IP
8fbef92b-7479-5892-aab2-09562c250850 | note | Responsibility - SE/PE/SPE
865eac12-1fed-53fd-9b48-afdde09bedd8 | note | Verifying Documents - This ITP
280e7a0f-55df-54a6-881b-3b5c6b1fd578 | date | Date Completed:
| checkpoint | 5.2 - Pre-pour Inspection
d65b0443-e813-5525-9187-67e7f411f678 | note | Reference - IFC Drawings 610.18
e41e07de-a4b2-508d-b8f3-f994ea440736 | note | Acceptance Criteria - Formwork location and RLs comply.
f87d7193-bf84-5e4e-b08b-e5c4a673a7f3 | note | ○ Any reinforcement has the required cover.
761a5bf5-96a7-5f41-aff7-f3eee0561321 | note | ○ Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
ebb8b60e-eda8-59b8-8651-b709b410496e | note | Method - Measure, Visual
89ed09de-24d9-5a83-9d53-c06a424da0f6 | note | Frequency - Each element
b1ca772d-7de1-5867-a001-1e1b61837fb3 | note | Category - IP
a706cd8d-96f7-5b85-9076-9c9e3ab9ceca | note | Responsibility - SE/PE/SPE
fb7f42ee-351b-5058-9cbb-06942e801198 | note | Verifying Documents - This ITP
b5f63541-5918-5e5f-8ce6-35513af9c346 | date | Date Completed:
| checkpoint | 5.3 - Weather Conditions
5787d4f4-74d2-59c0-b166-7d324fc1cc71 | note | Reference - 610.17 610.17 (a) & (e) Table 610.171
0d284465-b7e5-5bb5-8db5-3876c3df37cf | note | Acceptance Criteria - All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
92db101e-f037-51ac-bf1b-99607ad54212 | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
1bdf2663-30bb-5fb8-a054-0fccd5c4850a | note | Record: Required information on the Grout Pour Record.
02613f08-e46f-50ef-b558-065a226e918e | note | Method - Measure, Visual
d7f99928-ac0a-5dce-af5a-b03a8b1ef1bf | note | Frequency - Each element
83b97806-70e6-58da-be04-4f955fc404e7 | note | Category - IP
8092aeb0-214b-5a69-92fc-ae44ac8cd01a | note | Responsibility - Foreman, SE/PE/SPE
ed48f924-a25c-59e3-b0f7-3a256df489d9 | note | Verifying Documents - This ITP
6908a249-f376-508d-aa9a-ba286835e228 | date | Date Completed:
| checkpoint | 5.4 - Mixing Product
6c31f4c9-a0ed-5e62-a9d2-c541d788dd8e | note | Reference - Product TDS 610.28
cccb1905-0f94-5d49-8e5f-5d301c3263b2 | note | Acceptance Criteria - Size of mixer should match the application.
c8d6847a-a750-5319-bed8-689d3de400e9 | note | ○ Only whole bags to be mixed with potable water.
d74e1a18-e04c-5352-a0ce-cd6942abec62 | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
41ba46bd-bb79-5b75-8ede-0c03eaa6ebd1 | note | ○ Product poured into the mixer slowly.
72b20d1d-4dff-5147-8459-d67777fd5f7d | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
9ec75bec-e8bf-5ec7-9d6a-4a58004a6688 | textbox | Enter: Required information on the Grout Pour Record.
749c4721-a4f5-5d08-a41e-f7a45c04ec2b | note | Method - Measure, Visual
cb0157eb-bb32-5c0f-9c59-8476947455b6 | note | Frequency - Each batch
cc6512f2-90da-5e53-a062-72f08c4506b7 | note | Category - IP
95aa8fe9-54d5-5692-b951-78193fd00033 | note | Responsibility - SE/PE/SPE
8cb463c7-4ffd-50ae-bad9-8a4df7990940 | note | Verifying Documents - This ITP
0517cb28-bf1e-500a-bccb-c0dbdb5a3217 | date | Date Completed:
| checkpoint | 5.5 - Product Testing - Compressive Strength Cubes
4e54cdfe-c29c-596f-9385-a2afcc82bd60 | note | Reference - 610.28, 610.33
f9304faf-6d41-5f3c-b05e-3b00d599c182 | note | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
d0e66ae1-c350-5948-8bd5-15424ba86003 | note | ○ Testing is be in accordance with the following frequencies:
6993151e-e413-5c63-a7ff-d430260665e5 | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
359edb9e-8001-56c0-a71a-e06ea13a5240 | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
3a4ae9f6-2ff2-5c7f-bf1c-4420c6955b7b | textbox | Enter: Required information on the Grout Pour Record.
ff22c1e9-f025-5e59-8452-6db741fde58f | note | Method - Test
442077eb-ebd2-5a56-bc89-aea23bb65ce7 | note | Frequency - Each element
dc34f1af-431d-59d6-a83a-ccb6d777fdbd | note | Category - IP
cf092b39-2f8d-5b43-998a-418d723ecf40 | note | Responsibility - Tester, SE/PE/SPE
f8e4ea9c-cb2b-5dee-aff7-32b87fbc146e | note | Verifying Documents - This ITP
3a38d5c4-ae93-5cf4-ae59-80e3c1de186c | date | Date Completed:
| checkpoint | 5.6 - Placement & Compaction
769ccf39-38cf-5147-af3a-99371ccc2018 | note | Reference - Product TDS
631a505f-fdbc-5047-a00d-36912be0de82 | note | Acceptance Criteria - All batches are traceable.
f51f375b-2b96-5bf9-bd91-bb94d13166f1 | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
07aa46cc-78bc-5e72-8f0c-c63499e4e3f7 | note | ○ Product should flow to all areas and self consolidate.
1b5adad3-0c7a-52d5-bc9a-41494a628c29 | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
9b141031-c302-5341-a815-e0996a78500f | textbox | Enter: Required information on the Grout Pour Record
af779cfe-c395-5b17-b9a6-58d43a5d5d09 | note | Method - Visual
288c68aa-a5fe-548a-8848-05963508ff92 | note | Frequency - Each element
99e0f8db-dd65-58f6-a13c-dbf2a0b31abf | note | Category - IP
66921a70-f379-55a0-814d-20f86d12bea9 | note | Responsibility - Foreman, SE/PE/SPE
c05ea0eb-904c-5d26-b023-9fa8be24406c | note | Verifying Documents - This ITP
fbf63707-c4e3-515c-9e3b-dc06e4332cb4 | date | Date Completed:
| checkpoint | 5.7 - Surface Finishes
6ad086c0-7faf-50e8-be76-09e4e493a7bc | note | Reference - 610.28
b26c306d-120a-592c-b7c1-dadb1c401460 | note | Acceptance Criteria - Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
6cc052b9-9766-5e06-97c9-193654da6cc1 | note | Method - Visual
1b7d022b-1fbf-5d34-b2ab-7dd4fb7b07a9 | note | Frequency - Each element
b2b857bb-1e43-5030-924d-116c53109bdb | note | Category - IP
5a369663-005b-50fb-b970-a3bb32269fac | note | Responsibility - Foreman, SE/PE/SPE
ac33b703-5887-5547-a543-38ed59394f60 | note | Verifying Documents - This ITP
03726ee4-05b3-5a5e-97c6-1fd9546d8300 | date | Date Completed:
| checkpoint | 5.8 - Curing
f4230b7e-0d8d-52b6-b887-8a9a432d0bf7 | note | Reference - Curing Methodology 610.23 Table 610.231
d7831af3-542c-593d-b4d7-3725ee96a392 | note | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
4f0bf8db-75df-5086-bdc9-01546b037310 | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
cc3dd402-29be-55e8-9e6f-4db85234ba2f | note | Method - Visual
573dd916-cdb8-582d-be83-d8e5e20db330 | note | Frequency - Each element
7513f740-fd8d-5721-a0c4-48b2cfdcecb9 | note | Category - IP
734fdc82-cb36-59d9-8238-f60530ba9b59 | note | Responsibility - Foreman, SE/PE/SPE
16ecd117-dd27-5d06-b7e6-70c02132b83f | note | Verifying Documents - This ITP
0b22a83d-b5b8-55d0-9edf-7824a99f85cb | date | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Compressive Strength Test Results
15e938e2-54b2-5819-9dee-2eb13a5d3679 | note | Reference - IFC Drawings, Product TDS
cfdc2f6e-f1f1-5c43-a94b-e7d1fa5feac5 | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
8643f4ce-4219-58f2-9d62-ce85299d5e36 | note | ○ 28 day compressive strength per sample comply with the design strength.
89681cb5-09ca-5a21-8639-86a1180a5ec2 | note | Attach: Compressive Strength Test Results
cf407bfc-c22e-51ee-8cc6-5aeb9fc536c5 | note | Method - Document Review
fd753140-c061-5752-b033-1aa9a67cc53d | note | Frequency - Each cube
e8c1a335-7bfa-5108-bb44-3c0af9aaeeb2 | note | Category - IP
839b1b12-4afb-54a9-9c13-c7f352e236aa | note | Responsibility - SE/PE/SPE
d36250c8-3369-5842-8e3d-fa2375009a32 | note | Verifying Documents - This ITP
79b77633-93a5-5667-b74b-4d1c274c8bb0 | date | Date Completed:
| checkpoint | 6.2 - Surface Inspection - Cracks
7308da1a-e512-5e74-a20a-a259d794921b | note | Reference - 610.24
c60e5a04-cdd3-5845-a8c4-c5be22923aaa | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
e567c59f-d159-5eb9-ae83-cb279bd196f4 | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
8053f03f-17df-5d6d-a9fd-4d3f4a61f4a1 | note | Method - Visual, Measure
22ee1c20-34c6-5f92-bc51-3e5ab862aecd | note | Frequency - Each element
4276d6ac-ce4b-5a29-aeae-ab16bb7a2308 | note | Category - IP
da318bee-97d0-5ab6-b19b-79b9bb2cc92a | note | Responsibility - SE/PE/SPE
801d7990-c157-504f-af91-4ac05309582e | note | Verifying Documents - This ITP
ad485846-b847-52c0-98bd-e2c226c685e7 | date | Date Completed:
| checkpoint | 6.3 - Surface Inspection - Surface Finish
76488c40-7944-5b49-910b-3f255fd916b5 | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
dd17e992-a9e1-5f7b-9268-2357bb72ca0c | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
ecf32577-7124-56a3-9caa-6b4eed65f885 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
780d6f58-eabb-5a0c-b7a2-99752d76d0ef | note | Method - Visual
18333753-f2f4-536c-b99d-e6c1e4382be6 | note | Frequency - Each element
fed9f6de-15d9-5163-87a4-ab47ea364cf5 | note | Category - IP
86afebf2-f67f-5cd0-812c-b920c9cd9822 | note | Responsibility - SE/PE/SPE
877912ae-7638-5ad0-8945-973ae86aad75 | note | Verifying Documents - This ITP
5ae6fe32-5351-52a5-9777-4aafa2a62da6 | date | Date Completed:
| checkpoint | 6.4 - Measurement of Concrete Cover
c4f0f327-4aac-5356-ba76-3ec955f6ea56 | note | Reference - 610.34
1dc7dd31-359f-55f2-9f59-41db29e0190e | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
50aac30e-28fe-5cb4-a7f3-4d609a3f54e8 | note | ○ Minimum 10 no. measurements recorded in each area.
e46989f9-acaa-5668-a23b-dd0e69520447 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
d0cf5f61-d395-538d-82b4-080d2800a981 | note | Attach: Covermeter Check Record
bd2a5d23-cc37-516a-af26-a0c7e6da87cd | note | Method - Measure
3948fa03-7c3e-5105-b00b-fea73d172a09 | note | Frequency - Each element
ea177b7c-bbaa-50b7-9931-d28a5694ef31 | note | Category - IP
4f5b092a-f64b-5f16-b239-4e9f5292aac0 | note | Responsibility - SE/PE/SPE
a23a0d7b-b585-5083-a2f2-9375a4bec7c7 | note | Verifying Documents - This ITP
33c0ee9b-81ad-576e-ab96-2bcc80213a20 | date | Date Completed:
| checkpoint | 6.5 - As-built Survey
3531dc5c-5ea9-58e6-a8db-952eb3fb5e30 | note | Reference - IFC Drawings 610.47 (a), Table 610.472
1586b1c9-7faa-5262-8a8a-d4e1ec3e644d | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
a3d24cf7-f3a8-566a-9768-196676a302af | note | ○ Reduced level ±2.5mm
9925e5b9-e51a-51d4-93df-e814627ac8bf | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
90d15f94-b964-53b5-a8c3-3d64efbe8969 | note | ○ Deviation from flat surface ±1mm
4a8e1723-c630-51eb-9cd9-483c4de4b608 | note | Note: Different revisions of 610 have different clause numbers
1f38e466-b4d1-5f1b-8888-ba94d6ff3a36 | note | Attach: Survey As-builts / Survey Report
54ab0f91-7c8b-5f1b-9aa1-7818390157bd | note | Method - Document Review
bc2d727d-8f4c-5756-8269-420434b0e85d | note | Frequency - Each element
52670ba1-fdf2-58f8-a66f-980f4ec27d93 | note | Category - IP
c48e5ef0-86bd-556c-9a85-0901052cceb3 | note | Responsibility - Surveyor, PE/SE/SPE
77456f19-a522-5df1-8294-bf620930d5a4 | note | Verifying Documents - This ITP
64f55d70-74de-55b8-85f1-d69fb9cf27be | date | Date Completed:
| checkpoint | 6.6 - Non-conformance Report (NCR) Closure
011b2a17-bd35-59bd-9e19-d7f25e564a4b | note | Reference - MRPA Quality Management Plan
4cfb7446-d587-545f-8379-505592a41d98 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
90b164b7-21f0-51d4-9077-43baba6d40ad | note | Method - Document Review
5300e428-f6e3-57b0-a34d-a3ed58209806 | note | Frequency - Once, prior to closure of this lot / element / Work area
f725fa7a-7da0-5b6b-8682-b6013973d95b | note | Category - HP*
3233d283-6872-5ea3-92df-945814dd2e58 | note | Responsibility - PE/SE/SPE
bf3b69c9-369a-53cf-89bf-6335a89dd916 | note | Verifying Documents - This ITP
8e855e76-d921-5a94-817c-ebc797b1b48a | date | Date Completed:
| checkpoint | Final Inspection
0bdc67cc-f3ea-5bef-aff7-0591adaa72ee | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
b21dfa14-2034-5262-9ed7-942b80d44c45 | textbox | Name:
b97377f8-ea00-5cb6-8afe-e0bdefe4112d | textbox | Position:
92eaaed0-5aaf-5a80-86d3-d14b912989f3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 1 | itp | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation | dcbcfbeb-c210-4449-9a89-a119dcf5f8e1
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
f6383529-49d8-56eb-ba06-5a01383d031b | note | Document Title: ITP-122-STR-CPD -Precast Barriers and Kerbs Installation
5c9abf57-444c-504f-aeae-cdd52928671e | note | ITP Description: CPD -Precast Barriers and Kerbs Installation
a7c6cc13-9e0f-50cc-9188-0fa997489897 | note | ITP Number: 122
e5135bd5-42ec-52a5-ae31-6770f70488f6 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
54136beb-d494-5e74-8917-1440cb91e7ee | note | Discipline (e.g. CIV/STR/RAIL): STR
7bb2518c-f0f3-5695-bb7e-4be3bd26541d | note | Revision Number: 1
d546f5a8-0ea2-507b-9f1b-4b18b69fe2ae | note | Revision Date: 19/01/2024
7694ff07-8845-5046-8ca1-a22ff65407f0 | note | ITP created by: Andrew Carlini
97b9c826-d04a-5955-9101-113af18911cc | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
039fe781-83dd-5276-ba09-09a136e06c59 | note | Reference - VicRoads Section 610 Feb 2020
| checkpoint | 1.2 - Non Dependent
044524f2-02b0-5c30-843e-64d2a39ad16b | note | Reference - VicRoads Section 620 May 2009
| checkpoint | 1.3 - Non Dependent
c83d3581-d20f-5258-8021-9a95aa8a8f2c | note | Reference - VicRoads Section 630 October 2013
| checkpoint | 1.4 - Non Dependent
ba43cb52-c44e-51f1-9704-8f590cb759f4 | note | Reference - VicRoads Section 670 October 2013
| checkpoint | 1.5 - Non Dependent
6399ae26-b717-542f-8a6d-ef9843b35fa0 | note | Reference - VicRoads Section 671 October 2013
| section | 2. Preliminaries Materials
| checkpoint | 2.1 - Grout
c8d381c3-5677-5694-83c1-b21c57b0eabd | note | Reference - MRPA Quality Management Plan
619dd369-9d62-53f5-88d0-e1420f0960da | note | Acceptance Criteria - Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
90526186-0ee6-588d-ba6c-0007754829d3 | textbox | Enter: Teambinder Material Approval number
dfa0979a-2190-52aa-9ce3-5f87f5abeb6a | note | Method - Document Review
d06cdcb6-ccae-52a0-89d6-699a8dc39aee | note | Frequency - Once, for each product
1323e4f6-1c4c-5ef4-a735-2be1cd1f104b | note | Category - HP
df4bc97b-9954-5a15-988f-f2e4cec31d16 | note | Responsibility - Nominated Authority
05ebd81f-6c46-5c69-a561-2a06515b588f | note | Verifying Documents - This ITP
0907ca29-effc-5d86-8b6d-c64d880a3740 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Shims
f178c70b-fed4-5cc4-a0a2-3e2137bee850 | note | Reference - MRPA Quality Management Plan
c4ea7f71-a1ee-53bb-afb0-e50e1dce4cf5 | note | Acceptance Criteria - Details of the Shims to be placed beneath the precast elements to be submitted for review to the Nominated Authority.
c242a327-be07-5dad-ba67-4e13331b8095 | textbox | Enter: Teambinder Material Approval number
aedc183a-2216-5eda-b168-84839943b329 | note | Method - Document Review
05fa81f7-214c-5b7b-aff4-d772bffd09fe | note | Frequency - Once, for each product
979fc28f-e88d-58e4-b1c7-bbc502e8ba74 | note | Category - HP
7d1f7e66-aba7-50c1-a2a2-55ed5b8a413c | note | Responsibility - Nominated Authority
18a6c869-def1-5870-8fda-a37578262ae9 | note | Verifying Documents - This ITP
09e06f68-e9c5-5a34-9f9d-3b68240d0bf6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bitumen Board
21e3e88d-5dd8-5761-8a8a-22660cd9c9db | note | Reference - MRPA Quality Management Plan
b9b58b7e-8769-57c3-a7a7-30afba18ac24 | note | Acceptance Criteria - Details of the Bitumen Board to be placed between the precast elements to be submitted for review to the Nominated Authority.
55fbce2c-7990-5b24-b747-767a57ac6283 | textbox | Enter: Teambinder Material Approval number
8cf47468-cb1a-5172-b455-30f29c81c098 | note | Method - Document Review
292a0c1a-452c-5f3f-b60c-e827f56a2aee | note | Frequency - Once, for each product
5a8cbdd1-a047-5898-a3cd-f218f0fa3ce2 | note | Category - HP
e8c4ff70-db77-5732-8db3-bdbf1b52d0f3 | note | Responsibility - Nominated Authority
b5932c3b-4311-5414-b81e-271818fd0486 | note | Verifying Documents - This ITP
c80d5ac7-3530-59ea-9a33-9c5117101c58 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Abelflex
38b4ff9f-7160-56dd-9aea-a46a597c1cfb | note | Reference - MRPA Quality Management Plan
b8a5d2d1-0b46-5da2-ba5d-d457e8279a76 | note | Acceptance Criteria - Details of the Abelflex to be placed between the precast elements to be submitted for review to the Nominated Authority.
14214c45-b509-5c3a-a7ea-5824990a09bc | textbox | Enter: Teambinder Material Approval number
cf4e16b1-dd4d-5d29-8db1-37d1300d3815 | note | Method - Document Review
3d07a681-fafa-5c2e-b3e3-080a59141c43 | note | Frequency - Once, for each product
77e79fe5-1c75-5b46-9c30-df5c0bf432ff | note | Category - HP
717c139c-efa1-5abc-9897-155bc48b3985 | note | Responsibility - Nominated Authority
9b4644ca-415f-588b-818a-9b1e2a7bc3b4 | note | Verifying Documents - This ITP
c37000ad-1ba4-5812-96e7-6224f438228d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Precast Elements
d07805be-8880-518c-9200-5f32dfec4bfa | note | Reference - IFC Drawings VR 610
c508fe9c-299e-554d-a15b-e2ede3136b2a | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
c0e409a3-f1de-5ec3-9f5a-57372e0a384b | note | i. Certificate of Compliance / Birth Certificate
ddf3f85c-7cc6-5e1b-a617-08d402d1c9ae | note | ii. Compressive strength test results
9aee2bfb-46c9-5b15-89fc-029b8b06a4b4 | note | iii. Precast Lifting Design
251debd4-fa4f-5938-9269-c1911bd8ee53 | note | iv. Pre-pour check sheet / ITP
f2ae5362-ce4b-51b6-a125-2c1b3238125f | note | v. Post-pour check sheet / ITP
f05d37b4-e45f-59dc-93f6-e71f8623530b | note | vi. Covermeter check record
d79f9f1b-7e19-5077-b4b3-1b62579830e0 | note | vii. Record of dimensional measurements
2f3d0aef-f3fe-564e-b971-81dc98730b05 | note | All above documents are uploaded into corresponding Worklot.
ebc6ac92-729c-52e2-8393-0040347ad3ee | note | Method - Document Review
d16b979d-0c9b-5b91-9bac-219203687690 | note | Frequency - Each element
22895b96-2e7c-5c97-a4db-bd8e18203be7 | note | Category - IP
74dbed88-f264-5368-88ef-5acc5bd36b2c | note | Responsibility - PE/SE/SPE
4a96ab7d-5971-5761-98a3-9add1573f8ea | note | Verifying Documents - This ITP
a46a7a70-0fe9-5d2b-9793-a0e03a89f5dd | date | Date Completed:
| checkpoint | 3.2 - Bridge Deck / Foundation Compressive Strength
25ebcb7d-591d-5c9e-8268-e606c81bbcfa | note | Reference - 671.03
2c597354-f156-5dd2-aa68-fcccfa118b8e | note | Acceptance Criteria - For Preccast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
f2143ff4-039f-5686-87b2-58a7faf36b76 | note | Method - Document Review
c6ca7946-d0ac-5728-88e2-814f45415aec | note | Frequency - Each installation location
c5e08dd0-9eb1-5007-8f1e-c5e369841dbd | note | Category - HP*
52f8c2f7-6118-5fd8-b2c8-91cab75aa73f | note | Responsibility - SE/PE/SPE
0ec87aa1-f127-53ce-a24b-3d49a0b11344 | note | Verifying Documents - This ITP
aba0e334-dd71-55b9-a52c-1ce9b134b14f | date | Date Completed:
| section | 4. Pre-installation Activities
| checkpoint | 4.1 - IFC Drawings
e37db948-2665-50bd-9128-6abb70702539 | note | Reference - MRPA Quality Management Plan
6a0ec849-08af-56a7-b0e2-113d4adf6e37 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
b745af10-29a3-544c-aea8-152efbc1959e | note | Method - Document Review
ac430811-9391-54c0-b4a8-0f8594e6b6a1 | note | Frequency - Prior to starting Works and at regular intervals
ba528a03-ab05-5f2c-93eb-f6ea0d3deec5 | note | Category - HP*
ac5b1d0a-b9d5-5709-adb6-e33abe6180a5 | note | Responsibility - All
b78e7b1c-b70b-53b9-bc80-9ba6fc1a74b5 | note | Verifying Documents - This ITP Signed Off
0f8c14ca-4075-51d5-b2b1-33eef2018f3e | date | Date Completed:
| checkpoint | 4.2 - Survey Set-out of Precast Elements
a48747ab-b45c-59f4-92a4-ccca276aaba4 | note | Reference - IFC Drawings
ff5772f8-9349-5c04-9c87-ace9263472b8 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
9b63a396-4ac0-5a47-a2c1-b2e8fc445d1d | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
4d0dad05-753a-57d6-aee4-f6725dc943ed | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
e890f311-3439-54a7-93bc-35105d3b396c | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
90c3e77b-0bf4-5a69-a2d0-a76dd04a881d | note | Method - Measure, Visual
b7618d06-41b0-5cea-87fc-b9b9e99b93db | note | Frequency - Each element
4fa6ddb7-a2a9-52ea-86ba-856efd6326af | note | Category - IP
3210137a-6d46-5ea0-93ab-0b5261ff2495 | note | Responsibility - Surveyor, SE/PE/SPE
13ce24e6-13c9-5e2d-b0fc-87a9ad5b742f | note | Verifying Documents - This ITP
037eea51-3acd-5c0e-a38a-ed61e3f1adb9 | date | Date Completed:
| checkpoint | 4.3 - Bearing Shims or Bearing Strip Placement or Mortar Pads
2bb11bef-286e-55a8-924a-04f6175d69a8 | note | Reference - IFC Drawings
560f2b28-fac3-589f-80a5-b9a8cdc4b642 | note | Acceptance Criteria - Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
d502ee49-70ce-54a1-ac18-1e0046d98074 | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
5535a376-c680-5067-b1bc-38f367cc546b | note | Method - Measure, Visual
eca329f5-e9f3-5357-a4ee-51a21572255f | note | Frequency - Where applicable, each installation location
a9fe7921-956d-58fd-888e-e12e1f672b4b | note | Category - IP
57b3b62c-d9fd-5c1f-ba5b-f3b7d6a90538 | note | Responsibility - Surveyor, SE/PE/SPE
e5b3fdef-65d7-5eea-a8b0-5eef3a1d34ec | note | Verifying Documents - This ITP
45d8d7ea-6a23-5b8e-880e-a84c05f22bcd | date | Date Completed:
| checkpoint | 4.4 - Bitumen Board and Ableflex placement
cede9589-61c7-5871-abfb-cc552eab3b5a | note | Reference - IFC Drawings
32e2dda7-3552-58b5-96ea-d20111c42931 | note | Acceptance Criteria - Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
39b9c2d0-b2e6-56ab-9036-a39154ade0ea | note | Method - Measure, Visual
6312929f-2d1a-5756-a116-5e2f74fbb9cb | note | Frequency - Where applicable, each installation location
1920d53a-c5ff-58e2-bc49-4b811abbb173 | note | Category - IP
8d6f5d5c-dfff-5dcb-86b2-a71269f9e0d5 | note | Responsibility - Surveyor, SE/PE/SPE
009af049-21b5-572f-b2bb-540954eb21cb | note | Verifying Documents - This ITP
db836cb4-8e42-5ac2-ab8a-8ccd529377aa | date | Date Completed:
| checkpoint | 4.5 - Precast kerbs roughened surface
604639ae-b4dd-5ffe-8a79-eb385a0f1ecc | note | Reference - IFC Drawings Section 610.20
7fca641c-2afe-5e4f-bd85-61f63a318825 | note | Acceptance Criteria - Roughened surface means concrete surface shall be roughned as construction joint in accordance with IFC drawings and VR Section 610.20
2c93be35-48a3-5bf4-994a-c965d472bec3 | note | Method - Visual
d350928f-2a9f-5ff6-aae8-93cfb9dbc541 | note | Frequency - Each element
7271d59c-ff5e-579e-8472-d8e5e809be25 | note | Category - IP
cb29ff7e-ce3b-5f78-a22a-9c294cfea18d | note | Responsibility - Surveyor, SE/PE/SPE
4a3b3760-2a2c-54fc-bb78-8de2fcb3202f | note | Verifying Documents - This ITP Signed Off
ac8928c1-429e-55ec-9782-f1cc6c0a6d42 | date | Date Completed:
| section | 5. Installation Activities
| checkpoint | 5.1 - Precast Handling
1b05d33c-5e30-5d5b-b9d3-cb7aea2f68c8 | note | Reference - 620.07 Crane Lift Study
8b5235d5-ff31-55b2-a3a4-6a04f0a2e4ad | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
2ffdb81b-fee6-5a86-aa0d-db6a098000d6 | note | Method - Visual
c57a54d9-1b01-586b-a6fc-ef33eb0c52df | note | Frequency - Each element
535d1f66-43a5-58ad-8005-a2dbb480f07a | note | Category - IP
9b33ff38-2182-5bb1-ae84-20f04a738d9a | note | Responsibility - SE/PE/SPE
5795b6d1-bb15-567e-96c0-d7e69da033d5 | note | Verifying Documents - This ITP
815d4b7d-c0e1-5fcc-b72e-ffce79be8880 | date | Date Completed:
| checkpoint | 5.2 - Precast Placement
09287f00-8b53-5976-9337-41143fbc46f1 | note | Reference - IFC Drawings VR 670.05
5e0df7b1-5013-5998-8919-c8cdb417513f | note | Acceptance Criteria - Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
6a735383-c07e-5004-b306-cfe0f3c8ddf4 | note | Adjustments to be made to achieve following tolerances:
4fbfaec4-dc2e-5cf6-a245-f522a807d909 | note | (a) Departure from plan position .... 25mm
a53e3333-00a6-57cb-bec2-a73dc738a7e8 | note | (b) Departure from alignment ........ 5mm
abb86bb6-383b-5a47-a940-2c7b1f1a12fa | note | (c) Irregularities in alignment ......... 3mm in 3m
56d59de2-f16d-59dc-9e35-5a386a877379 | note | (d) Variation in joint gap width ....... 3mm
019b0ed9-1e36-57f3-8dd6-f4e336f0d342 | note | (e) Vertically of posts, panels, balusters and openings ... 2mm
cbd38737-91a2-5213-baa1-e6ee812fbcd1 | note | ○ The nominal gap between elements is as per the IFC Drawings.
08d2951a-0fa7-5881-81b7-10df7c63b578 | note | Method - Measure, Visual
f0778c63-c904-5455-a04b-f7e153be66d5 | note | Frequency - Each element
ea1ebd64-c37d-50f1-9f3b-0c6bef2e6424 | note | Category - IP
3ce0406c-f01b-5969-8d85-f6dda85847cd | note | Responsibility - Surveyor, SE/PE/SPE
62cca861-2810-5909-883d-007f3fdfa3a4 | note | Verifying Documents - This ITP
d991d9c3-cf97-5b7a-98b2-ac1a407feadc | date | Date Completed:
| checkpoint | 5.3 - Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
1819b323-7a0b-5794-8379-a43e5ca2c7ab | note | Reference - IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
067993dc-7c87-5cae-b4f2-efdbfcbe8e3c | note | Acceptance Criteria - Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
cac3936e-049c-5b18-b35e-2c75bb294153 | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
db5a2d51-c086-5d3d-b1fd-e98402ed3ace | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
d0e8018c-887b-546b-9a8f-b2c8cb11b3d4 | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
77539608-2b04-53d6-a288-62ef5f645722 | note | Method - Visual
f619ad8e-9b34-560f-8d86-56d868970f3d | note | Frequency - Where applicable, each bolted connection
38eaa1e8-5485-54d7-ba1a-77d92ecdab4a | note | Category - IP
aaa4dc79-66da-55ed-9820-3c6a5303c6e9 | note | Responsibility - SE/PE/SPE
75d0b9ac-9ac5-58e4-afa3-1c284bf97715 | note | Verifying Documents - This ITP
f86bc712-e3b0-51d4-a0ce-6331e9e21161 | date | Date Completed:
| checkpoint | 5.4 - Precast Traceability
f57ab36e-fa41-533c-af8e-2aca81cb706d | note | Reference - 620.09
855415d0-324e-56da-bb43-24f196d348dd | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
018c7c76-1693-560b-8dc7-0d8308351e61 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
cf6b1ecb-fc6c-5c78-9125-acf056b1e7fc | note | Method - Visual
63584100-4f9b-5094-92f5-aa34de8df9b5 | note | Frequency - Each element
c5bd0559-8955-5c80-8942-610181b4210f | note | Category - IP
d2dc337c-25e5-53c1-8e36-d09558e21c21 | note | Responsibility - SE/PE/SPE
c63867e8-b7d9-54c1-a8c1-1bd784eb995b | note | Verifying Documents - This ITP
bfde12e4-6966-5408-90e6-eab6ef5b525b | date | Date Completed:
| section | 6. Post-installation Activities
| checkpoint | 6.1 - As-built Survey
6391522d-8675-5de3-9ef9-455f4752ee2b | note | Reference - IFC Drawings VR 670.05
40f36976-ae58-56ce-9b23-cc3cacdc3966 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
9ead845a-4420-514c-b706-6ee5feef7412 | note | (a) Departure from plan position: 25 mm
53bd0c4d-c12e-5111-86d1-74937de01e1a | note | (b) Departure from alignment: 5 mm
98a83268-a7a2-5183-9f6f-e227811eab67 | note | (c) Irregularities in alignment 3 mm in 3 m
ac36c247-edca-53e8-86a4-aa58dd3a15f9 | note | (d) Variation in joint gap width 3 mm
a99f9905-8064-5e3c-a030-54f929687048 | note | (e) Verticality of posts, panels, balusters and openings ±2 mm
7d6a32ba-4059-574f-8b3e-7f872aa7cd20 | note | Attach: Survey As-builts / Survey Report
ea8ed7cb-4dea-58d2-8e7b-fe5ea5a32e2f | note | Method - Document Review
783a39e2-b346-5f38-8490-9a9569294984 | note | Frequency - Each element
0d5354f8-1c12-5c32-9733-7dfa866010a3 | note | Category - IP
1bace8ee-fd6b-5618-8faa-c06420d6b3f6 | note | Responsibility - Surveyor, SE/PE/SPE
8a55d85b-b889-58ca-bbc4-800a7e38f7d5 | note | Verifying Documents - This ITP
de0445fe-e505-5dcf-bd39-d74acae4851c | date | Date Completed:
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
d94c852a-a02e-54f5-bf3c-dc1d6191c2e8 | note | Reference - MRPA Quality Management Plan
a75337cb-98b0-5ff1-92e5-39db13135af2 | note | Method - Document Review
62c989ec-cdb1-515b-ab5f-58567acf4e85 | note | Frequency - Once, prior to closure of this lot / element / Work area
6a9c1117-dc1c-5dae-9e4a-83973aed63bd | note | Category - HP*
a14fc6db-799e-5881-aa03-68ae06d92059 | note | Responsibility - SE/PE/SPE
25acb7a9-c4a7-580b-9590-e3fe85648549 | note | Verifying Documents - This ITP
c7808271-5247-568c-a6d2-4250fd9cf123 | date | Date Completed:
| checkpoint | Final Inspection
f12f50b2-c77d-5a98-b848-4989b4be79f3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
40a2eb17-650f-5c71-bf39-8e87ef3d6538 | textbox | Name:
fd402052-0efe-5e9f-a365-10cc009651ee | textbox | Position:
9597eef7-0f27-542a-a396-490dd82acaf2 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-123-STR-CPD-Steel Structures Installation Rev 0 | itp | ITP-123-STR-CPD-Steel Structures Installation | 1df3141c-6415-4af6-bfc8-a45ca11c7620
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
7f0acb72-414f-5901-bb57-a5ed8cb2da00 | note | Document Title: ITP-123-STR-CPD-Steel Structures Installation
9d4635c3-ceb9-55a4-8b54-d1b416363c7a | note | ITP Description: Steel Structures Installation
fba1f99a-5789-5064-b1fa-a9d0df33377e | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
2e8a937b-996d-53ab-8107-f4b7c65301ca | note | Discipline (e.g. CIV/STR/RAIL): STR
53287cdf-d79d-5fac-a449-32915ca80a79 | note | Revision Number: 0
2c674c35-09a0-5825-96b4-04ba0b88974b | note | Revision Date: 19/01/2024
a43a2585-0c22-57bf-8ab2-55d59783ba7c | note | ITP created by: Andrew Carlini
f4743796-2c93-5270-a545-c4a726dd4633 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
9b30d034-08fe-58a6-9791-c2d50e575da1 | note | Reference - VR Section 610 Feburary 2020
| checkpoint | 1.2 - Non Dependent
6ca9fe65-3e60-598f-99e2-3884ef249eb8 | note | Reference - VR Section 630 July 2022
| checkpoint | 1.3 - Non Dependent
9e927761-0e67-5d24-aebb-38f106953a94 | note | Reference - VR Section 631 June 2017
| checkpoint | 1.4 - Non Dependent
ac2e2dde-71e6-56c4-9c9d-59f647e66ca4 | note | Reference - IFC Drawings
| checkpoint | 1.5 - Non Dependent
8ff3430d-ca40-5311-8e63-08062cb89f9f | note | Reference - AS4100
| checkpoint | 1.5 - Non Dependent
b873a1d3-158d-51e9-874e-da17eb36eb37 | note | Reference - AS5131
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Structural Steel Components
386cb4de-b409-586b-8fc2-d65b855caa89 | note | Reference - IFC Drawings MRPA Quality Management Plan
be42078c-ae3e-5ded-a239-0eac19c6738c | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
557bb190-7849-5a41-bef3-faea0ef87846 | note | Typically this consists of but not limited to:
dcb7b46f-8551-5829-ad2d-64b8b293829a | note | i. Certificate of Compliance
983617d9-0837-5573-8d3b-33fee62aa6ed | note | ii. Completed Fabrication ITP
b4703bfa-4aaf-5499-b6cc-d4a136ab807b | note | iii. Weld Procedure Specifications
574c188f-3f54-5cfa-8cf9-b14fb6e7138f | note | iv. Weld Procedure Qualifications
cf333f05-2cf7-5b0d-856e-3e99b8de2544 | note | v. Welder Qualifications
2671acfc-f7b6-56d0-80e7-1eec73220d21 | note | vi. Material Certificates and traceability
ab496b32-2a02-51f8-a855-6d46f33b4ccf | note | vii. Quality Assurance check sheets
9f1101c1-c7ca-5fdd-b045-3af04fefede3 | note | viii. Welding Consumable batch certificates
3835af73-ad8e-5227-82cd-23c76a26f8ae | note | ix. Coating certificate(s)
bdbf3c66-4e60-5444-862e-6bb3a537e74a | note | x. Non-destructive Testing (NDT) Reports
3d48a566-f9d1-50fc-a4d9-1012ec3519b9 | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
d0a64262-e69b-510a-8249-7f1f1eeca57a | note | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
22beee02-530c-50ab-b77f-144aa6d06d78 | textbox | Enter: Teambinder Material Approval number
cb5e8b9b-b6d7-58de-8ffa-c968239485e6 | note | Method - Document Review
2a694e98-c09e-500c-855f-004436b0e421 | note | Frequency - Each component
99259af1-f3f4-54cd-876c-987f5f7aeaa0 | note | Category - HP
032823eb-b536-5e65-97cf-922fc475d343 | note | Responsibility - Nominated Authority
1400d87d-568e-5cee-bc25-093848b89d15 | note | Verifying Documents - Conqa HP Release
bf23a436-34c2-5d88-b56d-b8e2a2f06079 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Fasteners
2c852c56-ec3b-5d59-a44d-49f432559714 | note | Reference - Section 630.20 IFC Drawing
b36a8b5d-a9b9-51f5-98d4-5941df4be969 | note | Acceptance Criteria - Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
557b257d-e04a-5cc5-b40c-9b07ada54eda | textbox | Enter: Teambinder Material Approval number
ec3f65eb-0f19-5c38-80c9-2080b4fe378f | note | Method - Document Review
2d91e464-c381-5f69-950e-88a527064dc6 | note | Frequency - Each component
11ade83e-89b2-599a-a9ec-79848c7ba681 | note | Category - HP
b90f6634-ddec-5b7b-8c25-37c9d3501f6c | note | Responsibility - Nominated Authority
c934b913-6e96-54dd-8ed5-30e2c3a3feba | note | Verifying Documents - Conqa HP Release
de465c85-7603-5df2-87d4-b6f64d2ed8b0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Base Plate Structural Grout or Mortar
e1357a8f-5acb-5f58-b1a1-dd7acd8097b2 | note | Reference - IFC Drawings Section 610.33
ce0ec526-4db8-5c4e-a253-18e87d6b5290 | note | Acceptance Criteria - Product to be selected based on the following criteria:
3d7134e1-bb47-5b5b-aa16-6ab657f2e604 | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
e9aeacf1-cc3f-53c9-a87d-6daed291d45b | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
1c6179d7-5865-581a-ab96-9c9ecfabc379 | note | iii. have a flowable consistency
d801ccfc-1f52-5e3c-b9f7-4e46397820af | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings
96315f92-629d-5e07-9648-da2327dbfd90 | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
6fc74ce7-5635-5054-8fbb-2687bbbbc6a1 | textbox | Enter: Teambinder Material Approval number
f68345eb-50f4-5b49-a930-2eb332d7ab66 | note | Method - Document Review
27e19123-68b3-5e38-b087-b1e36d3be374 | note | Frequency - Once, for each product, prior to placement of product
e33a9a5c-85ca-5379-914f-de941460b5c8 | note | Category - HP
44cca2e8-d716-53d8-bf98-9bf0cd2b764d | note | Responsibility - Nominated Authority
e23ca34e-b3d6-56d3-86f0-52a495942ac5 | note | Verifying Documents - Conqa HP Release
83daca93-15bd-5718-a125-7004df6ec529 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures
| checkpoint | 3.1 - Handling, Transport and Erection of Structural Steel Element
c27da26e-872a-58a7-ab1d-81dd02eb989d | note | Reference - Section 630.09 AS5131
24e5bb95-6185-5e42-a217-8ffb466d8e89 | note | Acceptance Criteria - Methods of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
03f1833d-4fd2-5fe5-9f27-15ca75772cce | note | An installation methodology and ITP in accordance with AS 5131 shall be submitted prior to installation. As a minimum, the installation methodology shall include the following procedures below, when appropriate:
67115cec-b382-549b-b654-1103c76579eb | note | (a) Lifting procedures for each component; transport to and handling on site
949b5325-f95a-5bd6-a7c0-4077a64ba5db | note | (b) Bolt tightening procedures for snug tight bolting
8a3673fe-2683-5907-b0e5-866af6ddd4eb | note | (c) Procedures for grouting of base plates
6ae20a54-6566-5b20-9130-ba8f7e3f640e | note | (d) Procedures for ensuring that components are erected in the correct sequence and position.
6cc0565e-3217-5aea-ad13-6f260fb6a564 | note | Attach: Subcontractor Installation ITP and Procedures
f6b95129-d757-562e-94b3-d8a91a0280d1 | textbox | Enter: Teambinder Approval number
910365b4-ef97-56aa-8458-1ba74fcf35a6 | note | Method - Document Review
f4c91c51-58b3-55d3-9582-65d80a853552 | note | Frequency - 4 weeks prior to installation
d56f5f70-d899-5ec8-8f2c-e4d001648d6f | note | Category - HP
217ace62-d0ee-50c4-b3d0-1633f1b97db6 | note | Responsibility - Nominated Authority
96992859-aa47-53e3-b9f3-943ee6fac94a | note | Verifying Documents - Conqa HP Release
3f4f711e-ac9e-5a50-806d-5f41c6970e95 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-installation Activities
| checkpoint | 4.1 - IFC Drawings
cb4db0e8-555c-59a4-8017-32737f4abc65 | note | Reference - MRPA Quality Management Plan
e4b29ddd-211c-5430-bfbc-88db27e9c526 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
88253430-3499-524d-a118-8531321d3a85 | note | Method - Document Review
e08377c4-f477-5313-9406-845c4f3d906e | note | Frequency - Prior to starting Works and at regular intervals
208f99ab-6648-5400-a693-968ddff65f25 | note | Category - HP*
83e5d418-4d94-5a9e-a54c-042f8fcae7e3 | note | Responsibility - All
277a8edc-e918-5ac0-8cfc-541feafc97ea | note | Verifying Documents - This ITP Signed Off
59159f2d-c211-52fe-a6a9-597e2bdace39 | date | Date Completed:
| checkpoint | 4.2 - Materials Inspection Checklist
4f000aad-e89d-5422-8585-246d4c52abb1 | note | Reference - IFC Drawings Section 630
67986ac7-a075-54ef-a7d9-b4dd7a9fcfac | note | Acceptance Criteria - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
22db09af-b88e-567e-a190-54f3495222cd | note | Method - Measure, Visual
cf07d1bc-6574-59de-83ec-05e8cd30bf7d | note | Frequency - Each component
4f9a3e76-dcff-5bc6-b955-f462bbaa7f8f | note | Category - IP
ea1e7494-195b-5dfd-a55c-81a84554456d | note | Responsibility - SE/PE/SPE
d6f197ed-d214-52ab-b7ac-eb8ade069885 | note | Verifying Documents - This ITP Signed Off
21df9057-478d-50c5-ad1b-0ed4f95200a9 | date | Date Completed:
| checkpoint | 4.3 - Materials Inspection Checklist
ce997a86-63f9-563b-ad2d-4051d4432056 | note | Reference - IFC Drawings Section 630
34d8281c-383c-5d0d-b6e3-0c08db6c1601 | note | Acceptance Criteria - Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
6f086a13-50ea-5633-8190-cd2c8ff52f48 | note | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
58ee46a3-4bc4-534e-8790-bafb80434b66 | note | Method - Measure, Visual
609244b6-b91a-584f-b8c5-2ae8f37a9a9f | note | Frequency - Each component
3f2e2ab3-2a67-5cab-9360-0754706b87f0 | note | Category - IP
774d186e-bdc3-5e6d-820a-505f5d603bb2 | note | Responsibility - SE/PE/SPE
c40e572b-c979-596f-a51f-7db11cd1d4e3 | note | Verifying Documents - This ITP Signed Off
f9e34c59-6c96-5c3f-a85c-69a9851a4fd3 | date | Date Completed:
| checkpoint | 4.4 - Materials Inspection Checklist
dad4ed97-1a68-5541-b630-2aadc712787a | note | Reference - IFC Drawings Section 631
a89eecff-c662-56ae-a4bf-ecf8228fa33f | note | Acceptance Criteria - Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
c932b7f4-da44-543d-bea3-fc222135a8f4 | note | Method - Measure, Visual
33b15db8-97ae-58ff-bf73-cf6a7dcdd261 | note | Frequency - Each component
d27590ca-a814-584e-8627-69a556bd4c38 | note | Category - IP
54110120-d1b4-5124-ad3b-21b469f36238 | note | Responsibility - SE/PE/SPE
33458bdd-1555-52ca-9f4b-fd2d1addbaf3 | note | Verifying Documents - This ITP Signed Off
d956be1b-13db-5ab3-86e5-8d7fee145714 | date | Date Completed:
| checkpoint | 4.5 - Materials Inspection Checklist
67ad0293-e9f9-57dd-a3b9-843442b5913b | note | Reference - IFC Drawings Section 631
f91d2ec6-81fa-5136-b6bd-abd483d32e50 | note | Acceptance Criteria - Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
5fcb9142-54da-5db8-b362-382142ab7c7b | note | Method - Measure, Visual
3682ac07-7925-5acd-8aef-bb3e53824dbf | note | Frequency - Each component
19641c94-bb56-5cf7-8576-5293adf727a6 | note | Category - IP
d3aaea78-1cf4-5fa5-adc4-0e12450b0049 | note | Responsibility - SE/PE/SPE
b5568d45-a75c-5f1f-8c2a-9d34a7d83b30 | note | Verifying Documents - This ITP Signed Off
0c6328f1-64aa-53a1-bf13-480ab81cc97c | date | Date Completed:
| section | 5. Installation Activities
| checkpoint | 5.1 - Bearing / Mounting Surface Preparation
2afa281f-5003-5e46-9236-c3a4102eb3f3 | note | Reference - IFC Drawings Product TDS
0f1f7570-53e6-5b60-a6eb-06e710d8c24f | note | Acceptance Criteria - Ensure the bearing surface is clean and free from any loose particles that will prevent solid seating of the parts.
7f81d13e-89be-5de6-904e-0eb86f8af2b6 | note | Method - Measure, Visual
2299fb70-97ec-5921-b398-8600f620c232 | note | Frequency - Where applicable, each installation location
125620f6-fb18-5521-810b-1d084f8a0730 | note | Category - IP
7929ff0a-39ec-5432-bad7-6f00f10a62f4 | note | Responsibility - SE/PE/SPE
f0272597-7597-520e-ac8b-e26f75a38793 | note | Verifying Documents - This ITP Signed Off
59b235a1-c347-5d30-9197-4364ee5c6d5f | date | Date Completed:
| checkpoint | 5.2 - Structural Steel Handling
2742ca97-e9b5-57e5-9e59-804fde619cd6 | note | Reference - Section 630.09, Section 631.14
f0a77c94-f4fe-5ef1-ab86-81ccbf38403f | note | Acceptance Criteria - The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
087c6d14-6e99-5619-8802-f635ce804dd0 | note | Method - Visual
3bcb82ac-95c7-501c-9100-7a9e1c64ef6b | note | Frequency - Each component
c8a50446-7935-52db-ab24-4d99f7aeb15b | note | Category - IP
5f08bd1e-a592-5c09-b894-c9d89c6a96a4 | note | Responsibility - SE/PE/SPE
c2315561-660b-5b66-a18b-7335e6b8a1bc | note | Verifying Documents - This ITP Signed Off
88877cfc-37dc-50ec-a7e4-a2952f8d3456 | date | Date Completed:
| checkpoint | 5.3 - Structural Steel Erection
d4e1fa2b-780d-51fe-b173-9967e22f45d4 | note | Reference - AS4100, AS5131 Section 630.12
f7f34220-8eac-542f-89d0-f16931f544dd | note | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
a7e74712-c249-5683-9033-2e61d9fc7e85 | note | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
a6f3e8d9-7b47-5da5-a42a-a0bbe18ff84a | note | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
d4d520fb-40f9-562e-a841-781053b9442b | note | Holes shall not exceed the greater of:
048dff5b-135c-5584-978f-4a8a04aa95bc | note | ○ 1.25 x bolt dia. OR bolt dia. + 8mm
91ada7b7-8128-5cd0-9432-feb36ebfc07e | note | Slots shall not exceed the greater of:
ddf6dadb-dce7-55a7-a854-947afcdfec9b | note | ○ 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
056d1f63-6bfe-552f-8750-b1dd638321a7 | note | Method - Measure, Visual
e4d88e25-0677-5203-bd56-416b2f3ba8c3 | note | Frequency - Each component
3404b260-4b48-54cb-9039-065a3be08474 | note | Category - IP
0c82539f-72a1-5b5b-b590-1d8468c4c0a8 | note | Responsibility - SE/PE/SPE
ea52c1c5-922f-513b-81e1-656fb26acdf4 | note | Verifying Documents - This ITP Signed Off
92e5a991-a449-5fbb-857b-2d7b7da831df | date | Date Completed:
| checkpoint | 5.4 - Fastener Tightening - Snug Tight Condition
3e20bc9b-18a9-504d-8373-23a599000bd6 | note | Reference - IFC Drawings Section 630.09, Section 630.21
143a57da-c9c1-535e-9e7d-09c9b6cc20ce | note | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
c6e8ebd6-dc32-5140-b0e8-2a02ca3f5195 | note | ○ For posts base plates, the arrangement is to be (from the base plate):
9fac47de-cbf9-5045-9f54-c22cf8d3f2b7 | note | – Base Plate
ab4d5022-f2c3-528f-b7d9-36972bee996e | note | – Washer as specified
2a4e6622-029e-5a5b-9fc1-5ce2fc3a18f7 | note | – Lock Nut as specified
99dd6a6f-72bc-5a54-adfc-600409df1573 | note | – Nut
56fffbaa-68ac-5d53-abcb-eade881ff979 | note | – Bolt protrusion (1 clear tread)
ddc74648-c9bb-51ab-9c05-19064ea63d44 | note | Method - Measure, Visual
08eb3a5a-1c84-5f2b-aff1-2c17103884fc | note | Frequency - Where applicable, each bolted connection
6fc3db50-6eb3-5d11-8e42-c6929473cccd | note | Category - IP
45002d3f-fe07-5833-a65e-36e1d49ffe4c | note | Responsibility - SE/PE/SPE
148a76fd-8c69-5293-921b-de75817db7d6 | note | Verifying Documents - This ITP Signed Off
9be6faf6-6ef4-50cb-9543-cef8a8f2aae7 | date | Date Completed:
| checkpoint | 5.5 - Fastener Tightening - Snug Tight Condition
9c3f7547-8bf1-518c-a886-e2188c29bcff | note | Reference - IFC Drawings Section 630
98d67950-552d-5d1e-a18c-a2027c24d19f | note | Acceptance Criteria - Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
59135a55-2a18-5f2f-a3a3-709d7f2486f9 | note | ○ Tapered washers shall be positioned if specified.
4c6b8fad-990d-53fb-8015-7413cd139f23 | note | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
89f537e3-4858-5070-96aa-6f2f48b0283b | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
c92ca887-b1bc-5294-ae3d-9066bed4084a | note | Method - Measure, Visual
57b6ec54-0912-57c4-ace7-a3a52db72b4b | note | Frequency - Where applicable, each bolted connection
40ef4eff-5087-5439-9adb-bc5cdefd8d4e | note | Category - IP
1765641d-d4d1-5edd-9ccb-c6d54a3d3ba0 | note | Responsibility - SE/PE/SPE
89fa5c54-0e90-584b-8db0-b0f12d068edd | note | Verifying Documents - This ITP Signed Off
9996c53c-8747-5328-8d8d-871de10bea66 | date | Date Completed:
| checkpoint | 5.6 - Survey Conformance
766001b9-3aa6-590f-93f9-3ed1c93a694b | note | Reference - IFC Drawings AS4100, AS5131
a9edc816-55e3-5cb3-b78a-961bbd70fd92 | note | Acceptance Criteria - Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
714b5aef-f595-566d-872e-c88d74c4ce12 | note | ○ Departure from RL = ±10mm
074db8c6-c45c-5db7-bbbd-2e4914dd80d3 | note | ○ Departure from plan position = ±6mm
e6503ee3-df14-5040-b211-5126f80c71fd | note | ○ Departure from alignment = ±6mm
ca37f49c-d532-5463-9276-e871c3cb0127 | note | ○ Irregularities in alignment = 25mm in 30m
6a00b89e-7a3d-5617-8f59-6566c411602d | note | ○ Projection of bolt = +25mm, 5mm
acf37470-f182-5dff-b9da-9c96fad32edb | note | ○ Location of beam = ±3mm
2a27026a-e015-5ce7-bd71-a57c0fffcf01 | note | ○ Location of column = height/500, 10mm max.
aecb1ded-085c-5624-866a-265ab21753e2 | note | Method - Measure, Visual
7bb0d227-9e3b-5aa5-96eb-63833617e8af | note | Frequency - Each element
fd624e7e-f6f2-5140-9346-883c93b0ee41 | note | Category - HP*
e64a0ce5-184d-5114-916e-05e6e5689d23 | note | Responsibility - SE/PE/SPE, Surveyor
d8e602c3-148e-5833-a6f4-c0c88bcf74db | note | Verifying Documents - This ITP Signed Off
c8c444ac-faad-5a09-b0f5-472ee1c4a200 | date | Date Completed:
| checkpoint | 5.7 - Base Plate Formwork Construction & Placement
8adfa90e-9885-58b1-86ee-8369381493d0 | note | Reference - IFC Drawings
3e165aa8-85ce-55d3-aca8-5500866747ac | note | Acceptance Criteria - Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
9ab83a76-53a7-529e-a3ab-7d37faf9e15a | note | Method - Measure, Visual
04eea8d6-46a2-591b-bbd6-aab210f57960 | note | Frequency - Each post location
d4649068-d7c9-5701-bdc7-452af1ef3159 | note | Category - IP
29669910-a25b-5b26-b08c-702d25b0f9b5 | note | Responsibility - SE/PE/SPE
e616adfe-0a86-50c7-b1ab-9a53b8e27d47 | note | Verifying Documents - This ITP Signed Off
10fbc612-9309-54df-b594-fafb5ac6b4a2 | date | Date Completed:
| checkpoint | 5.8 - Pre-soaking Concrete Surface
46d026c1-e458-5fb1-81f9-254c5fc08f60 | note | Reference - Product TDS
3115dee7-531e-5159-817e-f6dc35de8f8b | note | Acceptance Criteria - Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
66d843db-66f0-5bf6-aa4d-a68dc6794010 | note | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
479cfa53-8824-5bad-b18c-657ebf44980d | note | Method - Visual
45ca3240-c12a-55f2-9f0e-bfc8a48024e7 | note | Frequency - Each post location
5f495512-a26e-55e9-9041-51041de681ed | note | Category - IP
02300d91-2786-5cae-b851-47b283383aff | note | Responsibility - SE/PE/SPE
c4c4c544-2b26-586f-adb2-f398adfe6ef9 | note | Verifying Documents - This ITP Signed Off
c81f35c4-d3c2-5181-a331-cec62d780d69 | date | Date Completed:
| checkpoint | 5.9 - Weather Conditions
3a679cf1-ec33-5bc3-a447-b832356c1910 | note | Reference - Section 610.17 VR Table 610.171
f83f4036-5fa9-5e7b-81fb-d25f22d6207b | note | Acceptance Criteria - Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
f013f583-99e0-5db0-9fed-c8f8d3aa71c4 | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
d61451e6-b7bb-5383-bbec-2e22b2752d24 | note | Record: Required information on the Grout Pour Record.
87dc4192-75f4-522c-b257-56047f5af7ff | note | Method - Measure, Visual
c7341fd3-fae3-5311-9c74-dabf4a095e61 | note | Frequency - Each lot
43155bc2-1938-55c4-8ae0-34b854239920 | note | Category - IP
1206eb64-a8a9-50dc-b5de-16fac5d6e6ba | note | Responsibility - Supervisor, SE/PE/SPE
ca675b39-7a65-52f6-b9b0-d17278348cc0 | note | Verifying Documents - This ITP Signed Off
a17f8054-cda9-5088-a930-0513704b0640 | date | Date Completed:
| checkpoint | 5.10 - Mixing Product
fd15659b-935a-59ef-96ce-f1e143cdabf9 | note | Reference - Product TDS Section 610.28
b59dc752-39a3-5abb-b97c-f8b12b03f48c | note | Acceptance Criteria - Size of mixer should match the application.
bc11ba33-65fa-5f3c-b5df-8f2043e1d362 | note | ○ Only whole bags to be mixed with potable water.
cb3cbe6b-63b0-5c4c-855a-17c7c0e75cbc | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
c7a70830-dea4-5492-9d9b-d21ca2d350f8 | note | ○ Product poured into the mixer slowly.
495a09f0-e409-5189-8672-411853e7206b | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
48da0737-b44a-5de0-9605-a90f6aed88ff | textbox | Enter: Required information on the Grout Pour Record.
c7cb3007-22dc-5a5a-bbce-395582e75767 | note | Method - Measure, Visual
df953686-ac34-5802-bbe4-a7c83933b69c | note | Frequency - Each lot
a7d8527a-0793-530c-ae4e-512386f2fead | note | Category - IP
5bfc1aa2-ed2b-5e69-b568-3776c828381b | note | Responsibility - Supervisor, SE/PE/SPE
6b7d4197-b3b2-5440-8ce1-74c3f32d96e4 | note | Verifying Documents - This ITP Signed Off
ebd43256-32a0-57fa-9e50-a6529301598e | date | Date Completed:
| checkpoint | 5.11 - Product Testing - Compressive Strength Cubes
19555d57-eae5-5fea-b307-77ebe8a08b77 | note | Reference - Section 610.28, Section 610.33
289b7826-1136-529b-843d-604a41000713 | note | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
a7bceed6-f1c9-5060-b0c9-abf7c83b08a9 | note | Testing is to be in accordance with the following frequencies:
85de1ecb-635e-5fcb-a7db-13408ae061be | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
369ad864-a848-51ff-924b-77cca4e11ca1 | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
54de32be-7580-5025-9169-1a5d8b100799 | textbox | Enter: Required information on the Grout Pour Record.
76bd9101-935e-5bb3-9643-d0e739c6f81f | note | Method - Test
25779521-ffa1-5254-83b2-e79b91278e57 | note | Frequency - Each lot
da16f1cc-59f6-58aa-9ff0-251c315004da | note | Category - IP
1f0422ea-4036-59e2-b2cf-3e39b45d0ace | note | Responsibility - Supervisor, SE/PE/SPE
0ae6f809-c8b6-54c5-9bf2-a809ad6e72e9 | note | Verifying Documents - This ITP Signed Off
4a86010f-f651-50e8-a262-7a14d5a6eeec | date | Date Completed:
| checkpoint | 5.12 - Placement & Compaction
b98a523f-35fe-5424-bc20-ea4d03c7ef69 | note | Reference - Product TDS
76df2bd5-b437-54f4-9742-606a27c24a46 | note | Acceptance Criteria - All batches are traceable.
2bc44f61-e071-53f6-b748-72e2388e3965 | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
3ec5fcd8-dcfe-518e-9d97-b52c4eeca2dc | note | ○ Product should flow to all areas and self consolidate.
7a6533d4-29fe-53c5-b793-6feae40340e3 | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
f664e322-fc18-57b4-99bb-0e7cebcfbc99 | textbox | Enter: Required information on the Grout Pour Record
fb083370-7b80-5bb9-9818-5b95b6358877 | note | Method - Visual
c38e0eeb-186b-5ffd-a911-ebdeb49f90b9 | note | Frequency - Each post location
71a9a1d7-f56e-50a7-ae37-5503623bbf38 | note | Category - IP
83c946ff-424e-51ad-b2a4-b1b19e8acc54 | note | Responsibility - Supervisor, SE/PE/SPE
ea505bcc-0b10-5f4c-882a-59076f12139d | note | Verifying Documents - This ITP Signed Off
071c8d3c-893d-55e1-a9fc-795905749dfc | date | Date Completed:
| checkpoint | 5.13 - Surface Finishes & Protection of Works
d27b358a-70f7-554b-8cd0-c38ee4b743b8 | note | Reference - IFC Drawings Section 610.17
4cf83fc4-1848-5645-9225-b194d5784060 | note | Acceptance Criteria - If shaping of the unformed surface is required, shape prior to the product fully hardening.
64573f24-fe65-5b62-b98d-5b84b35aa58b | note | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
44b8fab7-d961-5c12-93a7-54bbab750dde | note | Method - Visual
aa5f4379-fc28-53b0-96df-7a78489079ce | note | Frequency - Where applicable, each post location
49527e5a-9deb-50d8-ab90-e4bbc983529a | note | Category - IP
b8381f31-e271-5723-8511-6fb8818cd54c | note | Responsibility - Supervisor, SE/PE/SPE
738c78b9-e7c4-5e3c-9d66-6fd2deff8b8f | note | Verifying Documents - This ITP Signed Off
ea3505ae-2661-5db9-840d-fbb02720214d | date | Date Completed:
| checkpoint | 5.14 - Curing
807b7090-b1cb-5755-b7a7-29c58998df9e | note | Reference - Curing Methodology 610.23 Table 610.231
0e6478f5-55b2-5a69-9a8b-d90a0e3448e6 | note | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
e3691bb9-ce82-51aa-af54-4bfab672e139 | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
dc19c9b2-1bcd-5577-8dfc-ab7ad2ca4d51 | note | Method - Visual
0a5d074e-bd92-5ff0-aa95-67c7ad46e49e | note | Frequency - Where applicable, each post location
c5dfa289-97de-55b6-b084-4a349a2e0c50 | note | Category - IP
a3c4d4af-ed22-5f03-a950-df64d36ae8d9 | note | Responsibility - Supervisor, SE/PE/SPE
ebdd5ba8-5165-5cf5-b33a-2e96363888da | note | Verifying Documents - This ITP Signed Off
8a6bbabf-eaca-5538-b195-8335fd537481 | date | Date Completed:
| checkpoint | 5.15 - Architectural Steel Erection
ce7af396-8002-5d3a-a9ab-eb689545033b | note | Reference - AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
fe0899a8-aa27-5b32-89c3-4f2fbda7cce0 | note | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level and square
51548781-8130-501b-a89f-034cb9a7324b | note | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
1efe4eda-b24e-5999-9afd-9ce95699bf37 | note | Method - Measure, Visual
166f965a-a35f-5148-a71e-14152fb3287a | note | Frequency - Each component
2a06ea5e-c9ab-5758-996f-9fa045e375a5 | note | Category - IP
fa185166-5464-59a5-abe4-d19a4f09b2aa | note | Responsibility - SE/PE/SPE
6e5b3863-2084-5cfc-ad29-29fb012d8129 | note | Verifying Documents - This ITP Signed Off
6bdf96a2-4f71-557a-a3c9-415840caf374 | date | Date Completed:
| checkpoint | 5.16 - Architectural Steel Erection-Fasteners
fee1aa2d-7d0a-5e9d-bb78-d7e50b8bafde | note | Reference - IFC Drawings Section VR 630
d893d6dc-7e20-5688-a920-d20190c9e0ce | note | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
ed029fa2-de55-505d-9225-a758de558e08 | note | ○ For architectural/Security screens, the arrangement is to be (from themounting post):
78ac8e13-1405-5b9c-84c2-8298697fefc1 | note | – Post
c56ed942-9b81-5af6-8e26-253814a49856 | note | – Washer (s) as specified
b2334368-b6d2-5f00-a2c4-2124258e8866 | note | – insulating washer
49d8f78d-884b-562f-be89-47c24fb5f987 | note | – insulating bush
3b3eec00-3056-544a-abf2-b15061f358e8 | note | – Insulating washer
8042356e-13e6-5a16-b6ff-7970bb600499 | note | – washer as specified
ae4d2906-6ece-5276-88fe-e08ee412348b | note | – Lock nut
c62eef13-a35b-54a1-a0ab-17a3b837086f | note | – Nut
1f9b0e8b-738c-5957-87a0-f61be1632d22 | note | – Bolt protrusion (1 clear tread)
e670be5f-ce22-55b1-9e57-c6c32a7de7b1 | note | Method - Measure, Visual
ccb207e4-5779-5cca-b0eb-45db6a82661d | note | Frequency - Where applicable, each bolted connection
3ecad6c5-2a9b-55d4-89c0-7281810d356e | note | Category - IP
09837ec6-e643-5d43-ae5b-c72eea741eb3 | note | Responsibility - SE/PE/SPE
27ae87ef-89ed-57bc-9b3d-a0186663308c | note | Verifying Documents - This ITP Signed Off
6e38f2f8-c42a-5657-9f79-b5e3ad3e4d4a | date | Date Completed:
| checkpoint | 5.17 - Installation of Electrical Isolation Materials
6f3de21f-6fd2-5ba2-82af-bbc6eb906d16 | note | Reference - IFC Drawings
b02c1ae9-3dfd-5863-8055-546a7b59468d | note | Acceptance Criteria - Installation of Electrical Isolation Material in locations specified on the IFC drawings (where applicable).
13586dd7-f3c5-552c-ace9-d4ab3e6a4f8c | note | Method - Visual
ccbf4985-988e-5d9e-a175-7e8033274ae8 | note | Frequency - Each component
e1d0c510-7c5d-5f37-8190-aed1766e3ae3 | note | Category - IP
7178e14b-b663-58a0-8675-c1d9e1c39b00 | note | Responsibility - SE/PE/SPE
e6ffff8c-5a7d-545c-b0a8-94dd4e157f99 | note | Verifying Documents - This ITP Signed Off
5c94300d-567b-5239-b5c4-0141b405bb74 | date | Date Completed:
| section | 6. Post-installation Activities
| checkpoint | 6.1 - Inspection of Coating
1b185e08-d2f4-594f-bfdc-82fb6c0f88a7 | note | Reference - IFC Drawings Section 630
ff53b66f-96fb-52fc-8964-8dd227907c7c | note | Acceptance Criteria - After installation Works are complete, inspect the steel element for damage to the coatings.
e6aa1427-8606-532d-b7d8-8da8a8e6e12d | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
fe8bfb44-9db8-5731-91a0-9dbea4dcb4bf | note | Method - Visual
0dbffd90-1668-5df8-a55e-c926d52892a1 | note | Frequency - Each component
cb6b787f-8f82-5f3d-aa18-94b19921891b | note | Category - IP
8fd7373a-9c36-5581-bbed-c49135b388be | note | Responsibility - SE/PE/SPE
fd7b4a71-8524-5b0e-9d93-9c67143e3d1b | note | Verifying Documents - This ITP Signed Off
65661022-dcf4-5d39-9574-3f161751acdd | date | Date Completed:
| checkpoint | 6.2 - Compressive Strength Test Results
a2a3a8f3-bedd-527d-9a76-a6538d0314fe | note | Reference - IFC Drawings Product TDS Section 610
219023e7-6580-5e8f-a465-178d2051b09e | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
a053c285-65db-5748-9cfb-0eb5ee85e7b5 | note | ○ 28 day compressive strength per sample comply with the design strength.
ec7c453d-2193-54f6-8c20-1d65051a1bc0 | note | Attach: Compressive Strength Test Results
3df64b69-e141-561e-a8c8-b9d1f225e777 | note | Method - Document Review
7e15ff47-c12e-53eb-bc60-797938f753cc | note | Frequency - Each Sample
e959681c-199e-56e9-927d-50bb14d19baf | note | Category - IP
62b79638-69b6-5e34-94e3-ddffd0d75b88 | note | Responsibility - SE/PE/SPE
55e6b076-dcc3-589e-83b4-3615d588ea8f | note | Verifying Documents - This ITP Signed Off
1a59ccdf-5e03-50c2-90eb-f174a05a3cc9 | date | Date Completed:
| checkpoint | 6.3 - As-built Survey
81f21c27-16dd-5806-b2a8-a7fc36811e8d | note | Reference - IFC Drawings AS5131
8719bc39-eba2-5c2b-9729-4e56a45c23d3 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
c81873d3-44b0-55cd-8f70-8b7c59a05e08 | note | ○ Departure from RL = ±10mm
ba2c6767-eab8-5f23-846b-3f799facc5db | note | ○ Departure from plan position = ±6mm
788bbf07-b14a-535b-ba75-6969901474af | note | ○ Departure from alignment = ±6mm
2b6307df-ca5c-50fb-9a90-e07b238ee98e | note | ○ Irregularities in alignment = 25mm in 30m
d16154a5-528b-5eef-b60d-c1c98557b8fe | note | ○ Projection of bolt = +25mm, 5mm
cb74fa95-234a-5e9f-8650-1bf11a19722e | note | ○ Location of beam = ±3mm
5f5eea9a-7384-500b-923e-45b36148694f | note | ○ Location of column = height/500, 10mm max.
862e60bb-fd2c-5f1c-95b7-16b6f21795c5 | note | Attach: Survey As-builts / Survey Report
07635867-456f-5669-a41f-add1a67e90f2 | note | Method - Document Review
f108318e-f613-5e27-a634-7749f4fe7b3c | note | Frequency - Each element
761aaf26-f703-58c6-8688-eef1c8e2e10d | note | Category - IP
7b702585-edba-5e5d-b0b1-dbb2c5f51b6b | note | Responsibility - Surveyor, SE/PE/SPE
a36b402d-c979-5a8b-89e9-d71f8cf49380 | note | Verifying Documents - This ITP Signed Off
f86c8767-0f96-5913-885e-17c8592414d1 | date | Date Completed:
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
8ca66df8-6ff9-535a-af5c-a8631b5dd8f9 | note | Reference - MRPA Quality Management Plan
0605dc92-e8b6-522c-b638-22f46e5839ae | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f96f9e74-ff1d-5ab3-8d05-4d8d70e3aa2e | note | Method - Document Review
ca18dc1b-c8f6-5ad7-91a8-4e2d750995d2 | note | Frequency - Once, prior to closure of this lot / element / Work area
0e66a7f0-b212-5a74-aecb-3b85ee059703 | note | Category - HP*
89d7a28a-2ddf-5b6e-873e-72b05ea46764 | note | Responsibility - SE/PE/SPE
69ef7be9-0192-5f6f-aac5-bc9f6fe68d02 | note | Verifying Documents - This ITP Signed Off
b1f39810-c423-549c-8d5c-e8b5671a8ccf | date | Date Completed:
| checkpoint | Final Inspection
4b19b077-dee9-5f92-af13-cdadf2597b31 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a0cd4f04-4647-5cd8-8e2e-8510c782ba4a | textbox | Name:
1e854934-4981-5c32-99d4-6ea431a15733 | textbox | Position:
1ffb7afd-41b9-5421-887a-ae8a324a4f35 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | itp | ITP-124-STR-CPD-Precast Super T Installation | 40e3383c-b5b9-41c5-af93-683f05f9e2b2
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
4e30ad57-09e3-5e2c-bc5c-025e8c844cda | note | Document Title: ITP-124-STR-CPD-Precast Super T Installaton
20326507-7fe6-5b88-a232-3a6eb3c1ed5f | note | ITP Description: CPD-Precast Super T Installaton
4a9740f1-bb31-57b8-9195-ba7e4707cbb0 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
1bc452a5-8f7c-5229-abc5-b8d126f233af | note | Discipline (e.g. CIV/STR/RAIL): STR
46b2e39d-5ce9-56c7-96ea-4392e7a2494b | note | Revision Number: 0
e194c0e6-ecd4-53c6-9ddc-2b6ff85a9335 | note | Revision Date: 19/01/2024
2410c9db-e37f-5df1-b0b4-19b4679b2ae1 | note | ITP created by: Andrew Carlini
82bb3bf5-2e76-5a34-94d0-63c3e40edd65 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
c20badeb-fdd3-5216-b9ab-fc02e144a73f | note | Reference - VR 652 June 2010
| checkpoint | 1.2 - Non Dependent
d79e449d-31db-515f-b339-c3d2104979d0 | note | Reference - VR 656 June 2010
| checkpoint | 1.3 - Non Dependent
49f7c010-6c9d-5304-8f7e-484d67d19cda | note | Reference - VR 610 February 2020
| checkpoint | 1.4 - Non Dependent
92c1c9d4-d1c9-5be9-b376-3f0cc003990f | note | Reference - VR 620 May 2009
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Epoxy bedding
43116f19-e9e9-5104-874f-97b2b4783900 | note | Reference - IFC Drawings
d4ac5f06-cc34-54cb-b1e8-bd9157daeae0 | note | Acceptance Criteria - Product to be selected based on the following criteria:
708d6335-11e1-50c6-a65a-1919b9bd843b | note | i. minimum compressive strength requirement as the Expoxy beeding is used to ensure the taper plate fullyengaes with the Girder.
00ab7680-86c6-5d19-876b-752635c1619b | note | ii. Can be applied in IFC specified nominal thickness (1mm)
84715a2e-b8dd-59ee-b04a-e33598b97f31 | textbox | Enter: Teambinder Material Approval number
96202eb2-cb05-5fc6-ac12-e9808093e22d | note | Method - Document Review
9ea8e314-2b37-5b29-91cf-fbdf95c2235c | note | Frequency - When applicable
a4ce9e78-e682-5eb4-998f-334c7907e39c | note | Category - HP
63a35460-55fc-5dbe-adc1-ac5583286e22 | note | Responsibility - Nominated Authority
c42a213f-6459-574f-b975-50f71c5dd204 | note | Verifying Documents - ConQA Hold Point Release
65a5bab0-f45e-57fa-b505-ed77fee3cf25 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Bolts
f34a31c8-6fc7-5be2-b50f-0adebfc2dda2 | note | Reference - IFC Drawings
ef80bfd3-db68-5002-8263-b5bd641f9326 | note | Acceptance Criteria - M16 property calss 12.9 Zinc Coated countersunk socket cap screw
b0c66f1e-f14b-5fb4-b6ce-e8dad737db84 | textbox | Enter: Teambinder Material Approval number
11c4270c-f740-5ceb-b25f-2353f76960f0 | note | Method - Document Review
d92afa3c-ab12-543d-b5a8-23c84786bcae | note | Frequency - When applicable
c887a6c9-76ad-561b-8cca-f8c95233cb93 | note | Category - HP
7d224455-55f7-5a51-a3cf-3e9eb09e49d6 | note | Responsibility - Nominated Authority
29276b7e-05ff-5708-b244-c5a06626f961 | note | Verifying Documents - ConQA Hold Point Release
52097e09-0158-5247-8971-7fc7592c69fc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Precast Elements
f8736d9a-4c9d-5049-93e6-0db8d4b1a446 | note | Reference - IFC Drawings 610.47 (a) Table 610.473 (Feburary 2020), 620.03
2ba94a44-68a5-5b01-a611-f9ef36d12fc1 | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
f66bfaee-f48f-5787-9785-ed31fa407499 | note | i. Certificate of Compliance / Birth Certificate
d32f8106-6e11-5894-9d77-a4d554eeaf80 | note | ii. Compressive strength test results
c86abbfb-dd77-52f1-93ad-5252f2a70d38 | note | iii. Precast Lifting Design
49c14a80-e8df-53a9-8552-bba1daa0a20c | note | iv. Pre-pour check sheet / ITP
76507e9c-eb20-5905-a236-326dd7550fdb | note | v. Pre-stressing check sheet / ITP
a9c25dc7-7a04-5025-801a-022f632472fb | note | vi. Post-pour check sheet / ITP
bbc0622f-0b1c-50c8-b54e-3efd9bcad0d8 | note | vii. Covermeter check record
0b391110-141f-5b09-8ef2-3b4c626974b2 | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
4a9cf96f-aa95-5b7d-984c-a9e516c57b86 | note | Note: Different revisions of 610 have different clause numbers
45762fb1-73bf-5e51-87f7-b0305de38564 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
19ad5f38-739a-5c87-95df-f5cb5c4a4c79 | textbox | Enter: Teambinder MDR Lot number
c845fe18-f658-5342-b493-613e39335f21 | note | Method - Document Review
c4cf0f46-5d7c-551e-8f6b-07326f2aa654 | note | Frequency - Each element
539cfce9-1fb7-55c8-b3ba-ae4a549d45b7 | note | Category - HP*
e72f3919-9f89-58da-ada0-0944baea92d4 | note | Responsibility - PE/SE/SPE
05415a6b-b833-5c08-9dc9-9563b391225d | note | Verifying Documents - This ITP
a14fd5ee-b5be-5275-97df-d41c56fce610 | date | Date Completed:
| checkpoint | 3.2 - Elastomeric Bearings
954af94f-d711-56b5-8552-375bf4471bc6 | note | Reference - IFC Drawings 652.02, 652.03, 652.04 AS5100.4 Appendix C and D
2cb3ab83-0033-5ea6-9335-d68268bcfee0 | note | Acceptance Criteria - Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
e68c632d-40b0-51e2-af61-94c814f230f3 | note | Tolerances:
5fcf271e-ed0e-5d57-b2ca-d6b7ff38a151 | note | ○ Dimensions in plan = +4mm, -2mm
1a7f2b9c-fb06-50fb-9e63-91b39f526a00 | note | Thickness =
dcbdd342-61b9-58af-b755-52ff1229dd1f | note | ○ ≤100mm = ±2mm
dcf87b9a-eecf-5b11-a3e3-88b59c691fcc | note | ○ >100mm ≤ 150mm = ±3mm
59af6d3a-afad-5f74-8f02-34c3ee90b173 | note | ○ > 150mm = ±4mm
bbfa9a71-a496-5ec2-9e3b-5e348c185e12 | note | Testing:
f7c03baf-adf1-54fb-bd57-69da01abdbb0 | note | ○ Each bearing tested under compression
6ee0ff99-dd7f-54fd-b6ff-a57d7aac6838 | note | ○ Batch tested for shear stiffness
7595462a-dd71-5250-bf4f-474becc1d405 | note | Attach: Elastomeric Bearing Test Reports
d1bb83ed-90ab-56fc-aaf9-0e5a57fe8558 | note | Attach: Elastomeric Dimensional Records
65b64446-28b3-589b-8084-7f0dfca04251 | note | Method - Document Review
6b84ef73-ca43-5c5b-929f-eddf574e1790 | note | Frequency - Each element
3cf1c858-cbca-56ea-80d4-61be871f146e | note | Category - HP
39f8dc45-4b29-540a-8303-e5f4910caff5 | note | Responsibility - PE/SE/SPE
7b40b088-ab9d-5937-8f3f-729793baebbc | note | Verifying Documents - This ITP
fa6ee6cf-9b04-5482-9637-8342598db676 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Tapper plates
e0f2aa94-548b-50e9-ba38-8ca9ba85af1c | note | Reference - VR 620.05
892bb7cf-ec63-5db8-b229-390d627a26e8 | note | Acceptance Criteria - Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm.
4ec2db97-ffef-564c-8948-05e5599ab463 | textbox | Enter: Teambinder MDR Lot number
0a5a7489-915f-5689-95ae-ef3f91b9b523 | note | Method - Document Review
5e2326b5-a4cd-573d-b886-04db39420783 | note | Frequency - Each Plate
08e002af-cfb0-5fc8-849b-eca20b3ed0c1 | note | Category - IP
06c981ed-f218-5e15-9090-95d370ab0841 | note | Responsibility - SE/PE
641fa1df-42a8-5e8b-822e-e7611b4eed45 | note | Verifying Documents - This ITP
77669dcb-4c33-5207-9430-8ea9d709e42a | date | Date Completed:
| section | 4. Pre-installation Activities
| checkpoint | 4.1 - Bearing Plates-Check
b3ed7087-1b8a-582f-9d7b-bcb2dec9f29a | note | Reference - IFC Drawing
8e0fd19c-ed03-5875-9c25-6a6b21ec4b66 | note | Acceptance Criteria - Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders.
122b2fb8-171d-513e-8abd-539ebd6c807e | note | ○ Ensure the plate and plate orientation are correct
1eac4ebe-9870-56cb-afd2-f75097fd31af | note | Method - Visual
58695601-1c58-5f9b-ae58-56c40378fecc | note | Frequency - Each Tapper plate
88de9300-5bb3-5267-bc91-c385e3bf4327 | note | Category - IP
14635378-a828-5962-96f2-764f6dc63cf2 | note | Responsibility - SE/PE
0e3d0f21-04a9-50dd-b1ac-281fdf1d6165 | note | Verifying Documents - This ITP
d5164eb9-49ce-50fc-b100-f0a04ad2d44c | date | Date Completed:
| checkpoint | 4.2 - Crosshead / Pedestal Tolerances
a98d4e03-579e-52fc-b30f-77dff740d712 | note | Reference - Survey As-builts / Survey Report
f59752e5-6d91-5d48-bacb-cbab4b6bf0dd | note | Acceptance Criteria - Re-check that the As-built dimensional tolerances comply with the requirements below:
ee41bf26-344b-5220-9462-efdcbb092bcf | note | ○ Reduced level ±2.5mm
dd7732f5-6099-5571-9b99-93bd87f7736d | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
67cedd8a-4f56-5d45-a048-6fda1ab23911 | note | ○ Deviation from flat surface ±1mm
17355081-64ae-5f03-b90b-9f6db2a5c380 | note | Method - Document Review
ec495866-1016-5e1d-ab05-1af75a0ad9d3 | note | Frequency - Each element
6f98e726-c462-5fa7-bafd-fd9655323ce1 | note | Category - IP
0bbc1d0d-dc8a-5d97-bcab-d7062817c62d | note | Responsibility - PE/SE/SPE
c52ee3bf-95c5-5b45-aa1a-d2531307c6a5 | note | Verifying Documents - This ITP
d9665077-f55a-5863-8be1-563cc4c4b9e8 | date | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Falsework Design and Certification
2a79ae6c-6cab-5915-b2ec-93eb29a13857 | note | Reference - 613.04 Temporary Works Design
2c117a57-b99d-5be9-beef-7dae21518920 | note | Acceptance Criteria - The Falsework drawings submitted shall state all design assumptions and shall include a statement of the loads and any dimensional changes due to loading in all members of the falsework. The drawings shall be fully detailed including all member sizes and materials, dimensions, levels, erection procedures and other relevant details including bracing, connections and foundations, to ensure that erection and inspection of the falsework can be undertaken without reference to any other documentation.
3d75bd32-2766-5807-a0df-a8b9844aa99c | note | Attach: Temporary Works Design
96ca2fa3-59b2-5ef0-81a7-90cb108c64dc | note | Method - Document Review, Visual, Measure
f6755e5f-fbda-5c49-87a1-dc1815cb7f5f | note | Frequency - Each element
3f8a4923-ad9b-580f-8a0b-34032e6ddd0c | note | Category - HP
6c3ebc0d-a18d-5aae-8f4f-4529af63ba65 | note | Responsibility - Temporary Works Designer, Proof Engineer
6673e548-4993-5d36-b551-7bb396a7d993 | note | Verifying Documents - This ITP
8433b7b4-dd76-57a5-9a2e-f5f136e588f5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Flasework Certification - Falsework Inspection
7597b88b-18bf-501d-ae76-7b25a281ea7e | note | Reference - 613.04 Temporary Works Design
05cb3fe6-07b8-5e7d-b7cc-31b468925b90 | note | Acceptance Criteria - The application of any permanent load shall not proceed until the signed Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed and accepted by the Nominated Party.
225a86ad-080a-5388-b1b0-6d89dbc896bf | note | Attach: Temporary Works Permit to Construct, Apply Load and Remove
5196b8ce-5e5a-5bca-b621-ee9aa34a040f | note | Method - Document Review, Visual, Measure
f49c3dd2-d9b1-560a-875a-bc534be22a3f | note | Frequency - Each element
b17a8d59-1747-59a3-bbbe-dfc85bacc25c | note | Category - HP
3ff9803f-182f-5521-ac0c-56b6be755c86 | note | Responsibility - Temporary Works Designer, Proof Engineer
2d23d448-286c-5bc2-95d6-c7ab98a882d7 | note | Verifying Documents - This ITP
3f7dfbaf-331d-5bc2-8d1b-9ae3c63c0f79 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Precast Handling
5910027f-086a-5877-b9cf-7e447a420e45 | note | Reference - 620.07 Crane Lift Study
4fd2a61b-123b-560a-a997-a65ed00bd171 | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
3075365a-f422-5d64-b249-0c78eeddaa3f | note | Method - Visual
62384675-6bb7-59b3-ac0d-7850c237de53 | note | Frequency - Each element
aa256a52-6d10-55f6-9862-977dc8909433 | note | Category - IP
65950e3e-87e5-5c92-a782-721e932e32d9 | note | Responsibility - SE/PE/SPE
83732e52-53dd-58af-8ea8-c17e978d4ec1 | note | Verifying Documents - This ITP
2b4d38bc-500a-53b2-9246-f0c0f9d14162 | date | Date Completed:
| checkpoint | 5.4 - Elastomeric Bearing Placement
a440ec42-7290-55ba-873f-fdbeb887673a | note | Reference - IFC Drawings VR 656.05
ce0cdd4e-e9fd-5314-b6ee-6ae313063bf4 | note | Acceptance Criteria - Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
45400d05-5d7d-5261-9c0a-7f4f29f2424e | note | Tolerances:
5898f97e-8786-5adf-b813-ba1ff285179c | note | ○ Plan position: ±2mm in any direction
bead8a06-04d4-519c-9a7e-2ab2308cac7d | note | ○ Level: ±2mm
c9408230-10da-5b9d-a519-e718ec7033ac | note | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
76932087-83b1-5aff-a478-bfcb61c00417 | note | Method - Measure, Visual
2163b904-8545-57eb-806b-1c41485ec3d5 | note | Frequency - Where applicable, each bearing location
9ef051b3-9b9a-53a3-8d3d-b7e306d577e8 | note | Category - IP
4ecccc33-db58-5df0-9002-8e29fa041d0e | note | Responsibility - Surveyor, SE/PE/SPE
840b8fd2-b41e-5be8-9217-6389caa55b66 | note | Verifying Documents - This ITP
41d12878-ca94-5df9-8145-649eac52bbfd | date | Date Completed:
| checkpoint | 5.5 - Precast Placement
7d728a3c-8663-59ab-ad7e-881659a6827e | note | Reference - IFC Drawings 610.27
740e5e11-85f9-5ca6-ad97-683b26f7696e | note | Acceptance Criteria - Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
0eaf3f5f-70fb-5171-9333-94924ebce9fd | note | ○ The nominal gap between elements is as per the IFC Drawings.
8b809e97-c271-550c-bcc1-6589c7da7cb8 | note | Method - Measure, Visual
6b94aaa6-44ec-5220-9dcd-90dd39c87a68 | note | Frequency - Each element
a72cd012-6db5-5ff1-9380-8b96febc8776 | note | Category - IP
b9abf54d-527e-55ff-a5d3-b20e48e2ea76 | note | Responsibility - Surveyor, SE/PE/SPE
444143e5-4557-5be8-9d8a-0d3b74bf004d | note | Verifying Documents - This ITP
13883bf3-27ad-50c7-a4d0-2325e770c9b8 | date | Date Completed:
| checkpoint | 5.6 - Precast Traceability
c6a40ab3-03f8-5621-9d13-9da1d88fe090 | note | Reference - 620.09
bb823412-34f1-535e-91ac-1bf4439e6ba7 | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
c0f97941-280d-5c42-a948-9524d58ef410 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
296c564d-0853-58f2-a7bd-6a7f60c86d39 | note | Method - Visual
d441a393-8c0f-56da-a7c8-3b8404391cda | note | Frequency - Each element
24b21494-c668-5b33-9ade-8f10255efda2 | note | Category - IP
7e2fd1b5-c425-5ba7-a657-a9f7578e5331 | note | Responsibility - SE/PE/SPE
aa458cd9-ccab-5120-88fa-bb36c720c368 | note | Verifying Documents - This ITP
689416bf-2e16-5e7e-905a-2f181844c98a | date | Date Completed:
| section | 6. Post-installation Activities
| checkpoint | 6.1 - As-built Survey
e5a1fa4b-4310-55d3-90e5-15a11f1f1f8f | note | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020)
da62e1dc-c3e7-5a3b-8dd4-d2192e94a57f | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
cd9b6839-0d5b-52f1-a7ca-ab900160e253 | note | Attach: Survey As-builts / Survey Report
859cb749-f1b5-5751-bd69-c36f158fab42 | note | Method - Document Review
dc19203f-e87f-55f5-9909-dbab3b0f7538 | note | Frequency - Each element
51cc4032-d41b-5abe-b0a4-4eb2fca9e525 | note | Category - IP
9407c706-67a0-5952-88da-5b93b4dddaf4 | note | Responsibility - Surveyor, SE/PE/SPE
c9aee547-f758-585f-a870-ce65ff8400a4 | note | Verifying Documents - This ITP
767b467d-01ea-59d0-b315-e9a3a76276fc | date | Date Completed:
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
182f04e6-c392-5c4f-8c8d-b8cb84ee5fcf | note | Reference - MRPA Quality Management Plan
551dc544-47e7-5fd8-89db-3fc076099ce2 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
359584d3-7e3c-5c3f-be71-fda13f6838eb | note | Method - Document Review
a61dc3d8-08d0-54c1-acd5-b547db68f781 | note | Frequency - Once, prior to closure of this lot / element / Work area
62df03aa-cd33-51d1-98dd-8d5b5ed4eb5d | note | Category - HP*
7d6eec41-3e7d-5e1a-9357-c0c8cc6ef017 | note | Responsibility - SE/PE/SPE
09a6f7c3-f36d-565e-95c2-eba7cae40085 | note | Verifying Documents - This ITP
a17ef0af-3174-5bd9-884b-b5bf0cf09570 | date | Date Completed:
| checkpoint | Final Inspection
1efa8641-bc6e-5e7d-87c6-3dd32e5c0b84 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
700c9bb4-2979-52c6-88b5-d9f566303ea6 | textbox | Name:
76635bbd-f048-5c63-b24e-03eff142d6ec | textbox | Position:
368751fe-511a-55ee-b610-21bd94f01346 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-125-STR-CPD-Precast Plank Installation Rev 0 | itp | ITP-125-STR-CPD-Precast Plank Installation | d76050dc-2499-4299-9ca7-99cef365564d
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
2b1ae403-d883-5d17-97e9-69462e07ad34 | note | Document Title: ITP-125-STR-CPD-Precast Plank Installaton
2e360715-79dc-5edf-a30d-46e39bbe15d7 | note | ITP Description: CPD-Precast Plank Installaton
a0d63bc0-2a26-5591-bf14-92f51e4455a2 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
2a1bd7a3-bc5b-566a-8892-a7c2c2b25c9a | note | Discipline (e.g. CIV/STR/RAIL): STR
d3e88b0d-058b-50e5-b83a-0206fefbddd2 | note | Revision Number: 0
14de5a8f-51eb-56d2-ba09-c7db5e4a3009 | note | Revision Date: 19/01/2024
48145ebe-1510-51d4-b34b-eb646a11a49d | note | ITP created by: Andrew Carlini
6d83cea2-795a-5fd8-963c-364403f82e44 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
bd7b36c9-d1e0-56bd-bd85-7a8d129a77c3 | note | Reference - VR 652 June 2010
| checkpoint | 1.2 - Non Dependent
8a790d94-1783-5f73-8d9b-e74df1ee22c8 | note | Reference - VR 656 June 2010
| checkpoint | 1.3 - Non Dependent
499582b1-4b3f-5c87-83ac-b2252d7e6493 | note | Reference - VR 610 February 2020
| checkpoint | 1.4 - Non Dependent
99db9bd5-04aa-5d6c-a130-1e5e55e44fe6 | note | Reference - VR 613 June 2017
| checkpoint | 1.5 - Non Dependent
0d939d3f-e5ad-583d-921a-35ae27b01f1f | note | Reference - VR 620 May 2009
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Precast Elements
26be249f-e6c5-59d8-ab93-1e8e7adf49d2 | note | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020), 620.03
9e165151-6449-564c-be48-d0c765960da9 | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
f83da78a-b395-509d-b9dc-b234805976ca | note | i. Certificate of Compliance / Birth Certificate
a86048ff-f96c-55d4-bebb-fd118f44d475 | note | ii. Compressive strength test results
db62cb1d-86da-5506-a047-4ae796798f89 | note | iii. Precast Lifting Design
4197193d-0959-5b28-a8c7-02529a05b562 | note | iv. Pre-pour check sheet / ITP
1e300acc-014c-54bf-8705-24f8ea9ecc40 | note | v. Pre-stressing check sheet / ITP
e63d56eb-e4db-5894-90ae-809869eab5eb | note | vi. Post-pour check sheet / ITP
7f5dcf2a-04a5-5994-b923-8464505d0daf | note | vii. Covermeter check record
13222f9f-c467-56aa-84ca-9d1337f10b2d | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
52f3cdb0-230c-5356-b06d-18036a8e69db | note | Note: Different revisions of 610 have different clause numbers
be20a7d9-9cec-5b85-891c-0b606f544992 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
8fad280c-7e90-5462-9126-ec649965cc3d | textbox | Enter: Teambinder MDR Lot number
d8fcb750-731a-5e04-8774-fe91dd81c35e | note | Method - Document Review
a30b8a44-2839-5028-b3db-c6b8ef058251 | note | Frequency - Each element
4c6a85b8-cf20-5fe2-8209-e3c5ee363d23 | note | Category - HP*
f6543c4e-a53c-552c-8b1f-142b74643732 | note | Responsibility - PE/SE/SPE
f51cd75c-51b1-5692-8ca9-74f7e341cc4a | note | Verifying Documents - This ITP
d2fca6ac-7bf9-5d97-99a1-6e00f18b5c54 | date | Date Completed:
| checkpoint | 3.2 - Installation Work Method Statements
2471498b-05a6-5a5e-b1c2-98c7216c1e43 | note | Acceptance Criteria - Installation of Precast Plank WMS to be submitted for review to the Nominated Authority
68f494ba-d22d-5064-a37d-b6fc0804b4a9 | textbox | Enter: Teambinder MDR Lot number
3b55d0ea-aea6-54e6-b378-61f975e7b1e7 | note | Method - Document Review
7c3187d5-7e98-54a0-9c4c-35f2dd1084ad | note | Frequency - Once, 4 weeks prior to Instrallation of Precast Plank
d34bf418-f5e2-55c8-a22e-6e77aab6d1a0 | note | Category - HP
98813a93-2b15-5ea7-a7b5-e4922ce39369 | note | Responsibility - Nominated Authority
e97c22f7-e826-5201-bc47-d8ec945c8f14 | note | Verifying Documents - This ITP
a90b7492-864a-562f-8880-e54851ac124e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
4cdaa64f-f7ad-5ed9-95e3-9bccd5fc847d | note | Reference - MRPA Quality Management Plan
e66994d3-d4a1-5d23-9dff-cd37030e4c66 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
d8908d86-373a-52d7-9a49-4321eec00b61 | note | Method - Document Review
a93ab8a2-b113-5b58-a217-66bdc5eeae21 | note | Frequency - Prior to starting Works and at regular intervals
143bb8f3-9f3f-515e-9d40-62d86ad005fb | note | Category - HP*
241130eb-6216-5cb0-9f95-23c7e088a507 | note | Responsibility - All
fa88ffee-7b7b-5a8d-8321-3d4bfd5e558f | note | Verifying Documents - This ITP
52279578-ad62-546e-a184-e57007e57b4d | date | Date Completed:
| checkpoint | 4.2 - Survey Set-out
bb816f3c-d1f7-5b99-b6ac-83a63f084e46 | note | Reference - IFC Drawings 610.47 (a) Table 610.472
db90aaef-20a8-51d1-838a-313034fc326d | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
ba83a9a2-1f8e-56d4-9ecd-2e39726a7801 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
a6dbb2bb-7069-588a-bdf0-7e2348da1889 | note | Method - Measure, Visual
e0129314-8b6f-5b9c-b69a-7a89104e012b | note | Frequency - Each element
b79056a9-5866-5785-9c8d-36aefae0391d | note | Category - IP
4393a3ee-8376-55d1-862f-bec6d9880052 | note | Responsibility - Surveyor, SE/PE
fcb6e75d-b2ca-5aad-9205-a7a8a42c71c2 | note | Verifying Documents - This ITP
0aeed401-ee84-59f4-a5b6-60840f168148 | date | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Falsework Design and Certification
f6f5cc29-212c-5fde-81d6-659ab991c91f | note | Reference - 613.04 Temporary Works Design
a1791891-e3c8-5122-b9ca-530f81aca013 | note | Acceptance Criteria - The Falsework drawings submitted shall state all design assumptions and shall include a statement of the loads and any dimensional changes due to loading in all members of the falsework. The drawings shall be fully detailed including all member sizes and materials, dimensions, levels, erection procedures and other relevant details including bracing, connections and foundations, to ensure that erection and inspection of the falsework can be undertaken without reference to any other documentation.
e9ce3fc2-59a1-5880-b55e-18c602bfd386 | note | Attach: Temporary Works Design
eedf22b7-2005-5841-8407-704d9ec770d5 | note | Method - Document Review, Visual, Measure
5584cfe4-9dee-5430-9938-bfbb7e60c6da | note | Frequency - Each element
9dcec5f2-9bad-52c4-be55-6caef0a87e1f | note | Category - HP
a7997785-8554-521a-990e-8a105a849aa0 | note | Responsibility - Temporary Works Designer, Proof Engineer
f513b09d-8591-5c1e-aa99-48cd8641df85 | note | Verifying Documents - This ITP
a496f733-9ba7-54af-b6b4-b12343978fa0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Flasework Certification - Falsework Inspection
4182431c-dc1f-5739-ac36-db5686235aa0 | note | Reference - 613.04 Temporary Works Design
a6e86705-898d-598a-a728-2ba613b368f9 | note | Acceptance Criteria - The application of any permanent load shall not proceed until the signed Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed and accepted by the Nominated Party.
df3c140c-4c67-54d5-95c4-f4f7d5e8f2b4 | note | Attach: Temporary Works Permit to Construct, Apply Load and Remove
8552602f-c438-5c2a-8e9b-0496d63bdd65 | note | Method - Document Review, Visual, Measure
caff009c-e587-5dde-ae53-ed392b9bbe63 | note | Frequency - Each element
43fcba7b-160b-50e3-8ad2-54f2de7a6359 | note | Category - HP
02836efc-49fe-54c0-a522-584898d952e3 | note | Responsibility - Temporary Works Designer, Proof Engineer
6491f349-2fe9-561a-903e-b226a90cca42 | note | Verifying Documents - This ITP
937a6c0d-547b-59bc-8eb9-e76beaf89621 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Precast Handling
33be24b5-b9c4-57e3-94f1-99d33b0ef01d | note | Reference - 620.07 Crane Lift Study
efa65122-1470-5e94-a95c-d772a04f3059 | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
fd7fef2a-3d4f-527a-8222-5040a216e5d3 | note | Method - Visual
6ec50a5e-dabf-57f2-bc38-5fe22c5251f7 | note | Frequency - Each element
5f4aaf6e-d7fd-5cc2-a60d-8ba237bd5344 | note | Category - IP
8e91fb4e-bea9-56ad-b3f6-c75e0482b29f | note | Responsibility - SE/PE/SPE
16e2aae0-b8bd-55e5-a6a0-8a707a89727e | note | Verifying Documents - This ITP
8b5b3393-f0d7-589f-a430-8a8b384cbfb5 | date | Date Completed:
| checkpoint | 5.4 - Precast Placement
004fb490-4870-51ac-8b34-27a230305256 | note | Reference - IFC Drawings 610.27
039ef6a4-a34f-5be3-84b4-9834292568e3 | note | Acceptance Criteria - Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
37897c04-11f3-518c-abfb-2a81188eb9a8 | note | ○ The nominal gap between elements is as per the IFC Drawings.
82cb0e0a-88b2-5b02-80bb-6d5753d23848 | note | Method - Measure, Visual
514c4269-25d7-5cca-86a9-77dfc2cd157a | note | Frequency - Each element
f80e23d1-0ff2-5d31-b13d-09957ab15c85 | note | Category - IP
9979d6ad-49e3-5684-a06e-854851c8a656 | note | Responsibility - Surveyor, SE/PE/SPE
7d0def6e-0147-56a2-9165-c07188896e55 | note | Verifying Documents - This ITP
3e068717-4eff-58f0-b527-e7eb3170a10f | date | Date Completed:
| checkpoint | 5.5 - Precast Traceability
e58fb506-8a74-5b0b-9d02-fa9ef13a1131 | note | Reference - 620.09
1c3b99dc-b76a-5595-8869-90c3768540fd | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
fb0deaa8-9033-5ca7-9928-e11127b8cd59 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
e380b67e-aa7b-51a4-b721-688dfa0b8970 | note | Method - Visual
d88eba52-2fa8-56f0-a789-87c0924fc078 | note | Frequency - Each element
1e6f20b1-161e-5ab4-9cd7-5e3b87cb8d16 | note | Category - IP
b78195d5-9fd8-5985-925d-bd0f888c4ace | note | Responsibility - SE/PE/SPE
fbba969a-743d-5f49-b82d-4a5e48e8245f | note | Verifying Documents - This ITP
9076ff5b-5e9c-523a-b274-66f1857b1963 | date | Date Completed:
| checkpoint | 5.6 - Platform and Stitch Pours between Planks
47ce4841-65bd-510a-9875-ae550d0163fe | note | Reference - Structural Concrete ITP
4f683277-482b-5a02-a9f7-b788cc6d5a0a | note | Acceptance Criteria - Precast elements shall be stitched together, either by the Stitches or by the Platform pours. Related Stitch and Platform Structrual Concrete Lots to be closed out.
44bdb619-e125-54b3-9400-36c4d737d803 | textbox | Enter: Teambinder Lot number
62e6f2b1-d83b-5403-9dcc-5b7ac0319a2c | note | Method - Document Review
191eae18-6561-59d4-b041-d1c8cd21ead8 | note | Frequency - Each element
e14389f7-8520-5090-877d-d31e13a17f6a | note | Category - HP
c7974377-0bd8-5909-ab04-5da299122396 | note | Responsibility - SE/PE/SPE
3e6b4a7c-bb94-5747-af2e-fd8b5c94e9e8 | note | Verifying Documents - This ITP / Structural Concrete ITP
d5e446c6-b986-5ba1-b4c3-b8aec49068e4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-construction Activities
| checkpoint | 6.1 - As-built Survey
7775d68f-b077-5c04-acf9-aefe1f159ea4 | note | Reference - IFC Drawings 610.47 (a) Table 610.472 (Feburary 2020)
5f298755-217c-5fdc-ac41-47ad8ed6b522 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
f639301e-f2f3-572a-ac99-6ac540a922ca | note | Attach: Survey As-builts / Survey Report
dfa942a0-cd5e-52f5-ab3c-4c1aa1817fcb | note | Method - Document Review
56c08418-4e48-58cf-a0a5-1587eb0042c9 | note | Frequency - Each element
e961ccba-b47f-5397-a110-9cab9b6a8dcc | note | Category - IP
52636941-18a7-5440-96c6-e6732add34e8 | note | Responsibility - Surveyor, SE/PE/SPE
5eccd729-0a0f-5ba2-9162-db16fa36f010 | note | Verifying Documents - This ITP
ae359cc1-a627-56da-ab93-dee89ea124ad | date | Date Completed:
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
d8739096-ab34-5a20-be4d-f4e70e34352e | note | Reference - MRPA Quality Management Plan
78af91bd-a77e-5ebd-bf44-39a5761bd359 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
b8d78380-783a-5ccf-9795-fea2eca58d7b | note | Method - Document Review
1af32bc4-3c75-58ca-980f-9c369f82c357 | note | Frequency - Once, prior to closure of this lot / element / Work area
86becf8d-014a-5b84-930c-185e496fe3be | note | Category - HP*
51f6eb19-4752-5efb-98c9-03cb080f00a6 | note | Responsibility - SE/PE/SPE
71be903c-589f-5c95-9122-24c2fff47c60 | note | Verifying Documents - This ITP
295f1dcf-5135-528c-a780-fd6b7b752092 | date | Date Completed:
| checkpoint | Final Inspection
37b29a00-1444-5165-9166-73206833a3f5 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
bda98452-6fd6-5e79-8e79-06fbc0394f8f | textbox | Name:
6bbb70d4-1f04-5da6-86c2-cb16c2f347b5 | textbox | Position:
b07c3c06-13f1-5379-a011-7dcd16f92ab1 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-126-CIV-RSS Wire Facing Wall Main Rev 0 | itp | ITP-126-CIV-RSS Wire Facing Wall Main | 20fcc269-03f4-4aa1-9f9e-ca0852db184d
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
e67349da-cb94-5052-866a-49430878e1aa | note | Document Title: ITP-126-CIV-CPD-Wire Facing Wall Main
6bec8604-3593-57fa-8375-0484bf9864e6 | note | ITP Description: CPD-Wire Facing Wall Main
ac690495-eb99-57dc-af99-c98e370b53f8 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
e72ec9fd-432b-5e81-87ff-96da785eac20 | note | Discipline (e.g. CIV/STR/RAIL): CIV
f4d648f6-cc0e-5032-9153-4abbf67c3503 | note | Revision Number: 0
ed4f39e5-f7bf-5975-8af3-558b4612457c | note | Revision Date: 01/12/2023
fe17837a-4afb-5b33-8d49-ac518bbddef2 | note | ITP created by: Matthew Dib
fab9e5be-ac7d-5b93-8cea-d992c4839ea5 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
c6ac2dd0-f740-54c0-bf2b-f1d98628adcd | note | Reference - VicRoads Section 682 November 2018
| checkpoint | 1.2 - Non Dependent
46ca9f13-7c04-5343-a856-d7b72b7208ca | note | Reference - VicRoads Section 204 December 2015
| checkpoint | 1.3 - Non Dependent
a72d5392-25ca-5f0d-8c70-f80f8c2f0c5f | note | Reference - IFC drawings
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Select fill
df49bfcc-9d51-5410-8287-61d770f3f2c3 | note | Reference - IFC Drawings VR 682
ecd53213-f24a-5c3e-8772-6c6daa01f191 | note | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
2231807c-1461-525d-a018-86fbc5133a5e | note | ○ UNIT WEIGHT (Max): ≤ 16 kN/m³
b36ceae5-db32-504c-b2e4-6d528c5f07d0 | note | ○ COHESION (Min): ≥ 0 kPa
3fe0dc2f-28b6-51fc-9e09-ed99c8a2c9b2 | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 36°
760bcf52-5045-571e-9052-971c426a8b44 | note | Gradation:
afa19003-602d-55e7-8862-0040b223f9b3 | note | ○ 150mm : 100% PASSING
445f4a5a-d08c-5e2e-ab2f-e2e0ae5f693d | note | ○ 37.5mm : 60 TO 100% PASSING
c72fe095-9b0f-5e80-be63-4200496831c0 | note | ○ 9.5mm : 25 TO 100% PASSING
ba3190eb-9ddf-5b15-ba53-8c15e8cade4e | note | ○ 2.36mm : 15 TO 100% PASSING
51f4e327-c4fa-51de-8bad-6c44a11391aa | note | ○ 0.6mm : 10 TO 100% PASSING
ad8e6874-f4f2-5ca3-8c20-d16c4236029f | note | ○ 0.075mm : 0 TO 15% PASSING
1919f5d4-ec7b-5bc4-8fd7-fb46858f8438 | note | Electrochemical Properties:
8009bc81-ce18-5dbf-9b3a-f7a3de320a08 | note | ○ pH: 5 - 10
5c3c0feb-f3fd-5db8-a0c3-81b2ca1828a6 | note | ○ RESISTIVITY >1000 Ω-cm
d1ba29a5-b85a-5c63-a59e-6360ba1601a6 | note | ○ CHLORIDES <200 mg/kg
4c0fb4e1-1f3d-58f1-b6dc-26a6e9d712ee | note | ○ SULPHATES <200 mg/kg
8b95c4c1-90d5-5604-9663-d3ee3429d08e | note | ○ ORGANIC CONTENT 0%
c42fcebc-f614-5bab-a23a-7495c38af174 | note | Structural Properties:
074659eb-ae54-541e-8541-fa5b1a6c7206 | note | ○ LIQUID LIMIT ≤ 30%
8bf3db07-2ad4-50d1-99b5-afd0fe73b0fa | note | ○ PLASTICITY INDEX ≤ 12
809709f3-ef34-5ccf-b1f3-1d73c2d4c3ef | note | The select backfill must meet the minimum requirements of Vicroads Type A filling
0a058390-aa9e-59d9-bf35-2f5984d0fe69 | note | Reference: Material approval in Teambinder
87388311-7a09-57e0-a0c7-84fb1264f08d | note | Method - Document Review
8045e7a4-3f7b-52f3-b91d-45a5ddd5a5ca | note | Frequency - Each material specification
ecc0b059-a55b-50c6-9a3f-78c838462f1e | note | Category - HP
d546782a-b404-5d29-8190-49e0ab605490 | note | Responsibility - Nominated Authority
3918a403-55e6-5e43-8aa3-0d4441301731 | note | Verifying Documents - Material approval
128964b9-782f-5e8f-a61d-3900859635d3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - General fill
97841cca-3fe2-5e68-986b-8f55d9301598 | note | Reference - IFC Drawings VR 204
20eff7fb-26a1-597e-b73e-471bcdd31ad3 | note | Acceptance Criteria - Backfill behind the reinforced block shall be Vicroads Type B or better in accordance with Vicroads standard specification 204:
e405eb8f-2a0d-59df-9ec2-8223e36b8182 | note | Select General fill shall comply with the requirements of the RSS designer:
8d08ffa2-3149-5caf-b514-d9d6832d3410 | note | ○ UNIT WEIGHT: ≤ 19 kN/m³
0b2e8bc1-5c95-5a60-870b-4f55c79240a8 | note | ○ COHESION (MIN): ≤ 2 kPa
a8f873ac-6f13-5a16-b4fd-4571885692fc | note | ○ INTERNAL FRICTION ANGLE (Min): ≥ 30°
99cfbee1-d8a3-5903-ba53-377fecc4f7fd | note | Reference: Material approval in Teambinder
6b044baf-0910-522e-b70a-7283c7395369 | note | Method - Document Review
aa379bda-40d3-5813-83f8-02802b02f52d | note | Frequency - Each material specification
a1bd387b-9c67-5ace-8fae-60913f5a3ec1 | note | Category - HP
5cd679c9-de67-5e7e-8fd9-84d1928dc45d | note | Responsibility - Nominated Authority
5fa06900-88e8-5664-9c3b-d7e6a8a57acf | note | Verifying Documents - Material approval
29a485f7-27a9-5698-a8c2-706828986b28 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Cobble stone backfill
045416ff-a80a-5e10-80ab-598b681c5fd7 | note | Reference - IFC Drawings VR 801, VR 715
c2154e04-ad95-5b58-bb4b-f65d6917caa6 | note | Acceptance Criteria - Cobble stone backfill shall have a minimum dimension of 100mm, and maximum dimension of 150mm.
dc0893fb-005f-51c3-aa8d-0915a0d1317f | note | ○ Cobble shall comply with the material requirements of 'sound' rock as specified in VR section 801:
d44f88dc-e783-52ee-9d08-d6e2fdf5d09e | note | ○ Cobble shall comply with the Los Angeles Value (LAV) for requirements for Gabion Fill.
dc245c2d-de88-516b-9aec-1c4b640af2f2 | note | Reference: Material approval in Teambinder
30b349d2-7079-5c5b-9666-203f22fec602 | note | Method - Document Review
0c0dbf59-13b0-5594-bf5a-5908e0774ee3 | note | Frequency - Each material specification
8f60e789-cbb4-5cbf-8558-1656dc99e4f8 | note | Category - HP
f86a11ac-d5c6-58b0-aad0-c54e4d37acab | note | Responsibility - Nominated Authority
4ef9cd7d-202b-539f-a930-886c58e3d719 | note | Verifying Documents - Material approval
af986bcc-7420-5737-a002-25fa52b57ab5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documents
| checkpoint | 3.1 - Wire Facing Units
f7b5abbf-6a93-577a-8b8d-c22860c607a0 | note | Reference - IFC drawings
371e0df4-1895-573c-94c8-a21da9a2fc0b | note | Acceptance Criteria - Supplier is required to provide the following Quality Assurance documentation, typically this consists of:
2ed5272f-95c9-5755-9902-85bee09dd3f7 | note | i. Inspection & Test Plans
b48550d4-51de-5e74-a0d2-32ddba6221ff | note | ii. Manufacturer Accreditations
5063f330-309c-524e-af70-d3de9dd02bb1 | note | iii. Material Certificates & Test Reports
1499e239-b7a9-59b2-a04b-5afd078a0e5b | note | iv. Welding Records
e52a839b-19da-5e0d-bdad-7341bfef2083 | note | Method - Document Review
e85ed771-85f2-5833-86c5-94a08f984abc | note | Category - HP
30cb87e8-6e95-5b50-add8-75cdf0481171 | note | Responsibility - PE
f64c111d-1ddb-5d21-951f-0e6ceee844a0 | note | Verifying Documents - MDR
36cd100b-93ee-5ee4-acf3-85c919e9a6c8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Foundation
63edfce5-dffd-52f5-9c7e-a9e0f1dab053 | note | Reference - IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007, MRP-080-C-SME-DRG-34-CPV-CSF-3012, MRP-080-C-SME-DRG-34-CPV-CSF-3013
c5a2194a-acfa-5bc4-aea0-19015da379ae | note | Acceptance Criteria - Foundation material under RSS shall adhere with minimum design bearing capacity.
84b5af9f-63b9-517c-9fc0-578d6495a29a | note | ○ RW1: 200kPa
43e547a8-a46f-5014-b6a8-b7a7098c57ce | note | ○ RW6: 250kPa
90ecc310-9eaf-5a09-8c09-bd3cc0b45780 | note | Method - Test, Document Review, Visual
16f8938f-0257-56e7-8417-2cb701b35dfc | note | Frequency - Each retaining Wall
95eb317d-558e-5aa1-9dec-a284e9ae5f3d | note | Category - HP*
0e488050-736e-5db6-b2b9-2d8dbb5bca28 | note | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
954c62cc-caa7-5690-b2f7-9a2541b7c426 | note | Verifying Documents - This ITP Signed off, Test results
6a44e54f-fd16-5fb1-8fa6-64e7a61ded82 | date | Date Completed:
| checkpoint | 4.2 - Foundation
8dc4c542-c8c3-5ec9-b3e5-9d1c63ba4ffb | note | Reference - VR 204.12, VR 204.11
0c8cedb6-5e09-54c7-a1f8-0d6f04faae16 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
b431af38-20ce-5d77-829c-8f3dc1e62a70 | note | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
a5ba8e03-e87f-5d78-a25a-99874d7bb884 | note | Method - Visual
19347de5-bd1e-537c-83ce-f9177c498492 | note | Frequency - Each retaining Wall
95f716dc-054b-5850-9656-1d7db5aa3d4f | note | Category - HP
76bb130c-cc7b-50df-a129-849b7c20ae36 | note | Responsibility - PE/Nominated Authority
a2a226be-873e-5920-8c4c-00bae8dc0709 | note | Verifying Documents - This ITP Signed off
796ff18e-8184-5338-b72b-f705c0e5e85f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Wire Facing Unit Installation
7090db04-75a8-5d9d-9c27-9d216defb572 | note | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1201, MRP-DPK-080-00-CSW-0033-0-1206 VR 682.20
91d375ad-447b-5f12-a411-978fe471d1d2 | note | Acceptance Criteria - The level and alignment of lift of wire units shall be checked progressively after placement of each lift and prior to placement of the lift to ensure compliance with the dimensional and positional tolerances stated in the design.
1d92f260-552d-583c-a615-19a183a465b3 | note | ○ The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
14c47cd7-57fa-5020-9451-a515b504e47b | note | ○ Refer to checklist for row of wire units
96dbcf35-0567-5b30-a58d-41e47f7c2308 | note | Attach: Lot map
c7a7720c-a766-50ee-b58a-8d8a8c94c442 | note | Method - Visual Measure
224164c8-3537-587b-a1ef-89bdcd7e8de3 | note | Frequency - Each row of wire units
d73f455e-d2e4-568b-85e2-f5542ac935c9 | note | Category - HP*
ffe86b16-bb78-5aa8-ab1f-4ada79c679ed | note | Responsibility - SE/PE
b6fcd04e-7668-5c31-a2be-c0de18412d5f | note | Verifying Documents - Inspection record checklist: CHK-00X-STR-CPD-Wire Walls- Wire Face Wall Installation
88459560-122d-5ba3-b9b2-ea806bde8946 | date | Date Completed:
| checkpoint | 5.2 - Fill
d84c1668-098b-526a-a389-d6c12d566e9e | note | Reference - VR682.16
c2d3ca8e-c798-5cd7-ae86-78818bbfc9dd | note | Acceptance Criteria - The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
71cc1bfe-8872-5f52-88c5-8519a5db708d | note | ○ No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
c254f7ef-d9f5-5e18-aff1-2d62a5df42ed | note | ○ Refer to checklist for each fill layer
d36d458b-2c58-5e2a-9359-848b7713b118 | note | Attach: Lot map
f8b09cac-9200-5613-ad18-dab6c454f408 | note | Method - Visual, Test, Measure
0cb0dde7-bd67-5c50-a735-534a277006cd | note | Frequency - Each layer of fill
cdfd88fd-4db6-5144-925b-b41d073cdf98 | note | Category - HP*
71bfc595-9d8d-5072-9ee1-963bcf6a5d4d | note | Responsibility - SE/PE
5311d01b-d544-51ea-8264-5bf8c3f21bc6 | note | Verifying Documents - Inspection record checklist: CHK-009-STR-CPD-RSS Walls-Fill Placement
7cfdea52-7e00-5185-ae56-b0bb164afcc2 | date | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
95e92a3a-3091-51cc-a4cc-2333953fd728 | note | Reference - MRPA Quality Management Plan, IFC Drawings
a57cedb2-eda8-5439-b2b7-84cbb886802b | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings.
8aecb37d-94cc-53cd-925b-64816afd2d2f | note | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
231592d5-1896-5d1d-b040-631de4d82162 | note | (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
2f06e5b2-f634-5883-8ee2-37edf86458ca | note | (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm;
d5556de6-336a-53f5-ba04-5dcdb47b0fc8 | note | (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height;
d62deb4c-c673-590a-aa6b-f0f09a7c5a4b | note | (e) The wall level shall not deviate from the specified level by more than ±20mm;
ff94ffcd-66fe-5a3c-8289-b17dd3fa4347 | note | (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap.
7cb5e9ab-8e6d-5e8b-a95c-5cddd3e394a9 | note | (g) The levelling course level shall not deviate from the specified level by more than ±3 mm;
ecf142ba-6d21-51c2-b049-88d9cffeb7d2 | note | (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise
c1a81816-46b5-587c-aa09-41429d058e2f | note | Attach: Survey As-built / Survey Report
d0a7c0fc-43d3-5cff-bd1a-5b4a5c8fc0ad | note | Method - Document Review
c6e96205-64ab-57c4-b0f1-13e11dc1825a | note | Frequency - Each element
ccecc883-30ec-5d16-89b3-21fce9c6e3a5 | note | Category - IP
1371d605-8a2b-5996-8e0b-03a4b8439836 | note | Responsibility - Surveyor, SE/PE/SPE
dda04bb9-699c-51b5-ba9c-cc582979f8f8 | note | Verifying Documents - Survey Report
911ce21f-838b-51ab-aa9f-7d0a9123d6b3 | date | Date Completed:
| checkpoint | 6.2 - Wall Post construction monitoring
1a01004b-2773-5ecb-9fea-28166b958bbf | note | Reference - IFC Drawings VR 682.20, VR 682.151
3c1d2b30-4d0e-559e-98f6-1a99c13c2ceb | note | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
7553ae5a-9b42-51b3-a34a-186c80390a96 | note | Method - Measure, Survey
5250961a-e8fa-56a8-acbc-d7b4c08d7f15 | note | Frequency - Each wall
9fae5879-ddbb-58e8-8b9e-d07f7bb70d6d | note | Category - IP
d96bb50b-09ca-5f99-a56b-f647e4d089d5 | note | Responsibility - Surveyor, SE/PE/SPE
cb91a2f9-7387-5b08-8ca2-21b145706851 | note | Verifying Documents - Survey Report
5e7e77d0-b489-5d3b-8f75-d9eb7cd1b618 | date | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
70da3a7f-81b1-5be0-a295-e3e97442b098 | note | Reference - MRPA Quality Management Plan
873d6cc1-7f15-51fc-9079-043a0198b7cb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
6ae7a1d6-fcae-5da4-b32e-ba1f6e88cd1f | note | Method - Document Review
d2f9202d-d384-544a-945e-4bcefbc4b456 | note | Frequency - Once, prior to closure of this lot / element / Work area
7dc6fc13-b20d-57c3-a895-6755dd575479 | note | Category - HP*
ab6b51d5-a2f9-50e7-beb4-c52eefa78951 | note | Responsibility - SE/PE/SPE
eaf0e954-3c77-5f07-9111-9a4b36628244 | note | Verifying Documents - This ITP Signed off
486972d2-98d0-5df6-869f-db31e7a351cd | date | Date Completed:
| checkpoint | Final Inspection
d8864831-53ae-5565-87a3-cbbc3f57970a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
900aa6c4-1a44-5754-9253-231658e2de9e | textbox | Name:
2b8ba198-d19d-564e-b50d-e1dec23f9e73 | textbox | Position:
8409a9e6-8849-50b2-97bf-7ea7bd6a542b | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-132-STR-CPD-Structural Concrete Crack Repair Rev 0 | itp | ITP-132-STR-CPD-Structural Concrete Crack Repair | 242bfef4-0ac6-43d0-b8af-7dd00ac6e8e1
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
631da067-37a1-570f-90cc-d2792eefb791 | note | Document Title: ITP-132-STR-CPD-Structural Concrete Crack Repair
8d1e1e1e-ae45-5ae6-a0b0-4b3134b3a92a | note | ITP Description: CPD-Structural Concrete Crack Repair
8a159ef0-42df-5805-9602-38805374a9b4 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c28c640f-8366-5749-a793-7cfdd8fbe924 | note | Discipline (e.g. CIV/STR/RAIL): 132-STR
08c26f47-4618-5352-b73b-1b312288b094 | note | Revision Number: 0
c250d177-b2ee-597d-989e-db04c78faa2b | note | Revision Date: 7/02/2024
3bca33b5-a1b0-52ba-8328-03b09ff31512 | note | ITP created by: Andrew Carlini
d649edb8-e703-51c3-8643-9eda3de8d987 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
9e94c57a-bd87-5917-afeb-726d24274351 | note | Reference - VicRoads Section 610 June 2019
| checkpoint | 1.2 - Non Dependent
e8bdf75e-3b1f-5d20-81fc-929fa2c75f6b | note | Reference - VicRoads Section 687 August 2018
| checkpoint | 1.3 - Non Dependent
2b9c0113-788f-5ba6-8488-1fca5dffc87c | note | Reference - VicRoads Section 686 November 2018
| section | 2. Preliminaries - Procedures & Documentation
| checkpoint | 2.1 - Assessment of Cracks
5717e585-c90a-5fb3-a904-a6bc3f053121 | note | Reference - 687.01, 610.24 (b)
4269348b-980d-599b-b412-267961f4978e | note | Acceptance Criteria - The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years practical experience in the diagnostic assessment and investigation of concrete structures.
d08a0a7b-870c-52c0-aeb8-35b3725f8b84 | note | ○ Cracks to be determined either as active or inactive.
db06a38c-125d-5366-a7d4-ce2a4b13a851 | textbox | Enter: Teambinder Correspondence Approval number
4a394877-f6c6-50c7-859f-7d2f5b766c4b | note | Or
0e86ac97-43ef-5800-adfe-263b9fc3fc41 | note | Attach: Correspondence
3acd207f-6fba-5e7f-99ec-624aec4f2fdb | note | Method - Visual, Measure
27ae4607-d409-5475-866d-af2e49bc447c | note | Frequency - For each element, prior to Works commencing
1c2fa1d7-d36e-5e9f-a71f-b70124e910b7 | note | Category - HP
39051c03-7f19-580f-94b3-874da9095976 | note | Responsibility - Nominated Authority
c3fd7225-cd35-5377-907f-73045b7a43b2 | note | Verifying Documents - ConQA Hold Point Release
ca1ed8af-607c-5977-a682-23a1d417aaa0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Work Procedures
22754a73-15f3-5069-b293-cb05c6309991 | note | Reference - 687.01, 687.09 (a), 610.24 (b)
e397430e-5d96-55af-b2ca-1fd0453e9a19 | note | Acceptance Criteria - The Contractor shall submit a crack repair procedure/procedures for review to the Nominated Authority.
44131421-42c4-59c5-b4b9-69576f139806 | textbox | Enter: Teambinder Correspondence Approval number
6895b9ff-5bc1-5aa5-85cf-fc47694a83cd | note | Method - Visual, Measure
f1f5e79b-57b6-5e45-9ff8-960a0407b97c | note | Frequency - For each repair methodology, 14 days prior to Works commencing
7752aac9-3f4d-5ed6-8e11-ed21d1e69e4b | note | Category - HP
fe5257d3-ad08-5420-8f87-3ae390938b10 | note | Responsibility - Nominated Authority
555e6b91-a102-5028-8638-c87d714e63d9 | note | Verifying Documents - ConQA Hold Point Release
81ed4305-ee6e-56bc-ab5f-8ee535bd6ea8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Materials
| checkpoint | 3.1 - Flexible Sealant Selection - Active Cracks
991fbdf5-31b7-5cb2-86d4-cc405869487c | note | Reference - Product TDS 687.05 (c)
663dacc6-ad41-5df8-8253-914f867b6e05 | note | Acceptance Criteria - Product to be selected based on the following criteria:
cf4e93c2-0bc3-52d9-b1c5-1e32e2619fe6 | note | i. provide for a minimum expectant movement of ±25%;
68ce6b0f-4822-5e11-a992-59e340c80b7f | note | ii. Whether or not the repair/sealant is subject to traffic (trafficable or non-trafficable)
5532b2db-b40e-50c6-a9d4-b55fa85915c9 | textbox | Enter: Teambinder Material Approval number
ea7ee059-aa50-57c7-b923-28792f4376fa | note | Method - Document Review
dd79e41a-0b62-5028-9069-1dcd28788fcb | note | Frequency - For each product, prior to Works commencing
f2007281-fead-586d-99f0-357bfae25c12 | note | Category - IP
91b84bc4-a005-5d26-9a48-93acc194e0c9 | note | Responsibility - Nominated Authority
81b36935-b41d-5dc0-a95d-a86a2e92af47 | note | Verifying Documents - This ITP
67ebb1b9-240b-5648-a790-dab699f6c4f2 | date | Date Completed:
| checkpoint | 3.2 - Epoxy Mortar or Paste Selection - Inactive Cracks
3d3f3190-4581-57dd-a5da-ab3162fef5cf | note | Reference - Product TDS 687.05 (b)
6cca2e14-9ec8-5ad0-9db9-827786181439 | note | Acceptance Criteria - Product to be selected based on the following criteria:
44f236a3-6a6e-5603-9fe5-bd671cbb4d50 | note | i. compressive strength @ 7 days ≥60MPa;
0e53d026-9802-5b45-b0f0-ac18ed7cd825 | note | ii. tensile strength @ 7 days ≥25MPa;
45002782-d983-5ce8-a129-01438c43a710 | note | iii. flexural strength @ 7 days ≥30MPa;
b7fae06c-396d-5deb-a25f-faaa792e2ea6 | note | Note: For the routing and sealing, injection nipple/entry port placement and surface sealing applications only.
bb832ac1-d1d0-5cbf-bd50-0cace5445656 | textbox | Enter: Teambinder Material Approval number
27dc14c4-51c6-5dbd-95e4-370e463401c8 | note | Method - Document Review
e0738c00-582a-5ba5-ab4c-3c7653f209fe | note | Frequency - For each product, prior to Works commencing
474d24ac-08af-50ac-abe5-7c77c3dc4faa | note | Category - IP
2710710d-c186-55d8-a473-fcaeb4432cf0 | note | Responsibility - Nominated Authority
cd4193d3-c2f5-58aa-8457-4a0b73984fd8 | note | Verifying Documents - This ITP
ab2fcc17-72b6-5ef1-b9d0-077e17ad0088 | date | Date Completed:
| checkpoint | 3.3 - Epoxy or Polyurethane Resin Selection - Inactive Cracks
5bf219e0-686c-569f-b680-a823c0f5b980 | note | Reference - Product TDS 687.05 (a)
006606f6-1265-519e-8a34-4a2bfbd3f9ba | note | Acceptance Criteria - Product to be selected based on the following criteria:
10c25e4d-9051-5788-b201-ca7dee49c488 | note | i. viscosity @ 20°C - 23°C 650cps max.
bc0ba4fe-bdc8-521d-b72a-afb8a1158c69 | note | ii. compressive strength @ 7 days ≥60MPa;
73c15f2a-30a2-5dbb-b98b-2358eecbfcd1 | note | iii. tensile strength @ 7 days ≥25MPa;
054dcccf-553c-5b88-a0d7-457f285c0107 | note | iv. flexural strength @ 7 days ≥50MPa;
f5669c28-b996-5c84-b5e8-6bf5ced76395 | note | v. adhesive strength at crack edges @ 7 days ≥2.5MPa (or concrete failure)
a7222112-b37a-525d-b5b3-99cf0cb23c97 | note | Note: For the resin injection or gravity fed applications only.
9e8f8aa7-7892-5000-b6eb-3a5ae5a62265 | textbox | Enter: Teambinder Material Approval number
73755444-44f6-531b-97cb-7272f275c6ab | note | Method - Document Review
e9e51a07-aa89-5b33-9f0c-580af8c6dbf9 | note | Frequency - For each product, prior to Works commencing
f7789e42-3122-525e-8081-ddea1e0f7bf8 | note | Category - IP
665573f4-a97c-529b-8948-1675cac3b67e | note | Responsibility - Nominated Authority
35cc4bf1-3af5-59a5-931b-d93b66c082b2 | note | Verifying Documents - This ITP
6c4dbe27-0eb9-5828-9657-af91c1467241 | date | Date Completed:
| checkpoint | 3.4 - Silane Selection - Inactive Cracks <0.2mm Width
c6a40cfd-aa90-5430-8f40-f284270435b0 | note | Reference - Product TDS 687.12, 686.05 (h) (i), 686.05 (c) (iii) (1 - 5)
98cca28b-e17c-5727-aee2-544122fde75f | note | Acceptance Criteria - Product to be selected based on the following criteria:
60834746-9fd1-574f-acc2-f37a0437f542 | note | i. active ingredient: ≥95% (penetrant)
d3e34639-aa2e-5cb3-bc88-99f8ca824265 | note | ≥80% (solid silane)
13423a92-6b22-5cdd-ab84-bedb4c33c26b | note | ≥80% (silane crème)
6b904a89-e09d-54b1-9a3f-f79d9ff6cb29 | note | ii. penetration depth: 5mm min.
4e3bb0e2-6308-53db-8bc9-1263b5ae8b08 | note | iii. contain a fugitive dye to enable coated areas;
6037ea27-aa44-5e39-966e-d04270a88c65 | note | iv. be compatible with a film-forming top coat;
ef22c34b-d26d-552c-a775-8c3b8bbb6897 | note | Note: For the protective coating of inactive cracks ≤0.2mm in pre-stressed elements and exposure classifications B2, C & U only - 0.2mm cracks are acceptable in other precast elements and exposure classifications.
64430763-f625-54e0-ac4b-81ef7a90cebc | textbox | Enter: Teambinder Material Approval number
10cc313e-baae-5fa9-9bf2-be4992c1b8c6 | note | Method - Document Review
66642803-ec52-545b-8b5b-37464f2e389d | note | Frequency - For each product, prior to Works commencing
87aa0d2c-ca77-57d1-af7b-5390fe8afa5f | note | Category - IP
9bad495f-235c-5145-ba98-e02f72067730 | note | Responsibility - Nominated Authority
2038f8d1-dc92-5879-ac4c-2bea69cdd497 | note | Verifying Documents - This ITP
9c43fd95-a7eb-50d8-b142-ce3740667310 | date | Date Completed:
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Contractor Competency
f3d48307-be87-57db-87ee-a5c3b794401d | note | Reference - 687.04
8c06ed92-be37-52ee-be88-e1f4009a12e7 | note | Acceptance Criteria - Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application.
805e8ed1-37a2-59c4-b5ca-832789ad1b22 | note | ○ Documented evidence to be available.
d0ac6d21-a049-512b-8d3e-2fd3ab212507 | note | Method - Document Review
ae0d3e71-c268-5b0f-999f-2db29e88ca64 | note | Frequency - Once, for each personnel, prior to starting Works
ccbc71f5-e039-554e-be78-abd52b69626b | note | Category - IP
1449c3d2-d8ee-5359-9f59-e1a0dbd49923 | note | Responsibility - SE/PE/SPE
7bdd4e57-ff92-5d62-ba61-5153d794a5c8 | note | Verifying Documents - This ITP
7705d710-647c-506d-8ff7-4315611e0722 | date | Date Completed:
| checkpoint | 4.2 - Injection Equipment
a5cec70a-157f-5695-8285-b46918ebb666 | note | Reference - 687.06 (a), 687.09 (c) (iii)
03918125-72df-5453-86db-7e3c6366cd17 | note | Acceptance Criteria - Injection equipment to be simple, easy to handle guns with pressure regulation or limitations in the operating range and be simple to clean and maintain.
52c940a2-9ea3-58b0-a36e-04fc15a99b06 | note | ○ Nipples/entry ports to have shut off valves or at least the ability to be capped to prevent leaks or air travelling back into the crack.
ee9c2bee-332d-5650-b9d2-9d839c1824d9 | note | Note: This ITP does not cover special purpose, multi-component injection pumps.
ed1dc177-6ba3-5e6d-8f86-916f1dd91119 | note | Method - Visual
6cf294a0-b8af-5c93-a0c2-0d6f6255f467 | note | Frequency - Once, prior to starting the Works
8b91e47d-5f61-5f23-a7ba-884318c48446 | note | Category - IP
cec8ab32-a0ca-58cf-8a88-a548565e078f | note | Responsibility - SE/PE/SPE
c119738b-a543-5b2b-bed3-ea3f58eba34e | note | Verifying Documents - This ITP
0af4b517-d255-5014-b237-2d638e6329bb | date | Date Completed:
| checkpoint | 4.3 - Weather Conditions
93229e9c-be27-5239-b7c0-00f60001d450 | note | Reference - 687.05, 687.09 (c) (i)
0ef5cc60-a60c-5612-9173-42d497de0f36 | note | Acceptance Criteria - Repairs are not to be undertaken when the ambient temperature is below 5C or 5C on a falling thermometer, or above 35C.
3a735064-0004-5267-80ba-9437b840aefa | note | ○ Cooling the materials is allowed should the need arise if temperatures inadvertently rise during the repairs.
eadbb762-2f81-5d8e-aa51-df77bb39a26b | note | Method - Visual, Measure
0dc7a707-b92f-5f4b-a6cb-72756db8f64a | note | Frequency - Prior to each repair
b37e296c-d3cd-5e68-8e26-a418db075fac | note | Category - SP
4e1eba8b-b97f-5b55-a777-7b920290b69e | note | Responsibility - SE/PE/SPE
ed11f65b-aab4-5bb2-bc0d-cae0a45771b1 | note | Verifying Documents - This ITP
fb5362b3-46f2-592a-80a2-8a54b33b8133 | date | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Surface Preparation
47fb3ea2-6eb3-5597-9139-c82252373963 | note | Reference - 687.08
0326cb44-8224-5187-9693-3cfc6e6efa18 | note | Acceptance Criteria - Cracks and surfaces located within 50mm each side of the crack to be cleaned of all loose particles, dirt, dust, curing compounds, grease or efflorescence by appropriate means.
060d98d9-11d6-525e-8d35-706957864637 | note | ○ Where cracks and surrounding areas have been moistened during the cleaning process, sufficient time or accelerated drying-out needs to occur unless the crack repair materials are water tolerant.
acd66f7a-39d0-52d5-9510-ca62e5bae71b | note | Method - Visual
756a00fc-d7e4-55e2-b78b-fe17a7f50e8e | note | Frequency - Each crack
e71980e4-8a9c-5c07-a633-66bc0a8ba50a | note | Category - IP
dd321ae7-2b2f-54d4-ba6a-3111fba32a07 | note | Responsibility - SE/PE/SPE
36e16b9a-6b8f-5094-9bf1-9801d157d54e | note | Verifying Documents - This ITP
8d56db4f-fc95-5ce8-8af7-f16e8bb99347 | date | Date Completed:
| checkpoint | 5.2 - Active Crack Repairs - Route & Seal Method
6aa06162-11bc-530e-b505-a66afd809cc0 | note | Reference - Crack Repair Work Procedure, Product TDS 687.10 (b) (ii), 687.15 (a - d)
5ee8bbcc-063e-5e69-bb04-d472d3bdd9bc | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
6988f117-0cef-5f04-93c5-9e6ed7eac73b | note | i. All materials in date and mixed as per the Product TDS;
0679d88d-21bd-51bd-937c-35b2ce2254da | note | ii. Saw cuts to be at a width to depth ratio of 2:1 and rectangular in section;
4f2ce46f-abd3-555d-9c53-2f98e304016f | note | iii Surface dust to be removed;
ccac4838-ea01-5532-9685-45744aef5508 | note | iv. Bond-breaking tape to be placed at the base of the chase/reservoir to limit sealant interface to 2 no. faces;
0836a506-c24a-562a-83bd-243ed5991805 | note | v. Where required, masking tape to sides of the adjacent surface to create a neat finish;
041b006e-2252-51dd-8abd-d239b3bf2948 | note | vi. Sealant gunned or tooled into the saw cut to completely fill the void;
54674928-fb77-55c7-931f-5cfbb84b05a2 | note | vii. Product shaped with a suitable tool to recommended profile;
97183bd6-702d-55f8-a50b-df2f6f8fc40d | note | iix. Repair to be protected from damage or adverse weather while curing;
2ea60739-831f-58fb-8c0c-fbfcd19a9616 | note | Method - Visual
df23ce35-01fb-58c1-a067-079496a8af1b | note | Frequency - Each active crack
1b150d36-c8a0-5f33-9e3d-ae47808ef985 | note | Category - WP
ded4e10a-5d92-5081-b839-eb2d71d81e81 | note | Responsibility - SE/PE/SPE
aed8cf86-9f69-5c8b-a254-f930b4d984a2 | note | Verifying Documents - This ITP
dc163beb-c101-569e-9b21-c2469c4f2b28 | date | Date Completed:
| checkpoint | 5.3 - Inactive Crack Repairs - Route & Seal Method
602e717b-2b3c-5093-bd9b-b338ef16014f | note | Reference - Crack Repair Work Procedure, Product TDS 687.10 (b) (i), 687.15 (a - d)
960b8bd6-7eb0-544e-b101-8182e8d26207 | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
221d7d38-3cb8-55fe-8d99-db10edc81575 | note | i. All materials in date and mixed as per the Product TDS;
30e12a6f-9d09-5fa5-b888-abb7e1c205de | note | ii. Saw cuts to be at a minimum width and depth of 10mm and V-shaped in section;
67a5f286-162e-591d-aee8-c97fdfda4f58 | note | iii. Surface dust to be removed;
7a2323ba-6b0e-5d19-9595-90cbb6fb2ff1 | note | iv. Epoxy mortar / paste placed into the saw cut to completely fill the void;
167c5e62-59c7-502b-8172-07c928741f45 | note | v. Product finished flush with the surrounding surface;
b2e37944-6e14-5dd7-b459-6d31f2b210fb | note | vi. Repair to be protected from damage or adverse weather while curing;
536e20df-ac59-57b8-9e76-16a3898130aa | note | Method - Visual
bbd83ff4-6a87-55f4-9380-b75ae71c2134 | note | Category - IP
7c90ac40-829d-57a1-92db-12c5172542ed | note | Responsibility - SE/PE/SPE
88fd1163-0144-5993-8e85-0c70597335ed | note | Verifying Documents - This ITP
2ec0e8ee-12e3-514a-8bf5-e6017c935a13 | date | Date Completed:
| checkpoint | 5.4 - Inactive Crack Repairs - Gravity Fed Method
21e5c28d-4897-51bc-b8e8-cb156939729a | note | Reference - Crack Repair Work Procedure, Product TDS 687.11 (b) (i - ii), 687.15 (a - d)
5508f3bd-0cab-59d5-b4d2-c994f8171f90 | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
56af1bf0-8523-5f29-be6c-f1471b4c954f | note | i. All materials in date and mixed as per the Product TDS;
bcd236a4-e953-55af-9885-f7b378b55b0f | note | ii. Where required, a water-tight reservoir, to be created with silicone or polyurethane sealant;
bb6aecc7-67f8-522e-b68a-801d4ce34f1f | note | iii. Epoxy resin to be poured onto the crack and either sufficient amount contained in the reservoir (if used) or worked back and forth by suitable means (such as a broom) until no more material can be absorbed;
595a6645-ca02-5155-b15a-f549875ed6d6 | note | iv. Excess material and reservoir can be removed as the epoxy resin gels;
3bca6743-2203-5e28-adcd-ab737ee2c13d | note | v. Repair to be protected from damage or adverse weather while curing;
05c16dbe-3481-5f8d-9faf-ec6ff358a4a3 | note | Method - Visual
b2861216-cc27-5b57-beb9-742a90e69954 | note | Category - IP
ac90d54f-79d5-51e2-878f-d565187e9249 | note | Responsibility - SE/PE/SPE
93efaec5-b39f-5476-a713-a72e5915ec63 | note | Verifying Documents - This ITP
f24bb8de-9196-57ea-873e-b361fc7c622a | date | Date Completed:
| checkpoint | 5.5 - Inactive Crack Repairs - Injection Method
6940607b-6ed4-5221-9a24-565b84f246df | note | Reference - Crack Repair Work Procedure, Product TDS 687.09, 687.14 (a), 687.15 (a - d)
5e2e51bd-4bd1-56ea-851d-3b3c4639df66 | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
e52a1303-9b2c-5b56-954a-dabb96469d51 | note | i. All materials in date and mixed as per the Product TDS;
1b29ee94-0529-5b02-a15e-dda44ed3a732 | note | ii. Each nipple/entry port coated in epoxy mortar or paste to create a water-tight seal to the entire perimeter;
cbaab2b7-4425-58dc-9478-f9a094a89c09 | note | iii. Nipple/entry port placement central over the cracks at 200mm spacings maximum (where cracks are through the full section, nipple/entry port placement shall stagger);
e649767a-8f37-5b36-9196-fd5ec9bdf803 | note | iv. Epoxy mortar or paste applied to the surface of the crack in between nipples/entry ports and the full height of the crack if within tolerance to eliminate resin leakage);
2da9f489-211a-50ae-8f53-317ec4239f93 | note | v. Once the epoxy mortar or paste has fully set, connect the injection gun to the lowest nipple/entry port (for vertical cracks) or at one end of the crack (for horizontal cracks);
dc5f234d-7f9f-5c84-87f8-920d52d76e72 | note | vi. Initiate the injection, applying pressure until resin can be witnessed entering the next nipple/entry port;
39ef2894-574c-533f-b098-9dba8a670f25 | note | vii. Stop pressure and close the valve of the engaged nipple/entry port and connect to the nipple/entry port where the resin appeared, working either upwards (for vertical cracks) or along the crack (for horizontal cracks) until all nipples/entry ports have been filled;
ecac0df4-bf1d-5a26-9018-c8b01ca9f408 | note | iix. Repair to be protected from damage or adverse weather while curing;
a3f58259-c967-564b-b715-9597635f1302 | note | Method - Visual
133ad420-f699-5368-9388-adc6dc48f698 | note | Category - IP
0dd6f304-9926-57cc-b054-d00198557394 | note | Responsibility - SE/PE/SPE
051a8a35-fc99-52d2-8beb-74f8f5c6adbc | note | Verifying Documents - This ITP
e19e43d5-b691-5500-8f0d-346f73f8f4fc | date | Date Completed:
| checkpoint | 5.6 - Inactive Cracks <0.2mm Width Repairs - Penetrant Coating Method
9376df2d-302c-5d79-92b7-e4c42c087b83 | note | Reference - Crack Repair Work Procedure Product TDS 686.07 (a) (i)
1bf07fa8-e06b-5a0f-873c-eea5cb14f521 | note | Acceptance Criteria - Approved procedure to be followed, steps to witness:
9bd08c8a-06ec-56f4-8dd9-891cebdec19f | note | i. All materials in date and mixed as per the Product TDS;
15d8354a-8bf0-5550-8655-59d1d8db8fba | note | ii. Silane to be applied with an airless sprayer (for penetrant) or brush (for Solid Silane or Silane Crème) , working from low to high areas and approximately 150mm beyond the extent of the crack;
b6264939-2caa-5850-a594-a70ec864473f | note | iii. Application rates to be as per the TDS for each type of product ensuring wet appearance;
a9415c42-bb89-5de5-8352-186d29ef97cd | note | iv. Re-coating if required;
05c4bf1c-308a-5653-a76e-113970911025 | note | v. Repair to be protected from damage or adverse weather while curing
18c3ba6f-15f9-5ba9-bfdf-08ae0f0637a5 | note | Method - Visual
c96ea42f-5e58-536e-a4cd-e85c3b3f622a | note | Category - IP
7422f4ff-d39a-5ad3-976a-e69cdf384039 | note | Responsibility - SE/PE/SPE
4fdb7ea7-9158-52ff-a5b0-19c169337814 | note | Verifying Documents - This ITP
6f5e5150-1677-5980-ac50-4bd7f7a5a70e | date | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Curing & Finishing
09725799-2f86-5df1-b995-1019265a3efa | note | Reference - Crack Repair Work Procedure Product TDS 687.15 (a - c)
452f24b9-427c-564d-a6f4-9b4f26af625c | note | Acceptance Criteria - After the repair materials have cured in accordance with the manufacturer's recommendations, any surface seal, nipples/entry ports and repair materials can be removed by suitable means.
413b175b-7514-5bf9-8433-af86c8cbf659 | note | ○ The surface shall be ground smooth, leaving no traces (indentations or protrusions) of a repair and if the repair location remains exposed, a fairing coat can be applied where not being coated with a pigmented coating system.
2dc6fee6-200c-55d2-8c2e-773b094fe860 | note | Method - Visual
6d18e846-e41e-5f62-9bc2-f7de86c7643c | note | Category - IP
256a50ee-72af-533c-869f-db19e58209c8 | note | Responsibility - SE/PE/SPE
debc2476-46e0-5ebb-adfc-5df22fba17a6 | note | Verifying Documents - This ITP
d96fb820-b638-5f33-bddb-117a61b3bac9 | date | Date Completed:
| checkpoint | 6.2 - Repair Verification
4e80b5ff-c816-58e0-b479-59f5c0e64422 | note | Reference - 687.16
257d7525-0a07-5076-802f-5151049c3afe | note | Acceptance Criteria - After 7 days minimum, 75mmØ core samples shall be taken to verify cracks are fully sealed.
ac57d4f7-b4fe-52d3-bcab-bd1983ce3c04 | note | ○ Cores to be located in conjuction with a covermeter to avoid reinforcement and approved by the Nominated Authority.
d3a92884-0476-5926-bd24-377ef7790936 | note | ○ 2 no. cores for the first 25m of crack and an additional 1 no. core sample for each 50m of crack or part thereof.
a01d4b87-1ec4-55ab-b16c-821add892cfe | note | ○ Core holes to be filled as per the cementitious repair ITP.
a60c82be-4f31-58f9-b88c-41fdfe9bb984 | note | Attach: Photographs of Core Samples
90fff03d-6b75-5e79-9689-0cc0898b3aeb | note | Complete: Structural Concrete Cementitious Repair ITP
b5dcafed-7b73-5676-976f-5d8b648f3428 | note | Method - Visual
871ea712-f76f-529d-b6c2-4feb0acae562 | note | Category - WP
bbb0463c-c6c9-551b-973d-777fdb174eb2 | note | Responsibility - Nominated Authority
9677719d-f299-5a63-967c-44aa8b3f8d32 | note | Verifying Documents - This ITP
ac317d51-b26c-5178-bbc1-9818ddc0ccf9 | date | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
ee2ee4cc-4390-531e-b2f4-7319addd07cf | note | Reference - MRPA Quality Management Plan
e72fbe6f-71c5-55db-aa91-b6d932b5c872 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
3cefec86-54c6-5c90-b034-d92939cea48b | note | Method - Document Review
dda5c6ee-b087-51a2-be30-38631eaac0de | note | Frequency - Once, prior to closure of this lot / element / Work area
97e40316-95f5-5c1d-877f-bbef510c84ca | note | Category - HP*
38adbabc-ce83-5baa-bf7a-f28b82829890 | note | Responsibility - SE/PE/SPE
d5eaa0f1-0ad0-5b1c-827e-c0511ccd614c | note | Verifying Documents - This ITP
a781c536-c3dd-5a08-a90c-3e90f18e9f2b | date | Date Completed:
| checkpoint | Final Inspection
dd54137c-b0dd-5dc9-8c86-a08aa6e142db | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5af36060-900a-545a-90c1-58437b1b0753 | textbox | Name:
e70e19c5-f246-5e24-8222-ae1abf7f4dd9 | textbox | Position:
becd476f-1f16-576e-80f0-ff1734c970f1 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-148-CIV-CPD-Chadoak Water Main Relocation Rev 0 | itp | ITP-148-CIV-CPD-Chadoak Water Main Relocation | 67257f18-026c-435b-b2c7-73732ff1fe71
| section | Referenced Documentation
| checkpoint-no-value | Referenced Documentation
a235e9a5-e146-5bb9-ad17-c765f4e4c2b8 | note | Document Title: CHA-02-ITP-WATERMAIN
16925244-5f36-5aa2-9c18-af05a6250762 | note | ITP Description: WATER MAIN RETICULATION
24acc1ee-6992-589f-9fe4-3debdfbd0d36 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
026b74ef-5ecd-561c-ad68-fbf1e0a371a9 | note | Discipline (e.g. CIV/STR/RAIL): CIV
e7a28ec2-3081-5aa4-8818-9781aa6930f1 | note | Revision Number: 0
98c2a85d-ee32-5506-83d0-5ffab1e2f672 | note | Revision Date: 24/07/2023
ea5abc1d-543b-5585-96a0-d20c2f78f38a | note | ITP created by: Daniel Griffin
238f17cf-5d02-50a3-a43c-6ac30d0c2a95 | note | References: WSA 03-2011-3.2 Project Risk Management Plan (PRMP) MRWA Standard Drawings
| section | 1.0 PRELIMINARIES
| checkpoint | 1.1 - The current Water Authority Approved revision drawings are being used. including subcontractors’ copy
156d32db-ac79-5ecf-a421-d4f42f984358 | note | Acceptance Criteria - Current revision drawings are being used, ensure drawings have been Issued as IFC
e0c105fd-1003-531c-954f-40a96130ec85 | note | Test/Inspection Frequency - Each Lot
d46a7ad6-d78a-549a-b168-fe705dbe8b1f | note | Key - R
d80cdc90-b6bd-5777-9828-348df32b0609 | note | By - PM SP
ab980f33-67f5-59bd-bdbe-6d6e44f0b5d6 | note | Record/evidence - This ITP signed
| checkpoint | 1.2 - Applicable Permits obtained (includes Excavation Permits, BYD, Road Opening Permits, YVW Approvals & etc.)
6e306691-9487-5680-b598-a9fb7eaee0c8 | note | Specification - Design Drawings (Refer to General Notes & Legend)
ee7515a2-f216-5ead-a8e7-30907ec9eb6d | note | Acceptance Criteria - Permits obtained prior to demolition or construction from the relevant authorities
2f4c29e6-2083-5b7e-a5bb-5373eb1f288b | note | Test/Inspection Frequency - Before job start
1b0ffa8e-eae4-5060-ae0f-132d21b19a49 | note | Key - R
79971018-b791-5ce1-aa2a-5dbdb5ecab05 | note | By - PM SP
7f48a2c3-89b4-5420-af10-e478bbad94a2 | note | Record/evidence - This ITP signed
| checkpoint | 1.3 - Check pipeline material’s compliances
8d393a1f-707b-54bf-83c1-c3e5f2e22948 | note | Specification - Design Drawings WSA 03-2011-3.2 Section 12.1
7e3047e7-915d-5f2c-a922-d17b3d17a0cf | note | Acceptance Criteria - Use only products and materials specified by the Project Specification, Design Drawings or as approved by the Water Agency
a8e29ebe-8bb9-5636-be1b-f7dcebec17a5 | note | Test/Inspection Frequency - Before job start
494f6c9d-1258-51dd-9df0-7fccc2624630 | note | Key - R
cbccfd96-d064-585c-a872-32707ce3c1af | note | By - PM
c2771eed-6012-5327-8b33-25f876dbc3af | note | Record/evidence - Material Certificates
| checkpoint | 1.4 - Delivery and On-Site Storage of Pipes and Fittings
b308509c-541b-5421-973f-a7e605e370ce | note | Specification - Manufactures Requirements WSA 03-2011-3.2, 11.5.3.4
c9250891-e6f3-59d7-b502-cb1cd261808a | note | Acceptance Criteria - Goods received satisfactory condition. Handled and stored in accordance with manufacturer’s recommendations.
6c382798-8b17-57c3-bf51-caaec8a0d12a | note | ○ Pipes are clean and free of mud/debris.
46041a99-0e8a-58f6-ab71-ddbf760609f8 | note | ○ Pipe Ends to be capped prior to installation to avoid Debris entering Pipe
43c92033-1971-5b69-9f41-e922c707ee39 | note | Test/Inspection Frequency - Each Delivery
f866b794-0770-5d8b-b0de-9b4b08a842bb | note | Key - R
5ad6f527-839b-5878-b4a5-38e7021526ba | note | By - PM
3a789360-dbd0-5329-85fd-8179c697172d | note | Record/evidence - This ITP signed
| checkpoint | 1.5 - Delivery of Pipe Bedding and embedment
94283d17-e2cf-5f90-8ae0-3d7b28e62b5b | note | Specification - WSA 03-2011-3.2 14.2
6b481f89-4c85-5c63-bb40-8c02e464a7e2 | note | Acceptance Criteria - Material to comply with WSA requirements. Material from an approved quarry From the Approved Products List
bf806ca3-49d6-58d7-9c07-0c27537b1a0d | note | Test/Inspection Frequency - Each Delivery
05dbe40a-4816-5d79-865d-0e47cf70c626 | note | Key - R
cb127483-951e-579d-a8e7-d74c3b06d85e | note | By - PM
b731d5b1-c2dd-538b-a0f7-0dde3bfce08c | note | Record/evidence - Material Certificates
| checkpoint | 1.6 - Site Set out Survey
2e2304c6-61fc-5a84-8b6e-17868181181d | note | Specification - Design Drawings
d848e2ec-abbb-5dca-ac15-414a0f4421e0 | note | Acceptance Criteria - Confirm extent of works and ensure all services are pegged/marked.
40396868-9f7a-5860-905e-709d54fb83ab | note | ○ Clearly labelled offset pegs indicating chainage and depth to invert.
2a3b6b57-75db-55fa-b4ba-0930a7bf662e | note | ○ Ensure survey set out is to latest revision of drawings
06af4f7b-adf6-58ef-b68e-da9dd406984e | note | Test/Inspection Frequency - Before job start
314a59e6-e251-5dd1-8d51-51a5936f30b7 | note | Key - R
958b7002-36e6-5f68-8204-161c4030d2fe | note | By - PM
06b0c419-6e3b-554a-ac77-f6a7baa075ad | note | Record/evidence - Survey Pegs, records
| section | 2.0 EXCAVATION (TRENCHING)
| checkpoint | 2.1 - Excavate Topsoil within Clearing Limits
8351e937-eea5-5f0a-aecd-e035daa472b2 | note | Specification - WSA 03-2011-3.2 13.12
ce23461d-2227-5b6c-9870-f57a2844c047 | note | Acceptance Criteria - Prior to excavating trenches, remove topsoil within the width of the Formation to a depth of 150mm
d941c535-e18d-5dcb-b3d7-d668bbdf8a9d | note | Test/Inspection Frequency - As required
29ef2746-c87b-5e00-8f31-aebc852e5aff | note | Key - SP
d49e14d7-4ec0-586e-8ff8-64b256452197 | note | Record/evidence - ITR-W- 02
| checkpoint | 2.2 - Excavate to required Width and Depth
58b46707-d882-5fa1-bf24-800ee1b64dd4 | note | Specification - WSA 03-2011-3.2 13.9.1 MRWA-W-202
d4222383-9adb-5386-b780-32c7ad07dbba | note | Acceptance Criteria - 1. Keep sides of the excavation vertical to at least 150 above the pipes in strata other than sand.
83891624-2456-5e70-a5ca-942e1e0640d1 | note | 2. Lay marking tape along route of the water main as per WSA03- 2012, MRWA edition.
a2bca771-56e5-5847-8694-e96f1d2647b2 | note | 3. Maintain minimum clearances between mains and services in accordance with Table.
c5f792e9-78e0-57e2-8bf4-b00d36744c24 | note | 5.5 of MRWA edition of WSA 03-2011.
fb1edb24-2a55-5305-b1a1-c4070e3e62bd | note | 4. Excessive excavation to be treated in accordance with MRWA edition of WSA 03- 2011. 5. Lay pipes in a shared trench at the same invert level where possible.
14c2366c-9c97-5d93-9d7b-7629476688a3 | note | 6. Maximum cover is 1.5 x minimum cover. This does not apply where main crosses under other services.
71453194-1f1d-5e56-8923-44405e043469 | note | 7. Cross water mains above other services (except Gas) wherever practical. When water mains pass under other services or obstructions, clearance under the obstruction or other service shall be minimised.
adfaf139-46da-5463-b9d0-a7d208fe509e | note | Test/Inspection Frequency - Each Trench
5f772acf-1512-5984-a59b-814ef68333cf | note | Key - SP/CR (WP)
4f4ad159-aa30-50af-a7b9-6f5a3139a942 | note | Record/evidence - ITR-W- 02
| checkpoint | 2.3 - Ensure pipe work is installed as per Minimum cover requirements
2c65f593-7cba-5b3e-b684-cb77c96f743a | note | Specification - MRWA-W-210
c9e3135b-3b12-5d0b-a371-541bd0d5af0b | note | Acceptance Criteria - As per Table 210-A
67685c5a-b7a7-529d-a47f-e0a195a6d1b2 | note | ○ Railway 1600mm
4f139f74-9f94-5923-917a-efa9a32ffef6 | note | ○ Waterways 1000mm
fc81a034-1d2b-5f0c-9c52-3c9e01c2ae34 | note | ○ Tramways 1200mm Major Roads 1200mm
56ec6e0f-3bd7-57b6-9e87-5b64446de124 | note | Key - SP
| section | 3.0 PIP INSTALLATION AND JOINTING
| checkpoint | 3.1 - Pipe laying – Confirm Levels
6eaaa76a-4c44-5388-9f67-30e10afe0009 | note | Specification - WSA 03-2011-3.2 Section 15 MRWA-W- 202
3a39523a-9a4c-51d3-b321-1c25a2d6cc3c | note | Acceptance Criteria - Pipes are laid to levels, grade, and alignment as per drawings Tolerances:
cb4c10e3-d684-5ddd-a115-07d8d7864732 | note | ○ ±100mm lateral
d8cdf065-dc08-5c98-ba90-8b28437eef4f | note | ○ ± 50mm vertical
ec5c5d96-bd16-591f-84e6-ae699a129690 | note | Test/Inspection Frequency - Each Pipe Section
41787c23-bc4c-51bb-a9eb-c493d00862f5 | note | Key - SP/CR (IP)
1fe2939e-db2c-58eb-b11a-dbaca7a9b722 | note | By - SP (WP)
02fe33a5-895d-5fe1-83ac-9af2596564d9 | note | Record/evidence - ITR-W-03
| checkpoint | 3.2 - Pipe Joint – Deflection
5c77152c-5233-5c9e-88a9-0bf767cc87dd | note | Specification - As per applicable Design drawings. WSA 03-2011-3.2 Section 15.2
182bfccc-4aa3-5d7f-a0fe-b0e8ee5401b5 | note | Acceptance Criteria - Joint deflection shall not exceed the maximum permitted deflection as recommended by the manufacturer.
3c74b8b6-e947-54ce-b794-14be8d9bb0c1 | note | Test/Inspection Frequency - Each Joint
455051f4-e490-5f71-ba92-77c41bd36cf9 | note | Key - SP/CR (IP)
27861d3a-4927-5f99-9d77-ee1fb5d565a7 | note | By - SP (WP)
48aea897-9b11-5336-a641-d0a10d4afb8e | note | Record/evidence - ITR-W-03
| checkpoint | 3.3 - Pipe & Fittings Jointing
bac9064d-06fc-5419-b81e-d37249b41be4 | note | Specification - WSA 03-2011-3.2 15.1.4 MRWA-W-103
60d8b336-5a13-5f77-b2bd-de8aac40f55e | note | Acceptance Criteria - Pipe to be installed as per manufacturers. requirements.
cd4c6dd1-bbd1-5966-8bcc-e0bf2d758f4f | note | ○ Pipes to have Witness mark and correct chamfer angle.
653fce84-0e54-59cb-9fff-565460b827b5 | note | Test/Inspection Frequency - Every Joint
be8ea8c8-3825-515e-98f7-5b7bc37ea048 | note | Key - SP/CR (IP)
f452c10c-9e04-5d63-ad3d-6739ae125c7a | note | Record/evidence - ITR-W-03
| checkpoint | 3.4 - Installation of valves, air valves & hydrants
40c601a2-8712-541c-bd98-51bd659b7564 | note | Specification - WSA 03-2011-3.2 Section 15.4 MRWA-W- 109, 205A, 300, 301, 302, 303, 304, 305, 307 and MRWA-W-308
9ac9fe0d-f99a-5a67-b6fc-2b87bd428886 | note | Acceptance Criteria - Ensure fittings are installed as per specification
a477a4d8-e096-5605-a4e3-2f077fe27b5a | note | Test/Inspection Frequency - Every valve and fitting
b5e5c5a8-cd53-556c-ba12-c2547bb55470 | note | Key - SP/CR (IP)
cbdc9211-1674-501a-8212-a71bad11c007 | note | Record/evidence - ITR-W-03
| checkpoint | 3.5 - Thrust and Anchor Blocks
67e24ca5-017d-5cda-9f19-158bed51739c | note | Specification - WSA 03-2011-3.2 Section 15.7 MRWA-W- 104A, 104B, 204, 205A, 205B, 205C, 206, and MRWA-W207
37dbe061-d419-57c2-82bb-af1ec0c960a4 | note | Acceptance Criteria - Ensure anchor blocks are constructed to WSA Standard Drawing WAT 1205 Concrete to be approved supplier
f28df057-7e87-504c-a8ea-c3139d570423 | note | Test/Inspection Frequency - Every valve and fitting
b0558c34-e389-5d25-a523-3567645163bd | note | Key - SP/CR (IP)
0b7ac67b-cd92-51eb-bb0e-6cbc6aaf6978 | note | Record/evidence - ITR-W-03
| checkpoint | 3.7 - PE BUTT WELDING
5a0e67e2-d9b7-51f3-88bd-1ee1300c11dc | note | Specification - MRWA 15.21.2
7e6abe24-e337-51d0-8c50-c177561981bf | note | Acceptance Criteria - All joints for polyethylene mains and fittings are to be butt welded in accordance with MRWA. 15.21.2.
e72e3ddc-a3cc-5220-bc12-1a1c214e6332 | note | ○ Electrofusion welds and fittings are not permitted for use without the express written permission of YVW inspector.
f25379cc-0d93-56f2-9b56-15f8fb961539 | note | ○ Butt welding equipment shall be inspected, tested, tagged, and calibrated every 12 months by an approved agent, and be subject to electrical equipment inspection test in accordance with AS/NZS 3760.
781c5e07-bf07-5368-979f-ebe26b9847eb | note | ○ Before commencing a welding operation, the operator shall check the machine as per manufacturer’s instructions, and the electrical cord shall not be damaged and check electrical test tag.
5aed7c7d-5469-53f0-84b9-20f498e3f884 | note | Conduct visual inspection of weld. Check:
295d5507-535f-5be1-b76a-22c324074f90 | note | – beads are same size and shape.
b196487d-d1cd-5efb-a341-e384ed35e140 | note | – beads are projected evenly around diameter of pipe.
916e8db2-248a-5747-9f91-0ead41357758 | note | – beads are acceptable height.
0ee548f4-fcde-5743-9d28-ce0dd36fec03 | note | – no cracks or obvious faults in beads
a44c49a5-c66e-5431-b22b-b79fa75bdb1b | note | Note: Randomly selected welds from pipeline should be removed and tested during operations.
071059cc-7548-5e94-84e2-f76aa2393619 | note | Control static electricity build-up/discharge:
a3cb057d-ad8c-5fa2-b749-411cd67d2a71 | note | – wet entire exposed pipe surface (use anti-static liquid or dilute soap and water)
f4324b18-81e1-5dd3-800f-766f032853dc | note | – wrap exposed pipe with wet tape conductors (or similar)
e7b7d8b5-fd65-51c3-b39b-ea092e079392 | note | – Re-wet as needed.
0c3ac6ce-db65-5b7f-98e4-1b32da36308b | note | Key - SP/CR (IP)
c47ce1fb-078e-5343-b2a2-219b482aabf5 | note | Record/evidence - Poly Weld Joint Report – WSA- ITR- W-03
| section | 4.0. Backfill and Compaction
| checkpoint | 4.1 - Embedment
89383397-1f71-5eca-8181-4dee26ec14d1 | note | Specification - WSA 03-2011-3.2 Section 16 Table 19.1 MRWA-W-200, 201, 202, & MRWA-W-203, MRWA Backfill Specification Design Drawings
2d264986-6960-5f04-94c3-7df907c64ed5 | note | Acceptance Criteria - Material to be worked around pipe to ensure all voids at haunches are filled.
f54fe17e-4337-573c-b48e-63abb2632c74 | note | ○ Standard compaction test as nominated on the design drawings
83f54670-2330-523c-90c3-fe200d0d0987 | note | Test/Inspection Frequency - 1 Test at Start of Works
edd40e0a-2d7e-545c-a407-01c8f9d29dee | note | Key - SP (WP)
b53d5356-f16f-58f8-bf7b-016e19868bc4 | note | By - WR (WP)
1a73d1be-ae9f-5402-8385-a6ad435e85e3 | note | Record/evidence - ITR-W-04 NATA Test Sheet
| checkpoint | 4.2 - Backfill Material
e1ce0fcd-d846-5404-9da5-07f2367f0140 | note | Specification - WSA 03-2011-3.2 Section 17 Dwgs MRWA-W- 200, 201, 202, & MRWA-W-203
29b81643-3cc6-5cf8-92c0-200d628077cb | note | Acceptance Criteria - Non-Pavement - Backfilled using select backfill material.
efbe097c-871d-58b5-af0a-1d8ead34d2c8 | note | ○ Pavement - Backfilled using 20mm Class 2 CR to underside of road preparation.
96447316-3a45-55ef-97f3-7ecf7907f3a8 | note | ○ Approved Materials to be used
d0c70b22-38d0-59ef-ab7a-cd44505899ba | note | Test/Inspection Frequency - Each Lot
5fefdf32-ff4f-5517-bcb9-b56e1e471037 | note | Key - SP/CR (WP)
cfbaa056-30d3-5a22-91b8-9fdcc92c9b52 | note | Record/evidence - ITR-W-04
| checkpoint | 4.3 - Backfill Compaction
3ff5fd25-087e-538e-9193-deffc2f44ee6 | note | Specification - WSA 03-2011-3.2 Section 16 Table 19.1 Dwgs MRWA-W- 200, 201, 202, & MRWA-W-203, MRWA Backfill Specification Design Drawings
8509d3cc-e85b-54c6-a310-383c278c5fa7 | note | Acceptance Criteria - Material to be compacted in layers as specified.
313e297c-4974-5bfe-93d3-000ec5199ea9 | note | ○ Standard compaction test as nominated on the design drawings
9862b7c5-7327-54c0-a9df-fd3479a7a65a | note | Test/Inspection Frequency - Tests determined by length of section and depth
c4f811f0-08be-5b30-b7aa-c7aa965f0e3c | note | Key - SP/CR (WP)
0a852bfc-d376-54f5-a03c-685f8d5f6e29 | note | By - WR (WP)
472f3900-68e4-5df9-8595-ec68e51ea802 | note | Record/evidence - ITR-W-04
| checkpoint | 4.4 - Detectable Marking Tape
13aa2486-3121-5a01-82fa-f8aa83b666c2 | note | Specification - WSA 03 2011 Section 15.12
808a79d5-39f2-5dd7-a789-650b912d6643 | note | Acceptance Criteria - Install detectable marking tape on top of the first compacted backfill layer of all water mains constructed using open-cut Trenching.
0fda3a7a-d81b-5c78-84a0-6e0f6fbec3d2 | note | Test/Inspection Frequency - Entire pipeline length
cd14c1c3-29da-5590-941d-af4f520523fe | note | Key - SP/CR (IP)
38624e1f-c45d-55d0-91d0-ad5216e7fc7a | note | Record/evidence - ITR-W-04
| section | 5.0 OTHER ITEMS
| checkpoint | 5.1 - Marker Posts
bfecac7c-c36f-5995-be17-57b6ac9bbba2 | note | Specification - WSA 03 2011-3.2 Section15.18 MRWA 300
03d1abb7-3a2e-5189-b3fb-2a0afcd08907 | note | Acceptance Criteria - Provide location marker posts, plates, and other markings for the location of hydrants and valves as per drawings.
9cb68eb2-f794-50d2-bf23-678b84972d02 | note | Test/Inspection Frequency - Each
ce049d0e-f636-539f-96c6-a715b92533eb | note | Key - SP/CR (WP)
87f63e94-016c-5dfc-86f7-ffbe402d9f6b | note | Record/evidence - ITR-W-04
| section | 6.0 TESTING & REINSTATEMENT
| checkpoint | 6.1 - Swabbing of Mains
c7937cf4-6203-5d4d-9acc-85eb30a6d87d | note | Specification - WSA 03 2011 3.2 Section 18.3
f765bf2d-9d05-5e27-9aea-275e13d73a51 | note | Acceptance Criteria - Entire pipe network to be swabbed to remove any foreign matter. Swab mains as nominated on the Design Drawings. Ensure Foam swabs are numbered and sized to be flushed through the pipe in full, and two swabs are used for each run.
c2e71a50-9f78-554f-b78f-5cad43434d54 | note | Test/Inspection Frequency - As required
b2c7bb1f-1220-5918-8782-d07802621b3a | note | Key - SP/CR (WP)
705d2f06-1d16-5dc3-9b89-2092e5f232f5 | note | Record/evidence - ITR-W-07.1
| checkpoint | 6.2 - Flushing of Mains
6dabba81-40b3-5f0c-b8af-1fd7263037a5 | note | Specification - WSA 03 2011 3.2 Section 18.3
e0f33045-7d61-5987-9bdb-4e45c1e48133 | note | Acceptance Criteria - Mains to be flushed in sections through hydrants of washouts which can develop a velocity of 0.75m/s. Mains shall then be drained and filled slowly with clean potable water.
1d6a1c9d-f889-530d-962b-f7f84b459f22 | note | Test/Inspection Frequency - As required
828be4d3-0aa9-554d-97fb-ce6bc9174bdb | note | Key - SP/CR (IP)
56010a84-07dc-52a0-a3f8-bf52f62b7261 | note | Record/evidence - ITR-W-07.2
| checkpoint | 6.3 - Hydrostatic Testing Mains
b477f2b6-893e-5df6-a5e2-6ecd889eab08 | note | Specification - WSA 03 2011 3.2 Section 19.4 MRWA 19.4.1.1 Design Drawings
6ca989cb-5794-5793-a683-c3bc0bd95337 | note | Acceptance Criteria - Test Mains to nominated pressure on design drawings.
02c00836-f8e9-55d9-9ffc-d4e2229d3891 | note | ○ Duration and allowable top up volume as per MRWA 19.4.1.1
f4d56f2e-5987-5b6d-9f69-84c8a68e3abd | note | ○ Test pressures, durations and witnessing recorded on record sheet.
dd621b5d-e119-5231-bf32-f7c457d41c8d | note | Test/Inspection Frequency - As required
628070e6-293e-5c03-8749-d48ab59eaa81 | note | Key - SP/CR (HP)
fa526082-9fe6-573a-abb1-307962230668 | note | By - WR/SP (HP)
2afd6c59-2230-5ae1-9aca-c85688413705 | note | Record/evidence - ITR-W-07.3
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Reinstatement / Finished Surface Levels
e9cba338-e36f-5112-9dec-bf9b2c3a43df | note | Specification - WSA 03 2011 3.2 Section 21.4
c923a089-37fe-585c-ab3a-d5c79d283683 | note | Acceptance Criteria - ±5 mm in road reserves, including sealed pavements.
7093efac-c14e-582a-9351-062bc544c080 | note | ○ ±5 mm in trafficable, private properties
1a33c490-8f8c-5773-a682-29aeff26f00b | note | ○ +50 mm, -20 mm in non- trafficable areas
55734d35-be2b-5544-a7bc-bc5b5fac32ca | note | Test/Inspection Frequency - Each Lot
3289b816-b05d-52e1-8943-d16a2d3d8426 | note | Key - SP/CR (WP)
b623efb4-04e7-5085-9096-87ef4f866203 | note | Record/evidence - ITR-W-07.4
| checkpoint | 6.5 - Disinfection
0c979654-209c-588a-87fb-d8f4615c2926 | note | Specification - WSA 03 2011 3.2 Section 20.1
3b4de40d-d27a-5d1b-8456-3cb444f8b6e0 | note | Acceptance Criteria - Mains >225mm to be disinfected in accordance with the MRWA Water Quality Compliance Specification
3aee90f6-62ea-59fa-adf2-b134c809e6d0 | note | Test/Inspection Frequency - Each Lot
1a352462-35ce-55e9-b95f-90513657d4c4 | note | Key - SP/CR (WP)
8d51c2a5-e6be-504d-853d-b60a6e5fe43b | note | Record/evidence - ITR-W-07.5
| checkpoint | 6.6 - Asset Recording
bb1a413d-fb5d-5e6e-bce2-671eb7447847 | note | Specification - Design Drawings WSA 03-2011 3.2 Section 21 & 24
f039ed50-2df1-56dd-a72b-9561813be831 | note | Acceptance Criteria - As-Built survey data, prepared, collated and submitted
1e19bf40-77fb-5b9e-878d-28ab190848e6 | note | Test/Inspection Frequency - At completion of each section and the job
8f463e4c-8f44-5cd5-8fcc-ff8c775ea2bd | note | Key - SP/CR (WP)
8b4e538c-59f9-52d7-8f7e-afb8186fc4ca | note | Record/evidence - As built Survey
| checkpoint | Final Inspections Verification/Approval
64e8a27b-34a9-509f-b9e9-4ca9a3ff7764 | note | ○ Inspections tests have been completed
cf2fd448-be55-5b79-95e7-718963896086 | note | ○ Inspections tests have been accepted
efcf7c58-d0f8-57ee-90be-128578e0fbf1 | note | ○ Plumbing Industry Commission Certificate of Compliance issued for hydraulic installation
3a5fa18e-1b69-50d1-99a1-a1bcb2dc4d78 | textbox | Foreman:
85d33772-699c-5243-b2d3-145a01937098 | textbox | Project Supervisor:
94e1f620-d2c4-5630-9c24-cf2544a4ae2c | date | Date:
| signoff | Sign ITP
| checklist | ITP-149-CIV-CPD-Chadoak Manhole Rev 0 | itp | ITP-149-CIV-CPD-Chadoak Manhole | 620da2f8-5de0-40ec-9f6e-380cca4bcb7b
| section | Referenced Documentation
| checkpoint-no-value | Referenced Documentation
1fd62bfc-2b01-5cfe-81c8-c90d74768c5e | note | Document Title: CHA-01-ITP-SEWER 183011
01739214-26ae-55b5-9b58-46909dd04812 | note | ITP Description: SEWER MAIN RETICULATION
8501ddb5-af22-5792-95c9-05d457fa1e8b | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c93e7f4e-060e-5602-a556-46671e3b6893 | note | Discipline (e.g. CIV/STR/RAIL): CIV
e0d4d62a-f9cd-5ecf-9bc2-636222db6a7c | note | Revision Number: 0
75668021-0abc-5105-af5a-e20be0c08b8e | note | Revision Date: 31/01/2024
c048990a-bf5e-5d9c-ba80-cc7ac1a9cbd2 | note | ITP created by: Renee Warren
ab9b6e7b-5317-59dd-9e30-142cb6bfac03 | note | ITP approved for use by: Luke McFarlane
f6829d8f-2209-5bde-9431-9c232593a442 | note | References: WSA 02 – 2014-3.1 Project Risk Management Plan (PRMP) MRWA Standard Drawings, Project Drawings – 21217s1B
| section | 1.0 PRELIMINARIES
| checkpoint | 1.1 - The current Water Authority Approved revision drawings are being used including subcontractors copy
9d004ae1-104d-5636-9320-a244aca7c01c | note | Acceptance Criteria - Current revision drawings are being used, ensure drawings have been Issued as IFC
858c34dd-df18-51c7-adb7-b53e2a3a613a | note | Test/Inspection Frequency - Each Lot.
f59ea823-45d7-5a39-8e0c-69cb0868fbd0 | note | Key - R
85830bba-31e5-558f-86f4-e3b35093c2c6 | note | By - P M SP
2fb11386-36a7-5edb-84b7-def902dcda8f | note | Record/evidence - This ITP signed
| checkpoint | 1.2 - Applicable Permits obtained (includes Excavation Permits, DBYD, Road Opening Permits & etc.)
11eeb8f8-aebb-50df-9a51-f3ce64c8c6cb | note | Specification - Design Drawings (Refer to General Notes & Legend)
ecd4ca38-ae87-5b3e-9b5d-7c05b1619444 | note | Acceptance Criteria - Permits obtained prior to demolition or construction from the relevant authorities
065edb1f-cbd0-5442-87d4-dec28cd5ec4a | note | Test/Inspection Frequency - Before job start
bae73f5e-7725-5bfc-8f0a-ed28baf9eafd | note | Key - R
d99249b2-b969-5813-a2eb-6a7b91a16682 | note | By - P M SP
1b867727-98b2-510e-b19a-1e3a4ad13bdc | note | Record/evidence - This ITP signed
| checkpoint | 1.3 - Site Set out Survey
bddfac0a-aa24-5acc-a9be-4bcfdc2d98b8 | note | Specification - Design Drawings
72ca18b9-8ff2-5bc3-a627-d29afdee8e81 | note | Acceptance Criteria - Confirm extent of works and ensure all services are pegged/marked Clearly labelled offset pegs indicating chainage and depth to invert.
9972ef4c-47b3-56e2-9cdb-f62fccc925be | note | ○ Ensure survey set out is to latest revision of drawings
136d3616-da75-5559-b617-de2bc12a7626 | note | Test/Inspection Frequency - Before job start
e8f02f23-f4a6-5079-964f-a444387316c8 | note | Key - R
350706b1-17bc-53a7-8b35-220065ab0fcf | note | By - PM
963c62cc-841b-537d-a843-7e2ec4aa58db | note | Record/evidence - Survey Pegs, records
| section | 2.0 MANHOLES
| checkpoint | 2.1 - Concrete Manhole
bdeffe3c-f974-5cb8-aa48-3c1adbf2bf74 | note | Specification - MRWA-S- 518 MRWA- S-520
a4eefb87-c244-51d3-b772-5d2e6e559db7 | note | Acceptance Criteria - Ensure Concrete Manhole are installed as per MRWA-S- 518 & 520 as per figure 518-F
dc115d11-ca62-5e8c-9e66-717d05f5ebf1 | note | Key - WP
7b149da2-1da1-5f5f-bcde-933968b4463f | note | By - SF
8bcb3b11-4de5-5847-a864-401167af2406 | note | Record/evidence - ITR-S-05.6
| checkpoint | 2.2 - Access Ladder
2759cce2-be5a-5cb2-a610-ee7e808ddbee | note | Specification - MRWA-S-314
ad761fa8-c34c-50ed-819b-a235f30fc97d | note | Acceptance Criteria - Ensure Access Ladder are installed as per MRWA-S-314
f3670152-93d6-50ce-9f28-34600ea65199 | note | Key - WP
146cb23f-37cc-5060-96ea-269eac22ba8f | note | By - SF
5bb3ff06-b502-551a-8ba1-2acc11efea2f | note | Record/evidence - ITR-S-05.2, ITR-S-05.3, ITR-S-05.4, ITR-S-05.5, ITR-S-05.6, ITR-S-05.7
| checkpoint | 2.3 - Manhole Lid
77a39c24-0d2f-5778-9a98-9f59ce78af3d | note | Specification - IFC
2222c694-636e-59f0-af26-a3d38096d5a9 | note | Acceptance Criteria - Class B concrete lid to used
| section | 3.0 PIPE BACKFILL & COMPACTION
| checkpoint | 3.1 - Backfill Compaction
1523d7cc-3c02-50f5-8a7a-3bd333cf0b94 | note | Specification - WSA 02–2014-3.1 Section 20.1.4 Table 21.7 IFC MRWA Backfill Specification Design Drawings MRWA specification No. 04-03.2
765d927a-3acb-5543-949c-53c1330c5501 | note | Acceptance Criteria - Material to be compacted in layers as specified
d341896a-d730-5985-8c98-58a85ee73980 | note | ○ Standard compaction test as nominated on the design drawings.
39948ac4-1001-594b-a632-6aca91f08085 | note | ○ 20mm CL4 or CL3 crushed rock or crushed concrete backfill.
ebdf07b7-691b-58b0-91a3-b202018659a1 | note | Test/Inspection Frequency - Tests determined by length of section and depth
86cd1d26-5ad1-557c-b1ee-576eec9bccb3 | note | Key - WP
783c1b4d-0554-5784-86ba-a365489a001e | note | By - SF
f2a8cd95-f322-5def-8554-dd391ea39294 | note | Record/evidence - ITR-S-06
| checkpoint | Final Inspections Verification/Approval
36d783eb-ee0a-5a48-a522-94d9e15dd63b | note | ○ Inspections tests have been completed
829cb2b5-e4f2-5aa2-aafe-2062426402cb | note | ○ Inspections tests have been accepted
16893a8a-82a5-5e77-b624-0646e6b88075 | note | ○ Plumbing Industry Commission Certificate of Compliance issued for hydraulic installation
169aaee9-3539-542c-b641-dcd8f12c3b27 | textbox | Foreman:
faea7348-4113-5c00-ae96-a20cee3c541f | textbox | Project Supervisor:
92eaed6b-cfe3-5d27-b9ee-7090bddc739c | date | Date:
| signoff | Sign ITP
| checklist | ITP-203-CIV-CPD-Landscaping-Ground Preparation Rev 0 | itp | ITP-203-CIV-CPD-Landscaping-Ground Preparation | 298ebee3-25b7-4fbd-9ffa-307b5b32184a
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
9b88c657-a501-5a20-ada9-70cd9275e587 | note | Document Title: ITP-203-CIV-CPD-Landscaping-Ground Preparation
1ecc2209-6f7a-5da1-9270-ff242fae5cbd | note | ITP Description: Landscaping - Ground Preparation (Subcontractor)
d54f8a14-5204-5a54-a329-b76451cbcc17 | note | Discipline (e.g. CIV/STR/RAIL): CIV
2db99f07-3d88-5c76-9c40-890cf7326bdd | note | Revision Number: 0
d80392ef-5472-56fa-8e50-6183b6de6fc6 | note | Revision Date: 2/10/2024
cadda596-28f4-5795-b4bd-9567ab7bd922 | note | ITP created by: Jason Quan/Derek Collins
9bed7913-b825-52cf-80a5-16b438bfd0ea | note | ITP approved for use by: Pradeep Talasila
d0bb0b12-f83d-5e87-89a2-191698d84f76 | note | References: VicRoads 720
d3c1c392-7125-54cb-8024-67f60cb76299 | note | ○ AS 4454
62d1f85c-e54a-5dd9-9456-ea5829cf3c93 | note | ○ AS 4419
af15808b-2843-57e8-b037-671e29da6e36 | note | ○ IFC Drawings
b1806db6-4045-54e4-86bf-f69be9cf343d | note | ○ Sub Contractor ITP
| section | 2. Preliminaries
| checkpoint | 2.1 - Check for correct documentation
5775ac56-d92a-5ae1-8772-e3c5cb5f93da | note | Reference - Drawings and drawing registers
26477c85-5d86-51f3-9ec2-2f683d0464c1 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
f82c9001-a0f1-5084-bc81-6ddf29c9e125 | note | – Using the correct and complete set of IFC drawings
c09df657-9455-501f-b8f9-719f87d6d394 | note | – All drawings are the latest revision
396cb78e-51a3-5592-8fc4-66318e73a5d8 | note | Method - Document Review
359a84e0-3df4-546e-aa3e-f87c6fcfcc8a | note | Frequency - Prior to Commencement of works
d0ff7c73-6676-5f98-83d9-466f5c2fa1fd | note | Category - IP
885232b8-55be-58f3-88ac-8628ae191a78 | note | Responsibility - SE
e9b30bc1-f8bd-54c6-ac32-f4c86b541cf2 | note | Verifying Documents - Sign ITP
72f8a6f3-4bc8-535c-85ce-0b2a1a55be94 | date | Date Completed:
| checkpoint | 2.2 - Submission and records
378a12cb-63f6-5ef9-b243-04495d2757f9 | note | Reference - Section 720.03
4c916da4-2d77-5f27-8850-d7f01de988d9 | note | Acceptance Criteria - Inspections, Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
0760cb9a-3603-547e-a172-475da4047794 | note | Following information shall be provided to the NA:
f9c29129-0c92-58b9-88aa-e4e50abc740a | note | ○ Samples
69715a85-1f53-58b4-bce6-9474a7de415f | note | – Mulch
cba59ae4-2297-5b96-9cff-6b58f65b77dc | note | – Imported topsoil
53349b51-b45c-5a4b-88da-cb264c0419a0 | note | ○ Records
fc45d603-f650-50b1-bf1c-6a4bde9d6caa | note | – Details of suppliers
c1fc3d4f-ab57-549c-be3e-3dbc6aa6143c | note | – Soil tests on imported topsoil
cbb612ee-1682-5361-a43f-32cb656cef7d | note | – Copies/Photos of fertiliser labels
811e006f-5504-5297-b4e0-1f4a969ea47b | note | Method - Document Review
a81cea87-441a-53be-98c8-e2a1ca1bee32 | note | Frequency - Prior to Commencement of works
ed205ac7-3152-5297-a450-2a980a61695e | note | Category - HP
77a59919-f109-5103-b2d9-98a48cbe9fda | note | Responsibility - SE, NA
688bfc6f-d007-5446-8334-8ac4a0904d94 | note | Verifying Documents - Issue to TeamBinder
89c11da3-b622-5667-8de1-3e84988b7030 | note | Attach: Records & certificates
dd3212cd-2c8b-5307-bcf5-d9b6215a7f81 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Supply of topsoil
4a88267e-9721-5e1a-ad43-ee7b703269fe | note | Reference - Section 720.04, Table 720.042 IFC Drawings
fa1db727-28aa-5d30-a023-77588d73c986 | note | Acceptance Criteria - Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
5a7aa251-6daf-595f-8ef7-be73e29c1c8b | note | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings .
6e29501c-bef4-5ec4-b2c6-8b984385e18a | note | Method - Verify, Doc. Review if applicable
a912c828-7bd9-5e98-9b50-b28dd33a809d | note | Frequency - Prior to Commencement of works
26690a78-c213-5615-90e2-a955ac27f455 | note | Category - IP
77a5f6d4-ab13-5fda-b538-6a1a8f910a78 | note | Responsibility - SE
d4472610-b250-5422-a1af-6a71d8495b06 | note | Verifying Documents - Sign ITP, Attach material conformance docs/Test Report
7f845051-ce5f-5659-8f99-a7c3303c92e4 | date | Date Completed:
| checkpoint | 2.4 - Supply of Mulch
9ac05693-c837-5eb5-b202-1a0798e39cb0 | note | Reference - Section 720.04, Table 720.044, AS4454 IFC Drawings
83f3eb72-5c76-54d1-97d1-c5a6c4179b73 | note | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
a157d88c-a0d7-574c-b5c7-369b15d10220 | note | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings.
5ebba82c-7dac-5f1f-be03-550c1d928e98 | note | ○ Imported Wood Mulch shall comply with Table 720.044.
c7721456-228a-586d-9088-94fdcd9c5bf0 | note | Method - Verify, Doc. Review if applicable
4f279d9b-b52d-5df1-810c-72d540267476 | note | Frequency - Prior to Commencement of works
c46fa7ae-dddf-5732-89a7-48d54a3e6c14 | note | Category - IP
fe987d88-014d-52cc-ab7b-0e11cf92493a | note | Responsibility - SE
c3ae28e7-5074-5530-87f3-b4ce63a4f72d | note | Verifying Documents - Sign ITP, Attach material conformance docs (if applicable)
3318f1fd-262a-5c00-bcaf-a13ff10b5175 | date | Date Completed:
| section | 3. Site Preparation
| checkpoint | 3.1 - Subcontractor ITP
d0e38add-93a1-588c-8bdb-683415527c18 | note | Reference - Subcontractor ITP
94c6521b-b01e-5e6b-bd10-4c1ae0eeea21 | note | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
d6fd3590-c092-50c8-bab7-ebe4fc38dbf3 | note | Method - Document Review
88ac17ac-5ad9-55fb-aa77-e12be5fc8df7 | note | Frequency - Each Lot
9d56e561-4927-5c69-849a-1471b67661f5 | note | Category - WP
620282a2-2b95-5e2e-960d-e43cdc8e8fb5 | note | Responsibility - SE/PE
5dd7baf6-80e6-558f-b2ab-26098dfeec69 | note | Verifying Documents - Sign ITP, Attach completed Subcontractor ITP
3618503f-7e65-5fb7-8d70-b54467aa601b | date | Date Completed:
| checkpoint | 3.2 - Soil Additives
0d1f7a7a-e59f-539d-b695-ce63c1081ff4 | note | Reference - Section 720.07 a) AS 4419
25441378-b7e9-58c2-92e7-f29affc618cd | note | Acceptance Criteria - Refer to Subcontractor ITP
49ad1d04-440c-5d77-824d-44a7a8515d67 | note | Method - Document Review
8d950c39-9721-59d5-8a4d-deae1dd94956 | note | Frequency - Each Lot
f5baaeca-1b2f-558e-b846-8b11648e7d3d | note | Category - IP
6521d0aa-4064-5c9a-be23-3dce8d7765f9 | note | Responsibility - SE
d4791802-ad4a-5b03-965c-28455709ce38 | note | Verifying Documents - Sign ITP, Attach Test Report, Attached Delivery Docket (if applicable)
061b6c4b-e4a5-5c92-a46c-1f025ced6f2c | date | Date Completed:
| checkpoint | 3.3 - Ripping of subsoil
1e380d6d-00ae-52c4-8530-43c5708193f2 | note | Reference - Section 720.07, Table 720.071
e2496fa0-f7c7-5b1f-8322-55d65dbe7370 | note | Acceptance Criteria - Refer to Subcontractor ITP.
a2ae5503-3e5c-5afb-958c-e740b7e97d60 | note | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
38075b76-bf62-5a4a-8234-e0b0dfe94477 | note | Method - Verify
b866db05-8e57-5805-89fe-0722cf11a44d | note | Frequency - Each Applicable Lot
3f96b626-4d5b-5ebb-a06f-258b471d1f46 | note | Category - HP
c74eb6cc-f379-53fc-86aa-a12130ead851 | note | Responsibility - SE, NA
ae73d596-3790-5e04-8732-d9df6d3643b2 | note | Verifying Documents - Sign ITP, Attach Lot Map/Marked Up Area Inspected
0e3605a3-1871-57ba-bb33-73db39cd14d3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Topsoil application
97b39d42-f359-563e-a94f-803073ab5a76 | note | Reference - Section 720.07
4ab94a4a-efa7-5987-a3a9-0ed3977b62fb | note | Acceptance Criteria - Site topsoil shall be used wherever possible, in preference to imported topsoil. Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in table 720.071.
522f8df1-c4f0-53c7-8f2b-249d3e6036da | note | ○ Situation
037c82cd-0a9b-51eb-a55e-f9a29af91a25 | note | – Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
e0cf42e7-3fad-5f2c-9b33-6c464d429ba7 | note | – Planting Areas in disturbed areas steeper than 3h:1v = 100mm Minimum
e8ec3950-3c18-5dad-a3bd-69aa89d30cac | note | – Grassing in disturbed areas =75 mm, except 100 mm in swales
f11a92de-87af-583a-8794-50c399e2f0f3 | note | – Individual Tree Planting within grassed areas =150 mm in disturbed grassed areas
9ce866f1-47a6-5ab2-86af-e14a466c19e9 | note | ○ Topsoil shall be spread on planting areas and grassed areas.
935b056b-d4b8-51ad-ae27-e4835d18f808 | note | Note: Topsoil shall not be compacted.
aa2bc941-04b9-553c-aeca-93311b3a8ef5 | note | Method - Verify
4dd3c618-6c52-5a61-83b5-7e02783b2965 | note | Frequency - Each Applicable Lot
59e8b662-5e35-524d-ae6a-ce926e6a5fce | note | Category - IP
b2fba135-5338-50fa-949b-d61f1641e36a | note | Responsibility - SE/Site Supervisor
3fd70d3e-1a70-5f7a-94b4-d308015ae031 | note | Verifying Documents - Sign ITP, Attach Delivery Dockets if applicable
b24b35d3-85d5-54ec-b256-7bcd69c83760 | date | Date Completed:
| checkpoint | 3.5 - Topsoil FSL - Topsoilling and Cultivation
0305b564-0493-5ac1-8260-c71950825e1f | note | Reference - Section 720.07
51909637-6813-53e0-a5fb-3a7e277e239d | note | Acceptance Criteria - Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
d823d050-5d4a-52f2-9e3b-6e1f17bc95c1 | note | Method - Verify
ec1711c0-009b-5b80-b9cb-fd0a080e1509 | note | Frequency - Each Applicable Lot
0cf7e97b-7b8b-5c3c-baf9-2e5090fa5dea | note | Category - HP
ba5aa377-8660-5e57-a065-3039442b733e | note | Responsibility - SE, NA
65de15e6-9340-5caf-ac9a-9d9a7f23c771 | note | Verifying Documents - Sign ITP, Attach Lot Map/Marked Up Area Inspected
c6b78739-d8aa-5dd7-b634-db41c4332c3b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Mulching
08cab3a1-f837-5771-a09b-fac44a41ed5d | note | Reference - Section 720.08 a) IFC Drawings
36864b42-3a45-58ec-b0d1-18752b626520 | note | Acceptance Criteria - Refer to Subcontractor ITP
998fc86d-fc72-5619-8752-1d03fdd4fd7b | note | Method - Verify
cc0827b0-2de3-58c9-af56-df1d26d90714 | note | Frequency - Each Applicable Lot
6faf8ce6-32a6-5954-828d-769a6a3a1593 | note | Category - IP
1973d69e-d2fa-55ee-a179-ba8125d98330 | note | Responsibility - SE, Site Supervisor
66417db8-4f81-5d60-80ae-a67cbf79b98c | note | Verifying Documents - Sign ITP, Attach Delivery Dockets
b992fd88-08ec-5569-8108-4ef3ec132fe6 | date | Date Completed:
| checkpoint | 3.7 - Weed and Erosion Control Mat
38446c8b-f0b8-5781-890b-30e5056acfe5 | note | Reference - Section 720.04 i) IFC Drawings
e2c4d0bf-ef0c-59db-97cd-ad76bc70dd55 | note | Acceptance Criteria - Refer to Subcontractor ITP
38a8d530-0f94-5cf0-9d97-fdf9bb4703a9 | note | Method - Verify
1ab88cdb-b116-56ae-86e3-8c2c22afbc59 | note | Frequency - Each Applicable Lot
6554b0ee-cec3-57b5-971b-94b88f28b753 | note | Category - IP
dbf11742-a599-53ef-b2e7-79b003edf0b7 | note | Responsibility - SE, Site Supervisor
3a6967b8-5ebb-559d-ae71-576891e47899 | note | Verifying Documents - Sign ITP, Reference TeamBinder Material Approval No. if applicable, Attach Delivery Dockets
c6cce345-25ac-5f20-a292-ba0c2296700d | date | Date Completed:
| checkpoint | Final Inspection
bca61562-e23b-58e6-b167-5cead1b1e2fb | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2864af3f-0f49-5de3-8f9e-6728b092a439 | textbox | Name:
31956de5-8c94-5e9b-82db-57103e2483ad | textbox | Position:
5acfa8a9-6d39-518f-a059-4e240c81c661 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-204-CIV-CPD-Landscaping-Planting Rev 1 | itp | ITP-204-CIV-CPD-Landscaping-Planting | 9e4d7a18-6467-48a7-83ab-f99726ac1a93
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
dbddaa85-d2e8-5ae5-8fe0-240b20aff472 | note | Document Title: ITP-204-CIV-CPD-Landscaping-Planting
c11f4e7e-1110-59aa-bf7f-9ecc04bb9b44 | note | ITP Description: Landscaping - Planting
4c73aae3-955b-578a-a309-79ca03c3822a | note | Discipline (e.g. CIV/STR/RAIL): CIV
91f18bf7-f8ef-51d2-b6b9-7a95f41a30af | note | Revision Number: 0
be17aae1-07a1-5520-8573-1699cb7042ee | note | Revision Date: 2/10/2024
bcda5be2-1fde-5df9-bad0-eae5060329c8 | note | ITP created by: Jason Quan/Derek Collins
3abf5e76-5ad2-50e2-97d1-e7527a07dd99 | note | ITP approved for use by: Pradeep Talasila
ac61ed49-5671-51c5-aad3-98b78c5b8676 | note | References: IFC Drawings
bf92d7c0-9e1f-505a-b91c-b9f4665c0caf | note | ○ AS 4454
ee7c3100-2b0e-5e63-ac39-110b3e0193af | note | ○ AS 4419
ca72b278-4587-57e6-aed7-d97692aacba9 | note | ○ IFC Drawings
3c23d8e2-7941-5c60-b6ac-4934d67ad4bb | note | ○ Sub Contractor ITP
| section | 2. Preliminaries
| checkpoint | 2.1 - Check for correct documentation
b74794ec-6b23-522c-ba25-0a2606e16928 | note | Reference - Drawings and Drawing Register
acdc21d9-8f90-5cc8-bcb7-6d347c2a62eb | note | Acceptance Criteria - Ensure that all employees and subcontractors are using:
cee55482-bd22-5ef9-bbcd-abbbf10096cb | note | – The correct and complete set of drawings
b57ffa16-069a-51d5-95ff-4cdfc074198e | note | – All drawings are the latest revision
b743700a-0f19-5e46-9918-09d3eb0302e0 | note | Method - Document Review
b44efda6-c282-5d6d-910a-1b9d8adfbbf4 | note | Frequency - Prior to Commencing works
297acf46-6fb0-57bd-afcd-83b04f75d50c | note | Category - N/A
21ee88ef-5dbe-5b67-8d1a-b66792c46da4 | note | Responsibility - SE
2e7963dc-1956-542b-a7d2-d13eabe2414c | note | Verifying Documents - This ITP
b43beb51-b89b-5952-ab48-240deca70dcf | date | Date Completed:
| checkpoint | 2.2 - Submission and records
9896fe70-cc3b-5a76-899a-247caf295d5b | note | Reference - VicRoads Spec.
01c6fa2b-b17e-5742-be88-b6c8fac5a0fd | note | – Cl.720.03
89ed34e6-0cf9-56c5-b077-716634a707a9 | note | Acceptance Criteria - Inspections, Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
837decae-c640-5177-902c-1d84b40b0a6d | note | ○ Following information shall be provided to the superintendent:
f67701eb-0808-53d4-a869-c44485c2850e | note | – Inspections of plant stock for all plant species
5a6026be-3604-5c18-9965-8ae57297ba20 | note | ○ Records:
d2964491-8841-5156-b2ab-133297fa43d1 | note | – Evidence of origin of indigenous provenance plant material
52cea890-865d-56c9-bb18-9c52e05d5acc | note | – Analysis certificates for grass seed
003722ef-5915-530c-8d3a-f6f89c61419e | note | – Details of suppliers
eec71052-26ca-5060-917b-615ee1478c25 | note | – Copies/Photos of fertiliser labels
f05f769c-ed01-5f2c-9665-50981ce55f04 | note | Method - Document Review
96c17454-8e86-5cdf-a36b-f6aa92b96212 | note | Frequency - Prior to Commencing works
a49f7df9-7483-55f5-8f85-e0e38a5ca441 | note | Category - HP
4abe28fa-5d89-56ce-b88c-cf7ab24894e8 | note | Responsibility - SE,Superintendent
dae396c5-2c2a-58fd-8a1c-105126c2c0d4 | note | Verifying Documents - This ITP, Attach Records to TeamBinder Approval Form
d69363f2-b4c2-5a48-8e8f-63d13cdf3f93 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Supply of Plant Stock
f5c087ae-c1c9-5370-a986-ed6a72ce5110 | note | Reference - VicRoads Spec.
adf541b8-e902-5a22-83e5-503071de63a6 | note | – Cl.720.04
9dd1fe1c-06d3-597a-ac9a-68e429f56b28 | note | – Table 720.041
190d6a03-5b91-5228-80ea-a668b9f74a5c | note | Acceptance Criteria - All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
c578b0e6-b554-54ad-ab01-42c4235f5d79 | note | ○ Plants are to conform to the supply properties specified in Table 720.041
0c381aa4-cd37-51bc-82ad-c3afa2f2bd70 | note | Method - Verify
e1be89ff-6df9-5558-bd5a-2807d4d51352 | note | Frequency - Prior to Commencing works
2bd927ef-9de6-5677-983b-280efdfd7918 | note | Category - N/A
ce2569d9-a5b3-5f0d-9c2f-bf128222c876 | note | Responsibility - SE
33360eb4-376d-5ed8-8aa5-7b96205e4cee | note | Verifying Documents - This ITP
3bea56f9-a520-53c7-914e-834b64b48c54 | date | Date Completed:
| checkpoint | 2.4 - Supply of indigenous plant stock
c04a7ae6-7534-5e78-ad16-c0ba329b425d | note | Reference - VicRoads Spec.
c7e5804c-ca76-5ad9-b96a-e2c050823a57 | note | – Cl.720.04
2316064c-27f5-506e-9622-03adb956b2ec | note | Acceptance Criteria - A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
93277025-c75f-5418-ad36-63eef20cd3e3 | note | ○ The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
03306561-68c1-5bab-8d24-6cc688975971 | note | ○ species name
02bcb2f7-72d9-55a5-8abd-a218912ab2e1 | note | ○ storage code
787afc63-fdbb-5e38-85c4-e994b36e9ec8 | note | ○ collection locality - Latitude/longitude or AMG
5e5c0ff6-1405-5a2c-a34a-c2fe5d27252b | note | ○ approximate number of parent plants sampled
3cf841dc-1b19-5ed2-a032-0b552854a744 | note | ○ approximate number of plants in that local population
bd3fa373-64c4-5dcc-82d6-42d038b06ce6 | note | Method - Verify
5107092c-66d1-5312-8422-7b2fbdb18e6e | note | Frequency - Prior to Commencing works
0b97176e-85bb-5c3e-9c7f-eff597cc3f80 | note | Category - N/A
12d328f2-f92d-5c42-ac5f-6a0394b6230f | note | Responsibility - SE
b4808f9b-f434-50b0-8cbd-96306b351d59 | note | Verifying Documents - This ITP
293feb1e-0e12-5028-bedc-dbead08283ba | date | Date Completed:
| checkpoint | 2.5 - Supply of grass seed
108209bc-d432-5e42-9a8d-dabcc38eb107 | note | Reference - VicRoads Spec.
ddbf3995-8b72-5055-9a25-758783128bd7 | note | – Cl.720.04
794a1872-3e03-577d-aef7-57dd801d1eee | note | – Table 720.045
9af68b66-c383-56ad-b886-4b16f5b82405 | note | Acceptance Criteria - Grass seed shall comply with Table 720.045
8f7785bb-f97d-5e05-816d-18e99db65735 | note | Method - Verify
322d93d5-3c09-54aa-ba56-41520e61fe65 | note | Frequency - Prior to Commencing works
ab5cabf5-3f39-5b84-9f34-5ba6fcaf95a8 | note | Category - N/A
ce7e80c1-4d2c-5a22-9200-624c67c8b150 | note | Responsibility - SE
fe7e6ef8-e66b-55e9-a90a-542eec7d0d22 | note | Verifying Documents - This ITP
f7e70521-2730-51e8-985e-445afdf54b43 | date | Date Completed:
| checkpoint | 2.6 - Check with Landscape Architect
6b2a716a-c417-5df8-90e5-54305784f62d | note | Reference - Recommended Verification Activities LXRP
01a8db0e-159f-56e9-9f9c-287b64afa500 | note | Acceptance Criteria - All Plants to be inspected and approved by the Project Landscape Achitect/Arborist/Certified Horticulturalist prior to planting to ensure the stock quality
36617054-7d10-52c8-acba-f17cc55dba74 | note | Method - Verify
16357452-8ed5-5448-b20e-3b4708971bf0 | note | Frequency - Prior to Commencing works
5c0a40f3-f264-5757-bd56-366d406ef8ba | note | Category - WP
7ce5075f-a4b0-55d5-9107-d7e4165f3c14 | note | Responsibility - SE
78d77fe9-e59e-53b5-88e0-d2ef1cc26ba1 | note | Verifying Documents - This ITP
60ac2450-1da1-5b8e-988f-1febadbb4c5a | date | Date Completed:
| section | 3. Subcontractor ITP
| checkpoint | 3.1 - Subcontractor ITP
5bb6dfac-062d-5806-86bb-b0921b212704 | note | Reference - Subcontractor ITP
4fde9257-df82-5a49-8206-c737c1641d7c | note | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
57aaa5ef-fbed-53f9-81d6-5943043bfd3b | note | Method - Document Review
651f6d98-4956-5ec8-bf23-17befb90cb6f | note | Frequency - Each Lot
fdacd02f-801b-590a-ae3a-64274f410df6 | note | Category - WP
126defa7-b89a-5f4d-a882-244a3efa3d23 | note | Responsibility - SE/PE
7e887009-b7c1-5841-bf42-befff91cc2e1 | note | Verifying Documents - Sign ITP
aafb884e-16a8-524a-9e91-63c218102d2e | date | Date Completed:
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Planting Section Approval
823cf8c7-af8e-50ae-ac4d-d824c9911a7c | note | Reference - VicRoads Spec.
8a34518c-f7da-5704-b098-06e1273abb2d | note | – Cl.720.06
2e8e456c-4e1c-58e3-bd39-531110f4939e | note | – Landscape Plus Planting ITP
46ebd1d5-10f0-5446-b6c9-e8c61c84e1d1 | note | Acceptance Criteria - Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
9fd00689-6208-5318-a8ad-10594af3dd2f | note | Method - Verify
e15e7a25-df05-5f7a-a839-72688620b5e2 | note | Frequency - Once
be6a0bc4-7d10-5a6a-926e-af4500f112f2 | note | Category - HP
4edcff2e-1bae-599c-b87c-21217912dbb9 | note | Responsibility - SE
0c42aab2-ff84-5359-a86b-2b3003897053 | note | Verifying Documents - This ITP
ebdbd169-9f38-59b7-807a-f5b3f01bfa9e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Pest and Weed Control
95c9b183-98e4-51f9-8fc2-8ccea77ce263 | note | Reference - Cl.720.05
bfa9274e-faa7-5da5-982d-918f94a3a398 | note | Acceptance Criteria - The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
c9d8698a-eae3-59a9-93f2-bbb6f06d6a4f | note | ○ Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
90375bf2-3dd1-5be2-9411-0cbaa550bfb2 | note | Method - Verify
4252ab9e-d78f-5df1-8e65-e2422119e197 | note | Frequency - Once
2616b15b-c952-57dc-b0fe-a2d6cfdfbd01 | note | Category - HP*
196fe410-1b77-5040-9271-2d3a62d99c1d | note | Responsibility - SE
5aac82d1-4873-5983-86cd-86dac63d846d | note | Verifying Documents - This ITP
1494389c-77d2-50fc-b79d-2b35e736537f | date | Date Completed:
| checkpoint | 4.3 - Setting out planting areas
68390771-a2d8-535f-8ef1-13b701564aac | note | Reference - VicRoads Spec.
57d3a990-ea06-5ac3-8503-4157aa324003 | note | – Cl.720.06
aef95e56-8f0d-5940-b6be-b3728f44f844 | note | Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings.
084935b9-9fdf-5ee6-b582-bace09684124 | note | ○ Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
af3a2a28-167f-5c45-953e-e24125c196ab | note | ○ Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
88837507-024a-5243-9b2d-feaf468ec028 | note | Method - Verify
395d049a-3bf0-50e2-be43-93511909a60e | note | Frequency - Each Applicable Lot
ec9f5358-cea1-5fce-9ace-7f8458461a0e | note | Category - N/A
09fc96df-b232-56af-8c74-f2b7d1a14aaf | note | Responsibility - SE
3bf67216-b824-5f26-a404-80714676cf6f | note | Verifying Documents - This ITP
34fe7f79-010b-5c0a-8876-b1c101c0faa1 | date | Date Completed:
| section | 5. Construction
| checkpoint | 5.1 - Planting
a6a46c9c-30b6-5d48-a89a-b74401e24f1e | note | Reference - VicRoads Spec.
8ead4ab7-2821-5368-b54c-105742ee7099 | note | – Cl.720.09
f571b18d-50d2-5fd5-82be-c2daa19fe9fd | note | – Landscape Plus Planting ITP
12c86a04-0624-5e80-af21-9a4c54d962fa | note | Acceptance Criteria - All planting will be undertaken in accordance to Landscpe Plus Planting ITP
b37cab87-598b-5cfd-8d6c-8a009112de46 | note | Method - Verify
f121a3d6-a136-5a13-aec5-f8a7da5e61b6 | note | Frequency - Each Applicable Lot
fb2662ef-9742-5f40-93d2-604ebfb86941 | note | Category - NA
95200c3d-611b-5ade-aa81-27f9cf52102f | note | Responsibility - SE,Foreman
80656432-740b-5171-81d0-4a6206217218 | note | Verifying Documents - This ITP
97f11251-7b9e-535c-96b0-0ec4c21081ab | date | Date Completed:
| section | 6. Completion
| checkpoint | 6.1 - Site Final Inspection
908b0e21-e415-51fe-9caf-9634e9cb7582 | note | Reference - Landscape Plus Planting ITP
768797f2-435b-5aa2-9a3d-ad99ee20f5ad | note | Acceptance Criteria - Landscape Plus ITP signed and completed
bea0698d-d355-53b4-ab8e-7405ebf72217 | note | Method - Document review & Site Inspection
2396b4e0-5e42-590f-b33e-8cf5af416815 | note | Frequency - Following completion of planting works
b93bfcfb-17c5-5606-9033-13130c3888ef | note | Category - N/A
9526a218-0db5-523a-ba30-faf74331e816 | note | Responsibility - SE
f1402e43-81b8-5d47-8763-218486d1cf06 | note | Verifying Documents - Sub-Contractor ITP completed, signed and to be attached
63d4a55a-0f73-52a8-9a14-5639a1745b51 | date | Date Completed:
| checkpoint | Final Inspection
ac4e86a6-3efe-5b46-ace1-348cae0fc468 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c6231273-ddc6-51c0-9f24-60a1230598b5 | textbox | Name:
c77bcf46-2a77-5857-bfc9-0dbd72075171 | textbox | Position:
5f192e10-614a-5c56-918e-316b012f8d78 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-205-CIV-Calder-Kerb Channel (Supply and Install) Rev 0 | itp | ITP-205-CIV-Calder-Kerb Channel (Supply and Install) | 4c633ec4-f628-4580-b814-e061212ff485
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
cee802a2-fb17-5962-92bd-3e39dcf2ca92 | note | Document Title: ITP-205-CIV-Calder-Kerb and Channel (Supply and Install)
8a176b03-6fc9-50d6-8a9a-004d6bb24ec0 | note | ITP Description: Calder-Kerb and Channel (Supply and Install)
99de4260-ce89-556e-bc35-809d70dfce9c | note | Discipline (e.g. CIV/STR/RAIL): 205-CIV
c42c82b7-c12b-535e-af7a-70407993b42d | note | Revision Number: 0
b2abf5eb-7b3b-5f1b-b79d-04a278b53844 | note | Revision Date: 4/10/2024
d23e8c8b-0a2a-52d1-9f5e-bce7caae9ad9 | note | ITP created by: Jason Quan/Derek Collins
b172ea2a-ff69-5fd0-af68-f06c0f419d4b | note | ITP approved for use by: Pradeep Talasila
ee6242e4-5d4b-55de-bf10-e69bc1e6dae4 | note | 1.1 - Non Dependent
b7461362-88a5-5cb1-8759-d750aeb2f32e | note | Reference: VicRoads Section
c1a449ed-7483-550a-8d9e-6f4b4aa8ff46 | note | 703 (August 2021)
7ea518ac-b739-5a95-abd7-34991296a2dd | note | VR SD2001
200229f0-8314-5c60-9ac2-5783ac43980a | note | VR SD2102
f4227233-5d7f-59f9-afe6-198e96b62300 | note | AS 2876
4f6be038-ef21-5245-867d-33fae8642a93 | note | AS1379
| section | 2. Preliminary - Materials
| checkpoint | 2.2 - Mix design
c73e0a96-9668-5539-9bd1-69c70cd927b5 | note | Reference - SD2001, AS1379 Section 703.05, 703.06, 703.07
c1301060-8106-5bfc-b236-139bbdd71e3d | note | Acceptance Criteria - Concrete used in kerb extrusion machines will not be subject to compressive strength requirements but shall have a minimum cementitious material content in the finished concrete as follows:
3973273d-8d38-598e-a437-a59eab585069 | note | – Traffic Routes – a minimum of, or equivalent to, 320 kg/m3 of cementitious material
2e7c9226-5dc1-56c7-872a-4062c66c0c0d | note | – Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material
cb103b67-bf0d-53e1-9fd2-c59d9fc3719d | note | ○ Where Kerb and Channel is placed and compacted with internal vibration between previously placed formwork, concrete shall be:
a24fcaf7-45bc-57ea-a375-124b1542d6ac | note | – Traffic routes - N32 portland cement–based concrete
9b91a034-093d-589c-9fd7-659064532459 | note | – Local Streets - N25 portland cement-based
f856f6ad-177e-5b24-823b-b6743ec0e4c4 | note | ○ Attach: TeamBinder Material Approval Ref No.
cb5a5a04-a716-59f7-a08f-7c417d6ccada | note | Method - Verify, Document Review
0ae12920-81ca-59c7-a669-6e30dc6985c1 | note | Frequency - Prior to commencing any activity
13de5114-17c6-5bc0-b016-0fa20921f802 | note | Category - MA
a5131a3e-059c-53c4-a1ed-a597e6423751 | note | Responsibility - Nominated Authority
b4e42db3-cad8-579d-98d9-53811ae50c3c | note | Verifying Documents - Conqa HP Release
54b7cd43-0512-54a3-9730-146670b4085e | date | Date Completed:
| checkpoint | 2.3 - Bedding Material
56a5fb77-b5e4-5945-a398-538990afddba | note | Reference - Section 703.21 IFC Drawings
00a05a68-c579-5cbe-b18e-b75d33320553 | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
810c7a7a-01e2-502f-b2f8-ad7eb15d3270 | note | ○ Attach: TeamBinder Material Approval Ref No.
7437cc63-40bc-5362-99b8-222378b73fb1 | note | Method - Verify, Document Review
6a5fd3a0-8936-53f4-8579-1f12d02783d2 | note | Frequency - Prior to commencing any activity
be501c2e-f067-5452-9327-57ac9e226191 | note | Category - HP
b79b5d54-882e-56b9-868e-f46ad6a32fa0 | note | Responsibility - Nominated Authority
73e298ea-5938-5295-8493-65089cb3dd7d | note | Verifying Documents - Conqa HP Release
855406b9-d59a-59b1-987e-ab37aa62f3b9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Curing Compound
fb0e3000-8b01-5528-af06-a16ff4f449ec | note | Reference - Section 703.10
cdca5635-8785-5d2f-b06c-e91d38415b80 | note | Acceptance Criteria - Curing compound shall comply with AS3799
0f0e69fc-52f0-530d-867b-ee74341704d6 | note | ○ Attach: TeamBinder Material Approval Ref No.
085f18ea-dbda-5494-ab83-45e7ed8822b9 | note | Method - Verify
a2a1b234-195d-5f3c-bd47-12022956a275 | note | Frequency - Prior to commencing any activity
3c81dfe3-753d-509c-bc85-be9a84784bcf | note | Category - HP
3a740295-5786-5aa7-9e85-f63bb11de292 | note | Responsibility - Nominated Authority
b2b2c325-ac55-5414-9a38-c6c11b4c0e12 | note | Verifying Documents - Conqa HP Release
e8455310-ebde-547b-b813-bb49682b63a6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminary - Documentation
| checkpoint | 3.1 - Check for correct documentation
03353f58-ad66-517b-aaff-30d1112d653e | note | Reference - IFC Drawings
45e0fef4-e9b8-5d87-8db9-05c426462371 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
39ce1800-60c8-5a15-8c53-aba33d8753f2 | note | – Using the correct and complete set of drawings
1ab578cc-2ac8-519c-b62b-03274e61cdca | note | – All drawings are the latest version
02cf65b3-2247-5e9a-94e8-b2d618c36cb5 | note | Method - Visual inspection
f8fe17da-d04f-5a52-a696-40ea0a24c790 | note | Frequency - Prior to commencing any activity
889fea32-3c1b-5301-afee-4fefaa8aecbd | note | Category - HP*
a7ae271a-49c0-5cd6-a7dd-c38dbf17b276 | note | Responsibility - SE/Site Supervisor
10aea496-5774-519d-b48a-c5813dfb08e3 | note | Verifying Documents - ITP Signed
f683b963-c42a-5ea2-9c27-80d931c97c3b | date | Date Completed:
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Setting out
771bc74c-e912-5029-b65f-d40147faed23 | note | Reference - Section 703.17 IFC Drawings
bb0ddcaa-f824-5ca5-98a0-be304620ffd2 | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
5460ca81-2538-5b16-97b4-6ecdba30d55f | note | ○ The superintendent will review and confirm set out.
66aa6b12-6ff2-5d13-9728-5589836487b9 | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
89f3dff4-ef78-5e80-a446-07c450058c72 | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
8a449df1-ef98-5b85-8186-9ce63ab8cb43 | note | Method - Verify
5cb1790e-f051-5244-acb9-b057fd91b89d | note | Frequency - Prior to start
7da67c61-4d8a-5f82-abdf-b342aa40bebd | note | Category - HP
b7924f21-4e5f-5402-8531-863e653ee03c | note | Responsibility - Surveyor/Nominated Authority
95f91577-a8e8-5597-9b7b-0afd736bc5fb | note | Verifying Documents - Conqa HP Release
35d3eaeb-5b59-5c6e-86ee-00945628930d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Bedding
3ccd0f11-14fd-5804-8f43-f38f383aa03b | note | Reference - Section 703.21
1318df58-a86b-5822-841e-b87e4fb0c28e | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
f0d28a23-42fd-5dbe-b6e2-9a105397fd98 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
94f25340-0146-5630-bae5-bb5ba6d337af | note | Method - Visual inspection
3d987208-1624-5feb-8124-8476ea1add54 | note | Frequency - Each lot
02bebd62-84f5-5d27-9606-f64bc019d91d | note | Category - WP
9ccb28ba-975f-567f-a084-092ca743cc75 | note | Responsibility - SE/Site Supervisor
3041c0cc-9515-5d0e-8e2a-936e3459f0a4 | note | Verifying Documents - ITP Signed
8bb21862-bc3f-58bf-87b6-2ac7a16c57cc | date | Date Completed:
| checkpoint | 5.2 - Formwork
4c73ab93-44f7-581c-929c-757d478b76f8 | note | Reference - Section 703.12 AS3610
b247a3f2-247d-51c4-b028-23f57c450b53 | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
00229724-4848-5edc-8e7c-fec4aff9a10a | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
12a081fe-ec7a-5b01-9bf9-bed72d642489 | note | Method - Visual inspection
db94455a-d3a1-51dc-abf6-e90e52e29f55 | note | Frequency - Each lot
0c473dc2-83a1-5bf5-a157-14cfd4b18a69 | note | Category - WP
3a3d267f-6dfb-520c-9d64-a984c96da8c0 | note | Responsibility - SE/Site Supervisor
4fea8efb-093c-55a2-a34c-029c8894f6c5 | note | Verifying Documents - ITP Signed
1d348179-5f29-5771-b93e-1935fd69b4a5 | date | Date Completed:
| checkpoint | 5.3 - Pre Pour Check
13e3dd14-6a0f-52fa-96d5-67eb6f1e656d | note | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
1b56eaaa-a0be-551b-991b-af9c21aa2681 | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
4604ccc3-1842-529e-9780-b1dbf95bc4e9 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
828e4ed7-2068-5bcb-a84f-ebf113ec0c86 | note | ○ Attach: Pre-pour Inspection Record
90c80cc6-f013-57e4-b04c-25623a08eedb | note | Method - Verify
3bee09a5-8ace-586c-91ce-197b0f9b5ca8 | note | Frequency - Each lot
e08c8a2c-f665-53ea-894a-8d1223090dcb | note | Category - HP*
16c0d057-3f3b-57bb-876b-ff8c2d27186c | note | Responsibility - SE/Nominated Authority
3f75541f-5950-5531-a2f6-dc0a30dfec5d | note | Verifying Documents - ITP Signed
14eea34b-e3f2-523b-978f-07c3fe1b2fba | date | Date Completed:
| checkpoint | 5.4 - Concrete placement
e5255e92-091b-5a74-bb7e-4588be7a34c5 | note | Reference - Section 703.08, Section 703.23
bffb9ef7-0056-55c7-b98e-bc385cff2143 | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
aafac16b-4df6-5315-adf2-f2f8f5cf8c9c | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
ea541ce8-e72c-5376-894d-5448de0266a4 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
d49035d1-92d7-5f45-acdd-88fe64ab5443 | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
d9154983-1af1-50b4-877c-9361dd9a6fef | note | ○ Attach: Concrete Pour Records
50f8bbd0-22e1-53d2-8f1b-30b5010331d8 | note | Method - Site inspection
7ab3dad5-56c0-55ff-a2dc-feff8985a069 | note | Frequency - Each lot
1d548748-c940-5bdb-9933-79bd58e6ed72 | note | Category - IP
b2f260bb-d03c-5dce-b0b1-20c166397e89 | note | Responsibility - SE
e52ad815-7efb-5f82-b055-37a0af534675 | note | Verifying Documents - ITP Signed
f9236df8-4100-566f-b219-71dc541de195 | date | Date Completed:
| checkpoint | 5.5 - Transitions
04590e58-2fdc-5da0-88b7-72e916baf3de | note | Reference - Section 703.24
5da4a069-bb59-5eb9-824e-27053c9cb08b | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
c4caf57e-7991-58d0-bc13-5a53cb129071 | note | Method - Site inspection
785f4459-5698-5e9d-bdce-fbf84c7d1b87 | note | Frequency - Each lot
806f28f2-0da8-5f27-9329-3956b7d4e13a | note | Category - IP
eecf5227-63ea-591b-807c-2c962ab1ade3 | note | Responsibility - SE
4b2241f7-f353-53d8-ae97-04dde9793e10 | note | Verifying Documents - ITP Signed
ad90d335-5713-558e-ad15-fb2d5fe06262 | date | Date Completed:
| checkpoint | 5.6 - Surface Finish
d9526129-de30-5ecb-ab00-a0c9de4822a6 | note | Reference - Section 703.25
29e3fad9-6364-5694-9ecd-21220338667e | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
15f1eb30-5255-54db-b50c-4df313b76eb2 | note | ○ Renderings shall be applied within 30 minutes of extrusion.
68b89ed8-d469-5ccd-9f51-5f6b2d8b2893 | note | ○ Concrete to have a neat appearance and uniform colour.
a4665a7c-d17e-54f1-83c6-54f80f155487 | note | ○ Class 3 finish required for external surfaces.
38b80ae7-0081-5c40-9033-0edd93280810 | note | ○ Class 4 finish required for permanently hidden surfaces.
84b1d833-7abf-5639-bfa2-5c93787c39df | note | Method - Visual inspection
dd684ea2-e602-5f9f-aa0f-fbe04826ec36 | note | Frequency - Each lot
9e2c3de3-66bd-5f98-924b-72aa36f7c117 | note | Category - IP
4a17b592-f50f-5468-b3dd-c242c020402d | note | Responsibility - SE/ Site Supervisor
4c5c42bc-8239-54d0-92d0-1de9558388d5 | note | Verifying Documents - ITP Signed
31f4dccc-cb90-5cb8-b200-f629a2ff06d7 | date | Date Completed:
| checkpoint | 5.7 - Formwork Stripping
043a386b-c162-5086-a141-3825c3368b8d | note | Reference - Section 703.12 AS3610
8f2c8b10-5f3f-5920-b486-1e534f0f18db | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
9cc301ad-398d-578e-a454-ed030024f11a | note | – External faces 2 days
ad5a5b53-dd6c-58b4-a727-8ef6abf2d361 | note | – Permanently hidden faces 1 day
419e0d36-96ec-525a-9d9c-34a790670042 | note | Method - Visual inspection
85bd68ca-3d63-5dec-85ea-c9df51b4d5f0 | note | Frequency - Each lot
5bf787ec-7499-5cfe-9acb-cff310c8dd2a | note | Category - HP*
81ebee85-7ad2-5a4b-85c1-551e7f1abf13 | note | Responsibility - SE/ Site Supervisor
1c94510e-a663-5f2b-85ba-c148014e892c | note | Verifying Documents - ITP Signed
7164ba00-1e1c-59cb-8b14-a507528cf0ef | date | Date Completed:
| checkpoint | 5.8 - Tolerance
abb34e64-d391-5471-ac87-ba5e1df3c4f7 | note | Reference - Section 703.15
297d195d-d2f5-515b-ae17-fe6d5d8e28dd | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
d0cef90d-7375-5fc6-949e-819346ce57b0 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
76d65967-ed94-5a7a-a9a3-0faa5f47429d | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
bb813876-bbca-5d90-8afe-62423aa1637b | note | ○ Attach: Post-pour Inspection Records
f363d92c-695b-5261-8d24-3d12a8271241 | note | Method - Verify
1a8a6f40-d669-5255-896d-b4d01bd8e0c2 | note | Frequency - Each lot
bc01aa61-8418-5453-91f9-32105e1c0e4e | note | Category - IP
e7d311dd-1921-564f-9ba6-4b1739c289ea | note | Responsibility - SE/Surveyor
a0646cbe-66d6-52c9-a8b1-3992e4c315bc | note | Verifying Documents - ITP Signed
120631f5-be1c-5c80-a0f8-8495f536bba0 | date | Date Completed:
| checkpoint | 5.9 - Curing
1f5adb69-4fd5-53d2-b491-6dd342a62edf | note | Reference - Section 703.10
961dfd4c-204b-5776-834a-ce1794673466 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
78946f07-6141-5832-8dfd-5b682cc46327 | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
1dce6e4a-3244-584a-8126-dffef098a6ea | note | Method - Visual inspection
9f3bb4b7-9fb5-5e9d-a07c-cf17b8b5773d | note | Frequency - Each lot
9fffc379-8327-54a0-898c-033e312d2adf | note | Category - IP
da305e90-34d1-55b8-bc1e-afcd086a50ef | note | Responsibility - SE/Site Supervisor
bd448348-7169-536f-902c-f4ed7a88a22e | note | Verifying Documents - ITP Signed
069327ec-cd4c-5c22-b586-dadc8de8f1cf | date | Date Completed:
| checkpoint | Include testing requirements for portland cement where requied
4d0263c8-fd7d-58a3-b50b-6af518176655 | note | Reference - Vic Roads 703.11
| checkpoint | 5.10 - Joints
833d9eef-5de4-59f6-bbe1-0488ffa59cb1 | note | Reference - Section 703.26
980acbb1-fc2b-5a47-98f4-2517e8b12907 | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
2d1ad44f-5315-56ba-b1d4-a1238cbb2a3b | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
9d456481-2f8f-5714-9f4e-d23047af9564 | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
761fe25f-c335-5476-893b-0b4d2bac08f9 | note | Method - Verify
86769484-263f-50fe-9d98-096729afd923 | note | Frequency - Each joint
ae2f63d1-0380-523f-a21c-6a0fe4323d97 | note | Category - IP
e67edcb2-232d-50b0-a91c-6d89ccfe8c9e | note | Responsibility - SE / Site Supervisor
191e47f7-7052-53a9-a443-02c2011f90e4 | note | Verifying Documents - ITP Signed
409820a8-f558-5aef-aeed-03cd21ac9105 | date | Date Completed:
| checkpoint | 5.11 - Protection of Concrete
4f0c9310-b690-550f-8cda-afa8cf9042f3 | note | Reference - Section 703.27
469e9434-fb0d-5f10-b546-0f2d1fa001a9 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
41071b18-7ba1-5ed7-abe6-9d6f0996b7d4 | note | Method - Visual inspection
f101f2a8-2ae4-5df3-80f5-aee3ade8e538 | note | Frequency - Each lot
25472611-3862-597d-b6fc-be32fb25d892 | note | Category - IP
87edf41f-cf1f-5140-983b-b156f6a0c571 | note | Responsibility - SE
2cfa26b2-7f73-5525-8c5a-18af0af10166 | note | Verifying Documents - ITP Signed
2ebd91d3-bc7b-5bbc-8ad0-7f2a8420102e | date | Date Completed:
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Backfilling
40ec9fb8-6804-5624-b4c5-9f184945f64c | note | Reference - Section 703.29
023f7440-3f48-5e13-a9e6-6ce7f6bdf054 | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
aa5eb475-4180-5319-baf7-ad33a72df6f7 | note | Method - Verify
b4a0126d-61aa-52aa-b11f-dd1c6fb3fb63 | note | Frequency - Each lot
ce0c4056-e7d9-5394-8c99-90f097f7e70e | note | Category - IP
cf617f16-06a1-5f5b-8341-20ae22c1c1db | note | Responsibility - SE
c09716cd-5f62-5fc5-a9ce-2522c1c00aae | note | Verifying Documents - ITP Signed
4ccbed5d-33c9-5a00-a75e-4d97a8fab2a8 | date | Date Completed:
| checkpoint | Marking of conduit locations
95a2d42d-6b89-5e46-998b-aa71ed46cdbd | note | Reference - 703.28
| checkpoint | 6.2 - Cracking of Concrete
bb203c35-7d60-5aa1-8d73-06d485ae2ce8 | note | Reference - Section 703.30
8a77247f-3f12-53c2-94ec-89165893a2e5 | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
299001bd-3fe3-5047-b51a-f039dbeccd3b | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
25fbcb63-b655-5cdd-8550-14484ec28616 | note | ○ Attach: Post-pour Inspection Record
a23fa726-7bdd-5943-b5a5-f1401c509f9b | note | Method - Visual inspection
ec9d1d3a-414f-59f9-93f5-217111728585 | note | Frequency - Each lot
665dc733-dcc0-5928-ae4a-264add6ed6f8 | note | Category - IP
cc865403-7a5f-56c5-a3a3-19aa4342efd1 | note | Responsibility - SE
c596002e-5f7d-54b8-8de3-abdeb07df3ff | note | Verifying Documents - ITP Signed
22f7cd26-08dc-5f9c-90bf-f702a465b2fd | date | Date Completed:
| checkpoint | 6.3 - Survey Conformance
89e785cc-ec8f-5b8f-9a3c-982bacb992a4 | note | Reference - Section 703.15
e7d78238-72a6-526e-9581-0f128b337d70 | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
0e9ba684-a813-5eef-9348-27263cfa50a9 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
47654baa-bfe9-525f-8aa9-036d3c0d2a64 | note | Method - Document Review
7bb7d9a4-f07f-533e-967b-e880a06183c5 | note | Frequency - Completion of each lot
cf0d9ba3-46ac-5264-986a-e07db83ddaba | note | Category - WP
a7ca31fe-77a8-563a-b9df-c9fdf2add194 | note | Responsibility - Project Engineer/ Surveyor
51c270b7-50bb-517e-abc2-e3496f186390 | note | Verifying Documents - As-built survey records
69795c0f-b2a2-5888-81c2-473abb0294ca | date | Date Completed:
| checkpoint | 6.4 - Non Conformance Report
a2ca4cbf-1405-5d02-9ea5-21f81f10c580 | note | Reference - MRPA Quality Management Plan
8c2cdd91-9a9f-5ec2-be32-3bce7d6f4597 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
fd3a52a3-b16c-5813-85a5-c5d3fc802d71 | note | Method - Document Review
fb627cce-757e-58a3-adcf-4a0e4842ec5e | note | Frequency - Once, prior to closure of this lot / element / Work area
c493fe83-a7d3-57a3-9234-c32797c8cbb2 | note | Category - HP*
2ea468a3-360c-5187-a9dd-6e1bf879ebaf | note | Responsibility - SE/PE/SPE
91a95f98-52f7-5f63-9c05-654878cfac44 | note | Verifying Documents - This ITP
25f5654a-028c-5c24-9574-e8304b8a14a1 | date | Date Completed:
| checkpoint | Final Inspection
57d1b2c8-d4b2-5656-b06c-30a3259d8232 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9617e0e3-fea5-595f-af76-5c47539bc5a7 | textbox | Name:
b0a084f7-2464-5c66-b454-031b51673fbd | textbox | Position:
183f0324-725c-5d6f-9575-291e42e57190 | textbox | Date Completed:
| signoff | Sign ITP
740110df-c98b-4968-adbf-c06c3a1ae4d4 | checklist | ITP-206-CIV-Calder-Street Lighting (Supply and Install) Rev 0 | itp | ITP-206-CIV-Calder-Street Lighting (Supply and Install) | 75b66bf6-a375-44b3-b2b7-078eda127f56
a8279d03-cfe0-48bc-b311-469455179c56 | section | 1. Referenced Documentation
87da1c6c-495b-46c9-ae8f-4cae1c207062 | checkpoint-no-value | Referenced Documentation
dec26291-7bf9-5ad6-a1f2-65f2b3cfb0e3 | note | Document Title: ITP-206-CIV-Calder-Street Lighting (Supply and Install)
b2f468dc-edeb-5334-8cbb-f733dff688b7 | note | ITP Description: Street Lighting (Supply and Install)
47274fbb-a0b4-583a-ba32-15748efa89ef | note | Discipline (e.g. CIV/STR/RAIL): CIV
c03e28a8-1e7e-5d0c-8f3a-b92ae7837ba2 | note | Revision Number: 0
58c94039-634a-5e1b-8312-a0ba0f190477 | note | Revision Date: 8/10/2024
2469b906-d223-527b-8f90-1e7a408c499e | note | ITP created by: Jason Quan/Derek Collins
45e46f68-4e7b-55c6-b9f7-908d016e0618 | note | ITP approved for use by: Pradeep Talasila
0929ade7-ed5a-53a9-81bd-5f34a65a7837 | note | 1.1 - Non Dependent
8bf856e6-ad91-58b8-ba0f-58735ef614ee | note | Reference - IFC Drawings
3dda0474-0afc-584f-86e6-5c62867cc1be | note | 1.2 - Non Dependent
3731d062-6d1d-5fff-98a8-d0e327a66597 | note | Reference - Jemena Electricity Networks
0909e222-1a9a-5534-a2af-0207dae2248f | note | 1.3 - Non Dependent
a67b5be7-fcd7-5171-ac7c-694daa829794 | note | Reference - VR Section 733
fe9baa81-ea48-5b16-a38c-ab7b6f62b603 | note | 1.4 - Non Dependent
e7dcf410-9c6c-58c9-adec-859c36053d63 | note | Reference - AS/NZS 3000
16b03ffb-1100-5db2-a3b7-2ac36994f973 | note | 1.5 - Non Dependent
e0495da4-2c94-526e-872c-3d03ff334afb | note | Reference - AS/NZS 1158.3.1
27ff1c0a-4eb0-4089-95e7-340a7be483b7 | section | 2. Preliminaries Preliminaries - Materials
e9305a16-7a62-49b1-8f5a-e675402734ba | checkpoint | 2.1 - Material Compliance - Obtain and review manufacturer documentations for the supply of materials.
e4afc56c-4db8-59b5-aaba-d6fa29fc8943 | note | Reference - IFC Drawings Section 733
7ffa172d-5e80-5bc1-ac82-952cd0e7a2af | note | Acceptance Criteria - Materials comply with IFC Drawings,VESI Standards.
2b2c86d2-8b68-5c8e-ae24-50e3c723c180 | note | ○ All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
20a62153-7932-5cab-8224-e52fd921d72f | note | * Enter: Teambinder Hold Point Release Number
81a69a78-8b6b-5358-bc51-62e645b535a9 | note | Method - Document Review
9590cbe1-eb0e-51e9-ac03-39982ff88816 | note | Frequency - Per Source
303b017f-0968-572f-a570-42babb0b57eb | note | Category - HP
59bf9b8d-a3de-5671-9be6-895e5a0b55da | note | Responsibility - Nominated Authority
7a804103-2b0f-5348-81d4-40bf53afc16f | note | Verifying Documents - ConQA HP Release
2e3c4541-e1c5-54d4-a838-e5f7e0de41b5 | date | Date Completed:
14fe2583-7d43-4e5f-b68f-f3caedf49b24 | signoff | AUTHORITY HOLDPOINT
dcea240e-be7f-4d88-8446-5180ab3e2853 | checkpoint | 2.2 - Inspection of supplied items upon delivery.
ac169164-f35a-58df-b51c-4bbfaae852f0 | note | Reference - IFC Drawings VR Std Dwg TC1064, TC1065
7552249f-8ddc-5033-9eec-2bee403ae12f | note | Acceptance Criteria - Supplied items are to correct spec, class, size, undamaged and brand new.
8f1b6007-5c6a-504f-913a-e2acfc6af442 | note | ○ Luminaires: At the time of delivery, the supplier shall provide hard copies of the following:
2769ce19-32d4-5ddd-9c71-665a66ddbf39 | note | — Installation Instruction Manual
d5ac3b42-0f40-52b3-b655-18fb1fcc5eb1 | note | — Operation Instruction Manual
1abab8d2-d4d7-5a23-86f9-537cfb3208db | note | — Storage, handling, loading and off–loading instructions
a9b35538-5ab2-5336-a79b-83afe6aabd17 | note | — Test Certificates
5b2150ed-ea48-5437-98b2-cb4455219bfd | note | — Warranty Information
893e1f9a-b756-588a-aa09-47589be97710 | note | ○ Attach Delivery Dockets & Records Required
98592730-2c62-5d87-b078-2983953f49ba | note | Method - Visual /Site Inspection & Document Review
3abef352-3397-5541-80ea-0b277a086f45 | note | Frequency - Per Delivery
3422c610-7fc4-57e7-84b1-84feeb77e1a5 | note | Category - IP
95ee7e8b-64ea-5afb-b47f-e5e89515a590 | note | Responsibility - SE/PE/SPE
314b4876-38f5-586f-a9ae-2a84a744e583 | note | Verifying Documents - This ITP Signed Off
f0639e24-bd8a-54e4-a8a0-0240056f4b91 | date | Date Completed:
1a0a9e2f-955d-4b66-984b-26832683c854 | section | 3. Preliminaries - Procedures & Documentation
c8465d32-c8c9-412c-91d8-ee1998c45f36 | checkpoint | 3.1 - ACCC Form (Australian Competition and Consumer Commission)
30879aea-e0e4-5b28-8c7a-bd6294a35ebe | note | Reference - MRPA Quality Management Plan, Jemena Electricity Networks
6ad435b5-5c96-531b-b2d6-bc29bcaa7b67 | note | Acceptance Criteria - Before any works commence, the accredited contractor shall obtain an "ACCC Form" from AusNet Services representative for permission to commence works.
ae858d61-c970-5b47-ae20-f1814b1d2b9e | textbox | * Enter: Teambinder Hold Point Release Number
ad78c23f-a115-516a-afe7-869d2131cf3f | note | Method - Document Review
8018e120-a676-5383-a94d-f5c6192557aa | note | Frequency - Once prior to works commencing
46e0b762-ac47-5f4e-b65c-954f8e000c44 | note | Category - HP
48bd4ec4-17c9-587c-a12f-cf6cd377acbc | note | Responsibility - Nominated Authority
a02826e7-d2f3-5e4b-bb09-feac3995530d | note | Verifying Documents - ConQA HP Release
584381b6-32e9-5e25-9592-7bd021e58b06 | date | Date Completed:
70c5d38f-9a3c-40cf-9dd3-2fee28cfe1ea | signoff | AUTHORITY HOLDPOINT
0935bdeb-5808-4805-8657-875f55ee1640 | checkpoint | 3.2 - Subcontractor Prequalificaiton
9836a9af-5122-5383-b3f1-225a07f0c0bc | note | Reference - MRPA Quality Management Plan, Jemena Electricity Networks
dbc318a8-3301-5916-980a-07de209f0199 | note | Acceptance Criteria - Subcontractor to be a VEDN (Victorian Electrical Distribution Networks) accredited contractor.
2c7b17ef-9094-508a-bf89-8301bfe81dc1 | textbox | * Enter: Teambinder Hold Point Release Number
78dc9443-6365-5280-b099-531351ea97be | note | Method - Document Review
3ab45f3f-73f7-579a-ba90-ac0072ca5a86 | note | Frequency - Once prior to works commencing
77cce1dc-9f2f-5010-8720-d88b2df9d250 | note | Category - HP
0ba40564-999d-5665-9f1e-3344fa0abe25 | note | Responsibility - Nominated Authority
3eecf81b-ed8c-5cf4-a025-413292fce24d | note | Verifying Documents - ConQA HP Release
9915c9e9-3382-5314-8499-aec747129244 | date | Date Completed:
11a41509-b633-40d6-b2be-4680aa965c62 | signoff | AUTHORITY HOLDPOINT
450aa986-4c49-4119-8c8a-256054de8576 | checkpoint | 3.3 - VESI (Victorian Electricity Supply Industry) Auditor
9919ca9a-63ee-599e-b896-5e8abd572a8c | note | Reference - MRPA Quality Management Plan, Jemena Electricity Networks
a2183ed3-b6cb-5116-931f-dace087a3423 | note | Acceptance Criteria - VEDN approved civil auditor. (VESI Auditor Register)
e8371d9e-f613-5258-b756-f69afb70c96f | textbox | * Enter: Teambinder Hold Point Release Number
6ba0fd1c-7216-5960-84f4-75ae6b054487 | note | Method - Document Review
c397b06e-4081-5d96-ba99-a520d7a99cc1 | note | Frequency - Once prior to works commencing
43eebd12-96cc-5550-997c-26c6c8b6b246 | note | Category - HP
f0063695-1cb8-5bec-b162-9abf63b51f06 | note | Responsibility - Nominated Authority
c05de636-aa06-5676-ad85-81a51be8b3ea | note | Verifying Documents - ConQA HP Release
36d7b4f1-021a-5b1e-9388-c5760c005427 | date | Date Completed:
dc9bee4d-4d66-4ce4-8ae9-4cee31679c8d | signoff | AUTHORITY HOLDPOINT
9e88a004-5469-4804-b2ef-dfdf629e2eb4 | section | 4. Pre-installation Activities
87860208-f645-4488-a724-2caa140b3cbc | checkpoint | 4.1 - IFC Drawings
17b8b404-67bc-53f9-9183-e7f992c907c5 | note | Reference - MRPA Quality Management Plan
f4aff7b3-3c9a-5e70-ac18-aa2bd5eddf35 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
4854e8c5-43d2-5279-8ebd-48a31ac7e435 | note | Method - Document Review
9374e65f-47f8-5a96-882a-ad7b5c84a017 | note | Frequency - Prior to starting Works and at regular intervals
830d4869-b804-53d4-97fb-8742c86d043d | note | Category - HP*
8c4c0938-fb9c-5e83-b500-2f6276fc9905 | note | Responsibility - SE/PE/SPE
4aec0a07-dc40-520f-b07a-6f7d2743e1d6 | note | Verifying Documents - This ITP Signed Off
80a4fdc3-0dff-5b84-b130-7f8760c6cad2 | date | Date Completed:
24cf64f0-363e-4e70-9188-7fb98dcc6b04 | checkpoint | 4.2 - Survey set out
102d15c2-e39f-5ee1-832c-fcb65e2c7e79 | note | Reference - IFC Drawings, Jemena Electricity Networks, Technical Specifications
bc241341-747c-5729-b6d2-3dd5919fdeb3 | note | Acceptance Criteria - Set-out survey carried out by a surveyor and within the tolerances as per IFC Drawings and AusNet drawings/specs.
dde91969-b204-5961-861d-7896e86f3bb1 | note | Method - Visual, Survey
e200adf9-e42f-5df8-a25c-6c47fa4fc7ff | note | Frequency - Each Element
f51e3f98-0fa2-57fd-a89a-7513c77ab8c8 | note | Category - IP
5c643db1-62a7-5ae4-86ed-53200f07a1db | note | Responsibility - SE/PE/SPE
f48a341c-5f35-574f-91a2-00f1da8d5cfd | note | Verifying Documents - This ITP Signed Off
82c44e70-9af0-57c2-a10f-55a38dbfd912 | date | Date Completed:
35a3086c-fbfa-49f1-9e1b-7b20a4bc777c | section | 5. Installation Activities
21cff384-0bc5-4214-b62f-7dc213af18fe | checkpoint | 5.1 - Pit and Conduit Installation
ab75a49f-7614-5678-b7f8-c9bc565e7c73 | note | Reference - IFC Drawings
3961c45c-516d-5c89-b371-4d73c07ba120 | note | Acceptance Criteria - Conduits and pits to be installed as per IFC Drawings
001ebe81-fcb0-5974-ac00-79a638822d42 | note | ○ Attach: Subcontractor Installation Checklist
2702b453-0ba4-59ba-9f1b-78e0be8dc993 | note | Method - Document Review, Visual
0556f6fa-005a-5486-a6c9-dd32af0e0f61 | note | Frequency - Prior to commencement
8c378da1-0b57-5214-b1c0-a5b293a1ad1b | note | Category - WP
ba1bbe90-c097-53c0-ae79-16eeaf4dfbdf | note | Responsibility - SE/PE
0346c385-a10e-5165-bf11-dcfc52f33e97 | note | Verifying Documents - This ITP Signed Off
eb409bc5-c6e4-5093-b312-d631fcadf20f | date | Date Completed:
8a051522-aeb9-4b3a-b03f-2995778820be | checkpoint | 5.2 - Conduit and Cable Detailing
0f4a2607-4126-5ffa-940a-0f3374f587aa | note | Reference - Jemena Electricity Networks Technical Specification
91de926b-8fb8-5cd2-bd41-058ddb7e7d62 | note | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer.
bf20b215-148d-582b-8321-1ba5c3609e86 | note | ○ Attach: Verification Document (As-Builts)
862bf422-7a16-592d-8b78-89d30d2dc0af | note | Method - Site Inspection
a09c8f0c-6f95-55a6-8780-0b0f0007a143 | note | Frequency - Upon completion of each section
1cfe32e1-a6ae-548b-86ec-27e208f14ea1 | note | Category - IP
5f49fbbc-f9ab-5cf7-ac9d-e6a31d622164 | note | Responsibility - SE/PE/SPE, Services Engineer
e6b46ee7-ac29-5349-b0f4-e3335e7747a9 | note | Verifying Documents - This ITP Signed Off
dc1ff3f1-fdb5-53e0-b2e8-331e8135154e | date | Date Completed:
86f8d7dc-3904-4ae5-ade7-985818366dbc | checkpoint | 5.3 - Prepare the plinth foundation (Excavation & levels)
b5622374-5f9c-531b-a94b-f21662cf6d44 | note | Reference - IFC Drawings
4003fb92-b9d7-5b89-9354-aef6d49c73b3 | note | Acceptance Criteria - Check levels conform to relevant drawing depending on type of pole to be installed.
db91e07d-c4bc-5744-a93f-22b4d4b45853 | note | Method - Visual, Survey
40058b30-32d3-54ce-bdfb-7f076c9ca7e7 | note | Frequency - Per Lot
5f911ae7-c828-5fa9-a59d-54e599368528 | note | Category - IP
27d0e170-0790-535e-bfc8-7bb507690810 | note | Responsibility - SE/PE/SPE
6da1a452-bc60-574b-b21e-a456d3ba20bc | note | Verifying Documents - This ITP Signed Off
fa5522b0-d7af-58f9-bb75-d24be840ebb8 | date | Date Completed:
98d9dba9-229a-4814-89f6-c37bdfa690c2 | checkpoint | 5.4 - Installation of Light poles
fed39075-8aa5-5dcb-87c2-436ab309771c | note | Reference - IFC Drawings
346b1633-5452-5d6b-bf24-4e9f9f8e7dda | note | Acceptance Criteria - Light Poles to be installed as per IFC drawings in accordance with VESI requirements.
8ce0b9a6-a278-5209-b64c-d02b74bea8b0 | note | Method - Visual /Site Inspection & Document Review
20c2010d-67a0-5a28-9c00-7007a2744fa7 | note | Frequency - Per Lot
241e9528-40bd-50a4-a812-b7232500bcdb | note | Category - IP
8d5f15ff-dc8d-56d9-8406-187894fa6985 | note | Responsibility - SE/PE/SPE
be36ed53-ac76-5adf-a983-25e4c0198c10 | note | Verifying Documents - This ITP Signed Off
99e9ac65-1877-58a6-9876-62724230a39c | date | Date Completed:
f43a45c7-a0ff-460d-8aa6-b6e05bf0bc8b | checkpoint | 5.5 - Asset Labelling
828ba87a-23bc-5eba-ac0b-82970bf6b24e | note | Reference - IFC Drawings
5ae9f064-a1fd-5874-a52e-355877775d40 | note | Acceptance Criteria - Pole Labelling to be as per IFC Drawings.
a6dd40ea-d7a9-5267-9c80-5229f9a074b5 | note | Method - Visual Inspection
39de4e97-10fc-532b-acbe-1ff13db45c28 | note | Frequency - Per Lot
aa5220f8-fa36-57af-9960-e78a886b99cf | note | Category - IP
52a4219f-5b76-546b-9144-8a6abe75ee46 | note | Responsibility - SE/PE/SPE
6179e3ba-8856-5e80-9df5-2583a29f03b2 | note | Verifying Documents - This ITP Signed Off
ba350c60-62a7-5464-b7d1-edbd87cfb6e4 | date | Date Completed:
2fa60ee2-28ae-44ce-8680-b839b14d692b | checkpoint | 5.6 - Commissioning & Testing (Civil Audit)
3658ca8c-5808-5bb6-ac43-0e0309759ee4 | note | Reference - Jemena Electricity Networks Technical Specification
c3a0dd8d-b90f-5b4a-8d02-d079102ed10e | note | Acceptance Criteria - Upon completion of all trenching and conduit install, a Civil audit by a VEDN approved Civil auditor will be completed and approved before procceding.
c92f022a-e217-5a8f-844c-26b314e0953d | note | Method - Commissioning & testing
28fefa7c-18b2-56ae-bd3a-1430717a199a | note | Frequency - Upon completion of each section
a05579b9-f05f-5a77-8fbd-600b79a9831e | note | Category - IP
d34e93a8-25d4-54cd-bda2-cc156a91b4c9 | note | Responsibility - SE/PE/SPE, Services Engineer
2f4ab1d1-fd05-57d7-bb15-a0938ecc8f7a | note | Verifying Documents - This ITP Signed Off
330475ee-d11b-57bb-bc07-7ed8af75130e | date | Date Completed:
5a668b86-9ce8-4741-9db1-4a8e09c96746 | checkpoint | 5.7 - Commissioning & Testing (Trench Inspection)
902b2964-0335-56e1-854a-72915151487e | note | Reference - Jemena Electricity Networks Technical Specification
d9bc0c23-5cb7-5a01-8c47-05bc6b8e9bdb | note | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer
8f872fbd-a714-5510-916d-4cc87d4872f7 | note | ○ Verification document: As-Builts
d4c28bec-205d-507a-b6da-7852088e6146 | note | Method - Commissioning & testing
231ed620-0f14-5874-b5ba-f869d6a5259c | note | Frequency - Upon completion of each section
6f0ac597-26e0-5851-9306-a34281b96b97 | note | Category - IP
ec9ddf95-cc71-5e33-947a-9c66dec2df94 | note | Responsibility - SE/PE/SPE, Services Engineer
753a98db-6e22-5e7a-b809-0f2395194f94 | note | Verifying Documents - This ITP Signed Off
d763ff0a-7e1b-5d38-85ef-5f6bf12f0f53 | date | Date Completed:
249ad669-4064-40fe-b3cf-41d839015e6a | checkpoint | 5.8 - Commissioning & Testing (Pre-commissioning)
e372941f-2d8b-53a1-8606-6d685cfb117d | note | Reference - Jemena Electricity Networks Technical Specification
2157e1f0-7ca7-50f5-9d61-ed4c47ecb0bc | note | Acceptance Criteria - Passing of the pre-commissioning audit with all non-conformances rectified.
67e5e1a1-ee66-53b8-928f-41a6657768e1 | note | Method - Commissioning & testing
c6c96720-80f0-5653-bc66-1d8e2587109e | note | Frequency - Upon completion of each section
54101ae9-89b8-5504-b344-da9d93414857 | note | Category - IP
c3bdaf04-94d8-5a1d-b99c-973939fbe884 | note | Responsibility - SE/PE/SPE, Services Engineer
f346cf81-ffcf-5259-829b-2c1cd6a713de | note | Verifying Documents - This ITP Signed Off
e3136470-e2cb-585b-b449-0eeeba6aa834 | date | Date Completed:
c2d2927f-8522-4b51-ae6f-8e5224232b85 | checkpoint | 5.9 - Commissioning & Testing (Final Audit)
2c8769aa-cd0f-5713-8081-d6d6a17f53dd | note | Reference - Jemena Electricity Networks Technical Specification
721d7571-2432-59c0-8799-7eb587c2dbaa | note | Acceptance Criteria - Passing of the final audit will be completed by Jemena Electricity Networks to inspect the completed works with all non-conformances rectified.
efa74651-f918-5152-8c74-8ab70115dd14 | note | Method - Commissioning & testing
7f665246-8af9-566f-a29e-99c0b8e39f37 | note | Frequency - Upon completion of each section
34309d6c-edd3-5b02-b6eb-e8f5986fa957 | note | Category - IP
7b5b2de9-ae40-52e8-a59d-b80ded9e4090 | note | Responsibility - SE/PE/SPE, Services Engineer
0708774f-1457-5845-b450-88a9e1cf06dc | note | Verifying Documents - This ITP Signed Off
b0a5e343-52f1-518d-9408-681215d252a1 | date | Date Completed:
9658930e-27c2-4631-a25b-06f5e794d496 | checkpoint | 5.10 - Testing and Certificate of Electrical Safety
c9af757e-3aee-51dc-ad68-dcb56a8941f8 | note | Reference - Jemena Electricity Networks Technical Specification, IFC Drawings
372ab464-3e43-5998-a801-ef864463695f | note | Acceptance Criteria - Prior to final acceptance, the contractor shall test all distribution cabinets, circuits, switches, PE Cells, luminaires, and all other electrical and electronic components for correct installation and operation
7106eae0-b79b-51a4-906d-76612f94b95e | note | ○ Attach Documentation: Certificate of Electrical Safety for electrical installation
a908d8cb-9c21-57c1-8a87-1cb027788447 | note | Method - Document Review
dffcefe8-aac3-513b-a2b6-461cf340da3d | note | Frequency - Upon completion/ Work area
6deb5afd-6454-5e87-a0e6-9741841ce211 | note | Category - IP
c6719613-0fd6-508f-9a57-9cd0a7d2dcc5 | note | Responsibility - SE/PE/SPE, Services Engineer
9bbe5847-01cd-590b-9233-539a2a1ff597 | note | Verifying Documents - This ITP Signed Off
97d62fd0-c997-5fb5-9452-456e5096ad28 | date | Date Completed:
9b00b7da-968e-4a27-8ded-4d1cf001cedf | checkpoint | 5.11 - PC Cert of Jemena Electricity Networks Agreement
34f0045b-7dbc-5fea-8dec-c862ccb6097a | note | Reference - Jemena Electricity Networks Technical Specification, IFC Drawings
da5511b8-ad65-5ead-b207-ef9e4474f047 | note | Acceptance Criteria - To be accepted and signed-off by MRPA and Jemena Electricity Neworks
500b6b42-0573-5d4a-89ff-02709a40a3fa | note | Method - Document Review
f1d8f272-275b-5739-9097-802dba72d567 | note | Frequency - Upon completion/ Work area
d06978c8-c35c-57b8-8c4a-3391f7808b06 | note | Category - IP
41bf4a01-7145-5ad5-ad56-61d3d58f628b | note | Responsibility - SE/PE/SPE, Services Engineer
fab5f760-5440-57aa-b75f-49345472e415 | note | Verifying Documents - This ITP Signed Off
e4b068b9-6712-506f-8aa3-c75e0a9df806 | date | Date Completed:
2bbb4695-97f8-4be3-b1be-ffb72713e894 | section | 6. Post-installation Activities
7165b23e-9758-42ee-a9fe-a6fb98074d6f | checkpoint | 6.1 - Verification of Subcontractor conformance records / signed ITPs including any relevant verification sheets.
0a1446f4-f614-570c-af37-7252a8077c6a | note | Reference - IFC Drawings Notes
075bc761-c823-569d-92f9-3c40c25da5f6 | note | Acceptance Criteria - Check conformance report against project conformance criteria.
e291b546-6b8c-5517-a9ac-0d6cc433973b | note | ○ Attach Verification Docs: QA Records, Signed ITP including any verification documents, Commissioning & Testing Certificates.
594e5c2f-c65f-56ad-905e-f32f8d6ade0f | note | Method - Visual /Site Inspection & Document Review
8561843d-8f0d-5fcb-ab0b-5ee7fec55c59 | note | Frequency - Per Lot
7398fb75-79f1-5974-b870-d0017b1347d5 | note | Category - IP
bec39430-d85d-505c-8b01-0f70c67d6e39 | note | Responsibility - SE/PE/SPE
ad2c38e5-8e04-5171-af68-d40c346a1c70 | note | Verifying Documents - This ITP Signed Off
218b4869-9f27-53fc-bcc4-2f76a685f46d | date | Date Completed:
6820fc5a-fc08-4265-92be-6ff2baeeb6f7 | checkpoint | 6.2 - As-Built Drawings
1c92dbba-611a-5212-9375-e5988a3340d2 | note | Reference - IFC Drawings Notes
fe078f07-f11a-5e12-a0ec-87dbe809ff5e | note | Acceptance Criteria - As built drawings for the metered lighting installations to be provided to the satisfaction of MRPA & Cardinia Shire Council.
3ac49ab2-5a2d-54c8-9035-4cc72a0f072a | note | ○ Attach: As Constructured Plans / As-Builts
c48ba1c6-370f-5e1d-ab2f-fd9ea0823e0a | note | Method - Document Review
6654f69a-2cf9-55d1-addf-6dafaa60bb0b | note | Frequency - Upon completion/ Work area
9fd11b95-ee30-5289-a2c8-d3bcda315950 | note | Category - IP
714088c7-6866-501e-8314-2acf53ec30b8 | note | Responsibility - SE/PE/SPE
1439e8a0-c73e-58d1-bfe0-9250c9c16659 | note | Verifying Documents - This ITP Signed Off
4eb459cf-1a47-568c-bf1f-798b981d4227 | date | Date Completed:
08b4cfad-4891-49b7-9632-dc3b9f2d6083 | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
a5eab65d-9eab-520b-ab83-dabfbacd4a0a | note | Reference - MRPA Quality Management Plan
3cd3c1b5-efed-5104-9576-ab07090632b2 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in TeamBinder.
69b9bde1-d2cf-59c0-ac15-dd32f6abd546 | note | Method - Document Review
4c8619a3-73bc-5888-a35a-87166deb86cb | note | Frequency - Once, prior to closure of this lot / element / Work area
bde66684-ebed-54d7-8765-e139c8cf8a42 | note | Category - WP
3b42ce1e-d0a5-5321-b416-226a6603b698 | note | Responsibility - SE/PE/SPE
090aea94-9839-5176-ab44-cb5df414b75c | note | Verifying Documents - This ITP Signed Off
726d3999-c038-5cf4-aef1-a04328b35ddf | date | Date Completed:
9f7ccbdb-aaaf-4050-966f-e4094110087b | checkpoint | Final Inspection
cb9e6021-8d3b-5ca0-a2f3-94715e406c5b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
cf83440d-1501-5c90-a250-92ee1e448c7b | textbox | Name:
6f9c169a-07c9-5e6b-9a76-2b6a2046e191 | textbox | Position:
e975a39b-db4d-5f33-a2b5-a3e646922de7 | textbox | Date Completed:
5d5a4637-7481-4be1-aebc-a4b5a619b759 | signoff | Sign ITP
| checklist | ITP-207-CIV-Guard Rail (Supply and Install) Rev 0 | itp | ITP-207-CIV-Guard Rail (Supply and Install) | a361f15f-a623-40de-8954-0d023c880aaf
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
bcc60310-5333-510c-8b53-977c330d7503 | note | Document Title: ITP-207-CIV-Guard Rail (Supply and Install)
e70de1f8-08e4-5e5b-be4d-b5b96416427f | note | ITP Description: Guard Rail (Supply and Install)
459e9ffc-ef7b-59ae-8c70-21cbc83431a8 | note | Discipline (e.g. CIV/STR/RAIL): 207-CIV
e40af2f4-855f-50a1-bbd6-e3ace6183208 | note | Revision Number: 0
d3eccba5-8c83-5a25-a225-da26e8a55dcf | note | Revision Date: 8/10/2024
11f6fdb0-05bb-50a4-bc7a-a2405e4ac715 | note | ITP created by: Jason Quan/Derek Collins
1b5f6a26-cbc4-5f0a-83ae-0accbdad65d8 | note | ITP approved for use by: Pradeep Talasila
b6ed1a9c-9d2d-54cf-87b6-820e3df65d86 | note | 1.1 - Non Dependent
529b6a70-2fe3-5d12-a7af-cc124a5c555b | note | Reference: VicRoads Section 708 November 2018
b7fb4d1d-6c2e-5c8d-a613-86e7cecd9b36 | note | 1.2 - Non Dependent
66a19d0f-de3c-5cf5-b4f2-dec22bc8b6e5 | note | Reference: VicRoads Section 703 August 2021
| section | 2. Preliminary
| checkpoint | 2.1 - Accepted Products and material confirmation
a66fec7e-08f7-5865-98d3-41fea6494d70 | note | Reference - VicRoads Spec. Cl.708.04
df31a1bc-9aac-554e-bb2d-a1a08fcc6ff2 | note | Acceptance Criteria - Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
988feea4-3466-584f-a632-a075ab2acef3 | note | ○ Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
a74b2639-4a59-5f07-aa5d-5a1380a86fbe | note | Method - Document Review
2149149e-923e-5df1-9aea-455662c38fb6 | note | Frequency - Each member material component
414a4d84-44c3-5c67-bd30-2e9e8f3bc5b6 | note | Category - HP*
7a024d18-c46e-51e8-a4ea-4daa094770e0 | note | Responsibility - Nominated Authority
31e28f28-408a-542c-94c8-c3d1e2b79091 | note | Verifying Documents - ConQA Hold Point Release
1a7d1c36-35c6-5c09-a11a-74f46319a3ce | date | Date Completed:
| checkpoint | 2.2 - Identification of guard fence components
0ac7122b-5379-50d0-93e6-049f7db8db15 | note | Reference - VicRoads Spec. Cl.708.05 (a)
cd38df59-0888-5886-be43-3432518984cd | note | Acceptance Criteria - w-beam sections, both ends of posts and all plastic components of proprietary end treatments unotrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
30bac8ea-7bed-579e-a11a-4800087bb795 | note | Method - Visual
6e8d8585-6f89-55c9-9b05-96acf5a58331 | note | Frequency - Each member material component
d89bb320-ea9b-5e3e-b44e-79af2e8a73a0 | note | Category - IP
cbb52816-7048-525a-9a3d-0e58789532d0 | note | Responsibility - SE/PE/SPE
a2dd1cdc-1076-58c3-ba41-e2eafd06c0f6 | note | Verifying Documents - This ITP
ade27064-48c6-59c9-b861-cfc75588e244 | date | Date Completed:
| checkpoint | 2.3 - Obtain and submit Material Test Certificate of Compliance for the barrier systems
f8956e7a-ae83-5322-95cf-541ff9f75eac | note | Reference - VicRoads Spec. Cl.708.05(b & c) AS/NZS 1594, AS1627, AS 4680 ISO/IEC 17025 a
f1e38d8f-cb9e-54ff-a005-c4cb2a3aa34c | note | Acceptance Criteria - Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
b1fc1d3b-3048-5873-bb5c-2f7b40fe241e | note | Method - Document Review
a7632e81-08fe-5061-8d8f-f3e4953aa258 | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
6f381d3b-35bb-5e19-b8d8-05f6bd3a9061 | note | Category - HP*
5a876d53-acf0-57a7-913c-fdbabdc6a9e6 | note | Responsibility - Nominated Authority
42a4160d-c2c6-5335-881f-1b039898bc42 | note | Verifying Documents - ConQA Hold Point Release
3a964614-f4c0-508c-8b4b-e4419b1cfcc9 | date | Date Completed:
| checkpoint | 2.4 - Obtain and submit Material Test Certificate of Compliance for the barrier systems
63a6ed23-03c6-5f4e-84ce-d465e14ce87b | note | Reference - 708.5 (c)
63a7b962-71a9-5eb6-8621-5e7217d96abd | note | Acceptance Criteria - W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250.
8c620196-5036-5239-966c-2def59f57de0 | note | ○ Steel posts and blocks shall be manufactured from steel which meets the requirements of AS/NZS 1594 Grade HA250.
ed7f7cc0-cd23-5d95-97d0-d2db3c45cc45 | note | ○ Terminal sections and stiffener plates shall be manufactured from steel which meets the requirements of AS/NZS 1594 Grade HA350.
e160c653-8fa4-5dcc-913e-5d06c02765ba | note | Method - Document Review
09b5cd7f-9c75-50e0-977e-a64b73988c1f | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
673d2906-eccd-529d-bcba-14dea08db66a | note | Category - HP*
2978d9b7-5ddf-5cef-abfe-ff0308e23f90 | note | Responsibility - Nominated Authority
39d84444-b114-54e9-888a-a30151598ede | note | Verifying Documents - ConQA Hold Point Release
ca8797bb-9ecf-5f5c-9b50-fc86de55ff2e | date | Date Completed:
| checkpoint | 2.5 - Verification of Protective treament/ galvanisation records
9abe7c5f-8a22-59b7-9cca-513fe77a6676 | note | Reference - VicRoads Spec. Cl.708.05(d)
d6e18cc4-0e11-52fd-838e-ced502246a1f | note | Acceptance Criteria - Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214
caf8e256-9586-5890-b46b-51996c6a30d8 | note | Method - Document Review
22f02e1d-bbc7-558e-a1f1-fac03cd60fd0 | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
9a4e808e-5060-5ec5-afec-3003bb4c7a78 | note | Category - HP*
773ef805-bb9c-5599-8ba5-7acc12bf01bb | note | Responsibility - Nominated Authority
f5df5ee5-36d8-5226-b0e9-1eb1363d1542 | note | Verifying Documents - ConQA Hold Point Release
5277c0d8-c3a0-5d0c-91f9-40259437165c | date | Date Completed:
| checkpoint | 2.6 - Concrete mix design
193a8bf4-3a9a-5cc7-bff4-a3167b5993c6 | note | Reference - VicRoads Spec. Cl.703, Cl.708.05(g) AS1379
c650de32-22e6-5284-b65e-fa8d40313a14 | note | Acceptance Criteria - Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
92a62520-6e5a-56c2-bfc8-f74fe0892b57 | note | (i) Portland cement-based concrete, N20 strength grade, or
5ef92fe8-ff56-5611-a4c9-e2bdbdaf510c | note | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
661ba0cd-2075-5265-a3c6-30c631417083 | note | Method - Document Review
392671e1-811f-5b03-a417-22b557fd2bb7 | note | Frequency - Prior to Commencing
432076e6-2695-50d2-9177-c73b50feb81a | note | Category - IP
6b2a8a44-eb5f-5d75-b193-b1e6299cac01 | note | Responsibility - SE/PE/SPE
4de2db11-07bf-5e8b-93b1-70c8e4356326 | note | Verifying Documents - This ITP
39165d56-a34c-5b22-94b9-dd4b18edea39 | date | Date Completed:
| section | 3. Construction Activities
| checkpoint | 3.1 - Survey Set-out
8d2636eb-872c-5d42-8a95-a5a7c2f6d2e8 | note | Reference - Project Spec. Cl.1190.07 IFC Drawings
1ea8838e-310d-5f68-ba1a-2d120fa83147 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element.
3bd59c4a-6b65-5c70-9e25-b2e584d73b87 | note | ○ Attach: Survey As-builts / Survey Report
0faede40-2b0a-577e-87de-1f202bdc781d | note | Method - Measure, Visual
12d2e9da-35ad-54bd-a881-f10de66313b1 | note | Frequency - Prior to Commencing Excavation
27b3d382-2bca-5181-ac07-3b9255affcd1 | note | Category - IP
c85d626e-8627-5b3f-9762-2c5f946f776c | note | Responsibility - Surveyor, SE/PE/SPE
421f6687-98ed-56d1-913d-04fe35c0e3f2 | note | Verifying Documents - This ITP
6f4054d9-7773-5157-a12e-3fd8d859e717 | date | Date Completed:
| checkpoint | 3.2 - Obtain approval of location and length
9f0508f4-660c-5b2b-8372-bd5214ce3e18 | note | Reference - VicRoads Spec. Cl.708.08 IFC Drawings
7dbe604b-96bd-5b6e-a99b-ca75a75ec463 | note | Acceptance Criteria - The required location and length of all guard fence shall be confirmed with the Superintendent.
6e9b39a5-15e2-5996-a3b6-5b9bade99b6c | note | Method - Measure, Visual
c01b4e9b-7e65-5ddb-852b-add8d27d1d98 | note | Frequency - Prior to Installation
d443036c-b04c-59a4-bc3a-667feaf3d385 | note | Category - HP*
3b638aed-b698-57ee-ba29-3c200066537b | note | Responsibility - Nominated Authority
777137db-5686-5114-9b66-f061a547e8cc | note | Verifying Documents - ConQA Hold Point Release
9cca0187-24d4-5cf1-88ab-bb8cb89566d8 | date | Date Completed:
| checkpoint | 3.3 - Install posts, rails and terminations
78f10c87-8010-5400-897c-a9607b4f6605 | note | Reference - IFC Drawings, VicRoads Spec. Cl.708 .07(a & d) IFC Drawings
6c3bcc29-5d65-566e-96c3-0cdeff19c7b6 | note | Acceptance Criteria - Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
6ec1ea6e-439d-54e5-8578-2036977aff59 | note | Method - Measure, Visual
6dd396a6-241b-5c23-ad64-3fcfd8b8254f | note | Frequency - During construction.
fd1a3a22-173c-5ebd-8313-75383d7ed4e9 | note | Category - IP
1dbcb028-225d-5bd8-8688-0b58e6cd0535 | note | Responsibility - SE/PE/SPE
c490aed5-992f-509e-8d03-956901fae68b | note | Verifying Documents - This ITP
7e1607e3-c2f4-5de0-8fc3-e11d1ee077c2 | date | Date Completed:
| checkpoint | 3.4 - Construct crushed rock base for maintenance strip
ed4cf049-e638-5e09-a257-d0c342b4f44a | note | Reference - VicRoads Spec. Cl.708 .11, Cl.812
d638f2f8-ca66-5934-880a-7a2ae799a90d | note | Acceptance Criteria - Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
8833b3a5-da5c-5348-b06f-c46ab58bf37e | note | Method - Measure, Visual
0f4de122-de26-5314-8dfc-0145e3de3f1f | note | Frequency - During construction.
8c004f2f-5b0c-5311-8318-5fa139e7126d | note | Category - IP
099d3d8c-7104-54a1-8b34-78a3a45c78aa | note | Responsibility - SE/PE/SPE
0a628909-6d60-50b4-ba4a-6ed6d3912671 | note | Verifying Documents - This ITP
4ddab8e0-38a2-54b1-bbca-a8f663db1110 | date | Date Completed:
| checkpoint | 3.5 - Construct concrete maintenance strip
9223f7fc-3b4e-52eb-a72d-05b54f82666f | note | Reference - VicRoads Spec. Cl.708.12a, Cl.708.5g, Cl.703.11
33df8e0e-5113-511d-983e-64b9a58a0300 | note | Acceptance Criteria - Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
81f1a1fd-7f8c-52cb-ba00-96c04d513795 | note | Method - Measure, Visual
6c9031b4-7e38-55bf-a438-0149100ce259 | note | Frequency - During construction.
88d82887-e1c2-57de-b70f-86050cf4f101 | note | Category - IP
7ec99d31-cbde-5580-bae0-3f58409a7d47 | note | Responsibility - SE/PE/SPE
01b2b3a2-fd2f-5ed7-86ad-fcfb0b13a7c1 | note | Verifying Documents - This ITP
ba3f0f61-0a1b-56ad-9b94-96a7c57a4b00 | date | Date Completed:
| checkpoint | 3.6 - Curing of concrete maintenance strip
dc9f3751-c3d1-50d0-bb98-d2d031c91239 | note | Reference - VicRoads Spec. Cl.708.16, Cl.703
36b3995a-2e72-5627-bdaf-837661abac78 | note | Acceptance Criteria - Concrete shall be cured either by water curing,wet hessian,polyethlyene sheeting adequately sealed against moisture losses, curing compound or combination thereof.
45b86901-e747-5822-8503-cd89a08d0604 | note | ○ Curing compounds to be in accordance with AS3799.
854244bd-3c86-59c8-862c-9e59af4d5354 | note | Method - Measure, Visual
4444d7fb-c7a8-5c30-b359-afdf8ffb9b36 | note | Frequency - no less than 7 days after concrete placement
3ecdfbbd-7636-5f82-8d19-e4948526804d | note | Category - IP
cb3fdd21-a41e-5749-b4a4-256641f85cde | note | Responsibility - SE/PE/SPE
0324ab0c-42fe-543e-8960-846ed8da446d | note | Verifying Documents - This ITP
ba7dd205-499f-50fe-bf30-22473c7b0aa5 | date | Date Completed:
| section | 4. Completion
| checkpoint | 4.1 - Delineators
201e574b-88ec-5b29-a056-4a0fd7c5bebf | note | Reference - VicRoads Spec. Cl.708.11, Cl.703.12
79a07361-cb3d-546d-b3c0-26e9b1130623 | note | Acceptance Criteria - Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
547461ea-d668-5244-8b7e-2894e7eacb3d | note | Method - Visual, Document Review
fe608a08-fb7a-5ea9-a4d7-271fe16efaad | note | Frequency - Once, immediately following the installation and prior to any Work commencing on the members
7defb2ae-d8be-5544-8e1b-af7755331c5e | note | Category - IP
d34886d9-cc43-5121-be95-bd9bd17dfd71 | note | Responsibility - SE/PE/SPE
47e2bc4b-4b74-5e5a-b6f3-1de3bb01925d | note | Verifying Documents - This ITP
1d59f4f2-9a9a-5096-87ae-d9abf734a8a9 | date | Date Completed:
| checkpoint | 4.2 - Existing Sign & markings Reinstatement
991dec91-be2e-545d-8561-84bbb2b9fa29 | note | Reference - VicRoads Spec. Cl.708.17 IFC Drawings
db7af514-0e3b-5822-8447-a5021a6b505c | note | Acceptance Criteria - The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
71ca19b5-f813-58bf-896a-ff49adc95e42 | note | Method - Document Review
6bf2200c-a4f7-5696-8c96-cfbcdaadff4c | note | Frequency - Each element
8807ae54-ff60-5722-8eb8-9959394a2a25 | note | Category - HP*
a511752e-4db1-5f68-b005-ad66e3127cd7 | note | Responsibility - Nominated Authority
f76e338a-d4da-57af-aeef-9ff29ec75361 | note | Verifying Documents - ConQA Hold Point Release
16d71174-2f33-543b-85af-6351fff35592 | date | Date Completed:
| checkpoint | 4.3 - Compliance Audit of Safety Barrier System Installation
8d974daa-0794-5d23-96da-c7f0bd6a054f | note | Reference - VicRoads Spec. Cl.708.10
5ed9f4b4-9519-5919-8458-831533b014ee | note | Acceptance Criteria - A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufactures installation Manual and specifiction for each end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
c8852e52-74fb-55c2-92b7-9f709226a8b3 | note | Method - Visual, Document Review
86ccc4f1-e845-54d3-b097-285d311d0a92 | note | Frequency - Each bridge beam
d4fbe0fc-3f1e-5f6b-9655-15bbe9de4ee1 | note | Category - HP*
60392a48-e195-5a9b-9c2f-3a8f382c794c | note | Responsibility - Nominated Authority
91d7c20f-5555-594d-b63b-ffcd9aae23bc | note | Verifying Documents - ConQA Hold Point Release
27404bfb-df50-5983-ae69-e2858c406c49 | date | Date Completed:
| checkpoint | 4.4 - Survey data captured for as-built purposes
a778d04c-126b-5642-8118-1c52d948e328 | note | Reference - IFC Drawings VicRoads Spec. Cl.708
b3e1e7ea-816c-503d-bc0c-d93d3ff9386c | note | Acceptance Criteria - As-built Drawings
88163bd0-fd89-5689-91b6-ba7e5a540c79 | note | ○ Tolerances as per VicRoads Specifications, Clause 708.
afb72e7d-be42-55c9-b641-75e18f0d9368 | note | Method - Visual, Document Review
e4fcb1a5-d7d0-560f-9912-0df9c89b3394 | note | Frequency - Where applicable
889a1e4f-b6ce-59ca-8916-5b6ec2cebbe9 | note | Category - IP
26af728b-ca9c-5006-b2d6-ce98d3b7f47a | note | Responsibility - Surveyor, SE/PE/SPE
8ad19297-be00-54bb-9c1f-8770e512a084 | note | Verifying Documents - This ITP
b710ac00-57a5-59ea-b72b-2146d7061943 | date | Date Completed:
| checkpoint | 4.5 - Non-conformance Report (NCR) Closure
e557c91b-ee2c-5bf7-b28c-4bed3f91c988 | note | Reference - MRPA Quality Management Plan
5976b9d4-9999-5888-aa89-d4995fbbd377 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
87d8f5ed-6509-52d5-8bcb-0644ba7c6730 | note | Method - Document Review
cdebd39a-7cc7-5e2b-914f-bcdcbec8d3d1 | note | Frequency - Once, prior to closure of this lot / element / Work area
c9e71fe4-6496-5657-9b97-1a86a078238d | note | Category - HP*
ab10ba38-daad-57e7-88b9-f93e496187aa | note | Responsibility - Nominated Authority
1d798d7f-c20b-5e40-8fee-7e22d4d6315c | note | Verifying Documents - ConQA Hold Point Release
a4f705fc-5233-538c-8d2c-5b6e3b85ef65 | date | Date Completed:
| checkpoint | Final Inspection
2ac6d763-7c1a-569d-ae0a-b85cf2550e71 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
86775706-6e30-54b7-9045-824beda7dc3a | textbox | Name:
bbe6a5ae-58d0-5a8c-b363-bd310a6467c3 | textbox | Position:
01a0d0b4-eff5-59da-b349-5d2b3123cb33 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-222-CIV-Calder-Residential Colorbond Fencing Rev 0 | itp | ITP-222-CIV-Calder-Residential Colorbond Fencing | 84b0c6f4-add1-412a-948f-6438cb52e8d3
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
91e75aae-3d07-5d69-bcda-65ac06eb637d | note | Document Title: ITP-222-CIV-Calder Park Drive-Residential Fencing
1f4556f2-16ad-5bb4-8949-4be1b2531c4c | note | ITP Description: Calder Park Drive-Residential Fencing
c55e4ea1-64c7-5887-ada2-ef90eb121507 | note | Discipline (e.g. CIV/STR/RAIL): CIV
02f104b6-9e50-5a39-aa99-2deb16cdf237 | note | Revision Number: 0
b02899df-3f6d-568f-91dd-6f6be0d2f049 | note | Revision Date: 12/11/2024
f982292a-4310-5b6a-814e-6172e2ed0390 | note | ITP created by: Jason Quan
b28b1acf-99a0-5f7b-8108-4d9acddec48d | note | ITP approved for use by: Pradeep Talasila
9dee0230-a09e-5e35-bbb7-9f46d392654f | note | 1.1 - Non Dependent
39a4dd87-72e8-5e5f-ac92-43ac77386909 | note | Reference: IFC Drawings, Manufacture Guidelines, Australian Standards
| section | 2. Materials
| checkpoint | 2.1 - Concrete
0c966c66-958f-5630-9d8a-2ec064243443 | note | Reference - IFC Drawings/Manufacture guidelines
fa3bb9ed-649a-568c-a9f5-39180384dbfe | note | Acceptance Criteria - Min 20 MPa concrete to be used as per Propietry Product Guidelines.
15884f5b-1155-56ff-b167-1431555ebe1e | note | Method - Document Review
42501ffc-2696-5117-9994-fb3a93ab2726 | note | Frequency - Each Mix
8a86b169-6836-539f-b58f-9696ff1e9b1a | note | Category - HP
3c9d8ac4-7fd1-569d-9e18-b5888638704e | note | Responsibility - SE/Site Supervisor
c1d2232f-6ea1-59c8-b706-a2f8450bacce | note | Verifying Documents - Supplier Certificate of Compliance
1782cfcc-0616-5635-b91b-acdc850ba283 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Steel Columns, Cladding etc
df690bef-788f-5e93-a095-06b94acc892a | note | Reference - IFC Drawings AS41000, AS1163
d22bfd06-67c9-58c2-a420-561be14086c6 | note | Acceptance Criteria - All Steel must comply with Australian Standards.
799f201e-7b5d-54c5-b449-20a3d17f32bd | note | ○ Steel section sizes must be checked on site.
378c9e9e-a87e-5454-accf-ca961c16fe68 | note | Method - Document review, Visual and Measure
d3b966d8-5d27-545a-b478-eb6ce6316469 | note | Frequency - All elements
559e61f4-7755-5c7c-8970-b2118e0f42d2 | note | Category - IP
602ca8ca-722c-576d-abd9-f738fdc1f2ce | note | Responsibility - SE/Site Supervisor
19a948b6-f4bd-5727-b18f-29c064d4776e | note | Verifying Documents - Supplier Certificate of Compliance
ac3cbd2b-6c3a-5cc2-8708-64c259c935ac | date | Date Completed:
| section | 3. Pre-construction / Pre-installation Activities
| checkpoint | 3.1 - Survey Set-out
8535086c-f835-540d-88b2-eef1a64af06e | note | Reference - IFC Drawings
3e24aa22-9b23-59b5-9b44-e030e20192f6 | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services and post locations
54c3aaac-033b-5456-a943-cbf9936388a9 | note | ○ Offset checked against the running edge prior to installation of posts.
464b6a17-6d14-51ea-b052-8d07d85c63b8 | note | Method - Measure, Visual
ab90cfa2-f1b3-5591-a43c-802ae0f80170 | note | Frequency - Each element
ec9faeb2-886f-5b1e-b84f-ba9a1cbfa788 | note | Category - IP
ce9151de-e6de-5e80-8f89-a85340d20781 | note | Responsibility - Surveyor, SE/PE
f7d7092e-f2d6-5f8d-ac34-a4f920efc657 | note | Verifying Documents - This ITP
cc4f27d9-ece5-56cb-a416-4f7455288605 | date | Date Completed:
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Excavation works
573ba9de-4169-5514-b6fc-5f415ed9c341 | note | Reference - IFC Drawings, Metroll - Colorbond - Metline
bd05e521-eca7-59bc-bd9c-7956ec145a1f | note | Acceptance Criteria - Excavation for post foundation must not undermine footing of existing structures.
9061418e-1856-5e32-a773-4789109807db | note | ○ Follow asset owners guidelines for work around their service.
68d14237-7330-5f03-9f56-4242b2f2eed6 | note | Method - Visual
dc9fcd13-14ff-5870-add6-96c70773a20c | note | Frequency -
618fc5f3-d6c4-5527-91dc-31a665e2702b | note | Category - IP
95e81243-455f-5138-bafb-d91327a2a280 | note | Responsibility - SE/Site Supervisor
b6f9ad35-b329-5158-9a2f-6b2a160d364b | note | Verifying Documents - This ITP
fbca5a8d-3b7a-513a-9342-cb0d4b1aecb1 | date | Date Completed:
| checkpoint | 4.2 - Ground Conditions
56ee8e27-78bd-5f72-ac1d-2696aa807af3 | note | Reference - IFC Drawings
6e22ed4a-4bdb-57ef-958b-cc233403fab6 | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
53a2e750-486a-5e09-8658-5130fc618e2b | note | Method - Visual
5292b2d8-740d-51c8-9024-90280b504820 | note | Frequency - Each post
c9a83a62-c141-536c-bd49-7f946980cbc3 | note | Category - IP
e63dc246-cb54-5c18-90f7-2899b1c5d858 | note | Responsibility - SE/Site Supervisor
98ece2ae-de21-5f95-a03c-a0815f7db260 | note | Verifying Documents - This ITP
0ffbfe18-912f-594c-a2e4-940b7c889134 | date | Date Completed:
| checkpoint | 4.3 - Fence Post Foundation
81df70ed-5d10-58b0-bbc1-aaedb5112bfc | note | Reference - IFC Drawings/Manufacture Guidelines
80d3d9e4-fe0d-5a88-b88c-ef5aa6da20ec | note | Acceptance Criteria - Minimim 20MPa concrete as Per Manufacture Guidelines
00a3abd4-371e-57ba-885b-17983b7baa52 | note | ○ Typical Footing: Footing dimension 900mm deep, with a 200mm dia
59bcbea7-ae71-53b7-b310-28ad7e7b8274 | note | Method - Measure
821c1add-71cc-55df-9ba5-cf089c22da9d | note | Frequency - Each footing
4a1ca5a8-7da4-57da-952d-3d8883c34410 | note | Category - IP
47109023-730e-53a5-9624-02fb2adcfb32 | note | Responsibility - SE/Site Supervisor
1b2e88ef-5286-585d-81cd-e66cfc0979c8 | note | Verifying Documents - Post and concrete dockets
6a2718a3-f98c-5b76-9fe7-9a57258fe115 | date | Date Completed:
| checkpoint | 4.4 - Fence Post Installation
f81ea200-bb36-540f-bed3-6ee6cb6570f5 | note | Reference - IFC Drawings/Manufacture Guidelines
02934c9e-a3dc-54a4-80e0-6f94ac1741d1 | note | Acceptance Criteria - Maximum post spacing 2365mm centres
7d12b717-6117-5efc-916d-0f3ec5e3cb4a | note | ○ Maximum post heights 2100mm above ground level. Vertical Tolerance (High Risk Areas): ±20mm from the design line.
e952053f-3baf-5671-ba44-333ec072a0e6 | note | Method - Measure
fee2f80e-1db4-55c7-9950-54088ec8334e | note | Frequency - Each post
4ad88d67-e8a7-5372-a0a3-e803eae7e34c | note | Category - IP
d70a2469-ec6c-5e92-b950-6980fef6bfb0 | note | Responsibility - SE/Site Supervisor
a0beb22d-e09c-5d81-b069-fd5dbd098498 | note | Verifying Documents - This ITP, Concrete Dockets
760c39a5-1493-5da9-9704-d2c0a4bd2902 | date | Date Completed:
| checkpoint | 4.6 - Assemble Fence Post
28ab4736-a5b0-5a9a-aca6-b79e8b5a7cf6 | note | Reference - IFC Drawings/Manufacture Guidelines
5c66c568-64c6-5517-91ec-321d60ef99eb | note | Acceptance Criteria - Assemble posts by screwing them back to back with 7 staggered screws.
d3f5f5b0-5948-5ee6-9bdd-d7a27d678ddd | note | ○ Use 7 x 10 - 16 x 16mm self-drilling screws.
b645e18a-59c2-5eeb-a7ae-1b4eabadb0c6 | note | ○ 2 x Screws approxiamiately 60mm from top of post.
bac854c0-4a84-5e41-ad94-5a7209742c71 | note | Method - Visual
6e3e088c-19a8-54f2-8fd7-ad4ff76a6ba7 | note | Frequency - Each post
c9121264-c25c-5654-8b86-a08bf9c45d6b | note | Category - IP
42457d2a-96ac-5acd-b967-f6d8c5b2283c | note | Responsibility - SE/Site Supervisor
dfc4abbb-5d7a-5063-8a54-bdd19e7a90a9 | note | Verifying Documents - This ITP
323695a8-f9e7-547a-adc0-764bfb7d75a9 | date | Date Completed:
| checkpoint | 4.7 - Bracing
9fbd3dcb-6807-5624-bdb2-9136c448f1e1 | note | Reference - IFC Drawings
e43d38ae-ca09-5875-9ec9-02be15f25303 | note | Acceptance Criteria - Powder coated SHS post as a corner for a neater finish. Either 50 x 50mm or 65 x 65mm for ends, corners and junctions.
a8d1acf2-b54d-55db-9db7-91d75b298fa0 | note | Method - Visual
7c82d99f-2c8f-54a9-bee5-27046103589b | note | Frequency - Each element
e1688f1e-b8a2-5880-9267-955196beefaf | note | Category - IP
dff44efb-997f-563c-9922-bc31247556d3 | note | Responsibility - SE/Site Supervisor
88b3f372-f39e-53a5-a544-19dd9f8638ad | note | Verifying Documents - This ITP, Steel delivery dockts
2e23d5a0-0614-516e-8527-0d49f9a895a3 | date | Date Completed:
| checkpoint | 4.8 - Installation of railing and infill sheets
e4491fd0-412a-5eb5-8f5d-ce5193464bd9 | note | Reference - IFC Drawings, Metroll - Colorbond - Metline
fb3dd9c1-53c4-59da-bc7b-6df10b7dd046 | note | Acceptance Criteria - Install bottom rail once concrete has fence post foundation has set 24 hours.
63659838-5d16-591e-8152-69657c9cf439 | note | ○ Slide infill sheets into the bottom rail ensuring a an overlap is allowed for between each sheets.
60c41b82-e2b0-5c3c-a128-9cefacd45ac4 | note | ○ Install top rail once the infill sheets are adjusted correctly.
63b66454-ff6f-5f07-8485-d1991bd12c05 | note | Method - Visual
0c43ff59-7b3e-5a39-bf62-921cf715ad5b | note | Frequency - Each element
67ca649f-dc09-5565-8042-c68ec948656e | note | Category - IP
88984c1e-2281-52e5-971e-84220282d4e1 | note | Responsibility - SE/Site Supervisor
aa9fc7f2-ccf1-5344-8901-8cf92ca26795 | note | Verifying Documents - This ITP, Steel delivery dockts
409afd7c-9c27-577b-b720-2dbff826275f | date | Date Completed:
| checkpoint | 4.9 - Installation of Lattice Panels
14565c25-5a47-57e9-9e64-206401198f9a | note | Reference - Metroll - Colorbond - Metline
6f7cd0b1-117a-5cc1-a0b0-3f0c2bdef201 | note | Acceptance Criteria - Where a 300mm lattice panel is used, install above top rail and fix it with 6 screws on either side to the top rail.
949fd697-597b-5788-addc-111791d040ff | note | Method - Visual
487c36ad-a01f-528b-9278-61113d37a40e | note | Frequency - Each post
21badb2d-2d9d-5821-a694-cd2f46779a8c | note | Category - IP
4269145b-f302-59b5-b01c-d408072461ac | note | Responsibility - SE/Site Supervisor
d60bd132-6bca-5392-8005-d672acf969c3 | note | Verifying Documents - This ITP
a41a6aa5-8f2f-5bf6-b863-4f48da77504d | date | Date Completed:
| checkpoint | 4.10 - Installation of plinths
fc6421eb-5c5e-5523-9cb2-1c19e30af223 | note | Reference - Metroll - Colorbond - Metline
83d3c5a1-1a85-5de3-bcdd-d4c6987880bb | note | Acceptance Criteria - Where plinths are applicable, insert the plinth into the post at the bottom of the panel.
33b6edc0-bdd3-5303-aa56-1f1fbcaae652 | note | ○ 1 Plinth = 155mm high
153869ea-8b5a-5dfb-bf78-59d9b4b3148a | note | ○ 2 Plinths = overlapped 265mm high
d4901abf-70a0-5f94-b47d-c877d16aca55 | note | ○ 3 Plinths = overlapped 375mm high
0285cada-ad01-5eba-9ea4-d1757f871642 | note | ○ 4 Plinths = overlapped 485mm high
edfaa99d-7585-5292-857d-e4506bc6e029 | note | ○ 5 Plinths = overlapped 595mm high
dc0e362d-e351-5651-8a86-5318d0270349 | note | – Where more than one plinth is used, a 50 x 50 x 1.6mm SHS post must be used.
f1b47179-c279-5127-b3ac-ba0c26a1c51a | note | Method - Visual
aadfd119-21ba-5153-bc45-083b798b8638 | note | Frequency - Each post
a8db53e3-0607-5030-95a8-3ac90a70380c | note | Category - IP
9be19506-ad60-58fc-ad21-380aa1e3ffc7 | note | Responsibility - SE/Site Supervisor
f7ec6873-32b7-510c-b109-948926d5735b | note | Verifying Documents - This ITP
891147f4-f5bf-586f-b0dc-b8b1f210bae3 | date | Date Completed:
| section | 5. Post-construction / Post-installation Activities
| checkpoint | 5.1 - Fence Height Clearance
e910625c-650d-540c-8b40-1945dcf3d1dc | note | Reference - Metroll - Colorbond - Metline
863e8868-1c3c-5500-81dc-7af741536b00 | note | Acceptance Criteria - 50 mm vertical ground clearance from Ground level to bottom of railing.
b399695b-cc5a-5f57-a760-e481d71c02a3 | note | Method - Measure
d1ef4213-9579-5332-97a0-62e0fbdebe4e | note | Frequency - Each lot
54f4505e-b8e1-53d1-84f7-c17ee87c2f31 | note | Category - IP
5c07f492-f0c3-5809-b37a-36f2e1457c18 | note | Responsibility - SE/Site Supervisor
910dad36-a903-53df-8041-adaf66071799 | note | Verifying Documents - This ITP
cb5786df-d737-59f8-9482-5e5790aaad1e | date | Date Completed:
| checkpoint | 5.2 - Asbuilt Survey
483a1618-d10c-54c1-8f0a-09a96cf678e1 | note | Reference - IFC Drawings
7e094875-7267-5492-b5ca-4b2078083c74 | note | Acceptance Criteria - Asbuilt survey report to be attach for the Residential Fence.
f69faee7-d290-551c-9106-4685cb4d4e0a | note | Method - Attach Report
99bee61d-0883-5f2f-8692-33b0905cf855 | note | Frequency - Each Lot
4f64ef55-ce4f-5e9a-9aa4-0a2dbf3c79bf | note | Category - IP
c544a078-48b2-5d8a-b12b-968d37d2dbe0 | note | Responsibility - SE/Site Supervisor
eb6d41d8-0bec-51b8-998a-e34de871a609 | note | Verifying Documents - This ITP
242fa0f7-6d14-5b3e-bdb2-d0ad36487f42 | date | Date Completed:
| checkpoint | Final Inspection
fb505497-290c-501a-bb19-104b1558e23e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8641df11-613a-5bf4-8f3d-93470d501ccf | textbox | Name:
4ac5411c-8293-5099-9075-df7d8c1784fa | textbox | Position:
181fdb2d-f5a6-5259-80c9-a23becbd4ef3 | textbox | Date Completed:
| signoff | Sign ITP
5b8fbd2a-ccd0-46bc-b791-6073ceb6efbb | checklist | ITP-248-STR-CPD-Bridge expansion joints Rev 0 | itp | ITP-248-STR-CPD-Bridge expansion joints | 1ebcc767-e5d6-43e0-8e35-8bbbf686f2c2
79f026a2-7f55-42cb-9fa3-140c34bb006d | section | 1. Referenced Documentation
9c730aa4-68f9-4434-8da9-a5ef8594d57b | checkpoint-no-value | Referenced Documentation
0055d728-646c-51d1-9b05-8052c6c6551e | note | Document Title: ITP-248-STR-CPD - Bridge expansion joints
19484e08-27be-5bf5-98fc-0a7d03d8e127 | note | ITP Description: CPD - Bridge expansion joints
8de0429d-c3aa-5b27-ad9a-f4becde801c6 | note | Discipline (e.g. CIV/STR/RAIL): 248-STR
5e9b8c67-47a6-5db5-afc9-c596a35d3a39 | note | Revision Number: 0
3a8dbf4c-2208-5192-b51e-14b95b429c42 | note | Revision Date: 4/04/2025
715a57e2-b15a-57eb-887d-5c08c7aa0714 | note | ITP created by: Will McCuskey
785d28c3-1179-51ec-98a1-89381dec6c44 | note | ITP approved for use by: Pradeep Talasila
ab541659-bc0f-51a6-84b3-31ff0f91f6f7 | note | 1.1 - Non Dependent
18f2797e-297d-5e90-883c-3eae1cd3e891 | note | Reference - VicRoads Section 660 January 2018
bf32fb6b-d748-5fd0-89d8-5bdab205d810 | note | 1.2 - Non Dependent
46f4953d-1e48-5166-b936-5bf836031dd9 | note | Reference - VicRoads Section 691 November 2018
af895951-d661-5d97-adf6-1c49c37175c3 | note | 1.3 - Non Dependent
296ef48a-0bf4-5826-a9c6-3412015be355 | note | Reference - AC-AR Installation Guide
dd57895b-17ba-4cb8-8cff-d8574a2606fa | section | 2. Preliminaries-Materials
f0609095-6c1a-4751-b692-3a73b275d958 | checkpoint | 2.2 - Expansion Joint Components
a87c161d-7a91-5f66-987b-bcb2ddbfe09f | note | Reference - IFC Drawings VR 660.03, VR 691.15
45d32f69-b797-5b55-a3c9-d7780609fc51 | note | Acceptance Criteria - Where applicable the joint material including joint sealant shall match the drawings or be an equivalent product
d3da6d43-273a-56c5-9f28-dff25cc99fec | note | ○ All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers.
e9180f6e-73dc-5e60-8caf-7b54e9b20dac | note | ○ The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming:
24e30086-619e-5e83-a385-b6341f729c8b | note | (a) manufacturer’s name and address
0c2b3c4c-4d04-585c-bd3f-372a40e30214 | note | (b) product reference
c15d98f9-9e62-533b-8664-451e9765ea9c | note | (c) batch number of identification
dcd8d808-ef39-5d2b-b7fb-521b2916b585 | note | (d) quantity manufactured in the batch
790158fd-894b-5710-af79-cb42126b178e | note | (e) date of manufacture.
3328c1fb-62f3-5ac0-970f-2d04add15087 | note | ○ All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients.
15059fc6-1169-5bea-8a6b-c7088309c6eb | note | ○ Attach Delivery dockets/Proof of purchase
5f719e85-a66c-50ff-a326-017c68b04a01 | note | Method - Document Review/Inspection
8c1cf1e4-a3e1-5e37-85b7-a193a3dec15f | note | Frequency - Where applicable, for each element
7b6b0321-3419-5af5-8a8c-0ee47252b6d8 | note | Category - IP
d030c662-396d-57d0-a771-fe565fcd1e17 | note | Responsibility - PE/SPE
4913c817-e369-5744-bc09-637b1413994e | note | Verifying Documents - This ITP
c1a54860-8af1-575e-8d5c-61a793f75f3f | date | Date Completed:
162868ad-36a1-4869-9096-2c9331e506ae | section | 3. Preliminaries-Procedures
64129a29-059e-41b7-a339-b61bfa2c04c2 | checkpoint | 3.2 - Expansion Joint Design
74d8a18c-3b1c-5314-959c-3bd4e137f02e | note | Reference - IFC Drawings VR 660.03
358f93a9-933d-5b99-87ea-d0fff725fd65 | note | Acceptance Criteria - The expansion joint system shall match the drawings.
bb93884d-bfae-55ee-b078-edfac1c80549 | note | ○ Where applicable, the joint sealant shall match the Drawings and installation manual
f97e6056-54d0-5b5a-8180-a3ccedbf0bd9 | note | ○ Specify the Joint type:
c35523a4-3348-5cbd-ba28-b515acc7a2eb | note | — AC-AR-125D for road
55aadb61-955e-56d3-b416-d366ccfc7744 | note | — P2-100D for SUP and Footpath
8fb7dd01-b8ff-54ac-bacd-24b888a26fce | note | Method - Document Review
af808f7a-7f81-5286-a899-d99f1d27e122 | note | Frequency - Where applicable, once, within 4 weeks of acceptance of tender
e07673e4-2fe7-5dd9-a83a-d4f103f6e902 | note | Category - WP
f79190a6-a352-5a52-965e-f237746cfd81 | note | Responsibility - SE/PE
5bd27ca0-5f03-5ed5-98cf-d38db4d7aee0 | note | Verifying Documents - This ITP
cbd821db-2267-5c5f-bcc1-d96bdf03391b | date | Date Completed:
0571b374-d861-4e09-a98b-0d5d1a5d20b2 | section | 4. Pre-construction Activities
b69218e6-74bd-4bfb-b441-8f9ed3bcbad0 | checkpoint | 4.1 - Expansion Joint Installation Temperature
73ba55d7-f007-5cd4-93a9-22bcf60f7980 | note | Reference - VR 660.04
0ae3493f-c2b9-5518-b229-0e6530768bc5 | note | Acceptance Criteria - The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers.
ab7fa294-d30c-58fc-8c62-83b22b14825a | note | ○ Installation Temperature = 150 - 250 Celcius
9b139c2f-1937-5b26-a239-79f357bd6656 | note | Method - Measure
37fa55e2-587b-54ee-acbe-90803b89951a | note | Frequency - At the time of installation
aa7ac631-ff8d-56e9-81ec-6756896fe4cd | note | Category - HP
1b23a6f9-c47d-5f11-825b-bddc40372780 | note | Responsibility - SE/PE
e938293c-d622-539d-997e-f1b241a14ce4 | note | Verifying Documents - ConQA Hold Point Release
45c1fe75-596c-563e-beac-314fff9e2afb | date | Date Completed:
e6d14d2a-611f-4e18-ad51-d51a11ba2dcd | signoff | AUTHORITY HOLDPOINT
0fd01dca-4fd1-40fe-bed3-337609c9cbd3 | checkpoint | 4.2 - Cast-in anchor inspection
4d4a2d52-e898-550a-a462-5ecd1f37ff80 | note | Reference - VR 660.04
d4ccde18-2519-57b6-a239-7252bc23c8f8 | note | Acceptance Criteria - Prior to casting deck conrete, the conctractor is to ensure that there is no conflict between the joint anchors, the deck reinforcement and any embedment.
dfdf6dd6-24ad-5862-a0e2-6d13bbe9b8e8 | note | ○ Reinforcement surrounding embedded anchorages shall be in achordance with the design requirements of the joint design
99281963-2096-5411-8c7b-5144922087de | note | Method - Visual
e9efcae7-1b2e-506c-abcb-129fe9c01589 | note | Frequency - Prior to casting
5b960df6-7c6d-549d-8891-450e6deb8697 | note | Category - HP
787ff859-9c1d-514a-9af4-4866c30f0fd5 | note | Responsibility - SE/PE
dea4e48e-2fe3-5d42-aee1-19b3f3f7b081 | note | Verifying Documents - ConQA Hold Point Release
52e58b91-6d61-590a-aa37-6246271c42c8 | date | Date Completed:
44bae7bd-7305-4433-98e4-b5a3815f2fc0 | signoff | AUTHORITY HOLDPOINT
15594466-b237-495c-8a4f-3c3feb4dfd2d | checkpoint | 4.3 - Post-pour Inspection of Expansion Joint Bearing Surface
b7c1790b-3152-51f4-89f0-2e0537dc128e | note | Reference - VR 660.04
142d1392-6274-5fb4-a4a4-39c3df574039 | note | Acceptance Criteria - The faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
c0d3f7c4-77de-57e1-8638-27ae9942cc2f | note | Method - Visual
c8ad0f88-0bc7-5f11-9f85-f2554ee025d1 | note | Frequency - Prior to joint sealant (where applicable)
bacf4b22-efba-52bf-8f2b-e4f1b32587ca | note | Category - HP
3c682373-285c-5104-9938-fd506ecb211e | note | Responsibility - SE/PE
3ed67fd8-035a-5712-aeed-f313e7d6c973 | note | Verifying Documents - ConQA Hold Point Release
ae02b7bc-5a53-507b-9763-a427663e3c75 | date | Date Completed:
ab3d2b32-6b1f-4cae-b869-c8cc8d4ca396 | signoff | AUTHORITY HOLDPOINT
498ec568-d147-4566-a494-b43cf2f4fce2 | section | 5. Construction Activities
01aac044-2370-4e22-9268-036b20191f31 | checkpoint | 5.1 - Expansion Joint Placement- Anchor Bolts
cc99d99b-294e-5b90-8ea1-144ccbe9dced | note | Reference - IFC Drawings, AC-AR Installation Manual
d149f1df-ff11-5468-b11e-73fd78308fca | note | Acceptance Criteria - After concrete strength is in excess of 30MPa, the anchor bolts can be tightenedvia the snug tight plus part turn method or with a claibrated torque wrench.
ae120d54-d111-5ad5-959c-9614ddd9d18c | note | ○ As per installation manual:
fa649c70-1d36-5dfb-98af-85aae57c00ce | note | — Part turn method: Snug tight + half turn
2565c71e-b8f7-54c9-8e72-cf99437dec75 | note | — Calibrated torque wrench: 400Nm
03993835-ae2a-5103-b6e4-979ab26b4a54 | note | ○ Attach: torque wrench calibration certificate
0bfec3c3-bd19-57b1-b8ae-af945df5cc4e | note | Method - Measure, Visual
0d0d2873-c2d3-5da2-b897-0a056c92ac55 | note | Frequency - AC-AR 125D (Road section) joints
598c69c1-c759-5d95-9a75-ca3450ddd908 | note | Category - IP
43a7d7e8-01e6-5994-b22e-dec84c51ada3 | note | Responsibility - SE/PE/SPE
fd594919-1aa8-5a06-af9f-e7f83e0b3190 | note | Verifying Documents - ConQA Hold Point Release
9abffb71-9493-5e66-8a7b-c432930e9c4b | date | Date Completed:
43b67971-c6f3-4ac4-8cae-703bfdaa1b99 | checkpoint | 5.2 - Expansion Joint Placement-Coverplate
d4fd8f9b-1baf-5e71-b46c-2797be68d33c | note | Reference - IFC Drawing
d9a53c46-e8eb-5866-b47a-bea00b500cd2 | note | Acceptance Criteria - Aluminium checker plate is installed with M12 Cuntersunk bolts as specified in the drawings
4e117033-30dd-54da-a489-b4b3b33497b4 | note | Method - Inspection
7d2e6aa0-7b31-56f9-b345-d2d8a4062024 | note | Frequency - P2-100D (SUP and Fottpath) Joints
98b9cd33-5209-5dc7-b798-31a00a6dbe0d | note | Category - IP
38f3466b-513e-58f1-81d2-f913ae8ad374 | note | Responsibility - SE/PE
18911c68-2584-5874-8ff4-5c46060c39f2 | note | Verifying Documents - This ITP
58a905af-9e42-5f57-b1fb-799cba517cd0 | date | Date Completed:
49c0c9d7-fb94-4673-8574-4a68629e9e3d | checkpoint | 5.3 - Expansion Joint Placement
1b0ea39b-8637-5459-adef-52281b10d3bb | note | Reference - IFC Drawings, AC-AR Installation Manual VR 660.04
aece2700-8db7-5c39-a4c6-4177fb838b63 | note | Acceptance Criteria - Check compliance with the Drawings, installation manual and tolerances:
f77c8c9c-13c2-51c8-a2e7-62e11b9c72e6 | note | ○ Joint gap = ±3mm (38mm is specified on the drawings)
a9b11626-7857-5c98-b1b1-1f9be88593a7 | note | ○ Deviation from plan alignment = 5mm max.
9e545551-fbf4-586d-b05d-9b62148b312b | note | ○ Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
96cb6e0c-8c5e-53e9-9079-7e572557397b | note | Method - Measure, Visual
49f58a79-7474-5732-b7db-ddb10a67321b | note | Frequency - Each element
ffcb7b83-a004-51ad-9626-6d282569bc60 | note | Category - HP
c8b8c5fe-595c-5dfb-aba8-41d0bb3da197 | note | Responsibility - Surveyor, SE/PE/SPE
2a875908-513f-511b-b520-75130e193a50 | note | Verifying Documents - This ITP
c2e72349-ce62-54d1-a5e3-3c72ce983689 | date | Date Completed:
7a035bbc-ec44-4fcd-9324-f8de65e1f210 | signoff | AUTHORITY HOLDPOINT
9cafdee3-1771-459f-a7cd-ccd67676b007 | checkpoint | 5.4 - Compression Seals, Inserts and Membranes
aa45bdd5-ec15-5a1e-96a9-5dafa9d18cfb | note | Reference - VR 660.04
de4054ca-dbbe-52c7-9077-6c8a2194c879 | note | Acceptance Criteria - Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
a09dc48a-dbbb-5d32-ba4b-acea65353a03 | note | ○ Completed joints shall be watertight.
bc11562d-3108-5994-bc63-6dc2638c0148 | note | Method - Visual
bb64e8c6-cc8d-5303-a788-fbee6b38d9bf | note | Frequency - Where applicable, each element
732b270d-0c6a-56b1-be69-744f0f62694c | note | Category - HP
010b760c-a49a-5c83-8aac-9d231e33fcfd | note | Responsibility - SE/PE/SPE
580f5e03-47e1-57d9-97f2-b277ad8038c4 | note | Verifying Documents - This ITP
5335251b-1f08-5fda-8a80-c8b7703fe73f | date | Date Completed:
e4e93333-7852-48ff-ba00-1493ebed6ec4 | signoff | AUTHORITY HOLDPOINT
141f78f1-47d6-4302-b5fb-4afb5cb66314 | checkpoint | 5.5 - Final Inspection of installed membrane system including all accessories
5c76b888-7199-5295-bab5-0977310b958d | note | Reference - IFC Drawings
63bf05db-dc17-5d70-bcae-9cce421dbf30 | note | Acceptance Criteria - No visual damage to the installed membrane system
aafff9c1-55c0-537b-b48c-561addf55246 | note | Method - Inspection
d7eaf4c2-3664-52d5-8040-11eba5692599 | note | Frequency - Once per Lot
7f8a8898-98cf-5593-bb37-d33220175aff | note | Category - IP
aace49b1-da63-53f8-81a7-3d12e9df6ab5 | note | Responsibility - SE/PE
4adc0ae6-1171-5e69-ad5b-ccbdae7deff6 | note | Verifying Documents - This ITP
510b256a-7d65-525a-9900-4a10d6377371 | date | Date Completed:
42d8b4ac-7b93-4f97-9423-29ca86733eeb | section | 6. Post-construction Activities
b4536573-6018-43f6-8acd-df13ea31f0e0 | checkpoint | 6.1 - Trafficking of Joints During Construction
3f1f3970-816d-5e05-9ac4-a9c4f83bac5d | note | Reference - VR 660.04
d9a12d23-dbcf-5860-8acf-3702aede05cb | note | Acceptance Criteria - Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
5b9f6129-05f8-5362-920b-f7301470566a | note | Method - Visual
872963eb-3268-5b4a-bc73-381c84660fe6 | note | Frequency - Where applicable, each element
cb85846c-3970-578b-9751-70ddb01d6a47 | note | Category - HP
9f550a47-b9ec-58c4-8dbf-82c71e657af3 | note | Responsibility - SE/PE/SPE
a49406af-b8ba-5904-aa44-c1b536c989e7 | note | Verifying Documents - This ITP
e6a1b5e5-caa3-59c4-9716-a92f7f5b4caf | date | Date Completed:
4d39e153-8a5a-4067-9335-9f4e3322ec99 | signoff | AUTHORITY HOLDPOINT
ebaa12ca-c8fc-4802-a33f-1a21062b1019 | checkpoint | 6.2 - As-built Survey
4f19465f-9e4c-50e9-b88a-902d04b7697b | note | Reference - IFC Drawings VR 660.04
872ef2e9-86d3-50ea-9345-1fc056aa310d | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 5.3 above.
7d9dbda4-d261-5863-9470-f35e641ca6c3 | note | ○ Attach: Survey As-builts / Survey Report
c5c3b24c-0274-5676-b304-8f90551fbd07 | note | Method - Document Review
98ab744c-759b-5bab-9b56-ef0356214ca8 | note | Frequency - Each element
08b2aab4-8ee6-5dce-9cfa-a3bb734a0c55 | note | Category - IP
48a82370-fc82-597c-b15f-6731a5d8b8b7 | note | Responsibility - Surveyor, SE/PE/SPE
6fdc410c-a2cb-59e2-9dfb-5123bb6444c9 | note | Verifying Documents - This ITP
188af581-fbbb-5827-afa5-c5e851c8b8ec | date | Date Completed:
67515fbb-c4a5-4fe8-9a35-067930ab1e8f | checkpoint | 6.3 - Subcontractor Product warranties obtained
82bd75f9-c7bb-5314-9015-3e64d0a9c5c3 | note | Reference - Work Method Statement, IFC Drawings
a298f28d-efed-52b0-a6d8-b60fe6fd3183 | note | Acceptance Criteria - Product warranties obtained and are compliant with what is specificed in IFC Drawings
6c662ddf-b04b-5379-a00b-e71ef7e5b7b9 | note | Method - Inspection, Document Review
98802313-a688-57c5-a01e-d047137cbf6f | note | Frequency - Once per Lot
59f46720-4bbc-59c5-8596-de189a3129c3 | note | Category - WP
0605607f-14fa-5460-a5d7-3bb91cfbbd55 | note | Responsibility - SE/PE
bc1749b6-679a-589d-bfc9-fe295a4ad947 | note | Verifying Documents - Copies of product warranties
d0602bad-d4f5-50b9-9123-bda8acfb5426 | date | Date Completed:
59c6c76c-187b-43a2-8a23-9be90b678aa4 | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
b72f92e6-941f-573f-a80a-413a9722adc7 | note | Reference - MRPA Quality Management Plan
1a0534cb-5bc1-5701-b99d-8e9641a358a3 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
fc1cad51-b1bb-5def-af42-4e3614470895 | note | Method - Document Review
cfce72af-63eb-5393-a153-32ec3a51c022 | note | Frequency - Once, prior to closure of this lot / element / Work area
65ad5312-799f-53d8-bedb-ed89e68a1cd1 | note | Category - HP*
bb7bc99d-00a0-5136-b275-de66d20b85d5 | note | Responsibility - SE/PE/SPE
15a40a6f-de14-528e-8234-b50548256700 | note | Verifying Documents - This ITP
ac7b2d2b-39d9-5ecb-9856-bcb7964f8ccc | date | Date Completed:
693e2b14-b942-483f-84d9-c4feb0b8ec2b | checkpoint | Final Inspection
55562166-f510-5683-9247-7a356140e36c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d19b695c-edc1-5a43-8ce8-a291ab62ec45 | textbox | Name:
ef44681d-c2c8-5143-96d9-49db7d0de639 | textbox | Position:
2a941140-6971-5676-8429-0d92646a9a0e | textbox | Date Completed:
90c7ca2a-cd67-4098-bd05-95864b0adda1 | signoff | Sign ITP
f84ab483-d7f8-478d-9d54-2c426d1a1ce6 | checklist | ITP-249-CIV-CPD-General Concrete Rev 1 | itp | ITP-249-CIV-CPD-General Concrete | 8b3fbbb8-6e0c-4bea-8b84-55f470820353
039fe7d4-1e86-4f12-b720-56b9d69c620f | section | 1. Referenced Documentation
d5b7d963-afad-4a24-8600-3f21f2e79302 | checkpoint-no-value | Referenced Documentation
b534850b-49d8-5a02-a0c9-98137440e731 | note | Document Title: ITP-249-CIV-General Concrete
3d8a8b7e-0807-55b3-913e-6728fe385b3b | note | ITP Description: General Concrete
50693e08-7a67-588c-995b-99d9706434cc | note | Discipline (e.g. CIV/STR/RAIL): 249-CIV
451e55c6-71cf-57ab-b0de-1d26bdaa3a29 | note | Revision Number: 1
1b4589fe-b24c-5242-aad7-8ce178229bf5 | note | Revision Date: 31/03/2025
be476faf-956a-5eb6-86a9-40c0ed2d9915 | note | ITP created by: Jason Quan
4eefcea0-4545-5f6c-9dc0-571e3db64daf | note | ITP approved for use by: Pradeep Talasila
3d56d48a-c1aa-5145-a16e-ddefd164a5a4 | note | 1.1 - Non Dependent
93a9206e-2aa0-59d1-bc87-41ca95d23cea | note | Reference - VicRoads Section 703 August 2021
e8e0e360-440f-50fe-9438-bd897c99277f | note | 1.2 - Non Dependent
bb4b6b51-b0b2-5c24-bf07-8e6db8d9b312 | note | Reference - VicRoads Section 812 July 2016
2f63e6fa-ad57-5b78-bd40-5f669209cb06 | note | 1.3 - Non Dependent
872c61a7-a857-5a03-879c-6618034f3d4b | note | Reference - AS1379-2007
af0da440-573f-584c-848b-0bb089fe4b4e | note | 1.4 - Non Dependent
7f205e26-0b23-52ac-a968-18b6fcd3faf4 | note | Reference - AS3610-2018
f2dd58ca-0ce6-5125-af5d-bfcacdcd777a | note | 1.5 - Non Dependent
ce4dd45a-ddb3-5696-a5a8-49cc03d028df | note | Reference - AS4671-2019
64e79def-46ab-4d43-ae03-019dd3c504a1 | section | 2. Preliminaries - Materials
4e6f5bc0-b780-4461-b681-5d88943b167f | checkpoint | 2.1 - Bedding Material / Base Layer
ec2fc906-4b92-5b9f-a103-7a670563f31a | note | Reference - IFC Drawings 703.21, 812.04
49488747-691b-5016-b7f6-0221ddf2b234 | note | Acceptance Criteria - Bedding material conform to specified requirements applicable to the class of product as detailed on the drawings.
d21e28d4-a2e8-5260-a783-08015bc97f21 | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
19d994ae-d93e-5bb5-8ce9-91446e310cc4 | textbox | Enter: Teambinder Material Approval number
67313d09-7818-5d06-9166-d5818cd24b09 | note | Method - Document Review
1e763e84-f8f0-525e-980d-282b76ffd9db | note | Frequency - Once, for each mix design, prior to placement of material
9d142397-293d-5027-b1f0-fa5369116900 | note | Category - HP
c75a0f9b-7741-54ca-805a-db0e058905b3 | note | Responsibility - Nominated Authority
68989a0e-381b-59c4-bc90-44c48125031a | note | Verifying Documents - ConQA Hold Point Release
80d6de86-9c0f-59b4-be94-b302dcf9abef | date | Date Completed:
f1112cc1-b806-41ae-a100-ea323edb8bcb | signoff | AUTHORITY HOLDPOINT
58cde26a-f7c2-4287-bb30-28f054f8732a | checkpoint | 2.2 - Concrete Mix
bc229cd4-e2c3-5aa7-be8a-66ad80339392 | note | Reference - IFC Drawings 703.05 (a), 703.07 MRPA Quality Management Plan
c487dd53-348c-50bd-bcda-caa4be5826fd | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
b0b636de-6035-5bd3-9aa2-ca0d6b712408 | note | ○ Paving concrete mix conforms to AS1379.
a14ee383-d3f6-5bb6-8397-500bbc23d429 | note | ○ SUP concrete mix is registered with VicRoads.
e98e268c-ea99-5810-b304-ef9063de80c3 | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
cf0f52d9-ee1c-510e-ad7e-e63ce047edb4 | textbox | Enter: Teambinder Material Approval number
df4dc68e-8bba-51e8-82dc-7ffa199c8f2b | note | Method - Document Review
a0cdb4b8-399f-5ea5-8326-3a28a05cafb6 | note | Frequency - Once, for each mix design, prior to placement of concrete
7e2df65d-aa12-532b-af6b-b8a66c815a23 | note | Category - IP
df7693eb-34b7-5043-97a9-a5bc55e9ed8a | note | Responsibility - Nominated Authority
9e06fc21-f33c-51d0-a23c-451d973fb020 | note | Verifying Documents - ConQA Hold Point Release
f405803c-18d5-5bb0-8bc2-f580e91f2d58 | date | Date Completed:
d2ea5598-f006-4e8c-977a-deb6c9f5eb2c | checkpoint | 2.3 - Reinforcement Certification (or ACRS Certification)
368cfc25-3893-5975-a864-ca7d9d6370a2 | note | Reference - 703.13 MRPA Quality Management Plan
9c1a2c4e-e8c2-5b1d-9b5d-4b7fda481e72 | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
e846f472-a934-5180-97f6-c9e0e6b5e05b | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
6a5f21ed-fe1f-58b8-969a-ab5161a4e2f0 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
d3d3c575-ef37-5f8a-b899-0feacd770b51 | textbox | Enter: Teambinder Material Approval number
9c9b6a82-0078-5b01-8eae-948f9f7e8f06 | note | Method - Document Review
36c7bff7-1d6a-5fce-ae8a-115643e62885 | note | Frequency - Once for each supplier, prior to placement of order
794575e0-4451-57dd-a387-df869ff947f6 | note | Category - IP
d252c662-0db2-54f2-9c5e-e6a0c4404bd0 | note | Responsibility - Nominated Authority
a502ecd4-2164-5662-b63d-a887345e036f | note | Verifying Documents - This ITP
f1304e2a-5b00-5a96-8537-9ea8b05f193a | date | Date Completed:
a993eea9-9fde-4dd3-991a-e43fbac67aca | checkpoint | 2.4 - Evaporative Retardant
bbcfb0a0-df86-526c-b9ad-85640a3a6582 | note | Reference - 703.09
42a91a26-a99e-5995-aeed-c84e7bdccc78 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
78c3517b-5bd1-5471-9584-0887284eeb99 | textbox | Enter: Teambinder Material Approval number
2d5be41c-351c-5f39-8b15-ca83804edd43 | note | Method - Document Review
86308c5f-5572-5530-aeb9-63a9b0abe206 | note | Frequency - Once, for each product, prior to placement of concrete
b8f11239-7185-57cd-8bd7-e46f464f12fd | note | Category - WP
ab8ffa7e-c067-52cc-a89f-6940e5c2239a | note | Responsibility - Nominated Authority
74bb7711-6f9e-5438-a566-4523a5106325 | note | Verifying Documents - This ITP
7663b4fc-3d1e-5bfb-acea-035e579a7678 | date | Date Completed:
8a207728-d78a-4145-b310-b6d335060557 | checkpoint | 2.5 - Curing Compound
b35490fa-ff50-5ac2-b958-d4ea306b8679 | note | Reference - 703.10 (a)
889c67df-70ad-5dbb-8f33-a99fe36813f7 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
90ddf9bc-31de-59e0-864a-027152572880 | textbox | Enter: Teambinder Material Approval number
46533ce4-d182-5bba-96c5-b12fa0826a04 | note | Method - Document Review
5632b9cb-43be-51b9-80cf-9a14f8d79228 | note | Frequency - Once, for each product, prior to placement of concrete
0a5c8752-9384-5cad-b3df-04ae9bd7976e | note | Category - IP
f1c75262-1245-55b4-9b0b-0f134b2d96d6 | note | Responsibility - Nominated Authority
c759e912-9fb9-5919-aa9f-9553115cc982 | note | Verifying Documents - This ITP
038461c1-0453-50e1-bdcd-1f598123f20a | date | Date Completed:
7581e1d3-e676-4615-bf66-5079936c3a41 | section | 3. Pre-construction Activities
c461a20e-a497-4c74-8b4e-23c5ea8a32a4 | checkpoint | 3.1 - IFC Drawings
9b1e2516-84c3-5fef-a821-070e9fd67454 | note | Reference - MRPA Quality Management Plan
8ee685b6-9ec7-53b5-bb41-56602438fef5 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
6687adde-9429-52ac-afa6-7055929bcb6d | note | Method - Document Review
44f93e5b-bfbb-530e-90e0-4ab0291e3cf1 | note | Frequency - Prior to starting Works and at regular intervals
9d52d44b-9ce0-5f63-b284-358f3bf18bd8 | note | Category - HP*
c62e7e89-a220-5831-99b6-0112f812d42f | note | Responsibility - All
8b262d09-3a94-5eab-b2fa-06a1f0790bab | note | Verifying Documents - This ITP
6fbe41c8-afbe-5798-8ab5-e9ee8b083093 | date | Date Completed:
d3aff484-c60c-4b26-a1ca-e138131deabf | checkpoint | 3.2 - Survey Set-out
245e6d9a-95bb-55ce-9900-900dc0e91e0e | note | Reference - IFC Drawings 703.17
612a9f39-0246-525e-b062-d489ade486c5 | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
a93c2191-786b-5380-9009-66e3ce76893a | note | ○ The Nominated Authority will review and confirm the set out.
00db5283-846f-5f9b-a9d2-d676da11d882 | note | ○ Attach: Survey Report
42e85af4-a88c-508a-99a3-39ca50bcc472 | note | Method - Document Review, Measure, Visual
cf3a1c41-8efe-5ced-9355-198b634d0de0 | note | Frequency - Where applicable, each lot
74918e79-f58c-5d3a-bd78-dc66474e3ac9 | note | Category - HP
df48766a-3470-55db-ba21-b1b85c0e6ea4 | note | Responsibility - Nominated Authority
910737e2-dfaa-51e4-b434-b609d3e47c47 | note | Verifying Documents - ConQA Hold Point Release
1db64908-ec9f-5b9f-bc80-87f8c0a01a27 | date | Date Completed:
ba61c9c4-d973-48de-86de-bc9e2c1e74d6 | signoff | AUTHORITY HOLDPOINT
54fd5c82-b276-434a-b297-3b4e3b3af13c | section | 4. Construction Activities
9ca40a21-6e66-4083-b53a-a31fea9bca33 | checkpoint | 4.1 - Excavation
072991db-ffce-56ef-a4bc-3bae50d273a2 | note | Reference - 703.2
0b30e850-fd80-5916-9616-88972e8010bf | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
9930a46c-a0cf-55ca-9462-08770906f3c2 | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
aad5ff40-5306-546b-ac15-6541f0b33f64 | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
168512f9-29c3-5e2d-bc42-32fd9a321bd0 | note | Method - Visual, Measure
2a52d079-5861-5c78-8b42-784db8b274e5 | note | Frequency - Where applicable, each lot
cca2bdb7-bd73-5b37-b666-1739881c9aee | note | Category - IP
43cb9fd5-8732-5a60-b300-ae567001aa31 | note | Responsibility - SE/PE/SPE
a55d5ee8-90f3-5818-91ac-f4b2233871b5 | note | Verifying Documents - This ITP
d9266e2f-82a4-5442-9e06-da839dca3ff1 | date | Date Completed:
5855ae2c-5a50-46dd-bf0a-dd8b16e056e2 | checkpoint | 4.2 - Bedding Material Placement & Compaction
7e0f339a-ce11-55a6-98ac-a98d674b015a | note | Reference - 703.21
f6f9ac32-0e9a-580a-9105-5f44713b62c8 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings).
a2dca8d2-d7e9-5de8-a57b-374af368a49d | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
cd20c69a-c3f8-582b-bf3e-7d0057daacfe | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
e2402250-0815-5239-b7ba-1bb3db43764d | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
7cab41cf-d959-5022-a808-5575234e9845 | note | ○ Attach: Bedding Material Delivery Dockets
f070ed0b-97ac-5fc4-a481-95a212d0a853 | note | Method - Visual, Measure
db01d74a-9442-5a18-8a09-fe7e1335a504 | note | Frequency - Where applicable, each lot
597f2e88-b309-52aa-ab6d-20edb9148ed9 | note | Category - IP
e319ca13-73bd-550f-9c63-d2b2da5ddbd8 | note | Responsibility - SE/PE/SPE
d89370f1-a926-5419-bb89-03a058bd4031 | note | Verifying Documents - This ITP
b2127b30-6389-5983-9367-4152561b49c2 | date | Date Completed:
e1682829-faae-4683-8702-e209f9530352 | checkpoint | 4.3 - Formwork Construction & Placement
3b315265-dd05-5f52-a950-f5e8a13e1717 | note | Reference - IFC Drawings 703.12
98489246-6ec9-50ef-9a23-e2b781c63126 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
3644249f-58fb-5e0e-9e8d-02e1b6074a9f | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional comformance.
d2a720f0-ab47-5da4-b247-ef25f49455eb | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
4d36c958-ccee-542d-82e6-1e60dc71c875 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
de056517-4f8a-59a6-aa42-a488a88f3ab2 | note | Method - Visual, Measure
72a8e7de-f4f3-5532-a7fb-401070aaa1b4 | note | Frequency - Each lot
0874ac73-254a-52f4-8a4f-83d3380177b9 | note | Category - IP
a345bc36-07ef-5a9c-aae7-4797ef8f1434 | note | Responsibility - SE/PE/SPE
80c00a11-46bc-53a4-8362-411ba495fd8a | note | Verifying Documents - This ITP
696ae6ef-b530-53a1-a4ca-d4dff85b7718 | date | Date Completed:
0c7f1408-4501-4326-b64a-f3a45ed46d8f | checkpoint | 4.4 - Construction Joints & Matching Exisiting Surfaces
b799a631-2699-504b-819b-fbe6da3ba022 | note | Reference - IFC Drawings 703.24, Relevant Council Standard Drawings
60737876-a85b-5dcd-b7d0-ce7df5cc6084 | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
b54e164f-2d48-55be-854f-f38209186848 | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
59ae8847-4ccd-5fd6-ada0-641634063f7f | note | i. Concrete cutting of a shear-key
3da8857d-77f3-5d25-b6aa-795f719dac94 | note | ii. Surface rouighening
b6228867-19a6-5a3e-8dd4-707305955dec | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
d703192e-344d-5d39-ad39-b80e1acb1ad9 | note | iv. Cutting a groove for sealant
39ac56c3-278a-5aed-9f3d-dabe2f8fdad2 | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
7ddf8b16-ec33-57d1-a70e-eb5fd23eafc4 | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
8a72cbc9-abce-556a-80b6-08d270f26c3e | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
c71f6d52-8cb4-5e2d-ab42-9bd9fe25133d | note | Method - Visual, Measure
ce128e90-5285-54d0-abf9-3a140f498b1e | note | Frequency - Where applicable, each lot
aab0bdde-98bd-53fe-9653-ec7c559afbbe | note | Category - IP
10416c62-280b-51ac-a6d6-d857e18653d1 | note | Responsibility - SE/PE/SPE
cdbe53ba-ff8a-5e7f-9599-ee7f8c1dedfe | note | Verifying Documents - This ITP
c0daccc1-f7d5-5512-be68-90ad6275fca6 | date | Date Completed:
6e6b0d57-084a-4200-8567-5f674f23d1df | checkpoint | 4.5 - Isolation Joints
61522680-6408-5159-9325-55e16e13feb8 | note | Reference - IFC Drawings 703.26 (c), Relevant Council Standard Drawings
cdf34668-d08d-55f7-928e-e02c42bd3357 | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
55c36357-b545-5a71-8c1b-e9ff7f7089c4 | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
f4fc809b-8892-5b7e-ba9d-70bab2b9112b | note | ii. at any location marked on the drawings
95f56451-ecc7-54e9-92f5-95aaa3d45418 | note | ○ The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
21fe7747-b4d6-5871-8120-b05c971503f7 | note | Method - Visual, Measure
6242ca49-355a-5053-b8e1-e4de890a88b5 | note | Frequency - Where applicable, each lot
31cd67fd-9dde-561e-82c6-0696c07d3c57 | note | Category - IP
7b2e247d-c081-5cf6-9478-342336ac2e70 | note | Responsibility - SE/PE/SPE
9314532e-7081-52d4-8ab3-c549feb859f1 | note | Verifying Documents - This ITP
9d5b1c46-87b3-5d6b-8491-30a2c4857017 | date | Date Completed:
3d6542c6-1bf8-4380-b8a8-9857cface71a | checkpoint | 4.6 - Reinforcement Placement
94b71f40-25d0-5455-802a-1c8e16b94aa8 | note | Reference - IFC Drawings 703.13
8d6318b1-1442-569c-b37c-8275d8fbdcd5 | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
eddebfee-a7f6-5225-abfb-e9108be830ca | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
45582223-19b3-5628-be74-cab3cf461704 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
cbc42e9b-122b-5e54-a97a-8e13cff00ee0 | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
45e74678-32fa-5bee-acb1-4a3023195218 | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
f3fb9a1a-da86-57e4-ac6c-2ccfe6061da3 | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
bf07a390-882b-5284-beb0-ebd6a929e7fb | note | Method - Measure, Visual
23f4a3e2-1aba-55bf-9ec8-a2a241caa8c9 | note | Frequency - Each element
69b98a26-2337-5f8d-9a6f-7ff84cdaeef5 | note | Category - IP
1969cd7c-7a8f-5496-a9ed-36c70702e2e0 | note | Responsibility - Foreman, SE/PE/SPE
a0982de3-fa3e-5342-842c-b06ae62460a0 | note | Verifying Documents - This ITP
9fa00b02-4388-5dd4-93bb-ce9342871cdb | date | Date Completed:
3793df93-8895-43a0-bf16-1a5602d9dc22 | checkpoint | 4.7 - Pre-pour Inspection
9f917be3-af82-5908-87ca-8692ec6520f8 | note | Reference - IFC Drawings 703.15, 703.21
c592c115-e39b-5aa8-b96d-e62549fdadbb | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
b7f24433-2375-575e-ad4f-10b43b822b89 | note | Method - Measure, Visual
81d0a7ce-0de9-559f-a499-2d515441a5ff | note | Frequency - Each lot
fb317de7-ad0f-5fc4-8929-5defa9e92a74 | note | Category - IP
6b91c9d2-442d-59b9-92bd-e5ecbecf4e7d | note | Responsibility - SE/PE/SPE
d322c9aa-0788-5016-a80b-df021fd5a023 | note | Verifying Documents - This ITP
e4166d59-8092-5a57-91de-9f84574220e9 | date | Date Completed:
f28716a0-c4ab-4eb8-943c-1672833950d0 | checkpoint | 4.8 - Weather Conditions & Evaporation Limits
967707c5-bc33-502f-aa1d-896b599806bf | note | Reference - 703.09
642af9e4-1f82-571e-9a3c-aea7fbdeb45b | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
660a19a0-d3f4-51da-8eec-b7cc2828b958 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
2138ab26-1961-53ee-b511-7e7c613e2ad0 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
50ed8b79-29e1-555a-a104-836eca2f25db | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
0cb48139-05a8-5fbe-982e-a427d08030a1 | note | ○ Record: Required information on the Concrete Pour Record.
7ec2236e-8168-5606-8119-249a27c862dd | note | Method - Measure, Visual
efef5ce2-059f-52dc-8b0e-46f46736ae84 | note | Frequency - Each lot
fb062ca4-d990-528d-9077-03a361611a54 | note | Category - IP
9d7594b3-0580-5ab5-85e4-640c7192b714 | note | Responsibility - Foreman, SE/PE/SPE
6a1bdc5e-4425-5505-8b55-1a36af163db6 | note | Verifying Documents - This ITP
384b5c1e-f744-5013-bf8f-fbf1b8282593 | date | Date Completed:
e3080bee-dfb0-4bb5-b00c-b5a73da8564e | checkpoint | 4.9 - Concrete Testing - Sampling Frequencies
bee2e45a-ef7b-5c04-b8f6-f932d44aa6cb | note | Reference - 703.11
6256c0cb-12e5-57f2-9a54-2f4f5e40eda3 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
cabf4274-2665-5b9d-bde8-f6b5cec00772 | note | ○ 0m³ to 50m³ = 1 sample
89dc1ed0-2d5e-5ba1-9ab8-d07f20e0f347 | note | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
889fc9cc-5e4d-5836-b1a1-12050a490829 | note | ○ Compressive strength cylinders = 2 no. 28 day strength.
69f32759-772b-5b87-8566-7fba06c2c054 | note | ○ Record: Required information on the Concrete Pour Record.
460459f3-9c4d-5789-b23e-cf07b6fa3331 | note | Method - Test
ec914da4-4641-5f47-bdbc-ef786272f15a | note | Frequency - Each lot
f460904f-6d5d-5c8f-9dd5-22a6c4ec7211 | note | Category - IP
21c719ab-993e-5fcb-bfe2-b6a6470ab4b9 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
748878b0-57e5-54b8-849a-3dda54ec22c4 | note | Verifying Documents - This ITP
334559d5-aa24-5f75-b6ee-44a3a58e768a | date | Date Completed:
0322f560-7c6b-4c26-ab65-31aae3d32d54 | checkpoint | 4.10 - Concrete Testing - Slump
e6ef30a3-971e-511b-ad06-37fa0c005e4e | note | Reference - 703.11
563d6fde-0279-5bed-b268-2770189912dc | note | Acceptance Criteria - Slump testing tolerances =
60aea11b-89bf-5093-b9ed-a84c5322cac9 | note | — <60mm = ±10mm
c42edfc1-50c9-5407-8f7b-85502c09cdc7 | note | — ≥60mm to ≤80mm = ±15mm
c5f12eeb-59b7-54c1-a5f7-2016b86bafa4 | note | — >80mm to ≤110mm = ±20mm
4435f555-1ad0-5262-b09d-50cdbf89b2ff | note | — >110mm to ≤150mm = ±30mm
2fd3b1f6-0854-53e8-b8d4-728fd43038df | note | — >150mm = ±40mm
95ad449f-1cc5-56d6-9cb2-1d1ea8efb512 | note | ○ Record: Required information on the Concrete Pour Record.
b0fb00b8-baef-593a-9325-aa98764def6d | note | Method - Test
8a6b0a7a-598f-5a25-8523-dbaac2086ea6 | note | Frequency - Each sample
21bbc0f5-d970-5399-ae07-87719e55ba43 | note | Category - IP
0cc533f2-8ba8-5dcc-a299-e71915ba0ccd | note | Responsibility - Concrete Tester
c86e24c9-a39e-5128-b72e-3faab5e40023 | note | Verifying Documents - This ITP
eca7f063-b777-55fe-941c-b13c0194f0ee | date | Date Completed:
5e456ee8-fb74-4afe-b718-9a4a7a8f4e90 | checkpoint | 4.11 - Concrete Testing - Compressive Strength Cylinders
35809e2d-9566-524f-97e1-b06190d9492f | note | Reference - 703.11
ef5ad601-e159-5cf2-8bad-460a2bd0de1f | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
29949f12-bc19-5530-91d3-023208664396 | note | ○ Record: Required information on the Concrete Pour Record.
8217e055-033a-5027-b755-01154475df2f | note | Method - Test
f1c35dfd-c76f-524e-8d63-45fa7af0bbe5 | note | Frequency - Each sample
af99a48a-c3ae-557d-95f8-36ed77f9dcf0 | note | Category - IP
d31848f8-dd11-595b-a8c6-d96e93e51ebf | note | Responsibility - Concrete Tester
4f4a45bd-8a81-5012-a6ab-5584e7a6edf8 | note | Verifying Documents - This ITP
6ad19442-b233-5f15-92ae-b798c9777f44 | date | Date Completed:
d89287ac-af4e-4e86-82bc-acb9b425210c | checkpoint | 4.12 - Supply & Discharge Rates
48a5a11a-cb5d-580d-8a7f-73ca03e33313 | note | Reference - 703.08, AS1379 Clause 4.4.1, AS1379 Clause 4.2.3, AS1379 Clause 4.2.5
918a31d5-b86d-5195-8c06-14c53ad2b7d5 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
0e6679f6-00a0-5b7c-b1d2-4760ed92891b | note | ○ Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
fa24272e-6c98-552b-ba28-618701014b15 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
a1330706-fc1b-5728-8732-9b41fa60aa4e | note | ○ If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
f329c09e-ae77-5d3c-a0c1-dd6206857581 | note | ○ Record: Required information on the Concrete Pour Record.
9a73e2c4-0dc7-5e4f-b564-041cabf8ba8e | note | Method - Measure, Visual
42f961f4-2450-5938-81b2-f4c378b62e6a | note | Frequency - Each load
41b50d7b-4410-596f-ab41-bc29c9705b5c | note | Category - IP
6c970fd5-19eb-5447-a0e8-53d9d691c79d | note | Responsibility - Foreman, SE/PE/SPE
887560ad-791f-5a71-9c77-7c0ee6a73251 | note | Verifying Documents - This ITP
3e0044fb-2fbb-5bae-8f8c-d6d1c1043ab1 | date | Date Completed:
f21bbe68-ce76-4143-917f-314bc3289475 | checkpoint | 4.13 - Placement & Compaction
770b46b9-9558-5f21-9cb6-b390beb5482a | note | Reference - 703.08
34d166f1-f0e0-5ebc-8555-6b5dac214e8d | note | Acceptance Criteria - All concrete batches are traceable.
38606ea4-da02-5817-9cad-22f8ddc7274e | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
3e1b0a90-9852-5c25-8572-ba5e9b74c6ec | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
8142a778-937c-5764-8a60-d6a4e940a35e | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
8f6d91f7-877d-5110-beb0-9d05b44c5cbf | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
50149c4c-d026-515d-9f44-f79466c5e353 | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
186595ac-63d6-53cd-8bb3-34c389dd5c78 | note | ○ Record: Required information on the Concrete Pour Record.
8c5da11c-2de5-5133-a9f9-065a4b4ba117 | note | ○ Attach: Concrete Pour Record
ee20afb5-fe8f-534a-b709-69132b7d6302 | note | ○ Attach: Concrete Dockets
f63c343a-df68-53ea-8da3-7f96687243f8 | note | Method - Visual
3106f8cb-4e7b-5a68-9eae-c3ad49a1b6c1 | note | Frequency - Each load
f7f946d8-641c-5637-b19b-278bb986d08d | note | Category - SP
459702e1-a3ff-5adc-b069-aff4efbf2ab7 | note | Responsibility - Foreman, SE/PE/SPE
c4d3a11a-76d7-5af8-8fb2-278def6a8cad | note | Verifying Documents -
2eee975c-bbac-5e7f-8906-bdc27af48224 | date | Date Completed:
32680f44-b02b-4bd5-a80b-c189c96cf047 | checkpoint | 4.14 - Surface Finishes
62faa911-0e28-584e-98b0-69c8b4f43228 | note | Reference - IFC Drawings, Relevant Council Drawings 703.25
bd89dcda-cb2a-5500-97ae-22f07d2b438f | note | Acceptance Criteria - Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
b2b46991-bf05-5bda-add0-a64d2abb2b65 | note | ○ All outside edges of slabs and all joints shall be finished with a suitable edging tool.
01b71d68-d7b0-555a-a3ef-c7a2eac12ea3 | note | Method - Visual
16350704-c0dc-5e4f-a1a2-ebf9220bd16a | note | Frequency - Each lot
4aa57d68-55c7-567e-9ff0-c03d8cf47fbd | note | Category - IP
604b089e-a5dc-5f80-bb3e-cd93a0011e30 | note | Responsibility - Foreman, SE/PE/SPE
b1742365-6e6b-5d2a-8b58-86c588d2c289 | note | Verifying Documents - This ITP
2f2a8234-6300-51a5-86b4-e6170d760c48 | date | Date Completed:
21c4305e-eff4-4d3a-b516-826cfd5da922 | checkpoint | 4.15 - Marking of Conduit Locations
98b073ea-e8df-5dba-84ba-451799901005 | note | Reference - IFC Drawings, Relevant Council Drawings 703.28
3d0ac5f7-7667-5289-86c6-63fa0cebf2bc | note | Acceptance Criteria - The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
72bdb927-5f0f-5dc6-96f4-c8cc1d13c6dc | note | Method - Visual
4cafc9b7-6be0-525f-a9b1-2169385c63d5 | note | Frequency - Each lot
32956ee4-8d50-5a96-a906-60981f65c46e | note | Category - IP
bcb201ac-4182-5735-93a7-c918733623c1 | note | Responsibility - Foreman, SE/PE/SPE
377dd62a-2a8d-5d2e-a77b-c0e4303e467c | note | Verifying Documents - This ITP
77f8796c-63cf-5a57-a8b9-88e45d3c33be | date | Date Completed:
d3e3e3f5-895d-483c-8d55-f5c3144a2d2b | checkpoint | 4.16 - Crack-control Joints / Weaken Plane Joints
b2df8805-cc2e-50c6-95d9-9fc900f6c3ff | note | Reference - IFC Drawings, Relevant Council Drawings 703.26 (b) (ii)
8ba0935f-f177-5da6-a01e-000a043b68ae | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
7666031c-82fd-5e85-a696-4a9ed0795b10 | note | Method - Visual
1af8176d-ed9d-5b60-8095-1430702aa1bd | note | Frequency - Where applicable, each lot
a8e46153-5197-5bf0-a0ed-21116853ea97 | note | Category - IP
d3d08e07-af56-5507-95d2-2e5b69aadfa9 | note | Responsibility - Foreman, SE/PE/SPE
f8f6145e-ecb3-5bb7-a382-36e08686eda8 | note | Verifying Documents - This ITP
edb23642-4c7a-55a4-aa0c-77baa0e1d139 | date | Date Completed:
02671f81-34b6-41bb-8c87-93a31a532346 | checkpoint | 4.17 - Curing
de096fd9-2171-5481-827c-b0c9707ceacc | note | Reference - 703.1
213dfe43-bcca-521f-a68e-b103a2a40763 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
1e42d3f7-847c-5d22-a673-e1225d624f36 | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
c4e51ba8-355b-541c-a0cb-6e8078ea7541 | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
4965f649-0cb8-543f-b507-5326b85fb9e7 | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
a795c901-b24c-57a9-b91a-6e7071fb49ea | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
09c7311a-97cf-594c-b1d1-b3f878cfe543 | note | Method - Visual
bab94d4e-8e0c-5965-8423-7a7a613d5c2a | note | Frequency - Each lot
27c46bff-733b-5b89-b622-6fe6f0c5eaa7 | note | Category - IP
eb867732-2949-5bda-b2c3-a9f21d53214c | note | Responsibility - Foreman, SE/PE/SPE
f83e8140-7175-5f7c-89a2-f2d589e4e76a | note | Verifying Documents - This ITP
e06e177e-e07f-5ec3-939e-b6973de22c97 | date | Date Completed:
bfc299d9-392e-4382-ba07-560d9208b383 | section | 5. Post-construction Activities
6305266e-658e-49e5-a20e-d129c9d078c1 | checkpoint | 5.1 - Protection of Newly Poured Concrete
1fb46877-291f-5036-8bd9-3576ba17fe6a | note | Reference - 703.27
1111b402-44fe-59a7-8976-b1858b9468a8 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
8e3abff7-587a-5ac8-81e6-cb74d8e7e07d | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
d7131f58-cb08-55f8-800e-accf4c91b3bb | note | Method - Visual
3189c11a-a916-52bb-b5f8-921e486e1425 | note | Frequency - Where applicable, each lot
2da1ae75-71e6-5e36-84ee-92d909ee89cd | note | Category - IP
aeab3ab4-0a78-59d9-83f0-33c81349bb07 | note | Responsibility - Foreman, SE/PE/SPE
4fcdaa63-1717-55a2-a89c-4f0d264f9a60 | note | Verifying Documents - This ITP
c1cad26a-578b-549a-8acc-44c16a4d8539 | date | Date Completed:
de6ec5d0-11b0-48fc-b69e-9731d4e41dc2 | checkpoint | 5.2 - Stripping Formwork
95a8c24a-12de-5e09-9763-65f2d79ea983 | note | Reference - 703.12, AS3610 Table C2
606067cd-a5c1-58f8-8ab1-2d81aaf390f2 | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
19a9a257-6a98-5f23-9878-6f11b6dc99b7 | note | i. 2 days for vertical formwork on external surfaces; and
c71b1268-c03f-59b3-b4e9-e8da2527020f | note | ii. 1 day for vertical forms on permanently hidden surfaces
deda09ef-3289-5f19-a69b-935e8d175cc6 | note | Method - Visual
b07b0626-5bd8-56d6-bcbb-2deffdb4700e | note | Frequency - Each lot
217b7d5b-fac7-5d9b-89c8-ff3e7780c4ab | note | Category - IP
01c26bef-778f-55c5-ba22-c66a9b5ae912 | note | Responsibility - Foreman, SE/PE/SPE
4271a95a-31b3-5495-9dcc-1192fe8e8bed | note | Verifying Documents - This ITP
ced078b9-88b9-556c-bf23-7e1899213566 | date | Date Completed:
42d9e600-4d03-48db-ad0b-d6b3391fbf77 | checkpoint | 5.3 - Backfilling & Pavement Restoration
15e8f8d1-0efb-53c0-a7e4-74e8d1ba3cf7 | note | Reference - 703.29
f18e608e-36f3-59e4-b715-7804f504dea1 | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
a9c308a9-14c6-5fd9-a467-648f93a870a9 | note | Method - Visual, Measure
9138c791-410b-5c65-bf25-b8ad41df6aec | note | Frequency - Each lot
db2eef07-e790-56b9-8200-7aa856280a02 | note | Category - IP
a3646dce-7eba-5d9c-99ce-5ff612d1e886 | note | Responsibility - Foreman, SE/PE/SPE
91655b81-dea6-51b1-baac-20d68a2de172 | note | Verifying Documents - This ITP
860f151a-da30-50b0-b3a5-a4476fa48ca2 | date | Date Completed:
635866f7-d7e2-403c-989e-f41dd4cc7fcd | checkpoint | 5.4 - Surface Inspection - Cracks
d20ef022-beb1-5648-8d1b-aa9ad9da631e | note | Reference - 703.3
b520dbc1-ba09-5063-bcfe-bf23c8b73966 | note | Acceptance Criteria - No cracks greater than 0.2mm.
966c76c9-c80f-535f-b268-4430b0c276f6 | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
d4e5086c-dc05-525b-bc72-97bd9b4d2271 | note | Method - Visual, Measure
494a98ca-bafe-50b7-86a6-9a8a47e517db | note | Frequency - Where applicable, each lot
dfdba2dd-da5e-5c26-b217-b2a5f862559d | note | Category - IP
05a8e394-74ca-5194-a3fe-1e473f69ce84 | note | Responsibility - SE/PE/SPE
6c680263-4874-5bd3-aa50-0da499af79fb | note | Verifying Documents - This ITP
6ea9d639-7096-57ac-842f-168ae2d1dc9c | date | Date Completed:
46b70ce2-96fd-4174-b1f1-8eded915cfa5 | checkpoint | 5.5 - Surface Inspection - Surface Finish
b5dd4913-a340-517e-89ff-31cbfae2ea7c | note | Reference - IFC Drawings, Relevant Council Drawings 703.25, 703.10 (a), AS3610 Clause 3.2
3d058cdd-189d-541b-8a48-ade2267906c3 | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
de4100a1-e7ff-5a9b-9a49-6818e04aad0f | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
02be2643-cca8-5dbe-9437-2bc967683f2d | note | ○ Class of finish:
b3054abb-aa93-59bf-8a54-563f54689dd1 | note | — Permanently hidden surfaces = Class 4
343fbc11-f69c-5428-abce-29f79dc6df93 | note | — All other surfaces = Class 3
ccc65ccc-4862-5a53-b4e1-d35978492c91 | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
7f5bc272-3836-5d47-ad93-28fb17268ea5 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
b67ba48e-9a9c-59e0-bfe0-d475c327edce | note | Method - Visual
20236e16-213a-5d04-9e3b-628fc070ab9b | note | Frequency - Each lot
5829fce4-a373-5046-a64c-1d8e15d999d9 | note | Category - IP
dee6dbe9-8017-51c0-b95f-63a237b54d52 | note | Responsibility - SE/PE/SPE
09fb3be5-ef5b-51f8-a1e7-1943360a1d0f | note | Verifying Documents - This ITP
1f0495e5-7115-5cd0-a1be-b22a08fed300 | date | Date Completed:
57c50b89-8396-4874-93e4-cc7a10398405 | checkpoint | 5.6 - Compressive Strength Test Results
e198fd13-21b5-5ac0-8c9c-1bf8d07e2e9b | note | Reference - IFC Drawings, Relevant Council Drawings 703.11 Table 703.111
4b9a07c0-048f-5633-a4ae-3b40dab13a91 | note | Acceptance Criteria - 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
f0b7647b-5e3e-52ab-a209-7d1a6fb9fae2 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
68841ef0-5a73-5885-89f2-2277fe326129 | note | ○ Attach: Compressive Strength Test Results
a690d684-3523-51e8-b920-1156ab38d80b | note | Method - Document Review
f28bea28-60ad-5716-9bc7-0c2fa8fde607 | note | Frequency - Each cylinder
a2fd1ea3-e045-59f2-b27a-e61b4731fcc3 | note | Category - IP
4aaf6f6a-3072-52e8-ad94-ff67457472f8 | note | Responsibility - SE/PE/SPE
dc5fcfd9-c0b1-5145-a864-15f907fdb793 | note | Verifying Documents - This ITP
331ef1f1-8586-5b5c-9e34-cb36d11b0e79 | date | Date Completed:
29b10373-6d2c-4bf4-9493-e51f414254e9 | checkpoint | 5.7 - As-built Survey
a0dc849b-0563-59d7-b64d-5bef169649be | note | Reference - IFC Drawings 703.15
4132ee45-046e-5aec-9387-89f19bf2eb58 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
5d977dd7-48df-5bc1-9670-b5ca983ef6f3 | note | ○ Departure from RL = ±10mm
de038b29-e069-583e-97b1-15fadd97e7d4 | note | ○ Departure from alinment = ±10mm
6b72c2ae-21c6-522a-bab7-141c36b5f2e1 | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
336743e3-b862-5689-8c1a-d1c26344d371 | note | ○ Irregularities in alignment = 5mm in 3m
999da8d0-4c8b-5bbd-a340-f54e0f31e21e | note | ○ Section dimensions = ±5mm
8bab0b2f-e2e1-5cfc-a7c1-df92566fcfc2 | note | ○ Section dimensions (less than 25mm) = ±3mm
7577baf6-86e9-5c27-9c3e-eb08c3ce56da | note | ○ Width of pavement = -5mm, +15mm
2a5a7e1e-7af3-5cbf-b7de-6c4d92fb5d5e | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
e668def9-4c29-54cd-86c0-70671181c967 | note | ○ Attach: Survey As-builts / Survey Report
b1446d3d-7c0c-5efe-9c2e-6d77302aa04c | note | Method - Document Review
2576a228-e8ed-5fd3-8836-b903bd6e1de0 | note | Frequency - Where applicable, each lot
fa9489ed-c319-512a-b769-fc68db0fd23d | note | Category - IP
0ef7c689-17ad-58f7-950d-a3da4d1895a8 | note | Responsibility - Surveyor, SE/PE/SPE
098ddbf0-b6a4-5de1-bb9b-545c2abb2edc | note | Verifying Documents - This ITP
3003ec0b-e693-5ea2-8efe-95d5f91598c7 | date | Date Completed:
b97969b3-27ac-4d99-aa9b-21af5cdeaee7 | checkpoint | 5.8 - Non-conformance Report (NCR) Closure
db467f08-9df5-52aa-a953-f414b7916f01 | note | Reference - MRPA Quality Management Plan
90a048a0-0861-5c60-b3a8-294fb6f6f210 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
07969181-a75b-54a2-9e74-f420c20582d7 | note | Method - Document Review
1e98ba3b-6074-58bf-8c82-4d1b9ee4826a | note | Frequency - Once, prior to closure of this lot / element / Work area
c2a5b268-71cc-56e7-a77c-f190b4b9f6a1 | note | Category - HP*
0cc7a38b-9481-5609-b3f7-571791611c4b | note | Responsibility - SE/PE/SPE
354af195-623e-5d37-bd2d-991e070a5ac0 | note | Verifying Documents - This ITP
5b8980f1-8a96-5138-a1af-5ca46f25c994 | date | Date Completed:
995d9e0f-1437-475f-988b-a5eea6791f1b | checkpoint | Final Inspection
b293ca9f-390f-5c4b-8785-1bbe479ed80e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
7ec06ea4-88a8-5493-836b-7061f5924cfd | textbox | Name:
0d0c1b92-cf78-54de-a6a9-8ef93bd8eb9f | textbox | Position:
62d53c28-16c3-5cc7-9823-3ec9a3aea960 | textbox | Date Completed:
a2739ada-15ad-448a-95ab-328ed2c13c7f | signoff | Sign ITP
| checklist | ITP-CIV Delineation Fence Rev 2 | itp | ITP-CIV Delineation Fence Rev 2 | a781bb97-5de0-4fd6-976a-0cfb40a28c01
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
06652cb8-7afe-56c2-8fca-803689d57ff7 | note | Document Title: ITP-CIV Delineation Fence
ef619aaf-0278-57ba-8ec6-6bac9dd53e4d | note | ITP Description: Delineation Fence
fc5b3a62-2b95-5f65-a732-75e6b2d78514 | note | Discipline (e.g. CIV/STR/RAIL): CIV
2e7c4e79-6c1f-55f3-bf48-a1ad31179e32 | note | Revision Number: 2
cd02860d-8d99-5ede-a40b-ace803a362f1 | note | Revision Date: 27/05/2024
| checkpoint | 1.1 - Non Dependent
af8789d9-f789-5fff-91d3-25dbd4bf97c4 | note | Reference - IFC Drawings
| checkpoint | 1.2 - Non Dependent
c9ca0978-ab80-5b04-b83a-f13dcc293558 | note | Reference - AS1657
| section | 2. Materials
| checkpoint | 2.1 - Concrete
8d7d68b0-a7ea-56e5-b451-044a9fac75de | note | Reference - IFC Drawings
ccdc1efe-8c04-507f-8edf-31727ceccd57 | note | Acceptance Criteria - 25 MPa concrete to be used as per IFC drawings.
b0487c99-2b07-5940-be64-bd6a174685c6 | note | Method - Document Review
ece7d9e0-2b1d-528c-896c-02b9582be942 | note | Frequency - Each Mix
dbee74c3-3c85-51ae-a154-1ac0b8dcec90 | note | Category - HP
c9a53cbe-6045-58ad-b2a1-29a5f3fffafc | note | Responsibility - SE/Site Supervisor
3297fcb1-c477-58f0-97e3-d58f456005b5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Steel components including posts, mesh and fittings
6369679b-23d1-5372-b1b6-28d9a83b2639 | note | Reference - IFC Drawings AS1657
eea58b03-95c0-58d7-a132-12e63af1458d | note | Acceptance Criteria - All Steel must comply with Australian Standards.
aaf858cc-87dd-5d69-a3e9-6a4a528cbb83 | note | ○ Steel section sizes must be checked on site.
3f25a061-ada7-56fe-b506-240353b54121 | note | ○ Steel posts to be CHS with a grade of C250
f74cd999-25ad-509e-8cbc-49bc952fffc4 | note | ○ Black PVC finish
e209ebab-4ea0-50ed-b736-3376e201bb53 | note | Method - Document review, Visual and Measure
ddd5ce1b-4e93-55f9-b913-829ab3e671dc | note | Frequency - All elements
6b3cab49-ff4e-5e31-a955-10654cb26411 | note | Category - IP
8d77a6f0-a35f-5178-b5e5-6e1a59fb29f1 | note | Responsibility - SE/Site Supervisor
06ea1e52-6da1-5df2-9c9d-abaf8964cec1 | note | Verifying Documents - Supplier Certificate of Compliance
981061af-24f3-52cb-98a4-aae2fa3e9b7b | date | Date Completed:
| section | 3. Pre-construction / Pre-installation Activities
| checkpoint | 3.1 - Survey Set-out
2963319b-dac5-5f0c-8a7a-837ad428ec20 | note | Reference - IFC Drawings
8a836d6e-1107-5d5d-b42d-caee31a9da11 | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, and fence start and end points.
818ffc72-5cf4-579e-9116-f2ba4105f033 | note | ○ Offset checked against the running edge prior to installation of posts.
21876a63-ccc1-5944-a457-bf3d13ea12f8 | note | Method - Visual and Measure
cd159edc-1caf-5be2-ae62-45349998ca03 | note | Frequency - Each element
359e94e6-7a7d-5624-9587-01e34a522f58 | note | Category - IP
4fb48da2-edbe-50ec-82eb-c2259f5c81c4 | note | Responsibility - Surveyor, SE/PE
5600f029-e2dd-54da-b27f-3c0388f3801e | note | Verifying Documents - This ITP
4b493dff-8438-574d-a489-9501b69440db | date | Date Completed:
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Excavation works
86e1c685-4c9a-517b-9699-bc420ec7efb1 | note | Reference - IFC Drawings
7e94a5bc-aea0-59fa-8813-f158b2b3d6a5 | note | Acceptance Criteria - Excavation completed by auger outside of service working limits.
5f0957a5-aec8-5331-852e-4be77a068187 | note | ○ Follow asset owners guidelines for work around their service.
3379d01d-bce1-5e00-8fa7-2dee5f914e52 | note | Method - Visual
495e8984-2722-5a14-be15-4eaf2c0675f7 | note | Frequency - Each fence footing
9593aaae-2cfb-5e0b-9ff0-837d0e14fd06 | note | Category - IP
28686d82-55af-52d8-aca1-d41dcdf90dbe | note | Responsibility - SE/Site Supervisor
1bb1d52f-1cbf-508e-8a68-bb8ad0210a82 | note | Verifying Documents - This ITP
3c6accc0-089c-5c10-b3e8-05ce3d43c0ac | date | Date Completed:
| checkpoint | 4.2 - Ground Conditions
d6bb4c7f-81bb-5f16-b48d-bc26b79dfa7e | note | Reference - IFC Drawings
97b8ec29-f794-57bd-8e04-d1664ad60d6a | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
0d8867c6-c304-56e5-9f5b-8bceac8189ea | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
6524d064-8a1d-5962-a8a8-61f2ef92cb79 | note | Method - Visual
348d8967-2d4d-5516-8ad6-baa329a92e1b | note | Frequency - Each post
edf1e94c-363f-59ee-8aba-5a19f4df5d61 | note | Category - IP
ac29039b-2c4a-59f1-b733-c7d62c4499ef | note | Responsibility - SE/Site Supervisor
a8f0aa74-0e06-5bb5-93ef-2bddfdd6fcc7 | note | Verifying Documents - This ITP
32f28da7-8cb3-51bd-83c7-10a2052e580d | date | Date Completed:
| checkpoint | 4.3 - Fence Footing
d6adfed0-34f9-5eba-a5f6-ef57dfa08ec2 | note | Reference - IFC Drawings
32903f80-7103-528a-9b61-489b45aad20c | note | Acceptance Criteria - Footing dimensions 600mm deep x 300mm diameter. Every second footing to have dimensions 1200mm deep x 300mm diameter.
c6e546cf-9cc6-55bd-b9d3-9751c3baa755 | note | ○ 25 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per VicRoads Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample.
6f504dbd-b240-5a40-84b4-364889298158 | note | Method - Measure
1bdbf506-8bf2-5be5-a87f-ac293ee19800 | note | Frequency - Each footing
90f73571-021c-5df0-8dc1-a9a4e91ff9b3 | note | Category - IP
4d40abf7-f791-5531-8444-993696123bb2 | note | Responsibility - SE/Site Supervisor
7ca0b552-6a3d-5cb0-8394-878cc631ccc4 | note | Verifying Documents - This ITP, Concrete Dockets
dca4bb07-f48a-51a9-97da-4e9758530cf3 | date | Date Completed:
| checkpoint | 4.4 - Fence Post Installation - Non-sleeved
a10e1524-6171-5066-b62a-20e33418c800 | note | Reference - IFC Drawings
9813c4da-1813-5902-b952-49914d46d511 | note | Acceptance Criteria - DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover.
e6b2cbcb-f6f8-5ec0-ae30-eff6d8de9e56 | note | Method - Measure
397a1fae-f1a0-51aa-89df-94a7174438de | note | Frequency - Each post
d95df2d1-204f-5035-85e4-163849afa84b | note | Category - IP
a90914b6-4673-52bc-b8c0-c55d124a02ea | note | Responsibility - SE/Site Supervisor
6d8b51c1-8aa7-57b5-a413-427c0b01b41d | note | Verifying Documents - This ITP
fd73e43a-a197-58bd-b9ea-dc64846149d1 | date | Date Completed:
| checkpoint | 4.5 - Chain Wire Mesh Installation
5fed803c-577d-5c1f-99b9-e7ef329b7762 | note | Reference - IFC Drawings
798534fc-a201-5e97-ac7e-dcec02ecd309 | note | Acceptance Criteria - Chain-wire mesh 1200x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications.
ab8634f6-2451-512f-aebf-a7c989c285aa | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
608ec6aa-eeb2-5743-8477-0b1e320adebc | note | Method - Visual
19f824dc-2142-5e9a-9b5a-6d67d348c3b1 | note | Frequency - Each element
1f5d4fc3-0b46-5602-a9c7-a36c2706e6f9 | note | Category - IP
27aea988-7428-569e-8305-1b1f89124136 | note | Responsibility - SE/Site Supervisor
24699c0a-cc01-58d1-899d-f693a281a246 | note | Verifying Documents - This ITP
24f22c01-d3cd-56c0-a9f1-dc9feaa7c700 | date | Date Completed:
| section | 5. Post-construction / Post-installation Activities
| checkpoint | 5.1 - As-Built Survey
d248a910-add6-5eda-ad35-fa3f1cb1381a | note | Reference - IFC Drawings
5f9ae0ba-b01d-5a04-8ede-146815ccdf3a | note | Acceptance Criteria - Posts are to be checked for verticality and ensure spacings do not exceed standards.
3be58476-e010-5eb9-8304-a31a287dc880 | note | Method - Measure
3b410450-0ffc-5602-85ec-dc676ca6b1cd | note | Frequency - Each lot
8ae32c12-cfc8-579a-b331-b15ac4207b68 | note | Category - IP
398a36ce-000e-5fcd-b9b5-3f30cc78414f | note | Responsibility - SE/Site Supervisor
f811d06f-e22f-5f8e-8934-c3aefbaebd03 | note | Verifying Documents - This ITP
74c9f943-7b90-57f9-a654-71be7da2455a | date | Date Completed:
| checkpoint | 5.2 - Non-conformance Report (NCR) Closure
0b14cd8e-3210-5061-9740-5e5495bcb2d4 | note | Reference - MRPA Quality Management Plan
f0724abd-f8a5-5ee0-98e3-e6ff531aad4d | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
1c9fa096-9db5-5293-ac9b-cc8660e81e89 | note | Method - Document Review
59d3a806-adfe-59ca-b88d-0a0df4d695c6 | note | Frequency - Once, prior to closure of this lot / element / Work area
e35149e3-38c4-5132-bbe9-d4e47e853ad5 | note | Category - HP*
87054ea5-f167-57d1-8ab8-2c1ae90ef547 | note | Responsibility - SE/PE/SPE
18775d6d-bcca-55f0-8b4a-c72b45840830 | note | Verifying Documents - This ITP
57a386ea-6982-5eaa-9607-cd0466915fa4 | date | Date Completed:
| checkpoint | Final Inspection
bfc7541d-19e5-5020-a47d-bf4a35021603 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a159e3ec-0d0a-57e3-a4bd-c171e14cbdf1 | textbox | Name:
84ac76ac-c898-5a34-91f2-95c883c0f867 | textbox | Position:
0c391f1f-8a15-53b6-b9f9-c9cc5e2f06d8 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | itp | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | c8409d6a-b18f-4202-9dde-fd86fdcd29b5
| section | 1 - Referenced Documentation
| checkpoint | Reference Documentation
aef1223d-f79a-5030-a0ce-8978a26e2e15 | note | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
5e5b7f30-2ff4-5737-95bb-f2bf73e8bb21 | note | ITP Description:Concrete Coatings (Protective &/or Decorative)
fddb0f0e-2c9f-5923-992c-f6908314ac4f | note | Discipline (e.g. CIV/STR/RAIL): STR
f1fb85f5-dfd5-5cc8-8bf9-16ce7d674548 | note | Revision Number: 2
2eb2c232-903a-5d57-a46a-319b6f656df9 | note | Revision Date: 11/12/23
eb25a5fe-7f70-5d11-a37c-b68eaa0cff21 | note | ITP created by: Mike Freeman
4b124020-3f1b-5d23-88e0-e5b5b6c0eeb0 | note | ITP approved for use by: Mike Freeman
3c967fb4-cb91-5cd8-b255-f7c819954281 | note | 1.1 VicRoads Section 685 November 2018
2463769d-94ed-598f-aea6-39fe300c463a | note | 1.2 VicRoads Section 686 November 2018
| section | 2 - Preliminaries
| checkpoint | 2.1 - Anti-graffiti System Selection
3b37663a-6459-5d89-ba9d-49871459dabb | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
9b960f94-f7cd-5851-942c-dc23a8db4026 | note | – – – – – – – – – – – – – – – – –
363b9262-d80f-5552-8bd2-f9af4d910942 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
0c033630-75b2-532e-a40a-0dfd20b44c3b | note | i. be either a film-forming or a penetrant system ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification) iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses (film-forming): WFT total = 175µm min. OR WTF per coat = 88µm min. DFT total = 100µm min. vii. adhesion to substrate (film-forming): 0.75MPa min. viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
f2f4e320-3caf-59f9-9971-22299d8f6f52 | textbox | Enter: Teambinder Material Approval number
66409958-3ffb-56e4-af62-77aaa3dded1f | note | – – – – – – – – – – – – – – – – –
8e3a3f8b-a7d0-59a9-8242-4aa7d111d8c5 | note | METHOD - Document Review
475cc402-94e9-539a-8015-67cb5d6487e2 | note | – – – – – – – – – – – – – – – – –
e26b2323-0a64-57ba-a666-8d5a539276d0 | note | FREQUENCY - Once, for each coating system, 14 days prior to application
f988b2d2-452f-5bbe-9e07-61fd931ee17d | note | – – – – – – – – – – – – – – – – –
ea8e4110-82d1-5be6-85dd-ab7c4e7f73bd | note | CATEGORY - HP
e29dbf02-4b12-5959-97ca-355805842f13 | note | – – – – – – – – – – – – – – – – –
04663cf2-da7c-5afa-aa15-24a46236805e | note | RESPONSIBILITY - Nominated Authority
ca69f714-eec9-5b3a-bf20-7b4eedc76898 | note | – – – – – – – – – – – – – – – – –
72f4a2eb-623f-51c2-aaad-30a8461828ab | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
3c5049b8-7654-5728-8d34-556819303106 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
c849a9ef-b48f-56a1-82d1-c70cd08ad81e | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
5676b11e-3486-5259-96bb-8d20d05e80ec | note | – – – – – – – – – – – – – – – – –
fe282828-9fab-5285-b268-7e2c0faa62ed | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
08560dc4-b8bf-53c7-9263-3000dae5400e | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
ee4dac17-bae5-52f9-ad6b-391844e39489 | textbox | Enter: Teambinder Material Approval number
4b7fb931-1f29-5ab8-aca6-6bf5a2c77410 | note | – – – – – – – – – – – – – – – – –
7ec21923-73a3-5b9a-9496-fc97c4c119a1 | note | METHOD - Document Review
18eaed65-4fca-571b-8250-405887fb4b90 | note | – – – – – – – – – – – – – – – – –
f77a47dd-b2b0-5271-a091-c919240b35ff | note | FREQUENCY - Once, for each coating system, 21 days prior to application
512663b3-961a-5092-85c4-325404305e27 | note | – – – – – – – – – – – – – – – – –
7a4e5c96-85af-57cf-8785-887260f55356 | note | CATEGORY - HP
b3512bac-ed34-56cf-b5ca-ea4bd5e39dec | note | – – – – – – – – – – – – – – – – –
143b9b8f-ffb2-55e5-a5f9-0edf053b0f16 | note | RESPONSIBILITY - Nominated Authority
b6b8806e-c358-5a05-ba5b-b5915283a686 | note | – – – – – – – – – – – – – – – – –
167c2aa1-ad64-54a1-8013-92cfae3f6334 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
d4f73ff4-da3c-5d10-989f-dedbec3dd1a9 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
29703d87-02ae-5978-ace7-38076058740c | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
00dee783-dce2-574a-9edb-ad1f3480d795 | note | – – – – – – – – – – – – – – – – –
d303b03b-3f05-5370-a452-450b0ae6a6de | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
5c80af5c-f7e3-5634-b701-e892ae62da95 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
74bbce89-d0f0-5bf5-bca4-7466072fa64f | textbox | Enter: Teambinder Material Approval number
88e002d2-5604-5f22-a9a8-9528f52a9db9 | note | – – – – – – – – – – – – – – – – –
c318e1b5-6532-54ad-8010-a4426ca0b9d8 | note | METHOD - Document Review
57652b29-ef8e-5b4e-af7a-536cc83577d6 | note | – – – – – – – – – – – – – – – – –
d34a0e6a-3de7-53ad-b9c3-4eca7c58dd27 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
d61855ee-594d-59d0-a077-10b9ccefc828 | note | – – – – – – – – – – – – – – – – –
23cf08f7-e5fb-513e-a540-5c564bed3001 | note | CATEGORY - HP
ee812295-112e-5abc-8225-b4238ca69e62 | note | – – – – – – – – – – – – – – – – –
6f85a848-4159-5296-a840-053b0b668d94 | note | RESPONSIBILITY - Nominated Authority
80ec1560-5c39-5899-a60a-3ed1ba000753 | note | – – – – – – – – – – – – – – – – –
ed3f5304-bcaf-57fa-9ad1-f6dcb7e0ac6a | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
4731a431-da11-5af2-a934-0d846cdfcf89 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
1e51c382-e31e-52d7-94ac-a095edf5bfbb | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
b430a396-243e-5a12-b0a1-96d2d774bb5d | note | – – – – – – – – – – – – – – – – –
f02cc46f-1d8e-5b1c-b563-64a17facbe04 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
2428d81d-17e1-5fbd-b653-6906e35ecc12 | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat ii. all coats to be compatible with each other Penetrants: iii. active ingredients: Silane = at least 95% Solid silane & silane cream = at least 80% Silane-siloxane & siloxane = not specified iv. application rates: Silane = 2 applications of 0.3L/m² min. Solid silane & silane cream = 1 application of 0.4L/m² min. Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS Film-forming coat: v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) vi. to be water or acrylic based, solvent-free vii. to be non-yellowing, colour-fast and not subject to fading viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure ix. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 200µm min. x. adhesion to substrate: 0.75MPa min. xi. able to bridge cracks up to 0.3mm wide xii. able to be re-coated within 24 hours xiii. have a minimum pot life of 1 hour xiv. compatibility to an alkaline surface xv. equivalent air thickness >150m xvi. equivalent concrete thickness >450mm xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s xviii. Water vapour equivalent air layer <4m xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
b819f756-9628-5857-84e0-8cd04a4c32ef | textbox | Enter: Teambinder Material Approval number:
681d98fd-ef2a-5c81-95b6-8ae0388b8a62 | note | – – – – – – – – – – – – – – – – –
3c4005f5-41ab-5f45-b26f-21833ce9f1dd | note | METHOD - Document Review
2c5cd687-1cc4-5065-8735-934febfdcaa3 | note | – – – – – – – – – – – – – – – – –
ab79641b-267e-548b-b107-ae552a4c8862 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
026b7cc2-0407-50cc-a624-e7ff482b3ae6 | note | – – – – – – – – – – – – – – – – –
7ab335ae-2b5d-5020-948d-ca6d976b2350 | note | CATEGORY - HP
7194619b-5ba3-591b-81b4-74a6ff5bebe2 | note | – – – – – – – – – – – – – – – – –
87ff35f7-fb7a-53ea-a2fa-d18aee498496 | note | RESPONSIBILITY - Nominated Authority
b77901c4-cb9e-594d-88b2-63a6c79cb0ef | note | – – – – – – – – – – – – – – – – –
aa9c5a55-63bf-5925-9b46-a07d2c03d98c | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
c0c0887f-82a7-5481-93bf-36326e3d4057 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Quality Documentation
f0fd61d5-0f0a-5625-bbda-201de60fe381 | note | REFERENCE - 685.05 686.04
ed78d374-6956-57f4-9097-5ec8fb0ebc76 | note | – – – – – – – – – – – – – – – – –
e638b65f-1c34-5d2a-90fd-f3b6a4b1e590 | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
bd07b42c-dabe-5c66-9203-a3ba243691b7 | textbox | Enter: Teambinder Hold Point number
83198e58-7ac5-5e24-b5fd-1d0490121190 | note | – – – – – – – – – – – – – – – – –
bcb9dfa5-55f9-5f7f-8f23-fd237e4454a1 | note | METHOD - Document Review
77ff7db6-56bf-5e77-a7ea-c5bc290e9375 | note | – – – – – – – – – – – – – – – – –
76920009-549b-5b1c-a7b6-9012165861d7 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
d89eb20a-9157-5962-b3bb-4f1c53eb9e31 | note | – – – – – – – – – – – – – – – – –
439f340a-80c0-590a-bd53-c58ab2d5e9c9 | note | CATEGORY - HP
47390118-1666-5c2d-82f9-5f9fd0245b70 | note | – – – – – – – – – – – – – – – – –
8b510f41-43e4-53de-a969-8610f1e4a239 | note | RESPONSIBILITY - Nominated Authority
c01d2bec-2d80-59db-8537-f3aab176c1a3 | note | – – – – – – – – – – – – – – – – –
a9c26ec1-e2a1-5e01-8f01-de4afebbe56a | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
cdf31fe3-0e26-5406-9ce4-bd4b58a39426 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Coating Personnel & Equipment
f74a4796-e19a-5df6-a706-4fb3c0ec0000 | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.19
4e541b55-1b50-58a8-931f-42f5be6af958 | note | – – – – – – – – – – – – – – – – –
533941b6-875d-5ff6-bf9e-d1112ce09536 | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
2c049f49-24d9-5332-9a6c-53cc7a37cc50 | note | – – – – – – – – – – – – – – – – –
6e3bc3f5-c12a-52d7-83ce-71915f1aea82 | note | METHOD - Document Review
5f0a1603-b810-56c0-a21b-2828971068dc | note | – – – – – – – – – – – – – – – – –
7c0d68f2-6459-51a4-83be-e92f2dbf6ecd | note | FREQUENCY - Once, prior to application.
5397f4d0-973b-52a3-a5d3-01237a0b48c3 | note | – – – – – – – – – – – – – – – – –
5a5d536e-afda-5ce3-80c4-684a79ac945e | note | CATEGORY - IP
602d15e4-5b20-56c4-95c8-b573c697e23c | note | – – – – – – – – – – – – – – – – –
4412e3b4-92e3-5dc1-afe7-fd13b13573c9 | note | RESPONSIBILITY - SE/PE/SPE
7006d8b6-49da-55de-8fec-b8143a781f32 | note | – – – – – – – – – – – – – – – – –
58e2e183-fd0b-5e40-b2f4-895c82b8da01 | note | VERIFYING DOCUMENTS - This ITP
7b4aa9d3-1bbc-5c68-9a9f-97cf6a64aaca | textbox | Date Completed:
| checkpoint | 2.7 - Protection of Adjacent Works & Property
e1bbc22e-a2fc-5e99-a95a-47aa0f93a134 | note | REFERENCE - 685.17 686.10
6128f646-baa5-5901-8016-ca487501b9c9 | note | – – – – – – – – – – – – – – – – –
356b00de-4bbc-5623-b2dd-fa49d2028a87 | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
46910a1c-1f5f-5530-b2e4-19f32d34519b | note | – – – – – – – – – – – – – – – – –
fb5ae482-4ee1-50e0-ab57-73f78c7b6886 | note | METHOD - Visual Document Review
9647b8c3-2a00-57f7-b0fe-e020c3d955d7 | note | – – – – – – – – – – – – – – – – –
59a11c68-3317-5d66-bc5c-e634522f65eb | note | FREQUENCY - Where applicable, 2 days prior to application.
8f8266b3-f29d-5978-a709-253964124410 | note | – – – – – – – – – – – – – – – – –
0efdc5e1-9166-5627-86c9-a74b55f3c384 | note | CATEGORY - HP
2a6b9a94-85a4-515b-b724-2ee805e637e0 | note | – – – – – – – – – – – – – – – – –
13aab145-1221-55d8-af44-a4f64468ed42 | note | RESPONSIBILITY - Nominated Authority
39996094-e0a0-5b06-9993-b3cfa2b90197 | note | – – – – – – – – – – – – – – – – –
0d27194f-7449-597d-acb5-4ef95c0d909a | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
51d3d5f6-bbcd-54c6-906d-86d895938cd5 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Minimum Concrete Curing Period
a7e34ee6-2461-5ed2-b4bc-2b2f7932069a | note | REFERENCE - 685.08 686.16
f938aabc-c330-56a8-ac0f-42ea03200fa2 | note | – – – – – – – – – – – – – – – – –
9cad5550-d2f4-5b51-be31-99020cd7c39b | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
d0f82731-bbeb-5486-b977-b54289708d4a | note | Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
31662402-a3fb-52eb-8eeb-e2122e36e08c | note | – – – – – – – – – – – – – – – – –
be15b02f-993a-53ed-9cb3-8aebcbf83e72 | note | METHOD - Visual Document Review
c0243d7a-17f2-5c83-b037-8014f34bac6d | note | – – – – – – – – – – – – – – – – –
a258f844-ef3e-5b0b-bdbc-525cbe70c388 | note | FREQUENCY - Once, prior to application.
5c48a8b4-2438-520c-a4f4-910c3c0d9a69 | note | – – – – – – – – – – – – – – – – –
c66d4c94-e2d2-5ba7-9cf8-3b9d39d0f257 | note | CATEGORY - IP
0de2e03e-56eb-5c69-a932-5925b6ee495e | note | – – – – – – – – – – – – – – – – –
e715b4ff-7c24-582a-af6a-98a290ab98fa | note | RESPONSIBILITY - SE/PE/SPE
6363067c-ad4d-5e0e-92e8-674a2b783553 | note | – – – – – – – – – – – – – – – – –
ebade83f-0bf5-5f18-b28e-dd4fcda606b7 | note | VERIFYING DOCUMENTS - This ITP
353df5d8-9684-56b8-9c3e-9878e1d134ae | textbox | Date Completed:
| checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
d3c7ff00-c1e3-56be-bceb-23bdc20da751 | note | REFERENCE - 685.11 686.13
4b49b69d-41e1-50d7-98a7-f77372f0fdef | note | – – – – – – – – – – – – – – – – –
3d39eb83-55d4-5c87-9047-abbb5dbbac3c | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
83169bdf-21ed-5e20-8342-390ef1ac3caa | note | Attach: Inspection Photographs OR
3e9d2ca9-e5f8-52bf-bd7a-b15b5f2bc496 | textbox | Enter: Teambinder Hold Point number
299b8972-3487-59cd-812c-5142901020b5 | note | – – – – – – – – – – – – – – – – –
0a3ea4f4-72bd-517a-a49c-c5f3674048ea | note | METHOD - Document Review
350c91c7-0618-58c0-a829-dfa24d9f17c3 | note | – – – – – – – – – – – – – – – – –
7356f9fd-65d9-5d91-a139-038282af2c81 | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
c4a9a30b-e875-5ba3-87c1-70618e15946c | note | – – – – – – – – – – – – – – – – –
d7923f2f-34d4-536b-8383-5bafaa7bccb1 | note | CATEGORY - HP
c024f128-508b-53c7-9fea-6c7a55f9874f | note | – – – – – – – – – – – – – – – – –
f98d9e95-5533-5905-93b7-588deba5ce3e | note | RESPONSIBILITY - Nominated Authority
1f94ba7c-3217-5d79-9f64-966b661f2e5f | note | – – – – – – – – – – – – – – – – –
1c4b87e2-af07-5d14-b1dc-b82a585ad9b2 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
bf02f5b9-7004-526a-978a-34b85ede9b9a | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Pre-application Activities
| checkpoint | 3.1 - Material Records
35101966-2bf6-5930-a65e-5deab8b4b1fc | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 686.12
96fa0e50-7aea-5871-b29f-04e44e86ea7b | note | – – – – – – – – – – – – – – – – –
d505a3d6-a154-5925-83a6-62f36cd16350 | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
ac19da55-ddc6-5dd8-b52a-1e7c1d578315 | note | Product beyond the manufacturer's shelf life shall not be used. Each product shall be traced to final location.
8625472c-8aaa-5ffc-af19-e164569bd173 | note | – – – – – – – – – – – – – – – – –
ef970107-14da-5984-9826-055d9565fa2b | note | METHOD - Visual
2dc70e52-04a6-5244-bac9-014a515d6b69 | note | – – – – – – – – – – – – – – – – –
e2ef4bbb-26c0-5f85-aaed-92da50386b58 | note | FREQUENCY - Prior to application
8e145edf-31a8-5fff-ad0d-dd754c2ce15a | note | – – – – – – – – – – – – – – – – –
3fb0d648-fd95-5f52-a066-d46d20e6a976 | note | CATEGORY - IP
a9f0be02-0356-5578-83e5-f97fc2d758cc | note | – – – – – – – – – – – – – – – – –
b052a95d-af3b-527b-8bbc-992303e616dc | note | RESPONSIBILITY - SE/PE/SPE
6c935915-428b-5c93-80a4-cf1e364b490e | note | – – – – – – – – – – – – – – – – –
df511538-bed5-56cc-9872-7a5498d5e649 | note | VERIFYING DOCUMENTS - This ITP
5ba18346-ca87-5f09-8cc5-541260b9f70f | textbox | Date Completed:
| checkpoint | 3.2 - Weather Conditions
7cc4778d-e8e2-523e-b153-d023a44845d0 | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
efd38d17-decd-5323-b370-07903aff5d00 | note | – – – – – – – – – – – – – – – – –
3da042e1-006a-5c08-a6d2-038e6f684c41 | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
4f5b5d73-89f0-576d-a9ab-fcb548d6f477 | note | i. windy conditions where spray/splatter may be generated ii. when wind-borne debris is likely to contaminate the uncured surface iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate vii. when the substrate surface is wet or damp (unless it is required for the coating system)
56eca42e-dc55-5551-b603-08a06cf8f827 | note | Weather conditions are to be recorded.
821747d3-dad1-53b4-891c-a7e3bdc0d593 | note | – – – – – – – – – – – – – – – – –
915dcfb7-bab9-5b24-b442-4d5840a8e18e | note | METHOD - Visual Measure
f7c0012d-08ce-5a82-be74-9609263309ba | note | – – – – – – – – – – – – – – – – –
ed66108d-89aa-51e7-a6ed-a85377a49bff | note | FREQUENCY - Prior to application and every 4 hours per shift
54aa65f0-c790-57b4-a6fe-7cad3abe8a5a | note | – – – – – – – – – – – – – – – – –
ffabc80a-f34c-5543-a038-b1d3f8e3d5b3 | note | CATEGORY - IP
4264e16e-932a-5095-9440-993fa47c8e95 | note | – – – – – – – – – – – – – – – – –
fad6e3e1-6be6-55c0-86dc-3904f6015c6e | note | RESPONSIBILITY - SE/PE/SPE
f272edcf-fd2f-57d8-9598-01ab60158a40 | note | – – – – – – – – – – – – – – – – –
978e1fe7-7690-5747-8707-6d1fb98c3090 | note | VERIFYING DOCUMENTS - This ITP
8d43b826-96e0-506f-984b-cf8a138a5b8b | textbox | Date Completed:
| checkpoint | 3.3 - Surface Preparation
dbca537b-852b-5b1f-be25-68cd83a5d169 | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
021d7a6d-93ec-5703-bb4d-7d9d7a9c6ecd | note | – – – – – – – – – – – – – – – – –
f7b78dab-1f16-5584-983b-d337c8b5f8b8 | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
31d3349d-b8d4-555a-97ba-903115b761e1 | note | – – – – – – – – – – – – – – – – –
bd91a4d7-37fc-529a-af42-4c5a0056023a | note | METHOD - Visual
46611d0f-d33b-5cfe-b69f-e9672af49f11 | note | – – – – – – – – – – – – – – – – –
f701f737-91d7-5137-bcc7-f48582e9204b | note | FREQUENCY - Once, prior to application.
e5707ee2-b394-5304-99a6-b3399b56db1c | note | – – – – – – – – – – – – – – – – –
77c321da-e6a9-5e88-a2ae-fcc75e31341e | note | CATEGORY - IP
7a951595-b3f1-5a96-aa8d-866ff1a263b1 | note | – – – – – – – – – – – – – – – – –
aadcfa6c-12ca-5c3d-9b55-baf81bc2e982 | note | RESPONSIBILITY - SE/PE/SPE
98e3e415-d865-53c4-b721-4501350ef4c2 | note | – – – – – – – – – – – – – – – – –
405761a2-1574-5cca-925e-f393506062cd | note | VERIFYING DOCUMENTS - This ITP
9b4cfe5a-9462-511b-880c-5b2571c064c2 | textbox | Date Completed:
| checkpoint | 3.4 - Surface Moisture Testing
10947aec-d9e7-529e-a1f9-8f491ad200a0 | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
e268f140-919b-532d-ac1b-12c12f120596 | note | – – – – – – – – – – – – – – – – –
45bee015-424d-5630-85f0-ad038b8f3884 | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
0e0607b5-6ab7-591d-a44a-517ed2abccad | note | – – – – – – – – – – – – – – – – –
3f7e1e23-5e9c-501f-886e-8a39031793ad | note | METHOD - Test
61dfdef7-3e01-54e9-a0bd-5d60877bb6c0 | note | – – – – – – – – – – – – – – – – –
292fd930-3212-5ab5-a8e9-a176142b308f | note | FREQUENCY - Immediately prior to application, test 1m²
fc059f19-2fcb-5d90-bbe6-d8635681f77d | note | – – – – – – – – – – – – – – – – –
9dba30fb-60e0-526b-ad0f-f5535ffcea94 | note | CATEGORY - IP
ecafd582-bc41-5b0b-9da7-db038bf9b36a | note | – – – – – – – – – – – – – – – – –
1292124c-a916-5829-bd44-ecf5df2611c7 | note | RESPONSIBILITY - SE/PE/SPE
0cb1c00b-7f5d-5856-8d86-186f1df20198 | note | – – – – – – – – – – – – – – – – –
7a75fa46-520d-5d2d-b610-6d9086b0c9d5 | note | VERIFYING DOCUMENTS - This ITP
039bd177-2773-5d2c-94db-ade4ff9ba398 | textbox | Date Completed:
| section | 4 - Application Activities
| checkpoint | 4.1 - Method of Application
399bf443-9ff3-5256-9969-d1fe2e050f13 | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
ccfbff13-525b-55b5-b8b1-7ccd7d383d0e | note | – – – – – – – – – – – – – – – – –
764d7985-4a46-57f9-bb06-3adf3f9ad91e | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
e8cb1c13-4b54-5f91-a1e3-42ce359bdc3c | note | Attach: Coating Application Record
a5be0b39-04b7-5275-8975-e4e50b518067 | note | – – – – – – – – – – – – – – – – –
310954af-1f13-586e-b35c-9594363dfd2a | note | METHOD - Visual Measure
15a7e271-89ef-5ae9-8c7e-e5ad3bd65607 | note | – – – – – – – – – – – – – – – – –
ef559202-69e9-5b9f-9bd4-3eec456a6fe0 | note | FREQUENCY - Each coat
ca0a3cc1-bd8d-546c-a61f-f2f348007cd9 | note | – – – – – – – – – – – – – – – – –
502aaf74-14f4-552b-884f-44f075939d1b | note | CATEGORY - IP
61e537e2-236b-5422-b3f6-7b751039eaad | note | – – – – – – – – – – – – – – – – –
6cadd845-43e8-537f-9abd-5c7384f5b449 | note | RESPONSIBILITY - SE/PE/SPE
8fa40dbb-0a25-5062-b970-f814be16c355 | note | – – – – – – – – – – – – – – – – –
87f219c0-6aee-52cf-a100-c8139dbd1a36 | note | VERIFYING DOCUMENTS - This ITP
0dbfdcac-1668-56ea-9383-913e5d5f91f9 | textbox | Date Completed:
| checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
014939c2-2ddd-5d1a-9bfa-a81fc78b9a3b | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
1cec9b12-e83e-5ea8-92de-ebb5d58adae2 | note | – – – – – – – – – – – – – – – – –
020b17c4-8611-5699-838b-9225c721c305 | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
05a18714-4533-5d42-a3a5-3a7c3668df2a | note | Attach: WFT Test Results
69a4da54-0614-5fbf-ba2f-e2f5955fa409 | note | – – – – – – – – – – – – – – – – –
cba610eb-d119-5ad6-80b1-7349563b68ee | note | METHOD - Test
9c7740a4-eb70-590b-aed1-d4c7de5c4369 | note | – – – – – – – – – – – – – – – – –
519193b0-8f36-5acb-9e97-06eb58638933 | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
0e984dba-baf9-5281-86d7-4b1a890a1a8a | note | – – – – – – – – – – – – – – – – –
272688dd-993e-5dfd-9b01-a41fc9a26661 | note | CATEGORY - IP
672f64a3-a31f-52ca-bbb9-7cb080d415c9 | note | – – – – – – – – – – – – – – – – –
e64287c3-5bb4-5f60-82d8-7bb7e5f515b2 | note | RESPONSIBILITY - SE/PE/SPE
f59b4af2-7a77-5959-b646-d3dee2a32c62 | note | – – – – – – – – – – – – – – – – –
509b4b02-fad2-5908-b302-a698718ccdfb | note | VERIFYING DOCUMENTS - This ITP
83cf7d10-7536-5fd8-8056-7627b372e483 | textbox | Date Completed:
| checkpoint | 4.3 - Inspection & Defect Identification
d948b8fa-9e0b-5ced-ade2-5e2c9e2a8dad | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
2b9edd08-65d6-5665-9baa-d2291f279195 | note | – – – – – – – – – – – – – – – – –
fd139cdf-8528-5e4c-9fbf-06be0ec932d5 | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
79783ccb-eaa3-541e-985b-f2890653dcfc | note | – – – – – – – – – – – – – – – – –
9aa78637-991a-5740-9261-13facf27dbf8 | note | METHOD - Visual
844d38ba-23bd-5e1b-8145-7df20db1e916 | note | – – – – – – – – – – – – – – – – –
121e75df-e351-5ac0-a705-cf7fff4a0fdc | note | FREQUENCY - After each coat
e8b4f7c1-3c7f-5296-ba67-d71319c0cfe3 | note | – – – – – – – – – – – – – – – – –
cbea51f2-4fc4-5efd-a774-84ee67d1f1ee | note | CATEGORY - IP
5c936da4-f722-576e-9736-ea1ed48e04a6 | note | – – – – – – – – – – – – – – – – –
f242d90d-6cf5-5d15-80df-5edfcff0ede4 | note | RESPONSIBILITY - SE/PE/SPE
922974f5-2360-5a95-b556-2e3f3e589153 | note | – – – – – – – – – – – – – – – – –
f458c7a2-8275-53b8-b1de-b7b0b49179fd | note | VERIFYING DOCUMENTS - This ITP
b3bb8a17-fb90-53f7-a632-43f301a62a4c | textbox | Date Completed:
| checkpoint | 4.4 - Drying and Curing
96676d45-d6d7-5812-ac2f-de8be70e59ba | note | REFERENCE - Coating System TDS 685.17 686.09
3ace204d-646c-5b50-85ef-0a627d292691 | note | – – – – – – – – – – – – – – – – –
b25c651c-12eb-53bf-8ee7-e456bc8e2589 | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
1c7235cf-e0d5-5c76-ad9a-05b2e2ccd9b0 | note | – – – – – – – – – – – – – – – – –
580139d7-bc2d-59aa-8a31-841591ad53f7 | note | METHOD - Visual
5d9403cb-e8fc-5968-b76a-fc3dd86d26bc | note | – – – – – – – – – – – – – – – – –
9f5d8955-d688-5b8a-839d-d2dccb456f0d | note | FREQUENCY - After each coat
8dd675ab-437c-5d22-ad68-51dde42f32e7 | note | – – – – – – – – – – – – – – – – –
be2ce64f-a5ec-5712-afc3-ca28ab43a03c | note | CATEGORY - IP
74b34841-a5b4-5d66-a379-eb72141eabb1 | note | – – – – – – – – – – – – – – – – –
a866f9a1-df98-5cbd-95bb-43cc51fd6442 | note | RESPONSIBILITY - SE/PE/SPE
f9e533da-f8f1-510e-abf2-a146b66087af | note | – – – – – – – – – – – – – – – – –
f8bae051-226f-55b8-9bc0-4a17995ecbdb | note | VERIFYING DOCUMENTS - This ITP
f1c4f71e-c08c-5f56-836e-b6ba6ab4e969 | textbox | Date Completed:
| section | 5 - Post-application Activities
| checkpoint | 5.1 - Clean-up & Waste Disposal
81a8aceb-21ef-5463-aac9-6810e5294ccc | note | REFERENCE - 685.09 (c) 686.10
aee9e6fd-a940-58ba-b444-85279a88813d | note | – – – – – – – – – – – – – – – – –
77d70ec7-7185-56e3-89f1-0ab432469070 | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
a34e1175-a1cc-547d-951b-87755042dca0 | note | – – – – – – – – – – – – – – – – –
41e37150-1a3e-59d1-9fcd-7c82cd0543da | note | METHOD - Visual
8df81a20-5fdc-5c36-a117-d7f311698fe0 | note | – – – – – – – – – – – – – – – – –
d30978ef-d8a2-517c-a439-51662c0ae4c9 | note | FREQUENCY - At completion of Works
17dc4159-e570-5a17-98f0-2ee05e8fa3d1 | note | – – – – – – – – – – – – – – – – –
125dc561-1e3b-5037-b58c-754f0df9cf0d | note | CATEGORY - IP
98136a13-8f04-5aef-b254-e54bf50f5df0 | note | – – – – – – – – – – – – – – – – –
1527af5f-67ef-518f-9c96-d122408abae1 | note | RESPONSIBILITY - SE/PE/SPE
2ce445c1-5047-5b95-8f3f-136248797825 | note | – – – – – – – – – – – – – – – – –
fae1dd11-81bd-5e4e-b1d0-bb354caf8b89 | note | VERIFYING DOCUMENTS - This ITP
0668478d-f306-51f2-9825-4963318d7ecd | textbox | Date Completed:
| checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
af8f8292-4f9c-5415-b7f6-5ee1984596ce | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
8fb30f52-fb28-5cce-b2b7-ed3c14eb843f | note | – – – – – – – – – – – – – – – – –
f6875188-fea9-511b-99fc-ccdc212520d1 | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
80064406-a67c-5075-9e39-95335112bab4 | note | No more than 15% of the readings shall be less than 90% of the required thickness.
44f2c405-695a-5d9d-b2e2-02f0c3b61097 | note | Attach: DFT Test Results
b6e2334e-fc3e-596b-9243-ec50e91f0c8e | note | – – – – – – – – – – – – – – – – –
7a2a1713-820c-5241-a545-7f981ae2aaa5 | note | METHOD - Test
a06ebf61-8307-5cd3-9c22-5a6eade39d98 | note | – – – – – – – – – – – – – – – – –
bfa0d18c-32b5-5052-bf7a-d38c08160e0e | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
d7291d2c-a1f7-570d-9b3a-fa63f2b53cbc | note | – – – – – – – – – – – – – – – – –
d4885f7c-13f7-5be8-aace-e07e9a861452 | note | CATEGORY - IP
3d20e145-7b99-5630-8c81-e8a2de3eacea | note | – – – – – – – – – – – – – – – – –
ed0d0402-46bf-5905-949d-b4ab75693179 | note | RESPONSIBILITY - SE/PE/SPE
c5dfe5a3-253c-5571-b2bd-b554b17f905f | note | – – – – – – – – – – – – – – – – –
49a648f9-2081-5443-ade1-bd735a33f6fa | note | VERIFYING DOCUMENTS - This ITP
b052b3a5-a09c-50a8-b426-84b3f2d25232 | textbox | Date Completed:
| checkpoint | 5.3 - Adhesion Bond Strength Testing
3a98e14d-3d79-5786-8900-a4b1a5bb6444 | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
56bdbd80-6208-539f-ae30-3778d6293213 | note | – – – – – – – – – – – – – – – – –
3e330636-f68c-54ed-b52d-5033c6b19816 | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
2c2f1dba-d1f0-5f49-b979-b65e98af6c20 | note | Attach: Adhesive Bond Strength Testing Results
1d14b847-ebc3-5175-a10d-10c66af60dab | note | – – – – – – – – – – – – – – – – –
d21bf8ef-0c41-54c0-b0aa-967f2acf3016 | note | METHOD - Test
b56f003d-eb48-5e34-86b3-fed06aa1d548 | note | – – – – – – – – – – – – – – – – –
903dc1d4-409e-5198-b65d-6409d57658ff | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
a91635e5-78fd-570e-aebb-d2c320ca2415 | note | – – – – – – – – – – – – – – – – –
2f20fcc6-bf06-5b33-a715-964c107a07c1 | note | CATEGORY - IP
8bdae910-5d0f-5429-b093-d879051d7212 | note | – – – – – – – – – – – – – – – – –
506b4453-8cca-53e9-b59e-b1ecb3d22524 | note | RESPONSIBILITY - SE/PE/SPE
9e7f8b01-8a44-573c-b159-cf7a8ffe50ce | note | – – – – – – – – – – – – – – – – –
f7f68b6b-f8a4-5590-be2b-797f5c8e7425 | note | VERIFYING DOCUMENTS - This ITP
93b4c548-f38d-5527-b7fa-d711214305c5 | textbox | Date Completed:
| checkpoint | 5.4 - Penetration Depth Testing
966fcf75-813b-54be-885a-7adc7beeece4 | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
b4afeffa-0838-5c3e-938d-d4dd20eecc45 | note | – – – – – – – – – – – – – – – – –
08d1ce56-c2cd-508d-8059-e969e91e0268 | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
6bd607e4-ea79-576e-9261-538d67501763 | note | Attach: Penetration Depth Testing Results
fea6656f-ae8c-5047-96ad-dd9cab32a7cc | note | – – – – – – – – – – – – – – – – –
c3d68b6d-a40e-5904-9037-a6fa1b557285 | note | METHOD - Test
69365936-e10d-5b1a-b723-366836e7d93d | note | – – – – – – – – – – – – – – – – –
df716e7d-9af7-5bb4-8284-d3f9586a395d | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
f8d81bdc-0ec8-5982-ad47-767415f77ee8 | note | – – – – – – – – – – – – – – – – –
d9f0c93e-bc2c-5134-be1b-df83d0e945a6 | note | CATEGORY - IP
878c7adb-ca2f-54bb-bf6c-a80dc405c8b8 | note | – – – – – – – – – – – – – – – – –
de77f407-c61c-5faa-a74b-c0f1e33e5082 | note | RESPONSIBILITY - SE/PE/SPE
bee967e1-b66d-5dc3-945b-05af3dcf857e | note | – – – – – – – – – – – – – – – – –
a14b9b8c-aae7-5761-851f-fa7125089393 | note | VERIFYING DOCUMENTS - This ITP
30860773-134d-5ca4-bbf8-1518a364dac1 | textbox | Date Completed:
| checkpoint | 5.5 - Non-conforming Coatings
a96c597c-cc2b-58ac-946d-bdc901d19c63 | note | REFERENCE - 685.14 686.17
e9491994-de9c-58e1-af6d-ba0be452d4fe | note | – – – – – – – – – – – – – – – – –
b40106ca-c659-524f-9174-1830843e7a23 | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
f79bda69-5ff3-5dee-a5b8-49167bab3ef0 | note | – – – – – – – – – – – – – – – – –
5b74aaa9-caa0-5b3e-9eb5-b984ee6e7439 | note | METHOD - Visual
762cdfe3-1a0d-503c-961f-bd841551167d | note | – – – – – – – – – – – – – – – – –
f3426c77-1812-58d0-94ed-6c2eb0a5cb32 | note | FREQUENCY - Where required
a5b2628c-21fb-54d2-bdfe-0b1800522f0b | note | – – – – – – – – – – – – – – – – –
a4e37670-4145-56a0-9d02-5d55158bf32a | note | CATEGORY - IP
b40dcc41-8c5f-53dc-af04-0779221ad7cb | note | – – – – – – – – – – – – – – – – –
712b8c87-6e2e-55b3-a0c0-80637b73bb15 | note | RESPONSIBILITY - SE/PE/SPE
bb39dfb6-a51d-5629-ac0d-ca902d9732ef | note | – – – – – – – – – – – – – – – – –
738bfd51-664e-5657-b83d-2ae129fe18bc | note | VERIFYING DOCUMENTS - This ITP
0f3419a3-fe68-512d-840d-b2335c11d9d1 | textbox | Date Completed:
| checkpoint | 5.6 - Coating Application Guarantee
511d3eed-83fa-5e44-9d25-fcd3d71a6eb8 | note | REFERENCE - 685.06 (b) 686.05 (a)
975e5b0e-5b5d-5d7e-81cc-d4750567cd1f | note | – – – – – – – – – – – – – – – – –
3d6a661c-3237-578f-a1df-f61de50e5f30 | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
bbba7dfe-2b6f-566d-82a6-90dd45177011 | note | Attach: Coating Application Guarantee
1e845caa-52a6-5806-a53b-9079d0a4c14d | note | – – – – – – – – – – – – – – – – –
abdc29bb-7b55-5951-aed7-11b6e863791e | note | METHOD - Document Review
7030b621-d228-560e-8b3a-0cf76b1d1848 | note | – – – – – – – – – – – – – – – – –
b482f02a-378c-5d85-be78-4f04ddb173f3 | note | FREQUENCY - At completion of Works
4fc87bfd-a5b9-5052-ab58-454966e49846 | note | – – – – – – – – – – – – – – – – –
39683206-c572-53e7-baa6-7244ceebfdbf | note | CATEGORY - SP
e4bdfdc8-5135-50a5-8d5a-29f21e404e4f | note | – – – – – – – – – – – – – – – – –
a84186db-39d5-5572-ad64-f1313f293e2c | note | RESPONSIBILITY - SE/PE/SPE
4ccedf4b-803d-5dd8-ba96-f5dcad60cab5 | note | – – – – – – – – – – – – – – – – –
8a3f1fda-30ea-539a-8ba0-452aeb3cc20e | note | VERIFYING DOCUMENTS - This ITP
86f62236-9304-5320-9485-1c065b178d1c | textbox | Date Completed:
| checkpoint | 5.7 - Repair to Damaged Coating
8e97eeee-0356-5c47-8ddd-50644ab3e6a2 | note | REFERENCE - 686.17
c573d9d0-a8a3-51ef-83ce-5de3fc6e85bb | note | – – – – – – – – – – – – – – – – –
252d1b5c-40c4-53b8-8bf0-114bddcc67bc | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
f10f4c1a-eb16-5889-b5ab-8929184f0006 | note | – – – – – – – – – – – – – – – – –
406a2312-37ab-52a3-a3ee-75ee9f0636b5 | note | METHOD - Visual
1dd4ff43-f5de-598f-a1d5-a5e33152c6dd | note | – – – – – – – – – – – – – – – – –
138cb7c2-14d9-5d4b-912d-c8c3176a1f65 | note | FREQUENCY - Where required
08ee66d1-f41e-56dd-ad05-eada81f7af72 | note | – – – – – – – – – – – – – – – – –
28e1cde7-4674-558f-8ed4-03cb88886a22 | note | CATEGORY - IP
d3141d50-7ab2-52b5-8f01-7bb613c48a9e | note | – – – – – – – – – – – – – – – – –
02c87db3-9384-52e5-b421-e65cc7302bb2 | note | RESPONSIBILITY - SE/PE/SPE
1669dda1-7b10-54d2-b127-2c296ad7cfff | note | – – – – – – – – – – – – – – – – –
e874a2dc-067b-56e5-bf4d-4affae44fbe9 | note | VERIFYING DOCUMENTS - This ITP
f345431c-c758-52c1-aeb7-399cbcd7f524 | textbox | Date Completed:
| checkpoint | 5.8 - Non-conformance Report (NCR) Closure
6ff28cd4-3162-53cc-a202-95b7540ffcb8 | note | REFERENCE - MRPA Quality Management Plan
cf625f1b-0df7-5c61-a53d-d72008ff843c | note | – – – – – – – – – – – – – – – – –
7a7a56a2-98a8-5449-99f7-177a579a8586 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
37b8ad66-81f3-5660-a510-d0ae0562c2fd | note | – – – – – – – – – – – – – – – – –
a7a23ca3-e4d1-562a-a302-1d13cdf46a1c | note | METHOD - Document Review
50d19fd4-4849-574b-b0de-cac105f1ebb7 | note | – – – – – – – – – – – – – – – – –
5451cb6d-1b46-508e-80ae-4214e7d59d12 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
98289b5b-efcb-5fc0-94fb-5c5a6b94f6ac | note | – – – – – – – – – – – – – – – – –
cc005129-4bc9-5715-a369-abdf5a00e671 | note | CATEGORY - HP*
c561d3f3-c067-5d24-a698-37b4f51ad470 | note | – – – – – – – – – – – – – – – – –
5beb6ef1-4c0a-5e63-a31f-55bec922a7d7 | note | RESPONSIBILITY - SE/PE/SPE
33822834-08fa-5fb2-b573-5bf85f66292a | note | – – – – – – – – – – – – – – – – –
0f74fcef-9de8-5167-9bef-962352ce1d4c | note | VERIFYING DOCUMENTS - This ITP
62c50dde-34ed-546a-b02b-0b312b75f346 | textbox | Date Completed:
| checkpoint | Final Inspection
5f51247b-dce1-5fcd-b0d7-dd2b97fa730d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
de947f70-a5f3-5095-b980-1e28abf6d9ad | textbox | Name:
6d05b64a-a81e-5186-a0e9-c5b035c1c512 | textbox | Position:
5c664c2b-5c6a-5877-9405-12b16410d981 | date | Date Completed:
| signoff | Sign ITP
13afebc1-3aab-45e8-9f5f-a14ce550f22c | checklist | OHLE-ITP-CAT5-ITP-OHLE BWA INSTALLATION Rev 1 | itp | OHLE-ITP-CAT5-ITP-OHLE BWA INSTALLATION | 765b7063-b892-481a-9382-75bc79bee6b5
bb085b07-675c-4a2b-896e-01d0fe7a84cb | section | 1. Referenced Documentation
7d073790-ed7a-4d5d-a8b1-62b979d72990 | checkpoint-no-value | Referenced Documentation
e2a5d820-610d-5287-a226-2560b231a4b6 | note | Document Title: OHLE-ITP-CAT5-ITP-OHLE BWA INSTALLATION
2fbc814b-3c78-5b6c-a8c8-89b2862e3fbd | note | ITP Description: OHLE BWA
78a5e6a8-fc98-54b7-9c9f-3b937e8ae35f | note | Discipline (e.g. CIV/STR/RAIL): OHLE
4ba6d23a-4dcf-58d0-bda5-69556e7e77ca | note | Revision Number: 1
07545103-7f00-5b8a-989c-0586222ca003 | note | Revision Date: 9/05/2023
b9c811dc-5255-5727-9df8-032150641c39 | note | ITP created by: Richard Johnson
212933fe-4ee1-5afa-9efe-638c9de0910e | note | ITP approved for use by: Andrew Pitts
ad572378-efdb-5fb2-a4e2-91afda1be35e | note | 1.1 - Overhead Line Electrification
9f3dc570-148f-5289-ba6b-e05537d9a327 | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
d9d40bcf-6a78-5a27-9cd8-768a4269bbb8 | note | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
cf2cc577-8f57-5eea-9856-5ccf1d3abf42 | note | Reference - VRIOGS 001 AS 4100
810d0ae2-16bf-5bd6-af51-f87561a06e77 | note | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
4b2a6788-6fe8-5a77-8735-d5385b31b9f7 | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
67585af3-f32a-42ff-b0b6-370ea05e39d1 | section | 2. Preliminaries - Materials
ff12d588-0246-4b7d-948b-27c068378abe | checkpoint | 2.1 - Procure materials. What materials? Has to be specific, one line item for each material. Materials to be in accordance with IFC design drawings and relevant MTM Standards.
e175c365-d4ea-5379-a991-0d347421c9dd | note | Reference - Relevant MTM Standards and AS, etc
dd85e1c5-0760-58dc-9ae1-c829a7195aad | note | Acceptance Criteria - To ensure materials are manufactured/fabricated as per IFC design drawings/MTM design range.
4d718df4-da6c-5cf2-b4b0-def48b260f41 | note | ○ Material Approval Form to be raised in TB prior to use on site.
05e24f21-e9a0-5ab5-b328-30ccd28ddfa9 | note | Method - Document Review
888e642f-91bb-5ba4-96ed-8b8222c2102d | note | Frequency - Once for each supplier, prior to works start
2ae90c27-2914-5f25-8a5c-801b03ed1e0f | note | Category - HP
262fb72a-94bc-5e5e-ad03-98a3c09ba8e4 | note | Responsibility - MRPA
aa680a9c-f77c-5b23-ae48-415189fa2802 | note | Responsible person - MRPA
bb6a4417-5ee7-580e-888a-47d13a3133c6 | note | Verifying Documents - This ITP Signed Off
d93f863d-bf02-5660-ac75-7471b8efe83d | date | Date Completed:
b9a9f8b2-396e-4c73-8ac9-dda35e050825 | signoff | AUTHORITY HOLDPOINT
9f459520-deb4-4a15-bd72-834080344493 | checkpoint | 2.2 - Materials delivered/collected to stores/Site.
701b351b-39a6-525e-8ef5-84f15c6f4f93 | note | Reference - Contractor - Site Material Control procedure.
30737f18-7d8d-581a-a420-a552c43a95f3 | note | ○ Cat5 Material received -Brunt and Camms Tracking sheet
474aa4e6-e68a-53e0-a59d-7e98dde54265 | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
57b2f05b-eadd-53ca-bd05-8f0e6ff5d9af | note | ○ Certificates of Conformity provided by MRPA
7b11c8af-4b6d-5b23-918a-db7df1ae9b6f | note | Method - Document Review
3d954afa-154c-53ed-beb2-aa17f50d52af | note | Frequency - Once for each supplier, prior to works start
5a4069a4-9ad8-51c6-a596-36bbae8c850e | note | Category - IP
a3492f5a-27ae-5a5e-9715-3cb3a1efb3e8 | note | Responsibility - MRPA Issue, CAT5 Receive
1f3d3fb2-3970-5dee-818a-f5fc0b587880 | note | Responsible person - MRPA
702ecacc-5ae6-5850-8520-5f5ec2cc3584 | note | Verifying Documents - This ITP Signed Off
b102b9f6-67d2-54c4-95b9-907b7fabc1b1 | date | Date Completed:
a75aa3b6-204d-4dcf-be60-d7abadba62be | section | 3. Preliminaries - Procedures & Documentation
554d3bad-b27d-4e90-b36d-b977b7e741a5 | checkpoint | 3.1 - Produce Work Package Plan
4d97a8b2-6f49-5e5a-8bcc-fbf165dacecf | note | Reference - Work Package Plan WAP_BR_184
300b6c5d-ed85-5a0a-ba25-314ee8bb7f5c | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
95d2ecba-d30c-5a6a-844f-8c6bd03b0447 | note | Method - Document Review
b526085f-ea29-5bc1-98e5-f91ffb35724f | note | Frequency - Prior to Works Start, TBC in accordance with MTM Standards
968a6e24-d7f4-5eb9-9c50-1d9979aaa477 | note | Category - HP
83d1c55b-3d5d-5b7e-99e1-5d3781a373b6 | note | Responsibility - MRPA/CAT5
a208c576-bf9c-5be3-a911-a3b1b09afb51 | note | Responsible person - MRPA/CAT5 Engineer
9e5bcc6e-d964-524f-809d-711e47609e92 | note | Verifying Documents - This ITP Signed Off
967d1e7f-1b0d-5cd6-974d-b9c0c2807c4e | date | Date Completed:
0a714254-ce4f-4101-a93b-68eb036d507a | signoff | AUTHORITY HOLDPOINT
93e456e7-c904-4be3-b922-f6c08cc8cf65 | section | 4. Pre-construction Activities
fc66b44e-44b8-4647-bb34-e7cf79d200e6 | checkpoint | 4.1 - Approval of IFC drawings
c4f820d3-9400-5001-a65f-e7a9b13c16c7 | note | Reference - Contractor Design Management procedure.
579ff3e3-2ab6-5e1b-9b4a-166a89b372b4 | textbox | Enter document no. here
317b0272-1c2d-598d-9ccc-79394a88ae3b | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
8e3803c4-df0b-5ffb-9f84-e7f42f6fd51e | note | Method - Document/Drawings Review
3447cc78-4862-58d4-a9f0-36940084cc8d | note | Frequency - Prior to Works and at regular intervals. TBC in accordance with MTM Standards.
03cd442c-b15d-55bb-b95f-68ce4635a699 | note | Category - HP
7add3a8b-16a8-5a55-8854-6d630de2bf09 | note | Responsibility - MRPA/CAT5
bde42ddb-936e-5178-bb89-24741584fae8 | note | Responsible person - MRPA/CAT5 Engineer
a589ce8d-5880-50e9-8855-92395cb01ebe | note | Verifying Documents - This ITP Signed Off
6972df20-f79d-570b-bbf0-0a309e5e82a7 | date | Date Completed:
1451048b-8b5d-4347-8fb1-d5e626a101cf | signoff | AUTHORITY HOLDPOINT
d7e942eb-5a60-4c75-8459-15f6f752f7cf | checkpoint | 4.2 - Lifting operations
fd22d494-70f7-5485-a5a7-57f6494e7d11 | note | Reference - Contractor - Permit to Lift Control procedure.
4914bc19-4962-50e2-af71-0267233e8030 | note | ○ Contractor - Site Material Control
a8cecb03-d02e-5224-84ae-7e0436abc557 | note | ○ Cat5 -LP-01
a95f32a3-1ed0-5efd-87a4-2b5537d76066 | note | Acceptance Criteria - Ensure all plant and equipment are operating within their SWL limits.
092ee917-827a-565e-b35a-595ab89137fb | note | ○ Permit to lift to be generated and signed off by Appointed Person.
656b53ad-134b-5394-a2d3-71e8126eac55 | note | Method - Visual, Document Review
7ab45d23-c3c2-5690-b452-8f6be3db4de6 | note | Frequency - Each plant and equipment prior to works start. TBC in accordance with MTM Standards.
5353e7c2-a841-556c-80d2-0fbe8f23daba | note | Category - HP
2d9d9fb8-51a7-58a6-9b59-e4e22aed9196 | note | Responsibility - MRPA/CAT5
a648717b-8b16-58aa-a7a4-f4b38ebc899f | note | Responsible person - MRPA/CAT5 Engineer
fb7608ff-9967-5d2e-9778-833a40383c2f | note | Verifying Documents - This ITP Signed Off
0cfc11b0-9d1f-5b49-8fc4-c10b131185e9 | date | Date Completed:
a4c558b3-d81a-4311-8763-997ffdb81832 | signoff | AUTHORITY HOLDPOINT
d4c41cc0-4b9b-4faf-a51c-7d618caa6a85 | checkpoint | 4.3 - Task Specific Permits
9915e58a-9e9c-54c1-ac30-a0d44dedde67 | note | Reference - Working at height permit.
6077ab8f-b00b-562a-9028-bdd80ff8d215 | note | ○ Hot works Permit, Permit to dig.
b3a33396-56fd-5f38-8746-6e2bade9f04d | note | ○ BWA Installation methodology
bcf0cedc-a4f9-5613-83be-a11f93017443 | note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
b4c5feca-636a-5597-9093-00332d37add1 | note | ○ Task Permits to be generated and signed off by appointed person.
b59d2c9d-d9ec-54ca-94b3-574e348014cf | note | ○ Task specific documents - MTM to issue permit to enter/Isolation permits etc.
50b7f172-836c-55dc-b5eb-79a4c9d8c812 | note | Method - Visual, Document Review
ce9ee2e6-fb7d-50cd-9b06-6ce909793b6c | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards.
3610831f-f12b-5938-85ee-b9ca79215458 | note | Category - IP
bd5145fd-8a5e-5e3b-81fd-581b41af8434 | note | Responsibility - CAT5/MRPA
b1743b39-688f-59a8-b112-55624fa5a0c1 | note | Responsible person - MRPA/CAT5 Engineer
d4ac4729-df02-5e13-ad84-f3d861459b7f | note | Verifying Documents - This ITP Signed Off
e9826f6d-aaca-52f8-83d1-2ad1cd4b93b8 | date | Date Completed:
de47e10b-e066-43b8-a658-3122bcb22776 | checkpoint | 4.4 - Pre-Installation check
c9148d86-223c-5590-a388-c5561bd6c554 | note | Reference - IFC wiring layouts, IFC cross sections and BOQ.
d33ccf16-d92d-5a7d-983f-7d34df8d452c | note | ○ Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
532115e8-d1b0-57f4-b09e-7d26abd56f23 | note | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
2836ef1d-aba2-5c25-a8b2-8eb3b38bb756 | note | Method - Visual, Document Review
61452c08-35d3-5d8b-af48-92f944b75420 | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards.
e0edeb17-cb85-5ed8-85a2-893671cff950 | note | Category - IP
fc309c45-379f-51a1-8482-aea5aedd53fb | note | Responsibility - CAT5/MRPA
6bfaee04-de11-5228-b775-0fba9e084575 | note | Responsible person - MRPA/CAT5 Engineer
b6f5f247-be72-55d8-95fd-d92b38947dc8 | note | Verifying Documents - This ITP Signed Off
11a20698-34dc-59e9-8815-340b37be943f | date | Date Completed:
840db8b4-ec81-49cf-b2b5-dbf6aaa3ddd9 | section | 5. Construction Activities
b88c43c1-fb8b-4888-a135-49db237b1972 | checkpoint | 5.1 - Install BWA at correct location
74fb1f33-ca32-518a-b79e-3fa4ba8448a6 | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
c83d7474-94b2-5007-bac0-6232290dffe3 | note | Acceptance Criteria - Ensure that the BWA is set correctly as per IFC design drawing/MTM design range, fit for the passage of trains.
422d116c-2952-58a4-935a-c933cf853cb0 | note | Method - Measure, Visual
ffdfae3e-655f-5a47-bb9c-1e6263e86f3d | note | Frequency - Each OHLE Structure
6adf1ba1-7dd1-5667-b9c5-8167b2e63bf9 | note | Category - IP
8193335c-ce7b-59bb-a287-7b7eac63d9aa | note | Responsibility - CAT5/MRPA
a1c23aa9-6a95-57cf-832c-1497a6d197d3 | note | Responsible person - MRPA/CAT5 Engineer
2074470e-ab71-5a83-bd3c-d30b05541b2b | note | Verifying Documents - This ITP Signed Off
4f4ebfab-10e6-51a6-8a18-d0b81e9b8950 | date | Date Completed:
6c8bdaab-0458-4996-b478-a65b7fcd8c8f | checkpoint | 5.2 - Check all fittings are secure.
4108d596-72c5-5655-ba45-687b35d330f3 | note | Reference - Manufacturers torque settings
99687968-3739-5e8e-8625-b9b3b03d564b | note | Acceptance Criteria - Ensure that the BWA is set correctly and fit for the passage of trains as per IFC design drawing/MTM design range. Engineer checking to ensure that the equipment is installed correctly to IFC design drawing/MTM design range.
306e676c-966c-5966-8cb6-f86746db7333 | note | Method - Measure, Visual
07b73f73-9b27-5fbd-b47c-468f0d3edabf | note | Frequency - Each OHLE BWA structure
319080b6-b9c9-5981-bd4d-85db34a0d66e | note | Category - IP
767a6d22-bd7f-53c6-82e2-223884a478f8 | note | Responsibility - CAT5/MRPA
09369aba-a529-52d0-9c6c-6c939a31e2d6 | note | Responsible person - MRPA/CAT5 Engineer
6a9f241e-2485-550b-9cc2-3b6ce90a66e0 | note | Verifying Documents - This ITP Signed Off
f9ec9658-e87e-51cb-b0dc-627f84a3baad | date | Date Completed:
8b21418c-4512-4f3d-a175-beed60acf2ae | checkpoint | 5.3 - Installation of wire supports at the correct height and stagger.
c2424afa-e801-5400-a969-2b6ad9f91fb1 | note | Reference - Install as per design drawings.
4936ce1d-5c8f-50a2-b9de-b61559173be3 | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
969e6ec0-ed2e-5053-8f71-606a568d47d7 | note | Method - Measure, Visual
b05ce3b1-b911-5b32-a616-58de707b1dce | note | Frequency - Each OHLE BWA structure
0ce5243e-846e-5fbc-8109-3d1a67bec83d | note | Category - IP
73599a4b-f8a8-5948-aa11-367782c6fdff | note | Responsibility - CAT5/MRPA
b7808132-025e-5117-b07b-6b64446cd80a | note | Responsible person - MRPA/CAT5 Engineer
a1ea49a5-df0c-57e3-92c5-f302159f5f82 | note | Verifying Documents - This ITP Signed Off
9a11aa86-78fd-5b9d-8887-1c89e66b71af | date | Date Completed:
17e7e0a9-9e44-4298-8e98-32405c89c004 | checkpoint | 5.4 - Check wire follows correct route.
9111835a-cb05-5071-a6d4-f33f757b2208 | note | Reference - Install as per design drawings.
a3e901ab-7a52-5ca7-a5df-9d0b056fb7a7 | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
9bcbef36-ce10-5ee0-b96e-23a98457dcd6 | note | Method - Visual
16eb0f1a-271a-5c9a-9b90-6aa0532c616b | note | Frequency - Each OHLE BWA structure
815f22f3-dfb3-52e2-b597-ee534a67ee8e | note | Category - IP
3c41b952-efb8-54ba-ae1a-10e39e0b1e1a | note | Responsibility - CAT5/MRPA
526bab74-a974-5c1c-8c41-c233d9fa432b | note | Responsible person - MRPA/CAT5 Engineer
b8cb68f5-6fff-5ff3-a576-4fa3ba5b6164 | note | Verifying Documents - This ITP Signed Off
1731a779-a1a1-5810-bf61-88a21e3af8ee | date | Date Completed:
a9dd55aa-07aa-48ba-838b-f59c82a08fc9 | checkpoint | 5.5 - Install to correct tension.
a24741f5-bd37-5e5b-99be-46a64e56c1cb | note | Reference - Install as per design, use span/ambient temp. tension charts.
103e6866-9b39-59b9-a076-f3a892d490a5 | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
9d313e93-8234-5748-a21f-bff8ceb048e6 | note | Method - Measure, Visual
b9c9aab7-6bdb-5bc0-862e-6661581f3da5 | note | Frequency - Prior termination
67b7c4ef-d18b-528d-b857-9b1b2a91bca1 | note | Category - IP
26358222-07de-56c4-b8e3-ed034f97477c | note | Responsibility - CAT5/MRPA
9fe5c32d-499c-5c5c-bb2c-a6e5cf756c17 | note | Responsible person - MRPA/CAT5 Engineer
133c079c-eeb9-59c1-9edf-2bd084dd2bb0 | note | Verifying Documents - This ITP Signed Off
0ca87322-b77d-542b-968f-b37e3bf6407a | date | Date Completed:
e3af0eec-5b8b-4a3d-9276-7c80f8cd286f | section | 6. Post-construction Activities
0ffdafc9-d99e-4c47-bffe-c3e612de9c95 | checkpoint | 6.1 - Defects/Temporary Works
8b032009-7f20-577e-b0d8-743bc4eb811f | note | Reference - IFC wiring layouts, cross sections and design drawings.
9135b4f0-74ce-53b2-90d1-fc8e3f2c003a | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
ed3e0554-370d-5d14-be18-3e0de85fc996 | note | ○ Defect list to be provided at the end of Occo identifying planned work to rectify
098be2f1-e20e-57f9-9d17-c614932e6f88 | note | ○ Attach Design mark up, Defect list, temporary bond register, and approved TW design
9ddb3e4f-c829-559a-8f8d-958748a0a17d | note | Method - Document Review, Visual
50da2742-2b15-5d1d-808f-4798f840b931 | note | Frequency - Each Anchor Termination
1001522f-99af-5194-9960-59da4d28cfce | note | Category - IP
16eb4c36-b7e6-5e21-bc73-374baab2916b | note | Responsibility - CAT5/MRPA
cc61a0d7-d4c2-54e2-bdd4-11b9dad459cf | note | Responsible person - MRPA/CAT5 Engineer
3eefe1e4-3df1-5eae-9e81-990a09c7192a | note | Verifying Documents - This ITP Signed Off
a744f368-808a-5e34-b6cb-0549189db40b | date | Date Completed:
63ee5afb-52db-4728-ae3b-141198df2130 | checkpoint | 6.2 - Relevant documentation readily available (As-built Survey)
d325e2de-949d-55bc-a463-9943736eb5fa | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
b2b063d2-0f1c-5286-87b4-da13e58aeacd | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
37265045-7cc3-5516-800a-e41604f4397e | note | ○ As built drawings and check sheets.CAT5/OHLE/CHK/003 check sheets.
04a7a837-1d29-5e75-8093-716eaa181783 | note | Method - Document Review, Visual
5b79f7dd-32e5-5d25-a33f-6a553c46a070 | note | Frequency - Each OHLE Structure
5258e158-87bd-5dea-8f52-5ce637ba946b | note | Category - IP
71037dac-da6b-5459-a577-16de4138db45 | note | Responsibility - CAT5/MRPA
5d47c8c7-5c93-5b4a-a34d-d4dcdc05667b | note | Responsible person - MRPA/CAT5 Engineer
1ad785b4-de12-5daf-8f66-b2c375f226c2 | note | Verifying Documents - This ITP Signed Off
70c2518a-8379-50bf-8823-95933c022edb | date | Date Completed:
ca002020-0c25-4422-bde6-91a42f9321f9 | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
0fbe5c63-0a3b-54e6-97c1-09f1ffd6cdbc | note | Reference - MTM Quality Management Plan
07c59215-93bf-58d4-a301-1cfca2461b5d | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
81701a52-7aa2-5955-832a-e6d5a13c9406 | note | Method - Document Review
c553ec57-4f12-5b43-80ea-56584076e116 | note | Frequency - Once, prior to closure of this lot / element / Work area
432555b5-511c-52bd-aee2-21e7d6e6e4d8 | note | Category - HP
7073bfa3-95e9-5871-9f10-be5a5735396f | note | Responsibility - CAT5/MRPA
a5b7c195-d733-504f-9342-ed4cc90849a1 | note | Responsible person - MRPA/CAT5 Engineer
f9a14431-7123-530a-9052-e207bc51cbbc | note | Verifying Documents - This ITP Signed Off
20c58f77-d4f5-5131-afd4-bfd93cfeebec | date | Date Completed:
ed490e65-3b03-46ae-9d74-efc2fd2bb017 | signoff | AUTHORITY HOLDPOINT
807529c6-eb70-488a-ace6-28edbef920cb | checkpoint | Final Inspection
333ad49b-a9d0-5bf1-ae5a-2bc1cc09ad7e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
be35f7a9-26af-5916-bf9b-46b4e34632d8 | textbox | Name:
5c7001c2-f5e1-5fe9-9cc2-d979458d4bfc | textbox | Position:
78b9a966-2556-54cd-96be-7706b2a221cf | textbox | Date Completed:
c5209631-cda6-4cb5-bd1f-314ce79e12ee | signoff | Sign ITP
f4c3e08a-0f8f-4686-b859-17abd0366e0c | checklist | OHLE-ITP-CAT5-OHLE STRUCTURE INSTALLATION Rev 1 | itp | OHLE-ITP-CAT5-OHLE STRUCTURE INSTALLATION | 91b93a18-3036-411b-8028-ff4ba5d7a9d6
27a8c9d2-7838-4c28-839e-483d464958fb | section | 1. Referenced Documentation
e5881f8c-6ce6-4ad7-8652-8bf73c60acc0 | checkpoint-no-value | Referenced Documentation
43cf2d0e-a533-5eeb-94bd-b4b00fd59a08 | note | Document Title: OHLE-ITP-CAT5-OHLE STRUCTURE INSTALLATION
82d7381e-5126-588e-90b7-f94e1c414528 | note | ITP Description: OHLE Structures
1cf4d450-21f4-5d19-93dc-4be2960b002c | note | Discipline (e.g. CIV/STR/RAIL): STR
ac3ea2b6-65a9-5e57-977f-1cbd0a3fb0f7 | note | Revision Number: 1
3afe8fdf-c99b-570e-9c61-dcaebb8c29df | note | Revision Date: 9/05/2023
b1666446-1a17-533a-87ed-c516f504df54 | note | ITP approved for use by: Cat5 Rail
648b4491-9225-5b03-8a7a-4a3fe9ec0cb8 | note | 1.1 - Overhead Line Electrification
f926c318-3769-5183-9812-64f76bb05fc9 | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
fbd23478-144e-57f4-809a-b27ba2ebebe0 | note | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
95f87cee-0565-5d51-8ce4-20a5bd0072fe | note | Reference - VRIOGS 001 AS 4100
59a74beb-9c0c-54b5-a9d6-3697c5d5dbb8 | note | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
cd538f44-4682-5f2d-b0ab-c6fbe95edda4 | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
8f5b58af-3315-537b-a026-9d7e16e7bf5a | note | 1.4 - Track Bonding for Signaling and Traction Return Current
944c39e6-2232-5d31-b21d-b006ccaebc0b | note | Reference - L1-CHE-STD-016(1) MEST 000002-05(1)
b41d3dd0-ee94-43eb-af4e-063eb278faa4 | section | 2. Preliminaries - Materials
2454af1f-c687-4bc5-84c6-8572bc6d5cab | checkpoint | 2.1 - Procure materials. What materials? Has to be specific, one line item for each material. Materials to be in accordance with IFC design drawings and relevant MTM Standards.
534d953c-75c2-503f-b897-c89f5574a573 | note | Reference - Relevant MTM Standards and AS, etc
c2fa8d5b-12e1-5365-ba4f-b28d350e5c58 | note | Acceptance Criteria - To ensure materials are manufactured/fabricated as per IFC design drawings/MTM design range.
c1d47459-25ca-5dee-aac9-c5870c6381c2 | note | ○ Material Approval Form to ba raised in TB prior to use on site.
29d8142c-ebba-5a93-9b80-f1d9e045ec9b | note | Method - Document Review
f4754ac0-b5af-545e-ae7a-e6c4e92cf1a1 | note | Frequency - Once for each supplier, prior to works start
53616df9-7492-5dee-8d4c-d671c8133e8e | note | Category - HP
6018eaff-a7d1-515c-83b3-704fe23e6f00 | note | Responsibility - MRPA
c4765587-8c4a-5ef8-ad6f-38e3434ecbe9 | note | Responsible person - MRPA
9017a06c-729a-5bf9-becd-726b052aa385 | note | Verifying Documents - This ITP Signed Off
52ef8854-ad98-59bc-9c1f-7dd67fece950 | date | Date Completed:
2fa40425-676f-432a-b51c-e87e663d516e | signoff | AUTHORITY HOLDPOINT
440e14e1-55df-48b9-b86d-941aed4f6031 | checkpoint | 2.2 - Materials delivered/collected to stores/Site.
8cfe766a-f321-549e-a8da-5f57bb31dc07 | note | Reference - Contractor - Site Material Control procedure.
0b6e3001-92bc-5efd-a9bd-e3004a8b1630 | note | ○ Cat5 Material received -Brunt and Camms Tracking sheet
046a7dc4-6801-56d3-8b4c-ca2c12783924 | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
c666ed3f-e075-5f84-a110-a1e48425e08f | note | ○ Certificates of Conformity provided by MRPA
dd7f24d8-f007-5a1d-aa6e-befe59e1fd22 | note | Method - Document Review
0c9081ab-51f3-5993-8314-b58dc130bc10 | note | Frequency - Once for each supplier, prior to works start
c46926b9-c165-5605-906c-444166c99dfd | note | Category - IP
b5d63594-8012-5aff-9632-db960a33d51d | note | Responsibility - MRPA Issue, CAT5 Receive
6d3414a8-77c7-57f7-b6dc-77e8c184d8c5 | note | Responsible person - MRPA
908eda42-c7bd-5ec0-931c-6891761b15fb | note | Verifying Documents - This ITP Signed Off
b7fd2d29-5230-5166-a089-94589024051f | date | Date Completed:
f7ae512d-7c82-4893-b5a6-5bfa5e0ac58d | section | 3. Preliminaries - Procedures & Documentation
2f2acf15-be08-42b6-9311-a615640a35a3 | checkpoint | 3.1 - Produce Work Package Plan
abc9a562-3eb7-5456-bce7-e788a127eb8a | note | Reference - Work Package Plan WAP_BR_184
ae9841d7-7e37-5508-9a57-4cc770d2a35c | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
920a3c8f-188a-5feb-9c68-f03ffbe54cfa | note | Method - Document Review
fb6bf572-5447-502e-94f3-44c07c1d0da6 | note | Frequency - Prior to Works Start, In accordance with MTM Standards
d088749c-aa8d-53b7-bb0a-52b5c01bc3cf | note | Category - HP
cf38eeff-960f-531c-af40-d0fd04a65a7a | note | Responsibility - MRPA/CAT5
81d6a8a0-447a-537d-bba8-db23c815e3ad | note | Responsible person - MRPA/CAT5 Engineer
3fedb31f-8012-58c0-88fa-b8b7e4e219f8 | note | Verifying Documents - This ITP Signed Off
033b5f4c-9060-5602-b538-4b3a736a830e | date | Date Completed:
1d01a092-ebc7-40c1-aa1c-5a27c4712bca | signoff | AUTHORITY HOLDPOINT
039ce87c-a514-4031-8727-3bfd1074f4d3 | section | 4. Pre-construction Activities
cf7c79aa-4cf6-4cb5-bc80-f2bcdf050ec9 | checkpoint | 4.1 - Approval of IFC drawings
7aeb8ae2-0de2-50d9-a22f-d5edd6aab8ec | note | Reference - Contractor Design Management procedure.
ba8389ad-6734-54ba-ab1a-308a95c00c4d | textbox | Enter document no. here
db4d335d-8d76-530a-ba45-9db4a0a31e5d | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
dccfbe58-5cde-5c56-b71b-e3f37252ed6c | note | Method - Document/Drawings Review
48140786-5edd-5a3c-bf7f-475e0f97e638 | note | Frequency - Prior to Works and at regular intervals. TBC in accordance with MTM Standards.
6b5b8ef1-dccc-5d9b-b155-f991649d220b | note | Category - HP
e43f2451-a94f-5589-aa76-af6d01af3eea | note | Responsibility - MRPA/CAT5
9ee559eb-104d-5cb9-a89e-51dd2066709d | note | Responsible person - MRPA/CAT5 Engineer
8dcc24ac-257a-54bb-8aac-5fb2b5f46d7b | note | Verifying Documents - This ITP Signed Off
0dc27b42-c945-53de-8082-63aa9484abd8 | date | Date Completed:
01992019-2305-4a2b-ae7d-b81eed865589 | signoff | AUTHORITY HOLDPOINT
62eb84cf-ba86-4b2e-bdaa-aac9d438b687 | checkpoint | 4.2 - Lifting operations
75eee142-e70f-58df-885e-ad17fe2b041a | note | Reference - Contractor - Permit to Lift Control procedure.
fcf2199e-2911-5458-8c0f-c26db91d9fdc | note | ○ Contractor - Site Material Control
1ffa597c-812e-51a7-b180-34fc5f9eb7fc | note | ○ Cat5 -LP-01
8b8f9b03-5b83-5528-a492-c1d29c0ee6a2 | note | Acceptance Criteria - Ensure all plant and equipment are operating within their SWL limits.
4a64bdf7-522d-550f-85b3-08f164e7a6b2 | note | ○ Permit to lift to be generated and signed off by Appointed Person.
dd0e00d2-ce66-5319-8701-b2914e54dc52 | note | Method - Visual, Document Review
7e319385-a19e-52e6-9075-1f553c84ce9a | note | Frequency - Each plant and equipment prior to works start. TBC in accordance with MTM Standards.
d8432417-dcff-598d-97db-3069158b39db | note | Category - HP
49454435-9a0c-502e-a0e8-77901ad2b48e | note | Responsibility - MRPA/CAT5
053b549b-4ecb-5447-8686-bbe30122c984 | note | Responsible person - MRPA/CAT5 Engineer
a82a6cce-0ff6-57d9-937f-55816b1b8ee7 | note | Verifying Documents - This ITP Signed Off
f7622645-afc3-54c5-9928-0a806b6fc86d | date | Date Completed:
d6ae205c-8fcb-4147-ab7f-8f5c5aa2b74e | signoff | AUTHORITY HOLDPOINT
13cff5cd-cf95-405f-9416-b2baefe8a5ab | checkpoint | 4.3 - Task Specfic Permits
40eaa954-9047-5718-a409-09ca88e4d4c1 | note | Reference - Working at height permit.
507f9426-86bb-5545-8cae-95af80bbfacf | note | ○ Hot works Permit, Permit to dig.
00f653ab-4558-582e-92ef-05fa932bae90 | textbox | Enter document nos. here
3fc3ce39-5bdc-5863-8de9-5fed5ebaf3ff | note | Acceptance Criteria - Ensure all task and activities have relevent permits issued and received.
f1b93276-1d1e-584d-875a-c35483f1a51a | note | ○ Task Permits to be generated and signed off by appointed person.
514b11e0-da54-5b6d-af2c-6e41b3c5aaa8 | note | ○ Task specific documents - MTM to issue permit to enter/Isolation permits etc.
9a0da0fe-8201-5f91-9ee8-37407d4c8542 | note | Method - Visual, Document Review
31867ed6-8afd-522e-bbf8-f7c6edc3dcfb | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards.
60102716-62bb-5faa-ae2f-279880b1ee0f | note | Category - IP
25c1a99e-1a5c-5a25-ae5f-9ac6c3d6b78d | note | Responsibility - CAT5/MRPA
cb310363-e036-5a64-b932-80d420b3bb2f | note | Responsible person - MRPA/CAT5 Engineer
01e0f512-5995-5a66-9353-43026c304d13 | note | Verifying Documents - This ITP Signed Off
549f1de9-f76e-5b89-a6dc-1fbe1a458f3c | date | Date Completed:
b7c6c7f6-509f-4f26-88f2-e89aed531f6f | checkpoint | 4.4 - Pre-Installation check
0c8cf9bb-117f-52ee-a76f-e9514635fc3b | note | Reference - IFC wiring layouts, IFC cross sections and BOQ.
b1822171-842a-5694-b320-86ccd65a7442 | note | ○ Engineering Drawings Management Policy (IFC/AsBuilt) L1-CHE-MAN-001
efe224db-d3a9-540c-b548-47e70b169c5c | note | Acceptance Criteria - Ensure that foundation holding down bolts match steelwork dimensions.
f75950c4-0753-5da5-b6f8-37f6c269e81a | note | ○ Supervision checking to ensurethat equipment is installed correctly.
bdcdda81-dcac-5182-9b40-85f97afbd4c6 | note | ○ Check sheets, relevant red pen drawing,site delap report to be attached.
f1e583ad-836d-572c-84e9-bdb465d662bc | note | Method - Visual, Document Review
b82b69ad-0907-555f-aece-d7d70aeb99e9 | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards.
1eeb5353-a223-5e7c-b0b0-f7492dfe2034 | note | Category - IP
dfaebc84-95bf-5e33-957a-d034d67b40d8 | note | Responsibility - CAT5/MRPA
fbf73913-dfaf-5c76-8dd8-b7b04c75ce4d | note | Responsible person - MRPA/CAT5 Engineer
1f35f931-0576-5813-864a-f1a7e83924b3 | note | Verifying Documents - This ITP Signed Off
f2c736f8-aaa7-5f80-b860-f9957e530f1d | date | Date Completed:
e5fe888d-b04f-4586-853e-b1447002b0c4 | checkpoint | 4.5 - Foundation Coordinates
089268a5-43da-5819-a49c-ece9adfe69fb | note | Acceptance Criteria - Ensure Complience with structure gauge clearances defined within MTM Spec.
3bc0fdcc-45df-58d9-9b1d-b35bd9745c11 | note | ○ Foundation ITP'S and As Built Coordinates accepted and provided
253f2af3-8c6e-5daa-8f35-02c72a4be77c | note | ○ As built documents - provided by MRPA.
f5311aad-36b1-57d8-bd8f-bf2f5be6c353 | note | Method - Visual, Document Review
962f0d50-8cdb-5454-8ba7-a46eb186c550 | note | Frequency - Prior to Works Start, TBC in accordance with MTM Standards
85ea70e1-04d6-5437-80f3-28612df965e6 | note | Category - HP
75de668d-0617-5fca-acb3-8886e1313a66 | note | Responsibility - MRPA
ee70a419-b3ad-55a4-91c1-e52a2a1e1cd7 | note | Responsible person - MRPA
fd98d4d6-bb59-5a16-91ea-12aaee9c216c | note | Verifying Documents - This ITP Signed Off
7e73d294-7ec2-5c61-9e5c-31419b5f6195 | date | Date Completed:
50b43948-b625-4166-af5f-7fd6da301879 | signoff | AUTHORITY HOLDPOINT
2cac8edd-664b-46bd-a765-8206d38138b0 | section | 5. Construction Activities
306b7f28-6efa-4f15-8ca3-37ff7a2bef66 | checkpoint | 5.1 - Erection of Steelwork
f1ec9947-2e06-5b81-86a1-92ae7f4db0fd | note | Reference - IFC wiring layouts, cross sections and BOQ.
b44c3c89-f631-50ae-9371-3c43c61c45d2 | textbox | Enter document nos. here and Relevant MTM Standards and AS, etc
fe8ab2af-88e3-5ea5-b230-c1f92c4716a7 | note | Acceptance Criteria - Ensure the safe installation of the correct steel to the correct orientation as per IFC design drawings/MTM design range.
8839fea8-d447-5c9b-891e-dbbd5ff72ce3 | note | ○ Supervision / checking to ensure that equipment is installed correctly.
594d2823-3a21-5196-aabb-6e216568ac37 | note | ○ Attach Check sheets, relevant drawings & BOQ.
3c8e16d8-ca1f-5192-9739-9fec2b73bd7c | note | Method - Measure, Visual
1a4551db-0d6e-526c-92ed-23035b953e89 | note | Frequency - Each OHLE Structure
7b6b1a60-b536-546a-bfd7-667d41d92419 | note | Category - IP
59e73923-ff50-5b0f-a65a-387cec7a2f7c | note | Responsibility - CAT5/MRPA
f24aca52-6ee0-5c64-a806-ee339606e233 | note | Responsible person - MRPA/CAT5 Engineer
f66813ce-7bd1-58f9-b90b-058ac5ae3b59 | note | Verifying Documents - This ITP Signed Off
1ba1cc1b-bc3d-50fe-b480-ad9d845d9bba | date | Date Completed:
463f9a0d-1314-4dac-bb39-84b230f1aee9 | checkpoint | 5.2 - Setting or rake / tightening of bolts
106a8f18-73cc-53f7-855f-7fadc2a76141 | note | Reference - IFC wiring layouts, cross sections and design drawings.
b594c8a2-0a5b-54d0-8198-e1a8a8f4dfb0 | textbox | Enter document nos. here and Relevant MTM Standards and AS, etc
ae535d6a-a8c5-5b08-ba86-2b8f28a1ea45 | note | Acceptance Criteria - Ensure the correct installation (prior to the application of loads) torequired rake as per IFC design drawings-MTM design spec.
4af1165b-e5d1-5ec8-8611-aae5d23e2ade | note | ○ Supervision / checking to ensure that equipment is installed correctly.
a3c0e45f-b727-5ae7-b96a-974f77aa8bfc | note | ○ Attach Check sheets, relevant drawings & designdrawings.
2d5ffd18-8abc-5007-888e-ff3daee252a6 | note | Method - Measure, Visual
243b8945-ef65-5747-afb1-d78d2d190bf8 | note | Frequency - Each OHLE Structure
201ed2bf-ebb8-5fe5-855b-6515f2acdfc6 | note | Category - IP
052ac327-4a99-52e7-9d5b-2353d450e7a0 | note | Responsibility - CAT5/MRPA
d8754aa7-c25f-587a-8e20-2d126a9ac1a5 | note | Responsible person - MRPA/CAT5 Engineer
509a5591-28fa-5a6b-a435-950762ed31ea | note | Verifying Documents - This ITP Signed Off
fbc15469-3ca0-56c4-a6bb-4b583be3701b | date | Date Completed:
8c5f0506-4db4-4ba7-8572-89d92f764bb1 | section | 6. Post-construction Activities
c0a3df9f-8505-4ae5-a850-eb2ba8553cb9 | checkpoint | 6.1 - Defects/Temporary Works
852990aa-4916-5056-b2d0-74fa7611c8de | note | Reference - IFC wiring layouts, cross sections and design drawings.
e17eace0-f383-5472-992f-6204432acf75 | textbox | Enter document nos. here and Relevant MTM Standards and AS, etc
83b5c590-788a-5afc-a6ab-2d449293e746 | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
7fee6c52-776d-5ee6-86b1-f0029d1cba4a | note | ○ Defect list to be provided at the end of Occo identifing planned work to rectify
f393dd65-d23d-5a1d-a057-ba1ab2aaa75f | note | ○ Attach Design mark up, Defect list, temporary bond register, and approved TW design
2e2362f6-88b6-5824-baff-42840bc7b40c | note | Method - Document Review, Visual
c6332d4b-99a1-5452-ae93-a1d8469f163e | note | Frequency - Each OHLE Structure
c4c7ecf2-fcba-5778-9897-2b65af339416 | note | Category - IP
3457a79e-c77e-5dde-aa14-36556800869c | note | Responsibility - CAT5/MRPA
d98eefee-2bf7-5f9b-aab6-9dca2b671e8f | note | Responsible person - MRPA/CAT5 Engineer
7273e2b2-d561-579f-b198-bd26afaf5aeb | note | Verifying Documents - This ITP Signed Off
b0361577-8b30-52ab-8bbb-1cf600c55ae2 | date | Date Completed:
ef3ba36a-da87-4424-afc9-d73dd15e675c | checkpoint | 6.2 - Relevant documentation readily available (As-built Survey)
04337e0e-92e3-5564-9927-f172dc03b650 | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
a93ca435-7b78-57f8-a5fe-98c88a113c94 | textbox | Enter document nos. here and Relevant MTM Standards and AS, etc
3f160dbe-ffbb-5e14-b1bd-26dba821305e | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
49630b05-8396-50a3-aef2-491365549d2e | note | ○ As built drawings and check sheets.CAT5/OHLE/CHK001 check sheets.
bf22236a-ae48-55ba-a8c4-309539ff9b22 | note | ○ Attach As built drawings and CAT5/OHLE/CHK001 check sheets.
87a478e4-755a-5d6f-8f7b-061a48cf8fc3 | note | Method - Document Review, Visual
2852da11-ed9d-5452-b122-a2342f71ff27 | note | Frequency - Each OHLE Structure
8c126fa9-dec6-57e1-af98-0121227b4c8a | note | Category - IP
c3923a78-a624-5107-92c5-0d56b8721d17 | note | Responsibility - CAT5/MRPA
31d5131d-cdd3-5e6a-b537-04d0d8ae2466 | note | Responsible person - MRPA/CAT5 Engineer
8b4371d1-cc6d-58d0-8b24-9e8318e9c2ae | note | Verifying Documents - This ITP Signed Off
743b92be-4601-57a2-92ad-afe13f053e82 | date | Date Completed:
5d7a0859-a9f6-4e7a-a493-871a1bf479a0 | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
286e83c5-3140-59e7-a170-48ff25b94ac1 | note | Reference - MTM Quality Management Plan
0a2b45c1-7c23-50e1-981c-a0c8c91385cd | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
43be34a5-dbf4-56fb-be2a-f3a7767761fe | note | Method - Document Review
35f15a97-14f2-5d81-9819-5a13d1f3e0d9 | note | Frequency - Once, prior to closure of this lot / element / Work area
55f32a05-2f92-575f-bff6-1b44a613c9d8 | note | Category - HP
a5d84072-024a-580f-a82c-ba9dd9288d6f | note | Responsibility - CAT5/MRPA
75a4dc6b-f24e-586a-9156-40c074dbf4a4 | note | Responsible person - MRPA/CAT5 Engineer
aeaa97b8-8890-5d6a-b86a-782497c18ff5 | note | Verifying Documents - This ITP Signed Off
13fcba2f-7add-5a6b-a760-bf58627080d5 | date | Date Completed:
d1d9b0db-83c3-42fb-9af7-6c4a32d4b323 | signoff | AUTHORITY HOLDPOINT
fd7d34e0-4697-43cb-9463-25903ec11eba | checkpoint | Final Inspection
72b146ca-6469-59ff-918a-b52edc705726 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5e4777df-a915-5802-8e07-efe099ed7a4e | textbox | Name:
a2f9e8d5-fa4c-5cb5-803e-565ce01b690d | textbox | Position:
1bef1814-5ba7-5940-b2be-f1e734e0151d | textbox | Date Completed:
779bce89-4566-48c3-b119-19532c06bb84 | signoff | Sign ITP