## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Membrane to plywood checklist - Court of Appeal | [5 empty] | Membrane to plywood checklist - Court of Appeal
section | Pre - Start
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Visual inspection of substrate ready for SWP
checkpoint | QA document recevied from main contractor
section | Plywood Substrate
checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint | No screws/nails/fixings popping up
checkpoint | Joints flush and even - minimum gap of 3mm
section | FiberTite - Main Roof
checkpoint | Correct glue as per specification
checkpoint | Prime substrate
checkpoint | Adhesive installed to substrate
checkpoint | Laying of mebrane into adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean laps prior to welding
checkpoint | Test weld with welding machine
checkpoint | Probe of seam with QA hook
section | Fibertite - Gutters
checkpoint | Correct glue as per specification
checkpoint | Prime substrate
checkpoint | Adhesive installed to substrate
checkpoint | Laying of mebrane into adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean laps prior to welding
checkpoint | Probe of seam with QA hook
section | Sumps
checkpoint | Continius sealant installed under membrane
checkpoint | Membrane dressed into outlets
checkpoint | Clamp/rings/basket installed
checkpoint | Flood test
section | Fibreclad flashing
checkpoint | Installed correctly according to specifications ( right way around )
checkpoint | Fixing and welding done according to specifications and details
checkpoint | Probe of seam with QA hook
section | Pressurebar installed
checkpoint | Installed correctly according to specifications ( right way around )
checkpoint | Fixings done according to specifications and details
checkpoint | Primer of Substrate
checkpoint | Silicone installed
section | Strips/Circles over cut out strops
checkpoint | Strops removed
checkpoint | Wipe and clean prior to welding
checkpoint | Probe of seam with QA hook
section | Review and sign off
checkpoint | Area left clean and tidy
checkpoint | All installation work completed, checked and reviewed as per specfications
checkpoint | Client/main contractor sign off