## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Greasy AG
| Scope |  |  | qa
Rows
|  | Hydraulics - New | grouping | hydraulics - new
|  | Level 02 - Zone 5 - Greasy Waste AG (GW) |  | QA | Hydraulics | New | Level 02 | Zone 5 | Greasy Waste AG (GW)
|  | Level 05A - Zone 1 - Greasy Waste AG (GW) |  | QA | Hydraulics | New | Level 05A | Zone 1 | Greasy Waste AG (GW)
|  | Level 05A - Zone 6 - Greasy Waste AG (GW) - Stack 1 (AA-AB, 16-17) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Greasy Waste AG (GW) | Stack 1 (AA-AB, 16-17)
|  | Level 05A - Zone 6 - Greasy Waste AG (GW) - Stack 2 (AA-AB, 16-17) |  | QA | Hydraulics | New | Level 05A | Zone 6 | Greasy Waste AG (GW) | Stack 2 (AA-AB, 16-17)
|  | Level 06 - Zone 2 - Greasy Waste AG (GW) - Grid (AA-AC, 14-19) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Greasy Waste AG (GW) | Grid (AA-AC, 14-19)
|  | Level 06 - Zone 2 - Greasy Waste AG (GW) - Grid (AC-AJ, 19-22) |  | QA | Hydraulics | New | Level 06 | Zone 2 | Greasy Waste AG (GW) | Grid (AC-AJ, 19-22)
Columns
|  | Employee trained for task & reviewed installation instructions |  | employee trained for task and reviewed installation instructions (product qr code / manufacturer's website / instruction manual)
|  | Notify & gain permit from principal contractor/client for inspection |  | notify and gain permit from principal contractor / client for inspection (hold point)
|  | Setout & alignment as per drawing |  | setout & alignment as per drawing (include revision below)
|  | Drawing & revision number(s) | Drawing & revision number(s) | setout & alignment as per drawing (include revision below)
|  | Correct material as per sample register |  | correct material as per sample register
|  | Grades, fittings & joints installed to standards including witness marks |  | grades, fittings & joints installed to standards including witness marks
|  | Fixings & seismic support to code requirements |  | fixings & seismic support to code requirements
|  | Expansion joints per floor installed correctly & clipped |  | expansion joints per floor installed correctly & clipped
|  | Pipe risers sealed per floor & capped off to prevent damage |  | pipe risers sealed per floor & capped off to prevent damage
|  | Correct ventilation installed including AAV |  | correct ventilation installed including aav
|  | Acoustic lagging installed to acoustic specification |  | acoustic lagging installed to acoustic specification
|  | Testing to 15KPA with air or full water test |  | testing to 15kpa with air or full water test
|  | Identifications of services |  | identifications of services
|  | Final sign off |  | final sign off - pass when satisfied to proceed (any issues please comment & add photos below)
|  | Area clean | Area clean | final sign off - pass when satisfied to proceed (any issues please comment & add photos below)