## Sheet1
1 | Identification and location of shallow services | Measure depth of cover to utility services | Trained contractor staff | Two measures per service (each side of the road) | Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | Mandatory HOLD POINT Designer Signoff Required | Marked up sheet | Site Engineer | Designer Signoff | 1 - Identification and location of shallow services | VERIFICATION ACTIVITY: Measure depth of cover to utility services | METHODS OR REFERENCE: Trained contractor staff | FREQUENCY: Two measures per service (each side of the road) | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Marked up sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | 1 - Identification and location of shallow services
2 | Milling / Cut to Waste Type O = 210mm Type C = 305mm Type W = 500mm | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm to design level | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff | 2 - Milling / Cut to Waste Type O = 210mm Type C = 305mm Type W = 500mm | VERIFICATION ACTIVITY: Survey As-built / Stringline | METHODS OR REFERENCE: Survey As-built / Stringline | FREQUENCY: 10m each lane | ACCEPTANCE CRITERIA: +0 / -20mm to design level | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Survey As-built / Stringline sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | VERIFICATION ACTIVITY: Measure depth of cover to utility services
3 | Existing subgrade / subbase | No unacceptable subgrade materials after excavation | Visual Inspection | Sitewide | Free of detritius and loose material | Inprocess Inspection | Photos | Site Engineer | Designer Signoff | 3 - Existing subgrade / subbase | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation | METHODS OR REFERENCE: Visual Inspection | FREQUENCY: Sitewide | ACCEPTANCE CRITERIA: Free of detritius and loose material | TYPE: Inprocess Inspection | RECORDS (Responsibility): Photos | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | METHODS OR REFERENCE: Trained contractor staff
4 | Type O = Contingency weak / soft spot | Benkelman Beam Test | BB Test on exisitng Subbase | 10m interval alternative wheelpath | If BB Deflection >2.1mm and CHAR(LESS)3.5mm, Mill Further 70mm CHAR(AMP) replace with AC20 asphalt If BB Deflection > 3.5mm - Designer to review and advise | Mandatory HOLD POINT Designer Signoff Required | BB test results | Site Engineer | Designer Signoff | 4 - Type O = Contingency weak / soft spot | VERIFICATION ACTIVITY: Benkelman Beam Test | METHODS OR REFERENCE: BB Test on exisitng Subbase | FREQUENCY: 10m interval alternative wheelpath | ACCEPTANCE CRITERIA: If BB Deflection >2.1mm and CHAR(LESS)3.5mm, Mill Further 70mm CHAR(AMP) replace with AC20 asphalt If BB Deflection > 3.5mm - Designer to review and advise | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): BB test results | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | FREQUENCY: Two measures per service (each side of the road)
5 | Type C CHAR(AMP) W = Contingency weak / soft spot | Scalar Testing | Scalar Testing on existing subgrade/subbase | 5m grid | Ensure exposed subgrade CBR ≥ 2. If CBR between 2 and 1 undercut 300mm and replace with woodhill sand wrapped in bidim A29 geotextile If CBR CHAR(LESS) 1 - designer to review and advise | Mandatory HOLD POINT Designer Signoff Required | BB test results | Site Engineer | Designer Signoff | 5 - Type C CHAR(AMP) W = Contingency weak / soft spot | VERIFICATION ACTIVITY: Scalar Testing | METHODS OR REFERENCE: Scalar Testing on existing subgrade/subbase | FREQUENCY: 5m grid | ACCEPTANCE CRITERIA: Ensure exposed subgrade CBR ≥ 2. If CBR between 2 and 1 undercut 300mm and replace with woodhill sand wrapped in bidim A29 geotextile If CBR CHAR(LESS) 1 - designer to review and advise | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): BB test results | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap
6 | All Areas Contingency Weak / Soft Spot | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff | 6 - All Areas Contingency Weak / Soft Spot | VERIFICATION ACTIVITY: Survey As-built / Stringline | METHODS OR REFERENCE: Survey As-built / Stringline | FREQUENCY: 10m each lane | ACCEPTANCE CRITERIA: +0 / -20mm No trafficking of the excavated subgrade | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Survey As-built / Stringline sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | TYPE: Mandatory HOLD POINT Designer Signoff Required
7 | Existing subgrade / subbase | No unacceptable subgrade materials after excavation | Visual Inspection | NA | Free of detritius and loose material | Inprocess Inspection | Photos | Site Engineer | Designer Signoff | 7 - Existing subgrade / subbase | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation | METHODS OR REFERENCE: Visual Inspection | FREQUENCY: NA | ACCEPTANCE CRITERIA: Free of detritius and loose material | TYPE: Inprocess Inspection | RECORDS (Responsibility): Photos | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | RECORDS (Responsibility): Marked up sheet
8 | AT AP65 = Pavement Type W | No non-compliant results | Material test results. The material requirements of AT AP65 are to be in accordance with Auckland Transport Series 0800 | Once | Construction layer shall be Compliance with TNZ B/2 | Mandatory HOLD POINT Designer Signoff Required | Testing Results | Site Engineer |  | 8 - AT AP65 = Pavement Type W | VERIFICATION ACTIVITY: No non-compliant results | METHODS OR REFERENCE: Material test results. The material requirements of AT AP65 are to be in accordance with Auckland Transport Series 0800 | FREQUENCY: Once | ACCEPTANCE CRITERIA: Construction layer shall be Compliance with TNZ B/2 | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Testing Results | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | ONSITE RESPONSIBILITY: Site Engineer
9 | AT AP65 = Pavement Type W | Compaction Testing | Clegg Testing - where there are plant restrictions. NZTA B/2 testing requirements need to be satisfied where there are no such plant restrictions. | 5m grids | CIV > 35. to be compacted in 150mm layers for the Plant Restricted areas. For NZTA B/2, unbound granular subbase shall be undertaken in 150 to 200mm lifts. | Mandatory HOLD POINT Designer Signoff Required | Testing Results | Site Engineer | Designer Signoff | 9 - AT AP65 = Pavement Type W | VERIFICATION ACTIVITY: Compaction Testing | METHODS OR REFERENCE: Clegg Testing - where there are plant restrictions. NZTA B/2 testing requirements need to be satisfied where there are no such plant restrictions. | FREQUENCY: 5m grids | ACCEPTANCE CRITERIA: CIV > 35. to be compacted in 150mm layers for the Plant Restricted areas. For NZTA B/2, unbound granular subbase shall be undertaken in 150 to 200mm lifts. | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Testing Results | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | CONTRACT MANAGER SIGNOFF: Designer Signoff
10 | AT AP65 = Pavement Type W | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff | 10 - AT AP65 = Pavement Type W | VERIFICATION ACTIVITY: Survey As-built / Stringline | METHODS OR REFERENCE: Survey As-built / Stringline | FREQUENCY: 10m each lane | ACCEPTANCE CRITERIA: +0 / -20mm No trafficking of the excavated subgrade | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Survey As-built / Stringline sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | 2 - Milling / Cut to Waste Type O = 210mm Type C = 305mm Type W = 500mm
11 | AT AP65 = Pavement Type W | Surface finish | Visual Inspection | All area | Free of detritius and loose material | Mandatory HOLD POINT Designer Signoff Required | Photos | Site Engineer |  | 11 - AT AP65 = Pavement Type W | VERIFICATION ACTIVITY: Surface finish | METHODS OR REFERENCE: Visual Inspection | FREQUENCY: All area | ACCEPTANCE CRITERIA: Free of detritius and loose material | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Photos | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | VERIFICATION ACTIVITY: Survey As-built / Stringline
12 | Concrete Subbase = Pavement Type W CHAR(AMP) C | Strength and slump | Concrete dockets CHAR(AMP) Lab Testing | each pour | Strength = 20MPa Slump = 130mm pump mix Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface | Inprocess Inspection | Concrete Dockets Slump Testing Report Cylinder Testing Report | Site Engineer |  | 12 - Concrete Subbase = Pavement Type W CHAR(AMP) C | VERIFICATION ACTIVITY: Strength and slump | METHODS OR REFERENCE: Concrete dockets CHAR(AMP) Lab Testing | FREQUENCY: each pour | ACCEPTANCE CRITERIA: Strength = 20MPa Slump = 130mm pump mix Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface | TYPE: Inprocess Inspection | RECORDS (Responsibility): Concrete Dockets Slump Testing Report Cylinder Testing Report | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | METHODS OR REFERENCE: Survey As-built / Stringline
13 | Concrete Subbase = Pavement Type W CHAR(AMP) C | Levels / thickness | Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour) | 10m each lane | +0 / -20mm Target thickness = 150mm | Mandatory HOLD POINT Designer Signoff Required | Stringline Sheet | Site Engineer | Designer Signoff | 13 - Concrete Subbase = Pavement Type W CHAR(AMP) C | VERIFICATION ACTIVITY: Levels / thickness | METHODS OR REFERENCE: Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour) | FREQUENCY: 10m each lane | ACCEPTANCE CRITERIA: +0 / -20mm Target thickness = 150mm | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Stringline Sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | FREQUENCY: 10m each lane
14 | Concrete Subbase = Pavement Type W CHAR(AMP) C | Rough trowel or Broom surface finish | Visual Inspection | All area | Rough surface verified over 100% of surface area | Inprocess Inspection | Production Recurs | Site Engineer |  | 14 - Concrete Subbase = Pavement Type W CHAR(AMP) C | VERIFICATION ACTIVITY: Rough trowel or Broom surface finish | METHODS OR REFERENCE: Visual Inspection | FREQUENCY: All area | ACCEPTANCE CRITERIA: Rough surface verified over 100% of surface area | TYPE: Inprocess Inspection | RECORDS (Responsibility): Production Recurs | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | ACCEPTANCE CRITERIA: +0 / -20mm to design level
15 | Type W CHAR(AMP) Type C | Blinding/CAT60 | Visual Inspection | each lot | ON CONCRETE SUBBASE Hand spray heavy tack coat emulsion (residual bitumen 1L/m2) Blinding sufficient to protect emsulsion from construction movement Manufacturer's guidelines for Hatelit XP installation and subsequent bitumen application on the concrete subbase in accordance with Hatelit XP installation guidelines. | Inprocess Testing | Photos | Site Engineer |  | 15 - Type W CHAR(AMP) Type C | VERIFICATION ACTIVITY: Blinding/CAT60 | METHODS OR REFERENCE: Visual Inspection | FREQUENCY: each lot | ACCEPTANCE CRITERIA: ON CONCRETE SUBBASE Hand spray heavy tack coat emulsion (residual bitumen 1L/m2) Blinding sufficient to protect emsulsion from construction movement Manufacturer's guidelines for Hatelit XP installation and subsequent bitumen application on the concrete subbase in accordance with Hatelit XP installation guidelines. | TYPE: Inprocess Testing | RECORDS (Responsibility): Photos | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | TYPE: Mandatory HOLD POINT Designer Signoff Required
16 | Type O = Contingency weak / soft spot | Grade 4 Membrane | Visual Inspection | each lot | ON EXISTING PAVEMENT Hand spray Heavy tack coat emulsion (residual bitumen 1L/m2) Grade 4 chip | Inprocess Testing | Photos | Site Engineer |  | 16 - Type O = Contingency weak / soft spot | VERIFICATION ACTIVITY: Grade 4 Membrane | METHODS OR REFERENCE: Visual Inspection | FREQUENCY: each lot | ACCEPTANCE CRITERIA: ON EXISTING PAVEMENT Hand spray Heavy tack coat emulsion (residual bitumen 1L/m2) Grade 4 chip | TYPE: Inprocess Testing | RECORDS (Responsibility): Photos | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | RECORDS (Responsibility): Survey As-built / Stringline sheet
17 | Hatelit XP Grid | Photos | Visual Inspection | each lot | Type W CHAR(AMP)C = required over concrete subbase Extend 500mm into existing pavement (with CHAR(LESS)20mm asphalt blinding) Extend 1m into Type O | Inprocess Testing | Photos | Site Engineer |  | 17 - Hatelit XP Grid | VERIFICATION ACTIVITY: Photos | METHODS OR REFERENCE: Visual Inspection | FREQUENCY: each lot | ACCEPTANCE CRITERIA: Type W CHAR(AMP)C = required over concrete subbase Extend 500mm into existing pavement (with CHAR(LESS)20mm asphalt blinding) Extend 1m into Type O | TYPE: Inprocess Testing | RECORDS (Responsibility): Photos | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | ONSITE RESPONSIBILITY: Site Engineer
18 | AC14HF CHAR(AMP) AC20 | Mix Design | Sign-off by Designer | Prior to starting | Sign-off by Designer | Mandatory HOLD POINT Designer Signoff Required | Mix Design Report | Site Engineer | Designer Signoff | 18 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Mix Design | METHODS OR REFERENCE: Sign-off by Designer | FREQUENCY: Prior to starting | ACCEPTANCE CRITERIA: Sign-off by Designer | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Mix Design Report | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | CONTRACT MANAGER SIGNOFF: Designer Signoff
19 | AC14HF CHAR(AMP) AC20 | Check weather reports | Check weather reports | Daily | No fog, rain or wet surface. Base temp ≥ 7o C | Inprocess Testing | AC check sheet | Site Engineer |  | 19 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Check weather reports | METHODS OR REFERENCE: Check weather reports | FREQUENCY: Daily | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C | TYPE: Inprocess Testing | RECORDS (Responsibility): AC check sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | 3 - Existing subgrade / subbase
20 | AC14HF CHAR(AMP) AC20 | Ensure previous layer is broomed clean | Visual | Prior to starting | Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer |  | 20 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean | METHODS OR REFERENCE: Visual | FREQUENCY: Prior to starting | ACCEPTANCE CRITERIA: Free of detritius and loose material | TYPE: Inprocess Testing | RECORDS (Responsibility): AC check sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
21 | AC14HF CHAR(AMP) AC20 | Production tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Inprocess Testing | Lab test | Site Engineer |  | 21 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Production tests | METHODS OR REFERENCE: Grading, binder content, max density, temp | FREQUENCY: As per M/10 | ACCEPTANCE CRITERIA: NZTA M/10 | TYPE: Inprocess Testing | RECORDS (Responsibility): Lab test | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | METHODS OR REFERENCE: Visual Inspection
22 | AC14HF CHAR(AMP) AC20 | Surface finish inspection | Visual inspection by the Engineer | Each lot | Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer |  | 22 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Surface finish inspection | METHODS OR REFERENCE: Visual inspection by the Engineer | FREQUENCY: Each lot | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | TYPE: Inprocess Testing | RECORDS (Responsibility): Inspection sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | FREQUENCY: Sitewide
23 | AC14HF CHAR(AMP) AC20 | Density testing | NDM | Every 10m each lane staggerd | Air voids to meet NZTA M/10:2020 | Inprocess Testing | Inspection sheet | Site Engineer | Auckland Transport Signoff | 23 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Density testing | METHODS OR REFERENCE: NDM | FREQUENCY: Every 10m each lane staggerd | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020 | TYPE: Inprocess Testing | RECORDS (Responsibility): Inspection sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff | ACCEPTANCE CRITERIA: Free of detritius and loose material
24 | AC14HF (Type O) | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | Thickness no less than 55mm | Inprocess Testing | Survey As-built / Stringline sheet | Site Engineer |  | 24 - AC14HF (Type O) | VERIFICATION ACTIVITY: Survey As-built / Stringline | METHODS OR REFERENCE: Survey As-built / Stringline | FREQUENCY: 10m each lane | ACCEPTANCE CRITERIA: Thickness no less than 55mm | TYPE: Inprocess Testing | RECORDS (Responsibility): Survey As-built / Stringline sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | TYPE: Inprocess Inspection
25 | AC20 (All three types) | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | Thickness no less than 100mm | Inprocess Testing | Survey As-built / Stringline sheet | Site Engineer |  | 25 - AC20 (All three types) | VERIFICATION ACTIVITY: Survey As-built / Stringline | METHODS OR REFERENCE: Survey As-built / Stringline | FREQUENCY: 10m each lane | ACCEPTANCE CRITERIA: Thickness no less than 100mm | TYPE: Inprocess Testing | RECORDS (Responsibility): Survey As-built / Stringline sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | RECORDS (Responsibility): Photos
26 | AC14HF CHAR(AMP) AC20 | Density testing | Cores air voids | Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Air voids to meet NZTA M/10:2020 Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot. 3 joint cores where possible/practicable | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Site Engineer | Auckland Transport Signoff | 26 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Density testing | METHODS OR REFERENCE: Cores air voids | FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020 Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot. 3 joint cores where possible/practicable | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required | RECORDS (Responsibility): RFI response | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff | ONSITE RESPONSIBILITY: Site Engineer
27 | AC14HF CHAR(AMP) AC20 | Thickness | Cores depth | Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Target thickness 155mm (no less than 155mm thickness for AC14HF and AC20 combined) Target thickness 100mm (no less than 100mm thickness for AC20) | Mandatory HOLD POINT Auckland Transport Signoff Required | Core test report | Site Engineer | Auckland Transport Signoff | 27 - AC14HF CHAR(AMP) AC20 | VERIFICATION ACTIVITY: Thickness | METHODS OR REFERENCE: Cores depth | FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | ACCEPTANCE CRITERIA: Target thickness 155mm (no less than 155mm thickness for AC14HF and AC20 combined) Target thickness 100mm (no less than 100mm thickness for AC20) | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required | RECORDS (Responsibility): Core test report | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff | CONTRACT MANAGER SIGNOFF: Designer Signoff
28 | AC14 | Mix Design | Sign-off by Designer | Prior to starting | Sign-off by Designer | Mandatory HOLD POINT Designer Signoff Required | Mix Design Report | Site Engineer | Designer Signoff | 28 - AC14 | VERIFICATION ACTIVITY: Mix Design | METHODS OR REFERENCE: Sign-off by Designer | FREQUENCY: Prior to starting | ACCEPTANCE CRITERIA: Sign-off by Designer | TYPE: Mandatory HOLD POINT Designer Signoff Required | RECORDS (Responsibility): Mix Design Report | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Designer Signoff | 4 - Type O = Contingency weak / soft spot
29 | Shape of road | 3m straight edge | NZTA M/10 spec | At joints and any other areas of concern | Irregularities CHAR(LESS) 5mm under straight edge | Inprocess Inspection | Check sheet | Site Engineer |  | 29 - Shape of road | VERIFICATION ACTIVITY: 3m straight edge | METHODS OR REFERENCE: NZTA M/10 spec | FREQUENCY: At joints and any other areas of concern | ACCEPTANCE CRITERIA: Irregularities CHAR(LESS) 5mm under straight edge | TYPE: Inprocess Inspection | RECORDS (Responsibility): Check sheet | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | VERIFICATION ACTIVITY: Benkelman Beam Test
30 | Temperature Limitations | Temperature | Contract Spec / M10 Spec | Every Site | Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree | Inprocess Inspection | Asphalt QA | Site Engineer |  | 30 - Temperature Limitations | VERIFICATION ACTIVITY: Temperature | METHODS OR REFERENCE: Contract Spec / M10 Spec | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree | TYPE: Inprocess Inspection | RECORDS (Responsibility): Asphalt QA | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | METHODS OR REFERENCE: BB Test on exisitng Subbase
31 | Surface Preparation | Visual | NZTA M/10 spec | Every Site | Swept clean; all necessary measures to prevent ponding prior to any surfacing | Inprocess Inspection | Visual | Site Engineer |  | 31 - Surface Preparation | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: NZTA M/10 spec | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing | TYPE: Inprocess Inspection | RECORDS (Responsibility): Visual | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | FREQUENCY: 10m interval alternative wheelpath
32 | Asphalt Production Tests for AC14 | Production Tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Laboratory Testing | IANZ Lab | Site Engineer |  | 32 - Asphalt Production Tests for AC14 | VERIFICATION ACTIVITY: Production Tests | METHODS OR REFERENCE: Grading, binder content, max density, temp | FREQUENCY: As per M/10 | ACCEPTANCE CRITERIA: NZTA M/10 | TYPE: Laboratory Testing | RECORDS (Responsibility): IANZ Lab | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | ACCEPTANCE CRITERIA: If BB Deflection >2.1mm and CHAR(LESS)3.5mm, Mill Further 70mm CHAR(AMP) replace with AC20 asphalt If BB Deflection > 3.5mm - Designer to review and advise
33 | AC14 - Layer thickness - 55mm compacted depth | Insitu | Contract Spec / NZTA M10 Spec | Continuous | 55 mm minimum and 60 mm maximum compacted depth Final asphalt level to be 5mm proud of lip of channel | Mandatory HOLD POINT Auckland Transport Signoff Required | Asphalt QA | Site Engineer | Auckland Transport Signoff | 33 - AC14 - Layer thickness - 55mm compacted depth | VERIFICATION ACTIVITY: Insitu | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec | FREQUENCY: Continuous | ACCEPTANCE CRITERIA: 55 mm minimum and 60 mm maximum compacted depth Final asphalt level to be 5mm proud of lip of channel | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required | RECORDS (Responsibility): Asphalt QA | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff | TYPE: Mandatory HOLD POINT Designer Signoff Required
34 | AC14 | Density testing | NDM | Every 10m each lane staggerd | NZTA M/10 | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Site Engineer | Auckland Transport Signoff | 34 - AC14 | VERIFICATION ACTIVITY: Density testing | METHODS OR REFERENCE: NDM | FREQUENCY: Every 10m each lane staggerd | ACCEPTANCE CRITERIA: NZTA M/10 | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required | RECORDS (Responsibility): RFI response | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff | RECORDS (Responsibility): BB test results
35 | Reinstatement of Linemarking and RRPM's CHAR(AMP) Apply Joint sealing | Visual | Visual inspection | Every site | Visual inspection | Inprocess Inspection | Photos | Site Engineer |  | 35 - Reinstatement of Linemarking and RRPM's CHAR(AMP) Apply Joint sealing | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: Visual inspection | FREQUENCY: Every site | ACCEPTANCE CRITERIA: Visual inspection | TYPE: Inprocess Inspection | RECORDS (Responsibility): Photos | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: | ONSITE RESPONSIBILITY: Site Engineer
36 | As-built information | Documentation | As-built drawings and ramm sheets completed | - | As-built records | Inprocess Inspection | - | Site Engineer | Auckland Transport Signoff | 36 - As-built information | VERIFICATION ACTIVITY: Documentation | METHODS OR REFERENCE: As-built drawings and ramm sheets completed | FREQUENCY: - | ACCEPTANCE CRITERIA: As-built records | TYPE: Inprocess Inspection | RECORDS (Responsibility): - | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff | CONTRACT MANAGER SIGNOFF: Designer Signoff
37 | RAMM DATA | Documentation | RAMM Sheet | - | RAMM Sheet | Inprocess Inspection | - | Site Engineer | Auckland Transport Signoff | 37 - RAMM DATA | VERIFICATION ACTIVITY: Documentation | METHODS OR REFERENCE: RAMM Sheet | FREQUENCY: - | ACCEPTANCE CRITERIA: RAMM Sheet | TYPE: Inprocess Inspection | RECORDS (Responsibility): - | ONSITE RESPONSIBILITY: Site Engineer | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff | 5 - Type C CHAR(AMP) W = Contingency weak / soft spot
VERIFICATION ACTIVITY: Scalar Testing
METHODS OR REFERENCE: Scalar Testing on existing subgrade/subbase
FREQUENCY: 5m grid
ACCEPTANCE CRITERIA: Ensure exposed subgrade CBR ≥ 2. If CBR between 2 and 1 undercut 300mm and replace with woodhill sand wrapped in bidim A29 geotextile If CBR CHAR(LESS) 1 - designer to review and advise
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): BB test results
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
6 - All Areas Contingency Weak / Soft Spot
VERIFICATION ACTIVITY: Survey As-built / Stringline
METHODS OR REFERENCE: Survey As-built / Stringline
FREQUENCY: 10m each lane
ACCEPTANCE CRITERIA: +0 / -20mm No trafficking of the excavated subgrade
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Survey As-built / Stringline sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
7 - Existing subgrade / subbase
VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
METHODS OR REFERENCE: Visual Inspection
FREQUENCY: NA
ACCEPTANCE CRITERIA: Free of detritius and loose material
TYPE: Inprocess Inspection
RECORDS (Responsibility): Photos
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
8 - AT AP65 = Pavement Type W
VERIFICATION ACTIVITY: No non-compliant results
METHODS OR REFERENCE: Material test results. The material requirements of AT AP65 are to be in accordance with Auckland Transport Series 0800
FREQUENCY: Once
ACCEPTANCE CRITERIA: Construction layer shall be Compliance with TNZ B/2
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Testing Results
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
9 - AT AP65 = Pavement Type W
VERIFICATION ACTIVITY: Compaction Testing
METHODS OR REFERENCE: Clegg Testing - where there are plant restrictions. NZTA B/2 testing requirements need to be satisfied where there are no such plant restrictions.
FREQUENCY: 5m grids
ACCEPTANCE CRITERIA: CIV > 35. to be compacted in 150mm layers for the Plant Restricted areas. For NZTA B/2, unbound granular subbase shall be undertaken in 150 to 200mm lifts.
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Testing Results
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
10 - AT AP65 = Pavement Type W
VERIFICATION ACTIVITY: Survey As-built / Stringline
METHODS OR REFERENCE: Survey As-built / Stringline
FREQUENCY: 10m each lane
ACCEPTANCE CRITERIA: +0 / -20mm No trafficking of the excavated subgrade
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Survey As-built / Stringline sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
11 - AT AP65 = Pavement Type W
VERIFICATION ACTIVITY: Surface finish
METHODS OR REFERENCE: Visual Inspection
FREQUENCY: All area
ACCEPTANCE CRITERIA: Free of detritius and loose material
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Photos
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
12 - Concrete Subbase = Pavement Type W CHAR(AMP) C
VERIFICATION ACTIVITY: Strength and slump
METHODS OR REFERENCE: Concrete dockets CHAR(AMP) Lab Testing
FREQUENCY: each pour
ACCEPTANCE CRITERIA: Strength = 20MPa Slump = 130mm pump mix Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface
TYPE: Inprocess Inspection
RECORDS (Responsibility): Concrete Dockets Slump Testing Report Cylinder Testing Report
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
13 - Concrete Subbase = Pavement Type W CHAR(AMP) C
VERIFICATION ACTIVITY: Levels / thickness
METHODS OR REFERENCE: Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour)
FREQUENCY: 10m each lane
ACCEPTANCE CRITERIA: +0 / -20mm Target thickness = 150mm
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Stringline Sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
14 - Concrete Subbase = Pavement Type W CHAR(AMP) C
VERIFICATION ACTIVITY: Rough trowel or Broom surface finish
METHODS OR REFERENCE: Visual Inspection
FREQUENCY: All area
ACCEPTANCE CRITERIA: Rough surface verified over 100% of surface area
TYPE: Inprocess Inspection
RECORDS (Responsibility): Production Recurs
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
15 - Type W CHAR(AMP) Type C
VERIFICATION ACTIVITY: Blinding/CAT60
METHODS OR REFERENCE: Visual Inspection
FREQUENCY: each lot
ACCEPTANCE CRITERIA: ON CONCRETE SUBBASE Hand spray heavy tack coat emulsion (residual bitumen 1L/m2) Blinding sufficient to protect emsulsion from construction movement Manufacturer's guidelines for Hatelit XP installation and subsequent bitumen application on the concrete subbase in accordance with Hatelit XP installation guidelines.
TYPE: Inprocess Testing
RECORDS (Responsibility): Photos
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
16 - Type O = Contingency weak / soft spot
VERIFICATION ACTIVITY: Grade 4 Membrane
METHODS OR REFERENCE: Visual Inspection
FREQUENCY: each lot
ACCEPTANCE CRITERIA: ON EXISTING PAVEMENT Hand spray Heavy tack coat emulsion (residual bitumen 1L/m2) Grade 4 chip
TYPE: Inprocess Testing
RECORDS (Responsibility): Photos
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
17 - Hatelit XP Grid
VERIFICATION ACTIVITY: Photos
METHODS OR REFERENCE: Visual Inspection
FREQUENCY: each lot
ACCEPTANCE CRITERIA: Type W CHAR(AMP)C = required over concrete subbase Extend 500mm into existing pavement (with CHAR(LESS)20mm asphalt blinding) Extend 1m into Type O
TYPE: Inprocess Testing
RECORDS (Responsibility): Photos
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
18 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Mix Design
METHODS OR REFERENCE: Sign-off by Designer
FREQUENCY: Prior to starting
ACCEPTANCE CRITERIA: Sign-off by Designer
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Mix Design Report
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
19 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Check weather reports
METHODS OR REFERENCE: Check weather reports
FREQUENCY: Daily
ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
TYPE: Inprocess Testing
RECORDS (Responsibility): AC check sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
20 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
METHODS OR REFERENCE: Visual
FREQUENCY: Prior to starting
ACCEPTANCE CRITERIA: Free of detritius and loose material
TYPE: Inprocess Testing
RECORDS (Responsibility): AC check sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
21 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Production tests
METHODS OR REFERENCE: Grading, binder content, max density, temp
FREQUENCY: As per M/10
ACCEPTANCE CRITERIA: NZTA M/10
TYPE: Inprocess Testing
RECORDS (Responsibility): Lab test
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
22 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Surface finish inspection
METHODS OR REFERENCE: Visual inspection by the Engineer
FREQUENCY: Each lot
ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
TYPE: Inprocess Testing
RECORDS (Responsibility): Inspection sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
23 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Density testing
METHODS OR REFERENCE: NDM
FREQUENCY: Every 10m each lane staggerd
ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
TYPE: Inprocess Testing
RECORDS (Responsibility): Inspection sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
24 - AC14HF (Type O)
VERIFICATION ACTIVITY: Survey As-built / Stringline
METHODS OR REFERENCE: Survey As-built / Stringline
FREQUENCY: 10m each lane
ACCEPTANCE CRITERIA: Thickness no less than 55mm
TYPE: Inprocess Testing
RECORDS (Responsibility): Survey As-built / Stringline sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
25 - AC20 (All three types)
VERIFICATION ACTIVITY: Survey As-built / Stringline
METHODS OR REFERENCE: Survey As-built / Stringline
FREQUENCY: 10m each lane
ACCEPTANCE CRITERIA: Thickness no less than 100mm
TYPE: Inprocess Testing
RECORDS (Responsibility): Survey As-built / Stringline sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
26 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Density testing
METHODS OR REFERENCE: Cores air voids
FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020 Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot. 3 joint cores where possible/practicable
TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
RECORDS (Responsibility): RFI response
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
27 - AC14HF CHAR(AMP) AC20
VERIFICATION ACTIVITY: Thickness
METHODS OR REFERENCE: Cores depth
FREQUENCY: Location to be jointly agreed with the Engineer on-site and be outside of wheelpath
ACCEPTANCE CRITERIA: Target thickness 155mm (no less than 155mm thickness for AC14HF and AC20 combined) Target thickness 100mm (no less than 100mm thickness for AC20)
TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
RECORDS (Responsibility): Core test report
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
28 - AC14
VERIFICATION ACTIVITY: Mix Design
METHODS OR REFERENCE: Sign-off by Designer
FREQUENCY: Prior to starting
ACCEPTANCE CRITERIA: Sign-off by Designer
TYPE: Mandatory HOLD POINT Designer Signoff Required
RECORDS (Responsibility): Mix Design Report
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Designer Signoff
29 - Shape of road
VERIFICATION ACTIVITY: 3m straight edge
METHODS OR REFERENCE: NZTA M/10 spec
FREQUENCY: At joints and any other areas of concern
ACCEPTANCE CRITERIA: Irregularities CHAR(LESS) 5mm under straight edge
TYPE: Inprocess Inspection
RECORDS (Responsibility): Check sheet
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
30 - Temperature Limitations
VERIFICATION ACTIVITY: Temperature
METHODS OR REFERENCE: Contract Spec / M10 Spec
FREQUENCY: Every Site
ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree
TYPE: Inprocess Inspection
RECORDS (Responsibility): Asphalt QA
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
31 - Surface Preparation
VERIFICATION ACTIVITY: Visual
METHODS OR REFERENCE: NZTA M/10 spec
FREQUENCY: Every Site
ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
TYPE: Inprocess Inspection
RECORDS (Responsibility): Visual
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
32 - Asphalt Production Tests for AC14
VERIFICATION ACTIVITY: Production Tests
METHODS OR REFERENCE: Grading, binder content, max density, temp
FREQUENCY: As per M/10
ACCEPTANCE CRITERIA: NZTA M/10
TYPE: Laboratory Testing
RECORDS (Responsibility): IANZ Lab
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
33 - AC14 - Layer thickness - 55mm compacted depth
VERIFICATION ACTIVITY: Insitu
METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
FREQUENCY: Continuous
ACCEPTANCE CRITERIA: 55 mm minimum and 60 mm maximum compacted depth Final asphalt level to be 5mm proud of lip of channel
TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
RECORDS (Responsibility): Asphalt QA
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
34 - AC14
VERIFICATION ACTIVITY: Density testing
METHODS OR REFERENCE: NDM
FREQUENCY: Every 10m each lane staggerd
ACCEPTANCE CRITERIA: NZTA M/10
TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
RECORDS (Responsibility): RFI response
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
35 - Reinstatement of Linemarking and RRPM's CHAR(AMP) Apply Joint sealing
VERIFICATION ACTIVITY: Visual
METHODS OR REFERENCE: Visual inspection
FREQUENCY: Every site
ACCEPTANCE CRITERIA: Visual inspection
TYPE: Inprocess Inspection
RECORDS (Responsibility): Photos
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF:
36 - As-built information
VERIFICATION ACTIVITY: Documentation
METHODS OR REFERENCE: As-built drawings and ramm sheets completed
FREQUENCY: -
ACCEPTANCE CRITERIA: As-built records
TYPE: Inprocess Inspection
RECORDS (Responsibility): -
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
37 - RAMM DATA
VERIFICATION ACTIVITY: Documentation
METHODS OR REFERENCE: RAMM Sheet
FREQUENCY: -
ACCEPTANCE CRITERIA: RAMM Sheet
TYPE: Inprocess Inspection
RECORDS (Responsibility): -
ONSITE RESPONSIBILITY: Site Engineer
CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff