## Sheet1
2.1 | Manufacture CHAR(AMP) Supply of Signages and Posts | Section 860 Section 860.06 Section 860.07 Table 860.071 Section 714.03 Section 714.06 IFC Drawings | Signs are to be manufactured in accordance with Section 860 and IFC Drawings Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071. Packaging and Storage of Sign to be in accordance with Specification 860.06. Signs and components shall be handled and transported so as to prevent damage. Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer. Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either: - Hot dipped galvanised; or - Pre-galvanised prior to forming Attach: TeamBinder Material Approval Ref No | Document Review | Prior to works start | HP* | Nominated Authority | Conqa HP Release | 2.1 - Manufacture CHAR(AMP) Supply of Signages and Posts | Reference - Section 860 Section 860.06 Section 860.07 Table 860.071 Section 714.03 Section 714.06 IFC Drawings | Acceptance Criteria - Signs are to be manufactured in accordance with Section 860 and IFC Drawings Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071. Packaging and Storage of Sign to be in accordance with Specification 860.06. Signs and components shall be handled and transported so as to prevent damage. Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer. Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either: - Hot dipped galvanised; or - Pre-galvanised prior to forming Attach: TeamBinder Material Approval Ref No | Method - Document Review | Frequency - Prior to works start | Category - HP* | Responsibility - Nominated Authority | Verifying Documents - Conqa HP Release | Date Completed: | 2.1 - Manufacture CHAR(AMP) Supply of Signages and Posts
3.1 | Check for correct documentation | IFC Drawings | Ensure that all employees and sub contractors are: - Using the correct and complete set of drawings - All drawings are the latest version | Visual inspection | Prior to commencing any activity | HP* | SE/Site Supervisor | This ITP Signed-off | 3.1 - Check for correct documentation | Reference - IFC Drawings | Acceptance Criteria - Ensure that all employees and sub contractors are: - Using the correct and complete set of drawings - All drawings are the latest version | Method - Visual inspection | Frequency - Prior to commencing any activity | Category - HP* | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP Signed-off | Date Completed: | Reference - Section 860 Section 860.06 Section 860.07 Table 860.071 Section 714.03 Section 714.06 IFC Drawings
3.1 | Setting Out - Position of Posts and Signs | Section 714.06 IFC Drawings | Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Superintendent before the erection of posts | Verify | Prior to start | HP* | Surveyor SE/PE Nominated Authority | This ITP Signed-off | 3.1 - Setting Out - Position of Posts and Signs | Reference - Section 714.06 IFC Drawings | Acceptance Criteria - Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Superintendent before the erection of posts | Method - Verify | Frequency - Prior to start | Category - HP* | Responsibility - Surveyor SE/PE Nominated Authority | Verifying Documents - This ITP Signed-off | Date Completed: | Acceptance Criteria - Signs are to be manufactured in accordance with Section 860 and IFC Drawings Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071. Packaging and Storage of Sign to be in accordance with Specification 860.06. Signs and components shall be handled and transported so as to prevent damage. Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer. Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either: - Hot dipped galvanised; or - Pre-galvanised prior to forming Attach: TeamBinder Material Approval Ref No
4.1 | Foundation | Section 714.06 ( c) Section 703 Brimbank Standards S520 | All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below: Post sizes 32mm and 50mm nominal bore steel = 225mm diameter Post sizes 80mm to 150mm nominal bore steel = 300mm diameter Frangible hardwood posts 180mm x 100mm = 300mm diameter Concrete Footing should be 300mm diametre and 700mm deep with 25MPa concrete mix as per Brimbank standards S520. Attach: Concrete Delivery Docket | Measure Visual | Per Lot | HP* | SE/PE Nominated Authority | This ITP Signed-off | 4.1 - Foundation | Reference - Section 714.06 ( c) Section 703 Brimbank Standards S520 | Acceptance Criteria - All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below: Post sizes 32mm and 50mm nominal bore steel = 225mm diameter Post sizes 80mm to 150mm nominal bore steel = 300mm diameter Frangible hardwood posts 180mm x 100mm = 300mm diameter Concrete Footing should be 300mm diametre and 700mm deep with 25MPa concrete mix as per Brimbank standards S520. Attach: Concrete Delivery Docket | Method - Measure Visual | Frequency - Per Lot | Category - HP* | Responsibility - SE/PE Nominated Authority | Verifying Documents - This ITP Signed-off | Date Completed: | Method - Document Review
4.2 | Post Installation in Sockets | Section 714.06 (d) Table 22 of AS 1742.2:2009 | For Post Size 32mm Socket size to be 50mm Nominal Bore Tube For Post Size 50mm Socket size to be 65mm Nominal Bore Tube The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface. The sign post must penetrate a minimum 450 mm into the socket. Depth of the socket should be as per Table 22 of AS 1742.2:2009. The sign post should be securely fixed into the socket by an approved vandal-proof method. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off | 4.2 - Post Installation in Sockets | Reference - Section 714.06 (d) Table 22 of AS 1742.2:2009 | Acceptance Criteria - For Post Size 32mm Socket size to be 50mm Nominal Bore Tube For Post Size 50mm Socket size to be 65mm Nominal Bore Tube The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface. The sign post must penetrate a minimum 450 mm into the socket. Depth of the socket should be as per Table 22 of AS 1742.2:2009. The sign post should be securely fixed into the socket by an approved vandal-proof method. | Method - Measure Visual | Frequency - Per Lot | Category - IP | Responsibility - SE/PE | Verifying Documents - This ITP Signed-off | Date Completed: | Frequency - Prior to works start
4.3 | Backfilling of Post Holes | Section 714.06 e | 32 and 50 mm Nominal Bore Steel Posts Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa. 180 mm x 100 mm Frangible Hardwood Timber Posts - frangible Hardwood Posts shall be erected in accordance with the drawings; - post-holes for frangible hardwood posts shall be filled with a mixture of gravel and cement (4% by weight) Attach: Delivery Dockets | Verify | Per Lot | IP | SE/PE | This ITP Signed-off | 4.3 - Backfilling of Post Holes | Reference - Section 714.06 e | Acceptance Criteria - 32 and 50 mm Nominal Bore Steel Posts Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa. 180 mm x 100 mm Frangible Hardwood Timber Posts - frangible Hardwood Posts shall be erected in accordance with the drawings; - post-holes for frangible hardwood posts shall be filled with a mixture of gravel and cement (4% by weight) Attach: Delivery Dockets | Method - Verify | Frequency - Per Lot | Category - IP | Responsibility - SE/PE | Verifying Documents - This ITP Signed-off | Date Completed: | Category - HP*
4.4 | Sign Fitting | Section 714.07 | Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows: -Signs up to 200mm in depth – one fitting per post - Signs 201 to 900mm in depth – two fittings per post - Signs 901 to 1200mm in depth – three fittings per post One extra fitting provided per post for each 400mm increment or part thereof above 1200mm. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off | 4.4 - Sign Fitting | Reference - Section 714.07 | Acceptance Criteria - Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows: -Signs up to 200mm in depth – one fitting per post - Signs 201 to 900mm in depth – two fittings per post - Signs 901 to 1200mm in depth – three fittings per post One extra fitting provided per post for each 400mm increment or part thereof above 1200mm. | Method - Measure Visual | Frequency - Per Lot | Category - IP | Responsibility - SE/PE | Verifying Documents - This ITP Signed-off | Date Completed: | Responsibility - Nominated Authority
4.5 | Mounting of Signs | Section 714.07 (d,e,i) IFC Drawings | Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground Signs shall be positioned in accordance with the following tolerances: (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign; (ii) +/-100 mm of the pegged sign location or specified location. When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that: (i) the uphill corner of the sign is a minimum of 800 mm above the ground; (ii) the sign at the longer post is 2200 mm minimum above the ground. Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰) After erection of each sign, all stiffening bars are to be removed. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off | 4.5 - Mounting of Signs | Reference - Section 714.07 (d,e,i) IFC Drawings | Acceptance Criteria - Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground Signs shall be positioned in accordance with the following tolerances: (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign; (ii) +/-100 mm of the pegged sign location or specified location. When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that: (i) the uphill corner of the sign is a minimum of 800 mm above the ground; (ii) the sign at the longer post is 2200 mm minimum above the ground. Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰) After erection of each sign, all stiffening bars are to be removed. | Method - Measure Visual | Frequency - Per Lot | Category - IP | Responsibility - SE/PE | Verifying Documents - This ITP Signed-off | Date Completed: | Verifying Documents - Conqa HP Release
4.6 | Masking of Signs | Section 714.08 | Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign. Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard. | Measure Visual | Per Lot | IP | SE/PE | This ITP Signed-off | 4.6 - Masking of Signs | Reference - Section 714.08 | Acceptance Criteria - Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign. Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard. | Method - Measure Visual | Frequency - Per Lot | Category - IP | Responsibility - SE/PE | Verifying Documents - This ITP Signed-off | Date Completed: | Date Completed:
5.1 | As-built Survey | Section 714.05, IFC Drawings | Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714. (a) Foundations The finished surface of concrete foundations shall be between 50 mm and 100 mm above the finished surface at the base of the sign and shall be shaped to ensure free drainage of water away from the base of the post. (b) Posts (i) Posts shall be straight (ii) Posts shall be vertical with a maximum deviation of 1 in 100 (iii) Post tops shall be 50 mm  10 below the top edge of the sign (c) Signs (i) Signs shall be mounted level with a maximum deviation of 1 in 100. . Attach: Survey Conformance Data/Report | Document Review | Per Lot | IP | Surveyor SE/PE/SPE | This ITP Signed-off | 5.1 - As-built Survey | Reference - Section 714.05, IFC Drawings | Acceptance Criteria - Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714. (a) Foundations The finished surface of concrete foundations shall be between 50 mm and 100 mm above the finished surface at the base of the sign and shall be shaped to ensure free drainage of water away from the base of the post. (b) Posts (i) Posts shall be straight (ii) Posts shall be vertical with a maximum deviation of 1 in 100 (iii) Post tops shall be 50 mm  10 below the top edge of the sign (c) Signs (i) Signs shall be mounted level with a maximum deviation of 1 in 100. . Attach: Survey Conformance Data/Report | Method - Document Review | Frequency - Per Lot | Category - IP | Responsibility - Surveyor SE/PE/SPE | Verifying Documents - This ITP Signed-off | Date Completed: | 3.1 - Check for correct documentation
5.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed-off | 5.2 - Non-conformance Report (NCR) Closure | Reference - MRPA Quality Management Plan | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed. | Method - Document Review | Frequency - Once, prior to closure of this lot / element / Work area | Category - HP* | Responsibility - SE/PE/SPE | Verifying Documents - This ITP Signed-off | Date Completed: | Reference - IFC Drawings
Acceptance Criteria - Ensure that all employees and sub contractors are: - Using the correct and complete set of drawings - All drawings are the latest version
Method - Visual inspection
Frequency - Prior to commencing any activity
Category - HP*
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP Signed-off
Date Completed:
3.1 - Setting Out - Position of Posts and Signs
Reference - Section 714.06 IFC Drawings
Acceptance Criteria - Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Superintendent before the erection of posts
Method - Verify
Frequency - Prior to start
Category - HP*
Responsibility - Surveyor SE/PE Nominated Authority
Verifying Documents - This ITP Signed-off
Date Completed:
4.1 - Foundation
Reference - Section 714.06 ( c) Section 703 Brimbank Standards S520
Acceptance Criteria - All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below: Post sizes 32mm and 50mm nominal bore steel = 225mm diameter Post sizes 80mm to 150mm nominal bore steel = 300mm diameter Frangible hardwood posts 180mm x 100mm = 300mm diameter Concrete Footing should be 300mm diametre and 700mm deep with 25MPa concrete mix as per Brimbank standards S520. Attach: Concrete Delivery Docket
Method - Measure Visual
Frequency - Per Lot
Category - HP*
Responsibility - SE/PE Nominated Authority
Verifying Documents - This ITP Signed-off
Date Completed:
4.2 - Post Installation in Sockets
Reference - Section 714.06 (d) Table 22 of AS 1742.2:2009
Acceptance Criteria - For Post Size 32mm Socket size to be 50mm Nominal Bore Tube For Post Size 50mm Socket size to be 65mm Nominal Bore Tube The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface. The sign post must penetrate a minimum 450 mm into the socket. Depth of the socket should be as per Table 22 of AS 1742.2:2009. The sign post should be securely fixed into the socket by an approved vandal-proof method.
Method - Measure Visual
Frequency - Per Lot
Category - IP
Responsibility - SE/PE
Verifying Documents - This ITP Signed-off
Date Completed:
4.3 - Backfilling of Post Holes
Reference - Section 714.06 e
Acceptance Criteria - 32 and 50 mm Nominal Bore Steel Posts Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa. 180 mm x 100 mm Frangible Hardwood Timber Posts - frangible Hardwood Posts shall be erected in accordance with the drawings; - post-holes for frangible hardwood posts shall be filled with a mixture of gravel and cement (4% by weight) Attach: Delivery Dockets
Method - Verify
Frequency - Per Lot
Category - IP
Responsibility - SE/PE
Verifying Documents - This ITP Signed-off
Date Completed:
4.4 - Sign Fitting
Reference - Section 714.07
Acceptance Criteria - Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows: -Signs up to 200mm in depth – one fitting per post - Signs 201 to 900mm in depth – two fittings per post - Signs 901 to 1200mm in depth – three fittings per post One extra fitting provided per post for each 400mm increment or part thereof above 1200mm.
Method - Measure Visual
Frequency - Per Lot
Category - IP
Responsibility - SE/PE
Verifying Documents - This ITP Signed-off
Date Completed:
4.5 - Mounting of Signs
Reference - Section 714.07 (d,e,i) IFC Drawings
Acceptance Criteria - Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground Signs shall be positioned in accordance with the following tolerances: (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign; (ii) +/-100 mm of the pegged sign location or specified location. When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that: (i) the uphill corner of the sign is a minimum of 800 mm above the ground; (ii) the sign at the longer post is 2200 mm minimum above the ground. Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰) After erection of each sign, all stiffening bars are to be removed.
Method - Measure Visual
Frequency - Per Lot
Category - IP
Responsibility - SE/PE
Verifying Documents - This ITP Signed-off
Date Completed:
4.6 - Masking of Signs
Reference - Section 714.08
Acceptance Criteria - Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign. Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard.
Method - Measure Visual
Frequency - Per Lot
Category - IP
Responsibility - SE/PE
Verifying Documents - This ITP Signed-off
Date Completed:
5.1 - As-built Survey
Reference - Section 714.05, IFC Drawings
Acceptance Criteria - Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714. (a) Foundations The finished surface of concrete foundations shall be between 50 mm and 100 mm above the finished surface at the base of the sign and shall be shaped to ensure free drainage of water away from the base of the post. (b) Posts (i) Posts shall be straight (ii) Posts shall be vertical with a maximum deviation of 1 in 100 (iii) Post tops shall be 50 mm  10 below the top edge of the sign (c) Signs (i) Signs shall be mounted level with a maximum deviation of 1 in 100. . Attach: Survey Conformance Data/Report
Method - Document Review
Frequency - Per Lot
Category - IP
Responsibility - Surveyor SE/PE/SPE
Verifying Documents - This ITP Signed-off
Date Completed:
5.2 - Non-conformance Report (NCR) Closure
Reference - MRPA Quality Management Plan
Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
Method - Document Review
Frequency - Once, prior to closure of this lot / element / Work area
Category - HP*
Responsibility - SE/PE/SPE
Verifying Documents - This ITP Signed-off
Date Completed: