## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
9a Albert Road
Whole Floor
Whole Floor
|  |  | Moisture |  | Floor Preparation - Moisture Fix
Main Entry Hall
|  |  | Floor Prep |  | Floor Preparation
|  |  | Noraplan Rubber |  | Rubber Installation
Main Bathroom
|  |  | Floor Prep |  | Floor Preparation
|  |  | Noraplan Rubber |  | Rubber Installation
Ensuite
|  |  | Floor Prep |  | Floor Preparation
|  |  | Noraplan Rubber |  | Rubber Installation

## Checklist Templates
Type | Name | Values
checklist | Floor Preparation - Moisture Fix
checkpoint | Check area clear of all other trades and their materials
checkpoint | Have moisture readings been taken or is it required | Yes, No
checkpoint | Is the pH level acceptable? | Yes, No
checkpoint | Check the concrete substrate dryness (RH)
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Grind Floor
checkpoint | Does floor have U3 finish (3mm variance over 3m) | Yes, No
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply Moisture Fix
checkpoint | Disc purged material
checkpoint | Apply Floor Levelling Compound
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Floor Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Rubber Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | Confirm materials prior to installation is free of any damage - Advise Project Supervisor if there is | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
section | Installation
checkpoint | Confirm rubber layout direction
checkpoint | Require instruction whether this needs to be acclimatised for a certain time | YES, NO, N/A
checkpoint | Confirm coving location/type if required
checkpoint | Check and measure area | YES, NO, N/A
checkpoint | Follow direction on approved HCF vinyl cut plans | YES, NO, N/A
checkpoint | Ensure the cuts are precise to fit the room dimensions | YES, NO, N/A
checkpoint | All seams to be cold welded as per instruction - check colour match
checkpoint | Glue out floors
checkpoint | Install rubber as per recommendations
checkpoint | Install coving & capping/sealant as applicable
checkpoint | Install & supply transition bars where different flooring types meet if applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)

## Template Guide
TEMPLATE GUIDE
Type | Name | Values
checklist | Template Guide (This is where you type the name/title of your checklist)
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.
PLEASE SHARE YOUR CURRENT ITP/CHECKLIST PACKS FOR US TO DIGITISE OR CREATE YOUR OWN BELOW.