## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation - Moisture Fix
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Have moisture readings been taken or is it required
checkpoint | Is the pH level acceptable?
checkpoint | Check the concrete substrate dryness (RH)
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Grind Floor
checkpoint | Does floor have U3 finish (3mm variance over 3m)
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply Moisture Fix
checkpoint | Disc purged material
checkpoint | Apply Floor Levelling Compound
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Rubber Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | Confirm materials prior to installation is free of any damage - Advise Project Supervisor if there is | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
section | Installation
checkpoint | Confirm rubber layout direction
checkpoint | Require instruction whether this needs to be acclimatised for a certain time
checkpoint | Confirm coving location/type if required
checkpoint | Check and measure area
checkpoint | Follow direction on approved HCF vinyl cut plans
checkpoint | Ensure the cuts are precise to fit the room dimensions
checkpoint | All seams to be cold welded as per instruction - check colour match
checkpoint | Glue out floors
checkpoint | Install rubber as per recommendations
checkpoint | Install coving & capping/sealant as applicable
checkpoint | Install & supply transition bars where different flooring types meet if applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checkpoint-no-status | Actions/Remedial Items
textbox | (if any)
signoff | Verified by CLIENT representative (Full name)