## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-288-CIV-HOP-L-Shape Walls Installation
ITP Description: |  | HOP-L-Shape Walls Installation
Discipline (e.g. CIV/STR/RAIL: |  | 288-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-07-08
ITP created by: |  | Cedric Guico
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Hopkins Road LXRP
Inspection & Test Plan - L- Shape Precast Retaining Wall Installation
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-07-08
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 610 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 610 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | VicRoads Section 620 May 2009 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VicRoads Section 630 October 2013 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Precast Elements | IFC Drawings 610.46 (a), Table 610.463 (November 2018) 610.47 (a) Table 610.473 (March/June 2019) | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019). Note: Different revisions of 610 have different clause numbers Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here) | Document Review | Each element | IP | PE/SE/SPE | This ITP
2.2 | Backing Rod and Joint Sealant | MRPA Quality Management Plan | Details of the backing rod and joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | IP | Nominated Authority | This ITP
3 | Preliminaries-Procedures
3.1 | AC Geo inspection |  | The formation level of the foundations shall be approved by the Geotechnical engineer before placement of blinding concrete commences. Bearing capacity of the founding material of L-shaped retaining wall needs to be verified by the Geotechnical engineer. The founding material is required to have a minimum undrained shear strength of 100 kPa to satisfy the bearing capacity. |  |  |  |  | This ITP
3.2 | Materials Inspection Checklist | 620.06 620.07 MRPA Quality Management Plan | General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings. Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to). Elements shall have unique identification and orientation marked (if applicable). Complete: Materials Inspection Checklist in ConQA | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
4 | Pre-installation Activities
4.1 | Survey Set-out of Precast Elements | IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element. Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance. Wall alignment will be surveyed and marked using control points. If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast. Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
4.2 | Pouring the blinding Concrete | IFC Drawings 610.18 | 50mm of blinding concrete (32Mpa) will be placed over the compacted ground to provide a clean, level, and stable working surface. The blinding is to be saturated before proceeding with precast L-Shape wall installation | Visual | Where applicable, each installation location | IP | Surveyor SE/PE/SPE | This ITP
5 | Installation Activities
5.1 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. JYC will position and align the precast L-wall using crane (type TBC) and rigging equipment which will be as per the approved lift study and it will be added to (07 Lift Study) Only certified riggers and dogmen will handle lifting operations. Lifting clutches will be attached at designated lifting points on the precast units as per Westkon’s Lifting design which will be part of the approved lift study. Verticality of the upright section shall be maintained throughout lifting operations Taglines will be used to control movement of the precast unit. The units will be lifted smoothly and slowly to minimize dynamic loads on the lifting gear. The L-wall will be lowered onto the blinding concrete, ensuring alignment with survey markers. Positioning may be adjusted manually using crowbars if required. | Visual | Each element | IP | SE/PE/SPE | This ITP
5.2 | Precast Placement | IFC Drawings Temporary Works Design 610.27 | Precast elements shall be placed into location or and not released from the crane until sufficiently braced, wedged or restrained by bolted connection, in accordance with the approved Temporary Works Design and/or IFC drawings. Make any adjustments necessary so that alignment between units, minimum end bearing, overall height and position remains in tolerance. The nominal gap between elements is as per the IFC Drawings. To ensure the horizontal alignment on the L-walls are maintained, the precast units will be held together on top using 150x150mm Z-plate and 15mm Z ties + nut: Ensure 20mm gap is in place, as per the IFC drawings | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.3 | Waterstop Seals, Compressible Seals | IFC Drawings Product TDS | Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists. Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings. Once all the Precast Units are tied together, the panels must then be grout flooded underneath to ensure full contact between the underside of the panel and the fill material. The side of the panels will be shuttered or sealed to ensure grout doesn’t flood the entire area. A high early strength grout mix will be delivered on a truck. The grout will be pumped from the top – through the pre-formed holes to ensure the entire space is filled. Grout samples will be tested at 6 hours, 8 hours, 10 hours, 12 hours, 14 hours, 16 hours, 18 hours, 20 hours, 22 hours and 24 hours. 10MPa is required to be achieved on the grout prior to any backfilling works commencing The process will be repeated for each L-wall unit, maintaining consistent joint spacing of 20mm. 20x20mm Proseries Flexi Seal Industrial grade sealant and Expanded Polyethylene backing rod will be installed to all joints along full height of the Precast Panels: | Measure Visual | Where applicable, each installation location | IP | Surveyor SE/PE/SPE | This ITP
5.4 | Subsurface Drainage (Megaflow) | IFC Drawings 702.03 702.06 702.07 702.09 (f) | Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists. The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings. Joints in the drainage shall be over-lapped 450mm min. by the geotextile. Weep holes shall be checked for obstructions. Drainage installation will be completed progressively after each Precast element is installed in the steps outlined below. Prior to commencing the drainage install for the L-Shape wall, the surface of the L-Shape wall will be cleaned to remove dirt, dust, and debris before applying waterproofing. TamSeal 10GM High performance Elastomeric liquid is to be applied to the back of the L-Shape wall using spray as per the manufacturer’s instructions ensuring 2mm target dry film thickness is achieved for proper waterproofing and allowing the membrane to cure. The TamSeal 10GM is to be applied 300mm high up precast wall and 300mm wide along base slab. The 50mm thick blinding layer (either compacted sand or lean mix concrete) will be placed along the base of the L-Shape wall on the TamSeal 10GM, ensuring the surface is level and smooth and allowing sufficient curing time (if concrete is used) before proceeding. The Megaflo Green Drainage System @ 1:200 gradient will be positioned at the base of the L-Shape wall as per the design drawings ensuring proper alignment and connection to the stormwater drainage outlet. The drainage pipe will be secured in place before backfilling with Type A Fill. The Drainmat Geosynthetic medium with A34 Geotextile Fabric will be fixed against the back of the L-wall, ensuring full coverage. The mat will be secured using approved fasteners or adhesive. Free draining granular backfill to VicRoads Spec 702 will be placed on the MegaFlo, wrapped with BIDIM A14 to discharge at a suitable point at end of wall down slope. Install approved Drainmat Geosynethtic Medium with A34 Geotextile Fabroc or Approved Equivalent as per the IFC drawings | Measure Visual | Where applicable, each installation location | IP | Foreman SE/PE/SPE | This ITP
5.5 | Precast Traceability | 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report | Visual | Each element | IP | SE/PE/SPE | This ITP
5.6 | Product Testing - Compressive Strength Cubes | 610.28 610.33 | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Enter: Required information on the Grout Pour Record. | Test | Each element | IP | Tester SE/PE/SPE | This ITP
6 | Post-installation Activities
| Compressive Strength Test Results | IFC Drawings Product TDS | 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Attach: Compressive Strength Test Results | Document Review | Each cube | IP | SE/PE/SPE | This ITP
6.1 | Joint Sealant Application | IFC Drawings | The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod. | Visual | Where applicable, each element | IP | Surveyor SE/PE/SPE | This ITP
6.4 | As-built Survey | IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.5 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
6.6 | Monitoring of L-Shape Wall |  | Allowances shall be made for monitoring of L-Shape wall movements during construction. Minimum two survey markers for each 10m at the top of the wall and middle of the wall (only for wall more than 3m) shall be installed to monitor the displacement in three directions. Monitoring shall be carried out once a week during construction to the end of practical completion and once in every six months following practical completion up to defects liability period by installing Prisms. The construction team to maintain and not damaging the survey markers at all time. | Visual | Where applicable, each element | IP | Surveyor SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /