## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-289-CIV-ADL-Heavy Duty Vehicle Crossing, Shared Use Path and Footpath
ITP Description: |  | ADL-Heavy Duty Vehicle Crossing, Shared Use Path and Footpath
Document Number (in Teambinder):
Discipline (e.g. CIV/STR/RAIL: |  | 289-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-07-09
ITP created by: |  | Abhi Patil
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP to be used at Akuna Dr Only
Inspection & Test Plan - Heavy Duty Vehicle Crossing, Shared Use Path and Footpath
|  |  | Document No.: | 0 |  |  |  |  | Revision: | 0
[9 empty] | Date: | 2025-07-09
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 304 August 2013 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 703 April 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | Council IDM SD 250 IDM SD 236 IDM SD 205 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | AS 1379-2007 | N/A
1.5 | Non Dependent | VicRoads Section 812 July 2016 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.6 | Non Dependent | IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012 | N/A
2 | Preliminaries - Materials
2.1 | Bedding Material Placement & Compaction | IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012 812.04 703.21 | Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK Material is registered with VicRoads in accordance with Code of Practice RC500.02. Enter: Teambinder Material Approval number [free text box] | Document Review | Each Lot | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Concrete Mix | IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.05 (a) 703.07 | Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings: Heavy Duty Vehicle Crossing (PA1): - Concrete Strength: 32Mpa Shared Use Path (F1): - Concrete Strength: 32MPa - Min 30% SCM Footpath (F2) - Concrete Strength: 32MPa - Min 30% SCM - Macro-Synthetic Fibre Reinforced Concrete can be used in lieu of steel reinforcing path given council approval Enter: Teambinder Material Approval number [free text box] | Document Review | Each Lot | HP | Nominated Authority | ConQA Hold Point Release
2.3 | Reinforcement | IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.16 | Reinforcement shall comply with AS4671. Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings: Heavy Duty Vehicle Crossing (PA1): - Two layers of SL82 Mesh (Top Cover Min 60mm) Shared Use Path (F1): - SL82 Mesh Placed Centrally Footpath (F2) - SL72 Mesh (Min 50mm Cover to All Edges) Enter: Teambinder Material Approval number [free text box] | Document Review | Each Lot | HP | Nominated Authority | ConQA Hold Point Release
2.4 | Evaporative Retardant | 703.09 610.17 (f) | Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of concrete | HP | Nominated Authority | This ITP
2.5 | Curing Compound | 703.10 (a) 610.23 (d) | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of concrete | HP | Nominated Authority | This ITP
3 | Preliminaries - Documents
3.1 | Survey Set-out | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.17 | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. The Nominated Authority will review and confirm the set out. Attach: Survey Report | Document Review Measure Visual | Each lot | HP | Nominated Authority | ConQA Hold Point Release
3.2 | Lot Map | MRPA Lot Management Plan | Attach Marked drawing indicating the location of this Lot Attach: Lot Map | Document | Each Lot | HP* | SE/PE | Attached Lot Map
4 | Pre-Construction Activities
4.1 | Site Clearing & Grubbing | IFC Drawings | If not completed during the site establishment, the work area needs to be cleared and grubbed. Complete: Site Clearing & Grubbing ITP before proceeding with this ITP. | Document Review Visual | Where applicable | IP | SE/PE/SPE | This ITP
4.2 | IFC Drawings | MRPA Quality Management Plan | Ensure that all employee and sub contractors are: - Using the correct and complete set of drawings | Document Review | Prior to starting Works and at regular intervals | HP* | SE/PE/SPE | This ITP
5 | Construction Activities
5.1 | Excavation | 703.20 IFC Drawings IDM SD 250 IDM SD 236 IDM SD 205 | Where the new vehicle crossing is proposed at exostomg vehicle crossing locations, the existing granular subbase can be compacted and retained under the new base. Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face. Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face. | Visual Measure | Each lot | IP | SE/PE/SPE | This ITP
5.2 | Excavation-Pavement Thickness Increases for Crossings | 703.21 IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012 Relevant Council drawings: IDM SD 250 IDM SD 236 IDM SD 205 | Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing. Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
5.3 | Bedding Material Placement & Compaction | 703.21 IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012 Relevant Council drawings: IDM SD 250 IDM SD 236 IDM SD 205 | Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings : Heavy Duty Vehicle Crossing (PA1): - 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness) Shared Use Path (F1): - 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness) Footpath (F2) - 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness) Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted. The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary. All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation. Attach: Bedding Material Delivery Dockets | Visual Measure | Each lot | IP | SE/PE/SPE | This ITP
5.4 | Compaction Testing | 703.21 304.08 (a) & (b) 304.11 (a) IDM SD 250 IDM SD 236 IDM SD 205 | Compaction shall meet the following requirements: Scale of Surface Level Measurement = Scale C Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test) Mean Value of Density Ratio % (3 tests) not less than 100% Modified Maxmumum Dried Density (3 tests) not less than 97% Attach: Mean Value of Density Ratio or Modified Maximum Dried Density | Document Review Visual | Where applicable, each lot | IP | SE/PE/SPE | This ITP
5.5 | Formwork Construction & Placement | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.12 | Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance. Joints in formwork shall be constructed such that loss of mortar is prevented. Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation. | Visual Measure | Each lot | IP | SE/PE/SPE | This ITP
5.6 | Construction Joints & Matching Existing Surfaces | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.24 Relevant Council Standard DrawingsRelevant Council drawings: IDM SD 250 IDM SD 236 IDM SD 205 | Where applicable, construction joints shall be placed where the new construction ties into existing structures. Consult the relevant Council Standard drawings for the joint detail, these may require: i. Concrete cutting of a shear-key ii. Surface roughening iii. Drilling and insertion of dowel bars (may also be galvanised) iv. Cutting a groove for sealant Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings. Matching of new to existing concrete paving shall be such that it appears identical to the existing section. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
5.7 | Isolation Joints | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.26 (c) Relevant Council Standard Drawings IDM SD 250 IDM SD 236 IDM SD 205 | Where applicable, isolation joints shall be placed: i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features ii. at any location marked on the drawings The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
5.8 | Expansion Joints | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.26 (a) (ii) & (b) (i) Relevant Council Standard Drawings IDM SD 250 IDM SD 236 IDM SD 205 | Where applicable, expansion joints shall be placed: i. on either side of vehicle crossings ii. at junctions with existing footpaths and shared use paths iii. at junctions with bridges iv. at intervals not exceeding the Council maximum spacings (typically 12m). The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations. Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings. Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
5.9 | Reinforcement Placement | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.13 Relevant Council Standard Drawings IDM SD 250 IDM SD 236 IDM SD 205 | The correct mesh type and location as shown on the IFC drawings. Heavy Duty Vehicle Crossing (PA1): - Two layers of SL82 Mesh (Top Cover Min 60mm) Shared Use Path (F1): - SL82 Mesh Placed Centrally Footpath (F2) - SL72 Mesh (Min 50mm Cover to All Edges) Minimum cover of 50mm at edges has been achieved (including tie wire locations). Any splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum). Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement. | Measure Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.10 | Pre-pour Survey | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.15 | A pre-pour survey carried out by a surveyor. Erected formwork and base layer within the tolerances below: Departure from RL = ±10mm Departure from alignment = ±10mm Rate of change of deviation from RL or alignment = 10mm in 10m Irregularities in alignment = 5mm in 3m Section dimensions = ±5mm Section dimensions (less than 25mm) = ±3mm Width of pavement = -5mm, +15mm Attach: Survey Report | Measure Visual | Each lot | HP* | Surveyor SE/PE/SPE | This ITP
5.11 | Pre-pour Inspection | Section 703.09 Section 703.21 Section 610.17a), b) & c) | Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings. Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface. | Measure Visual | Each lot | HP* | SE/PE/SPE | This ITP
5.12 | Weather Conditions & Evaporation Limits | 703.09 610.17 (a - f) Table 610.171 | Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record. | Measure Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
5.13 | Concrete Testing - Sampling Frequencies Footpath, Industrial Driveway, Traffic Island | 703.11 610.16 (b) AS 1379-2007 Cluse 6.2 | The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade Correct quantity of cylinders manufactured per sample. Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record. | Test | Each lot | IP | Concrete Tester Foreman SE/PE/SPE | This ITP
5.14 | Concrete Testing - Slump | 703.11 610.16 (c) | Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record. | Test | Each sample | IP | Concrete Tester | This ITP
5.15 | Placement & Compaction | 703.08 | All concrete batches are traceable. Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints. Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects. Vibration continued at each point until air bubbles cease to emerge from the concrete. Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets | Visual | Each load | SP | Foreman SE/PE/SPE
5.16 | Surface Finishes | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 Relevant Council Drawings IDM SD 250 IDM SD 236 IDM SD 205 703.25 | Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool. After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor. Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610. All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces | Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
5.17 | Crack-control Joints / Weaken Plane Joints | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 Relevant Council Drawings IDM SD 250 IDM SD 236 IDM SD 205 703.26 (b) (ii) | Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings. | Visual | Where applicable, each lot | IP | Foreman SE/PE/SPE | This ITP
5.18 | Curing | 703.10 | The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these. Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS. The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings. Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred. | Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | Crack-control Joints / Weaken Plane Joints | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 Relevant Council Drawings IDM SD 250 IDM SD 236 IDM SD 205703.26 (b) (ii) | Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures: <20°C = within 24 hours of finishing operations ≥20°C - 35°C = within 4 hours of finishing operations | Visual | Where applicable, each lot | IP | Foreman SE/PE/SPE | This ITP
6.2 | Protection of Newly Poured Concrete | 703.27 | All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause. Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days. | Visual | Where applicable, each lot | IP | Foreman SE/PE/SPE | This ITP
6.3 | Stripping Formwork | 703.12 AS3610 Table C2 | Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete: i. 2 days for vertical formwork on external surfaces; and ii. 1 day for vertical forms on permanently hidden surfaces | Visual | Each lot | IP | Foreman SE/PE/SPE | This ITP
6.4 | Backfilling & Pavement Restoration | 703.29 | At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging. | Visual Measure | Each lot | IP | Foreman SE/PE/SPE | This ITP
6.5 | Surface Inspection - Cracks | 703.3 | No cracks greater than 0.2mm. If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair. | Visual Measure | Where applicable, each lot | IP | SE/PE/SPE | This ITP
6.6 | Surface Inspection - Surface Finish | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 Relevant Council Drawings IDM SD 250 IDM SD 236 IDM SD 205 703.25 703.10 (a) AS3610 Clause 3.2 | After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. Class of finish: Permanently hidden surfaces = Class 4 All other surfaces = Class 3 At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair. | Visual | Each lot | IP | SE/PE/SPE | This ITP
6.7 | Compressive Strength Test Results | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 Relevant Council Drawings 703.11 Table 703.111 | 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results | Document Review | Each cylinder | IP | SE/PE/SPE | This ITP
6.8 | As-built Survey | IFC Drawings MRP-120-C-SME-DRG-12-NPT-CPT-0012 703.15 | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from alignment = ±10mm Rate of change of deviation from RL or alignment = 10mm in 10m Irregularities in alignment = 5mm in 3m Section dimensions = ±5mm Section dimensions (less than 25mm) = ±3mm Width of pavement = -5mm, +15mm Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges. Attach: Survey As-builts / Survey Report | Document Review | Each lot | IP | Surveyor SE/PE/SPE | This ITP
6.9 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /