## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0394 - ITP-008 - In-situ Pits and Culverts REV0 | itp |  |  |  |  | CC0394 - ITP-008 - In-situ Pits and Culverts REV0 | 34b9ca2b-5c5d-4e27-bf49-d08930f8c03f
section | Lot Conformance.
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
textbox | Lot opened date:
textbox | Lot opened by:
textbox | Date lot closed:
button | NCR raised? | Yes, No
textbox | NCR Raised Date:
button | NCR closed? | Yes, No
textbox | NCR Closed Date:
textbox | NCR Number:
textbox | Comments
holdpoint | AUTHORITY HOLDPOINT
section | 1.0 Planning
checkpoint | 1.1 - Determine lot size
label | Acceptance criteria - Lot Size = Each construction stage
label | Acceptance - Refer Lot Map
label | SI Key - S
label | Resp. - SE
label | Remarks / record (e.g., test frequency, reports, certificates, checklist etc) -
bool | Lot Map
checkpoint | 1.2 - Survey Setout
label | Ref docs - IFC Drawings
label | Acceptance criteria - Base of excavation and extents of pits/culverts pinned and checked to be correct line and level per IFC drawings.
button | Acceptance | Yes,No,N/A
label | SI Key - S
label | Resp. - SE
checkpoint | 1.3 - Concrete mix
label | Ref docs - IFC Drawings
label | Acceptance criteria - Confirm correct concrete mix in use prior to commencement of pour
label | Acceptance -
textbox | Concrete mix:
textbox | Strength: |  |  | MPa
textbox | Slump: |  |  | mm
textbox | Aggregate size: |  |  | mm
textbox | Additives:
label | SI Key - H
label | Resp. - SE
section | 2.0 Construction
checkpoint | 2.1 - Install Reinforcement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Reinforcement installed as per IFC Drawings and Specifications.
button | Acceptance | Yes,No,N/A
label | SI Key - H
label | Resp. - SS
label | RJE Global - H
label | Remarks / record (e.g., test frequency, reports, certificates, checklist etc) -
bool | Pre-pour checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Formwork Setout and positioning correct
label | Ref docs - IFC Drawings
label | Acceptance criteria - Formwork installed in accordance with IFC drawings to correct dimensions.
button | Acceptance | Yes,No,N/A
label | SI Key - H
label | Resp. - SS
label | RJE Global - H
label | Remarks / record (e.g., test frequency, reports, certificates, checklist etc) -
bool | Pre-pour checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Concrete jointing
label | Ref docs - IFC Drawings
label | Acceptance criteria - Construction joints to be installed in accordance with Civil Drawings and notes using correct materials.
button | Acceptance | Yes,No,N/A
label | SI Key - H
label | Resp. - SS
checkpoint | 2.4 - Concrete Placement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Check Correct Mix supplied?
textbox | MIX:
label | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | ○ Concrete to be tamped/vibrated to increase density and prevent voids, honeycombing or surface defects.
button | Acceptance | Yes,No,N/A
label | SI Key - S
label | Resp. - SS
label | Remarks / record (e.g., test frequency, reports, certificates, checklist etc) -
bool | Docket
checkpoint | 2.5 - Concrete Testing
label | Ref docs - IFC Drawings
label | Acceptance criteria - Samples to be taken from chute at a frequency of 1 test per 50m3.
label | ○ Each sample shall consist of two cylinder specimens for 28 day testing. Number of samples to be taken from Table 503.051.
button | Acceptance | Yes,No,N/A
label | SI Key - S
label | Resp. - SE
label | Remarks / record (e.g., test frequency, reports, certificates, checklist etc) -
bool | Test report
section | 3.0 Conformance check
checkpoint | 3.1 - Finish
label | Ref docs - IFC Drawings
label | Acceptance criteria - Confirm finish is in accordance with IFC Drawings and specification.
button | Acceptance | Yes,No,N/A
label | SI Key - S
label | Resp. - SS
checkpoint | 3.2 - Visual Inspection
label | Ref docs - IFC Drawings
label | Acceptance criteria - Do not cover or conceal work until it has been inspected by Symal.
button | Acceptance | Yes,No,N/A
label | SI Key - H
label | Resp. - SE
checkpoint | 3.3 - Concrete testing
label | Ref docs - IFC Drawings
label | Acceptance criteria - Confirm specified compressive strength has been achieved
label | Acceptance
textbox | Specified strength: |  |  | MPa
textbox | Result achieved (28 days): |  |  | MPa
label | SI Key - H
label | Resp. - SE
checkpoint | 3.4 - As-Builts
label | Ref docs - IFC Drawings
label | Acceptance criteria - As-built survey of work lot attached.
label | ○ All points within tolerance.
button | Acceptance | Yes,No,N/A
label | SI Key - H
label | Resp. - SE
label | RJE Global - H
label | Remarks / record (e.g., test frequency, reports, certificates, checklist etc) -
bool | As-Built attached
holdpoint | AUTHORITY HOLDPOINT