## Project Structure
Folder Structure |  |  |  | Checklists
Site QA
Ground Floor
OMKT Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
KWH Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
Y-Junction Detail
|  | Metal Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Under Slab Insulation |  | ITP 002 Installation of Soffit Insulation
|  | FF&E Installation |  | ITP 006 FF&E Installation
Fire Stairs
|  |  | Speedpanel Scissor Stair Dividing Wall | ITP 001 Speed Panel
Level 1
1E
|  |  | Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Skirting | ITP 007 Skirting Installation
|  |  | Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Suspended Ceiling Framing & Sheeting | ITP 005 Installation of Ceiling System
|  |  | Balcony Wall and Ceiling- Framing and Sheeting | ITP 003 Installation of Internal Partitions
|  | 1F |  | Same as 1E
Fire Stairs
|  |  | Speedpanel Stair Pressurisation Shaft 1 | ITP 001b Speed Panel
|  |  | Speedpanel Stair Pressurisation Shaft 2 | ITP 001b Speed Panel
|  |  | Speedpanel Scissor Stair Dividing Wall | ITP 001 Speed Panel
Northern Core Risers & Plant Rooms
|  |  | Speedpanel Northern Core Risers & Plant Rooms | ITP 001a Speed Panel
KWH Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Garbage Room Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
Y-Junction Detail
|  | Metal Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Timber Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Under Slab Insulation |  | ITP 002 Installation of Soffit Insulation
|  | FF&E Installation |  | ITP 006 FF&E Installation
Level 2
2A
|  |  | Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Skirting | ITP 007 Skirting Installation
|  |  | Suspended Ceiling Framing & Sheeting | ITP 005 Installation of Ceiling System
|  |  | Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Balcony Wall and Ceiling- Framing and Sheeting | ITP 003 Installation of Internal Partitions
|  | 2B |  | Same as 2A
|  | 2C |  | Same as 2A
|  | 2D |  | Same as 2A
|  | 2E |  | Same as 2A
|  | 2F |  | Same as 2A
|  | 2G |  | Same as 2A
|  | 2H |  | Same as 2A
Fire Stairs
|  |  | Speedpanel Stair Pressurisation Shaft 1 | ITP 001b Speed Panel
|  |  | Speedpanel Stair Pressurisation Shaft 2 | ITP 001b Speed Panel
|  |  | Speedpanel Scissor Stair Dividing Wall | ITP 001 Speed Panel
Northern Core Risers & Plant Rooms
|  |  | Speedpanel Northern Core Risers & Plant Rooms | ITP 001a Speed Panel
OMKT Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Garbage Room Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
KWH Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Garbage Room Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
Y-Junction Detail
|  | Metal Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Timber Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Under Slab Insulation |  | ITP 002 Installation of Soffit Insulation
|  | FF&E Installation |  | ITP 006 FF&E Installation
Level 3
|  | 3A |  | Same as 2A
|  | 3B |  | Same as 2A
|  | 3C |  | Same as 2A
|  | 3D |  | Same as 2A
|  | 3E |  | Same as 2A
|  | 3F |  | Same as 2A
|  | 3G |  | Same as 2A
|  | 3H |  | Same as 2A
Fire Stairs
|  |  | Speedpanel Stair Pressurisation Shaft 1 | ITP 001b Speed Panel
|  |  | Speedpanel Stair Pressurisation Shaft 2 | ITP 001b Speed Panel
|  |  | Speedpanel Scissor Stair Dividing Wall | ITP 001 Speed Panel
Northern Core Risers & Plant Rooms
|  |  | Speedpanel Northern Core Risers & Plant Rooms | ITP 001a Speed Panel
OMKT Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Garbage Room Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
KWH Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Framing | ITP 003 Installation of Internal Partitions
|  |  | Garbage Room Suspended Ceiling Sheeting | ITP 005 Installation of Ceiling System
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
Y-Junction Detail
|  | Metal Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Timber Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | FF&E Installation |  | ITP 006 FF&E Installation
| Level 5 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 6 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 7 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 8 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 9 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 10 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 11 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 12 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 13 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 15 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 16 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 17 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 18 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 19 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 20 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 21 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 22 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 23 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 25 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 26 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 27 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 28 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
| Level 29 |  |  | Same as Level 3 (change room numbers to match level, rooms numbers highlighted)
Level 30
|  | 30A |  | Same as 2A
|  | 30B |  | Same as 2A
|  | 30C |  | Same as 2A
|  | 30D |  | Same as 2A
30E
30F
30G
30H
Fire Stairs
|  |  | Speedpanel Stair Pressurisation Shaft 1 | ITP 001b Speed Panel
|  |  | Speedpanel Stair Pressurisation Shaft 2 | ITP 001b Speed Panel
|  |  | Speedpanel Scissor Stair Dividing Wall | ITP 001 Speed Panel
Northern Core Risers & Plant Rooms
|  |  | Speedpanel Northern Core Risers & Plant Rooms | ITP 001a Speed Panel
OMKT Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
Fire Stairs2
Y-Junction Detail
|  | Metal Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Timber Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Under Slab Insulation |  | ITP 002 Installation of Soffit Insulation
|  | FF&E Installation |  | ITP 006 FF&E Installation
Level 31
|  | 31A |  | Same as 2A
|  | 31B |  | Same as 2A
|  | 31C |  | Same as 2A
|  | 31D |  | Same as 2A
Fire Stairs
|  |  | Speedpanel Stair Pressurisation Shaft 1 | ITP 001b Speed Panel
|  |  | Speedpanel Stair Pressurisation Shaft 2 | ITP 001b Speed Panel
|  |  | Speedpanel Scissor Stair Dividing Wall | ITP 001 Speed Panel
Northern Core Risers & Plant Rooms
|  |  | Speedpanel Northern Core Risers & Plant Rooms | ITP 001a Speed Panel
OMKT Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
KWH Corridor
|  |  | Corridor Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
|  |  | Corridor Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Suspended Ceiling Framing& Sheeting | ITP 005 Installation of Ceiling System
|  |  | Garbage Room Wall Framing & Sheeting | ITP 003 Installation of Internal Partitions
Fire Stairs2
Y-Junction Detail
|  | Metal Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | Timber Door Frame Installation |  | ITP 004 Door and Door Hardware Installation
|  | FF&E Installation |  | ITP 006 FF&E Installation
| Level 32 |  |  | Same as Level 31 (change room numbers to match level, rooms numbers highlighted)but adding Under Slab Insulation
|  | Under Slab Insulation |  | ITP 002 Installation of Soffit Insulation

## Checklists
type | name | values
checklist-flat | ITP 001 Speed Panel
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Panels installed as manufacturer's specifications
label | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Comprehensive first of type inspection
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist-flat | ITP 001a Speed Panel
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Panels installed as manufacturer's specifications
label | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Penetration cut, trimmed and sealed as per builder' drawings
label | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Door Frame installed as per manufacture's specification
label | Acceptance Criteria: Plumb, square and same height, core-filled
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Flashing head-protection
label | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Comprehensive first of type inspection
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist-flat | ITP 001b Speed Panel
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Panels installed as manufacturer's specifications
label | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Penetration cut, trimmed and sealed as per builder' drawings
label | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Door Frame installed as per manufacture's specification
label | Acceptance Criteria: Plumb, square and same height, core-filled
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Flashing head-protection
label | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Fully sealed joints one side in pressurized shaft
label | Acceptance Criteria: Continues beads
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: H
label | Lendlease Inspection Code: H
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Comprehensive first of type inspection
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist | ITP 002 Installation of Soffit Insulation
section | Materials delivery
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1.
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
section | Under Slab Insulation
checkpoint | Insulation dimension checked against drawings and Setout; Insulation types confirmed against Insulation set out plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Series: BR3ADS2-Insulation Ceiling Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | The foil surface of the insulation board should face down
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Fix insulation panel to concrete soffits with minimum 5 No. Appropriate insulation fasteners with a minimum head diameter of 35 mm
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Tape board joints with a minimum 96mm wide appropriate aluminium foil tape, detail as per attached Installation Instructions
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Exposed board edge covered with foil tape lapped 48mm on to underside
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Check against cast-in penetrations. All penetrations/collars/dampers to be fully exposed
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist | ITP 003 Installation of Internal Partitions
section | Wall Framing
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Wall framing completed to Rondo designs, checked for square, plumb and twisting
label | Acceptance Criteria: slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Allowance for access panels and service penetration
label | Acceptance Criteria: Bridging Track supported by offcut studs
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | Acceptance Criteria: Jamb header or sill used correct components
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Plywood Noggins and structural stud installed for all fixtures
label | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | Acceptance Criteria: Plumb, square and same height, core-filled
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
section | Wall Sheeting
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Caulking to acoustic / fire / smoke/ details.
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Penetration sheeted and sealed as per builder' drawings
label | Acceptance Criteria: Opening square and flush, fully sealed
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
section | Sheeting (Close Wall)
checkpoint | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Insulation completed as per acoustic report, partition plans and spec
label | Acceptance Criteria: As required Insulation, no gap can be seen
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Plywood Noggins and structural stud installed for all FFE
label | Acceptance Criteria: Checked against current RLS
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL2Internal Architectural Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Close wall
label | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Caulking to acoustic / fire / smoke/ details
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Set and sand ready for painting
label | Acceptance Criteria: Meet Level 4 of finish requirement
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Siniat & Rondo Inspection
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist-flat | ITP 004 Door and Door Hardware Installation
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Opening dimension checked against drawings and Setout, Door types and leaf size confirmed against partition plan
label | Acceptance Criteria: Latest Drawing Revision Checked
label | References: Series:BR3ADB2-Wall Setout Plans; Door Schedule - BR3AT1332[C2]
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Door frame installed as manufacturer's specification to Top, bottom and both sides
label | Acceptance Criteria:Straight and plumb and square, no sharp edge, gap less than 20mm, sealed with silicone
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Door Hardware Installation and Check
label | Acceptance Criteria: Correct Hardware type followed as shop drawings. All of door hardware followed the finish Schedule
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Door Smoke sealed cabinet
label | Acceptance Criteria: Latest Drawing Revision Checked
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist | ITP 005 Installation of Ceiling System
section | Ceiling Framing
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Ceiling framing dimension and FCL checked against drawings and Setout, Ceiling types confirmed against RCPs
label | Acceptance Criteria: Latest Drawing Revision Checked
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADG1-Reflected Ceiling Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | All above-ceiling services are installed and ready for ceiling framing
label | Acceptance Criteria: Confirm with Lendlease that all wall service rough ins have been completed and approved prior to sheeting
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Ceiling framing completed as Rondo designs
label | Acceptance Criteria: Suspending point max 1200mm*1200mm Grid, TCR @max 600 space and max200 from wall, FC @max 600 space and max 100 from wall. Correctly braced. Two sides fixed and two sides free
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Bulkhead and Bracing completed as Kanuf designs
label | Acceptance Criteria: Anchor used with Load sharing washer
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Allowance for access panels and service penetration (Lights and Grill)
label | Acceptance Criteria: Framing not in the way of services or AP
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Coordinated RCP drawing series
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Timber Noggins and Ceiling support installed as required
label | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
section | Close Ceiling
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Check all services roughed in and not using ceiling frame as a support, all seismic supports have been installed for service by others, ceiling closeout checklist received by Lendlease
label | Acceptance Criteria: Minimum 3mm gap kept from ceiling frame
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Installation of acoustic insulation to the ceiling
label | Acceptance Criteria: acoustic insulation must extend 900mm from acoustic wall
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADS2-Insulation Ceiling Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as pec
label | Acceptance Criteria: Staged Fixing @200mm max centre at edges, fixing @300mm max centre in field, Staged butt joint by 600mm min. Back blocking battens used on butt joints
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Access panel installed as required
label | Acceptance Criteria: Correct location, square with wall or bulkhead
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Caulking to acoustic / fire / smoke/ details.
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Set and sand ready for painting
label | Acceptance Criteria: No bubbles, no lump, square, not over sanded
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Siniat&Rondo Inspection
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist | ITP 006 FF&E Installation
section | Materials
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
section | FFE Installation
checkpoint | All of FFE Products must approved by Lendlease
label | Acceptance Criteria: Sample Form Approval Finish Schedule
label | References:Series: BR3ADL2-Internal Architectural Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | All of FFE products have to supported by Noggins
label | Acceptance Criteria: Noggin Markup Plan
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | No unreasonable gap or holes on the wall
label | Acceptance Criteria: Eye Inspection
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Height and location must follow the requirement
label | Acceptance Criteria: Noggin Markup Plan
label | References: Series: BR3ADL2-Internal Architectural Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | FFE installation should not affect the wall finish. The wall with good patching as well
label | Acceptance Criteria: Eye Inspection
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checklist | ITP 007 Skirting Installation
checkpoint | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Set out Timber skirting size & type as per wall finish set out plan
label | Acceptance Criteria: Latest Drawing Revision Checked
label | References:Series: BR3ADL2-Internal Architectural Details; BR3ADB2-Wall Setout Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Timber skirting installed as manufacturer's specification to Top, bottom side
label | Acceptance Criteria: Straight and plumb and square, no sharp edge, gap less than 3mm, sealed with silicone Ref
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | No unreasonable gap or holes on the wall
label | Acceptance Criteria: Eye Inspection
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | Timber skirting fixing and inspect for damage prior to hand over
label | Acceptance Criteria: Inspected and approved
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result: