## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Stormwater Risers |  |  |  |  | Yes | QA - Stormwater Risers | 1aa190a2-c235-4ff3-91d5-86eaea352d53
checkpoint-status |  |  | checkpoint | Stormwater riser installed
checkpoint-status |  |  | checkpoint | Tested and passed
checklist-flat |  |  | checklist | Water Risers |  |  |  |  | Yes | QA - Water Risers | 27395220-d173-4ae4-bbde-d109aa06dab8
checkpoint-status |  |  | checkpoint | Water riser installed
checkpoint-status |  |  | checkpoint | Manifold installed
checkpoint-status |  |  | checkpoint | Tested and passed
checklist-sectioned |  |  | checklist | Plumbing Fitoff |  |  |  |  | Yes | QA - Plumbing Fitoff | 42255fcd-789f-4273-a885-c035373b4d72
checkpoint-group |  |  | section | Area readiness
checkpoint-status |  |  | checkpoint | Is the area ready for fitoff?
checkpoint-group |  |  | section | Wash Hand Basin
checkpoint-status |  |  | checkpoint | Wash hand basin is installed
checkpoint-status |  |  | checkpoint | Basin level and secure
checkpoint-status |  |  | checkpoint | Waste connection watertight, plug supplied
checkpoint-status |  |  | checkpoint | Water connection watertight, tap secure
checkpoint-status |  |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-group |  |  | section | Toilet
checkpoint-status |  |  | checkpoint | Toilet is installed
checkpoint-status |  |  | checkpoint | Securely fixed, silicone at floor
checkpoint-status |  |  | checkpoint | Flush and cistern fill operation checked
checkpoint-status |  |  | checkpoint | Water connection watertight – cold water
checkpoint-group |  |  | section | Shower
checkpoint-status |  |  | checkpoint | Shower is installed
checkpoint-status |  |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-status |  |  | checkpoint | Waste clear
checkpoint-status |  |  | checkpoint | Cover plate fixed securely
checkpoint-group |  |  | section | Bath/Shower
checkpoint-status |  |  | checkpoint | Bath/shower is installed
checkpoint-status |  |  | checkpoint | Waste clear, plug installed
checkpoint-status |  |  | checkpoint | Divertor operation working (where applicable)
checkpoint-status |  |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-status |  |  | checkpoint | Cover plate/spout fixed securely
checkpoint-status |  |  | checkpoint | FWG
checkpoint-status |  |  | checkpoint | Grate flush with floor or slightly below
checkpoint-status |  |  | checkpoint | Waste clear of debris
checkpoint-group |  |  | section | Amenity Areas / Kitchens etc.
checkpoint-status |  |  | checkpoint | Amenity areas / kitchens etc. are installed
checkpoint-status |  |  | checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint-status |  |  | checkpoint | Water connection watertight, tap secure
checkpoint-status |  |  | checkpoint | Waste connection watertight
checkpoint-status |  |  | checkpoint | Dishwasher connection watertight
checkpoint-status |  |  | checkpoint | Wastemaster connection watertight
checkpoint-status |  |  | checkpoint | Overflow connection watertight
checkpoint-status |  |  | checkpoint | Waste clear, plug installed
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Council Verification
holdpoint |  |  | signoff | Plumbing inspection complete and passed as satisfactory
checkpoint-status |  |  | checkpoint | South Auckland Plumbing Verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checkpoint-status |  |  | checkpoint | Main Contractor verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checklist-sectioned |  |  | checklist | Plumbing Preline |  |  |  |  | Yes | QA - Plumbing Preline (Ground Floor) | 5fc3bafc-9d9f-46a8-9c62-d41837b8ea6a
checkpoint-group |  |  | section | Preline
checkpoint-status |  |  | checkpoint | Area accesible
checkpoint-status |  |  | checkpoint | Area readiness - is the area ready for preline?
checkpoint-status |  |  | checkpoint | Floor peno marked
checkpoint-status |  |  | checkpoint | Nogs marked
checkpoint-status |  |  | checkpoint | Stackwork installed
checkpoint-status |  |  | checkpoint | Pipeout installed
checkpoint-status |  |  | checkpoint | Pipework securely clipped
checkpoint-status |  |  | checkpoint | Acoustic lagging installed
checkpoint-status |  |  | checkpoint | Thermal lagging installed
checkpoint-status |  |  | checkpoint | Fire collars installed
checkpoint-status |  |  | checkpoint | Outlets correct height - waste
checkpoint-status |  |  | checkpoint | Outlets correct height - water
checkpoint-status |  |  | checkpoint | Shower tray / flange installed
checkpoint-status |  |  | checkpoint | Floor flanges installed
checkpoint-status |  |  | checkpoint | Projection of mixers etc correct distance past finished wall
checkpoint-status |  |  | checkpoint | Nogs for second fix installed
checkpoint-group |  |  | section | Corridor Mains
checkpoint-status |  |  | checkpoint | Corridor mains run to riser
checkpoint-status |  |  | checkpoint | Corridor mains connected to riser
checkpoint-group |  |  | section | Balcony Downpipes
checkpoint-status |  |  | checkpoint | Balcony riser run / installed
checkpoint-status |  |  | checkpoint | Balcony downpipe and overflow installed
checkpoint-status |  |  | checkpoint | Balcony flange installed
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Hot Water
text | 0a7e6990-34d4-5e6b-8220-9ff9e7b68c85 |  | textbox | Specified to |  |  | kPa
text | edb22a3c-7195-5062-8531-6d1269bffccf |  | textbox | Test pressure |  |  | kPa
text | 8936ac49-6261-5cf7-bab2-85266525f880 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Cold Water
text | 85e83231-f333-55a5-8d6f-fc52f3a87fec |  | textbox | Specified to |  |  | kPa
text | b00d80c2-d1b8-5448-b2fe-5b819712a54c |  | textbox | Test pressure |  |  | kPa
text | 4b8d5bef-b38d-5a07-aeda-e7d8c4b5d44d |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Soil/Waste Pipes
text | db812c24-d936-5f70-918d-3a88eda97f71 |  | textbox | Specified to |  |  | kPa
text | 441e13c1-c1a9-5973-93eb-fcde43d34a77 |  | textbox | Test pressure |  |  | kPa
text | 49db7bde-617a-590f-b278-1a6b75060458 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Vent Pipes
text | 75d7c7be-3bfc-5d02-892d-7291b11f0cf1 |  | textbox | Specified to |  |  | kPa
text | a8d4f3ec-97d8-5ad1-a8cc-83ee27278bdf |  | textbox | Test pressure |  |  | kPa
text | 16589937-2658-5bd9-a43f-87934b0df083 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Gas Services
text | 44d0d2f9-10de-59cd-9228-3d5e879736b4 |  | textbox | Specified to |  |  | kPa
text | 995fb99f-7ef2-58f4-84a6-a89272bbd813 |  | textbox | Test pressure |  |  | kPa
text | 967ad462-d583-5be8-b038-29f3d809cdc4 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Other
text | 5a708367-96ee-5192-8041-3392729d086e |  | textbox | (specify other)
text | d04e9083-c67e-5c6e-b27c-01727e7323d1 |  | textbox | Specified to |  |  | kPa
text | c9a00fad-1f26-57f0-8082-e1fd2bc8c61c |  | textbox | Test pressure |  |  | kPa
text | 01006ed5-f4c2-51d1-930b-1fa769ad46a5 |  | textbox | Duration
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Council Verification
holdpoint |  |  | signoff | Plumbing inspection complete and passed as satisfactory
checkpoint-status |  |  | checkpoint | South Auckland Plumbing Verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checkpoint-status |  |  | checkpoint | Main Contractor verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checklist-sectioned |  |  | checklist | Hallways |  |  |  |  | Yes | QA - Plumbing Preline (Hallways) | 72810e84-bde1-41e1-82ea-eb4bf17421a9
checkpoint-group |  |  | section | Preline
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Area readiness - is the area ready for preline?
checkpoint-status |  |  | checkpoint | Floor peno marked
checkpoint-status |  |  | checkpoint | Nogs marked
checkpoint-status |  |  | checkpoint | Stackwork installed
checkpoint-status |  |  | checkpoint | Pipeout installed
checkpoint-status |  |  | checkpoint | Pipework securely clipped
checkpoint-status |  |  | checkpoint | Acoustic lagging installed
checkpoint-status |  |  | checkpoint | Thermal lagging installed
checkpoint-status |  |  | checkpoint | Fire collars installed
checkpoint-status |  |  | checkpoint | Outlets correct height - waste
checkpoint-status |  |  | checkpoint | Outlets correct height - water
checkpoint-status |  |  | checkpoint | Shower tray / flange installed
checkpoint-status |  |  | checkpoint | Floor flanges installed
checkpoint-status |  |  | checkpoint | Projection of mixers etc correct distance past finished wall
checkpoint-status |  |  | checkpoint | Nogs for second fix installed
checkpoint-status |  |  | checkpoint | Pipework securely fixed
checkpoint-status |  |  | checkpoint | Lagging installed to Hot Flow and Return
checkpoint-status |  |  | checkpoint | Seismic installed (add a N/A to this)
checkpoint-status |  |  | checkpoint | All rooms connected to mains
checkpoint-group |  |  | section | Corridor Mains
checkpoint-status |  |  | checkpoint | Corridor mains run to riser
checkpoint-status |  |  | checkpoint | Corridor mains connected to riser
checkpoint-group |  |  | section | Balcony Downpipes
checkpoint-status |  |  | checkpoint | Balcony riser run / installed
checkpoint-status |  |  | checkpoint | Balcony downpipe and overflow installed
checkpoint-status |  |  | checkpoint | Balcony flange installed
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Hot Water
text | 7014e45e-d3bb-5473-ba65-89925dc6391b |  | textbox | Specified to |  |  | kPa
text | c9825a00-3483-54c2-9604-dabb5443c5c6 |  | textbox | Test pressure |  |  | kPa
text | 633fd4af-e7ac-5474-9254-c8b95aae9696 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Cold Water
text | 0496f4a7-e8ea-5287-9fc3-24555f69e848 |  | textbox | Specified to |  |  | kPa
text | e1561ad8-92a5-53b3-9308-618d28be84a6 |  | textbox | Test pressure |  |  | kPa
text | d8e29379-b8b8-55fa-93f7-14492c8a038b |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Soil/Waste Pipes
text | 31754545-0f8e-5d86-8b11-b407b3396471 |  | textbox | Specified to |  |  | kPa
text | 66f59a06-a157-5338-b6af-37ae753b00fb |  | textbox | Test pressure |  |  | kPa
text | d8b46f74-b71e-5c95-8d9e-1aac503a0d23 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Other
text | da02fc33-739f-5c57-8b68-c0f70829f6a4 |  | textbox | (specify other)
text | 5897cebf-19b1-5fcc-8925-0ee934f578eb |  | textbox | Specified to |  |  | kPa
text | 7133c66d-9c5f-5cb8-9756-dc7b39d59a3d |  | textbox | Test pressure |  |  | kPa
text | 72a381c0-d96a-5246-9323-2a07ad973b9b |  | textbox | Duration
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Council Verification
holdpoint |  |  | signoff | Plumbing inspection complete and passed as satisfactory
checkpoint-status |  |  | checkpoint | South Auckland Plumbing Verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checkpoint-status |  |  | checkpoint | Main Contractor verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checklist-sectioned |  |  | checklist | Plumbing Preline |  |  |  |  | Yes | QA - Plumbing Preline (Levels) | 7bf7d7f3-d25e-46d7-964a-c64b60c34383
checkpoint-group |  |  | section | Preline
checkpoint-status |  |  | checkpoint | Area accesible
checkpoint-status |  |  | checkpoint | Area readiness - is the area ready for preline?
checkpoint-status |  |  | checkpoint | Floor peno marked
checkpoint-status |  |  | checkpoint | Nogs marked
checkpoint-status |  |  | checkpoint | Stackwork installed
checkpoint-status |  |  | checkpoint | Pipeout installed
checkpoint-status |  |  | checkpoint | Pipework securely clipped
checkpoint-status |  |  | checkpoint | Acoustic lagging installed
checkpoint-status |  |  | checkpoint | Thermal lagging installed
checkpoint-status |  |  | checkpoint | Fire collars installed
checkpoint-status |  |  | checkpoint | Outlets correct height - waste
checkpoint-status |  |  | checkpoint | Outlets correct height - water
checkpoint-status |  |  | checkpoint | Shower tray / flange installed
checkpoint-status |  |  | checkpoint | Floor flanges installed
checkpoint-status |  |  | checkpoint | Projection of mixers etc correct distance past finished wall
checkpoint-status |  |  | checkpoint | Nogs for second fix installed
checkpoint-group |  |  | section | Corridor Mains
checkpoint-status |  |  | checkpoint | Corridor mains run to riser
checkpoint-status |  |  | checkpoint | Corridor mains connected to riser
checkpoint-group |  |  | section | Balcony Downpipes
checkpoint-status |  |  | checkpoint | Balcony riser run / installed
checkpoint-status |  |  | checkpoint | Balcony downpipe and overflow installed
checkpoint-status |  |  | checkpoint | Balcony flange installed
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Hot Water
text | cb8ed47b-c7da-5ed1-8204-9c72405f29bb |  | textbox | Specified to |  |  | kPa
text | d5eb18e7-cd5a-5d8a-a9e1-4269f1e385af |  | textbox | Test pressure |  |  | kPa
text | 82281a5f-a280-5c1b-9e70-d9c606f01b65 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Cold Water
text | 764ec242-5f25-5f1b-9083-0c511f8553d0 |  | textbox | Specified to |  |  | kPa
text | 1f2186b4-6b25-53ab-8f52-e7173b75d1b3 |  | textbox | Test pressure |  |  | kPa
text | 3ea0f32e-7753-5ac6-b3d0-99a75e1408dc |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Soil/Waste Pipes
text | b0a9939c-3a55-56d8-ae48-718d0cad6f6c |  | textbox | Specified to |  |  | kPa
text | 9ee4c273-1623-5ce8-91ea-a0e3505c51a0 |  | textbox | Test pressure |  |  | kPa
text | a5b3820c-4d4e-553f-8b20-60bb86494af4 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Other
text | be3ae5a7-f7f4-5659-8a77-6fd1482bf1d4 |  | textbox | (specify other)
text | 4cad228a-a623-55d5-98ee-c4a0d33dd057 |  | textbox | Specified to |  |  | kPa
text | 7ec56bc1-2a7e-556d-941f-e44eac14615f |  | textbox | Test pressure |  |  | kPa
text | 66bc4fbf-46d9-5391-a859-36601e36c054 |  | textbox | Duration
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Council Verification
holdpoint |  |  | signoff | Plumbing inspection complete and passed as satisfactory
checkpoint-status |  |  | checkpoint | South Auckland Plumbing Verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checkpoint-status |  |  | checkpoint | Main Contractor verification
holdpoint |  |  | signoff | Plumbing Complete and ready for lining
checklist-flat |  |  | checklist | Sewer Risers |  |  |  |  | Yes | QA - Sewer Risers | 9d2f18e2-4c37-4958-aa49-2d0ccd2e8be5
checkpoint-status |  |  | checkpoint | Sewer riser installed
checkpoint-status |  |  | checkpoint | Tested and passed
checklist-sectioned |  |  | checklist | Underslab |  |  |  |  | Yes | QA - Underslab | dcb00195-268e-45da-b762-1fdaf1ba80e5
checkpoint-group |  |  | section | Pipework
checkpoint-status |  |  | checkpoint | Service
select | 35eaf756-aebf-5294-b365-3aa4266da72b |  | dropdown | Service being checked | Stormwater, Waste Water, Gas, Water supply, Other
text | e8f7454a-37f0-5e8a-b029-bc56bfee2b8c |  | textbox | (specify other)
checkpoint-status |  |  | checkpoint | Pipework Material as specified/scheduled/drawn
checkpoint-status |  |  | checkpoint | Grid lines and fitting dimensions confirmed
checkpoint-status |  |  | checkpoint | Drain invert checked
checkpoint-status |  |  | checkpoint | Gully position checked
checkpoint-status |  |  | checkpoint | Floor levels established
checkpoint-status |  |  | checkpoint | Falls checked
checkpoint-status |  |  | checkpoint | Drainlayer/Plumber interface Points established
checkpoint-status |  |  | checkpoint | Penetrations co-ordinated with main contractor
checkpoint-status |  |  | checkpoint | Pipework backfilled correctly
checkpoint-status |  |  | checkpoint | Identification strip installed if required
checkpoint-status |  |  | checkpoint | Open ends of pipework capped off to prevent dirt ingress
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | Cold Water
text | 04c0042c-f4bb-5fc6-b1e9-09184a0da7f4 |  | textbox | Specified to |  |  | kPa
text | 469012a0-65e6-5e63-ac00-265d00b1d8af |  | textbox | Test pressure |  |  | kPa
text | 24887bc1-904c-52a0-8f28-1c112d7659fa |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Waste water
text | 771ffb8a-37ac-5bd8-a2df-d848d28f7dfc |  | textbox | Specified to |  |  | kPa
text | 1b8dc31d-d57b-5ea9-8a02-c477dff887b6 |  | textbox | Test pressure |  |  | kPa
text | 97458a3f-46e6-52bc-83f8-e8c284df6f8d |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Gas Services
text | d28f1b82-70d6-5472-aade-61fcd65f73e0 |  | textbox | Specified to |  |  | kPa
text | 5fd315eb-b4b9-5ace-97f2-73a81ce31469 |  | textbox | Test pressure |  |  | kPa
text | 3cb5baec-e6b0-5801-9cfb-416510ad21a8 |  | textbox | Duration
checkpoint-status |  |  | checkpoint | Other
text | 3913d5c6-3c7c-5f8c-954a-cea1081ddfb3 |  | textbox | (specify other)
text | fb130977-9c5b-5858-97dd-0cb1a8bc86c0 |  | textbox | Specified to |  |  | kPa
text | b2cdc9ef-c76f-53a9-b8c1-59ce32e3b1da |  | textbox | Test pressure |  |  | kPa
text | 377ee419-a706-5234-be59-74528e799219 |  | textbox | Duration
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Council Verification
holdpoint |  |  | signoff | Plumbing inspection complete and passed as satisfactory
checkpoint-status |  |  | checkpoint | South Auckland Plumbing Verification
holdpoint |  |  | signoff | Plumbing Complete and ready for backfill/ concrete pour
checkpoint-status |  |  | checkpoint | Main Contractor verification
holdpoint |  |  | signoff | Plumbing Complete and ready for backfill/ concrete pour