## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Preline Progress
| Scope |  |  | Preline
Rows
|  | First Fix - Ground Floor - Region A | dynamic | First Fix | Ground Floor | Preline | Region A
|  | First Fix - Ground Floor - Region B | dynamic | First Fix | Ground Floor | Preline | Region B
|  | First Fix - Ground Floor - Region C | dynamic | First Fix | Ground Floor | Preline | Region C
|  | First Fix - Level 1 - Region A | dynamic | First Fix | Level 1 | Preline | Region A:
|  | First Fix - Level 1 - Region B | dynamic | First Fix | Level 1 | Preline | Region B
|  | First Fix - Level 1 - Region C | dynamic | First Fix | Level 1 | Preline | Region C
|  | First Fix - Level 2 - Region A | dynamic | First Fix | Level 2 | Preline | Region A
|  | First Fix - Level 2 - Region B | dynamic | First Fix | Level 2 | Preline | Region B
|  | First Fix - Level 2 - Region C | dynamic | First Fix | Level 2 | Preline | Region C
Columns
|  | Hallways - Area accessible |  | Area accessible | Preline
|  | Levels - Area accessible |  | Area accesible | Preline
|  | Area ready for preline? |  | Area readiness - is the area ready for preline? | Preline
|  | Floor peno marked |  | Floor peno marked | Preline
|  | Nogs marked |  | Nogs marked | Preline
|  | Stackwork installed |  | Stackwork installed | Preline
|  | Pipeout installed |  | Pipeout installed | Preline
|  | Pipework securely clipped |  | Pipework securely clipped | Preline
|  | Acoustic lagging installed |  | Acoustic lagging installed | Preline
|  | Thermal lagging installed |  | Thermal lagging installed | Preline
|  | Fire collars installed |  | Fire collars installed | Preline
|  | Outlets correct height - waste |  | Outlets correct height - waste | Preline
|  | Outlets correct height - water |  | Outlets correct height - water | Preline
|  | Shower tray/flange installed |  | Shower tray / flange installed | Preline
|  | Floor flanges installed |  | Floor flanges installed | Preline
|  | Projection of mixers |  | Projection of mixers etc correct distance past finished wall | Preline
|  | Nogs for second fix installed |  | Nogs for second fix installed | Preline
|  | Pipework securely fixed |  | Pipework securely fixed | Preline
|  | Lagging installed to Hot Flow & Return |  | Lagging installed to Hot Flow and Return | Preline
|  | Seismic installed |  | Seismic installed (add a N/A to this) | Preline
|  | All rooms connected to mains |  | All rooms connected to mains | Preline
|  | Corridor mains run to riser |  | Corridor mains run to riser | Corridor Mains
|  | Corridor mains connected to riser |  | Corridor mains connected to riser | Corridor Mains
|  | Balcony riser run/installed |  | Balcony riser run / installed | Balcony Downpipes
|  | Balcony downpipe & overflow installed |  | Balcony downpipe and overflow installed | Balcony Downpipes
|  | Balcony flange installed |  | Balcony flange installed | Balcony Downpipes
|  | Hot Water |  | Hot Water | Testing
|  | Cold Water |  | Cold Water | Testing
|  | Soil/Waste Pipes |  | Soil/Waste Pipes | Testing
|  | Other |  | Other | Testing
|  | Area left clean & tidy |  | Area left clean and tidy | Handover
|  | Council Verification |  | Council Verification | Handover
|  | South Auckland Plumbing Verification |  | South Auckland Plumbing Verification | Handover
|  | Main Contractor verification |  | Main Contractor verification | Handover
Fitoff Progress
| Scope |  |  | second fix
Rows
|  | Second Fix - Ground Floor - Region A | dynamic | Site QA | Second Fix | Ground Floor | Region A
|  | Second Fix - Ground Floor - Region B | dynamic | Site QA | Second Fix | Ground Floor | Region B
|  | Second Fix - Ground Floor - Region C | dynamic | Site QA | Second Fix | Ground Floor | Region C
|  | Second Fix - Level 1 - Region A | dynamic | Site QA | Second Fix | Level 1 | Region A:
|  | Second Fix - Level 1 - Region B | dynamic | Site QA | Second Fix | Level 1 | Region B
|  | Second Fix - Level 1 - Region C | dynamic | Site QA | Second Fix | Level 1 | Region C
|  | Second Fix - Level 2 - Region A | dynamic | Site QA | Second Fix | Level 2 | Region A
|  | Second Fix - Level 2 - Region B | dynamic | Site QA | Second Fix | Level 2 | Region B
|  | Second Fix - Level 2 - Region C | dynamic | Site QA | Second Fix | Level 2 | Region C
Columns
|  | Is the area ready for fitoff? |  | Is the area ready for fitoff? | Area readiness
|  | Wash hand basin is installed |  | Wash hand basin is installed | Wash Hand Basin
|  | Basin level & secure |  | Basin level and secure | Wash Hand Basin
|  | Wash Hand Basin - Waste conn. watertight/plug supplied |  | Waste connection watertight, plug supplied | Wash Hand Basin
|  | Wash Hand Basin - Water conn. watertight/tap secure |  | Water connection watertight, tap secure | Wash Hand Basin
|  | Wash Hand Basin - Hot & Cold waterflow/no water hammer |  | Hot & Cold waterflow satisfactory, no water hammer | Wash Hand Basin
|  | Toilet is installed |  | Toilet is installed | Toilet
|  | Toilet - Securely fixed, silicone at floor |  | Securely fixed, silicone at floor | Toilet
|  | Toilet - Flush and cistern fill operation checked |  | Flush and cistern fill operation checked | Toilet
|  | Toilet - Water conn. watertight – cold water |  | Water connection watertight – cold water | Toilet
|  | Shower is installed |  | Shower is installed | Shower
|  | Shower - Hot & Cold waterflow/no water hammer |  | Hot & Cold waterflow satisfactory, no water hammer | Shower
|  | Shower - Waste clear |  | Waste clear | Shower
|  | Shower - Cover plate fixed securely |  | Cover plate fixed securely | Shower
|  | Bath/shower is installed |  | Bath/shower is installed | Bath/Shower
|  | Bath/Shower - Waste clear, plug installed |  | Waste clear, plug installed | Bath/Shower
|  | Bath/Shower - Divertor operation working |  | Divertor operation working (where applicable) | Bath/Shower
|  | Bath/Shower - Hot & Cold waterflow/no water hammer |  | Hot & Cold waterflow satisfactory, no water hammer | Bath/Shower
|  | Bath/Shower - Cover plate/spout fixed securely |  | Cover plate/spout fixed securely | Bath/Shower
|  | Bath/Shower - FWG |  | FWG | Bath/Shower
|  | Bath/Shower - Grate flush with floor or slightly below |  | Grate flush with floor or slightly below | Bath/Shower
|  | Bath/Shower - Waste clear of debris |  | Waste clear of debris | Bath/Shower
|  | Amenity areas/kitchens etc. are installed |  | Amenity areas / kitchens etc. are installed | Amenity Areas / Kitchens etc.
|  | Amenity/Kitchens - Hot & Cold waterflow/no water hammer |  | Hot & Cold waterflow satisfactory, no water hammer | Amenity Areas / Kitchens etc.
|  | Amenity/Kitchens - Water conn. watertight, tap secure |  | Water connection watertight, tap secure | Amenity Areas / Kitchens etc.
|  | Amenity/Kitchens - Waste conn. watertight |  | Waste connection watertight | Amenity Areas / Kitchens etc.
|  | Amenity/Kitchens - Dishwasher conn. watertight |  | Dishwasher connection watertight | Amenity Areas / Kitchens etc.
|  | Amenity/Kitchens - Wastemaster conn. watertight |  | Wastemaster connection watertight | Amenity Areas / Kitchens etc.
|  | Amenity/Kitchens - Overflow conn. watertight |  | Overflow connection watertight | Amenity Areas / Kitchens etc.
|  | Amenity/Kitchens - Waste clear, plug installed |  | Waste clear, plug installed | Amenity Areas / Kitchens etc.
|  | Area left clean & tidy |  | Area left clean and tidy | Handover
|  | Council Verification |  | Council Verification | Handover
|  | South Auckland Plumbing Verification |  | South Auckland Plumbing Verification | Handover
|  | Main Contractor verification |  | Main Contractor verification | Handover
Water Riser Progress
| Scope |  |  | water risers
Rows
|  | First Fix - Level 1 | dynamic | Site QA | First Fix | Level 1 | Water Risers
|  | First Fix - Level 2 | dynamic | Site QA | First Fix | Level 2 | Water Risers
Columns
|  | Water riser installed |  | Water riser installed
|  | Manifold installed |  | Manifold installed
|  | Tested & passed |  | Tested and passed
Sewer Riser Progress
| Scope |  |  | sewer risers
Rows
|  | First Fix - Level 1 - Region A | dynamic | First Fix | Level 1 | Sewer Risers | Region A
|  | First Fix - Level 1 - Region B | dynamic | First Fix | Level 1 | Sewer Risers | Region B
|  | First Fix - Level 1 - Region C | dynamic | First Fix | Level 1 | Sewer Risers | Region C
|  | First Fix - Level 2 - Region A | dynamic | First Fix | Level 2 | Sewer Risers | Region A
|  | First Fix - Level 2 - Region B | dynamic | First Fix | Level 2 | Sewer Risers | Region B
|  | First Fix - Level 2 - Region C | dynamic | First Fix | Level 2 | Sewer Risers | Region C
Columns
|  | Sewer riser installed |  | Sewer riser installed
|  | Tested & passed |  | Tested and passed
Stormwater Riser Progress
| Scope |  |  | Stormwater Risers
Rows
|  | First Fix - Level 1 - Region A | dynamic | First Fix | Level 1 | Stormwater Risers | Region A
|  | First Fix - Level 1 - Region B | dynamic | First Fix | Level 1 | Stormwater Risers | Region B
|  | First Fix - Level 1 - Region C | dynamic | First Fix | Level 1 | Stormwater Risers | Region C
|  | First Fix - Level 2 - Region A | dynamic | First Fix | Level 2 | Stormwater Risers | Region A
|  | First Fix - Level 2 - Region B | dynamic | First Fix | Level 2 | Stormwater Risers | Region B
|  | First Fix - Level 2 - Region C | dynamic | First Fix | Level 2 | Stormwater Risers | Region C
Columns
|  | Stormwater riser installed |  | Stormwater riser installed
|  | Tested & passed |  | Tested and passed