## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Seacliff Wastewater Treatment and Disposal Upgrade |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561469 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council |  |  |  |  | B | Report by Breach | CM | Construction Manager
Contract Number: | 9776 |  |  |  |  | C | Check | CR | Cust. Representative
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[6 empty] | E | Examine | MC | Material Controller
ITP Number: | 2 |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Access Tracks |  |  |  |  | I | Inspection | PM | Project Manager
Discipline: | Earthworks |  |  |  |  | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | Seacliff Watewater Treatment Plant Upgrade - 1110: Earthworks (General) |  |  |  |  | O | Operation | QE | Quality Engineer
[6 empty] | R | Review | QM | QA Manager
Drawings: | 310103025-01-001-C101 to C103, C110 to C112 and C155 |  |  |  |  | S | Subcontractor | SP | Supervisor
[6 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Sebastian Charlin |  | Date: | 2023-10-25 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
3.1 | Review all Drawings and Documents | Review all drawings and documentation provided to the Contractor. | Prior to the commencement of Works it must be ensure that all necessary documentation has been provided. | ITP | Prior to the commencement of Works | Visual | R | PM/QE
3.2 | Setting Out Levels and Alignment | All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4 | Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer | Compliance surveys or spot checks | Prior to the commencement of Works | Visual, Instrumental | H | SP/QE/SV
3.3 | Service location and Hydro Vacumming | Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1 | All services identified in B4UDig, plans and mark outs has been physically located | Plans Mark out, photos | Prior to the commencement of Works | Visual | H | CR
3.4 | Aggregate Site Delivery | Sourced GAP65 basecourse and AP20 Running course aggregate shall be clean free from clay, all organic matter and other deleterious materials. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1110: 8.5.1, 9.13 | Visual Inspection, Engineer approval | Delivery Docket, Laboratory test results per source material | Prior to the commencement of Works | Visual, Lab Test | H | QE/SP/MC
3.5

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
4.1 | Site Clearance | The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1 | Location approved by the Engineer | Dumping Docket | After site clearance | Document Check | C | QE/SP/CR
4.2 | Trees Removal | No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2 | Engineer Approval | Engineer Writen Authorisation | Before remove any tree | Client Consultation | H | CR
4.3 | Removal of Topsoil | Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4 | Engineer Approval | Engineer Writen Authorisation | Before Topsoil Removal | Client Consultation | C | CR
4.4 | Hazardous Waste and Contaminated soils | Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3 | Dumping site approval for contamiantion type | Dumping Docket | If constaminated soils are found | Document Check | C | QE/SP/CR
4.5 | Checking Levels and Alignment | Compliance surveys or, at a minimum, spot checks, shall be provided to confirm that subgrade levels achieve appropriate accuracy particularly beneath road pavement layers. Specs 1000: 3.2.4 | Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer | Compliance surveys or spot checks | During and at the end of the Excavation | Visual, Instrumental | C | SP/QE/SV
4.6 | Subgrade | The subgrade CBR must be tested 5 working days prior to construction. Specs 1110: 9.12.1, Drawing C155 | CBR ≥ 5 | CBR Checksheet | Every 50m of track (not confirmed) | On site Test | H | QE/CR
4.7 | Basecourse | On completion of all metalling the surface shall be maintained smooth and level, true to grade and cross section. Specs 1110: 9.8, 9.12.2, 1000: 3.2.4, TNZ F/1 Clause 10 and NZTA B/2 | Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer | Compliance surveys or spot checks | During and at the end of the filling and compaction | Visual, Instrumental | C | SP/QE/SV
4.8 | Basecourse Compaction / Consolidation Testing | Maximum density of each metal course layer must be determined. Density meter testin shall be carried on the layers. Specs 1110: 9.12.3, NZTA Clause 7.6 | Dry Density ≥ 95% MDD | Nuclear Density Meter (NDM) Results Sheet | Each 300mm lift shall be tested 1 per 100 m2 (square metres) on a nominal 10m by 10m grid pattern. | On site Test | H | QE/CR
4.9 | Earthworks Tolerance | Earthworks shall be constructed to the tolerances table in Specs 1110: 9.11 | Parameters inside of the permissible deviation | Compliance surveys or spot checks | During and at the end of the earthworks | Visual, Instrumental | C | SP/QE/SV
4.10
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Engineer didn’t provide any track setout data. Do we remove as we are unable to conform due to client supplied docments being insufficent Reply: Ok, and how the track will be surveyed? With the drawings? Reply: Patterson Pitts have done a model based on there initial survey / setout. But this has been fudged to tie into the site conditions. Will do an asbuilt survey at the end.
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As above

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
5.1 | As-built Drawings | Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2 | Engineer Approval | QA records | At completion | - | H | QE/CR
5.2 | Surplus Materials and Refuse Disposal | All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2 | - | - | At completion | Visual | C | QE/SP/CR
5.3 | Cleaning | Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3 | - | - | At completion | Visual | C | QE/SP/CR
5.4
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: