## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 561469-ITP-0002 - Access Tracks (DG-QA-TP018) | itp |  |  |  |  | 561469-ITP-0002 - Access Tracks (DG-QA-TP018)
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Review all Drawings and Documents
label | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
label | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
label | Verifying Document - ITP
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - R
label | Inspection: By (Role Key) - PM/QE
checkpoint | 3.2 - Setting Out Levels and Alignment
label | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
label | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
label | Verifying Document - Compliance surveys or spot checks
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/SV
holdpoint | HOLD POINT
checkpoint | 3.3 - Service location and Hydro Vacumming
label | Inspection Point: Quality Control Activity - Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1
label | Acceptance Criteria - All services identified in B4UDig, plans and mark outs has been physically located
label | Verifying Document - Plans Mark out, photos
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR
holdpoint | HOLD POINT
checkpoint | 3.4 - Aggregate Site Delivery
label | Inspection Point: Quality Control Activity - Sourced GAP65 basecourse and AP20 Running course aggregate shall be clean free from clay, all organic matter and other deleterious materials. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1110: 8.5.1, 9.13
label | Acceptance Criteria - Visual Inspection, Engineer approval
label | Verifying Document - Delivery Docket, Laboratory test results per source material
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual, Lab Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/SP/MC
holdpoint | HOLD POINT
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Site Clearance
label | Inspection Point: Quality Control Activity - The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1
label | Acceptance Criteria - Location approved by the Engineer
label | Verifying Document - Dumping Docket
label | Frequency - After site clearance
label | Inspection Type (Visual, other) - Document Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR
checkpoint | 4.2 - Trees Removal
label | Inspection Point: Quality Control Activity - No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Engineer Writen Authorisation
label | Frequency - Before remove any tree
label | Inspection Type (Visual, other) - Client Consultation
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR
holdpoint | HOLD POINT
checkpoint | 4.3 - Removal of Topsoil
label | Inspection Point: Quality Control Activity - Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Engineer Writen Authorisation
label | Frequency - Before Topsoil Removal
label | Inspection Type (Visual, other) - Client Consultation
label | Inspection: Key - C
label | Inspection: By (Role Key) - CR
checkpoint | 4.4 - Hazardous Waste and Contaminated soils
label | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3
label | Acceptance Criteria - Dumping site approval for contamiantion type
label | Verifying Document - Dumping Docket
label | Frequency - If constaminated soils are found
label | Inspection Type (Visual, other) - Document Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR
checkpoint | 4.5 - Checking Levels and Alignment
label | Inspection Point: Quality Control Activity - Compliance surveys or, at a minimum, spot checks, shall be provided to confirm that subgrade levels achieve appropriate accuracy particularly beneath road pavement layers. Specs 1000: 3.2.4
label | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
label | Verifying Document - Compliance surveys or spot checks
label | Frequency - During and at the end of the Excavation
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/SV
checkpoint | 4.6 - Subgrade
label | Inspection Point: Quality Control Activity - The subgrade CBR must be tested 5 working days prior to construction. Specs 1110: 9.12.1, Drawing C155
label | Acceptance Criteria - CBR ≥ 5
label | Verifying Document - CBR Checksheet
label | Frequency - Every 50m of track (not confirmed)
label | Inspection Type (Visual, other) - On site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 4.7 - Basecourse
label | Inspection Point: Quality Control Activity - On completion of all metalling the surface shall be maintained smooth and level, true to grade and cross section. Specs 1110: 9.8, 9.12.2, 1000: 3.2.4, TNZ F/1 Clause 10 and NZTA B/2
label | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
label | Verifying Document - Compliance surveys or spot checks
label | Frequency - During and at the end of the filling and compaction
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/SV
checkpoint | 4.8 - Basecourse Compaction / Consolidation Testing
label | Inspection Point: Quality Control Activity - Maximum density of each metal course layer must be determined. Density meter testin shall be carried on the layers. Specs 1110: 9.12.3, NZTA Clause 7.6
label | Acceptance Criteria - Dry Density ≥ 95% MDD
label | Verifying Document - Nuclear Density Meter (NDM) Results Sheet
label | Frequency - Each 300mm lift shall be tested 1 per 100 m2 (square metres) on a nominal 10m by 10m grid pattern.
label | Inspection Type (Visual, other) - On site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 4.9 - Earthworks Tolerance
label | Inspection Point: Quality Control Activity - Earthworks shall be constructed to the tolerances table in Specs 1110: 9.11
label | Acceptance Criteria - Parameters inside of the permissible deviation
label | Verifying Document - Compliance surveys or spot checks
label | Frequency - During and at the end of the earthworks
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/SV
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - As-built Drawings
label | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - QA records
label | Frequency - At completion
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Surplus Materials and Refuse Disposal
label | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
label | Frequency - At completion
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR
checkpoint | 5.3 - Cleaning
label | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
label | Frequency - At completion
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR