## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing | itp |  |  |  | Yes | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing Rev 0 | 6c87b5eb-de3d-467a-a162-126d74a04804
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | ec9d73c8-ad39-520b-ae67-0fba6f606d6c |  | note | Document Title: ITP-CIV-SSB-Rail Delineation Temporary Fencing
label | 332b2197-155a-5209-a978-753baacc2640 |  | note | ITP Description: Rail Delineation Temporary Fencing for Camms Road
label | e9b41770-43a8-598b-b852-e34148cb9f5f |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | b8f52ffa-a427-5227-92c4-adb0d6c3ff40 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | c77a6e1d-3785-559b-a88d-eb1c9bbb8e1b |  | note | Revision Number: 0
label | 177694cb-fb29-553a-abae-153c51ca0e2b |  | note | Revision Date: 11/08/2023
label | c185b33b-1b7d-51fd-94a9-22b0239a8f74 |  | note | ITP created by: Isaac El Zayat
label | d9c7c88e-04bd-5392-9ba2-c3b401f16996 |  | note | ITP approved for use by: Aldrin Guinchoma
label | ce94261a-8749-5de5-b86a-5ad6e0f26349 |  | note | 1.1 Non Dependent
label | 2e4290a9-27c0-5938-89c6-1aaf547955db |  | note | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete
label | 4a78021c-33ea-5853-af05-31394837c17f |  | note | REFERENCE: IFC Drawings
label | a62c25db-85fd-5d30-8415-32b9d7e61eb8 |  | note | – – – – – – – – – – – – – – – – –
label | 21e60ba6-dddb-51fd-8acb-469ea603df23 |  | note | ACCEPTANCE CRITERIA: 32MPa concrete to be used as per IFC drawings.
label | 09c81732-154d-5489-b745-d121bf8ea13f |  | note | – – – – – – – – – – – – – – – – –
label | 5bc24c93-ac54-57e0-b010-2acad315b789 |  | note | METHOD: Document Review
label | dd595eb5-5f7b-5640-b440-52335ab84a8c |  | note | – – – – – – – – – – – – – – – – –
label | c2daac0a-1ebd-548c-9881-58eb26a2f631 |  | note | FREQUENCY: Each Mix
label | 07933187-3632-5217-9f5a-83b863d6a1e8 |  | note | – – – – – – – – – – – – – – – – –
label | 2874d2cd-74f4-59b8-9717-7a78b49d2032 |  | note | CATEGORY: HP
label | f0d3cef4-5d03-5dd9-b7fd-8c6102e39f7c |  | note | – – – – – – – – – – – – – – – – –
label | d542df31-513c-50c1-b84f-e2796a7bc1bb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 26b06228-a51c-58c9-baa8-839d816614b2 |  | note | – – – – – – – – – – – – – – – – –
label | c81bc904-0551-50db-915b-f4a72273219d |  | note | VERIFYING DOCUMENTS: Certificate of Compliance
text | 4a44364c-e899-5036-b4e9-506466180010 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Steel components
label | b30eeef2-ffc4-5bde-b6f3-f677f0280087 |  | note | REFERENCE: IFC Drawings AS41000, AS1163
label | 285fecec-9482-5e69-b491-d2745eb68497 |  | note | – – – – – – – – – – – – – – – – –
label | f4475997-e8b4-5632-9fed-41c83671f1ca |  | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | bd682eda-b412-5082-b1a5-97a96839c744 |  | note | ○ Steel section sizes must be checked on site.
label | f5ff98ce-241e-5bed-9957-084504462119 |  | note | ○ Steel posts to be CHS with a grade of C250
label | f9479c56-3e9a-53d5-a606-7aca77fd7919 |  | note | – – – – – – – – – – – – – – – – –
label | cc18b9df-8005-5c8c-aa54-f8f4fafc15a5 |  | note | METHOD: Document review, Visual and Measure
label | f0504c31-21c3-5d09-ab0c-4aeed7292947 |  | note | – – – – – – – – – – – – – – – – –
label | 8e6ce503-9ea9-5336-985d-d0091fa79452 |  | note | FREQUENCY: All elements
label | 55631e09-091d-5ee1-bb43-ed81790ae083 |  | note | – – – – – – – – – – – – – – – – –
label | 6233ec51-54d9-5e81-9f93-38427557ae59 |  | note | CATEGORY: IP
label | a3200242-9e7b-5939-b566-d9ace19f6bf5 |  | note | – – – – – – – – – – – – – – – – –
label | dd60bcb9-5b44-5c75-a2d9-27e1b3d19e58 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ea0e1a05-0360-54ee-b72d-4b9fd7ed6665 |  | note | – – – – – – – – – – – – – – – – –
label | 0cd153f9-7c3e-5709-8599-a28bd4e0382a |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
text | 71660e72-f831-5b48-9803-316adc293132 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Excavation works
label | 1ce32fc0-60cc-52d3-9e16-f6fbd5a2ee8b |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | 551e9f4b-b6a6-5893-bd5e-e1b5ad307ff7 |  | note | – – – – – – – – – – – – – – – – –
label | 9cfed8be-e4c3-56e4-a366-d6ceb5c5fbe5 |  | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine track and comply with PTDT requirements.
label | c66e598c-d606-5119-b4e9-217dd99b5b64 |  | note | ○ Follow asset owners guidelines for work around their service.
label | 1c85925c-5e89-544d-836f-0e747618ede6 |  | note | ○ Excavation must use Non Distructive Digging in the rail corridor
label | f1c79e83-1753-542e-8977-4032d01e1169 |  | note | – – – – – – – – – – – – – – – – –
label | ebda8d61-c159-515b-bbfd-f057547b09ea |  | note | METHOD: Visual
label | 862645ee-f440-56aa-9056-abcd1fde8457 |  | note | – – – – – – – – – – – – – – – – –
label | e6482c43-47bd-5f29-ae18-b4df4dab5759 |  | note | CATEGORY: IP
label | f16f4022-deb7-5b4f-809e-04afc50f4055 |  | note | – – – – – – – – – – – – – – – – –
label | 711cbbbe-b1cf-59af-8207-1412e798439a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0a27d7ac-d712-5826-ab89-39ef05f97a47 |  | note | – – – – – – – – – – – – – – – – –
label | 55d9347b-3565-596e-90b3-c41882558d96 |  | note | VERIFYING DOCUMENTS: This ITP
text | 86daf07d-3f50-5c62-9824-635b7ae355f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 8631d05f-4b77-5cb5-9a2d-0fdca28fbccb |  | note | REFERENCE: IFC Drawings
label | 0fb51cb3-0c09-5d3e-a144-d348f737ac63 |  | note | – – – – – – – – – – – – – – – – –
label | 4831ba62-74d1-5b82-abf5-1fcde34f728b |  | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | a25fcc91-cf50-5466-ae17-8e90440aa4ad |  | note | ○ Offset checked against the running edge prior to installation of posts.
label | 010a4776-141c-519c-a941-e781468cee78 |  | note | ○ Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | 9d5e1af0-75ab-5ee7-b50d-3cf40000d2a2 |  | note | ○ Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | f9a472db-2fbc-5f7b-94b8-33f4b004db0c |  | note | – – – – – – – – – – – – – – – – –
label | f0f11594-9290-540c-821d-a636023e8417 |  | note | METHOD: Measure, Visual inspect
label | d54c7543-6046-5d85-b387-0f5bebe4c050 |  | note | – – – – – – – – – – – – – – – – –
label | 67d7ab01-ceff-58dc-9bbf-a459edda10e2 |  | note | FREQUENCY: Each element
label | fd0ac6b1-b7e7-5c20-8deb-5181876a1a3b |  | note | – – – – – – – – – – – – – – – – –
label | de202cc5-3c9a-52ea-a7fc-6dcecd15d817 |  | note | CATEGORY: IP
label | 7c4b3350-8bca-5cb2-947b-32bbefe6468d |  | note | – – – – – – – – – – – – – – – – –
label | b476da41-ec15-5af9-bcce-3afb998d1638 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | a969ae34-013e-5f74-ae1d-f2e8aa39614b |  | note | – – – – – – – – – – – – – – – – –
label | 548d3a69-cde6-5187-b0ca-804a85d8c46a |  | note | VERIFYING DOCUMENTS: This ITP
text | 26f9c3dc-51d4-5760-87ca-bbdef40ab0db |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Ground Conditions
label | 726fb64b-4e44-5b85-aa4e-068072eba8fe |  | note | REFERENCE: IFC Drawings
label | d0f466e2-f62a-5fec-b27f-6d89e091e94c |  | note | – – – – – – – – – – – – – – – – –
label | 72d01026-9c8f-5d36-938e-8dff910815a4 |  | note | ACCEPTANCE CRITERIA: All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | 2c866593-2b41-5404-a7bd-e393b36b50b9 |  | note | – – – – – – – – – – – – – – – – –
label | 69d289fe-53d7-5050-846b-71cd1da71a36 |  | note | METHOD: Visual
label | a52c2c35-2bcb-5b69-87ec-77fa193e7e6b |  | note | – – – – – – – – – – – – – – – – –
label | c34a4ba0-48be-550e-9b5d-ae9fe023ba6a |  | note | FREQUENCY: Each post
label | 64efbcb2-91e0-58cb-9480-480eb5eb5071 |  | note | – – – – – – – – – – – – – – – – –
label | a7752b9d-5386-55c7-b13a-aa8dded4f51b |  | note | CATEGORY: IP
label | 6e80c0e3-be96-5699-a2bf-a2ad70864ff6 |  | note | – – – – – – – – – – – – – – – – –
label | a27aae94-0de2-596f-b0e4-8a282cbd07dc |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ee3fbe81-e3d8-519b-a274-8632be3c0bc1 |  | note | – – – – – – – – – – – – – – – – –
label | f80cb3c5-5ecf-5343-b30e-fc7ecdaa892a |  | note | VERIFYING DOCUMENTS: This ITP
text | 9d9c53a1-1522-5a00-92f1-3d26f5b6bd47 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Post Foundation
label | 3446ceea-4454-5f9c-8f53-5d0f274d8295 |  | note | REFERENCE: IFC Drawings
label | d33f6558-c39b-54ff-8a50-64bd78e181c1 |  | note | – – – – – – – – – – – – – – – – –
label | d4a82137-26ff-55ed-958c-9080ce3eb96f |  | note | ACCEPTANCE CRITERIA: Concrete
label | 69763eff-b431-54a0-a7b3-2c0fa6fe2564 |  | note | – 300mm Dia
label | 7a7a2493-13eb-58ad-a6cf-2352584efd44 |  | note | – 1000 mm Depth
label | 1a16fcd6-b039-5d2f-b59f-9eb8ba821da0 |  | note | CHS Sleeve:
label | 9da1f657-cfe0-5c42-854b-db649e58b2a1 |  | note | – Depth 1400
label | 91c3dbf1-7e9c-5a81-b229-5d2455ee860b |  | note | – Other Dimensions as per IFC
label | a09fd334-165d-566b-80fb-246a3ee96860 |  | note | Direct Driven:
label | e94e8e57-150d-5d73-bd08-8d70b9cf06c4 |  | note | – 88.9x4 CHS
label | 2b040436-a7b0-54db-8ac4-5d60a9d0f8c2 |  | note | – Depth: 1500
label | f9759267-9b29-55b0-8ecc-86d26cb774a8 |  | note | Spacings:
label | 55dc6496-5687-5dbe-bdbf-33eb723097f0 |  | note | ○ Typical: 2700 max
label | 9798de3c-e4f9-5669-8a67-89331b703fe9 |  | note | ○ Gates: 1350
label | ec307f70-e980-53b9-923f-4c4d45ba214a |  | note | ○ Refuge: 1200
label | bea79e93-a762-5651-a18c-a15f20929811 |  | note | – – – – – – – – – – – – – – – – –
label | a02bce53-cc42-5b2b-8678-f11f65d3b360 |  | note | METHOD: Measure
label | 5347af57-0498-5b28-bfe2-dae14be60741 |  | note | – – – – – – – – – – – – – – – – –
label | 7588c96b-c495-5be8-a991-420fd1a1af19 |  | note | FREQUENCY: Each footing
label | 65e52681-7886-5181-9433-111e3176e3ef |  | note | – – – – – – – – – – – – – – – – –
label | e39cb3c0-0c0a-5514-918c-516a4ad99d24 |  | note | CATEGORY: IP
label | 049ce94e-ecb4-5aba-b96c-fe761f795f00 |  | note | – – – – – – – – – – – – – – – – –
label | 21405875-fa14-5d7b-86f8-18a1118e33a9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fe16ac70-7456-5b60-8204-4db30b652b16 |  | note | – – – – – – – – – – – – – – – – –
label | 8bfa800c-5b72-576d-91d6-8833b5361624 |  | note | VERIFYING DOCUMENTS: This ITP
text | 453d66a5-56f2-5f07-96b8-fea87c00b7e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Post Installation
label | 082a1f3e-6519-5fd2-bbc7-301904cfc174 |  | note | REFERENCE: IFC Drawings L1-CHE-STD-005
label | b25962d9-92da-54fc-b369-67fe42bd4181 |  | note | – – – – – – – – – – – – – – – – –
label | 94a329ec-3b7d-54b9-befe-8032f0ce7967 |  | note | ACCEPTANCE CRITERIA: Up track: Minimum offset 3000mm from centreline of track.
label | eda6477e-cda3-52de-96f1-72bebfb46cf8 |  | note | ○ Down track: Minimum offset 2200mm from centreline of track.
label | 9d8f9fa4-6c24-55f1-9507-291b923586fd |  | note | ○ Maximum post spacing to be 3.1m
label | fe82249f-ff33-5e38-abe3-c0937cde5852 |  | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
label | 88de0b25-10af-5a39-9413-1637aa81dffc |  | note | ○ Max. post height 1800mm above ground level.
label | 6a5e3c06-c080-5298-9b12-4b8538ff4378 |  | note | ○ Vertical Tolerance: ±20mm from the design line.
label | 0d1149b6-cb4a-5e48-a81b-4b6e43354719 |  | note | – – – – – – – – – – – – – – – – –
label | 2c436b2a-b0ea-54cf-b954-23175f6a7b5f |  | note | METHOD: Measure
label | 07bbe768-204c-5c2a-9465-34713eb521d2 |  | note | – – – – – – – – – – – – – – – – –
label | 18b27c06-1340-5aa1-9c2e-3d3e218a1f3c |  | note | FREQUENCY: Each post
label | 80364c84-0f52-5381-a147-8b4492919e78 |  | note | – – – – – – – – – – – – – – – – –
label | 25c88331-8888-5265-a381-1b5e7dddd042 |  | note | CATEGORY: IP
label | de2c5619-69ab-5243-852c-b2163eca0363 |  | note | – – – – – – – – – – – – – – – – –
label | f0163aa8-6941-5a02-b45c-0b5b59d2e24f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 36bffe66-b5d5-5e00-b9f5-df0a2f0eff7a |  | note | – – – – – – – – – – – – – – – – –
label | 5c14e2cd-1c86-52f2-a140-691a108a02cc |  | note | VERIFYING DOCUMENTS: This ITP
text | 68904b44-93be-5e16-b69d-79e08f68b4bc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Chain Wire Mesh Installation
label | 25b27bcd-72fb-581c-8bc6-110af0351257 |  | note | REFERENCE: IFC Drawings
label | fae80f24-5c69-597e-b80f-2ab9e75f90ae |  | note | – – – – – – – – – – – – – – – – –
label | a9ce0599-a9a9-5770-ad24-05199a46193f |  | note | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
label | 5c4b5526-308c-5dd4-9f44-6d22c98bb24e |  | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | 540b7f55-8037-58a8-94d7-8b85ad33a235 |  | note | – – – – – – – – – – – – – – – – –
label | e807892d-1672-5464-8ec5-53fc2182dadb |  | note | METHOD: Visual
label | 035c8f11-bf16-5fd9-ae50-d29e8af16028 |  | note | – – – – – – – – – – – – – – – – –
label | bdae91cf-a3b9-528b-a88a-7f2d7ebc5077 |  | note | FREQUENCY: Each element
label | c00ccefb-4779-5061-ad2b-894c76e39bc2 |  | note | – – – – – – – – – – – – – – – – –
label | fc67b590-b253-52ea-8af4-8c143dbddf67 |  | note | CATEGORY: IP
label | b25b21ec-6ec7-5873-bbb0-663d3c31426f |  | note | – – – – – – – – – – – – – – – – –
label | 07fdacb9-2f00-552d-a8f0-93bafa433583 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 449a7ba5-2215-581f-a5f5-a059cc39cc0f |  | note | – – – – – – – – – – – – – – – – –
label | 07181ad3-457d-50ba-8b94-77959cf1197e |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b37dd69-644f-59aa-b5ef-f3e92a1be07b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Bracing
label | 71254aab-1833-5d22-ae64-4ac53333b449 |  | note | REFERENCE: IFC Drawings
label | 8db5cbf3-e02e-5e78-98ff-0840bfaa2376 |  | note | – – – – – – – – – – – – – – – – –
label | 0ffdd3f6-0526-56ab-a249-a901d8c01987 |  | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 1361af66-5e89-5acf-8fc8-dd17bd950b0d |  | note | ○ Bracing to be installed on both sides of the fence at the fence corners
label | ca9053e3-fa46-56aa-8dd2-094b638f2529 |  | note | – – – – – – – – – – – – – – – – –
label | d9833b19-b1a1-55b0-9847-cef5fa705727 |  | note | METHOD: Visual
label | e395b762-1873-5283-ace1-2e179d2c7d75 |  | note | – – – – – – – – – – – – – – – – –
label | 25b40fb2-4287-5965-8f5c-6501eb4c3a74 |  | note | FREQUENCY: Each element
label | 21608c98-c365-5fd3-b1cb-d1614602bef6 |  | note | – – – – – – – – – – – – – – – – –
label | 5270e350-4b4d-536a-bbfa-f2dbdb52456f |  | note | CATEGORY: IP
label | a9d8903a-83fe-5c6e-a1cf-9a9c1186fbc9 |  | note | – – – – – – – – – – – – – – – – –
label | b9c9fd1e-5bb3-52a1-ab2b-776de3ade79a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1acdc240-a508-5f84-b79e-d2ebc25b6ae2 |  | note | – – – – – – – – – – – – – – – – –
label | 246344ef-1aab-5dca-8ed8-a9968d355a91 |  | note | VERIFYING DOCUMENTS: This ITP
text | fa8dcdd2-e4a6-5f94-8074-717e1be4d324 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Refuge Installation
label | 4840f0dd-5f59-5971-a68e-f23d6b4e8e5d |  | note | REFERENCE: IFC Drawings
label | 97cd7143-95d2-5c79-b2bb-67fcf3d7970b |  | note | – – – – – – – – – – – – – – – – –
label | e01de92e-1f3d-586c-acbb-6ef4c55345bc |  | note | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
label | 9111e748-586f-57f1-a4f8-fb97a872a905 |  | note | ○ No chain wire mesh to be installed at refuge access.
label | 45f24409-130c-5f5a-a9b2-3f600de23904 |  | note | ○ Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
label | 61339afc-d051-5967-a711-e2ccdb16a49b |  | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | 442265e2-156e-5eab-847b-5d4317d1bb48 |  | note | – – – – – – – – – – – – – – – – –
label | 803f6c62-0e48-5575-8c9e-9152f79f4caa |  | note | METHOD: Visual
label | 422a636f-2cfc-5326-8143-bea683196870 |  | note | – – – – – – – – – – – – – – – – –
label | fc27830e-e20e-563f-aaf7-16b46286d066 |  | note | FREQUENCY: Each element
label | 34cf5c02-e8d1-571e-8e45-7d838cd95e41 |  | note | – – – – – – – – – – – – – – – – –
label | e08049ef-47d0-5b2b-8069-97c81c7a08bb |  | note | CATEGORY: IP
label | c24f8841-594e-5dbe-83df-7fa5d12b4f57 |  | note | – – – – – – – – – – – – – – – – –
label | 9fc41de0-8891-51ed-a388-73f4e1cd922a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 347699e2-111a-5a5c-8dbc-faed195487d5 |  | note | – – – – – – – – – – – – – – – – –
label | 0d31a6fc-fc60-5371-8217-e0e85cd99215 |  | note | VERIFYING DOCUMENTS: This ITP
text | 777b63df-8631-5936-a83d-efdc3439c140 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Refuge Signage
label | 3e53b2b0-9ba6-5081-9a2e-388ab3f85fae |  | note | REFERENCE: IFC Drawings
label | 6ab36f94-3c39-59b4-b158-98d4fae7d423 |  | note | – – – – – – – – – – – – – – – – –
label | 9c2bb6d7-0827-5281-9955-0ece193d0ecc |  | note | ACCEPTANCE CRITERIA: Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
label | 1ba18b0f-f949-5822-b09a-f4d0d7c3a0c5 |  | note | – – – – – – – – – – – – – – – – –
label | 5c5c0056-e5c9-58f2-8772-9bcfefb70014 |  | note | METHOD: Visual
label | 485e5f83-95ec-5d8d-b9fa-1ec40e15bfee |  | note | – – – – – – – – – – – – – – – – –
label | eeb18d1f-4a57-5333-919f-08d3f31e7074 |  | note | FREQUENCY: Each element
label | 21fa4787-049a-53db-8a93-8baa13235d95 |  | note | – – – – – – – – – – – – – – – – –
label | a00dfc65-6ac2-5005-9a7d-6baf9b9ccb9e |  | note | CATEGORY: IP
label | d78ce728-8a31-5b25-886b-315f8234c1cf |  | note | – – – – – – – – – – – – – – – – –
label | 5c07eeb4-ad47-52fc-9d47-3d0e436d6b75 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 70e8cdd7-cde7-54db-9566-87bd8ccec541 |  | note | – – – – – – – – – – – – – – – – –
label | 1c0c96a6-1d9c-51e9-80c1-14bc3eaf20d0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5dccd4a1-47fc-5f80-9951-f2acdef52245 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Fence Height and Track Clearance
label | 6a6506f1-2d58-57e1-a2fc-5c0e477363b0 |  | note | REFERENCE: IFC Drawings
label | a8e38ac5-1cc8-5694-9a53-e8b30f6cfc33 |  | note | – – – – – – – – – – – – – – – – –
label | 7c740cca-0c63-5343-af82-46aa48537023 |  | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | e2530150-c500-5640-aa8b-29a6a51c6546 |  | note | – – – – – – – – – – – – – – – – –
label | 8193ed29-aa06-5903-82fd-fcb330606f83 |  | note | METHOD: Measure
label | 1e133529-02a1-5945-a91e-88617807a13a |  | note | – – – – – – – – – – – – – – – – –
label | b207691f-0b40-584d-b6de-d2de0570da84 |  | note | FREQUENCY: Each lot
label | 82ab422c-c9ea-57f2-b6b6-3d37d13d55b0 |  | note | – – – – – – – – – – – – – – – – –
label | 31dd574a-360e-5955-b22a-0a312cdf1c9f |  | note | CATEGORY: IP
label | 0d5bae00-7c04-5e8c-8a82-f6dd5146dfb9 |  | note | – – – – – – – – – – – – – – – – –
label | 371fb225-c4a6-5243-8443-8864e5b45cf7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fbff6749-f858-54a7-b125-e81b8946985b |  | note | – – – – – – – – – – – – – – – – –
label | f2cd56e6-ed3d-5088-a7e5-18d87391f842 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1e6d8259-d4bc-540c-9af5-6d3036a9b1ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | a7d23049-ba58-5a14-bbb6-13932c5e539f |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 316b3e8f-8b54-5352-b4c8-6d45b1c48767 |  | textbox | Name:
text | ec28943a-8618-536a-aa52-cbab2b8edb92 |  | textbox | Position:
text | 81aec31c-8625-532c-b7e0-471a8a120913 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-058-CIV-SSB-Clearing and Grubbing | itp |  |  |  | Yes | ITP-058-CIV-SSB-Clearing and Grubbing Rev 0 | 9d6a1460-07c1-43a8-8237-58c631a15a14
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 31c2a1d4-2c66-582f-ae55-6a049067cc65 |  | note | Document Title: ITP-CIV-SSB-Site Clearing and Grubbing
label | 7afd9272-d2f5-5cd3-b29a-2e919e2d3c24 |  | note | ITP Description: SSB-Site Clearing and Grubbing
label | ff680ed1-e886-5745-87a9-123881da8364 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 441645c8-52f8-58bd-ba79-f6c9219e971d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 287d55c3-2784-5d46-ae64-f160c01ed66f |  | note | Revision Number: 0
label | 3be47f7e-c6c1-56c5-80b0-661b26e99be0 |  | note | Revision Date: 9/08/2023
label | 42a424bc-1537-56dc-9c9b-cc0cc66840ee |  | note | ITP created by: Jason Lee
label | 0f388fee-3b6a-5f07-a2a8-cd9d186bdcf6 |  | note | ITP approved for use by: Jon De Castro
label | a22a7ca3-e2df-573f-a244-40c1a0d40826 |  | note | 1.1 Non Dependent
label | b69f5641-6789-568d-9839-d5a1eca2f7b0 |  | note | Reference: VicRoads Section 201 (Feb 2023)
label | 381faa81-b369-585e-b4cf-250908514234 |  | note | 1.2 Non Dependent
label | 8bc2ff87-dd5f-56b9-bc12-a4c030bb48e2 |  | note | Reference: VicRoads Section 204 (Dec 2015)
label | c174001d-f089-5c10-8ad6-d1ed5269eb43 |  | note | 1.3 Non Dependent
label | 5d265fef-da7e-595e-8d0f-d77467c9297e |  | note | Reference: IFC Drawings
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-group |  |  | section | Preliminaries - Documentations
checkpoint-status |  |  | checkpoint | 3.1 Environmental Controls
label | 9bcdcdac-d9f7-5655-ad44-2bad0007b2d6 |  | note | REFERENCE: MRPA Environmental Management Plan
label | 96ce087d-4861-50c0-b098-49c68718613a |  | note | – – – – – – – – – – – – – – – – –
label | f05db4d9-491c-5350-b981-d67df7b2d0d6 |  | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities.
label | f15b63c9-df07-5c12-8c42-07db6e747f5e |  | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
label | c98d9431-3a87-5758-85ec-513166153e79 |  | note | – – – – – – – – – – – – – – – – –
label | 03f75504-815b-5edf-a1f8-f17dfa688cc4 |  | note | METHOD: Visual
label | 020e66ae-8b77-5d03-a7e8-ae484351d3ec |  | note | – – – – – – – – – – – – – – – – –
label | e3f030dc-22ee-51fc-9c83-5509a2609d5e |  | note | FREQUENCY: Where applicable, prior to starting Works
label | 9009c487-b2fd-568f-ad7d-b3f10b7c1be1 |  | note | – – – – – – – – – – – – – – – – –
label | d8b44800-a296-5212-ae2c-51c1083aea4a |  | note | CATEGORY: WP
label | 8a1abdd1-37d0-5143-83fe-ee406696dc24 |  | note | – – – – – – – – – – – – – – – – –
label | ad4f93fc-4c7d-5ed5-8d87-85c0a357ae60 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 396ab0a4-5e74-51f3-9ded-44fd7301d23b |  | note | – – – – – – – – – – – – – – – – –
label | 1d75e653-6aef-5922-b6aa-bcf9f55b9abc |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 1de62e4f-a072-5516-b4cb-e15b68f2e17f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Vegetation Removal Permit
label | 5289ee3c-772a-51cb-8de1-7d40d276e461 |  | note | REFERENCE: MRPA Environmental Management Plan
label | ce5be544-4488-5e79-8b70-3128f1440099 |  | note | – – – – – – – – – – – – – – – – –
label | d9394939-87e0-5198-a546-423dd67c26a3 |  | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat:
label | 155df37b-2f6f-5ece-aad0-2798f8df1e9a |  | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
label | ea8fee6f-a9aa-5f15-92a6-db86eb2315a6 |  | note | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
label | 072fa043-1509-5d34-929d-30813377eaa0 |  | note | ii. fence and sign all sites nominated as No-Go Zones.
label | 0fcd399d-fe17-5a5d-862e-477d7acf3c9b |  | note | Attach: Vegetation Removal Permit
label | 19e7c9e3-3f81-577b-85eb-c994d9f49f6e |  | note | Attach: Ecologist's Report
label | ee01f70a-4106-52c0-ba9f-0e629f7c8b30 |  | note | – – – – – – – – – – – – – – – – –
label | 14edc8af-049e-56d7-a4e5-742586004bdd |  | note | METHOD: Document Review, Visual
label | 163648ae-0f77-5eed-b6d7-854ad249a390 |  | note | – – – – – – – – – – – – – – – – –
label | 7b7c2dda-d8d1-595c-8fe9-10e60929d976 |  | note | FREQUENCY: Where applicable, prior to starting Works
label | 91341cf5-facb-5bb2-bd58-b97cb879ed5e |  | note | – – – – – – – – – – – – – – – – –
label | 6d22d2db-8fa0-54ce-b5e2-ca4cb5635405 |  | note | CATEGORY: HP*
label | 5dba7b3d-39b4-5078-8629-f5662f886c27 |  | note | – – – – – – – – – – – – – – – – –
label | 0866cc46-7de1-55eb-a95c-70bbaee8b80c |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 6f25588a-829b-55e6-ac76-eb5450a88ec8 |  | note | – – – – – – – – – – – – – – – – –
label | ddf3a782-e3a5-5088-8ec6-b31dd2119dbd |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 1e9bdff7-8428-51bd-ae3e-d9914b6e3576 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out / Limits of Work
label | 9df2ee72-5a6b-5988-b669-c2c9e4e3e58d |  | note | REFERENCE: IFC Drawings Section 201.03
label | c45bc1ce-bca6-582b-9ce0-9d9274291309 |  | note | – – – – – – – – – – – – – – – – –
label | ee22e862-16a8-5553-b967-89b2ba63aaec |  | note | ACCEPTANCE CRITERIA: The limits of clearing and grubbing shall be:
label | b4c60fb8-38a8-52e7-92b2-23747a1895f9 |  | note | a. the limits defined on the IFC drawings
label | f54dd88b-bb1b-5c57-bf8c-094d29a2fc30 |  | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
label | 31362beb-848f-5b21-854e-d85aa02dfbc3 |  | note | c. no more than the width required for completion of the Work under the Contract.
label | 9d13a548-35f1-5c10-a075-8b3b7bcb029d |  | note | – – – – – – – – – – – – – – – – –
label | ecb2eda9-4c13-59e3-84f5-8742f9da22c3 |  | note | METHOD: Measure, Visual
label | 77590177-7a2f-560a-8b1f-c63eed510c00 |  | note | – – – – – – – – – – – – – – – – –
label | ec3872f3-e713-5fb4-8ebc-dc0463d1dadf |  | note | FREQUENCY: Once, prior to starting Works
label | 97692512-4508-5e10-bbe5-f90ea3687cfe |  | note | – – – – – – – – – – – – – – – – –
label | 5a9e7979-6005-59cb-b81b-bd5ecc2b2bb4 |  | note | CATEGORY: IP
label | a693b7e4-21d2-5b2a-91d6-92918f0e31f7 |  | note | – – – – – – – – – – – – – – – – –
label | 5d701ba1-8372-5e36-a5ed-c8444cd9c941 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 78a39e6c-7154-5ac3-a961-8ed372c0e881 |  | note | – – – – – – – – – – – – – – – – –
label | fe2e8694-3b12-556d-a856-13bbdf5ccea7 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 81c5b90f-f5f0-50b8-9d31-4db1bfed32d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Cultural Heritage and Areas of Significance
label | 1ac195cf-bb93-5941-8caa-279f7a3a61a8 |  | note | REFERENCE: MRPA Environmental Management Plan Section 201.10
label | 68e635b5-65a1-5c8a-b743-78fa2356ac65 |  | note | – – – – – – – – – – – – – – – – –
label | f562a2c6-582f-51e9-a21d-8255e13fda6a |  | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | f80acabd-1a08-5488-89a4-cac6c78597d3 |  | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
label | 509e98a8-7115-5237-b8e6-cede8122a219 |  | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | 6b3bf29c-4875-508b-b72c-d9a268fe4531 |  | note | Attach: Cultural Heritage Report
label | 11b2f4b7-ef57-5587-b836-8bc7d8157243 |  | note | – – – – – – – – – – – – – – – – –
label | 8da9ad42-ec53-5c78-8673-bda8d6cc18cd |  | note | METHOD: Document Review, Visual
label | fe096d8c-5a8f-5423-9363-572bb3d92104 |  | note | – – – – – – – – – – – – – – – – –
label | 456098f2-62bb-5d20-a3be-60ef54061606 |  | note | FREQUENCY: Where applicable, prior to starting Works
label | f195cb62-7959-560f-be0e-e680f3847468 |  | note | – – – – – – – – – – – – – – – – –
label | 50a58e7f-a424-55f7-afcb-8c976079cc87 |  | note | CATEGORY: HP*
label | 992c253e-f24c-5191-8520-d73f8075a170 |  | note | – – – – – – – – – – – – – – – – –
label | 9d89ea46-4cd6-58fd-b4ab-91436d1a1ca7 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | a26cef06-257d-5534-b185-7d9d62111351 |  | note | – – – – – – – – – – – – – – – – –
label | 558ee11d-0270-5dec-8e29-230c016adf86 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | fdbe8ba1-c445-5025-87a8-cc020b5fac0d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Stripping of Topsoil
label | 1c1a6efb-13af-598a-a0af-7c39c8ebb503 |  | note | REFERENCE: IFC Drawings Section 204.05
label | 1948916a-35fb-5568-be16-b9c738d1127c |  | note | – – – – – – – – – – – – – – – – –
label | 4af300ca-11e6-5bab-a9a6-b84fd2671467 |  | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
label | 9901233d-3f90-5957-8ba2-136beee80e81 |  | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | ec840400-b930-56ac-8a06-d44cf5037a67 |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | c8529ead-281b-590a-b412-a4db425cd018 |  | note | – – – – – – – – – – – – – – – – –
label | 2d7918f4-ee1f-54ac-8e8d-534f7ffc4413 |  | note | METHOD: Visual
label | c34c9ecb-472e-5467-a6d9-6fd5c62dabc2 |  | note | – – – – – – – – – – – – – – – – –
label | 323eac5b-fd4a-5893-9ce4-60018cc11c22 |  | note | FREQUENCY: Each Site
label | 5012a42a-e3e0-5cd5-8239-4e42a335702d |  | note | – – – – – – – – – – – – – – – – –
label | 96f70a72-b998-5f8b-9339-7c3ab67d5a90 |  | note | CATEGORY: IP
label | 730b59f6-4e1a-504d-87a8-4b18217571fd |  | note | – – – – – – – – – – – – – – – – –
label | 8540d81f-28ee-51b9-a7dd-39107571e6ee |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | d06cb9dd-91a6-5108-8c4c-65119cf2eb4c |  | note | – – – – – – – – – – – – – – – – –
label | 3df6a9f6-363d-5e38-8066-3b8d3eb4104f |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 96c6b0de-cc26-5434-ae3b-0eed931d719c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Stockpiling
label | 0a66492c-ce9a-5a54-a8e0-80bb0f921268 |  | note | REFERENCE: MRPA Environmental Management Plan Section 204.05
label | a49a971a-b417-5573-be91-d4d402323592 |  | note | – – – – – – – – – – – – – – – – –
label | f594bb8d-1375-5cb9-a7b1-0f772fdbb3fd |  | note | ACCEPTANCE CRITERIA: Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
label | 85573849-4670-5690-9cbe-0f1bccbfe38a |  | note | ○ If this clearance is not possible,additional protection shall be provided.
label | 059eb324-8232-5837-9274-d5a7026509ba |  | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
label | 7853fed8-d4c2-5657-ada9-74d8ffe0d2ef |  | note | ○ Topsoil shall be re-spread as soon as practicable.
label | e6b91db9-ca9e-5f17-9993-c6cb5564def8 |  | note | – – – – – – – – – – – – – – – – –
label | 1f7c7739-259a-5b58-a977-f909690948f6 |  | note | METHOD: Visual
label | 60f88afb-6cf9-542e-acb4-0114102cbfb7 |  | note | – – – – – – – – – – – – – – – – –
label | 048c3af5-65f2-516a-a574-4ada34cdd056 |  | note | FREQUENCY: Where applicable, each Site
label | ce10b04e-52de-57e7-91e5-167affe06b91 |  | note | – – – – – – – – – – – – – – – – –
label | 7b7c3496-697d-5a06-9dc7-417a7dbc4607 |  | note | CATEGORY: IP
label | 50ad76d2-3ee0-5c5b-bffb-02612ae58a75 |  | note | – – – – – – – – – – – – – – – – –
label | 3bb33179-93e2-5c06-9195-1b874b09a50b |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | a7554a6d-51a1-557d-a095-51f12bfc7f4b |  | note | – – – – – – – – – – – – – – – – –
label | 1ddd2ccf-63c3-5a02-9ce4-98ef838d8a73 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 3ac5c1af-1df1-5ed7-ba9f-e82a32ef07a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Abandoned Services
label | baa303bb-ffbf-5b1a-b2bb-20ee8cd28a82 |  | note | REFERENCE: IFC Drawings Excavation Permit Section 201.05
label | 67812e51-02ac-58d9-ba45-f3428c492c9e |  | note | – – – – – – – – – – – – – – – – –
label | 766f5f82-7f4b-51c1-8bf0-3fbe99ed774f |  | note | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
label | db462803-4a5e-5680-8a82-24f80acc3dd2 |  | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | 6b416c3c-6e5c-5833-abad-ca2bd7f5cff2 |  | note | ○ Decommissioned services to be disposed of in a suitable manner.
label | 9ba23c36-153c-5b98-8e73-917544e74edd |  | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
label | 4cece54c-3d22-5497-bf60-d35b6a73517a |  | note | – – – – – – – – – – – – – – – – –
label | 1c5c4354-7fc1-5642-9257-fa0f93f59873 |  | note | METHOD: Visual
label | 1b01df17-792b-5ac5-8482-8114e8253fcb |  | note | – – – – – – – – – – – – – – – – –
label | 998201b7-7031-5483-a3b3-0f998beab866 |  | note | FREQUENCY: Where applicable, each Site
label | cad2f0bd-237f-5f18-9b55-50bb7068d400 |  | note | – – – – – – – – – – – – – – – – –
label | 926d113d-9141-5192-a717-260edbeeb5f4 |  | note | CATEGORY: IP
label | 026baf7a-53a9-5b66-8457-0c75d0de6dd4 |  | note | – – – – – – – – – – – – – – – – –
label | 1141177c-1beb-58e6-9126-6df75a14776a |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 452ba0c1-8c0c-5884-87b1-257579e57a86 |  | note | – – – – – – – – – – – – – – – – –
label | 697b27bd-abfe-5775-a0db-504948ce8255 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 0c981773-099d-574d-b038-92f4507dd995 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Clearing of Trees and Vegetation
label | b50fd0bb-3afa-5fd3-a7d0-80d14986617e |  | note | REFERENCE: IFC Drawings Section 201.04
label | edda8b12-cb3b-5aa7-8d88-5b85ffcd5bb0 |  | note | – – – – – – – – – – – – – – – – –
label | d99d2fe6-46d0-5cd4-958e-177f640cc09d |  | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertaken outside of the specified limits of work.
label | f29f8dd7-4ced-5da9-900e-eb55bad85780 |  | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | 55e947be-de95-5ec5-a067-3f6a4b512ad2 |  | note | – – – – – – – – – – – – – – – – –
label | f3b42f80-afa9-59b0-8d5c-14b4f8c5ae07 |  | note | METHOD: Visual
label | e6dc1a4d-ab53-599d-95d4-dff5c35fb58a |  | note | – – – – – – – – – – – – – – – – –
label | aae1f575-f75a-54a0-a936-5cff338ebfaf |  | note | FREQUENCY: Where applicable, each Site
label | cf9838ec-2798-5156-a21e-940e1c2ce460 |  | note | – – – – – – – – – – – – – – – – –
label | 9030e0cf-86eb-58ad-8beb-551e35ae8f3d |  | note | CATEGORY: IP
label | 8ccfd5fc-6231-5f0a-8e85-80c11a467004 |  | note | – – – – – – – – – – – – – – – – –
label | 1b73d4ab-7d78-599a-8234-492e336d6054 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 70117845-893b-5ba7-8e55-69a4420333a6 |  | note | – – – – – – – – – – – – – – – – –
label | 5a7707fc-1b78-527a-803f-2fde8c0a039a |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 0e79bb0d-614e-527c-8bcb-0451fb10062b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Grubbing of Vegetation
label | 9b15bc7c-8e62-56bb-b7e9-5ff3e273b76f |  | note | REFERENCE: IFC Drawings Section 201.05, Section 201.06
label | aa3c7b8f-0412-526c-ac72-2a0fd34a1897 |  | note | – – – – – – – – – – – – – – – – –
label | 399ccc37-66da-587d-bf0f-78c2a4974478 |  | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
label | d0e0f363-2d24-5c50-b007-faa4608f09b2 |  | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
label | b6a541ee-2e2f-5e02-8c3c-0ad05239c3c9 |  | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
label | dc9dfed8-14ca-540d-8be5-6f7864cb7492 |  | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
label | 4123beb9-9bce-5e1b-90c6-865c0b170115 |  | note | – – – – – – – – – – – – – – – – –
label | 47693c78-de49-5131-b9fc-a12360dc84ff |  | note | METHOD: Visual
label | c10eb20d-0fd7-57d3-a6d7-0a1c8ed75bf0 |  | note | – – – – – – – – – – – – – – – – –
label | 0777c875-a576-54b3-b361-402bb6fffcef |  | note | FREQUENCY: Where applicable, each Site
label | d411f435-4c07-537c-9dd8-df509560be3c |  | note | – – – – – – – – – – – – – – – – –
label | 3433eda4-a006-55d8-85ef-8affeca7d325 |  | note | CATEGORY: IP
label | 5be6c186-58ba-53a8-bc16-119b38777b65 |  | note | – – – – – – – – – – – – – – – – –
label | 5542d11c-8f8e-57d6-b136-8d3d7d7eda02 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | c759cfea-f04a-59ae-a9fd-4424149f9e51 |  | note | – – – – – – – – – – – – – – – – –
label | 380d1c7d-1e3b-584f-94bc-ed6ce8899b3e |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 7e9baa61-03cc-5b17-afb8-2b5257e96f9b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Disposal of Materials & Vegetation
label | 29d9058b-8055-5719-89b3-7b2cb8d928de |  | note | REFERENCE: Section 201.07
label | 98f5d6f7-11be-5c4d-b67b-ea979ee9f1d5 |  | note | – – – – – – – – – – – – – – – – –
label | 76b09e1a-9c84-5b7d-b2dd-aa6b964d0c91 |  | note | ACCEPTANCE CRITERIA: Salvagable material to be used wherever possible, the remainder is to be remove from site.
label | 1b4a2841-2d07-5567-8731-712a1b25002c |  | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
label | d69c8b99-dced-5977-8db8-d3445897ab9f |  | note | ○ Tree trunks and large branches shall be removed from the site.
label | 173ef519-f359-5fae-b35e-c4a08603fd19 |  | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | 6f8bae2d-773d-5585-ad75-82425eaa1482 |  | note | Attach: Delivery Dockets (for Items sent off Site)
label | ce04331f-2967-59bf-9eca-6d3173e14f1c |  | note | – – – – – – – – – – – – – – – – –
label | 20f19455-b349-5872-8b0c-4296ba1183e4 |  | note | METHOD: Visual
label | a951c5e2-feb2-500f-a123-b4ba1fe3ffbd |  | note | – – – – – – – – – – – – – – – – –
label | ed35bcee-8c07-5103-b63a-cf1a86c15b6b |  | note | FREQUENCY: Where applicable, each Site
label | 604da063-34a7-50c7-a360-1e8be23c7bb7 |  | note | – – – – – – – – – – – – – – – – –
label | 5f082774-711b-5095-9db4-d535eae9fcda |  | note | CATEGORY: IP
label | b6a13b3e-1583-5b12-9f5b-85dd382024a5 |  | note | – – – – – – – – – – – – – – – – –
label | df7119ab-a9f2-5447-b355-b9ac261a9b87 |  | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | 86fe2415-2f65-5626-ad88-2bd379215a86 |  | note | – – – – – – – – – – – – – – – – –
label | 3476491f-a775-58e6-8e48-c6d1bfac77d8 |  | note | VERIFYING DOCUMENTS: This ITP Signed-off
text | 40ddc51b-6a19-5ece-93d9-2825c0443bde |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b519626d-2102-5e97-9124-5918766d9998 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | bdf29a0e-268a-5055-8331-e8ec00eb513b |  | textbox | Name:
text | b23c98d7-b87e-51e6-ae06-943b2c62f739 |  | textbox | Position:
text | ce378ea6-23fd-57f8-a591-49af20f143bb |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-056-CIV-SSB-Subgrade Preparation - Road | itp |  |  |  | Yes | ITP-056-CIV-SSB-Subgrade Preparation - Road Rev 0 | c47369ae-e017-4a33-93e0-e81567b3736d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 43f1a6b4-521c-559b-8716-f46c9ba08ad4 |  | note | Document Title: ITP-CIV-SSB-Subgrade Preparation - Road
label | fd3dd5b3-7d7b-5f48-b032-e8f438be3fe4 |  | note | ITP Description: SSB-Subgrade Preparation - Road
label | 4d5aaeca-1881-5e6b-9463-7d44ffbbbfeb |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c21832a1-4fb4-5bf6-9b42-2247a076b161 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 273c51aa-23c8-54a0-9ca9-9d662907b064 |  | note | Revision Number: 0
label | c4f95be2-ffb3-5317-aec3-4311cd96b507 |  | note | Revision Date: 11/08/2023
label | df307c58-caf9-5e44-af0e-ab400354add8 |  | note | ITP approved for use by: Victor Mira
label | e3771424-2177-5951-8a50-765b9db83fd7 |  | note | 1.1 Non Dependent
label | 050dfb9d-9974-5f4b-861b-7fdc3755b27b |  | note | Reference: VicRoads Section 204
label | 54fec37a-c5ae-5cea-a2d2-d31c51433b9a |  | note | 1.2 Non Dependent
label | e5b25163-fbed-5585-82e1-8dfc3a7fd833 |  | note | Reference: VicRoads Section 173
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Material Approval
label | 72862695-1125-5a19-87e8-a3086266123e |  | note | REFERENCE: VR 204.04 (C)
label | f198a012-b50c-5b02-8bd2-0bcf5bdd43ac |  | note | – – – – – – – – – – – – – – – – –
label | 969b55b7-eeff-51b8-baa2-39a6267e1ff2 |  | note | ACCEPTANCE CRITERIA: Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
label | 74f5db17-7f5d-5510-ac53-0331d7c591db |  | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
text | 21c18480-bf8f-5b5d-bae6-2a8a6985e210 |  | textbox | Enter: Teambinder Material Approval number
label | 99073c38-e0bf-57db-97b7-2b7e28f304e7 |  | note | – – – – – – – – – – – – – – – – –
label | 69170ad1-8c52-522f-939a-f1fb7b5f095c |  | note | METHOD: Document Review
label | 360c2264-ad88-588c-89e9-b9d2d355a0d2 |  | note | – – – – – – – – – – – – – – – – –
label | c4fcfbe9-e148-5bda-935d-bd0ceae7255f |  | note | FREQUENCY: Once, for each mix material
label | 2e261e98-2b0f-5492-a21a-946ab3d31782 |  | note | – – – – – – – – – – – – – – – – –
label | a2d10b82-a27f-5b76-bed1-7708277f048d |  | note | CATEGORY: HP
label | 127a1708-9efe-579c-ba39-d9a8fd49a661 |  | note | – – – – – – – – – – – – – – – – –
label | e1e10970-820d-56ed-bf76-4bb02080ea11 |  | note | RESPONSIBILITY: Nominated Authority
label | 66c931c3-bc1c-56fd-a92c-4fce157acae9 |  | note | – – – – – – – – – – – – – – – – –
label | b6ed2c20-9b1f-564f-9ccf-e5a47bd9986f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 03106aa2-ea45-5ac6-9289-2c505d5288c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Non Dependent
label | 7fc23713-ec1c-56f5-b3d8-c82560876c5c |  | note | REFERENCE: N/A
label | a7807b01-e0d0-5390-9c01-76943f23be17 |  | note | – – – – – – – – – – – – – – – – –
label | 24a28126-4db6-51e3-9608-d750166eaf62 |  | note | ACCEPTANCE CRITERIA: N/A
label | c40c586b-83af-5800-a7ee-b722a002f587 |  | note | – – – – – – – – – – – – – – – – –
label | 7d42cecd-ac90-5ed0-a21c-20a9e9454e93 |  | note | METHOD: N/A
label | 5222a907-62ee-5708-ab99-678b69d4f1e8 |  | note | – – – – – – – – – – – – – – – – –
label | 36673688-a8fe-5f44-94b8-6ba7be9038bd |  | note | FREQUENCY: N/A
label | 791b7f6d-1f45-582a-b587-e62a40c54d19 |  | note | – – – – – – – – – – – – – – – – –
label | 90232f03-c94b-52f5-bc1c-103a5906271c |  | note | CATEGORY: N/A
label | 5f2b51cf-18ab-57c0-841f-3afded2abab2 |  | note | – – – – – – – – – – – – – – – – –
label | a43175ae-62fe-505b-b60f-897cb6a773dc |  | note | RESPONSIBILITY: N/A
label | b3d4c8bc-2115-5b67-9fc8-2ba7e6143b38 |  | note | – – – – – – – – – – – – – – – – –
label | 0a941dfb-53aa-5cf4-8a63-3d1d59f36021 |  | note | VERIFYING DOCUMENTS: N/A
label | 3602c07d-7085-5791-a9bc-cff0a09980dc |  | note | Date Completed: N/A
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-Out
label | ca3cb0a6-e33a-5102-9f88-58439fec3ad2 |  | note | REFERENCE: IFC Drawings
label | 9c124884-1468-5904-9a7a-f9ace9b8a736 |  | note | – – – – – – – – – – – – – – – – –
label | 3d24f37b-6574-5264-955f-8eb067f02cd4 |  | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | de6e43e0-395a-507a-9fea-f77fa852ce20 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | ec380872-4b3d-585f-9495-643285373ea8 |  | note | – – – – – – – – – – – – – – – – –
label | 17b002d8-2d9d-56b7-bc94-9d35c15f543b |  | note | METHOD: Verify
label | d2f2867c-c725-512e-8ec0-4603d0373de9 |  | note | – – – – – – – – – – – – – – – – –
label | b7e924df-e3ee-569c-9daf-9828694098ad |  | note | FREQUENCY: Prior to commencement of excavation
label | 4788bd36-9cc8-53c0-b954-5f61fcd2dd6e |  | note | – – – – – – – – – – – – – – – – –
label | 65cca9f7-fea9-5b6d-98e5-d07d7d2b5457 |  | note | CATEGORY: IP
label | 97cf5727-7833-556d-977d-2a0b6fda2265 |  | note | – – – – – – – – – – – – – – – – –
label | 65fe314d-7685-5321-a54e-36fa8794a140 |  | note | RESPONSIBILITY: SE/Surveyor
label | 976675df-2906-5be8-808d-2e0126fc27e7 |  | note | – – – – – – – – – – – – – – – – –
label | 9814210e-82df-53c1-8973-b828b0d2710a |  | note | VERIFYING DOCUMENTS: This ITP
text | e5274ee4-d38e-5efa-80e8-c59632623e0a |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Inspection of Subgrade Material-Subgrade Material Properties
label | 9a7fb192-5f58-5baf-b993-32b2908b58a6 |  | note | REFERENCE: Section 204.06 (c), Section 204.06 (e) IFC Drawings
label | c4339e6c-ad67-573b-ac97-73935c402f87 |  | note | – – – – – – – – – – – – – – – – –
label | d12d64b4-4640-5eea-996b-893b7842669a |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | b51e5b02-6e5a-54c2-a776-912d81a88538 |  | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | 2576035e-f803-5df4-816b-119461caa397 |  | note | ○ Assigned CBR ≥ 2.5%
label | b3918b64-014a-5b53-bb67-860de0577f60 |  | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | 77de24b1-24d7-556b-9618-e85388d35bd4 |  | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | d428b87a-62f0-5abc-bff4-12c5c705d25f |  | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | 9c3c3cdb-a2f1-5457-a2fd-878a49fbb6c4 |  | note | Attach: Laboratory testing Verification:
text | 9f88e21c-fde8-5859-b780-7c7ae86a66c8 |  | textbox | Enter: Type A fill Lot Number:
label | b845a033-d7c2-59ab-9b0c-7ccba176f38f |  | note | – – – – – – – – – – – – – – – – –
label | 4be2c54d-e431-5829-8075-3b1c4ed5a175 |  | note | METHOD: Verify-Document Review
label | b4bf38ba-dc97-534d-9258-356ea9020450 |  | note | – – – – – – – – – – – – – – – – –
label | a652ef41-06e5-5108-9f9c-1151d9f5f321 |  | note | FREQUENCY: Each lot
label | 2fe936a8-30d6-5281-bec6-78d2b59738fe |  | note | – – – – – – – – – – – – – – – – –
label | 4422d136-0e87-599e-8239-50f383c7e8fc |  | note | CATEGORY: HP
label | e3c54ca0-ce71-5c2a-bef6-7d18ef19ac38 |  | note | – – – – – – – – – – – – – – – – –
label | d444da0e-7d61-539e-8aad-f1af07b9a51c |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 429aa6b7-49ef-5f86-bb5e-3293de259e2d |  | note | – – – – – – – – – – – – – – – – –
label | be3fa3fd-dd88-5320-903c-48928607e25c |  | note | VERIFYING DOCUMENTS: This ITP/Test Report/Referenced Lot number
text | 98ffe92d-3d8b-5e46-8188-183f4cb8d0ea |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 Material classified as silt
label | 21c0c27d-724a-58b4-b0a2-580c089a1773 |  | note | REFERENCE: Section 204.04 b)
label | 70dd408c-793b-5852-85d3-ac0fd2bce180 |  | note | – – – – – – – – – – – – – – – – –
label | 7628b37d-15c6-5e93-9e44-5bfabdba07e5 |  | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | 9f1f25ca-c335-50f3-94af-421fae5cd320 |  | note | – – – – – – – – – – – – – – – – –
label | 09f9440d-debe-52ea-9579-f171504e2225 |  | note | METHOD: Document Review
label | a69488af-9cd8-5659-a02b-a0690ef39056 |  | note | – – – – – – – – – – – – – – – – –
label | 5dd1ba1b-e446-536b-8a3f-9b7926f2c0d1 |  | note | FREQUENCY: Prior to commencing
label | 7b4fac0d-7135-5dec-9f76-9cbef350bcb7 |  | note | – – – – – – – – – – – – – – – – –
label | 4ec2fd2d-1401-551c-bca2-37e1ca2bf1df |  | note | CATEGORY: HP
label | d0cf831e-fbc8-5001-be13-191c08cb6b02 |  | note | – – – – – – – – – – – – – – – – –
label | ba6af5a2-c58d-5f25-b500-4c4d2527fe00 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 1e6676c4-65bb-5cbb-9b43-e40ba7fa2bed |  | note | – – – – – – – – – – – – – – – – –
label | a82bdc1d-5e8f-59cd-b799-017a7b915bf8 |  | note | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation, Signed ITP/ records
text | 6cbadbab-282e-55be-99f3-e64b78d1b860 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Acceptance of Rock Subgrade (where applicable)
label | f1b4ab8d-656a-5380-88e0-78c061e55fec |  | note | REFERENCE: Section 204.06 f)
label | e5dee5ea-ff0f-5b79-989a-d6b63c2b2fc3 |  | note | – – – – – – – – – – – – – – – – –
label | e5643806-96a8-50af-b396-c5492e8113db |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 9374921d-471b-55b4-a848-f0a556704c88 |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | fc95fd9a-6bb5-578f-b2cd-50824bb644e6 |  | note | – – – – – – – – – – – – – – – – –
label | 3dee2f0f-b636-5d95-a0ce-dec007396cf4 |  | note | METHOD: Site Inspection/ Document Review
label | 754765f0-3b95-5cb4-8f56-1c4ccd9592fd |  | note | – – – – – – – – – – – – – – – – –
label | d61c5edb-d893-57ef-8323-5490d18bbc3e |  | note | FREQUENCY: Prior construction of the regulating layer
label | d2c562d1-2460-50c0-8a6b-052f44089179 |  | note | – – – – – – – – – – – – – – – – –
label | fffc0ae2-ae73-5d30-b06b-16a5857b4a5e |  | note | CATEGORY: HP
label | 4b0c2042-4483-5220-84b4-7d48d866db6e |  | note | – – – – – – – – – – – – – – – – –
label | 9ba87b82-10d3-52eb-b8c4-f4906cfc23be |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 52d51c3a-cfa4-5eb9-a9aa-cfcf79997bec |  | note | – – – – – – – – – – – – – – – – –
label | 475efa8e-0125-5129-8283-02fc54367e40 |  | note | VERIFYING DOCUMENTS: This ITP
text | a5304167-9904-5334-ad52-c0d7cfb22d30 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Unsuitable Material
label | 263648d1-3b90-5917-b80a-6f991e3ddd59 |  | note | REFERENCE: Section 204.07 d)
label | 0c81f2e8-f8c6-528e-bf33-0e5f92a35c28 |  | note | – – – – – – – – – – – – – – – – –
label | 40385ad7-4258-5a78-9b7a-9a00acf0cf39 |  | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | dfd4e832-54c2-56f7-8419-81374646c17e |  | note | – – – – – – – – – – – – – – – – –
label | b2c2ae2b-bad8-5a70-957f-6a77b6ba4489 |  | note | METHOD: Visual inspection
label | 882ef4bc-11b5-5566-bf65-61b1e45ccdcb |  | note | – – – – – – – – – – – – – – – – –
label | 906b7737-a966-50bf-bcd2-aa586a67c9e7 |  | note | FREQUENCY: Each lot
label | a4c86912-cbaa-5283-ae2f-2fbb65bc89ff |  | note | – – – – – – – – – – – – – – – – –
label | 525545d4-e116-5a2b-b09d-290beb6936f8 |  | note | CATEGORY: HP
label | 4b67f3b2-745c-5a2c-8fa3-2aed71d49c40 |  | note | – – – – – – – – – – – – – – – – –
label | 19260519-9ba4-5c81-a6ea-b0b75742cf29 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | d2e81e58-dd36-5fd6-818d-43296fc29bdc |  | note | – – – – – – – – – – – – – – – – –
label | b761b80f-92cf-59ce-a5af-29d10ad1f065 |  | note | VERIFYING DOCUMENTS: This ITP
text | ab19cf57-64d6-58d5-9e25-e2a0b9465a97 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Groundwater
label | 152e1013-f707-522a-8e78-3bca87fde8fc |  | note | REFERENCE: Section 204.06 h)
label | c0e3c65c-a7f0-520e-9dfb-122de4ccba16 |  | note | – – – – – – – – – – – – – – – – –
label | 5115ecd2-7d5a-5d4e-9566-b7386c86bd03 |  | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | b14fa0dc-c5b5-5dda-aada-d828d5beeb6b |  | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | 30781549-88cc-5914-ab5c-7fce6afaaa64 |  | note | – – – – – – – – – – – – – – – – –
label | 3f39096c-6973-54b8-a3e8-a52c21e26ef3 |  | note | METHOD: Visual inspection
label | fdc3d21b-6fe0-51e2-9516-994f405a9234 |  | note | – – – – – – – – – – – – – – – – –
label | f35ba411-65fc-55eb-9f42-40e4982043c1 |  | note | FREQUENCY: Each lot
label | 9785ac06-6456-531a-9aab-0a0520fa9a51 |  | note | – – – – – – – – – – – – – – – – –
label | b6dc25d8-1ee3-532d-9d03-53f9259ed7e6 |  | note | CATEGORY: HP
label | baa9e1c5-baee-56d0-8e6a-47c4f062fbbd |  | note | – – – – – – – – – – – – – – – – –
label | 70e757e7-16f3-5b59-92c3-8feec91d9bb4 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 2f31140c-68be-592c-aa36-d667c6f2fc26 |  | note | – – – – – – – – – – – – – – – – –
label | bf5ae979-82d8-593f-82f3-cb4cace083b5 |  | note | VERIFYING DOCUMENTS: This ITP
text | def140bd-38db-596b-b360-d5ad09c3cdd4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Cut to Fill Zones
label | ddcfb788-d94c-5697-8841-4b16c2f4e110 |  | note | REFERENCE: Section 204.06 g)
label | d41763af-bcfe-5419-b6d0-af1359b11072 |  | note | – – – – – – – – – – – – – – – – –
label | 11e8e4d9-8fb9-506f-910b-777f5aa1a7fe |  | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | 618026d6-1010-55e0-98e6-ca612b7f222b |  | note | – – – – – – – – – – – – – – – – –
label | 919d220f-7780-54bf-a21f-91700f16d9d2 |  | note | METHOD: Site Inspection
label | c5583104-8770-5120-8367-0862de976328 |  | note | – – – – – – – – – – – – – – – – –
label | 33b7f408-5ba3-55eb-8c48-edc7e1ad3283 |  | note | FREQUENCY: Each lot
label | bfc7900f-7e5f-5945-a6a2-50e88d3ef1de |  | note | – – – – – – – – – – – – – – – – –
label | 143e6b06-f90f-55d9-8356-ed6308e3aa04 |  | note | CATEGORY: IP
label | ba9ba640-a25b-5233-974b-efe22267ade0 |  | note | – – – – – – – – – – – – – – – – –
label | bb198729-6790-515a-aa5a-9ed17feaac4d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8d6e5b43-6c6e-5a86-8719-2bd4ce1a69da |  | note | – – – – – – – – – – – – – – – – –
label | cb56ef4a-5908-501e-8634-13c3a7442a41 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | d023d1c0-fc18-5b02-b1de-d87f9425b1d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Proof Roll
label | 3b50f972-5138-52bc-b19a-002be202d65d |  | note | REFERENCE: Section 173
label | a96d8080-d2e6-5c46-8d4d-26a6d2575db3 |  | note | – – – – – – – – – – – – – – – – –
label | 1f6fe37a-7e89-5bb4-a631-e60a007e3e21 |  | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 446745fb-0847-5585-a3d2-c30bff017d95 |  | note | – – – – – – – – – – – – – – – – –
label | a63518ff-0ae2-5e2c-ace4-257438c13126 |  | note | METHOD: Visual inspection
label | bcf1accc-0e7a-50e1-bd32-0ca79736d882 |  | note | – – – – – – – – – – – – – – – – –
label | 8785a5d3-750d-539a-bcb9-8cad567a38d4 |  | note | FREQUENCY: Each lot
label | 9d3546ac-2f88-5c6e-a588-601c9a41f6e7 |  | note | – – – – – – – – – – – – – – – – –
label | 90dc1a5f-9ed3-57de-8a78-8373f7821cfd |  | note | CATEGORY: HP
label | ecf82675-f1c4-51d5-8608-fee86ea5a2da |  | note | – – – – – – – – – – – – – – – – –
label | 787ba668-dfef-5b8a-82b4-abc9294bb95f |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 920f8aff-c366-5870-92f9-0ca2f5fec438 |  | note | – – – – – – – – – – – – – – – – –
label | 72d3af76-fc09-50ee-8dfc-55eeb0191980 |  | note | VERIFYING DOCUMENTS: This ITP
text | fef5ca9d-5bc5-5d0f-8d19-dee01bcbfd8d |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Compaction Testing
label | d261768c-41b4-5a41-a790-056ff1c9fd93 |  | note | REFERENCE: Table 204.131
label | 98aeec87-3f3b-5025-9423-d41767d4618a |  | note | – – – – – – – – – – – – – – – – –
label | bb15fd21-45f7-5628-b3f2-355fa70e11aa |  | note | ACCEPTANCE CRITERIA: All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | f4d00e56-a660-5218-857c-c709aa90b1b9 |  | note | ○ Ripped and re-compacted material below Cut Floor Level
label | b495fe56-ee36-5ab1-8b3b-4f66fa351187 |  | note | ○ Scale A: Characteristic Density Ratio 99%.
label | 043dbcdc-ed9d-5643-9946-2a16b439d8aa |  | note | ○ Scale B: Characteristic Density Ratio 98%.
label | d01b9687-ceb4-5dc5-80b5-125220127a1f |  | note | ○ Scale C: Mean Value of Density Ratio: 100%
label | e48f4bb7-b774-5ddd-8eec-b2d836924a17 |  | note | Attach: Compaction Test Result:
label | c4602536-8e26-591b-bf8d-cf1a8693bb49 |  | note | – – – – – – – – – – – – – – – – –
label | 218b1e14-8250-5d0e-987d-d3140bc04821 |  | note | METHOD: Document Review
label | d0550e8d-8474-575c-a1d9-ebb9763cd94c |  | note | – – – – – – – – – – – – – – – – –
label | 7a1f6b90-cbd5-59ce-8e88-c92697e54a87 |  | note | FREQUENCY: Each lot
label | 88ebffb2-6f51-5c01-8227-db0026f0d2d3 |  | note | – – – – – – – – – – – – – – – – –
label | 9fbfcd89-40b7-5d87-837a-29dec83ee075 |  | note | CATEGORY: IP
label | 5c40642a-91ec-554a-b3cb-95823373a4c0 |  | note | – – – – – – – – – – – – – – – – –
label | bb09f10f-88d5-5ccd-8c57-d6fc4a0ec15a |  | note | RESPONSIBILITY: PE/SE
label | ad57c6f2-d44d-5196-aef7-cf5cb4a1b5cd |  | note | – – – – – – – – – – – – – – – – –
label | 4163a074-01dc-5407-b9ac-88620c8d2f9f |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report
text | 439a0e88-8eca-551d-8fb3-b59c57f5ecc1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Post Compaction Material Property Testing
label | ac99a703-9313-5218-9bbd-45ad5139e52d |  | note | REFERENCE: Section 204.04 (c), Section 204.14 (a) and Table 204.141 For Scal A Section 204.14 (b) for Scale B IFC Drawings
label | ba418250-5f19-5fba-80c7-93ab9deb293c |  | note | – – – – – – – – – – – – – – – – –
label | c119b231-a987-5fe2-9419-6cd1db143982 |  | note | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
label | 6a1aafb4-6e09-5fe9-a4d6-362182d574c0 |  | note | Scale A:
label | b5389c87-068e-57ff-b21a-140c04da34ec |  | note | CBR and Swell as per IFC for design packge:
label | f3052f6a-97f5-5412-91c6-b96ee9c23fab |  | note | ○ MRP-DPK-087-00-CDR-0002-0
label | bb34619d-c722-5c44-b5ae-37650617d181 |  | note | ○ as per table VR 204.141
label | 432a4400-ac83-5ca7-8b7f-4b4293f743ff |  | note | Scale B:
label | 196ff042-b0cd-5744-846f-fe2a1bf261de |  | note | CBR and Swell as per IFC for design packge:
label | fd83fb0c-22fe-5fff-8987-93d82143141c |  | note | ○ MRP-DPK-087-00-CDR-0002-0
label | 0a9e69ae-0987-5b67-a59c-a41c2254a4ca |  | note | ○ First Lot for Max Particle Dimension:
label | ba62fdf4-6fc3-57e0-9e1a-621c4be40955 |  | note | ○ After compaction Type B material shall have a maximum particle dimension of not more than:
label | ef4d0d6e-e46a-534d-b8dc-a217094dde62 |  | note | – 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
label | 5d5ecdd7-d0d5-55f7-aac4-33cb17cd0d51 |  | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 84f66be1-7eda-58f5-b23f-d3c7b7c08195 |  | note | Attach: Post compaction test results:
label | 45e3424b-4fce-5d69-901b-10180ec151da |  | note | – – – – – – – – – – – – – – – – –
label | 539fafb4-685b-5f4d-8d2e-a7332447d0e3 |  | note | METHOD: Review Document
label | ee861b40-acfa-5d56-92ae-e668359e97bb |  | note | – – – – – – – – – – – – – – – – –
label | b2f834a2-d9e8-5441-8bf6-a540d1fb17c8 |  | note | FREQUENCY: Refer to Section 204
label | 14d394ad-0fa4-5e45-8268-05cce7ef1c2d |  | note | – – – – – – – – – – – – – – – – –
label | e15d7c65-92c6-5df9-a5f3-7004293083f3 |  | note | CATEGORY: IP
label | 57a9fa61-a0e6-5fd4-a3e2-e2a3c86d2d22 |  | note | – – – – – – – – – – – – – – – – –
label | e92f37d2-72f8-56ad-9c01-7670a63f6220 |  | note | RESPONSIBILITY: PE/SE
label | ccc79817-abe0-54a0-8357-d5c3ebfa678e |  | note | – – – – – – – – – – – – – – – – –
label | f71c1277-2d6e-58dc-adc4-846fc004ab88 |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
text | 44471867-362e-531c-b2a0-51f81fe2b6dc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Survey Conformance
label | 08321b5e-67c1-5368-80c8-592b2e102b26 |  | note | REFERENCE: VicRoads 204.03f,g and h
label | 9bc124d4-d01a-5328-8f1b-1fda15bf1fcd |  | note | – – – – – – – – – – – – – – – – –
label | 6b78f629-e7fd-55dd-b2e5-6a566f62d724 |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | c272b85b-6b8f-50df-af67-981fee50fc7e |  | note | Level tolerances (Scale A):
label | ffd60f9c-54df-5f24-8224-09343a499d1f |  | note | ○ Range x = +5, -15mm
label | d649d53d-0c6e-5844-9335-bc99447f2884 |  | note | ○ Max S = 12 mm
label | 66d9d045-8aed-52a1-973e-79a88210fa64 |  | note | ○ 80 measurements per lot
label | 13836022-acde-534d-82b5-d00288961110 |  | note | Level tolerances (Scale B):
label | c96be512-c037-5db1-9816-65f2971d5509 |  | note | ○ Range x = +5, -25mm
label | b68d04c4-5b2d-54b1-89a7-7389bd1256c9 |  | note | ○ Max S = 15 mm
label | 237c2e45-0de3-520e-94d1-3cd07e25331f |  | note | ○ 40 measurements per lot
label | f8f7ea42-f4ac-5946-956f-65272f3b7b77 |  | note | Level tolerances (Scale C):
label | b0205a51-7117-5688-b6f0-8abc8c07f63c |  | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 8a9ec1ac-ae9d-5e88-9d6d-1613af00f74e |  | note | – – – – – – – – – – – – – – – – –
label | f8fbeb2e-2d28-5bdd-8bfe-ceba3e509969 |  | note | METHOD: Review Document
label | ca3cbdbb-ef47-5329-916b-8892b6eab40c |  | note | – – – – – – – – – – – – – – – – –
label | df4eb765-a079-5692-8b0c-41c8f651b230 |  | note | FREQUENCY: Each lot
label | 20f347f0-3b05-5764-a09b-25100f76d129 |  | note | – – – – – – – – – – – – – – – – –
label | 97d41209-01db-5be6-82ec-8f53bbc8eab9 |  | note | CATEGORY: SCP
label | ed2b9122-9072-5c85-b7cf-b18fb3b4add8 |  | note | – – – – – – – – – – – – – – – – –
label | c59a9788-cb66-5a05-a73f-964b0b58ddf3 |  | note | RESPONSIBILITY: SE/Surveyor
label | 82aa7d03-47e9-5542-8cae-1a746deb6b4c |  | note | – – – – – – – – – – – – – – – – –
label | c8bbeafd-7197-5c2f-a975-70a10f780ca8 |  | note | VERIFYING DOCUMENTS: Sign ITP, Attach Survey Report
text | 742513f2-d118-510b-8b49-efe6b50d9b07 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | c05c783b-5b0f-519a-88f6-b1daaa6d8cca |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2f7954a7-3d9c-537a-a150-28fb0564b9d6 |  | textbox | Name:
text | 278a50b3-e91e-5274-9bcd-7533476aae5f |  | textbox | Position:
text | b33132bd-0368-52c3-8914-c4c21fa16718 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-088-STR-SSB-CFA Piling | itp |  |  |  | Yes | ITP-088-STR-SSB-CFA Piling Rev 0 | d3e61578-6c22-4a6f-87fd-2ba278163233
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | ce37ef73-4e8a-5b31-84a7-13ab05eaa17d |  | note | Document Title: ITP-088-STR-SSB-CFA Piling
label | f9f382c9-466a-5a6f-9409-97ff3ccc83bb |  | note | ITP Description: CFA Piling
label | 0383d153-fa28-53aa-9e5f-91e59483d9d6 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 9fa81cf5-bb44-5721-a5a7-482a97868bb5 |  | note | Discipline (e.g. CIV/STR/RAIL): 088-STR-SSB
label | 9931dbc4-0014-5a03-9a37-5fbb4a3b02b7 |  | note | Revision Number: 0
label | 739096e2-4ddb-5a55-8aa0-77f07df7064f |  | note | Revision Date: 6/10/2023
label | 5d7314c8-b206-5b95-8e75-3141ad10dd07 |  | note | ITP created by: Victor Mira
label | f0b87ae0-6173-5c9c-9a68-0414afc22e13 |  | note | ITP approved for use by: Victor Mira
label | e00f86c9-68dd-589b-9d54-6550d8f69b31 |  | note | 1.1 Non Dependent
label | deec25ad-cb5e-589d-83fd-7a5b873573f6 |  | note | Reference: VicRoads Section 607 March 2015
label | e01c462f-cfbd-5b14-9c9b-3e7749f4d91a |  | note | 1.2 Non Dependent
label | b53992ca-f875-5cea-92cd-e2abf3cb9aca |  | note | Reference: VicRoads Section 610 June 2019
label | 38e74d20-fa1f-5879-93ac-78ffcb87392e |  | note | 1.3 Non Dependent
label | 52103ce4-e79d-5546-a511-1c39558ba210 |  | note | Reference: VicRoads Section 611 November 2018
label | 1fc603d5-7899-507b-b1d0-51f008ea79e0 |  | note | 1.4 Non Dependent
label | 6ec2342c-d4ab-59b3-aa36-102d20ee1284 |  | note | Reference: AS2159-2009
label | f0425074-4384-529a-9f6f-344b7e0b59fc |  | note | 1.5 Non Dependent
label | 4bf407fb-36e9-586e-9060-5104ce71bb47 |  | note | Reference: AS3810.1-2015
label | 3ab0aeb3-be95-56fb-8fb6-d3bf680c7457 |  | note | 1.6 Non Dependent
label | 8f54073a-225a-59e0-ba49-08a372349636 |  | note | Reference: AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 78255ff4-0c25-58f1-a03f-0556f2ba7a83 |  | note | REFERENCE: 610.07 Table 610.071
label | 79add433-0035-5554-aaef-cb2fcf9dbab5 |  | note | – – – – – – – – – – – – – – – – –
label | 49608451-a0a0-5d86-ae15-e2e6bf9e43e1 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 83a3f782-c89d-59d7-b884-8cd20b8d97e2 |  | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | ff5e37ca-f19a-5884-92ab-6aabdbc9e980 |  | textbox | Enter: Teambinder Material Approval number
label | 9d700b82-0ebc-566c-aa9d-4ae207706787 |  | note | – – – – – – – – – – – – – – – – –
label | 5b3ac936-2b6c-5207-9020-231462a052b9 |  | note | METHOD: Document Review
label | 486c39a3-65c4-527d-acdb-a42ac38a8757 |  | note | – – – – – – – – – – – – – – – – –
label | eb3ef777-f8b3-51fe-bb88-c6b87bf06dff |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 8b484514-4c86-5fcf-b2b8-641df1d548b2 |  | note | – – – – – – – – – – – – – – – – –
label | 7648f3e7-a414-5d58-81ba-616546d8f6eb |  | note | CATEGORY: HP
label | 93502526-a0d0-58dc-9a3c-1d19a1410430 |  | note | – – – – – – – – – – – – – – – – –
label | ad0f964e-dd17-54a6-ba7c-15ee5b4734c2 |  | note | RESPONSIBILITY: Nominated Authority
label | 9bfab37f-8f47-5792-a649-c4684d0205c4 |  | note | – – – – – – – – – – – – – – – – –
label | 2beaecf4-7fae-53e9-93d4-7a25b9cee91c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 0ded282d-791d-558f-b40a-3e0f85f9a91d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 7bd65bad-5e0c-5e52-a595-469296e9342c |  | note | REFERENCE: 611.05 (a)
label | 82b0ef7f-6589-5cb1-bc3a-0a55724cb63c |  | note | – – – – – – – – – – – – – – – – –
label | 8abe62d7-91d7-5d40-986e-fd26aca0f862 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | ed127fc3-b5c9-5b5b-b9e5-1984ba60c947 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | c6b4da98-b01b-5815-a0a2-8cea3b45c243 |  | textbox | Enter: Teambinder Material Approval number
label | 6285d169-9a52-5016-91aa-ad3ab385531a |  | note | – – – – – – – – – – – – – – – – –
label | af94afb6-508d-5346-9979-52c34f0340f4 |  | note | METHOD: Document Review
label | 2808050f-ec43-597d-84fb-1e5a6c09a11f |  | note | – – – – – – – – – – – – – – – – –
label | 50b81989-76cf-5ef8-a15e-e140989dad9b |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | d1f2c93e-5676-59ce-8544-88560a29aa84 |  | note | – – – – – – – – – – – – – – – – –
label | 46447890-728a-5914-a0a4-22de4ff66040 |  | note | CATEGORY: HP
label | d12ad430-999d-5bd4-b6ce-6dca3472632e |  | note | – – – – – – – – – – – – – – – – –
label | 34ec5b8b-2b05-5b68-a45e-400a62266726 |  | note | RESPONSIBILITY: Nominated Authority
label | e8cab6b5-b4cc-5c03-bada-cfb9b0ae25bd |  | note | – – – – – – – – – – – – – – – – –
label | bcfaf1f4-103b-58dc-86d0-dfd7e001a4e0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 96b31571-04ee-594f-856a-414c85f6d9da |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 2daf3003-daec-532d-9895-fcc702b5115d |  | note | REFERENCE: 610.26 (a)
label | bfcc2a23-4d6e-5e0d-9812-c91ddb47d474 |  | note | – – – – – – – – – – – – – – – – –
label | c16abb5e-9ee8-53e5-8cf0-4df0ab34f4f9 |  | note | ACCEPTANCE CRITERIA: Wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
text | 8d89fcc0-3fd0-58a3-acb0-79cdcd75ba41 |  | textbox | Enter: Teambinder Material Approval number
label | 0f90ab9f-052d-5552-8c52-4d557cbe99d3 |  | note | – – – – – – – – – – – – – – – – –
label | 041625c5-b487-5e57-907a-e0efd71f7773 |  | note | METHOD: Document Review
label | 10086686-6d63-50c8-bf5f-c51d0cd25793 |  | note | – – – – – – – – – – – – – – – – –
label | efed78c9-fbbc-590c-9f48-1178ac288cf8 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 9f37edd0-fef6-51ce-9ec8-6af861eaf651 |  | note | – – – – – – – – – – – – – – – – –
label | 0258d279-2d27-54c6-b532-850b976908b1 |  | note | CATEGORY: HP
label | a1c57d98-c8fe-50ce-88d3-b8a8d5692df4 |  | note | – – – – – – – – – – – – – – – – –
label | 2122adb4-e5bc-5aeb-88c6-a74855a7485f |  | note | RESPONSIBILITY: Nominated Authority
label | 94f9d6d1-402f-5077-8447-87b88388732b |  | note | – – – – – – – – – – – – – – – – –
label | 818f3d70-901c-52a3-9de2-15f951c4f9b5 |  | note | VERIFYING DOCUMENTS: This ITP
date | b04159f0-e229-5c9d-af9c-b09a1d08a58f |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | 367852f8-e2d9-55fd-a572-878baebd9965 |  | note | REFERENCE: Piling platform design
label | b4a86204-665b-5df5-9661-a4cf5aada2ce |  | note | – – – – – – – – – – – – – – – – –
label | 88774f8a-9d68-502d-9681-3120e6dd8f0b |  | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement.
label | 385be268-61d9-5194-a3aa-e8af6e241eba |  | note | ATTACH: Piiling Platform Certificate
label | d6c82414-a00f-5335-a484-b3838ee9e33e |  | note | – – – – – – – – – – – – – – – – –
label | 31662025-e223-5b00-8042-1afdc178d2ff |  | note | METHOD: Document Review
label | 6cec18db-1edf-5ade-ae2f-86d272ccd71b |  | note | – – – – – – – – – – – – – – – – –
label | 6b52529c-3d39-5ace-884f-f6bf8f97264a |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | a712c1d3-4732-5263-a232-6899e4c732e5 |  | note | – – – – – – – – – – – – – – – – –
label | ebf0fab2-a1a1-5b82-9555-a89c53b2152d |  | note | CATEGORY: HP
label | 34b2d6b0-5d3c-5205-b06f-51c36ac131c9 |  | note | – – – – – – – – – – – – – – – – –
label | 23356866-44ce-560a-b547-c47a7f231145 |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | a0af1c07-83f1-5e83-81d3-8f3e5aa2d464 |  | note | – – – – – – – – – – – – – – – – –
label | 3026f215-2e42-549d-b1ca-58cdbc986d99 |  | note | VERIFYING DOCUMENTS: This ITP, Platform Certification
date | ba4c118c-057d-558e-939d-004883e32896 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete CFA Pile Design
label | 6a1ae8bd-7739-585b-994f-a082666ae9a2 |  | note | REFERENCE: 607.01 IFC Drawings
label | ea2471da-3230-5f14-9432-d0b93fd5b606 |  | note | – – – – – – – – – – – – – – – – –
label | 08499d74-8acf-5b3f-9da0-9b9d79887e39 |  | note | ACCEPTANCE CRITERIA: Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
text | 239f8a1e-1686-5eb9-9071-d7aaaa6d98f1 |  | textbox | Enter: Teambinder Approval number
label | 6e07dc0b-9200-5f27-8e8e-a74ff9c17099 |  | note | – – – – – – – – – – – – – – – – –
label | 6612fbe4-d193-5ee5-b9ac-fc330093212d |  | note | METHOD: Document Review
label | 367fe31c-3497-5ead-a778-c3642a96d389 |  | note | – – – – – – – – – – – – – – – – –
label | 9e3da163-8e60-537b-a17a-1d7e2c4095a4 |  | note | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
label | 9c39b601-8a7a-5ad8-a1d7-931d7bb44dbe |  | note | – – – – – – – – – – – – – – – – –
label | bd91fbb7-2464-5b57-94db-82a838c986a3 |  | note | CATEGORY: HP
label | 868d0a67-3ca2-51ee-8a6f-a98d9c7bfea8 |  | note | – – – – – – – – – – – – – – – – –
label | 3b985391-e031-5e3d-b335-1cae722aef19 |  | note | RESPONSIBILITY: Nominated Authority
label | 175ed209-27a3-5dd1-9400-0c9decd2418e |  | note | – – – – – – – – – – – – – – – – –
label | 16d360a0-5cea-5da1-92d6-0831308077ac |  | note | VERIFYING DOCUMENTS: This ITP
date | 1cbebf6f-807c-54c2-be0d-cc55b184f1d0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Piling Operations Work Procedure
label | 4e9060c1-e956-570e-9341-57bdee8a820f |  | note | REFERENCE: 606.03 (a)
label | 1815493b-8184-515d-8b4d-091d9eb42e18 |  | note | – – – – – – – – – – – – – – – – –
label | 9a2bcfd5-25d9-56d7-8f61-2261fc82f8cf |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | e0380fd9-53c0-5272-b9c6-45611a4ec6b3 |  | textbox | Enter: Teambinder Approval number
label | 67071498-e961-56a5-8179-35f0eb260b63 |  | note | – – – – – – – – – – – – – – – – –
label | a985af60-e19f-5c14-8a46-a01c4be2980c |  | note | METHOD: Document Review
label | 0f5925b3-2ac5-5bf8-b41a-2b9ac0c7f322 |  | note | – – – – – – – – – – – – – – – – –
label | bd0c6efa-fbba-5824-a18d-a1927ca34628 |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 105bf3a1-a7f9-56bf-990b-eff503151a53 |  | note | – – – – – – – – – – – – – – – – –
label | 044c55dd-30f6-59db-8078-2ff265910f2c |  | note | CATEGORY: HP
label | 1d593e2f-6a06-5429-978a-cddd1ab4dd05 |  | note | – – – – – – – – – – – – – – – – –
label | 110c4cd2-ab5f-5b15-935f-50d645e6122a |  | note | RESPONSIBILITY: Nominated Authority
label | 1df8b480-9afb-55f4-a215-c1ea4e31cd31 |  | note | – – – – – – – – – – – – – – – – –
label | 08a36ffa-bf42-5841-ad23-b66363dccb6f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 28200b30-098a-5e7a-b473-047836185049 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | 61c6daee-2dfd-542e-ba20-7a382a762019 |  | note | REFERENCE: 607.04
label | 732075ee-d818-5b61-ba47-8a8cea223545 |  | note | – – – – – – – – – – – – – – – – –
label | 7359427f-8b64-5ddf-9e73-8e1dc534b47e |  | note | ACCEPTANCE CRITERIA: Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
text | 6d26025e-5fa1-545d-9576-2d13bb15b743 |  | textbox | Enter: Teambinder Approval number
label | 5772f720-0d9d-5668-8563-234ae2f84ddb |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 75705bd9-1748-5735-ac89-fcc4c804b5bb |  | note | – – – – – – – – – – – – – – – – –
label | b13baa63-5db8-5511-b723-fb29b5e48bf7 |  | note | METHOD: Document Review
label | 83fe223d-d974-5345-bf63-d8b3f5b0ea98 |  | note | – – – – – – – – – – – – – – – – –
label | 9bd8a5b2-d9aa-5be7-86db-22fc6f76af59 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 7d703e67-ce49-58b8-8560-377822191af0 |  | note | – – – – – – – – – – – – – – – – –
label | bc898154-95dc-553d-a8d0-b4c4093f1012 |  | note | CATEGORY: HP
label | 9ba45203-95a2-5611-905f-4c299f602146 |  | note | – – – – – – – – – – – – – – – – –
label | c0ea5c15-3753-5a43-8627-3ea1463a86d2 |  | note | RESPONSIBILITY: Nominated Authority
label | 527d26ad-6af4-5581-8531-909f49287ae2 |  | note | – – – – – – – – – – – – – – – – –
label | 45994e4e-06e8-56d3-a3b2-9b6f50d5cfc5 |  | note | VERIFYING DOCUMENTS: This ITP
date | 9ad12ddf-f9bb-5d61-a416-06a3fff46d58 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Dynamic Pile Testing Procedure
label | ffbc2438-a24c-5aaf-abe0-e96995acebd7 |  | note | REFERENCE: 607.07
label | cc626ac1-f783-513a-9326-3773161be8de |  | note | – – – – – – – – – – – – – – – – –
label | 448c4288-106f-5a85-8ee5-d0e54ebcbfb8 |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 38200a75-af1c-5890-864a-92607af6a430 |  | textbox | Enter: Teambinder Approval number
label | 6f4ca88f-c509-544b-9b7a-438c1486c034 |  | note | – – – – – – – – – – – – – – – – –
label | c8a080bd-74cd-5482-9ab4-881d20e394ce |  | note | METHOD: Document Review
label | 2d0a399a-3075-50d8-a0f4-411134a6c229 |  | note | – – – – – – – – – – – – – – – – –
label | 60a3ef58-eeda-59d4-a487-c3fed8551f89 |  | note | FREQUENCY: Once, prior to testing
label | d6639a63-232f-52ec-b829-19392a252f08 |  | note | – – – – – – – – – – – – – – – – –
label | 9a1b1b8f-9d69-53f8-8276-4f77308e167a |  | note | CATEGORY: HP
label | e336f652-0b5a-57fd-be5f-f87fb6e7dad4 |  | note | – – – – – – – – – – – – – – – – –
label | f77fda92-1e5e-5c95-a910-014bcfe48dfa |  | note | RESPONSIBILITY: Nominated Authority
label | 385b0d33-65a5-5617-b1bc-b77c1c24ef7f |  | note | – – – – – – – – – – – – – – – – –
label | a9471b2e-5392-5083-926f-209c5e9203f0 |  | note | VERIFYING DOCUMENTS: This ITP
date | 799fd910-5af3-5dc7-8130-bdace764deb0 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Pre-qualified Pile Testing Consultant
label | aea3b065-ecfa-509e-ad67-f58a74a05f9f |  | note | REFERENCE: 607.07
label | 26e59fc1-c23e-50a3-993c-d4ee119fe105 |  | note | – – – – – – – – – – – – – – – – –
label | 980c931e-9f8d-5083-88b5-d89e65375227 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | af911ab6-56b2-5002-975b-230482aa69b0 |  | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
text | 7aafb37d-c3c7-5915-8b77-5a0614f3458d |  | textbox | Enter: Teambinder Approval number
label | 433b83b8-7984-51c4-887e-e4273dc66512 |  | note | – – – – – – – – – – – – – – – – –
label | 45d062f3-37b4-51f8-b65c-b242646abc8b |  | note | METHOD: Document Review
label | 93686288-f15f-5d5b-8ae2-8166b339c4e9 |  | note | – – – – – – – – – – – – – – – – –
label | c20a8953-c93e-5977-8f1b-9293862272ed |  | note | FREQUENCY: Once, 2 weeks prior to testing
label | 665d0c32-a94b-51a0-8312-b4a0f440d8b1 |  | note | – – – – – – – – – – – – – – – – –
label | f7329050-acd4-5f1a-aee4-5606858f7624 |  | note | CATEGORY: HP
label | 9fc8f1f1-1f4b-532d-9d58-5d5b8a3caffb |  | note | – – – – – – – – – – – – – – – – –
label | 6306dc3f-b31e-5f42-8ab7-7bad4ec4188c |  | note | RESPONSIBILITY: Nominated Authority
label | 6f4abe53-3a91-5182-8797-d274f5d7c203 |  | note | – – – – – – – – – – – – – – – – –
label | 9aabeca8-225c-5e5b-838b-19e598ffd57c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | fde87147-16e2-5fc0-8f13-958226288d4e |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
label | f86c6f37-dc0b-5fee-8a67-89596071360a |  | note | REFERENCE: 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
label | fd321fdf-40db-573c-b5c1-150b903f00e0 |  | note | – – – – – – – – – – – – – – – – –
label | ffcb4a38-4167-5ff8-9a0f-490c169a4a41 |  | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | 68649927-7992-5402-9726-70f78e634cfa |  | textbox | Enter: Teambinder Approval number
label | 36a0d57e-a136-56b4-889d-56a7387b1629 |  | note | – – – – – – – – – – – – – – – – –
label | bac90f7b-8be7-53ea-8742-7a271e56b52f |  | note | METHOD: Document Review
label | 16eb88e2-7cab-5c80-bfe6-1d73c7779d15 |  | note | – – – – – – – – – – – – – – – – –
label | 0c1a48d6-d11a-5abb-8a72-c390c556b383 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 573f0454-941a-5740-a880-cfb408872c05 |  | note | – – – – – – – – – – – – – – – – –
label | 758d975e-ddee-516e-9f9a-6388557e7464 |  | note | CATEGORY: HP
label | 9860dcbf-b240-5fef-9ec3-3cf4ecc6f49c |  | note | – – – – – – – – – – – – – – – – –
label | 7e16a135-3f28-53ce-88b3-b191b19190e9 |  | note | RESPONSIBILITY: Nominated Authority
label | a79b98d0-a868-5d3b-ac15-ceb08002e833 |  | note | – – – – – – – – – – – – – – – – –
label | d8aadd38-de18-5ecb-aa34-dc7c230e5816 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 512142dc-8906-580a-9c32-f4f02f293d2b |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 6cbe3aae-92d8-51f0-8845-604710e27cd8 |  | note | REFERENCE: MRPA Quality Management Plan
label | ebfb51e5-91ce-5dcf-811b-dc3d591ef3d1 |  | note | – – – – – – – – – – – – – – – – –
label | 82e81376-0688-5064-be8b-acad138af265 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 9122d00a-1d11-5a21-b2e9-1d96c64cb806 |  | note | – – – – – – – – – – – – – – – – –
label | afbac224-561a-5c9e-862f-4d57a235a5e1 |  | note | METHOD: Document Review
label | 0f4a4015-b958-581e-96d5-2a158842fa02 |  | note | – – – – – – – – – – – – – – – – –
label | 59ba392d-cf90-542a-980a-3f03719d0550 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 3e666726-00ec-50d5-83e5-88559b42792f |  | note | – – – – – – – – – – – – – – – – –
label | bf84d808-9eba-5e07-bdb4-d55505a08f3e |  | note | CATEGORY: HP*
label | 4a1bbf32-16a7-5c76-8c76-5e7474ae63d3 |  | note | – – – – – – – – – – – – – – – – –
label | b3f7f45e-14d7-5d81-929f-66d6c8222b16 |  | note | RESPONSIBILITY: All
label | 933cd9cf-8a78-5463-bbed-bf89a2b73705 |  | note | – – – – – – – – – – – – – – – – –
label | 47a216ce-26d1-5d63-92f4-11683a576d8c |  | note | VERIFYING DOCUMENTS: This ITP
date | f19e295c-68e2-5c9e-8d88-28cd4148f625 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 085b8400-2040-5134-ba2f-a24f9966b1a9 |  | note | REFERENCE: IFC Drawings 607.06 (a)
label | f03974ef-0c9d-5c87-bc73-27e827fbbe5a |  | note | – – – – – – – – – – – – – – – – –
label | 0476ec99-803e-5efe-9e42-b013665ffef4 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 7fe4dda2-415d-5f9f-9003-7fcfb20c42df |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 5aed1df6-3574-5002-8295-e51428599242 |  | note | – – – – – – – – – – – – – – – – –
label | 89239d70-d462-52ae-9094-4f4cee8b8b0d |  | note | METHOD: Measure, Visual
label | 55ff35a3-cee0-5225-8a7b-c61c8fdbd408 |  | note | – – – – – – – – – – – – – – – – –
label | a4216ab5-fa9f-5b09-b2ea-1e00e71d4123 |  | note | FREQUENCY: Each pile
label | df8d1009-271f-531c-93a3-45c95c6ba806 |  | note | – – – – – – – – – – – – – – – – –
label | 24d23c7b-e3f6-5d92-ac90-3274164ecdd0 |  | note | CATEGORY: IP
label | 1fd1cdd1-d51f-5028-867c-73eebaad3a21 |  | note | – – – – – – – – – – – – – – – – –
label | 701cac65-b38e-55a4-aa4a-9e5e8cdaefb5 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 7dd9f119-3419-52b8-91e1-acb7587b87dc |  | note | – – – – – – – – – – – – – – – – –
label | 0a68846e-15c2-53d2-b958-c77eb6c3951b |  | note | VERIFYING DOCUMENTS: This ITP
date | 3f0ba86f-61f3-5019-9415-69503bc28317 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 83a11a23-115a-584e-b542-ab42ff3c9dac |  | note | REFERENCE: 607.05
label | ee671884-afe6-50ed-a0e8-517e7b9dcc0c |  | note | – – – – – – – – – – – – – – – – –
label | a87901c2-2de8-5129-8953-b68a64f99518 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
label | 9d4b6070-e384-566e-be52-5e9fefcf0c9f |  | note | ○ Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 Mpa
label | befb2217-100d-58d0-abee-c9750e1856cd |  | note | – – – – – – – – – – – – – – – – –
label | 40a3b7d7-c56f-5a78-ac7c-e199a855e79f |  | note | METHOD: Measure, Visual
label | 6251b6e4-6aca-5eba-a549-823b9b838526 |  | note | – – – – – – – – – – – – – – – – –
label | 1e91fba9-653f-50e1-8d58-42fc28f5f63b |  | note | FREQUENCY: Each pile
label | 08cc4f44-7195-507c-b063-06e923565db9 |  | note | – – – – – – – – – – – – – – – – –
label | 910d7c5d-1f09-5cff-8997-c7ec7a84e6b9 |  | note | CATEGORY: HP*
label | 1952dc61-d804-5e02-a661-80751bf7eee8 |  | note | – – – – – – – – – – – – – – – – –
label | cd6da1fb-d060-5b9a-a9e9-c87c6d8e2496 |  | note | RESPONSIBILITY: SPE/PE
label | 930e2a14-b424-56cd-86c9-62f4088530f9 |  | note | – – – – – – – – – – – – – – – – –
label | 139ea829-398d-5aa3-b58d-e92c6260d418 |  | note | VERIFYING DOCUMENTS: This ITP
date | 92d17f58-1c4c-56db-8aac-fbfc7ca8d5d1 |  | date | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Reinforcement - Inspection
label | 71cc85e3-7300-5cfb-8936-e20c7c67077d |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | e58173aa-50b6-5d06-bbb6-e15606408ab5 |  | note | – – – – – – – – – – – – – – – – –
label | 5518a310-8609-5aa2-a835-c0d8cc5fb2e6 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | b88a9b05-ba65-5565-9227-5dcaa6b87907 |  | note | ○ Projecting reinforcement is the correct length and location.
label | dc9d9f1f-7f8b-5e8a-a5b7-8910bbf0dfbf |  | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ce182849-d444-5f4e-8003-aaf3505784d8 |  | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | d42bacb0-8798-58b4-b94d-1668cc2a844e |  | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | da3edd89-0d34-55aa-a760-ce9dce75edee |  | note | ○ The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
label | fc2857d5-e576-5df6-8d78-2585664e8820 |  | note | – – – – – – – – – – – – – – – – –
label | 26dc6085-4b4e-520c-a1e0-6a21f864a0aa |  | note | METHOD: Measure, Visual
label | 36247318-cebe-5a0d-8dd4-534f7067f1bb |  | note | – – – – – – – – – – – – – – – – –
label | c43ea7f4-8ca9-5b73-b68f-d9ee171a7770 |  | note | FREQUENCY: Each pile
label | ef69c6fa-944f-5da6-b657-27bd6ad43e0b |  | note | – – – – – – – – – – – – – – – – –
label | feb23be9-aa79-5350-899e-e98c85e01a19 |  | note | CATEGORY: IP
label | c78be086-dbda-52b6-be44-0e49bebdb27c |  | note | – – – – – – – – – – – – – – – – –
label | d2ecb7ac-4eca-56e1-86e8-62bc31f9ddae |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 3eb1a448-5ff7-5e1c-9d91-d0d7aadaa20c |  | note | – – – – – – – – – – – – – – – – –
label | a58eb6c6-03c7-5a1d-878a-104ad0d6495e |  | note | VERIFYING DOCUMENTS: This ITP
date | 724e3aaf-c0f8-5fb2-b28d-90f1a38858cc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Reinforcement - Electrical Continuity
label | e493912b-5be9-504a-97b2-77b2802918b8 |  | note | REFERENCE: IFC Drawings 610.29 (d), 610.43
label | 18212ef2-6e35-599a-99a5-e81ca9f2a683 |  | note | – – – – – – – – – – – – – – – – –
label | e63f36d4-104f-5b35-ba43-14fc199f93b6 |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | a81895c3-230b-5073-a92d-d614bd861764 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 59736c91-d7f5-56ad-8e18-818280ce819c |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | 4d59e3a1-84ed-5489-b655-0b57330abb23 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 1886bacc-4579-5203-a636-2a6d764ea664 |  | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 928b2f18-5aa7-5f8a-90e4-f281ce4b7e75 |  | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 2a9b0ce5-04bb-5a76-acce-8721d97ab70a |  | note | – – – – – – – – – – – – – – – – –
label | 37cfdd2f-50b9-57c3-bbe1-7ea3db67d7cd |  | note | METHOD: Measure, Visual
label | fcc56d71-c530-5b3c-a101-896e55fadc9a |  | note | – – – – – – – – – – – – – – – – –
label | b525e2eb-2ba7-5bf5-a972-507da7fce95c |  | note | FREQUENCY: Where applicable, each pile
label | a0767561-74ba-58ca-802c-f5d20b925127 |  | note | – – – – – – – – – – – – – – – – –
label | 200684bf-df27-5f34-84dc-391a1c03d10e |  | note | CATEGORY: IP
label | 3a00e492-fb52-5eaf-9a3c-bc3d6727e7dd |  | note | – – – – – – – – – – – – – – – – –
label | 76ca7d32-99e3-5fd3-a6b4-45e7a94ef191 |  | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
label | 98c53ee7-e27d-5173-86fe-3a06072c86b6 |  | note | – – – – – – – – – – – – – – – – –
label | 3a63c3a0-51f2-571b-a125-38839cee3ee6 |  | note | VERIFYING DOCUMENTS: This ITP
date | 240ef8bb-746c-5c39-99ef-cdbb5ed773bc |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Augering Operations
label | fcdbaca9-0c23-59c6-b09b-402638ebcc2a |  | note | REFERENCE: IFC Drawings 607.04
label | cf151e9e-e445-58c9-9153-d90ab2f777e1 |  | note | – – – – – – – – – – – – – – – – –
label | 109cf183-117e-58b2-83df-f85682f856b2 |  | note | ACCEPTANCE CRITERIA: Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | caeb467f-a0a4-5cb1-a8d2-d22914f82857 |  | note | ○ The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
label | 09765511-eac2-5413-ac31-c7c77227e361 |  | note | ○ Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
label | 28094a3f-7062-5b57-ac64-cbfd69413d53 |  | note | – – – – – – – – – – – – – – – – –
label | 2e852797-d569-5375-a94c-afadac9b6d1c |  | note | METHOD: Measure, Visual
label | 29639528-a711-59f5-9e6c-db4abf11fc21 |  | note | – – – – – – – – – – – – – – – – –
label | 6dfbeb58-690a-52bf-a5f0-e2ea9b346b8d |  | note | FREQUENCY: Each pile
label | 164c5f35-af5b-5edc-aa98-b45a4f8bd4a3 |  | note | – – – – – – – – – – – – – – – – –
label | 4fbc5f7a-c8b7-5141-9801-b69ad10d557a |  | note | CATEGORY: IP
label | 4532ee6b-0d83-55e6-bcd8-31238bfbe361 |  | note | – – – – – – – – – – – – – – – – –
label | be7c161f-5943-5735-9bec-790915c6c5de |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | dddea390-4f3b-50dc-b3a0-f8ffd4ca0ee5 |  | note | – – – – – – – – – – – – – – – – –
label | 838d3a92-b172-5fa8-8a2b-6c7a57558294 |  | note | VERIFYING DOCUMENTS: This ITP
date | e935d3db-5a0d-5de5-a917-2c40cd25f302 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Inspection of Excavated Material
label | 71fc95cd-b548-53e2-9396-d70a9ce5e50a |  | note | REFERENCE: 607.04
label | d6d4b4d3-3874-5e17-b2f0-2fc87aaa52cd |  | note | – – – – – – – – – – – – – – – – –
label | b39e7e9b-0032-5a6e-b7ce-672a4b703fea |  | note | ACCEPTANCE CRITERIA: Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 49693156-86da-5c5a-8b7f-25a8d873afbd |  | note | Attach: Geotechnical Field Sheet or Report
label | f2db6836-bea0-5541-8e0b-db43d020fd89 |  | note | – – – – – – – – – – – – – – – – –
label | b3cf4ed2-a78f-52d8-beb7-cbef2a13b07d |  | note | METHOD: Measure, Visual
label | 76a1363d-1f72-5283-80b9-5478c2423490 |  | note | – – – – – – – – – – – – – – – – –
label | 87f60046-488f-59d0-aea2-7b816f4b4c5e |  | note | FREQUENCY: Each pile
label | 33bf5ec6-ef34-54ca-a98d-1cb37f021970 |  | note | – – – – – – – – – – – – – – – – –
label | 36626423-dce4-5bbf-8c8e-d74931b30bb2 |  | note | CATEGORY: HP
label | 51e603d8-78fd-5f09-a5db-9410414acfea |  | note | – – – – – – – – – – – – – – – – –
label | 69493d29-491a-5be9-98ba-d413598738fb |  | note | RESPONSIBILITY: Geotechnical Engineer
label | c99bece1-b435-576b-a1b7-ac994c9a970d |  | note | – – – – – – – – – – – – – – – – –
label | 05a0bd0f-9efe-5650-a3b3-65aeddfd2c5d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | 239684ae-3c8b-57c9-89cc-8591b24d84da |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Increase in Depth Beyond Design
label | f9124dcd-63e7-5c3e-9779-ccc927a48077 |  | note | REFERENCE: 607.04 (a - d) Piling Operations Work Procedure
label | 49365e61-4848-5e66-951b-ca5e73d15d73 |  | note | – – – – – – – – – – – – – – – – –
label | f2915281-9ba8-538f-9837-cebb72d20b0d |  | note | ACCEPTANCE CRITERIA: Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
label | 63f98458-887a-5fbe-9860-cbab85de43f7 |  | note | ○ A full account of the changes shall be submitted for approval to the Nominated Authority:
label | 0d1142f5-4490-596f-9823-24f22d5545cf |  | note | Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
label | 4b42d1dd-27e7-5643-be42-a7d6554682ea |  | note | – – – – – – – – – – – – – – – – –
label | bccd2a1a-d64d-5579-9215-62e461e035e0 |  | note | METHOD: Measure, Document Review
label | 4769f511-22d4-5cd0-8d47-0f37f2f6cc12 |  | note | – – – – – – – – – – – – – – – – –
label | 1676d798-c39f-50a2-bd3e-92405436ab65 |  | note | FREQUENCY: Where applicable
label | c2c17470-925c-54f5-acdc-d1b5f7ae5256 |  | note | – – – – – – – – – – – – – – – – –
label | 2b64afbe-4aa4-5cfe-88e5-838f4da72b43 |  | note | CATEGORY: HP
label | 5ed44b24-af6f-5c4b-a437-ddc09662b651 |  | note | – – – – – – – – – – – – – – – – –
label | bc398501-5918-5a72-8693-07ea401d856b |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 8af1d52c-929f-53f3-872b-171abb89e0ba |  | note | – – – – – – – – – – – – – – – – –
label | 1704fbfe-5448-5674-927a-5f792aec80d9 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | f9664053-79b4-5daa-8273-e7385a13f601 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Weather Conditions & Evaporation Limits
label | 6c4354bb-d852-52c0-8018-8944342ef096 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | 5a1df9d5-edc6-5c55-a509-a5894a1ca898 |  | note | – – – – – – – – – – – – – – – – –
label | 2bfbf3ac-1c99-52c4-8445-372dc54e38d3 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 3ea0d18b-60a5-5514-8e8f-ac6ba200ea6e |  | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ebdc9e67-5ffb-53aa-ac9a-fb22f6e21162 |  | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 628a5fb2-e53c-555d-bd25-908615bb9017 |  | note | Record: Required information on the Concrete Pour Record.
label | 0207048a-9d59-5e53-95c2-5b4b3a7a8aeb |  | note | – – – – – – – – – – – – – – – – –
label | 579bdd69-d9e1-58fa-8803-43eb36e30b06 |  | note | METHOD: Measure, Visual
label | 6b83db97-ad3d-5e29-b0c0-7119bda0bf93 |  | note | – – – – – – – – – – – – – – – – –
label | a5ae7fd0-cfe3-5061-9a9b-9e39b467e608 |  | note | FREQUENCY: Each pile
label | e25d8e69-2d97-50bf-81cd-4f27f0782d75 |  | note | – – – – – – – – – – – – – – – – –
label | 3147301b-9326-5ea8-81ea-6d4430876e89 |  | note | CATEGORY: IP
label | 4a2ac6ef-6741-53af-a100-b88bc4480934 |  | note | – – – – – – – – – – – – – – – – –
label | 052e952e-0171-5b7d-8d30-476a74cd23cf |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fb436669-b701-5d6f-b8f9-3b723421700b |  | note | – – – – – – – – – – – – – – – – –
label | beb40417-efb0-5041-8030-9420435e2143 |  | note | VERIFYING DOCUMENTS: This ITP
date | 10b82ba4-839f-5762-91f1-036142b6c433 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Concrete Testing - Sampling Frequency
label | ac7d0bb7-39ad-55ba-8f77-67607991cf8f |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | 1d85bd2c-cc53-5148-8ffd-f98dee8a74fc |  | note | – – – – – – – – – – – – – – – – –
label | 7578848b-3589-5dfb-8d00-b4dcdb3c6803 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 6628801e-91d8-58e2-a0b6-719d28c7fef7 |  | note | 0m³ to 10m³ = 1 sample
label | 9fbeb11c-1230-53c7-a0f7-b308753c661d |  | note | 10m³ to 25m³ = 2 samples
label | b70783f5-c31f-574a-8d5d-cb0a10ff5584 |  | note | 25m³ to 50m³ = 3 samples
label | 024ffec2-ac2b-547d-9dbc-ef13bac034ce |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 3cbbbc94-49a5-5ff3-b5ff-8c25a3fa1671 |  | note | ○ For each additional 50m³ and additional sample shall be taken.
label | 0ae47074-e043-52ec-9887-7f59ed77406c |  | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | db5197d1-6aa5-5641-91eb-781087e3629d |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 3bd648e9-23e9-52db-9aef-78c988e5d58f |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | a4f19947-3038-55f9-9e55-ffa5b75ce72e |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 457ddedb-2a49-512d-96a5-d7e476beef5d |  | note | Record: Required information on the Concrete Pour Record.
label | de9bb299-49f2-53f0-908b-8d56b1431b47 |  | note | – – – – – – – – – – – – – – – – –
label | b84a4e04-b62f-51c8-a4db-9e8786dce195 |  | note | METHOD: Test
label | 51a1e4aa-1327-5602-8024-9e980ddef260 |  | note | – – – – – – – – – – – – – – – – –
label | 23c9c9a3-d9b6-56c2-bfd3-18eb3eaa3d6d |  | note | FREQUENCY: Each pile
label | 7b8d6229-4dca-5a60-b159-5809154295d4 |  | note | – – – – – – – – – – – – – – – – –
label | 2575d3f3-3cba-5829-a767-f396132298af |  | note | CATEGORY: IP
label | 993dcf6c-e699-5dae-a508-ad7d7a61d1ca |  | note | – – – – – – – – – – – – – – – – –
label | c213cdca-a3dc-5d87-a0e0-0d1641ced218 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | e4f8abde-6567-5383-97a2-a0a0ce9abf96 |  | note | – – – – – – – – – – – – – – – – –
label | db32c4f0-e06d-59c8-9921-bce02f9c181c |  | note | VERIFYING DOCUMENTS: This ITP
date | e67c3525-aa9e-5f30-ac14-379b30be2b72 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Concrete Testing - Spread, Passability & Viscosity
label | 5e2dc623-9b53-5eb8-bf78-96e775507633 |  | note | REFERENCE: 610.13 (b)
label | 15c863ac-ddb1-574d-80e2-9732a509e952 |  | note | – – – – – – – – – – – – – – – – –
label | 8f8d3f22-a83a-562e-9381-1438e1dc0160 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | 593674fa-5430-5247-bc7c-9e088e404520 |  | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | d11a385b-dd49-52d9-8b5b-0229f24830fc |  | note | ○ Passability = ≤10mm (aggregate height differential)
label | 10ac6740-46da-5c60-99ae-ad8854cfb615 |  | note | Record: Required information on the Concrete Pour Record.
label | 99ab5fd4-ae66-55e1-a373-9d47039b29d0 |  | note | – – – – – – – – – – – – – – – – –
label | d171d348-0130-5000-9041-ffae8ac654bf |  | note | METHOD: Test
label | d6855e56-8457-5ac6-a0d9-1a6490046304 |  | note | – – – – – – – – – – – – – – – – –
label | 13a47615-5744-5507-be00-be23d3d27046 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 62946e57-a8bd-5589-bd6b-34223c6ac4fd |  | note | – – – – – – – – – – – – – – – – –
label | 8ea9b865-7623-5eb4-8355-592f159f1463 |  | note | CATEGORY: IP
label | cbfec71b-d19f-58c6-9f40-32793a855397 |  | note | – – – – – – – – – – – – – – – – –
label | 60d1bfc2-ca9c-5372-b823-a77fc5b31473 |  | note | RESPONSIBILITY: Concrete Tester
label | 4ed410e5-f63a-5133-93ac-4778a23a2be5 |  | note | – – – – – – – – – – – – – – – – –
label | 215c2bb6-63b9-53e9-9a97-049ef3220173 |  | note | VERIFYING DOCUMENTS: This ITP
date | 545b0136-5480-56f0-9ef7-9e7eb392b03c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Compressive Strength Cylinders
label | f0c78711-6bd0-539e-9b2a-a4be8c971b7d |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | b00e08a6-63db-5373-a89c-2df8daca0a58 |  | note | – – – – – – – – – – – – – – – – –
label | b60dfe3e-5f6d-579c-9a86-dcb60433d71a |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 653d7941-1dcd-53bc-9a60-8017ecf8d9f9 |  | note | Record: Required information on the Concrete Pour Record.
label | d45f1c54-a644-5c80-ab55-5974a7d62f38 |  | note | – – – – – – – – – – – – – – – – –
label | fc711092-c709-597d-b116-1bab7c7084e6 |  | note | METHOD: Test
label | bf2fdc4e-a54d-5a61-b5a0-df9badb87d3e |  | note | – – – – – – – – – – – – – – – – –
label | 99972190-acba-5c92-9c8d-16b38acc7faa |  | note | FREQUENCY: Each sample
label | 5e3d3585-6b65-505a-8ed5-c7d8bd3d22f3 |  | note | – – – – – – – – – – – – – – – – –
label | ae043bf1-f888-5c23-801d-3bb2533fa8b2 |  | note | CATEGORY: IP
label | 41a1d36c-1f20-5521-95db-7b5b6ec23946 |  | note | – – – – – – – – – – – – – – – – –
label | 462db342-c01c-5e80-a0bf-81220451a24b |  | note | RESPONSIBILITY: Concrete Tester
label | 536b87da-3a19-5812-97d7-62e347f2b879 |  | note | – – – – – – – – – – – – – – – – –
label | 0d0e7f0e-d6c7-5208-a04c-0de8f0baefd4 |  | note | VERIFYING DOCUMENTS: This ITP
date | ee3e51c0-0365-5570-8877-530506af4145 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Placement & Compaction
label | d9f51a49-e7c6-502f-8b17-43993afc5966 |  | note | REFERENCE: Piling Operations Work Procedure 610.18 (a) & (b), 610.18 (d) (i), 607.04
label | e937d999-b1f3-52d5-bb9e-067a32c67af3 |  | note | – – – – – – – – – – – – – – – – –
label | 4997cf07-aee7-54f8-968c-892665635212 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 898f8009-0403-565e-8ca6-8444d2fd0bb9 |  | note | ○ The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
label | eb25a466-1e4a-5c09-8296-dfca6fb34bb4 |  | note | ○ The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
label | 85e8b27b-040e-56b6-8b4c-519c20ee1d7a |  | note | ○ Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
label | 9e1d5c24-5cf8-54c4-8734-38426d72da6c |  | note | ○ Concrete shall not be dropped freely from a height exceeding two metres
label | 670d0627-dcd1-5901-9d38-20f53c8ffe98 |  | note | Record: Required information on the Concrete Pour Record.
label | 7744503c-a0b2-5291-a263-0358dd4d0452 |  | note | Attach: Concrete Pour Record
label | 0e01ed58-de64-5079-b6c4-e669f4984f5a |  | note | Attach: Concrete Dockets
label | 7abf77d8-ae91-591b-9d91-c9563353b184 |  | note | – – – – – – – – – – – – – – – – –
label | a8ddd601-10b4-5e03-8930-bc363af5f085 |  | note | METHOD: Visual
label | 53c10c88-dd04-5097-8a81-f74955a76599 |  | note | – – – – – – – – – – – – – – – – –
label | 09f5c2e3-eb34-5ccb-bbaf-2333e127c394 |  | note | FREQUENCY: Each load
label | 4e3d870d-0b2f-5ed3-8b39-6dd9ba167ed2 |  | note | – – – – – – – – – – – – – – – – –
label | 4342c1f0-02c0-5715-b503-4bfabb32d49f |  | note | CATEGORY: SP
label | 7bdc4771-f26d-569b-90cc-b8165e24a9a4 |  | note | – – – – – – – – – – – – – – – – –
label | 3592eed4-3302-58ac-bc33-06cc9b83c45c |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
date | 02946fac-f1d3-578d-9c79-d67446ec4d4a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Reinforcement - Placement
label | ce0991c5-0a13-5d92-95ca-195a23c75154 |  | note | REFERENCE: IFC Drawings 607.04
label | 00190cb7-0a0c-59a6-b53b-d097004f58b8 |  | note | – – – – – – – – – – – – – – – – –
label | ccc2c1e2-d28e-5939-a435-ec3ea83daf2d |  | note | ACCEPTANCE CRITERIA: The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
label | 18df4be8-bbc1-5f0d-9e38-f6ae8771192d |  | note | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
label | 75d2d33e-da21-5de2-a0b6-fa19c8ec8368 |  | note | ○ If the cage cannot be positioned into its final level, the pile shall be rejected.
label | 8f29b8c7-7f7e-56d6-9de5-80fa7912fc4d |  | note | – – – – – – – – – – – – – – – – –
label | c0befef7-6255-5147-b38d-cf35b1d29f6d |  | note | METHOD: Measure, Visual
label | 91eab24d-cf54-517a-9f6f-6875e4df196e |  | note | – – – – – – – – – – – – – – – – –
label | 9a5e0784-501b-58a9-8996-6b7c17295266 |  | note | FREQUENCY: Each pile
label | 684ce3a6-dcc3-52c4-a735-b357586a4e03 |  | note | – – – – – – – – – – – – – – – – –
label | 1047a014-24ec-520a-b124-1af0c6f34096 |  | note | CATEGORY: IP
label | f32ab5a1-d42a-59ae-b98f-3a105ff1a55f |  | note | – – – – – – – – – – – – – – – – –
label | 437ee4ef-b999-56de-819b-0f6ea5baa849 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | e08b014a-0c31-5bef-9bae-2cd63c8c5dfe |  | note | – – – – – – – – – – – – – – – – –
label | a115dfc8-d804-5457-a76e-d0f2087daf03 |  | note | VERIFYING DOCUMENTS: This ITP
date | 126dff5e-b0b4-523c-a0d6-9cfaf502da77 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Cast-in Items
label | 3c2c83f6-59c0-526b-958d-327a27e7ca5f |  | note | REFERENCE: IFC Drawings 610.46 (a) Table 610.462 (November 2018)
label | 1fd6a4f7-5a4f-56be-8c74-ca4f5d5a5a9a |  | note | ○ 610.47 (a) Table 610.472 (March/June 2019)
label | c2ac5438-cf98-5fb4-bf12-099f42937442 |  | note | ○ AS3810.1 Table 3.3.6.2
label | cc9b041e-8bc7-5f41-bf7d-e0d51c37dc61 |  | note | – – – – – – – – – – – – – – – – –
label | 8d88710e-467d-53d4-ac96-50487bbf7154 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
label | f0771329-3e57-57b7-95c8-f480267ea620 |  | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 44c4a07b-63e1-5c9e-b23d-26ba54ba16b1 |  | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 3cf8b8bf-bdee-598c-bd4a-cf963b0941d2 |  | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 436738de-4698-565c-9fd9-3dbff70dcea7 |  | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | f5c8d27e-e6a9-57e6-bb39-84112e3b5ac0 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | bf197ad8-db8c-5859-8db0-c44599022e4d |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 79572661-e04f-561f-9f43-432238085da3 |  | note | iii. Ducts and conduit location = ±12mm
label | 51718b28-3504-5559-946a-a9690c8e4050 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | d6be6812-4bc6-54a0-a12a-85358fc349e1 |  | note | – – – – – – – – – – – – – – – – –
label | 540f38bf-0cff-52b2-836a-bfc3302671b7 |  | note | METHOD: Measure, Visual
label | 6b7eaf0b-711f-5e4b-a255-bd6072e46aed |  | note | – – – – – – – – – – – – – – – – –
label | 683dd1be-521a-5cda-be3f-7171bf7e8e78 |  | note | FREQUENCY: Where applicable, each pile
label | dea35585-b472-5680-aeb3-ecbbfcd8074e |  | note | – – – – – – – – – – – – – – – – –
label | 5aa0bdb0-398d-5677-b045-f75639d5ae22 |  | note | CATEGORY: IP
label | 435c6e37-cee7-58cd-8947-fe6c7049a62a |  | note | – – – – – – – – – – – – – – – – –
label | da010cf0-96ea-5f56-a499-f09bf4ce8de4 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 9a2d4287-4483-503d-82c0-05c05fde6027 |  | note | – – – – – – – – – – – – – – – – –
label | 6cd847fc-5829-5e44-bdd1-62e49a37deed |  | note | VERIFYING DOCUMENTS: This ITP
date | e64249c7-058f-5017-9cf3-40962fc29968 |  | date | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | 7bef164d-ae2c-52a8-a450-1975892f6034 |  | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 607.04
label | f02a7fa5-809d-5e61-a112-06e0852936b4 |  | note | – – – – – – – – – – – – – – – – –
label | f9205aae-9e43-5266-815a-112b2ed5ae01 |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | 5b30e2da-9ebb-5bb7-bade-4296dae3596d |  | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 817fe356-09fb-57b8-906b-3aa32c63f1bf |  | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
label | 01c2a79b-2e7b-5b47-8948-3dfe9e789ffd |  | note | – – – – – – – – – – – – – – – – –
label | 3db81e58-01a0-5d24-b189-0bd81669f348 |  | note | METHOD: Measure, Visual
label | 605d81ed-2cea-575f-8bca-0f5912f3de0c |  | note | – – – – – – – – – – – – – – – – –
label | 5cff535d-afa9-5d85-bdfb-0eeb79c1ee2c |  | note | FREQUENCY: Where applicable, each pile
label | cb317560-1340-5e7f-befd-be021f1c42f8 |  | note | – – – – – – – – – – – – – – – – –
label | 1f6a7455-dfb8-5216-8a92-a2e8209c1f75 |  | note | CATEGORY: IP
label | 0359b341-c601-5b14-8fcb-bda69fbffd5d |  | note | – – – – – – – – – – – – – – – – –
label | fbbfed90-f65e-565b-bf17-3612acc9b6c8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 26bf46fb-07f5-58b4-9a9f-c085ab1f9e21 |  | note | – – – – – – – – – – – – – – – – –
label | 8075161e-b72e-54af-8af7-105380acd7e5 |  | note | VERIFYING DOCUMENTS: This ITP
date | a7af3056-0950-516c-a842-8e1c38e37cc8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 9d39fd02-4ce9-5030-b1e3-37d86a0062b1 |  | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
label | f84c1f03-2de4-5b40-a2be-395cb5adcc73 |  | note | – – – – – – – – – – – – – – – – –
label | c005c0f0-2a0e-5690-b970-072be1196d57 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 562d5435-97d8-55de-aff1-04b3f0aaffcf |  | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | d2e5098f-66e8-5ce8-8f69-a54e053537d4 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 75d2af20-8ad1-5831-918a-decbffd2db8b |  | note | Attach: Compressive Strength Test Results
label | 04e96597-eaf3-5d6c-9894-3e62b417553d |  | note | – – – – – – – – – – – – – – – – –
label | f9bca2ad-3692-5231-b577-7b504c1d0b1e |  | note | METHOD: Document Review
label | fcaa88e1-2538-552c-9df7-4e1a213795c5 |  | note | – – – – – – – – – – – – – – – – –
label | 809383ad-a030-56a1-af48-3bb593563136 |  | note | FREQUENCY: Each cylinder
label | 9c891015-39a0-5ad5-be4f-b1f8610bbee0 |  | note | – – – – – – – – – – – – – – – – –
label | 2a60605a-484b-5f41-b935-03213d203ee5 |  | note | CATEGORY: IP
label | 2a5253aa-311e-58d9-bced-5f6b0092aae1 |  | note | – – – – – – – – – – – – – – – – –
label | 536e328d-d62b-5618-9d28-697c107c0074 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 674ce256-2596-5a15-9f2d-66bc22a4fb94 |  | note | – – – – – – – – – – – – – – – – –
label | 15f64e95-e718-5866-9570-39856bdefbed |  | note | VERIFYING DOCUMENTS: This ITP
date | 702beb48-3fa1-5036-b8a7-694ba4e5aa9a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 00864ccf-c2e7-549a-9070-7d3ec5d62cc0 |  | note | REFERENCE: 607.07 AS2159 Clause 8.8
label | 2a6d7b7e-f0fa-5503-a58d-b02db6b1840e |  | note | – – – – – – – – – – – – – – – – –
label | 450bc72a-1aa1-5afd-a47d-0cccbd4aeb61 |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | adcb6431-ded1-5d5c-bafd-8a0ddf9b9db5 |  | note | ○ Cross-sectional area = ≥90%
label | 7ec9b674-f4ab-5a05-a5b8-70936e1cf458 |  | note | Attach: Pile Integrity Test Report
label | b4d80fdc-990c-5d90-a291-86657f9cb086 |  | note | – – – – – – – – – – – – – – – – –
label | 2e2d9e09-ac8c-57c5-a67f-de3dadc516d7 |  | note | METHOD: Document Review
label | 81f187cb-fac3-5a26-b2d9-ae45fcde2ec6 |  | note | – – – – – – – – – – – – – – – – –
label | 92adc1e3-4234-5db4-88c5-696bb3c03e52 |  | note | FREQUENCY: Each pile
label | a1bb3602-fd55-52a8-9e06-e802936d31f8 |  | note | – – – – – – – – – – – – – – – – –
label | 85743e41-d18c-5136-a007-415402d3c804 |  | note | CATEGORY: IP
label | 153eeceb-31a2-5174-a085-9497fa59fa04 |  | note | – – – – – – – – – – – – – – – – –
label | ae9f86f8-2d9b-5738-a234-c094a7397a26 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 4ab01659-9478-561d-9ff0-d50e2c1fd4fa |  | note | – – – – – – – – – – – – – – – – –
label | 94ca1e02-3e64-5d78-b672-423957c5390a |  | note | VERIFYING DOCUMENTS: This ITP
date | 133c7689-a2ea-5b50-9f71-ef45888ed198 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Dynamic Pile Testing
label | d3164511-61e9-5ec3-b8ba-b0c361e47b5c |  | note | REFERENCE: 607.07 (b) AS2159 Clause 8.7
label | 3f0a954b-937c-5c3a-b70d-e1f1dd54b7d0 |  | note | – – – – – – – – – – – – – – – – –
label | f14a479a-f0cb-524c-b9dc-18f9e04595f0 |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | ffd457e9-b484-557a-b0fb-ec4a976d801c |  | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
label | 2be4bac9-b885-5a19-a0d3-4dde2aef5fbd |  | note | Attach: Dynamic Pile Test Report
label | 2f30e772-6a75-5017-9c29-ecfe64d7a57d |  | note | – – – – – – – – – – – – – – – – –
label | 54aeccb8-890a-5c24-ad56-df4671745119 |  | note | METHOD: Document Review
label | 658f8039-ce16-5b03-9b70-39ff428082d6 |  | note | – – – – – – – – – – – – – – – – –
label | 87120cf2-08b3-5a19-b82e-2c72da7acec0 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | caa3c493-22ff-504d-894e-510c444eb0c9 |  | note | – – – – – – – – – – – – – – – – –
label | 871fdcc6-fe67-5a45-9ba2-9d579c91ab88 |  | note | CATEGORY: IP
label | 0a706749-7b70-5906-a0d3-1bbfb0cb1819 |  | note | – – – – – – – – – – – – – – – – –
label | e14dabb8-89c8-5e13-9576-6ce6c491c892 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 0c6f4e71-2bce-51e6-b4e4-c591e5accaf3 |  | note | – – – – – – – – – – – – – – – – –
label | f38b6867-345f-52fc-8653-47ffb6b6c568 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3b2beda6-c96a-5c42-9a8d-e2cac5a28756 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 As-built Survey
label | c281510d-156a-51ca-8472-2fa6f48bdcdf |  | note | REFERENCE: IFC Drawings 607.06 (a & b) AS2159 Clause 7.2.2
label | 3bd64545-9446-5526-8816-dca9bb04e8fb |  | note | – – – – – – – – – – – – – – – – –
label | 2fd3fdd2-4271-584a-bda6-051c9408c122 |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 1dab2f0a-1665-5ce4-8473-88abd27a7be5 |  | note | i. Centre of pile head plan location = ±75mm
label | da5d8ec4-9376-5cc3-9407-bc34928aa3c6 |  | note | ii. Variance from vertical or rake = 1:50
label | 521ebe53-c830-5157-9929-2319a93e56c8 |  | note | iii. Irregularities in straightness = 1:100
label | 6f60fece-aaf0-5d31-8027-074d482e3130 |  | note | iv. RL = ±25mm
label | 5787ac3d-cbe8-5322-999f-2f813aa50804 |  | note | Attach: Survey As-builts / Survey Report
label | 83c76d28-3b69-5a72-a849-a63f4abc9ae2 |  | note | – – – – – – – – – – – – – – – – –
label | fa5dd911-cfa3-583d-a396-6cc61d7fb344 |  | note | METHOD: Document Review
label | 4ee4401f-6495-583e-b437-0422317cdb92 |  | note | – – – – – – – – – – – – – – – – –
label | b1e72821-4a70-5e7e-9107-4813674a239d |  | note | FREQUENCY: Each pile
label | 7479e714-053c-53d5-aec5-4a5c397c4c72 |  | note | – – – – – – – – – – – – – – – – –
label | 423180c8-be90-576d-a392-75f63db5a613 |  | note | CATEGORY: IP
label | c24047d4-86af-5723-a73d-16611789e6d4 |  | note | – – – – – – – – – – – – – – – – –
label | f69743a7-f5e8-52cc-87af-6564201dc56b |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 4c752cba-4c6b-51c9-a757-6cc3624be485 |  | note | – – – – – – – – – – – – – – – – –
label | da537542-7966-5e7e-b41f-cc9073ca8ec9 |  | note | VERIFYING DOCUMENTS: This ITP
date | 3a13f2cf-e496-59c5-823c-a00fea1e2153 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | 285d42de-6e77-5ef4-bade-ffd58e6f0853 |  | note | REFERENCE: MRPA Quality Management Plan
label | 8da411c2-cd18-596a-8e4e-cc0a1ab80b07 |  | note | – – – – – – – – – – – – – – – – –
label | ec613088-7a1e-505a-8ecc-fa70bfe0bdc4 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1813bfaf-cd76-5917-a6dc-ba56e0ff075b |  | note | – – – – – – – – – – – – – – – – –
label | 35ba151b-82b1-5a88-ac5b-26601cf3e8ef |  | note | METHOD: Document Review
label | 18220dbb-0d0e-59df-9e52-6f99c30882f6 |  | note | – – – – – – – – – – – – – – – – –
label | 89a38244-6f50-57f0-ab49-79080c4cfc1b |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | f8b4a8c5-2110-5357-8f7d-6b43669fcff4 |  | note | – – – – – – – – – – – – – – – – –
label | f87fc22e-aa4b-5582-a3b2-c9a4733300a1 |  | note | CATEGORY: HP*
label | bbb8baf0-c02c-5b1b-835f-36c3c989d792 |  | note | – – – – – – – – – – – – – – – – –
label | ca721224-81c7-5244-8c0e-2704fd3b053d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4aa76577-c2bf-5d24-af70-311964defd83 |  | note | – – – – – – – – – – – – – – – – –
label | 8fdb0309-bc25-565a-af81-8d7bec21f06c |  | note | VERIFYING DOCUMENTS: This ITP
date | ea549437-e0d5-5974-a552-041cf88789be |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | ade42c8e-cc3e-52cc-9d3b-e95f1725a8fb |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b71565bd-6a4d-522d-ae58-f0a2c6755796 |  | textbox | Name:
text | 38993dc6-6259-5e1b-bd29-18691443d425 |  | textbox | Position:
date | 38459256-5491-5501-b890-cb0b4417df56 |  | date | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-053-STR-SSB-Bored Piling |  |  |  |  | Yes | ITP-053-STR-SSB-Bored Piling Rev 0 | e03702b7-ddba-496a-9339-005e25b3359b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 3e779f93-32eb-5df1-b569-0f4831f664d5 |  | note | Document Title: ITP-053-STR-Bored Piling
label | 926b15c6-16aa-5b9f-a782-48a7b5b905eb |  | note | ITP Description: Bored Piling
label | 246c3cdd-bb27-51dd-9632-64a715de6bc3 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 62c3eb0e-6fa8-5458-970a-85bfd4e240ef |  | note | Discipline (e.g. CIV/STR/RAIL): 053-STR
label | b2dc183a-025e-5a17-a1e0-d00df2ecde5f |  | note | Revision Number: 0
label | df936f2f-e7dc-5a9c-960c-afa4089f4cef |  | note | Revision Date: 11/10/2022
label | e633e78a-1d17-559f-bc6d-2d62a86916bc |  | note | ITP approved for use by: Victor Mira
label | 6e168bc7-9e17-560c-98b4-dd88846e4413 |  | note | 1.1 Non Dependent
label | 34bbfe00-602f-55d9-af5d-35fbf67b2b2c |  | note | Reference: VicRoads Section 606 July 2017
label | f16c8176-5569-50e1-a510-ec23258c0fa1 |  | note | 1.2 Non Dependent
label | 36c9023a-e270-533d-80c1-a7d5f1eebced |  | note | Reference: VicRoads Section 610 Feb 2020
label | 41955c0a-9961-5acd-a606-c92c9cd23c4b |  | note | 1.3 Non Dependent
label | 8d765d58-e0e9-5679-a32b-870ee1bfcea2 |  | note | Reference: VicRoads Section 611 November 2018
label | 8d3a2ec4-c31b-5acd-a538-6299d33894b0 |  | note | 1.4 Non Dependent
label | 7530dd1c-4b4e-5966-a9ef-12a7561e3b44 |  | note | Reference: AS2159-2009
label | c95fbb58-9376-5bce-9661-92b600315b00 |  | note | 1.5 Non Dependent
label | 51a73135-0f58-546b-9b8c-3a688fe88950 |  | note | Reference: AS3810.1 2018
label | 1ba23957-c205-5d23-b529-4c5cabd36ffb |  | note | 1.6 Non Dependent
label | a5934898-51d0-5304-b82e-c943773d48f8 |  | note | Reference: AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 941a16cc-2c20-5675-9cd1-6c2b5ea0c3db |  | note | REFERENCE: 610.07 Table 610.071
label | eb6ebe6e-360f-528a-ab87-391658604bad |  | note | – – – – – – – – – – – – – – – – –
label | fe177f23-b430-5866-af71-091a459e816b |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 2b1675e8-9f6b-5529-aeca-172c298a1d62 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 270b3928-c341-5a17-8fe6-280e6b59a19b |  | textbox | Enter: Teambinder Material Approval number
label | 1540c9f4-056f-5a70-9803-cb23cfeddff0 |  | note | – – – – – – – – – – – – – – – – –
label | 8a80406a-b036-5279-8a00-8c2c1de0c7f9 |  | note | METHOD: Document Review
label | fb963b6b-1f76-50db-8b50-45b8da7faefc |  | note | – – – – – – – – – – – – – – – – –
label | 0cc9a842-e533-5e07-8332-34854cc086ee |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 6236d37b-62c2-5d2b-bb98-0bbb50691d94 |  | note | – – – – – – – – – – – – – – – – –
label | 74900eda-3024-56ff-9785-9afcfc542cba |  | note | CATEGORY: HP
label | 53273832-94bd-5ddc-9bb2-b254d5194dab |  | note | – – – – – – – – – – – – – – – – –
label | 5abffe1a-306d-50f0-8caf-f66e6fb3e6fd |  | note | RESPONSIBILITY: Nominated Authority
label | 7c6156c7-b0cf-5de6-98bc-692b081b2a51 |  | note | – – – – – – – – – – – – – – – – –
label | f1d52cf6-2e84-51dc-8c07-2e728058842d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ac45fbf5-53f5-5002-8ec4-e4c660fd91b4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 2a0e4ed0-55f7-5ab1-972d-a4e2d82574c3 |  | note | REFERENCE: 611.05 (a)
label | c46fb620-dd8f-5fc4-a25f-811c5c7a143d |  | note | – – – – – – – – – – – – – – – – –
label | c346f5a2-391e-55a9-bd30-1d45278891ad |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | e6b0fa22-9de5-5920-b86e-d679017bc688 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | ec099a58-c8e8-5dac-a326-085c754fd691 |  | textbox | Enter: Teambinder Material Approval number
label | f8d90997-0f27-5b3e-b6ec-75963d24cebb |  | note | – – – – – – – – – – – – – – – – –
label | e3fc1327-8d16-51a5-8d85-cea7199c12b1 |  | note | METHOD: Document Review
label | 69f11c12-bb4d-580b-af24-a884c5356680 |  | note | – – – – – – – – – – – – – – – – –
label | b98fc91c-cb9c-5e7b-b9c0-bc948d370f15 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | f0175d6c-050c-5abb-a8bd-7913c57fe6c7 |  | note | – – – – – – – – – – – – – – – – –
label | 4dce3071-58dc-598f-a46f-5dc19df80a64 |  | note | CATEGORY: HP
label | 3515bc0f-d6b2-542f-9845-e124609fdb20 |  | note | – – – – – – – – – – – – – – – – –
label | e5e42af5-19cb-5c06-895d-69bc3f0f0cba |  | note | RESPONSIBILITY: Nominated Authority
label | 55f1ec4c-b392-53bd-b6ad-c55c133e3eab |  | note | – – – – – – – – – – – – – – – – –
label | 10dd8e46-15b7-5b78-908c-20ed53abd465 |  | note | VERIFYING DOCUMENTS: This ITP
text | a5ce4ff8-bec6-5617-9b67-b39238395bb7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
label | cecbdc14-156a-564e-a126-e241ce1abd4f |  | note | REFERENCE: 610.26 (a)
label | b6deab1b-51c3-5cde-8924-7d006a3dad18 |  | note | – – – – – – – – – – – – – – – – –
label | 8afe296d-ef4c-5c15-b1e8-e8e097c9d419 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | 653a0315-69e5-5ef5-a6e4-877150236b8d |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 85770361-1a80-5e82-aa56-b4fe1383107a |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 5a1bddc7-bfcb-5609-b7c6-19b357b20f63 |  | textbox | Enter: Teambinder Material Approval number
label | 68047fbd-3706-50ad-b41d-ee570452626c |  | note | – – – – – – – – – – – – – – – – –
label | d218b103-1fe1-5f02-beb6-944685d9473d |  | note | METHOD: Document Review
label | 1a4519e2-04ed-5aa7-9980-98f08fdd86c2 |  | note | – – – – – – – – – – – – – – – – –
label | 25f51cd2-b2bb-59b7-8461-d88aee9c1fe8 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 79176b08-8de4-5572-b3e3-d4f7f3867dd6 |  | note | – – – – – – – – – – – – – – – – –
label | 53ccb156-3b1a-57ed-ae90-ac316e7d076d |  | note | CATEGORY: HP
label | 9ed3d253-f53c-5863-b83e-b42ddb0f03df |  | note | – – – – – – – – – – – – – – – – –
label | cc3c4db3-2c18-5301-b840-85984bc9e97d |  | note | RESPONSIBILITY: Nominated Authority
label | e6547f30-7265-55a8-8e55-33121e36d6d0 |  | note | – – – – – – – – – – – – – – – – –
label | 986b7eb8-275f-5555-96aa-1be3b57b0e0b |  | note | VERIFYING DOCUMENTS: This ITP
text | cbcabe1e-c48f-5487-9fe7-10bddb067556 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | 872bdc04-7e18-5b26-9e86-75a27cfc23a0 |  | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
label | 435f6fda-2095-5c98-935f-604e3ec66c7d |  | note | – – – – – – – – – – – – – – – – –
label | 872a1ef1-e5d5-5a8f-92f7-f4c96e5ec457 |  | note | METHOD: Document Review
label | 649c27ee-8b50-5220-b7ae-1a8baa4639c9 |  | note | – – – – – – – – – – – – – – – – –
label | 42094b59-ea9b-5638-b522-5c64f2180aee |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | 8a7bee26-0442-5512-9c4d-86c07aa5afa5 |  | note | – – – – – – – – – – – – – – – – –
label | d0ea6ac6-e3e0-5984-9b55-4e7808069c42 |  | note | CATEGORY: HP
label | 2c38b223-e49d-5d38-96a7-97ad35424700 |  | note | – – – – – – – – – – – – – – – – –
label | f8b62633-fae8-5887-8b12-99574f148d64 |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | 3a5ad411-682c-5939-abce-fbc63c85fa9a |  | note | – – – – – – – – – – – – – – – – –
label | 2c32a45f-a95b-5a97-85ea-02ceacb783dc |  | note | VERIFYING DOCUMENTS: This ITP
text | 2d6b02d9-0807-5d7e-a870-0538fc79e877 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Piling Operations Work Procedure
label | c22ecb84-e503-5c28-a513-7a327cae13d0 |  | note | REFERENCE: 606.03 (a)
label | 0f3e6c41-60bf-596a-ad95-131c13c5b37b |  | note | – – – – – – – – – – – – – – – – –
label | 8bb9b383-e8ca-5bcc-b919-cc60bfce44c2 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 2760059d-2513-5c4a-b1a6-efdbcf7761f6 |  | textbox | Enter: Teambinder Approval number
label | 2fed6c2c-5e85-5809-a49d-feda9cf50054 |  | note | – – – – – – – – – – – – – – – – –
label | 4950638a-a6c4-5e8a-adae-f6233d696718 |  | note | METHOD: Document Review
label | b529d8aa-ab1c-509c-abe5-728b65424e4c |  | note | – – – – – – – – – – – – – – – – –
label | 235ed496-6711-58d4-8776-b1e6a806bf28 |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 41d1e063-6dfc-50e4-9ef5-362cf70b7d24 |  | note | – – – – – – – – – – – – – – – – –
label | 40b62bcd-918c-5a33-a513-faac791da619 |  | note | CATEGORY: HP
label | a0ff54a5-961b-5378-9465-ba7aeb6f01f6 |  | note | – – – – – – – – – – – – – – – – –
label | 1c6a8d2d-7418-50af-bd1d-da5461450989 |  | note | RESPONSIBILITY: Nominated Authority
label | 787485fa-edf1-5789-934a-3944f7d53bb3 |  | note | – – – – – – – – – – – – – – – – –
label | 34656c9f-8bb7-5e40-9a8d-62902b0a397c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 231fa042-d1cc-5075-b450-a94c1f61f7be |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Temporary Steel Casings
label | 2ff5c3fb-5189-590c-b5f8-5ed1b25adb70 |  | note | REFERENCE: 606.03 (b)
label | c4832d7e-d7ce-5d43-ac5b-ab4f207fbbf4 |  | note | – – – – – – – – – – – – – – – – –
label | 2118a8f6-684e-5e74-bfb7-741e2dccb146 |  | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | b43144bd-d661-5f36-9848-6321d9621695 |  | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 3d234586-1f4f-5ee1-8436-876961b300aa |  | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | 4ca75c62-1649-5f77-80cf-24be51a66d4c |  | textbox | Enter: Teambinder Approval number
label | 0092f992-dc99-5ea7-9fdb-534a1531152d |  | note | – – – – – – – – – – – – – – – – –
label | 76a53576-5611-5f1f-9152-16bbbed0ac3e |  | note | METHOD: Document Review
label | 89c1455f-dbe6-5caf-b115-32536de61b48 |  | note | – – – – – – – – – – – – – – – – –
label | 1ff73abd-0fa3-51d3-a52c-ff8afa719d32 |  | note | FREQUENCY: Where applicable, once, prior to use
label | 99d30d8e-594d-59bb-8571-645f376774d8 |  | note | – – – – – – – – – – – – – – – – –
label | 36a7d277-6630-5560-9d6d-a5c96eef8cc8 |  | note | CATEGORY: HP
label | 3a86384e-aa95-5663-8b33-8f174b445293 |  | note | – – – – – – – – – – – – – – – – –
label | cac74c9f-74c2-5362-b71a-bc5153b82f76 |  | note | RESPONSIBILITY: Nominated Authority
label | e88d6fd0-4583-5a03-bbd6-ca666be43ac1 |  | note | – – – – – – – – – – – – – – – – –
label | 1ebcbab7-6060-57c2-b911-e5549f72454e |  | note | VERIFYING DOCUMENTS: This ITP
text | 7c779421-b18b-5574-bddf-1d5fae86b4dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | 3add7cec-31ef-5b4c-9ed9-ca56a7e64828 |  | note | REFERENCE: 606.06 (a)
label | 5e44ed80-5997-51f4-9fb6-252d30dcc7c7 |  | note | – – – – – – – – – – – – – – – – –
label | e75bf48a-ade5-579a-b8aa-cc5a57f655ff |  | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | cfb1a414-1e8c-582e-98d9-b7e54273eddc |  | textbox | Enter: Teambinder Approval number
label | ec55a1ec-4d29-5e66-808f-e385b408532c |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 474aff2d-781b-5af3-bfa4-b3a73b827a49 |  | note | – – – – – – – – – – – – – – – – –
label | 7f3884ee-ebde-5792-9675-6de1b4bb6fc0 |  | note | METHOD: Document Review
label | 6921638d-083f-5dc5-9f75-633aea20aa46 |  | note | – – – – – – – – – – – – – – – – –
label | ad8ef4bf-650c-5c18-a557-166d005fe30b |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | f722ca60-262b-55e3-9834-19dcd2888941 |  | note | – – – – – – – – – – – – – – – – –
label | 98e8e834-3aeb-5833-9db9-9e51159e8854 |  | note | CATEGORY: HP
label | 0b06d24d-125a-5546-b853-15b0b7ad8885 |  | note | – – – – – – – – – – – – – – – – –
label | f2d13015-311c-5b2f-869f-a2b48407c730 |  | note | RESPONSIBILITY: Nominated Authority
label | 8439a7fa-a23b-5d80-8bc1-eeef2cb94247 |  | note | – – – – – – – – – – – – – – – – –
label | 28b73fef-624a-52c0-b20b-3f8063ace0b2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 104682bd-891e-5000-a7aa-4b833ab3710b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
label | 8d07e610-041f-575d-8990-56c974b7f07a |  | note | REFERENCE: 606.03 (c)
label | d94e036b-ff4f-595b-88b2-a561e69fcdd2 |  | note | – – – – – – – – – – – – – – – – –
label | 2a842f17-519f-55ad-a810-93f31b58e407 |  | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 09f1670b-31ea-5933-89af-95e7a56bc201 |  | textbox | Enter: Teambinder Approval number
label | 53df5c46-16de-5027-812f-b2d61e34d349 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | cecbd039-797d-5f4e-950f-24137eb21ebc |  | note | – – – – – – – – – – – – – – – – –
label | dec48c30-86c2-5eae-b9ed-3274ad98a855 |  | note | METHOD: Document Review
label | c6498d35-2cc7-5856-8dd2-a7eac9ca963d |  | note | – – – – – – – – – – – – – – – – –
label | 4a9fd476-9417-5376-9428-8a2f3f0eb298 |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | 8481ac1a-6061-5b45-846a-3058cd85777f |  | note | – – – – – – – – – – – – – – – – –
label | db3a796f-822c-500e-91ac-3963d71cf3a3 |  | note | CATEGORY: HP
label | 6d4cae52-18a5-56fe-8a11-32dab24e598a |  | note | – – – – – – – – – – – – – – – – –
label | f66ecd06-33cb-58a4-811c-a99d80d579d4 |  | note | RESPONSIBILITY: Nominated Authority
label | c32dd49c-6f0a-52b3-8839-7c51be75053e |  | note | – – – – – – – – – – – – – – – – –
label | 32e409c5-1af4-55a1-bca9-e0239345f3fe |  | note | VERIFYING DOCUMENTS: This ITP
text | 4167edba-29e5-5de9-a4a0-4868fefdac08 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Dynamic Pile Testing Procedure
label | 3bb4982c-602e-52ce-a88b-97a8d564aaef |  | note | REFERENCE: 606.07 (c)
label | 123c5eed-fd7c-5336-8cbe-72922422653a |  | note | – – – – – – – – – – – – – – – – –
label | 57881b7c-677b-5607-b308-ad5a6057ae7e |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 407fc805-c775-5191-8797-82601d9283d9 |  | textbox | Enter: Teambinder Approval number
label | 899ebcb8-5cdf-5834-af40-45d69c9d764e |  | note | – – – – – – – – – – – – – – – – –
label | 359a32c7-5e55-5fb7-9d0c-fc22409588a1 |  | note | METHOD: Document Review
label | e9700d91-47b1-52e7-8cbe-2842f92baec6 |  | note | – – – – – – – – – – – – – – – – –
label | 34626023-76ab-5c9c-866d-e39395603733 |  | note | FREQUENCY: Once, prior to testing
label | 8f552ce8-d801-5106-a624-d6b6ededb984 |  | note | – – – – – – – – – – – – – – – – –
label | 42aa0cf7-ff09-5165-a0ed-eeedcd062e77 |  | note | CATEGORY: HP
label | 084a2391-f420-53b5-b048-5912fe69cee4 |  | note | – – – – – – – – – – – – – – – – –
label | e67936dc-6163-5f4d-83bc-671b46aaec56 |  | note | RESPONSIBILITY: Nominated Authority
label | 6b234cf5-d5a5-5fe6-acc7-8b0adad81d74 |  | note | – – – – – – – – – – – – – – – – –
label | 7f5b9ab1-4a57-5ee4-9ae7-92e90361ab09 |  | note | VERIFYING DOCUMENTS: This ITP
text | d8cdc248-cabf-59fd-9f5f-590b65a0ceee |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Pre-qualified Pile Testing Consultant
label | 6efc42f9-e241-5ef6-b14f-5d789e38d53b |  | note | REFERENCE: 606.07
label | 1ed10013-8050-548f-a055-c26a45f01538 |  | note | – – – – – – – – – – – – – – – – –
label | aeede161-5ba7-57cf-b7ca-e5207f5d3e56 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | 4cb61ecc-ee89-5e5f-9cbf-a376b291eda4 |  | note | Details of the consultant to be submitted for review to the Nominated Authority.
text | 87dc1559-080d-5a9e-ab15-c33ea14822f6 |  | textbox | Enter: Teambinder Approval number
label | 25afd119-23ec-52ec-a89f-f91e37ab364d |  | note | – – – – – – – – – – – – – – – – –
label | b0facab6-d8d6-511d-a728-a8943aca7d73 |  | note | METHOD: Document Review
label | 531ef812-0f39-5bd1-9030-f053cdd65b2b |  | note | – – – – – – – – – – – – – – – – –
label | ec8996d5-6d24-5253-a527-b9454c59a85d |  | note | FREQUENCY: Once, two weeks prior to testing
label | baf0c402-2316-519a-b337-f33621a94a41 |  | note | – – – – – – – – – – – – – – – – –
label | ec6d7407-8b92-5e02-b093-6ac7820e1846 |  | note | CATEGORY: HP
label | 0ad84e3e-f78c-5a77-a479-6c6ff9289df3 |  | note | – – – – – – – – – – – – – – – – –
label | 4c1a8182-f38d-5f3b-b081-5ca8efa6df34 |  | note | RESPONSIBILITY: Nominated Authority
label | d615a409-be1f-5695-8a85-9342fc99c8cd |  | note | – – – – – – – – – – – – – – – – –
label | 2af67ebd-aa4e-5c4a-9e9b-63327fcd37ef |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 50f7b956-52ff-5a77-a93a-a374893dcb52 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
label | f86d384a-9893-549b-8847-ec66867c7a95 |  | note | REFERENCE: 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | 7ceb68dd-1f8f-5843-9f1a-66fb243daf4e |  | note | – – – – – – – – – – – – – – – – –
label | 65bffa2e-8ef7-5790-8b9d-71d913b283db |  | note | ACCEPTANCE CRITERIA: Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | 217a172c-321c-5e79-82ce-fe2788519571 |  | textbox | Enter: Teambinder Approval number
label | 808f6cdc-48c9-57c3-80ca-b0f275d1c943 |  | note | – – – – – – – – – – – – – – – – –
label | 287f9101-b01a-569c-a0a7-4703b2e15526 |  | note | METHOD: Document Review
label | b8d40a8d-09d8-5123-8b94-552b180231c2 |  | note | – – – – – – – – – – – – – – – – –
label | 7d296d59-0ecf-5b17-93dc-128d1d97d651 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | d1445881-73ef-50c0-8ff8-76f6d9b52e0e |  | note | – – – – – – – – – – – – – – – – –
label | 51691f4c-fc5e-5054-874e-20605ca4da30 |  | note | CATEGORY: HP
label | daa394fd-fddf-5a81-872c-817bd3fdaf1a |  | note | – – – – – – – – – – – – – – – – –
label | 0745ddc9-2672-5948-9e8f-a81bae671354 |  | note | RESPONSIBILITY: Nominated Authority
label | 5880147f-25e4-5f48-ad84-218797e22930 |  | note | – – – – – – – – – – – – – – – – –
label | 60030d64-b85c-596b-be1f-3ee84bf41772 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3a1b2054-aa52-563f-a95c-5a7e62a2e162 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | f8568de4-33dc-5acf-b4b3-3be955513578 |  | note | REFERENCE: MRPA Quality Management Plan
label | a757bcee-03d8-5aba-ac0e-c75ed79524fa |  | note | – – – – – – – – – – – – – – – – –
label | a35e22a4-f9c6-5b3d-9f60-97c33ca345fa |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 7ad5ec8c-4a18-594c-a607-1ea1c524fefc |  | note | – – – – – – – – – – – – – – – – –
label | 43fb9970-1d9a-5163-9495-ea59bc2cb351 |  | note | METHOD: Document Review
label | 8f298032-d17c-5fa7-a608-9e3579e815a1 |  | note | – – – – – – – – – – – – – – – – –
label | 43f985ab-0e27-58ea-a433-b651ccb1fc77 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | b01b922f-fed3-5da0-8140-ed05637f5178 |  | note | – – – – – – – – – – – – – – – – –
label | ae693699-e51c-5838-8898-a6aa04fd7ee2 |  | note | CATEGORY: HP*
label | 99d3fc18-5419-5ad5-9cb1-204a10be0659 |  | note | – – – – – – – – – – – – – – – – –
label | 8a5e2df6-f933-536c-8f78-37d867aa6ddb |  | note | RESPONSIBILITY: All
label | 6327f7ed-24eb-52df-957f-39c58a2d400f |  | note | – – – – – – – – – – – – – – – – –
label | c56f7766-6c34-5c72-96d9-77b8f03ef125 |  | note | VERIFYING DOCUMENTS: This ITP
text | d0d1b552-7a62-5268-88a9-d2e1da9af9b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | c0050535-ec00-5b1a-aed5-ec72d873fbc4 |  | note | REFERENCE: IFC Drawings 606.08 (a - c)
label | 98e7112a-ed83-5f01-8a4f-139118f71734 |  | note | – – – – – – – – – – – – – – – – –
label | a82dd41d-15a7-57db-a709-acbffbc7ca0f |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 92361831-ee7c-51ef-89f6-78a2b89fc5be |  | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | ac77cde7-fbcc-574a-be9d-600fdf1d07bc |  | note | – – – – – – – – – – – – – – – – –
label | 7bc3350f-c562-51be-b215-a4742d6f88ac |  | note | METHOD: Measure, Visual
label | 6d963c03-a853-5fb1-9a5e-4594d8bc0659 |  | note | – – – – – – – – – – – – – – – – –
label | a50bfb06-25ee-5f60-bc31-1201abe3c9bb |  | note | FREQUENCY: Each pile
label | ec91d7e7-22d1-5f12-bf1e-a358ee1434e8 |  | note | – – – – – – – – – – – – – – – – –
label | 4b49669b-90ca-5d3f-ba64-d8e7b67fba40 |  | note | CATEGORY: IP
label | 685d3381-389d-5f1d-b3b0-fd9e1f28e674 |  | note | – – – – – – – – – – – – – – – – –
label | 2e6f8126-08ef-5d15-9c80-6fea6cc6632d |  | note | RESPONSIBILITY: Surveyor, SE
label | 48a620fe-b633-5939-9038-4e6b01f49411 |  | note | – – – – – – – – – – – – – – – – –
label | d07f1bd7-c951-5bc2-b4f7-d3201dba3e6f |  | note | VERIFYING DOCUMENTS: This ITP
text | 02791c64-ae11-54c0-8e7a-bcfe8fd02b75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | d268d5fb-5097-56c4-b908-f586c498005f |  | note | REFERENCE: 606.04
label | 571e442f-3d6a-5aad-9575-0eae5b115d24 |  | note | – – – – – – – – – – – – – – – – –
label | 4c8b2fd0-68b2-5323-a1ce-2722eca9a224 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not:
label | 7fc0db62-bc25-5343-8a63-c4196ff7f14e |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 4eeb74c7-b16f-550f-a03b-098cef8c1159 |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | 98a09c19-0110-5ddc-91b0-59740ee11559 |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 553b4560-a503-5c91-99a3-a8171cf23a5c |  | note | – – – – – – – – – – – – – – – – –
label | 3d32afa8-5609-5e40-854f-08a023abaf99 |  | note | METHOD: Measure, Visual
label | 7ce2e205-0153-52c6-b00c-2740ec6096b6 |  | note | – – – – – – – – – – – – – – – – –
label | 7d64f9fe-2f17-5bc5-b9c8-ff5ab10b2933 |  | note | FREQUENCY: Each pile
label | f2ddce00-b4f3-5368-b17b-0b45606c6d7f |  | note | – – – – – – – – – – – – – – – – –
label | 86900af8-18fd-5b92-adc6-5383a728e080 |  | note | CATEGORY: HP*
label | 4748d0f8-36ec-5ad3-94d5-66445aa839ad |  | note | – – – – – – – – – – – – – – – – –
label | 6706da26-824e-5eb5-891e-5079423a5068 |  | note | RESPONSIBILITY: SPE/PE
label | 412f6dce-e0f7-5062-874d-84d398e1d5d9 |  | note | – – – – – – – – – – – – – – – – –
label | 454c7326-e444-5ae5-8bad-008dc2b5e428 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3c8612d8-9b44-522c-bdb6-3f80f7e2de50 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | ddfbdc17-e048-52a7-8ffd-d3a0c70b9b9d |  | note | REFERENCE: IFC Drawings 606.03 (a)
label | ad1c4225-4618-52de-86c4-3a826bf30b66 |  | note | – – – – – – – – – – – – – – – – –
label | b252f0a4-383e-5921-b883-f15c6265f7ba |  | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | e0142377-e723-5b22-b058-d79cd5796946 |  | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 3b06e9e2-29d5-558e-b955-097dbb41f202 |  | note | • Excavation clean and de-watered (where applicable) for inspection.
label | 12884335-7fe4-5d76-8ed1-d47f7b888a3a |  | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 41399950-3bc7-5b24-86d2-4f7004ef6144 |  | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
label | 8e563f03-27cd-5300-a279-095b1abec5bd |  | note | – – – – – – – – – – – – – – – – –
label | b8126d90-f1e2-59b1-b626-f825540d3b91 |  | note | METHOD: Measure, Visual
label | 0531cd92-2d3a-59ef-9804-3655ee88db0b |  | note | – – – – – – – – – – – – – – – – –
label | 546861cf-fbf7-56d8-8a2f-346612be24d5 |  | note | FREQUENCY: Each pile
label | df3d3f5e-0e48-58e1-803c-b18ceaa23a98 |  | note | – – – – – – – – – – – – – – – – –
label | 47182788-35d7-5e6b-ac5b-18112a9c4b16 |  | note | CATEGORY: IP
label | 60da6cb7-621c-514a-af1d-2a34fc09471c |  | note | – – – – – – – – – – – – – – – – –
label | 6d719055-9a75-5265-9831-c554fc27761b |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 095e60ad-40c7-53d3-92cd-307198adeecb |  | note | – – – – – – – – – – – – – – – – –
label | 0a41ffdb-01e0-5c4d-9844-c1c14f841796 |  | note | VERIFYING DOCUMENTS: This ITP
text | b08b2cc7-c376-5d95-ad39-a9f4a114f53d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | cf657713-a524-544c-941e-cf911f50f08d |  | note | REFERENCE: IFC Drawings
label | 66fca597-ea68-5b6a-8030-d8834b4b99de |  | note | – – – – – – – – – – – – – – – – –
label | 0ce51d4e-bd03-51dd-bd51-50f15a8899f5 |  | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | b2d09a53-f373-5524-afde-98b49d550c2d |  | note | – – – – – – – – – – – – – – – – –
label | b6a97393-9c16-551d-8ad8-2188622d4f1e |  | note | METHOD: Measure, Visual
label | b52c29ef-0f70-5859-b011-b0f3941a95d2 |  | note | – – – – – – – – – – – – – – – – –
label | 74879c65-1c33-5166-b547-df7d9d31c4c9 |  | note | FREQUENCY: Where applicable, each pile
label | 84a86778-85cd-5671-b8d8-ef4eb57022a3 |  | note | – – – – – – – – – – – – – – – – –
label | a32adf1f-4e37-54c5-92ad-10e4330e8d87 |  | note | CATEGORY: IP
label | 00eaf6f1-bfef-556d-9e37-c13611efa98b |  | note | – – – – – – – – – – – – – – – – –
label | 11972a2e-dcbc-5981-a31c-6eae13ef1b7f |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 0af9fdaa-c7a8-5dd6-8949-58e1813599c6 |  | note | – – – – – – – – – – – – – – – – –
label | e77a1b0e-c539-5152-bf95-8f8df6b34149 |  | note | VERIFYING DOCUMENTS: This ITP
text | 20d840ce-c9f5-5e0e-8ee6-c9bce2a065dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | 6dbee983-e29a-5188-bfb9-abd633b29ccf |  | note | REFERENCE: 606.05
label | 67bfba29-62d1-531b-9535-da02c5a464c6 |  | note | – – – – – – – – – – – – – – – – –
label | 750bf1ad-a350-5b15-992b-c0fe9beec670 |  | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 51971968-23c7-5fbb-8783-883551559693 |  | note | Attach: Geotechnical Field Sheet or Report
label | 6345365a-8694-5b4a-bfd5-6e8c17f17a0d |  | note | – – – – – – – – – – – – – – – – –
label | 05b2f277-c42e-51f5-8fcd-273893fe9381 |  | note | METHOD: Measure, Visual
label | f1f32f37-844a-5bd0-b395-7efd3b4bea37 |  | note | – – – – – – – – – – – – – – – – –
label | 9ba9b66c-0ad9-529b-9c01-279fbf61593c |  | note | FREQUENCY: Each pile
label | 3656e087-8bfa-59cb-8f8b-6feee3fcb66c |  | note | – – – – – – – – – – – – – – – – –
label | 84ee6a5a-ab60-5e3f-b19d-a8dcb87a5faf |  | note | CATEGORY: HP
label | 1b3786f1-402d-5dbc-8e98-f9b93ebcafc7 |  | note | – – – – – – – – – – – – – – – – –
label | 2b2baabd-21be-5b34-bdeb-779b3a854c42 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 0dce1279-ae5c-54d3-940a-7fd81d69f5ca |  | note | – – – – – – – – – – – – – – – – –
label | 63a37005-e686-557b-b164-190fad11197a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 7bb331bc-292a-55e4-9cbc-f3d9aca501f2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement - Placement
label | 0ab0f5a8-aaee-5be3-ba12-560b0ddbd0e2 |  | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
label | dd9c59c3-50e5-5468-bdcd-66a722329938 |  | note | – – – – – – – – – – – – – – – – –
label | 0e9a0b04-b067-5c8d-9f89-8f0adb5e562b |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 141197e7-8f37-51b0-be3c-381d818beccc |  | note | • Projecting reinforcement is the correct length and location.
label | 7fc9d350-14fc-5d49-94d6-4be62d38cf8c |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 99588dff-00b0-5a93-afd1-0f76e1871a7e |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | 3437824c-990b-5b1b-98c2-f4a7a3511d2b |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 3ead3e77-7b50-5769-8e95-42cabfa497e6 |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 28c5157a-052e-5316-bfc6-b9255bd1510b |  | note | – – – – – – – – – – – – – – – – –
label | bd28504f-0ab7-53e3-9711-859f37913666 |  | note | METHOD: Measure, Visual
label | 8e5ee3ab-50da-5e3b-8608-aa2423ba43d0 |  | note | – – – – – – – – – – – – – – – – –
label | 869c9bf7-b589-53c1-9b91-bb85200ab0d4 |  | note | FREQUENCY: Each pile
label | 5c3e44e8-c5a9-5115-8091-c2518317cdfe |  | note | – – – – – – – – – – – – – – – – –
label | b0c1b315-3eeb-5935-ae3b-24acd7cff46f |  | note | CATEGORY: IP
label | cfe1fff1-6274-5fdf-892d-1e2aa1653267 |  | note | – – – – – – – – – – – – – – – – –
label | 13e17386-5a99-5cc8-99ee-19c690c197d2 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 52411d72-955a-581f-b5f7-7f138979e7a9 |  | note | – – – – – – – – – – – – – – – – –
label | a749c53d-fc97-51f6-9494-0ec665766e3a |  | note | VERIFYING DOCUMENTS: This ITP
text | 08d69192-bb1d-5915-b610-4364acf7a9d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | c5779768-0bfb-5af6-a14e-8d2d686004d7 |  | note | REFERENCE: IFC Drawings 610.29 (d) 610.43
label | d7951f6d-7482-5152-9592-f71676c01278 |  | note | – – – – – – – – – – – – – – – – –
label | d2f8bc86-0aba-57bb-8d31-a127f6017adc |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | 0bb10d21-26e0-5a58-abba-8014734a6265 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 244cb006-bf98-500c-9fca-372415297748 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | cba62678-1573-5054-917d-f43be26d9f60 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 3df695e3-7d19-5959-99bf-2e2cbb190815 |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 523b4fec-2261-586e-a8c2-a65123a7c6a2 |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 18e9fb04-050e-5d8a-bba3-99a3c66e3cdb |  | note | – – – – – – – – – – – – – – – – –
label | 2b0e1af0-8ca3-57cd-ad63-c045f45cfb7c |  | note | METHOD: Measure, Visual
label | 5f017c6c-a12e-5146-ab2d-ab04e7c94428 |  | note | – – – – – – – – – – – – – – – – –
label | 61da597f-a19a-50b6-8be2-5c1b21a05dcb |  | note | FREQUENCY: Where applicable, each pile
label | 5fe55377-3845-5b67-b125-53c41c0abf8a |  | note | – – – – – – – – – – – – – – – – –
label | 8b136fc9-97f8-57b3-b295-2b0df59cdf38 |  | note | CATEGORY: IP
label | 7dc54f45-eb91-583e-8c4d-362e61bf0c4b |  | note | – – – – – – – – – – – – – – – – –
label | 9633d664-0703-58fc-805d-c6b474e2e958 |  | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
label | 86e9fd64-bc66-5f06-8aab-4ee29506f0bc |  | note | – – – – – – – – – – – – – – – – –
label | 6f70eb62-3221-5250-8168-530cbb0cb14b |  | note | VERIFYING DOCUMENTS: This ITP
text | 5e0eb8f0-c31b-50c6-b156-34a8c198336c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | fe32844f-4bed-55e0-87cf-e7cb17409e22 |  | note | REFERENCE: IFC Drawings 610.46 (a), Table 610.462 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
label | 4d2c3489-5331-558e-bdc6-1d2bf5e62bc2 |  | note | – – – – – – – – – – – – – – – – –
label | e032a61f-3f57-511f-bb29-a7929637f2c8 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | a4af778c-08cc-5f1b-83a3-38e4feb1c672 |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 8791efca-b106-5985-805b-2298ef735362 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f8ddc543-0771-588b-b901-5ab9d855fc54 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | ced37e0c-99c1-5a73-94e8-c6b75b6bee7c |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 6db3b2bb-f514-5542-9c96-0b9202448e63 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | afd4bd31-e7e2-5c7d-ab56-8275222948d6 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | c2c1d39b-34b2-5513-9ae7-a4fa16b98a92 |  | note | iii. Ducts and conduit location = ±12mm
label | 54a9490c-1b24-5454-905c-2a20e75706a5 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | b05ae382-697f-5352-b3fb-b11a5b9c0bc6 |  | note | – – – – – – – – – – – – – – – – –
label | 0c6f25b3-2cb2-540d-9d97-198707e3809f |  | note | METHOD: Measure, Visual
label | 15668efe-f910-50fb-a36f-5d8c620f564b |  | note | – – – – – – – – – – – – – – – – –
label | e84711d0-10af-57e5-b9c5-cc7eb28e8034 |  | note | FREQUENCY: Where applicable, each pile
label | 477c2d6f-1c9b-583d-9396-ed05174002d9 |  | note | – – – – – – – – – – – – – – – – –
label | 02b2790d-a331-577b-bf95-2b27fe1b614f |  | note | CATEGORY: IP
label | a8b17f3a-8c64-5a9c-bfc5-9919dd1bb724 |  | note | – – – – – – – – – – – – – – – – –
label | 6d7651e8-5b95-5a4e-8ab5-f3a40bce44aa |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 0e737688-2fc5-591f-a941-0c790646661f |  | note | – – – – – – – – – – – – – – – – –
label | 379c9419-b6e3-5ff7-b569-ca53e90eff8f |  | note | VERIFYING DOCUMENTS: This ITP
text | 239bb120-5ea8-570e-877f-cd2bfb59b6e4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | aec9448c-3f49-58c8-bffb-3a4219c400d4 |  | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
label | ed988ccf-811a-560c-be58-60f53ddb3184 |  | note | – – – – – – – – – – – – – – – – –
label | b5810a87-fc5c-557a-87b5-c47d7befa6b3 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 94986449-34b9-5484-8350-1a5883aac0a3 |  | note | • All foreign material has been completely removed from the excavation.
label | 0e650d7d-f573-56c7-97cd-1b1dcf3fbbd0 |  | note | – – – – – – – – – – – – – – – – –
label | a3ac4ca8-db97-514a-a453-9f98481b48b4 |  | note | METHOD: Measure, Visual
label | b0df3c99-abaa-55e0-bf4c-ef61faf87b02 |  | note | – – – – – – – – – – – – – – – – –
label | 21da78f0-9f39-5d3a-aaae-1d5c88466403 |  | note | FREQUENCY: Each pile
label | 3c464046-7cc3-51ea-998e-e5f833c3b05d |  | note | – – – – – – – – – – – – – – – – –
label | 6de6c2e9-0279-5f14-a158-305ee55b4073 |  | note | CATEGORY: HP
label | 309529c8-e0e1-5bb5-9be1-f7f0499627b1 |  | note | – – – – – – – – – – – – – – – – –
label | 352601b7-dbbd-59fd-8d1e-73fd317a72c7 |  | note | RESPONSIBILITY: Nominated Authority
label | f23c90b0-44da-5ad1-9672-6a1dfd515d10 |  | note | – – – – – – – – – – – – – – – – –
label | 01c46415-9c3d-5cf3-8049-5f0298b5f95b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9c6c2fc3-4d35-5f59-8921-75dc4c0ffcef |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | d51e64b2-ef2d-5730-a772-bfec68cffe09 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
label | 319b32b5-1d58-5d7e-b37c-5384f8438cb6 |  | note | – – – – – – – – – – – – – – – – –
label | 7c9dbdc0-4eba-5338-940f-bce9881b2b45 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | d5e7ee18-b6cc-56ab-9975-2ed604898c79 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 8fcb5a9b-cea2-57c0-bd7e-0d4e0c13d791 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 5fff7795-c309-5d25-8e6b-cd3e33510455 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | b0ad208f-d5a3-5ace-b5d3-8de30a760eb7 |  | note | Record: Required information on the Concrete Pour Record.
label | d6a37cc1-7b59-5abd-8566-b292ac639743 |  | note | – – – – – – – – – – – – – – – – –
label | 8324f3d9-174b-5dd6-828c-8238e52aea1b |  | note | METHOD: Measure, Visual
label | c5f60aed-5ffc-500d-aad6-99c1b3982e28 |  | note | – – – – – – – – – – – – – – – – –
label | 0832c559-a854-5126-971a-cc498240a507 |  | note | FREQUENCY: Each pile
label | bd66fdfd-68b4-5271-81df-01d38cdfe3b2 |  | note | – – – – – – – – – – – – – – – – –
label | c7650907-4e7b-59cc-9cbe-6795931a94b9 |  | note | CATEGORY: IP
label | 69469389-66d9-5317-8ce9-9385f4c7ef1a |  | note | – – – – – – – – – – – – – – – – –
label | d9bd4ae7-f39b-53b3-8dae-4e91aee3bd54 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b16389f0-80a9-5f55-968e-52823da89b61 |  | note | – – – – – – – – – – – – – – – – –
label | 6ae4b127-8c1e-54ae-afe6-1c73b1341962 |  | note | VERIFYING DOCUMENTS: This ITP
text | e37f9c59-f83c-58d6-ad3e-af5e32f04eb1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | 0ef40f34-b5ed-5d5d-a23f-178817e3973f |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | 3368c2d4-4171-51f9-b83c-b917c878e801 |  | note | – – – – – – – – – – – – – – – – –
label | 581f63df-edcc-5e79-9824-269bb8b1abb9 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 9478d5f6-8a35-5977-9233-b9a10dc4b386 |  | note | 0m³ to 10m³ = 1 sample
label | a3058852-f2dd-5154-9bc7-aa46886b8f50 |  | note | 10m³ to 25m³ = 2 samples
label | b290fa30-ffbe-5c96-805e-fbf08c88768b |  | note | 25m³ to 50m³ = 3 samples
label | b83379f7-39d9-588d-825c-e3b511bd75d7 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 9c4a0b1d-77d4-50bb-8070-a25450b24bcb |  | note | • For each additional 50m³ and additional sample shall be taken.
label | 657565dd-0505-5d12-88f9-eaa2af1d3708 |  | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | f5f0cb20-92a1-51c2-88d0-9ba4defb3643 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | df01f0cc-2fb3-51ab-85df-628bc60caf88 |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 58e04722-0197-50e5-81c8-e0bd8af2ecab |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 93e87183-bd10-560d-a240-75405d6ecfe9 |  | note | Record: Required information on the Concrete Pour Record.
label | 1a3153f5-2685-5673-bca4-c1b7b23c169b |  | note | – – – – – – – – – – – – – – – – –
label | b75ff32b-f7e5-5f3d-a700-91b68b8f12cc |  | note | METHOD: Test
label | 2a46e046-7c2f-5d7c-acb3-53af6aca59b0 |  | note | – – – – – – – – – – – – – – – – –
label | 09dcf212-2eea-54f8-8bce-867d8284310f |  | note | FREQUENCY: Each pile
label | a5d26ecb-3f95-5764-aca6-1d47880a490d |  | note | – – – – – – – – – – – – – – – – –
label | 7fce780d-c539-5db5-bedb-d40f239c86f2 |  | note | CATEGORY: IP
label | a8155d83-b433-5765-bee0-9581329ec0f1 |  | note | – – – – – – – – – – – – – – – – –
label | 467ee8d8-9706-5da7-9225-922fdd08796a |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | d741dd6f-78c0-5bd6-9be8-1766d93ff6e5 |  | note | – – – – – – – – – – – – – – – – –
label | 39599ccb-2f02-5337-a845-5cdb88f89563 |  | note | VERIFYING DOCUMENTS: This ITP
text | c8b5c515-5071-59a2-953b-1bdfd14dee43 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | 25bbde4a-27e8-5f06-8ffe-c666bdd11432 |  | note | REFERENCE: 610.13 (b)
label | 3a867ef0-afd2-5109-8478-0307137bff8a |  | note | – – – – – – – – – – – – – – – – –
label | cf175af7-9264-558e-94d7-ece78e8eb7fc |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | e77f4ca5-fb45-51a5-910f-3a4a1f09385d |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | c88d8a8f-7267-5280-9d8b-e37fb1da6c35 |  | note | • Passability = ≤10mm (aggregate height differential)
label | f456b928-de8a-5cd7-b592-a220995b51ca |  | note | Record: Required information on the Concrete Pour Record.
label | 495ca548-6d06-56d1-aad5-ee9a4ac423e6 |  | note | – – – – – – – – – – – – – – – – –
label | 0a5d52e6-0afa-5c47-baf3-c908305e649d |  | note | METHOD: Test
label | 8b2f5cdf-9280-5ea4-a0ab-3483165c99bb |  | note | – – – – – – – – – – – – – – – – –
label | a2b81406-8741-521e-9977-79cca9bab06d |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 06773d12-04c7-5177-ab9a-8de4a4badebe |  | note | – – – – – – – – – – – – – – – – –
label | af6cd45d-fc3a-5467-bf9d-3aea4a6a9522 |  | note | CATEGORY: IP
label | f520da25-40d7-5331-9196-7708c3e02245 |  | note | – – – – – – – – – – – – – – – – –
label | ed539f99-0f7f-5b89-b59c-661c25ea7605 |  | note | RESPONSIBILITY: Concrete Tester
label | 07852a82-f4bb-554b-93af-757056703b57 |  | note | – – – – – – – – – – – – – – – – –
label | f86da9c0-d9c5-51aa-8743-2f32f4c56c83 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8cd8bec6-9b72-578f-881d-bed59d5985e1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | ec3883bc-1524-5e8c-a068-9f50027d69e0 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | 8c5ca500-29b4-5572-b071-644d66f15c5e |  | note | – – – – – – – – – – – – – – – – –
label | b47b01eb-dc35-5f39-a706-521bf36df788 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 5732e763-0a7e-5994-ae6a-5efc979fc742 |  | note | Record: Required information on the Concrete Pour Record.
label | 0511a59d-6f53-5dfb-b872-0c3344ed2a3d |  | note | – – – – – – – – – – – – – – – – –
label | b057c8cb-2d9d-581f-a4a3-02c3f47caa51 |  | note | METHOD: Test
label | 7b69b9fc-136e-5634-9e4d-5d8d8dc239d9 |  | note | – – – – – – – – – – – – – – – – –
label | cc2b989e-5ffc-5dab-b723-21e802716874 |  | note | FREQUENCY: Each sample
label | 6376fbf1-ce83-5bb4-9fe6-398e22384188 |  | note | – – – – – – – – – – – – – – – – –
label | 41347a79-8f67-5761-ac04-5aba9ef0e146 |  | note | CATEGORY: IP
label | 93681792-12c8-5d65-be91-b6b312805c36 |  | note | – – – – – – – – – – – – – – – – –
label | 54ec6182-351e-5836-ad13-383542bb19ec |  | note | RESPONSIBILITY: Concrete Tester
label | 2ff109be-33af-5319-a5ee-e21b085bb453 |  | note | – – – – – – – – – – – – – – – – –
label | 37904152-5e0a-5334-b6f1-bd8c37538714 |  | note | VERIFYING DOCUMENTS: This ITP
text | ed174a8d-ff8b-55d7-81ac-66f53e977b0d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | fd6e180f-8007-53f0-bdcf-6a97d5e9d73a |  | note | REFERENCE: Piling Quality Procedure 610.18 (a) & (b) 610.18 (d) (i) 606.06 (a & b)
label | bbc87a57-c5fe-56e9-a85c-dbe1a23e34ab |  | note | – – – – – – – – – – – – – – – – –
label | 771d951b-bcf8-5651-9061-4b9c7f6e719c |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | 6f802b8a-f987-5cd9-b3b9-f52ce1e4bc58 |  | note | • All concrete batches are traceable.
label | b3d38e5a-954f-5b57-b98e-e7e87ef1a313 |  | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 05fbd8bd-c6d8-5496-adc8-9e2307037a12 |  | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | b72ebfab-a267-5400-8e0b-d69c9f6a538a |  | note | • The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 8e66b6f0-c8e1-5f04-8f04-4aac13054ceb |  | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 0e12994a-020c-5c1a-a3f9-dc855a78f7e7 |  | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 87424df1-f47c-5407-9cc8-842db2a10c50 |  | note | Record: Required information on the Concrete Pour Record.
label | 3adc00fc-7bee-52d1-a2fa-9f484d106a01 |  | note | Attach: Concrete Pour Record
label | d678cdeb-b317-5dde-a439-babdf3565ef0 |  | note | Attach: Concrete Dockets
label | d1336547-d67d-5ed0-8c62-8f5debac8da5 |  | note | – – – – – – – – – – – – – – – – –
label | 072d8bdb-377d-5b27-911b-b59b9310ff7f |  | note | METHOD: Visual
label | 2420f2f0-487a-5f15-a208-f63f3355b4a1 |  | note | – – – – – – – – – – – – – – – – –
label | 13fb2b26-c3b2-5978-8332-bff69aa56ffa |  | note | FREQUENCY: Each load
label | a3bcd20e-0bba-59ad-98a1-efef0725106d |  | note | – – – – – – – – – – – – – – – – –
label | c06c43bf-d9b3-55f5-a516-0f674b721ef0 |  | note | CATEGORY: SP
label | 61b5f67e-e191-56c5-ac06-95e1b3d44a5d |  | note | – – – – – – – – – – – – – – – – –
label | b5ba36d7-f8fa-5d33-9086-dfda1d801eab |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
text | 7733b376-bb14-5234-8a9d-0c534d2d352b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 0d761eb8-99e8-537d-8ad4-0ef5e6de13f5 |  | note | REFERENCE: IFC Drawings 610.31 610.20
label | 86f9a53c-f7e5-599f-9b10-80ed8c26f8bb |  | note | – – – – – – – – – – – – – – – – –
label | 4eeca337-ac4b-57fe-87c8-caf8cd910704 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 26309abb-2110-589a-9a3e-c0a6a4f8b363 |  | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 76aab080-d2b1-5fb8-a282-683b26fc2d93 |  | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | d3a46d65-70de-52e2-a13e-a93ab8f06f66 |  | note | – – – – – – – – – – – – – – – – –
label | d750caee-e2a6-5b80-8c4f-5b38ad4a55b3 |  | note | METHOD: Visual
label | 51b94231-81b6-5463-9099-ed7eb314bf19 |  | note | – – – – – – – – – – – – – – – – –
label | 1588c1b5-5f7f-5ffc-960b-5d4a24bd61d4 |  | note | FREQUENCY: Each pile
label | 1d70ea6b-af60-53ea-bd1f-10beb17c7803 |  | note | – – – – – – – – – – – – – – – – –
label | 15b9284e-d5dc-58a0-a0bb-10b02103a68a |  | note | CATEGORY: IP
label | 22017291-535f-5e32-ae9f-2066e07abefc |  | note | – – – – – – – – – – – – – – – – –
label | 13168a56-48a5-5a4f-a149-ad11c0c36cda |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 27718c8f-0d48-5c27-a946-698c58dadf62 |  | note | – – – – – – – – – – – – – – – – –
label | 93afa108-21d6-5e4f-80b7-580c29c64554 |  | note | VERIFYING DOCUMENTS: This ITP
text | f49d177e-84bb-5c1d-ac83-f1287885f725 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | a35a1395-5ba0-51c8-bd80-b3a6f555dc26 |  | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 606.06 (a & b)
label | 06baa5f0-cb05-58b2-8e4a-cb9440e19e62 |  | note | – – – – – – – – – – – – – – – – –
label | 497334a1-4237-589a-a972-8165d7bafa99 |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | e81c681e-a3fc-5f71-86c7-f3425b1c51c4 |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 2cdf6ad6-0df0-53b9-9c73-d1b91b13ab1b |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | d513c63d-65ef-5340-bed2-1ffa52547244 |  | note | – – – – – – – – – – – – – – – – –
label | a7531f63-444f-531f-806e-a81a928260d7 |  | note | METHOD: Measure, Visual
label | 39f0b93e-8c5d-5b18-8e1e-59c79845a93a |  | note | – – – – – – – – – – – – – – – – –
label | 5feef4a9-1091-5c67-94e9-5d010a457afb |  | note | FREQUENCY: Where applicable, each pile
label | ddd7e43d-2a0b-5ef5-84c8-a1a1e0fc8ec9 |  | note | – – – – – – – – – – – – – – – – –
label | ce078fa7-2f28-5199-8383-1d70ec2df69d |  | note | CATEGORY: IP
label | cd75d82e-f6b6-599c-ab4b-1c434e1c2edf |  | note | – – – – – – – – – – – – – – – – –
label | 06554806-b026-5685-975c-23597c73dc6f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3f47f00e-d1e5-5b4b-992b-13d6a5ca1a31 |  | note | – – – – – – – – – – – – – – – – –
label | 0af724d2-a189-54e9-b86a-502aee1e18f0 |  | note | VERIFYING DOCUMENTS: This ITP
text | ae5c577a-8921-55a2-8779-78b8a2391b57 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | cbed9ec4-f4ae-52a1-8106-f5675e36d5bc |  | note | REFERENCE: IFC Drawings Table 610.05.051 610.16 (g)
label | 74d36346-f5f4-52df-a6e8-267398569422 |  | note | – – – – – – – – – – – – – – – – –
label | 92b3a5fb-9e3c-5489-9ba8-ec26dda0e2c5 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 3d5ca9bc-a78d-516d-8e51-fc6496310dae |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 0786d6dc-f624-509d-b9fa-313d5ad01395 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 92710a56-c23b-5c8b-8445-ba43eae0db35 |  | note | Attach: Compressive Strength Test Results
label | 877146d2-d4a8-5707-a08d-1781031ef103 |  | note | – – – – – – – – – – – – – – – – –
label | a230532e-e713-5813-9b21-26d22d717a3a |  | note | METHOD: Document Review
label | 1ece919b-c936-5c15-ae74-e4b92ae0e677 |  | note | – – – – – – – – – – – – – – – – –
label | 6eb7b19a-30ec-597b-8fc4-f3fc6eb4c2c6 |  | note | FREQUENCY: Each cylinder
label | dd8c695b-8228-59e4-9258-d570130e9781 |  | note | – – – – – – – – – – – – – – – – –
label | 065d8868-3c0d-5d17-bd53-be2eb5d82658 |  | note | CATEGORY: IP
label | 850e472e-f900-5d9b-9fbb-6575e05ba867 |  | note | – – – – – – – – – – – – – – – – –
label | 7a921fc4-c414-5450-bd8f-1b3ea7fd4ef7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0e02434f-d120-5f0f-8304-420d50949645 |  | note | – – – – – – – – – – – – – – – – –
label | 31acc580-13b8-5820-9214-101680427fcc |  | note | VERIFYING DOCUMENTS: This ITP
text | 5c71fd28-65fe-509b-ac3b-f707ea5e7aa7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 34489083-0cf4-5377-97ab-0d15981aacaa |  | note | REFERENCE: 606.07 (a, d & e) AS2159 Clause 8.8
label | 59def6eb-33aa-50b2-8e51-1463eec49314 |  | note | – – – – – – – – – – – – – – – – –
label | 8db43e17-e389-5145-9ce2-c6f492b845c0 |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 54229314-3721-5d37-b80a-5a2aa0e10959 |  | note | • Cross-sectional area = ≥95%
label | 50ae2fe2-74d5-55fe-8aa9-08a78e612210 |  | note | • If any test fails, all piles shall be tested.
label | 99ec655a-b15c-58e8-8176-969310710dea |  | note | Attach: Pile Integrity Test Report
label | 4adbd8d8-6e3a-56ea-9bae-6af78e57405f |  | note | – – – – – – – – – – – – – – – – –
label | 51abb88c-445c-5751-a0bb-5cc4028dfe1d |  | note | METHOD: Document Review
label | b7cc1458-3376-5a3b-8a8f-5b8a41df340b |  | note | – – – – – – – – – – – – – – – – –
label | d0a0e821-2b79-526a-9c21-3782962857db |  | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | ee931a78-9eba-5e18-a25a-c072e186eb47 |  | note | – – – – – – – – – – – – – – – – –
label | 09ad1d2e-13ad-57cf-9b9c-5bbd6d659b8b |  | note | CATEGORY: IP
label | 51bdf18d-1686-55cf-b37d-22feb688436e |  | note | – – – – – – – – – – – – – – – – –
label | a3910dca-276b-5d77-a924-5f36adce41d2 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 9366cf7c-322b-5fdd-9231-ed9fa2cf273f |  | note | – – – – – – – – – – – – – – – – –
label | b66620c3-af5b-59e7-9d11-4937f54f6e9b |  | note | VERIFYING DOCUMENTS: This ITP
text | a15dcd91-c44e-54aa-8af0-42d0df8c67e8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Static Load Testing
label | 8fa2952e-8b3e-59f4-b359-82d49947a468 |  | note | REFERENCE: IFC Drawings 606.07 (b, d & e) AS2159 Clause 8.4
label | e9dc46dd-2d19-5ab5-9d22-aae75122cf27 |  | note | – – – – – – – – – – – – – – – – –
label | c2fd5d9a-fc19-56e9-8779-0f9a2def5daa |  | note | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | 4f3f9445-9bfd-5a92-8c8a-eb40e8adb94c |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | c394a371-4136-5028-9344-98db2690a5f5 |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | 19f78f32-62e1-5468-895a-96279e815cb0 |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | b7bb2580-b435-54a5-9898-af8885b8539c |  | note | Attach: Static Load Test Report
label | ea3dee8c-d330-540e-85f5-7b6d5f557b28 |  | note | – – – – – – – – – – – – – – – – –
label | 0daf8d6a-cc14-5be6-a6ba-0905bbfc7031 |  | note | METHOD: Document Review
label | b0278f04-8320-5699-8a79-dcaa0370cde1 |  | note | – – – – – – – – – – – – – – – – –
label | 2b652acb-90e4-5b7f-8e0c-a74f64c9013a |  | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
label | 2d3c8ed2-c3a4-5aa9-9475-742de5364346 |  | note | – – – – – – – – – – – – – – – – –
label | a6fc1eb1-134b-5821-afb3-db8383cb5b4f |  | note | CATEGORY: IP
label | 00f2776d-6123-5d4e-afe6-f5da4c8072c5 |  | note | – – – – – – – – – – – – – – – – –
label | 56c915af-b3cb-52bf-a581-3d605671969d |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 4f50c1c3-4fc7-5546-8a3a-3f23c0639312 |  | note | – – – – – – – – – – – – – – – – –
label | 2140f516-eafa-5763-8434-d48236e86a42 |  | note | VERIFYING DOCUMENTS: This ITP
text | ad2bff45-5e0c-53cd-aa59-fdc3ca05f92c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | e0fd7af3-817f-5270-b7d8-8c633360d1ad |  | note | REFERENCE: 606.07 (c, d & e) AS2159 Clause 8.7
label | 9c879cfa-edfa-5ed2-aa08-f5f58d03ea97 |  | note | – – – – – – – – – – – – – – – – –
label | fdd57f8c-18cb-5766-97d4-c12615cc1b45 |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | 27ac50c3-e764-5f31-8e4c-989092073278 |  | note | Measured Ultimate capacity = ≥ values on IFC drawings
label | d0b64a48-a830-5062-ac5d-eaaa82318678 |  | note | Attach: Dynamic Pile Test Report
label | b0d61f88-759c-54de-9d79-1cfd499fdfa4 |  | note | – – – – – – – – – – – – – – – – –
label | efe95a01-36b4-5bda-a01b-c81d41a6a453 |  | note | METHOD: Document Review
label | 450f7055-9924-5519-aa1c-14a07c49d788 |  | note | – – – – – – – – – – – – – – – – –
label | c96ebc1f-99ff-5132-a1b6-0f5b190e2e9c |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | b1448f93-6028-59c9-b9b5-015a2c8c96f2 |  | note | – – – – – – – – – – – – – – – – –
label | 3b642563-d674-546c-8271-5a4ecc08a50b |  | note | CATEGORY: IP
label | eeea3685-4d92-51da-9f97-d01af1d938cd |  | note | – – – – – – – – – – – – – – – – –
label | 2d8dc730-bb04-5726-8fe4-23cdedab77f9 |  | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
label | 3e659148-5302-5418-a49e-239b159697fe |  | note | – – – – – – – – – – – – – – – – –
label | 7dc30864-caf3-5530-9bc6-6e37bed712c3 |  | note | VERIFYING DOCUMENTS: This ITP
text | bc3543a7-8f57-52b4-8603-505a0f07e92c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | 2f4d8cdf-1906-5a27-9e25-0ed3d4ed5d69 |  | note | REFERENCE: IFC Drawings 606.08 (a - c) AS2159 Clause 7.2.2
label | 3f15c219-1392-5583-92f8-86205a15170c |  | note | – – – – – – – – – – – – – – – – –
label | 00f6530a-f988-5c07-ac83-6f968004df49 |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 77a5082d-a0a6-514d-ab94-4a4a210b0145 |  | note | i. Pile head plan location = ±75mm
label | f5028a51-e933-5fb7-9437-6af72aa60347 |  | note | ii. Variance from vertical or rake = 1:100
label | c45fa42f-4160-579f-9044-b7231f441978 |  | note | iii. Irregularities in straightness = 1:100
label | 4d4212b0-c828-5ad0-be18-03c397270f50 |  | note | iv. RL = ±25mm
label | 8990839e-1bfb-50e3-af96-a01d70faf6ab |  | note | Attach: Survey As-builts / Survey Report
label | 41bfeafd-395e-5454-96af-a96f7624af3e |  | note | – – – – – – – – – – – – – – – – –
label | e5a33d2e-693d-51c4-bc44-da65dc3d326d |  | note | METHOD: Document Review
label | 4b1500b9-2771-504f-b4f6-2f9e74d09783 |  | note | – – – – – – – – – – – – – – – – –
label | 64c02500-df77-5cbf-bbfb-c0add0c7dc5e |  | note | FREQUENCY: Each pile
label | fc5a0f51-7c3f-5480-b5e4-30aea4e99ca0 |  | note | – – – – – – – – – – – – – – – – –
label | f9ef3e50-e7b4-53f7-84d2-3eece36860c9 |  | note | CATEGORY: IP
label | c3c40ace-4d7d-5968-aab9-c7b0ae847e8e |  | note | – – – – – – – – – – – – – – – – –
label | 2114f26c-5cef-5159-bb49-5de60d42e9db |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 16154ae5-3aee-5865-9126-9d79c7be197c |  | note | – – – – – – – – – – – – – – – – –
label | 608bc0fc-1634-58a6-a334-c8092b899aa6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 12204703-9300-5cce-ac1b-17cef2b718cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | cafe9266-53b6-5392-9679-b1a071be7b2c |  | note | REFERENCE: MRPA Quality Management Plan
label | 88332635-95a9-5973-bf34-9d4bc34e76eb |  | note | – – – – – – – – – – – – – – – – –
label | 3711deab-c05e-5df2-9f2c-d51836593294 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 00ef86c3-ef4f-5dcc-b629-ae514f6ee85e |  | note | – – – – – – – – – – – – – – – – –
label | 8c9c699d-8f01-5ba8-9a33-e8e2a89b6e62 |  | note | METHOD: Document Review
label | 502988e0-7ceb-588f-a899-216454e5346f |  | note | – – – – – – – – – – – – – – – – –
label | ad983036-4157-5f5a-baa1-496b1070e4ff |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | b8c11c63-386d-51bf-bad1-97ba8d92b27d |  | note | – – – – – – – – – – – – – – – – –
label | b1800cd7-0f2d-585d-b1b1-a816ddf80826 |  | note | CATEGORY: HP*
label | b18c3f9b-5d8a-5a1c-b034-1fcf5105fa9e |  | note | – – – – – – – – – – – – – – – – –
label | 340dadef-d945-50c5-bd59-2768337d1174 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b9788f93-bb61-5a88-826d-02f157a65662 |  | note | – – – – – – – – – – – – – – – – –
label | fd10df2a-a440-5349-be4c-50b125be4617 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9c689bc4-dd86-58f8-8914-d38923729003 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 600c0e73-1d0b-5d6d-8436-164f25379f77 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 34953e20-dec5-504c-9fde-76bc5ee207ad |  | textbox | Name:
text | 3425c2e7-9c84-5a30-805b-afa9a69dd763 |  | textbox | Position:
text | beff82c2-e6aa-5ba5-91c5-15888ce25759 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP