## General
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check point | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | M2F |  |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | DS2681-SH58-ITP-M-019 Anchorbloc Materials DS2681-SH58-ITP-C-004 Anchorbloc Retaining Wall |  |  | Version: | Rev 1 |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Anchorbloc Wall | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Civil | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | MCIP SH58 East of Moonshine Road to Transmission Gully- Project Specification | [5 empty] | O | Operation | ST | Superintendent | Nick Talbot | NT
[7 empty] | R | Review | PE | Project Engineer | Dehan Erasmus | DE
Drawings: | 80510096-02B-900-C470 | [5 empty] | S | Subcontractor | SE | Site Engineer | Tyrese Dickson | TD
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) | Tyrese Dickson |  |  | Date: | 2025-07-10 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
Construction Manager |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-07-15
Project Manager |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
QA Advisor |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: please add the whole number and description from the WBS, ask me for the numbers

## Materials
SECTION 3 – MATERIALS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.1 | Material Compliance - Precast Anchorbloc | Prior to construction | Project Specification CL 18.1.5 | The Contractor shall provide to the Engineer, full details and specifications of the anchorbloc including ACEGrid and locking bar. Details to be provided by manufacturer | Technical/ product data sheet, Delivery dockets, ITR-Incoming Mateirla Inspection (DN-QUA-QC-10) | Prior to works | Document Review | H | ER
3.2 | Material Compliance - AP65 (M4 if required) basecourse | Prior to construction | Project Specification CL 18.1.5 | *free of unsuitable material as defined in the Earthworks Specification. *Fill to contain no more than 20% passing a 75μm sieve. *Fill to have maximum particle size of 100mm *Fill particles shall be able to be incorporated within a single layer. Further, less than 30% of particles shall be retained on the 37.5 mm sieve. *Unless otherwise approved, the MSE Wall Fill shall have a Liquid Limit less than 70% and a PI less than 6%. *MSE Fill shall be able to be tested in accordance with conventional compaction test methods for soil. Where Nuclear Densometer is used, these methods require less than 20% retained on the 37.5 mm sieve. Where between 20% and 30% of particles are retained on the 37.5 mm sieve the above test methods shall still be adopted and test reports annotated appropriately including reference to any test calibration or correction adopted | IANZ Lab Report | Prior to works | Lab Test Report | H | ER
3.3 | Geogrid for Anchorbloc Wall | Prior to construction | Project Specification CL 18.1.5 | The Contractor shall provide to the Engineer, full details and specifications of geogrid reinforcements details including manufacture data STRATAGRID SGU80 to or equivalent to be used as per 80510096-02B-900-C470 Rev 1 drawing | Technical/ product data sheet, Delivery dockets | Prior to works | Document Review | H | ER
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: specify the components required, concrete, reo, etc
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: is the Achor bloc precast?, do we have the QA for this?
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: you just need to cite the clause number etc, no need to add the whole clause. Thanks Reply: need specific requirements for baskets, fill etc. Reply: need survey set out evidienc
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: what geogrid is used, ie Reinforcement Uniaxial monolithic HDPE 60 kN/m tensile strength geogrid (ie. Tensar RE540 geogrid or equivalent approved as per NZTA Materials list) or a single sheet of hexagonal, PVC-U coated galvanized, double-twist, woven steel mesh (ie. terramesh or equivalent approved as per NZTA Materials list)

## Construction
SECTION 4 – CONSTRUCTION Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
4.1 | Foundation Test Requirements | Following Excavation | Project Specification Cl 18.5.4 | Minimum of 3 blows/100 mm penetration | Scala Testing Record Sheet DN-QUA-QC-04 | 10m intervals | Witness Point | W | SE
4.2 | Foundation Subgrade | Following Excavation | Project Specification Cl 18.5.2 | The foundation for the retaining wall subgrade must be inspected by the Engineer and shall be approved for the placement of the wall facing elements and reinforcement elements | Site Instruction - Hold point release / email | Following Subgrade digout | Hold Point | H | ER
4.3 | Foundation AP65 - Compaction | Foundation prep | Project Specification Cl 18.5.5 | Foundation Compaction: 95% MDD and+/- 2% of OMC as determined from the plateau test/or lab testing. None less than 92% 1 set of NDM tests (comprising 5 No. NDM tests per set) are required per 200mm fill lift | NDM Test Results DN-QUA-QC-09 | 1 set of NDM tests (comprising 5 No. NDM tests per set) | Hold Point | W | SE
4.4 | Anchorbloc Placing | Survey as-built | Project Spec Cl 18.5.7 | Anchor blocks shall be placed into correct position, alignment and angle according to drawings | Photo Record, as-built records | Continuous | Witness Point | W | SV
4.5 | MSE Wall Backfill AP65 - Compaction Testing | MSE Wall Backfill | Project Specification Cl 18.5.5 | Foundation Compaction: 98% MDD and+/- 2% of OMC. None less than 95% 1 set of NDM tests (comprising 5 No. NDM tests per set) are required per 200mm fill lift | Photos | Placement/ Prior to backfill | Witness Point | W | SE
4.6 | MSE Wall Backfill AP65 - Visual Inspection | MSE Wall Backfill | Project Specification Cl 18.5.2 | The backfill must be witnessed by the engineer with fill layers not exceeding 200mm. | Visual Inspection | Placement/ Prior to bakcfill | Hold Point | H | ER
4.7 | Placing Geotextiles/geogrid | MSE Wall Backfill | Project Specification Cl 18.5.2 | 80510096-02B-900-C470 Wrap top, bottom & front edge with STRATAGRID SGU80 | Photos | Placement/ Prior to backfill of upper layers | Hold Point | H | ER
4.8 | As-built Survey | Upon completion of works | Project Spec Cl 18.5.7 | As built survey record completed | As-built records | At completion | Witness Point | W | SV
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: is there excavation required to specific dimensions?
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add check sheet no.
Note on J4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need info
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RFI Reply: This is meant to be done on site. The ER can be onsite for this and give us approval
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add check sheet number
Note on J7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: as built survey needs to be done by surveyor