## Cover Page
Inspection and Test Plan
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL details
Project Name: | State Highway 58 Safety Improvements | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Initial
Customer: | NZTA | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | [6 empty] | C | Check | SPE | Senior Project Engineer | Jamie Nisbet | JN
Area/ Sub-System: | Bridge 3 |  |  | Lot ID Number: | TW-001 |  | D | Dimension Inspection | PE | Project Engineer | Natalia Jimenez | NJ
[7 empty] | E | Examine | SE | Site Engineer | Livingstone Lameko | LL
ITP Number: | DS2681-SH58-ITP-TW-001 |  |  | Version: | 1 |  | H | Hold Point | SV | Surveyor | Jim Robbins | JR
ITP Description: | Temporary works for bridge 3 | [5 empty] | I | Inspection | QM | QA Manager | Diliban Sengottian | DS
Discipline: | Crane pad & Cofferdam | [5 empty] | M | Monitor on Random Basis | ST | Superintendent | Nick Talbot | NT
Specification: | Project Specification, SH58 Safety Improvements, Stage One REV0.0 | [5 empty] | O | Operation | PS | Project Supervisor | John Marsters | JM
[7 empty] | R | Review | SR | Stantec Representative | Sam parkinson | SP
Drawings: | 2681-TW-001 | [5 empty] | S | Subcontractor
[7 empty] | V | Visual Verification
Prepared By: (Name) | Natalia Jimenez |  |  | Date: | 2025-07-21 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Natalia Jimenez |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Mark Hedley |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspections
Inspection and Test Plan
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity Include frequency, if applicable. | Acceptance Criteria | Specification Reference | Verifying Document | Inspection/ Test |  | Inspection Point/ Signature & Date
[6 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.01 | Sheet piles | Prior to works | Prior to installation, a visual inspection of the sheet piles will be conducted to ensure they are in good condition. The inspection will verify that the sheet piles have the required length to reach the necessary depth for proper driving | Please refer to Bridge 3 – Temporary Works Design. | Visual | V | SE
3.02 | Steel Waler Beams | Prior to works | Confirm steel section 360UB44 | Dwg 2681-TW-003 | Visual | V | SE
3.03 | Welds | Prior to works | All welds to be visually inspected and if any defects are found, they need to be reported. | Please refer to Bridge 3 – Temporary Works Design. | Visual | V | SE
3.03 | Concrete | Before removing any walers | Report all QA for concrete to the Engineer including delivery dockets and report on placing before removing any Walers. | Please refer to Bridge 3 – Temporary Works Design. | Check | H | SE

## Inprocess Inspections
Inspection and Test Plan
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity Include frequency, if applicable. | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[7 empty] | Key | Inspection By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
4.01 | Location and marking of the cofferdam and crane pad. | Prior to works | The final location of the cofferdam and the working platform should be clearly marked on-site, ensuring the dimensions and alignment with respect to the pier extension, and considering the proximity shown on the drawing. | Please refer to Bridge 3 – Temporary Works Design. | Prior to sheet piles instalation | Dimension inspection | D | SV
4.01 | Sheet piles installation | During construction | The sheet piles will be driven down with the excavator to just below the platform level, ensuring the design height is achieved and that the piles have reached rock level. Report sheetpile embedment depths to the TW Engineer | Please refer to Bridge 3 – Temporary Works Design. | Driven down of sheet piles | Hold Point 1 | C | TWC |  |  | Permit to Load
4.03 | Top waler installation | During construction | Check the levels of the underside of the waler to ensure it is just above the top of the new pier. Install and support the Top Waler. Drive the sheet piles around the waler. Weld the Top Waler in place. | Please refer to Bridge 3 – Temporary Works Design. | First waler installation | Inspection | I | SE
4.04 | Lagging installation | During construction | During the lagging installation between sheetpiles and bridge Abutment, ensure there is sufficient space for the formwork, with a minimum clearance of 900mm. The lagging must be securely fastened both to the sheet pile and the pier. As new boards are placed underneath, they may need to be held to the lagging above. Uuse vertical boards nailed to the lagging above if necessary to hold the new lagging in place. | Please refer to Bridge 3 – Temporary Works Design. | During construction | Check | C | SE
4.05 | Second waler | During construction | Monitor excavation and ensure that measurements are being taken to not exceed depths. The TWC shall inspect the waler before excavation proceeds. Excavate to a maximum depth of 2.25m, then install the brackets and the second waler. Pack the space between the waler and the sheet piles with grout bags. Support the Waler using chains from the Waler above if necessary until excavation has continued far enough to weld the bracing leg to the bracket. | Please refer to Bridge 3 – Temporary Works Design. | During cofferdam excavation | Hold Point 2 | I | TWC |  |  | Permit to Load
4.06 | 3rd waler | During construction | Monitor excavation and ensure that measurements are being taken to not exceed depths. Excavate to 3.58m (max) BGL, install brackets and install 3rd Waler. Pack between Waler & Sheetpiles with grout bags. Support the Waler as noted above if necessary as excavation proceeds. TWC to inspect Waler before excavation proceeds. | Please refer to Bridge 3 – Temporary Works Design. | During cofferdam excavation | Hold Point 3 | I | TWC |  |  | Permit to Load
4.07 | Welds | Welding review | All welds to be visually inspected by the TWC and any defects reported to the Engineer. Each of the 100mm long stubs are to be identified, marked and photos of each sent to the Engineer for approval. | Please refer to Bridge 3 – Temporary Works Design. | During welding process | Inspection/ Hold point | I | TWC
4.08 | Welds | Welding review | All welds to be 6mm Fillet Weld all round UNO. | Please refer to Bridge 3 – Temporary Works Design. | During welding process | Inspection/ Hold point | I | SE
4.09 | Platform level | Prior to works | The platform level must be 325mm below the road level at the center location of the bridge. | Please refer to Bridge 3 – Temporary Works Design. | Before platform works | Check | C | SE
4.1 | Reidbar | During construction | Install reidbar ties 500mm below top of platform
4.11 | Cofferdam excavation | During construction | TWC to inspect bracket braces before excavating to full depth. Fully de-water and clean out down to rock level | Please refer to Bridge 3 – Temporary Works Design. | Cofferdam excavation | Hold Point 4 | A | TWC
4.12 | Concrete toe | During construction | Cast concrete toe support 400mm thick. Report all QA for concrete to the Engineer including delivery dockets and report on placing before removing any Walers. Remove second and third walers after 7 days. | Please refer to Bridge 3 – Temporary Works Design. | After excavating to full depth | Hold Point 5 | A | TWC
4.13 | Hydro response | After sheet pile installation | PVC sheeting is to start from the far side of the bridge and continue past the cofferdam, as advised by the waterproofing contractor. | Please refer to Bridge 3 – Temporary Works Design. | After sheet pile installation | Action | A | SE
4.14 | Hydro response | After sheet pile installation | Attach the PVC sheeting to the sheet piles and to the concrete bridge pier beneath the bridge. | Please refer to Bridge 3 – Temporary Works Design. | After sheet pile installation | Action | A | SE

## Inspection Handover
Inspection and Test Plan
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity Include frequency, if applicable. | Acceptance Criteria | Verifying Document | Inspection/ Test |  | Inspection Point/ Signature & Date
[5 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
5.01 | Final Handover | Documentation | All hold points must be formally reported to the Engineer for inspection. A photographic record of the inspected works shall be maintained. Proceeding beyond any hold point requires explicit approval from the Engineer. | Permit to Load | A | TWC
SECTION 6 – COMMENTS
|  |  |  | Customer Release Granted: |  | ☐ Yes | ☐ No | Date:
Certificate Number: