## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
df729b3c-3315-48f2-a9d5-35188d27738b | checklist | DS2681-SH58-ITP-C-002 Earthworks Cut | itp | DS2681-SH58-ITP-C-002 Earthworks Cut
67451a6a-8cea-4ef4-a602-3d151731a5f4 | section | SECTION 4 – IN-PROCESS INSPECTIONS
eb5fd506-7948-4670-96c6-7831c5fafefd | checkpoint | 4.1 - Topsoil Depth Checks
de3d5445-3307-5b23-8aba-28f82720e2d1 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
44f07abe-85b7-54db-b372-d03d9a585c2c | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
a4de364f-08bf-5b9c-b022-6dc85551c8d9 | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
5510836b-ae61-540a-b704-85c3a5a6bfe6 | note | Verifying Document - Site Photos, Record Sheet
4103d90f-e4e8-5da3-82b6-0ff867bb7135 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2eb5b3dc-7fbe-5392-8414-62b6bcdc5cf3 | note | Inspection Type (Visual, other) - Witness
9e0530ad-9dea-5be2-8d73-2a9795b48e4e | note | Inspection: Key - W
d4639d9a-6767-5269-beb3-1215691074e9 | note | Inspection: By (Role Key) - SE
7f30c528-f201-40dc-a527-ab421a6f883e | checkpoint | 4.2 - Hazardous & Classified Soils
a664ce29-a8e5-5d63-bf17-014a35d000d3 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
f27256d6-4592-5d4e-b73e-a3f74a51ddcb | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
3936fc1e-e1d7-59bf-809a-00f5e6081b10 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
ca6b4c12-6d5d-5ba8-9c78-a9d7afb7bd23 | note | Verifying Document - Visual, Site Photos
4c1efc39-f017-5255-86c2-be965b493de3 | note | Frequency - Continuous
5133fb55-1305-57a9-92d0-3b06cc30e7bb | note | Inspection Type (Visual, other) - Witness
1cb75dd6-d38d-54c4-8a6a-1d495d5c3c41 | note | Inspection: Key - W
8e4f7cfc-35d6-5afe-b23d-7b61efbc098f | note | Inspection: By (Role Key) - SE
7486c58c-9fb9-4a38-88b8-d8792c7aa396 | checkpoint | 4.3 - Final Cut Observation Monitoring
347fdff0-3102-5435-ab25-bee766125209 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.6
4c207fc2-d9dd-50df-b46f-e08c487449e2 | note | Specification Reference - Continuous visual assessments conducted with Stantec Representative. Contractor to address design change if instructed
3ba2bd1d-904b-51b3-b6d0-9bb09aa69e01 | note | Acceptance Criteria - Agreement with Engineer's Rep
66603339-865d-527b-956f-0eb5c2b210cb | note | Verifying Document - As Required by Stantec Representative, QC-01 Earthworks Checksheet
4f7df1dd-eee8-52c9-81fc-4ba03ad868e4 | note | Frequency - As requested by engineer
d2081a75-cfd1-5c2e-b034-a5ec45a3a4b5 | note | Inspection Type (Visual, other) - Hold
56b79a36-efd0-5403-a2ad-bb8a1356d7da | note | Inspection: Key - H
dbb2871b-47f9-592a-8990-7dd356b5fdf4 | note | Inspection: By (Role Key) - ER
f191c6b6-2aab-4164-96e9-e47a0b3675af | signoff | AUTHORITY HOLDPOINT
2cdfb66a-9389-4627-8667-eef40cd2af5f | checkpoint | 4.4 - Cut Batter Tolerances
132eeb5a-fe9d-5df7-9be4-782120e3ef4c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.7
56c83086-c7e9-591b-b20c-40fe8793f938 | note | Specification Reference - Post-construction - Excavation of batters complying with design issued and within tolerance
ee66d3c0-49a5-5d67-a4b8-18faff38f4bf | note | Acceptance Criteria - Slope Tolerance 1H:1V or Flatter: +300 / -300 mm
79a3c917-608e-50cd-ab7f-e9fde7c7f119 | note | ○ Steeper than 1H:1V: +300 / -600mm
bc450905-2158-5089-979e-c8eff2fda31f | note | Verifying Document - As-Built and DN-QUA-QC-01 Earthworks Checksheet
207498a5-e043-56c3-835c-476f874fa023 | note | Frequency - Continuous
efa9913e-4bbe-5fbd-93b7-b9e6a3302e68 | note | Inspection Type (Visual, other) - Witness
d3cab161-6063-560d-945e-a4cc933e71a5 | note | Inspection: Key - W
ab994e35-4b7d-51e2-9377-c0539f957500 | note | Inspection: By (Role Key) - SE/SV
9ac63d2d-3fdf-41a8-8a9e-87424a2ecd20 | checkpoint | 4.5 - Site Fill Material - Segregation of Material Type
6f0f9b0b-029a-522d-a566-d1cf24cf370c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.8
aceeaf6b-a147-5532-9113-38bc69c47f73 | note | Specification Reference - Moisture sensitive material stockpiled
bb49d682-186e-5a46-813b-e57556aa8fa2 | note | Acceptance Criteria - Drainage blanket (polythene cover) if any material is stored on site to avoid saturation
c7f353d1-7f18-5f61-872b-b7f030221da3 | note | Verifying Document - Visual, Site Photos
801989f2-a1a7-5cb5-a394-0c7653136733 | note | Frequency - Continuous
e72a8aec-2da8-56be-bced-9018554b9697 | note | Inspection Type (Visual, other) - Witness
0d762aba-083d-5501-b776-f4c5925a4422 | note | Inspection: Key - W
08311d38-a7ef-5a95-b4bd-5c3fa8e79616 | note | Inspection: By (Role Key) - SE
192b71df-9dfe-44fb-ad89-61f682f2a57c | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
e676d3ad-166c-4de3-98c3-ae9896beecb7 | checkpoint | Inspection Point/ Signature & Date
b072bae1-74c0-5098-bd68-d5405a971db5 | date | Date:
18d8e4a4-5b1d-58d0-8bf9-f29766a313f4 | textbox | Customer Requirements Verification Record / Location/ Hold Points
2a4a07e0-640c-4290-bbe6-638dd12e0a67 | signoff | Downer Signature
90218fb0-56ec-4157-b8eb-076f3f2fd692 | checklist | DS2681-SH58-ITP-C-003 Earthworks Fill | itp | DS2681-SH58-ITP-C-003 Earthworks Fill
d8549d1c-6084-4eb6-aa34-e1037e972367 | section | SECTION 4 – IN-PROCESS INSPECTIONS
9c62c46d-be03-4325-a269-2e1cce813bfd | checkpoint | 4.01 - Topsoil Depth Checks
5b8fa5b8-196b-5600-971a-f3b6d4d676fc | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
a452a378-61e0-5c00-b74c-c726008ddc11 | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
03b3720f-8844-514c-9229-a15264506e4d | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
08613c48-b482-5be7-a20d-be6627cb7408 | note | Verifying Document - Site Photos, Record Sheet
5e42a0de-49e9-5c4a-9848-bd849cebdb25 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2795d9b2-d7e0-5caf-8f7a-d709a310f2ca | note | Inspection Type (Visual, other) - Witness
3c37b622-502a-5fdc-8c4e-c6d62706b017 | note | Inspection: Key - W
a7deaea1-b306-5546-aefc-792f32b9a252 | note | Inspection: By (Role Key) - SE
4f861c4d-56fa-4f86-853b-b326a5bf7d87 | checkpoint | 4.02 - Hazardous & Classified Soils
31f36bba-8168-5228-8e14-d54e6ebb023d | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
602225a7-35c1-539c-84a2-97e895accb97 | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
9e4f6c65-b625-582f-9951-e8ae49d7aa98 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
4aa4b873-ce3c-5c30-9ddc-6654f6e713b5 | note | Verifying Document - Visual, Site Photos
9a2e7738-8add-5898-b720-a8718215117e | note | Frequency - Continuous
54149323-7e72-5849-b492-bf0b4e9e66bb | note | Inspection Type (Visual, other) - Witness
25ac1de1-7c21-582e-addc-72843b5c923a | note | Inspection: Key - W
3618481a-1a64-57a8-9586-d337c91a4efe | note | Inspection: By (Role Key) - SE
c77466cb-88d4-4d6d-a030-db3f490b0008 | checkpoint | 4.03 - Subgrade testing - Trim and Compact
5a6340d0-a1e7-59c4-9ff0-588daa5c7eeb | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.10
b3e2023e-c87d-5688-9fe8-5c28b6e001fb | note | Specification Reference - Trimming & Compaction of in-situ subgrade. Conduct plateau test.
73cd4ba2-b734-5a25-bb8e-51f26523c1bc | note | Acceptance Criteria - N/A
a3135f5c-ffa6-566b-a008-acdf06b7a12a | note | Verifying Document - Plateau worksheet
cd56e528-0d47-5c9b-abb4-a6f1f7588792 | note | Frequency - Full surface
76f971c6-ab70-5525-bc64-d7cd53497773 | note | Inspection Type (Visual, other) - Witness
f9e71c06-ff1d-5a81-b94c-c384b2eb2de0 | note | Inspection: Key - W
9af2e9cd-1409-5027-b8b4-57fd373d5b98 | note | Inspection: By (Role Key) - SE
6e0b306e-8217-45b6-aa98-3f2da0ad944c | checkpoint | 4.04 - Subgrade testing - Scala
f0fc626b-ce1b-5fc1-a9e2-beb9b21d8252 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.11
36376860-ec21-5a49-8311-bb3c84021acb | note | Specification Reference - Scala Testing
f2c390cd-8a69-5e01-80fd-4edcc1f34413 | note | Acceptance Criteria - 1 blow per 100mm is the minimum requirement for general fill placement
e92b1fd8-2193-5e1c-828b-0e6a473a274b | note | Verifying Document - DN-QUA-QC-04 1m Scala Worksheet
deec5fd9-20d3-5143-a3bc-06d8138e21c3 | note | Frequency - Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
35e62849-6a45-54a6-a33a-948f4a254b61 | note | Inspection Type (Visual, other) - Witness
e6ad1732-5fb2-569e-ab78-d897cd7be49c | note | Inspection: Key - W
2e49b9f7-548e-5556-99db-562e0914b2eb | note | Inspection: By (Role Key) - SE
d08f3a23-a67f-46a3-b73b-2d43b3bf99fb | checkpoint | 4.05 - Subgrade testing - Benkelman Beam
28f510e5-01d5-515a-973a-2b22920e6ab5 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.12
bf32ece9-b533-5d25-826a-80b1481b63e4 | note | Specification Reference - Benkelman Beam Testing
4dfdc5b1-2fd1-5773-a841-951f1236e3f9 | note | Acceptance Criteria - Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm
3a4a1436-0c04-582c-9fe8-166f28a73d8e | note | Verifying Document - Lab report
8167b6e0-f261-5c03-b8b7-7e2a11cf30eb | note | Frequency - Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
5d887dfa-3825-5eb6-918c-a27123ab1be0 | note | Inspection Type (Visual, other) - Witness
e06d1c39-0759-5f50-bf41-af433f55d06c | note | Inspection: Key - W
de8ed31f-dca1-543c-ab81-20618767ee4f | note | Inspection: By (Role Key) - SE
69f4e90b-552e-439b-988f-1e72f0b7b957 | checkpoint | 4.06 - Subgrade testing - Proof Roll
1839ae8e-4785-5e89-ae30-6878bdbefa44 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.13
b84289c8-b380-5f42-9801-1dc5845914e1 | note | Specification Reference - Proof Roll
c1f942b1-a560-533c-b67e-43446bab6d03 | note | Acceptance Criteria - As instructed by the Engineer
6d7c2351-765a-59e4-8dd6-c7b85ae08027 | note | Verifying Document - Visual Assessment - Sign off on ConQA by Engineer
cd2ca153-edff-5158-b93a-c3c9bff4a274 | note | Frequency - Proof Roll: Full surface using suitable plant
a473ece9-ef13-57d1-b8b3-63e66c288983 | note | Inspection Type (Visual, other) - Hold
17decdd9-724b-5160-953e-fbe77be61e8c | note | Inspection: Key - H
b1837a51-96fb-5325-b4fc-49fde76f9d1e | note | Inspection: By (Role Key) - ER
4034b935-2e19-43c5-8b87-422e5ce2a877 | signoff | AUTHORITY HOLDPOINT
d234d476-891c-4e8b-ac9e-658ab18f53bd | checkpoint | 4.07 - SIL Layer
904aecf4-f0cc-573f-b855-48af75eaacc6 | note | Inspection Point: Quality Control Activity - TNZ F/1
8a1fda63-0c20-570c-bfb2-2df5f5cc97d3 | note | Specification Reference - SIL Layer detail, if required
994492a1-c6cd-5a5e-b303-6092164af202 | note | Acceptance Criteria - As instructed by the Engineer
91c0ddac-fcd6-5183-8322-3d3771852b34 | note | Verifying Document - ConQA Sign off
9390676f-62e2-5e80-af62-a9feec2f8987 | note | Frequency - Per Lot
68aee8ba-7933-5343-81f9-997a6891b16a | note | Inspection Type (Visual, other) - Hold
8ea3ca79-8f36-5d18-b6a4-b250727a9ef3 | note | Inspection: Key - H
d7b39f34-5a0f-593e-8547-293759cbf1ad | note | Inspection: By (Role Key) - ER
9e8be85e-82e8-4591-8c89-c4c62823b4f9 | signoff | AUTHORITY HOLDPOINT
baff8782-7812-409c-955d-22faaf8a2d45 | checkpoint | 4.08 - Fill Compaction Trial
3b1aa582-7080-50f7-a743-4d1a834e0c3e | note | Inspection Point: Quality Control Activity - Project Spec Cl 15.6.11
b59340bf-1c1e-5b01-9685-d1d249c2da6f | note | Specification Reference - On-site Testing - NDM, Visual, Shear Vane
3072fcc1-2d40-5f8c-a101-d668ffc305b1 | note | Acceptance Criteria - Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P
a16bbc46-f692-5511-98cc-f9dba2f08730 | note | Verifying Document - NDM Worksheet, Shear Vane Worksheet, Plateau Density Sheet
245f9472-8924-59b7-af93-07fabe64fbc0 | note | Frequency - When a new type of fill material is used
cb7f9df4-0ad0-511e-9839-256019215ea8 | note | Inspection Type (Visual, other) - Hold
9ad8e962-7572-5e64-9aef-a31d67b4fc4e | note | Inspection: Key - H
c9c7d82b-adec-5235-81cc-c72bb9211895 | note | Inspection: By (Role Key) - ER
f985a566-05fe-4bca-aa0a-63ece48458e9 | signoff | AUTHORITY HOLDPOINT
ac487538-1b27-4fb7-82cb-3d1c832dc83b | checkpoint | 4.09 - Fill Backfill layer thickness
9dc0ddd5-7081-5c5b-aad6-244ddd534627 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.8
9100536d-2452-5d74-8636-8012cb1a7aa7 | note | Specification Reference - Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction
b573abdd-0e24-5b25-9997-15ae932b717b | note | Acceptance Criteria - Fill placement not exceeding 230mm
c7aae880-1974-5f3b-9be6-50d71e180eb1 | note | Verifying Document - Visual, Site Photos and NDM check sheets, DN-QUA-QC-09 NDM Worksheet
e281d108-66fa-59e2-8851-f46838f6719d | note | Frequency - Every layer
6f256caa-f61b-5b64-b071-a38145b5f2e7 | note | Inspection Type (Visual, other) - Witness
be7beb94-ad2b-54dd-83f0-38c8f5564a6d | note | Inspection: Key - W
35b64125-bc7b-5da4-be26-97b71b7af86c | note | Inspection: By (Role Key) - SE
bcc30a6b-119d-4743-8a79-baaf6dc3ee43 | checkpoint | 4.10 - Fill Compaction Testing Laboratory
613ffacb-21f8-55a0-ac5a-8f2d6e0c9561 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.12
abf1c975-f467-550d-8803-5f63bbcc3a2f | note | Specification Reference - Water Content, Standard Proctor and Wet Sieve.
87cb7aef-ee1d-547e-ac81-b90003b86845 | note | Acceptance Criteria - N/A
404f0300-be8d-57c5-9ae3-09ef3f08131c | note | Verifying Document - IANZ report
45d7b2e9-2ab1-5bbb-ba2e-47b28b92899d | note | Frequency - WC - 1 test per 400m3 with 2 tests minimum per day, MDD & WS - 1 test per 2000m3
e4b62afa-6a64-517f-bfcf-bfb487b48f5d | note | Inspection Type (Visual, other) - Witness
78e96303-1f07-5a1a-b96e-b20bc84fe4c0 | note | Inspection: Key - W
66ee5b0c-a583-5bca-87d4-fe169198728e | note | Inspection: By (Role Key) - SE
4d840a77-0d83-418d-8eaa-5d3ace198277 | checkpoint | 4.11 - Fill Compaction Testing Site
170c0ce9-da4c-51cd-a656-534cc2598816 | note | Specification Reference - Compaction test by plateau
4cd4ea6f-fd7d-5182-9cb9-7ecd963f4105 | note | Acceptance Criteria - Plateau Testing to determine true MDD value based on site conditions
f435ba24-e53f-5101-81ee-295144d7851c | note | Verifying Document - DNZ Plateau Test work sheet
95c64cd4-0399-5ee6-84c8-fe44e0fe532b | note | Frequency - Daily
05ff474c-f5e3-5368-a1e9-39775e6ad1b0 | note | Inspection Type (Visual, other) - Witness
9df4d291-794f-5154-8fd0-3f6e2da0ae60 | note | Inspection: Key - W
8cd77cf0-88d2-5621-9a62-ae0a6c6560e3 | note | Inspection: By (Role Key) - SE
9bb0e863-25ab-4e2e-a5c8-736f7a3cbf9e | checkpoint | 4.12 - Fill Compaction Testing Site
a0f51fc5-3327-536a-a294-1323489b698c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.10, Project Spec Cl.15.6.12
e70d9530-82db-512d-bb7d-6470d91d214f | note | Specification Reference - NDM and OMC testing of fill material, Shear Vane
15556765-8e6f-5346-b003-a5130be21e1e | note | Acceptance Criteria - Moisture Content: between-2% and +4% of OMC
7fcab2ac-a9ab-5872-b45d-bd68049bbef8 | note | ○ Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95%
a801c928-555b-535f-9716-82c12c5aa57f | note | ○ Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only)
e54e9950-49f6-5033-8c0b-245f5090e787 | note | Verifying Document - NDM Record Sheet, DN-QUA-QC-09 NDM Worksheet, Shear Vane Sheet (Cohesive soil only)
6fb339aa-e367-5272-b3ec-08785b7ada50 | note | Frequency - NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day
017b0e48-efcf-5a5e-bb2b-aa847de2c09d | note | ○ Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only)
d36e4bf3-83f7-5ad9-b4a1-1195d43e9525 | note | Inspection Type (Visual, other) - Witness
479c803f-863e-5ecf-995d-ac9522d1ed37 | note | Inspection: Key - W
91ffb9e9-9267-5718-9b08-82760cad3387 | note | Inspection: By (Role Key) - SE
49dc47d4-4477-45df-98df-0234e7253c87 | checkpoint | 4.13 - Fill Tolerances
40d82a36-02ad-5737-8acb-c456c28f5187 | note | Inspection Point: Quality Control Activity - Project Spec Cl. 15.3.11
9e700a68-8e22-58e3-9974-7d3dfdfa1e95 | note | Specification Reference - Survey of finished surface
e79c980c-87de-5e44-b10b-3236c822d8b2 | note | Acceptance Criteria - Tolerance of +-50mm
447e271e-bca4-5ebb-add8-7fc00e2da9c3 | note | Verifying Document - As-built
bb9bf85e-e97c-59a1-ae14-091787bbd065 | note | Frequency - At Completion
460b02c8-ced0-56fb-9524-2652fccfcaa1 | note | Inspection Type (Visual, other) - Witness
7feba2b6-df9e-5aa3-954c-fc41cf3abc3b | note | Inspection: Key - W
d7211d8d-3c2a-58ce-ac35-6a15b5ea8287 | note | Inspection: By (Role Key) - SE/SV
b9a3e932-94cd-4693-a41e-146bbf0d7650 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
91d48c13-d2f8-45c4-af23-fde24dbb16ad | checkpoint | Inspection Point/ Signature & Date
c5b2747d-ce3f-524a-a1e6-6023b29c528c | date | Date:
db896672-4da5-53f6-9550-09d229e89fb7 | textbox | Customer Requirements Verification Record / Location/ Hold Points
f5dea672-25bd-4897-adf3-d2ef22a81c2d | signoff | Downer Signature
b4397342-998b-4cfc-bc0c-aa011a10cb00 | checklist | DS2681-SH58-ITP-C-015 – Barriers (W-Section) | itp | DS2681-SH58-ITP-C-015 – Barriers (W-Section)
22c96591-dea7-455e-b650-473542926e45 | section | SECTION 4 – IN-PROCESS INSPECTIONS
260258f4-e738-4ad8-aec3-296787ddec7a | checkpoint | 4.1 - Ground beam installation (Pre-Pour)
d6c8f9dc-4ec6-544f-92f5-11f98648c649 | note | Inspection Point: Quality Control Activity - Ground beam installation (Pre-Pour)
278eec01-987a-57a3-8a36-491647e7211f | note | Acceptance Criteria - A concrete pre-pour inspection to be carried out by Engineer to check formwork and reinforced steel (where required), checking dimensions, reo sizes as well as ground preparation.
9604974f-00fe-5726-b753-276007ec6b23 | note | ○ Concrete strength requirement of 30MPa minimum. Specification from NZTA 2014 Technical Memorandum: Road Safety Hardware Series Standard Detail Ground Beam
edde2cab-e0ee-5384-a4e8-e5e94b60c445 | note | Specification Reference - PS Cl24
10aafe94-9e98-5826-8e10-f7a6211212b8 | note | Verifying Document - Pre-pour Inspection Sheet, Concrete Docket, Photos
35dca340-b546-5269-98de-31fb245720e0 | note | Frequency - Prior to every concrete pour
2c0bc421-ed2e-5bfc-8238-bc89c35f905c | note | Inspection Type (Visual, other) - Hold Point
4f1b788e-6d0d-54d8-82e4-909ca77863da | note | Inspection: Key - H
56351287-3c9a-5154-b693-05ecb76af936 | note | Inspection: By - ER
13fd3178-0566-4a56-a8cd-b14d333570ce | signoff | AUTHORITY HOLDPOINT
3fc4f03c-dc94-4f21-b464-c854ab39bb8d | checkpoint | 4.2 - Ground beam installation (Post-Pour)
0c861283-229d-5081-9e78-5473e0ec4790 | note | Inspection Point: Quality Control Activity - Ground beam installation (Post-Pour)
d6bf60ca-d279-52cb-aa92-fd69cd0bcaa8 | note | Acceptance Criteria - Post pour inspeection to check concrete finishes are up to the required specification. No honeycoming. Any defects to be reported to the Engineer with remediation proposal.
04913f40-93c0-5703-b817-06e12c2922dc | note | Specification Reference - PS Cl24
6b0f1d2c-a4c8-5a12-a5f5-454c11207d07 | note | Verifying Document - Post-pour Inspection Sheet, Concrete testing results, Photos
947e5cde-e2a1-5c20-8c69-9cd3eeae1f37 | note | Frequency - After stripping formwork on each concrete pour
5bd310ea-1ec3-526b-839b-a7740a00b7d7 | note | Inspection Type (Visual, other) - Witness Point
2fe3c27d-e902-5574-8ad2-f1ca3b87bf0b | note | Inspection: Key - W
85c271c5-89f6-5dd5-935f-795a9636248e | note | Inspection: By - SE
b67d631c-b921-4d14-89bb-050d327566cd | checkpoint | 4.4 - W-beam positioning behind kerb
021bc717-ea6f-56bd-8775-86062604c039 | note | Inspection Point: Quality Control Activity - W-beam postioning behind kerb
32476581-01ce-5765-8b47-08d9938451ad | note | Acceptance Criteria - Unless detailed in the drawings, where barrier is placed behind a kerb, the face of the barrier is to be no more than 200mm behind the kerb face. Where barrier is placed further than 200mm behind the kerb face this shall be agreed on site with the Engineer prior to installation.
1098442e-5f9b-55d0-8b7d-e484bb68945a | note | Specification Reference - PS Cl22.1.2
6c334316-7edc-5c6e-8c33-d5e9b2f18444 | note | Verifying Document - Engineer Inspection / Measurements Photos
93127c6d-c802-5add-9c4e-73b0812edb0b | note | Frequency - Where Used
bc3cde51-7ebe-5a6b-9040-65eeddeac595 | note | Inspection Type (Visual, other) - Witness Point
6df073e0-cc75-55f5-ac04-56413dcab337 | note | Inspection: Key - W
bec0095e-5f5a-5c0d-8d89-77d64f97f9d9 | note | Inspection: By - SE
8227f627-4a05-4b77-97a8-6e5ee0e844dc | checkpoint | 4.5 - Nesting W-beam barrier
18fabf0f-e868-5f4d-8f58-8aa74ba45e90 | note | Inspection Point: Quality Control Activity - Nesting W-beam barrier
566274ed-eb00-5b48-8a92-830ffc75f062 | note | Acceptance Criteria - Nesting of weak post systems shall be in accordance with manufacturer's instructions.
14c78059-cebd-50f6-bd9a-d90b94f57f78 | note | Specification Reference - PS Cl22.1.7
23213fbe-7fec-56b4-a29f-910ee42408b4 | note | Verifying Document - Photos
b02b1bd2-aff0-5bdc-a14d-45225de33145 | note | Frequency - Where Used
780ce2f2-d606-5aa7-8adb-f46d8d68dd41 | note | Inspection Type (Visual, other) - Witness Point
ba703978-0a42-51d7-8da6-15e74d09fddd | note | Inspection: Key - W
2ab99b72-e14f-5ae5-adb1-ec7412d9a4a9 | note | Inspection: By - SE
df6daf53-b44d-423c-a840-00f9ff50e628 | checkpoint | 4.6 - Barrier Checklists
4783be03-7460-54f0-aa72-25eb2d6d2d71 | note | Inspection Point: Quality Control Activity - Installer Checklist
32501f7b-7677-592d-90fc-c596019d4e9d | note | Acceptance Criteria - An approved barrier installation checklist shall be completed by a person with demonstrable recent experence in barrier installation and signed by the Contractor for each barrier installed and provided to the Engineer within four weeks of installation.
61c9a90c-b447-5859-927b-b16a7234fcdc | note | Specification Reference - PS Cl22.1.6
7932da93-7e89-587d-afa4-8dbbb81abb23 | note | Verifying Document - Installation Checksheet, Photos
b3c4f860-1ceb-5cbe-9c43-3fc3ed023863 | note | Frequency - Per Barrier String
937843ef-f0f2-5a6c-9861-aedcbecd88b8 | note | Inspection Type (Visual, other) - Witness Point
4df711a0-32d6-5f19-907a-6694c26d4149 | note | Inspection: Key - W
29a9ae3f-f7d9-51ca-bc0a-35570c7d851c | note | Inspection: By - SE
1b93c212-3534-4def-80a2-179566ef9481 | checkpoint | 4.7 - Survey
ef1f3160-0e1c-592e-a286-79bd237faf9b | note | Inspection Point: Quality Control Activity - Survey Pick-up
830c0475-8a2d-5234-948e-f84e1ef6c389 | note | Acceptance Criteria - Installed as per the contract drawings
3a628baf-617f-51ec-830e-ed923504c76b | note | Specification Reference - N/A
0d273fda-783e-59e0-87b9-698ed54a5086 | note | Verifying Document - Survey As-Built
6a77bd78-77a4-5cbf-944b-70c6556e6959 | note | Frequency - Per Barrier String
1bdf939f-e386-5b45-95e7-5c7d63d981fc | note | Inspection Type (Visual, other) - Witness Point
ef440001-61b6-5731-853f-5b19deb45caf | note | Inspection: Key - W
2ed920ab-0dcd-552e-867a-f148dc4beb8a | note | Inspection: By - SV
23769390-b34f-4246-8b54-8bc1f86087f9 | checklist | DS2681-SH58-ITP-C-016 – Barriers (Wire Rope) | itp | DS2681-SH58-ITP-C-016 – Barriers (Wire Rope)
8b307aaf-7cfb-439a-985d-b932b268b3ff | section | SECTION 4 – IN-PROCESS INSPECTIONS
895f9fff-59be-425c-97f9-bdfba1d5dc05 | checkpoint | 4.1 - Terminal End (Pre-Pour)
c75cd18a-23c7-5556-b56b-69dac0a336ea | note | Inspection Point: Quality Control Activity - Terminal End (Pre-Pour)
7f17b22b-fa7f-587b-8919-431461f8b314 | note | Acceptance Criteria - A concrete pre-pour inspection to be carried out with the Engineer to check dimensions of trench, formwork and reinforcing, anchor points and ground preparation.
857a3ce8-ae66-5b9f-ab6c-874904e0cbb9 | note | ○ Concrete strength requirement of 30MPa minimum.
21c385be-d707-5e5a-a8fa-13be941b2a2c | note | Specification Reference - PS Cl24
02d22036-d50d-534f-9c0b-367f58dcb969 | note | Verifying Document - Pre-pour Inspection Sheet, Concrete Docket, Photos
35ce600c-8124-5c38-8368-dc15b2f01e40 | note | Frequency - Prior to every concrete pour
a07f2605-ba57-5bb9-afc8-406570c4f06d | note | Inspection Type (Visual, other) - Hold Point
f1e51a4c-dffa-5f3a-a860-9ada1f916cbb | note | Inspection: Key - H
d4dbc312-9140-5d25-aa71-e6f96de5a315 | note | Inspection: By - ER
e4782dd6-e7fa-4e4e-b98b-dde1dc5af7a4 | signoff | AUTHORITY HOLDPOINT
81878c4c-8b02-409b-bcf1-218e90e2a316 | checkpoint | 4.2 - Terminal End (Post-Pour)
25da25fe-d19c-5d24-b1e0-9dfac0b8a408 | note | Inspection Point: Quality Control Activity - Terminal End (Post-Pour)
2c3df04e-3b86-5a8e-8706-6863d12387cd | note | Acceptance Criteria - Post pour inspeection to check top surface finish and ensure anchor points are in place
c353edd7-15eb-5eb0-a14c-5de77bb0d653 | note | Specification Reference - PS Cl24
cf5e1b64-2b00-557e-8f54-e6645f4212dc | note | Verifying Document - Post-pour Inspection Sheet, Concrete testing results, Photos
2c9266d4-d60d-5dc5-b0a2-e39a07aecbf2 | note | Frequency - After stripping formwork on every concrete pour
7a5dd6df-5848-531a-95af-60e9cc0c2a4a | note | Inspection Type (Visual, other) - Witness Point
a543e02e-5f68-528f-8e9f-63010ef1a9af | note | Inspection: Key - W
da797c42-7f46-50e4-b7c4-2cd1ac88a9b2 | note | Inspection: By - SE
b857356f-f49b-4dec-923c-474d76a8c1ae | checkpoint | 4.3 - Barrier Checklists
e0891539-68e2-5608-95df-88d3e0df155a | note | Inspection Point: Quality Control Activity - Installer Checklist
1583aed8-20f9-56ae-be7f-b8680ab1a56e | note | Acceptance Criteria - An approved barrier installation checklist shall be completed and signed by the Contractor for each barrier installed and provided to the Engineer within four weeks of installation.
1e8541a3-869d-5f57-b944-eb5fc04fba10 | note | Specification Reference - PS Cl22.1.6
2cfdd7ae-1d2d-508b-9396-9b6e18d50045 | note | Verifying Document - Installation Checksheet
c8e0d1db-23e7-5b18-b2a3-47074f2b65db | note | Frequency - Per Barrier String
75f71fd8-7d59-5b36-928e-d763496e0948 | note | Inspection Type (Visual, other) - Witness Point
6743524d-6185-5e95-8dee-bec77951c1d6 | note | Inspection: Key - W
66d16be9-4a4b-5f46-b942-e7126c7d282c | note | Inspection: By - SE
1d7b6e18-4483-4b6e-9466-8a58dff233be | checkpoint | 4.4 - Survey
981a7b23-d116-51ec-8b8f-3bf7b46fbe6a | note | Inspection Point: Quality Control Activity - Survey Pick-up
f2ad8a6a-f38b-51b3-955d-16b9d4b892cc | note | Acceptance Criteria - Installed as per the contract drawings
3210996f-9ccc-5e8f-af9b-e3200bcbf716 | note | Specification Reference - N/A
61d59f6b-8687-532a-91e0-39fcecbd5f7a | note | Verifying Document - Survey As-Built
c178f6f6-1a88-5b4c-bf32-d0ede7e17bbe | note | Frequency - Per Barrier String
3f3bfb59-864c-5fc8-aeb9-aed4f06aa3e9 | note | Inspection Type (Visual, other) - Witness Point
eaa014e5-5462-56c7-9856-21d40e0a0f0a | note | Inspection: Key - W
35ec1067-b2a1-5a48-9a73-7b18eac9e8bb | note | Inspection: By - SV
74365bc3-cd1c-4bf5-ad92-dc3caf907c9f | checklist | DS2681-SH58-ITP-M-002 – Barrier Materials | itp | DS2681-SH58-ITP-M-002 – Barrier Materials
471a096f-65e5-46a0-9d8c-6f5778509964 | section | SECTION 3 – RECEIVING INSPECTIONS
e484edf5-e8f1-4831-afa2-aa0bb258bd6e | checkpoint | 3.1 - Barrier materials (Standard W-Section)
db79f351-9494-5982-84b0-0b96406407f1 | note | Inspection Point: Quality Control Activity - Barrier materials (Standard W-Section)
13b8cade-0bef-5b3f-bcff-7acb0271dcf2 | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
8b163a3c-226c-5985-aa27-787ebb0e7369 | note | ○ W-section to comply with MASH TL-3
232c7304-09dc-5937-92a6-ceeb61b49352 | note | Specification Reference - PS Cl 22.1.1 NZTA M23
fbc1629b-0857-5885-bd0a-2ffcbcdbdea1 | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
8ed1b730-66ad-57a0-a334-fe8a05efeb6c | note | Inspection: Key - W
a3312eff-23cb-5b0e-8c0b-35df136e1363 | note | Inspection: By - SE
0992ddb7-b8f9-476c-8b0d-9e51b9095280 | checkpoint | 3.2 - Barrier materials (End Terminals W-Section)
97dc9cdc-3622-59c1-b262-67e7feebb0d5 | note | Inspection Point: Quality Control Activity - Barrier materials (End Terminals W-Section)
23f3d615-2291-545f-9b61-cfe7b1c2aabd | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
660ba2d5-4bd3-5927-84e5-7738a4489213 | note | ○ Leading End Terminals to comply with MASH TL-3
520643f6-0cc8-5406-9561-049be3cb3e65 | note | ○ Trailing End Terminals to comply with MASH TL-3
4ef63b43-90f0-58cd-9188-8fb6e0edd2af | note | Specification Reference - PS Cl 22.1.4 NZTA M23
849e27ca-c8a8-52f0-b52a-b45b8ba6867b | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
a6948697-3b35-5d71-8e0e-17108a527a18 | note | Inspection: Key - W
e9374a95-696b-532c-b12a-ea52e324152f | note | Inspection: By - SE
7452e330-8449-4b4e-a175-9583779d5d58 | checkpoint | 3.3 - Ground Beam: Concrete Mix Design
32801ec8-21f2-5480-b9af-95ad01ec8f4f | note | Inspection Point: Quality Control Activity - Prior to works
703a732f-3243-5872-adbf-c936b014dc17 | note | Acceptance Criteria - Contractor to provide Concrete Design Mix information to the Engineer. 30MPa Mix
053295dc-d926-54a7-b890-7a75e9f9f4b4 | note | Specification Reference - PS Section 24 Per Manufacturer Specifications
f2db903d-5252-58f7-a44a-27a39eaaf44e | note | Verifying Document - Mix Design
76638934-6c9e-5e35-9a6d-7018f5465526 | note | Inspection: Key - H
2eb135c1-191b-50c9-a3bb-bc5361010e18 | note | Inspection: By - ER
6504a965-f15a-4e72-97a6-b8f7b0cc347c | signoff | AUTHORITY HOLDPOINT
4bd47eb0-06c8-433c-9ab7-63b825aab5ff | checkpoint | 3.4 - Barrier materials (Thrie Beam)
f0521525-f947-50af-8cdb-63b27d7a73a8 | note | Inspection Point: Quality Control Activity - Barrier materials (Thrie Beam)
539e307b-bea8-5eb6-bdb5-8b7b21afd893 | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
5c22bd5d-e0de-5c01-a734-9bb51178e5b7 | note | Specification Reference - PS Cl 22.1.1 NZTA M23
6370f7cf-c2dc-5d00-915e-a0c580fb81e9 | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
45e26742-1ab8-5575-9d5d-cff308f93976 | note | Inspection: Key - W
dcdf5167-58c0-54af-89da-8801a2e6cb11 | note | Inspection: By - SE
2a50eba3-8c21-40e0-88ac-cc1d768a0100 | checkpoint | 3.4 - Barrier materials (Thrie Beam Transitions)
615cd999-83c1-5334-98b4-3c4174f8870c | note | Inspection Point: Quality Control Activity - Barrier materials (Thrie Beam Transitions)
c1cb9cc2-309e-52ae-86fe-8c82f6a5894f | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
950f113e-e503-5e98-9b8c-d7882890691d | note | Specification Reference - PS Cl 22.1.3 NZTA M23
b0e8c93c-67d9-58ab-8eb3-2f46c813dc5e | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
84eb2e97-084b-566e-8c09-04f1893e03b2 | note | Inspection: Key - W
fdeecb55-0319-5daa-8ec3-c1258138f04f | note | Inspection: By - SE
e68dc3f2-6ac7-4c85-8f30-5d2b948f07b5 | checkpoint | 3.5 - Barrier materials (Wire Rope)
94651e0c-127f-58e5-b829-5e7fcf96de64 | note | Inspection Point: Quality Control Activity - Barrier materials (Wire Rope)
730f0aaf-e24c-5696-ac14-1b93bcdd5dc2 | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
a1b40703-529b-5e87-9243-d87c9ff6f02a | note | ○ Wire Rope to comply with MASH TL-4.
03efe69b-2f77-5e33-a3ab-e537c9002a5c | note | Specification Reference - PS Cl 22.1.1/22.1.8 NZTA M23
2fbc2c9e-82d7-52fb-ab8c-02f343ec424c | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
9c5f3090-0cdb-5697-9720-3527f0a8c504 | note | Inspection: Key - W
c10d80e7-eb24-5417-b43e-f2d7b03f3d29 | note | Inspection: By - SE
123ac222-293e-4a1c-98c9-5e8dd681f18b | checkpoint | 3.6 - Terminal End: Concrete Mix Design
d04fe5f4-d8de-5d58-84a8-8febc400e946 | note | Inspection Point: Quality Control Activity - Prior to works
8eb8ecd6-d25b-58fa-ac93-8f9d1f1d1842 | note | Acceptance Criteria - Contractor to provide Concrete Design Mix information to the Engineer. 30MPa Mix
35f1dc3d-f242-52de-8657-65a33219c1fd | note | Specification Reference - PS Section 24 Per Manufacturer Specifications
bd0ad8ce-2923-5afa-8991-ea5429c5d267 | note | Verifying Document - Mix Design
0d4b8669-296f-589d-8373-0c7f5a9bca39 | note | Inspection: Key - H
44b70f7d-ef25-5251-a350-95fea634f58b | note | Inspection: By - ER
59afb7f2-432d-4da9-adcf-80a4a2dbf5b9 | signoff | AUTHORITY HOLDPOINT
3e057d11-4fde-4940-ad40-044528697159 | checklist | DS2681-SH58-ITP-M-018 Earthworks Materials | itp | DS2681-SH58-ITP-M-018 Earthworks Materials
58292683-ff6e-4b9c-a15c-e67e34c450e1 | section | SECTION 3 – RECEIVING INSPECTIONS
5e44d725-1630-472f-bd79-01ba92b790a4 | checkpoint | 3.1 - Pre-Construction Survey
b9b7905e-c23e-5cdb-a8f6-635d63445278 | note | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
31ff9d67-1ead-5222-b63c-29ab88a7560f | note | Specification Reference - Drone/GPS
c203eb51-f0a5-5ce8-b6d6-c0b614115687 | note | Acceptance Criteria - Receipt of survey by engineer
98bb493b-d4dd-57e1-a7c7-e83d973342b7 | note | Verifying Document - Topo Survey
0ee5708c-0c7f-5f17-bef2-aae0829e82b5 | note | Frequency - Prior to works - each lot
5647ce7f-29a9-5d0b-b62e-ca4bdc8de760 | note | Inspection Type (Visual, other) - Witness
c35d10d2-94d4-5b0c-9150-77ec04395548 | note | Inspection: Key - W
f9cec978-8728-5a00-96f6-234faab89a65 | note | Inspection: By (Role Key) - SPE & SV
fb6a885f-bc2e-44b8-bf18-5b5936d5de9e | checkpoint | 3.2 - Use of Flighty's Mound material for fill
83e9871d-9b43-5302-9dc6-d7ad045e5cda | note | Inspection Point: Quality Control Activity - N/A
19512bdd-e48b-51dc-89c4-ddfb0de869f2 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
9a4a79a1-2839-5ff4-a126-b0d3452930bf | note | Acceptance Criteria - Confirmation of use
34debe48-a486-546e-904b-6e8014a5a664 | note | Verifying Document - Mail Confirmation from Stantec Representative
6fac3a31-1810-5553-85f6-764a647fa647 | note | Frequency - Start of Earthowrks
5cfd1f51-236d-5777-9593-c8d3aca01c76 | note | Inspection Type (Visual, other) - Hold Point (where required)
9dcd6d82-1c02-5c55-8f6b-61d8d9ced0c4 | note | Inspection: Key - H
443625b6-2d56-5441-8eb8-c89c4b793db6 | note | Inspection: By (Role Key) - ER
83210422-9963-4264-bb3a-721408b0dc84 | signoff | AUTHORITY HOLDPOINT
f57b4c64-1650-4198-bbff-6b3f97bf845d | checkpoint | 3.3 - Use of Moonshine Rd Cut material to be used for fill
23f8223e-8878-53d3-a0b4-46e2e20161d7 | note | Inspection Point: Quality Control Activity - N/A
09355543-d1e1-5825-a9fc-1daeb67f5fa1 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
0c975a8c-c57d-505d-90a6-9cef5f592b6e | note | Acceptance Criteria - Confirmation of use
afb5a1e2-9d9b-593a-af56-f933dbe7038a | note | Verifying Document - Mail Confirmation from Stantec Representative
263b8a98-db66-5c08-91b7-43ddb035d10b | note | Frequency - Start of Earthowrks
ff7f016b-96ef-54bc-b0c7-6e9de2b2743a | note | Inspection Type (Visual, other) - Hold Point (where required)
e959f38a-476c-594c-bad8-8c5109c06a9d | note | Inspection: Key - H
5606d63e-4aa1-5450-9549-55346f1476fd | note | Inspection: By (Role Key) - ER
138b6ec4-b6f6-4d1f-83df-1d656388dcf6 | signoff | AUTHORITY HOLDPOINT
f8ec3898-e7a6-4d2e-9c03-9042496922bf | checkpoint | 3.4 - AP65 Material acceptance
12b60150-0d1a-5092-b38b-a943450949d2 | note | Inspection Point: Quality Control Activity - Specification Cl 17.1.11
8ff19d59-64b5-5ed9-87fc-a16e9060919e | note | Specification Reference - Material Testing and Compliance
f1bd496b-69e9-5504-9056-4bf90fb73070 | note | Acceptance Criteria - IANZ Testing
7b731e0d-5131-5a74-bf8c-b1abebe2a40d | note | Verifying Document - Testing report
3a9226aa-7744-5c32-b720-be008fc9a112 | note | Frequency - Every 1000m3 or change in material source
035aa4a9-d40b-570e-8c9c-72f347b723f5 | note | Inspection Type (Visual, other) - Hold Point
d6f21f79-9c71-50b0-a284-291368871795 | note | Inspection: Key - H
7619a487-0163-5a7f-8316-c16039c2ed5f | note | Inspection: By (Role Key) - ER
e36c2d94-b8f8-442b-b6fc-196ba4557a0c | signoff | AUTHORITY HOLDPOINT
0d369293-c495-45e7-8aba-cda22b54a1e0 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
1588c0dc-9eea-4e9a-8789-a22b28d2b3c1 | checkpoint | Inspection Point/ Signature & Date
f07723a8-9764-5ffd-b451-4922c8f1ca26 | date | Date:
44f8fdc4-4407-5786-b498-e4fe329d162c | textbox | Customer Requirements Verification Record / Location/ Hold Points
72ab6684-5339-492b-a21c-93214725af5a | signoff | Downer Signature
1d7c48f8-a084-4c68-a0b7-6b33cd20cf0c | checklist | ITP-001 RC In-Situ | itp | ITP-001 RC In-Situ
9a5137c8-bbad-47b0-801e-e36c101a42fc | section | SECTION 2 – IN-PROCESS INSPECTIONS
f052922d-835e-46a9-b974-670495f07f48 | checkpoint | 2.01 - Reinforcing & Formwork - Cover
f831e5ff-31dc-5294-be64-cc87dce85eb3 | note | Inspection Point: Quality Control Activity - Reinforcing cover to formwork
a8e8c281-1b71-5234-a9f4-a8883055930b | note | Specification Reference - PS Cl. 24.1.13 Table 20.2.2
35196041-e32b-53ba-81c6-56f23da889a3 | note | Acceptance Criteria - TABLE 20.2.2: CONCRETE EXPOSURE CLASSIFICATION — MINIMUM COVER FOR 100 YEAR DESIGN LIFE
a190a936-06ba-5313-b937-1cd85ec6c55c | note | — — — — — — — — — — —
52d7205f-f3cc-5a58-912d-0f6aff2fd37b | note | Exposure Classification ¦¦ Specified Compressive Strength (f'c) — 30 MPa, 40 MPa, 50 MPa
c32f8e7c-3ffb-5f59-8ffe-20da29744627 | note | — — — — — — — — — — —
dfb31e03-17a5-567d-bc94-468cda314714 | note | A2 ¦¦ 40mm, 35mm, 35mm
058f6209-a88d-5cb3-9acb-93b088f90983 | note | B1 ¦¦ 50mm, 40mm, 35mm
6b0ed5c3-cadc-58b6-b764-2f52ddc5194b | note | B2 ¦¦ 65mm, 50mm, 40mm
609d8c10-5c7e-5f16-8e4e-847fbdee0f7f | note | — — — — — — — — — — —
aac68a80-f9d7-5eee-ad79-64b0521fc0b9 | note | Verifying Document - Pre-Pour Inspection
0923bb71-288d-5179-83a2-399c7fb7e68c | note | Frequency - Per Pour
cd6d4f02-dc86-553d-a2a4-84ec784a15b7 | note | Inspection Type (Visual, other) - Documentation
0acfc478-fa65-53a8-981b-afd7fd145bde | note | Inspection: Key - H
84407da7-d02a-57c1-8778-2e49b4ec56ff | note | Inspection: By (Role Key) - ER
d73ba83c-e18e-4d8e-9662-eeb45222170a | signoff | AUTHORITY HOLDPOINT
f834b1bf-38aa-467e-8f4e-71f18cb33d5c | checkpoint | 2.02 - Reinforcing & Formwork - Reo placement and bar bending
288e0887-38d2-5c00-a11b-8cd881501e40 | note | Inspection Point: Quality Control Activity - Reo placement and bar bending
85d48625-21bf-5556-9a1c-1e89f4aabb03 | note | Specification Reference - Ensure reinforcing bends comform to NZ standards and project specifications
eec091b5-c646-54fb-a813-97f417ff9ef5 | note | Acceptance Criteria - Bars shall be cut and bent in accordance with NZS 3109 to the shapes indictated in the drawings and placed correctly in the arrangement shown;
6fe1a1db-a5e3-5e28-ab11-e030be082539 | note | ○ Unless noted on drawings reinforcing bars to be bent to min bend diameters outlined in NZS3101;
9ce88da7-5ec1-5101-985b-db4f674b7050 | note | ○ Heat bending of bars is prohibited
ff27e326-1dec-5c7e-a3c1-b34e71e9b348 | note | Verifying Document - Pre-Pour Inspection, Bar bending schedule
4e3c32e5-e04d-55e8-a73c-dc425d61cf34 | note | Frequency - Per Pour
581b8cef-e9b3-518d-9a13-65d540afeba9 | note | Inspection Type (Visual, other) - Documentation
e802cce5-d6f8-5e14-b8fe-97ac6f9a777f | note | Inspection: Key - H
2b0f94d8-7442-5b49-8356-9899c55176f6 | note | Inspection: By (Role Key) - ER
7176dfd3-727c-4918-bd52-148ef5e0802b | signoff | AUTHORITY HOLDPOINT
41b0961f-2c23-4f5b-86a0-d0d37fefe5ce | checkpoint | 2.03 - Reinforcing & Formwork - Formwork
6cf75c48-a053-53fa-82a4-ea87a83f82ad | note | Inspection Point: Quality Control Activity - Formwork
a506504c-cfe3-50d6-846d-ce7fc7a2367b | note | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109, PS Cl. 24.1.16
5234e75a-35be-5b8b-8fa7-3fa17223c9fe | note | Acceptance Criteria - Formwork to be constructed so that finished concrete will be to the shape, lines and levels shown on the drawings;
28e85dbf-a585-5b57-ab12-76735f5938a5 | note | ○ All forms shall be designed such that exposed concrete edges have a min 20mm chamfer unless otherwise indicated on the drawing;
0f4db29c-ba64-5869-a53b-c6119a808a61 | note | ○ Interior surfaces of the forms shall be treated with a release agent. Any reinforcement in contact with the release agent shall be cleaned thoroughly;
2be3c2b5-ae61-56e0-b412-6cb4c5e478f3 | note | ○ Forms to be sufficiently watertight to prevent grout loss
ea76fdab-d189-5c43-8e46-3e661264f5b7 | note | Verifying Document - Pre-Pour Inspection
c5c85d18-ed4e-5e34-9373-cb0eab0bb5e7 | note | Frequency - Per Pour
7f70c6c6-1547-5021-ba97-c176b4680c6c | note | Inspection Type (Visual, other) - Documentation
ff0a3100-d6ee-53df-ab54-33799e01f602 | note | Inspection: Key - H
d4ce15e3-fe9d-524e-937a-388d00fbca8f | note | Inspection: By (Role Key) - ER
8beaafab-e89d-4fb1-b947-78d146e0d7ce | signoff | AUTHORITY HOLDPOINT
59ba7d3e-4d0a-4528-8a38-301f2c584ed1 | checkpoint | 2.04 - Formwork and Pour - Finishes
87f019ac-dd38-5b6f-90f7-5451048f1012 | note | Inspection Point: Quality Control Activity - Formwork and Pour
8a90af33-ab71-5d15-8a88-644d168488e6 | note | Specification Reference - PS Cl. 24.1.16
8c59ef89-c969-5f9d-b31b-5048c4e4a637 | note | Acceptance Criteria -
f5957b3e-6fc0-5cda-99b0-6a5320d15803 | note | Verifying Document - Photo & Pre-pour Inspection
ed11c89e-acb3-55d8-8336-fe094ecf47bb | note | Frequency - Per Visible Surface
a6aa407b-6b48-5f71-8e61-a700288d479d | note | Inspection Type (Visual, other) - Documentation
6cbb0b93-ad32-530c-a153-f5702a3603e2 | note | Inspection: Key - W
aaa2b9d2-29ef-549d-8acc-186441d98a9e | note | Inspection: By (Role Key) - SE
820a48e1-eea0-4ee9-8d09-2d577fcc9510 | checkpoint | 2.05 - Concrete Pour
fcb9a19c-6ff0-5e4d-9ff3-0cf0bf79a58a | note | Inspection Point: Quality Control Activity - Concrete Placement
672d9de1-1f28-5bce-8638-b5edb564e557 | note | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing
4044aa86-b691-549b-b215-487bccec8c94 | note | Acceptance Criteria - Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer.
4cf64a08-84a4-554c-92e0-fa2306aaf6a1 | note | ○ Concreting to be a continous operation between ends of members and/or properly formed construction joints.
e79ee082-239f-589f-a4be-f9923ec26c38 | note | ○ Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m.
c794e989-37dd-50c9-8b7e-544a065c4c85 | note | Verifying Document - Pre-Pour Inspection
6c06b881-a9a2-5d13-aa58-6ac61eec75b0 | note | Frequency - Per Pour
4caea056-09ad-5291-8a82-1c0566db7c90 | note | Inspection Type (Visual, other) - Documentation
40a28413-2758-5395-b0ce-4ac8813cb1cc | note | Inspection: Key - W
81588555-43ab-5dc3-a0b2-a11a54bc249a | note | Inspection: By (Role Key) - SE
8d6b717f-5893-41b0-a1ce-ead160f21c88 | checkpoint | 2.06 - Concrete Pour
b7a0c85b-7907-5b6b-b4ac-25579f1912fa | note | Inspection Point: Quality Control Activity - Concrete Test Cylinders
99b5627e-c6d0-5235-8310-fd95e412f394 | note | Specification Reference - PS Cl.24.1.14
267d7096-3164-54a4-8455-30362e8978cb | note | Acceptance Criteria - A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days.
7d9c4a15-37b6-5833-9249-718733c96fcc | note | ○ Strength of concrete = Dependent on Mix Design.
3074f9ae-642e-5cfe-958c-e8a88cf5fa20 | note | Verifying Document - Lab Report
87fdafc6-3e77-5fde-a2fe-48a74672d3bb | note | Frequency - Per batch
8dd8e531-dd1a-59b4-ba96-f02d5878871b | note | Inspection Type (Visual, other) - Report
72467d16-5639-55a4-a6f9-36583ea2a7fd | note | Inspection: Key - W
df3653b6-2985-5885-a99d-66d83e75dbfd | note | Inspection: By (Role Key) - SE
50f153ad-c03b-4659-abd1-f45626cbbd21 | checkpoint | 2.07 - Concrete Pour
6dcd202d-4cce-5688-8398-d5759357353c | note | Inspection Point: Quality Control Activity - Approved Concrete Mix Design
64e0cf71-3486-5106-95d6-20a4ccbfb3dd | note | Specification Reference - PS Cl 24.1.3
56997b59-1d32-5b56-998a-ebb6ee49b357 | note | Acceptance Criteria - Confirm correct mix design brought to site
7b3d2d8b-b19b-5bd2-8dec-5747148afd02 | note | Concrete Docket Showing:
9163bb08-6eba-5b29-b8ff-e211e3e6849f | note | ○ Mix Design Item Code
2b2c60cc-462b-5d9c-99a1-0fb900884bb2 | note | ○ 28 day specified strength = 45MPa
9fb569f2-5e8e-5afb-bdd5-19aa44019328 | note | ○ Concrete placement method that the mix was designed for - Pump Mix
f27b8797-fd30-5905-95b5-f1e558e64739 | note | ○ Type of supplementary cementitious materials (if used);
ffdb9a9b-2ee1-5fcc-9d4c-d72037071e9e | note | ○ Slump (target and actual slump when measured);
0217ddf2-3868-5f70-9cc6-93113eec0225 | note | ○ Order and Delivery Quantity
83aeec74-c594-5873-a4df-f917ed1aa733 | note | ○ Load Time out of plant
4e2f4bde-e0dd-5558-a987-b815a3f8a260 | note | ○ To site time
1099e568-6e7c-5506-8edb-05fa9ef53a37 | note | ○ Unload Time
08ce4c8e-461e-5f0d-aa77-82fd0d713861 | note | ○ Associated Products e.g. cement and additives
5df2e309-6381-5b59-9c9a-e714d95f51e5 | note | Verifying Document - Concrete Docket
de0b3cf9-c0bf-5360-8172-1919bf9bdb9f | note | Frequency - Each truckload
c5713675-7233-5ba1-8ee9-7a71ccb932f2 | note | Inspection Type (Visual, other) - Documentation
d8d4ebd0-ee8c-5745-9e34-9000e710a5b8 | note | Inspection: Key - W
852729b8-49ca-5707-a0ea-1d0a551c1224 | note | Inspection: By (Role Key) - SE
2a5c2fef-d00f-498f-85a6-2f32f3d1251e | checkpoint | 2.08 - Concrete Pour (1)
dba1c30f-4306-5365-8cc4-09ca8b1b1147 | note | Inspection Point: Quality Control Activity - Slump Test
a52350be-1ac1-5ea9-b657-d59e38f15601 | note | Specification Reference - PS Table 9.1
f9686b1a-dcc8-593c-a390-3f5230dec325 | note | Acceptance Criteria - Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm.
82b64d94-ba23-53a9-97e5-830892016019 | note | Slump test tolerances:
6c7f7c5a-d110-53dd-89f0-b724ad37874f | note | — — — — — — — — — — —
918464ea-6afc-5999-adc3-325aabd71d59 | note | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
9098a3ae-4ad8-5570-84d4-a29b6fd3b329 | note | — — — — — — — — — — —
8ee8577f-053f-58bd-81f5-3b7eb851c442 | note | 60 or less ¦¦ ±20
e93d9376-61f0-580e-a85c-a6bca1ba5bab | note | 70 - 110 ¦¦ ±30
772767f1-3d3d-5dce-8f54-1ff49e20dc56 | note | Greater than 110 ¦¦ ±40
18e2b044-3901-5de4-aac2-46cb4bf55754 | note | — — — — — — — — — — —
59a994c0-e540-5279-bd80-6fbbbf3b792d | note | Verifying Document - Visual/Photos
d4e8ca20-6dc9-58bd-beb2-0772727b0c20 | note | Frequency - Each truckload
7ed7ef57-63b3-508c-a18d-beb550c21583 | note | Inspection Type (Visual, other) - Test
ad878cf2-9ba9-51c1-8b3c-0b05d6885d6e | note | Inspection: Key - W
2afa7e65-950d-581e-8f83-a3161f4dac65 | note | Inspection: By (Role Key) - SE
2f8b3ac2-d02a-4951-80d4-1ca12497af27 | checkpoint | 2.08 - Concrete Pour (2)
69631847-9c9e-5d6c-8ef5-a0aa6dea4ad5 | note | Inspection Point: Quality Control Activity - Time Limits
fca06a29-903e-530c-924d-3b158a7ca842 | note | Specification Reference - PS Cl 24.1.17
9b332ec9-7e20-5742-a0a5-64354a4015d9 | note | Acceptance Criteria - Incorporated in the works within 90minutes of batching.
9cc994d2-d619-5fae-8a7e-71cffff00958 | note | ○ Incorporated in the works within 30minutes of discharge from concrete truck/agitator
ad254525-6ef0-5d18-a0df-d672e2abd676 | note | Verifying Document - Dockets & pour sheet
6c299560-b4f0-5e91-bb63-ded2ef7eb88c | note | Frequency - Each truckload
102c195b-857c-53ed-a72d-479eb7daf0ed | note | Inspection Type (Visual, other) - Dockets
a5b3aade-2499-5cbe-8b57-cd0fac3583c3 | note | Inspection: Key - W
b961ef7a-792f-5a1c-8ca0-bf40d0742ab6 | note | Inspection: By (Role Key) - SE
630bd1f5-c3ad-4677-8b96-4c23bc2b9351 | checkpoint | 2.09 - Concrete Pour
2a2d3fa1-9081-53ec-b707-46f4b1af0d7b | note | Inspection Point: Quality Control Activity - Concrete Vibration
68095e1e-3e69-5d1f-bb18-af1bfe16e1dd | note | Specification Reference - Clause 7.6 of NZS 3109
a5b0e28d-9523-5e93-9e3f-031ede5828e1 | note | Acceptance Criteria - All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: -
db3433db-172e-5247-83d5-f5fba579d980 | note | ○ All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured.
26a959f0-7095-5d3a-aed7-8f83b8f2ce8b | note | Verifying Document - Visual/Photos
b5195e1d-2285-548c-9cf7-421c298e1788 | note | Frequency - Per Pour
48fa90bf-941b-5d0d-8ad1-4d1253a3f810 | note | Inspection Type (Visual, other) - Visual
10f8ab5a-074f-52c4-9f36-82a3a0468ddc | note | Inspection: Key - W
38b5f3e6-52c7-55f8-a4ee-a91922208de7 | note | Inspection: By (Role Key) - SE
21d324b9-f40e-4be9-876b-13f5724bc88a | checkpoint | 2.10 - Post Concrete Works
810ca072-3d5c-5fc5-9908-41708e859328 | note | Inspection Point: Quality Control Activity - Curing
5cff1ff6-5d68-5865-ab9b-8cc6e8acc3d9 | note | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109
ca3ed8a9-a831-5329-b83d-3cab2bb6d651 | note | Acceptance Criteria - Concrete to be cured for min 3 days;
97f4509e-9985-53c6-8c30-0a975ed6c684 | note | Verifying Document - Pre-Pour Inspection
69a5d4b7-4494-59ad-9039-5b8ae328343a | note | Frequency - Per Pour
12b89d33-a80e-5559-b53f-b0745da55839 | note | Inspection Type (Visual, other) - Documentation
08a06ac7-d099-5ac8-bf10-6a0a68bbec7f | note | Inspection: Key - W
b8d5e833-b8a7-5216-b4d0-f467b7e67157 | note | Inspection: By (Role Key) - SE
71c9dfa8-1139-491a-ab2d-c153a1b42cfd | section | SECTION 3 – FINAL INSPECTION AND HANDOVER
47e58792-ef08-4ecd-8c83-2034474b2634 | checkpoint | 3.1 - Survey As-built
8f61b2bc-c062-583d-8869-2ce746151367 | note | Inspection Point: Quality Control Activity - Survey as-built
0b7ee739-3ccf-52f7-a5af-c078cc54b183 | note | Specification Reference - Specification Cl 26.4 & AS2159 (Page 167)
fbc100a3-b630-596e-b085-c2602277d33f | note | Acceptance Criteria - As-built survey CAD File
18c3541d-44c9-5cfb-aa39-38216065d0ee | note | Verifying Document - As-built survey CAD File
ebc0df53-b3e9-5904-8787-76a9fcec5aa1 | note | Inspection Type (Visual, other) - Documentation
c1184332-1c24-5a1b-87aa-48b2fbae9695 | note | Inspection: Key - C
10e9b802-6d65-579b-a385-8fcf4a3ddf00 | note | Inspection: By (Role Key) - SE/ER/SV
608836c6-d580-4f07-bb61-5452dcef50e4 | checkpoint | Inspection Point/ Signature & Date
052dfe16-b9a5-5211-a7e5-3c3d2601c7ec | date | Date:
e7a27068-7764-5ad4-8f35-403b7aae59dd | textbox | Customer Requirements Verification Record / Location/ Hold Points
2c0a8af2-57ab-4160-b432-d3bb383f6a4b | signoff | Downer Signature
22c4a63c-dfe5-4c5b-8872-81e9b4a3c37b | checklist | Ω (DEPRECATED) ITP-0002 Earthworks Cut | itp | ITP-002 Earthworks Cut
58292683-ff6e-4b9c-a15c-e67e34c450e1 | section | SECTION 3 – RECEIVING INSPECTIONS
5e44d725-1630-472f-bd79-01ba92b790a4 | checkpoint | 3.1 - Pre-Construction Survey
b9b7905e-c23e-5cdb-a8f6-635d63445278 | note | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
31ff9d67-1ead-5222-b63c-29ab88a7560f | note | Specification Reference - Drone/GPS
c203eb51-f0a5-5ce8-b6d6-c0b614115687 | note | Acceptance Criteria - Receipt of survey by engineer
98bb493b-d4dd-57e1-a7c7-e83d973342b7 | note | Verifying Document - Topo Survey
0ee5708c-0c7f-5f17-bef2-aae0829e82b5 | note | Frequency - Prior to works - each lot
5647ce7f-29a9-5d0b-b62e-ca4bdc8de760 | note | Inspection Type (Visual, other) - Witness
c35d10d2-94d4-5b0c-9150-77ec04395548 | note | Inspection: Key - W
f9cec978-8728-5a00-96f6-234faab89a65 | note | Inspection: By (Role Key) - SPE & SV
67451a6a-8cea-4ef4-a602-3d151731a5f4 | section | SECTION 4 – IN-PROCESS INSPECTIONS
eb5fd506-7948-4670-96c6-7831c5fafefd | checkpoint | 4.1 - Topsoil Depth Checks
de3d5445-3307-5b23-8aba-28f82720e2d1 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
44f07abe-85b7-54db-b372-d03d9a585c2c | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
a4de364f-08bf-5b9c-b022-6dc85551c8d9 | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
5510836b-ae61-540a-b704-85c3a5a6bfe6 | note | Verifying Document - Site Photos, Record Sheet
4103d90f-e4e8-5da3-82b6-0ff867bb7135 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2eb5b3dc-7fbe-5392-8414-62b6bcdc5cf3 | note | Inspection Type (Visual, other) - Witness
9e0530ad-9dea-5be2-8d73-2a9795b48e4e | note | Inspection: Key - W
d4639d9a-6767-5269-beb3-1215691074e9 | note | Inspection: By (Role Key) - SE
7f30c528-f201-40dc-a527-ab421a6f883e | checkpoint | 4.2 - Hazardous & Classified Soils
a664ce29-a8e5-5d63-bf17-014a35d000d3 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
f27256d6-4592-5d4e-b73e-a3f74a51ddcb | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
3936fc1e-e1d7-59bf-809a-00f5e6081b10 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
ca6b4c12-6d5d-5ba8-9c78-a9d7afb7bd23 | note | Verifying Document - Visual, Site Photos
4c1efc39-f017-5255-86c2-be965b493de3 | note | Frequency - Continuous
5133fb55-1305-57a9-92d0-3b06cc30e7bb | note | Inspection Type (Visual, other) - Witness
1cb75dd6-d38d-54c4-8a6a-1d495d5c3c41 | note | Inspection: Key - W
8e4f7cfc-35d6-5afe-b23d-7b61efbc098f | note | Inspection: By (Role Key) - SE
7486c58c-9fb9-4a38-88b8-d8792c7aa396 | checkpoint | 4.3 - Final Cut Observation Monitoring
347fdff0-3102-5435-ab25-bee766125209 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.6
4c207fc2-d9dd-50df-b46f-e08c487449e2 | note | Specification Reference - Continuous visual assessments conducted with Stantec Representative. Contractor to address design change if instructed
3ba2bd1d-904b-51b3-b6d0-9bb09aa69e01 | note | Acceptance Criteria - Agreement with Engineer's Rep
66603339-865d-527b-956f-0eb5c2b210cb | note | Verifying Document - As Required by Stantec Representative, QC-01 Earthworks Checksheet
4f7df1dd-eee8-52c9-81fc-4ba03ad868e4 | note | Frequency - As requested by engineer
d2081a75-cfd1-5c2e-b034-a5ec45a3a4b5 | note | Inspection Type (Visual, other) - Hold
56b79a36-efd0-5403-a2ad-bb8a1356d7da | note | Inspection: Key - H
dbb2871b-47f9-592a-8990-7dd356b5fdf4 | note | Inspection: By (Role Key) - ER
f191c6b6-2aab-4164-96e9-e47a0b3675af | signoff | AUTHORITY HOLDPOINT
2cdfb66a-9389-4627-8667-eef40cd2af5f | checkpoint | 4.4 - Cut Batter Tolerances
132eeb5a-fe9d-5df7-9be4-782120e3ef4c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.7
56c83086-c7e9-591b-b20c-40fe8793f938 | note | Specification Reference - Post-construction - Excavation of batters complying with design issued and within tolerance
ee66d3c0-49a5-5d67-a4b8-18faff38f4bf | note | Acceptance Criteria - Slope Tolerance 1H:1V or Flatter: +300 / -300 mm
79a3c917-608e-50cd-ab7f-e9fde7c7f119 | note | ○ Steeper than 1H:1V: +300 / -600mm
bc450905-2158-5089-979e-c8eff2fda31f | note | Verifying Document - As-Built and DN-QUA-QC-01 Earthworks Checksheet
207498a5-e043-56c3-835c-476f874fa023 | note | Frequency - Continuous
efa9913e-4bbe-5fbd-93b7-b9e6a3302e68 | note | Inspection Type (Visual, other) - Witness
d3cab161-6063-560d-945e-a4cc933e71a5 | note | Inspection: Key - W
ab994e35-4b7d-51e2-9377-c0539f957500 | note | Inspection: By (Role Key) - SE/SV
9ac63d2d-3fdf-41a8-8a9e-87424a2ecd20 | checkpoint | 4.5 - Site Fill Material - Segregation of Material Type
6f0f9b0b-029a-522d-a566-d1cf24cf370c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.8
aceeaf6b-a147-5532-9113-38bc69c47f73 | note | Specification Reference - Moisture sensitive material stockpiled
bb49d682-186e-5a46-813b-e57556aa8fa2 | note | Acceptance Criteria - Drainage blanket (polythene cover) if any material is stored on site to avoid saturation
c7f353d1-7f18-5f61-872b-b7f030221da3 | note | Verifying Document - Visual, Site Photos
801989f2-a1a7-5cb5-a394-0c7653136733 | note | Frequency - Continuous
e72a8aec-2da8-56be-bced-9018554b9697 | note | Inspection Type (Visual, other) - Witness
0d762aba-083d-5501-b776-f4c5925a4422 | note | Inspection: Key - W
08311d38-a7ef-5a95-b4bd-5c3fa8e79616 | note | Inspection: By (Role Key) - SE
192b71df-9dfe-44fb-ad89-61f682f2a57c | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
e676d3ad-166c-4de3-98c3-ae9896beecb7 | checkpoint | Inspection Point/ Signature & Date
b072bae1-74c0-5098-bd68-d5405a971db5 | date | Date:
18d8e4a4-5b1d-58d0-8bf9-f29766a313f4 | textbox | Customer Requirements Verification Record / Location/ Hold Points
2a4a07e0-640c-4290-bbe6-638dd12e0a67 | signoff | Downer Signature
0fd3b40d-d5bc-4ee1-b7cf-cd706f2c2b77 | checklist | Ω (DEPRECATED) ITP-0003 Earthworks Fill | itp | ITP-003 Earthworks Fill
4db9a2cd-fead-4294-8bda-07b7e01f9ed0 | section | SECTION 3 – RECEIVING INSPECTIONS
33804c9b-8306-4ef4-af37-b1fadcbb644f | checkpoint | 3.1 - Pre-Construction Survey
e2804895-a838-508c-bbb7-43797df277f7 | note | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
b40edbe2-e1c0-5dcb-8c3e-0b54df45b607 | note | Specification Reference - Drone/GPS
0eaf6ac2-7a41-583a-9fd1-eaa7ba8cb0a8 | note | Acceptance Criteria - Receipt of survey by engineer
849af7f9-f7dc-5970-9ac9-249dc805c4c7 | note | Verifying Document - Topo Survey
75f5bc98-01ce-5c4a-8099-d2120b4139b8 | note | Frequency - Prior to works - each lot
6a3baaa9-45ee-5a22-a888-971cdcfbebdf | note | Inspection Type (Visual, other) - Witness
83370141-d3cb-5408-bcf3-08952a10fd8d | note | Inspection: Key - W
7d34db44-95ae-56cb-bc7f-8eb78d6bda17 | note | Inspection: By (Role Key) - SPE & SV
fb6a885f-bc2e-44b8-bf18-5b5936d5de9e | checkpoint | 3.2 - Use of Flighty's Mound material for fill
83e9871d-9b43-5302-9dc6-d7ad045e5cda | note | Inspection Point: Quality Control Activity - N/A
19512bdd-e48b-51dc-89c4-ddfb0de869f2 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
9a4a79a1-2839-5ff4-a126-b0d3452930bf | note | Acceptance Criteria - Confirmation of use
34debe48-a486-546e-904b-6e8014a5a664 | note | Verifying Document - Mail Confirmation from Stantec Representative
6fac3a31-1810-5553-85f6-764a647fa647 | note | Frequency - Start of Earthowrks
5cfd1f51-236d-5777-9593-c8d3aca01c76 | note | Inspection Type (Visual, other) - Hold Point (where required)
9dcd6d82-1c02-5c55-8f6b-61d8d9ced0c4 | note | Inspection: Key - H
443625b6-2d56-5441-8eb8-c89c4b793db6 | note | Inspection: By (Role Key) - ER
83210422-9963-4264-bb3a-721408b0dc84 | signoff | AUTHORITY HOLDPOINT
f57b4c64-1650-4198-bbff-6b3f97bf845d | checkpoint | 3.3 - Use of Moonshine Rd Cut material to be used for fill
23f8223e-8878-53d3-a0b4-46e2e20161d7 | note | Inspection Point: Quality Control Activity - N/A
09355543-d1e1-5825-a9fc-1daeb67f5fa1 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
0c975a8c-c57d-505d-90a6-9cef5f592b6e | note | Acceptance Criteria - Confirmation of use
afb5a1e2-9d9b-593a-af56-f933dbe7038a | note | Verifying Document - Mail Confirmation from Stantec Representative
263b8a98-db66-5c08-91b7-43ddb035d10b | note | Frequency - Start of Earthowrks
ff7f016b-96ef-54bc-b0c7-6e9de2b2743a | note | Inspection Type (Visual, other) - Hold Point (where required)
e959f38a-476c-594c-bad8-8c5109c06a9d | note | Inspection: Key - H
5606d63e-4aa1-5450-9549-55346f1476fd | note | Inspection: By (Role Key) - ER
138b6ec4-b6f6-4d1f-83df-1d656388dcf6 | signoff | AUTHORITY HOLDPOINT
f8ec3898-e7a6-4d2e-9c03-9042496922bf | checkpoint | 3.4 - AP65 Material acceptance
12b60150-0d1a-5092-b38b-a943450949d2 | note | Inspection Point: Quality Control Activity - Specification Cl 17.1.11
8ff19d59-64b5-5ed9-87fc-a16e9060919e | note | Specification Reference - Material Testing and Compliance
f1bd496b-69e9-5504-9056-4bf90fb73070 | note | Acceptance Criteria - IANZ Testing
7b731e0d-5131-5a74-bf8c-b1abebe2a40d | note | Verifying Document - Testing report
3a9226aa-7744-5c32-b720-be008fc9a112 | note | Frequency - Every 1000m3 or change in material source
035aa4a9-d40b-570e-8c9c-72f347b723f5 | note | Inspection Type (Visual, other) - Hold Point
d6f21f79-9c71-50b0-a284-291368871795 | note | Inspection: Key - H
7619a487-0163-5a7f-8316-c16039c2ed5f | note | Inspection: By (Role Key) - ER
e36c2d94-b8f8-442b-b6fc-196ba4557a0c | signoff | AUTHORITY HOLDPOINT
d8549d1c-6084-4eb6-aa34-e1037e972367 | section | SECTION 4 – IN-PROCESS INSPECTIONS
9c62c46d-be03-4325-a269-2e1cce813bfd | checkpoint | 4.1 - Topsoil Depth Checks
5b8fa5b8-196b-5600-971a-f3b6d4d676fc | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
a452a378-61e0-5c00-b74c-c726008ddc11 | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
03b3720f-8844-514c-9229-a15264506e4d | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
08613c48-b482-5be7-a20d-be6627cb7408 | note | Verifying Document - Site Photos, Record Sheet
5e42a0de-49e9-5c4a-9848-bd849cebdb25 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2795d9b2-d7e0-5caf-8f7a-d709a310f2ca | note | Inspection Type (Visual, other) - Witness
3c37b622-502a-5fdc-8c4e-c6d62706b017 | note | Inspection: Key - W
a7deaea1-b306-5546-aefc-792f32b9a252 | note | Inspection: By (Role Key) - SE
4f861c4d-56fa-4f86-853b-b326a5bf7d87 | checkpoint | 4.2 - Hazardous & Classified Soils
31f36bba-8168-5228-8e14-d54e6ebb023d | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
602225a7-35c1-539c-84a2-97e895accb97 | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
9e4f6c65-b625-582f-9951-e8ae49d7aa98 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
4aa4b873-ce3c-5c30-9ddc-6654f6e713b5 | note | Verifying Document - Visual, Site Photos
9a2e7738-8add-5898-b720-a8718215117e | note | Frequency - Continuous
54149323-7e72-5849-b492-bf0b4e9e66bb | note | Inspection Type (Visual, other) - Witness
25ac1de1-7c21-582e-addc-72843b5c923a | note | Inspection: Key - W
3618481a-1a64-57a8-9586-d337c91a4efe | note | Inspection: By (Role Key) - SE
c77466cb-88d4-4d6d-a030-db3f490b0008 | checkpoint | 4.3 - Subgrade testing - Trim and Compact
5a6340d0-a1e7-59c4-9ff0-588daa5c7eeb | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.10
b3e2023e-c87d-5688-9fe8-5c28b6e001fb | note | Specification Reference - Trimming & Compaction of in-situ subgrade. Conduct plateau test.
73cd4ba2-b734-5a25-bb8e-51f26523c1bc | note | Acceptance Criteria - N/A
a3135f5c-ffa6-566b-a008-acdf06b7a12a | note | Verifying Document - Plateau worksheet
cd56e528-0d47-5c9b-abb4-a6f1f7588792 | note | Frequency - Full surface
76f971c6-ab70-5525-bc64-d7cd53497773 | note | Inspection Type (Visual, other) - Witness
f9e71c06-ff1d-5a81-b94c-c384b2eb2de0 | note | Inspection: Key - W
9af2e9cd-1409-5027-b8b4-57fd373d5b98 | note | Inspection: By (Role Key) - SE
6e0b306e-8217-45b6-aa98-3f2da0ad944c | checkpoint | 4.4 - Subgrade testing - Scala
f0fc626b-ce1b-5fc1-a9e2-beb9b21d8252 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.11
36376860-ec21-5a49-8311-bb3c84021acb | note | Specification Reference - Scala Testing
f2c390cd-8a69-5e01-80fd-4edcc1f34413 | note | Acceptance Criteria - 1 blow per 100mm is the minimum requirement for general fill placement
e92b1fd8-2193-5e1c-828b-0e6a473a274b | note | Verifying Document - DN-QUA-QC-04 1m Scala Worksheet
deec5fd9-20d3-5143-a3bc-06d8138e21c3 | note | Frequency - Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
35e62849-6a45-54a6-a33a-948f4a254b61 | note | Inspection Type (Visual, other) - Witness
e6ad1732-5fb2-569e-ab78-d897cd7be49c | note | Inspection: Key - W
2e49b9f7-548e-5556-99db-562e0914b2eb | note | Inspection: By (Role Key) - SE
d08f3a23-a67f-46a3-b73b-2d43b3bf99fb | checkpoint | 4.5 - Subgrade testing - Benkelman Beam
28f510e5-01d5-515a-973a-2b22920e6ab5 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.12
bf32ece9-b533-5d25-826a-80b1481b63e4 | note | Specification Reference - Benkelman Beam Testing
4dfdc5b1-2fd1-5773-a841-951f1236e3f9 | note | Acceptance Criteria - Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm
3a4a1436-0c04-582c-9fe8-166f28a73d8e | note | Verifying Document - Lab report
8167b6e0-f261-5c03-b8b7-7e2a11cf30eb | note | Frequency - Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
5d887dfa-3825-5eb6-918c-a27123ab1be0 | note | Inspection Type (Visual, other) - Witness
e06d1c39-0759-5f50-bf41-af433f55d06c | note | Inspection: Key - W
de8ed31f-dca1-543c-ab81-20618767ee4f | note | Inspection: By (Role Key) - SE
69f4e90b-552e-439b-988f-1e72f0b7b957 | checkpoint | 4.6 - Subgrade testing - Proof Roll
1839ae8e-4785-5e89-ae30-6878bdbefa44 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.13
b84289c8-b380-5f42-9801-1dc5845914e1 | note | Specification Reference - Proof Roll
c1f942b1-a560-533c-b67e-43446bab6d03 | note | Acceptance Criteria - As instructed by the Engineer
6d7c2351-765a-59e4-8dd6-c7b85ae08027 | note | Verifying Document - Visual Assessment - Sign off on ConQA by Engineer
cd2ca153-edff-5158-b93a-c3c9bff4a274 | note | Frequency - Proof Roll: Full surface using suitable plant
a473ece9-ef13-57d1-b8b3-63e66c288983 | note | Inspection Type (Visual, other) - Hold
17decdd9-724b-5160-953e-fbe77be61e8c | note | Inspection: Key - H
b1837a51-96fb-5325-b4fc-49fde76f9d1e | note | Inspection: By (Role Key) - ER
4034b935-2e19-43c5-8b87-422e5ce2a877 | signoff | AUTHORITY HOLDPOINT
baff8782-7812-409c-955d-22faaf8a2d45 | checkpoint | 4.7 - Fill Compaction Trial
3b1aa582-7080-50f7-a743-4d1a834e0c3e | note | Inspection Point: Quality Control Activity - Project Spec Cl 15.6.11
b59340bf-1c1e-5b01-9685-d1d249c2da6f | note | Specification Reference - On-site Testing - NDM, Visual, Shear Vane
3072fcc1-2d40-5f8c-a101-d668ffc305b1 | note | Acceptance Criteria - Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P
a16bbc46-f692-5511-98cc-f9dba2f08730 | note | Verifying Document - NDM Worksheet, Shear Vane Worksheet, Plateau Density Sheet
245f9472-8924-59b7-af93-07fabe64fbc0 | note | Frequency - When a new type of fill material is used
cb7f9df4-0ad0-511e-9839-256019215ea8 | note | Inspection Type (Visual, other) - Hold
9ad8e962-7572-5e64-9aef-a31d67b4fc4e | note | Inspection: Key - H
c9c7d82b-adec-5235-81cc-c72bb9211895 | note | Inspection: By (Role Key) - ER
f985a566-05fe-4bca-aa0a-63ece48458e9 | signoff | AUTHORITY HOLDPOINT
ac487538-1b27-4fb7-82cb-3d1c832dc83b | checkpoint | 4.8 - Fill Backfill layer thickness
9dc0ddd5-7081-5c5b-aad6-244ddd534627 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.8
9100536d-2452-5d74-8636-8012cb1a7aa7 | note | Specification Reference - Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction
b573abdd-0e24-5b25-9997-15ae932b717b | note | Acceptance Criteria - Fill placement not exceeding 230mm
c7aae880-1974-5f3b-9be6-50d71e180eb1 | note | Verifying Document - Visual, Site Photos and NDM check sheets, DN-QUA-QC-09 NDM Worksheet
e281d108-66fa-59e2-8851-f46838f6719d | note | Frequency - Every layer
6f256caa-f61b-5b64-b071-a38145b5f2e7 | note | Inspection Type (Visual, other) - Witness
be7beb94-ad2b-54dd-83f0-38c8f5564a6d | note | Inspection: Key - W
35b64125-bc7b-5da4-be26-97b71b7af86c | note | Inspection: By (Role Key) - SE
bcc30a6b-119d-4743-8a79-baaf6dc3ee43 | checkpoint | 4.9 - Fill Compaction Testing Laboratory
613ffacb-21f8-55a0-ac5a-8f2d6e0c9561 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.12
abf1c975-f467-550d-8803-5f63bbcc3a2f | note | Specification Reference - Water Content, Standard Proctor and Wet Sieve.
87cb7aef-ee1d-547e-ac81-b90003b86845 | note | Acceptance Criteria - N/A
404f0300-be8d-57c5-9ae3-09ef3f08131c | note | Verifying Document - IANZ report
45d7b2e9-2ab1-5bbb-ba2e-47b28b92899d | note | Frequency - WC - 1 test per 400m3 with 2 tests minimum per day, MDD & WS - 1 test per 2000m3
e4b62afa-6a64-517f-bfcf-bfb487b48f5d | note | Inspection Type (Visual, other) - Witness
78e96303-1f07-5a1a-b96e-b20bc84fe4c0 | note | Inspection: Key - W
66ee5b0c-a583-5bca-87d4-fe169198728e | note | Inspection: By (Role Key) - SE
4d840a77-0d83-418d-8eaa-5d3ace198277 | checkpoint | 4.10 - Fill Compaction Testing Site
170c0ce9-da4c-51cd-a656-534cc2598816 | note | Specification Reference - Compaction test by plateau
4cd4ea6f-fd7d-5182-9cb9-7ecd963f4105 | note | Acceptance Criteria - Plateau Testing to determine true MDD value based on site conditions
f435ba24-e53f-5101-81ee-295144d7851c | note | Verifying Document - DNZ Plateau Test work sheet
95c64cd4-0399-5ee6-84c8-fe44e0fe532b | note | Frequency - Daily
05ff474c-f5e3-5368-a1e9-39775e6ad1b0 | note | Inspection Type (Visual, other) - Witness
9df4d291-794f-5154-8fd0-3f6e2da0ae60 | note | Inspection: Key - W
8cd77cf0-88d2-5621-9a62-ae0a6c6560e3 | note | Inspection: By (Role Key) - SE
9bb0e863-25ab-4e2e-a5c8-736f7a3cbf9e | checkpoint | 4.11 - Fill Compaction Testing Site
a0f51fc5-3327-536a-a294-1323489b698c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.10, Project Spec Cl.15.6.12
e70d9530-82db-512d-bb7d-6470d91d214f | note | Specification Reference - NDM and OMC testing of fill material, Shear Vane
15556765-8e6f-5346-b003-a5130be21e1e | note | Acceptance Criteria - Moisture Content: between-2% and +4% of OMC
7fcab2ac-a9ab-5872-b45d-bd68049bbef8 | note | ○ Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95%
a801c928-555b-535f-9716-82c12c5aa57f | note | ○ Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only)
e54e9950-49f6-5033-8c0b-245f5090e787 | note | Verifying Document - NDM Record Sheet, DN-QUA-QC-09 NDM Worksheet, Shear Vane Sheet (Cohesive soil only)
6fb339aa-e367-5272-b3ec-08785b7ada50 | note | Frequency - NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day
017b0e48-efcf-5a5e-bb2b-aa847de2c09d | note | ○ Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only)
d36e4bf3-83f7-5ad9-b4a1-1195d43e9525 | note | Inspection Type (Visual, other) - Witness
479c803f-863e-5ecf-995d-ac9522d1ed37 | note | Inspection: Key - W
91ffb9e9-9267-5718-9b08-82760cad3387 | note | Inspection: By (Role Key) - SE
49dc47d4-4477-45df-98df-0234e7253c87 | checkpoint | 4.12 - Fill Tolerances
40d82a36-02ad-5737-8acb-c456c28f5187 | note | Inspection Point: Quality Control Activity - Project Spec Cl. 15.3.11
9e700a68-8e22-58e3-9974-7d3dfdfa1e95 | note | Specification Reference - Survey of finished surface
e79c980c-87de-5e44-b10b-3236c822d8b2 | note | Acceptance Criteria - Tolerance of +-50mm
447e271e-bca4-5ebb-add8-7fc00e2da9c3 | note | Verifying Document - As-built
bb9bf85e-e97c-59a1-ae14-091787bbd065 | note | Frequency - At Completion
460b02c8-ced0-56fb-9524-2652fccfcaa1 | note | Inspection Type (Visual, other) - Witness
7feba2b6-df9e-5aa3-954c-fc41cf3abc3b | note | Inspection: Key - W
d7211d8d-3c2a-58ce-ac35-6a15b5ea8287 | note | Inspection: By (Role Key) - SE/SV
b9a3e932-94cd-4693-a41e-146bbf0d7650 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
91d48c13-d2f8-45c4-af23-fde24dbb16ad | checkpoint | Inspection Point/ Signature & Date
c5b2747d-ce3f-524a-a1e6-6023b29c528c | date | Date:
db896672-4da5-53f6-9550-09d229e89fb7 | textbox | Customer Requirements Verification Record / Location/ Hold Points
f5dea672-25bd-4897-adf3-d2ef22a81c2d | signoff | Downer Signature