## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-M-004 Anchorbloc Materials | itp |  |  |  |  | DS2681-SH58-ITP-M-004 Anchorbloc Materials
section | SECTION 3 – MATERIALS
checkpoint | 3.1 - Material Compliance - Precast Anchorbloc
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - Project Specification CL 18.1.5
label | Acceptance Criteria - The Contractor shall provide to the Engineer, full details and specifications of the anchorbloc including ACEGrid and locking bar. Details to be provided by manufacturer
label | Verifying Document - Technical/ product data sheet, Delivery dockets, ITR-Incoming Mateirla Inspection (DN-QUA-QC-10)
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Material Compliance - AP65 (M4 if required) basecourse
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - Project Specification CL 18.1.5
label | Acceptance Criteria - free of unsuitable material as defined in the Earthworks Specification.
label | ○ Fill to contain no more than 20% passing a 75μm sieve.
label | ○ Fill to have maximum particle size of 100mm
label | ○ Fill particles shall be able to be incorporated within a single layer. Further, less than 30% of particles shall be retained on the 37.5 mm sieve.
label | ○ Unless otherwise approved, the MSE Wall Fill shall have a Liquid Limit less than 70% and a PI less than 6%.
label | ○ MSE Fill shall be able to be tested in accordance with conventional compaction test methods for soil. Where Nuclear Densometer is used, these methods require less than 20% retained on the 37.5 mm sieve. Where between 20% and 30% of particles are retained on the 37.5 mm sieve the above test methods shall still be adopted and test reports annotated appropriately including reference to any test calibration or correction adopted
label | Verifying Document - IANZ Lab Report
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Lab Test Report
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Geogrid for Anchorbloc Wall
label | Inspection Point: Quality Control Activity - Prior to construction
label | Specification Reference - Project Specification CL 18.1.5
label | Acceptance Criteria - The Contractor shall provide to the Engineer, full details and specifications of geogrid reinforcements details including manufacture data
label | ○ STRATAGRID SGU80 to or equivalent to be used as per 80510096-02B-900-C470 Rev 1 drawing
label | Verifying Document - Technical/ product data sheet, Delivery dockets
label | Frequency - Prior to works
label | Inspection Type (Visual, other) - Document Review
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checklist | DS2681-SH58-ITP-C-004 Anchorbloc Retaining Walls | itp |  |  |  |  | DS2681-SH58-ITP-C-004 Anchorbloc Retaining Walls
section | SECTION 4 – CONSTRUCTION
checkpoint | 4.1 - Foundation Test Requirements
label | Inspection Point: Quality Control Activity - Following Excavation
label | Specification Reference - Project Specification Cl 18.5.4
label | Acceptance Criteria - Minimum of 3 blows/100 mm penetration
label | Verifying Document - Scala Testing Record Sheet DN-QUA-QC-04
label | Frequency - 10m intervals
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.2 - Foundation Subgrade
label | Inspection Point: Quality Control Activity - Following Excavation
label | Specification Reference - Project Specification Cl 18.5.2
label | Acceptance Criteria - The foundation for the retaining wall subgrade must be inspected by the Engineer and shall be approved for the placement of the wall facing elements and reinforcement elements
label | Verifying Document - Site Instruction - Hold point release / email
label | Frequency - Following Subgrade digout
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Foundation AP65 - Compaction
label | Inspection Point: Quality Control Activity - Foundation prep
label | Specification Reference - Project Specification Cl 18.5.5
label | Acceptance Criteria - Foundation Compaction: 95% MDD and+/- 2% of OMC as determined from the plateau test/or lab testing. None less than 92%
label | ○ 1 set of NDM tests (comprising 5 No. NDM tests per set) are required per 200mm fill lift
label | Verifying Document - NDM Test Results DN-QUA-QC-09
label | Frequency - 1 set of NDM tests (comprising 5 No. NDM tests per set)
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Anchorbloc Placing
label | Inspection Point: Quality Control Activity - Survey as-built
label | Specification Reference - Project Spec Cl 18.5.7
label | Acceptance Criteria - Anchor blocks shall be placed into correct position, alignment and angle according to drawings
label | — — — — — — — — — — —
label | a) Position on plan: ± 50 mm
label | b) Dimensions on plan: ± 50 mm
label | — — — — — — — — — — —
label | Verifying Document - Photo Record, as-built records
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SV
checkpoint | 4.5 - MSE Wall Backfill AP65 - Compaction Testing
label | Inspection Point: Quality Control Activity - MSE Wall Backfill
label | Specification Reference - Project Specification Cl 18.5.5
label | Acceptance Criteria - Foundation Compaction: 98% MDD and+/- 2% of OMC. None less than 95%
label | ○ 1 set of NDM tests (comprising 5 No. NDM tests per set) are required per 200mm fill lift
label | Verifying Document - Photos
label | Frequency - Placement/ Prior to backfill
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.6 - MSE Wall Backfill AP65 - Visual Inspection
label | Inspection Point: Quality Control Activity - MSE Wall Backfill
label | Specification Reference - Project Specification Cl 18.5.2
label | Acceptance Criteria - The backfill must be witnessed by the engineer with fill layers not exceeding 200mm.
label | Verifying Document - Visual Inspection
label | Frequency - Placement/ Prior to bakcfill
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Placing Geotextiles/geogrid
label | Inspection Point: Quality Control Activity - MSE Wall Backfill
label | Specification Reference - Project Specification Cl 18.5.2
label | Acceptance Criteria - 80510096-02B-900-C470 Wrap top, bottom & front edge with STRATAGRID SGU80
label | Verifying Document - Photos
label | Frequency - Placement/ Prior to backfill of upper layers
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8 - As-built Survey
label | Inspection Point: Quality Control Activity - Upon completion of works
label | Specification Reference - Project Spec Cl 18.5.7
label | Acceptance Criteria - As built survey record completed
label | — — — — — — — — — — —
label | a) Position on plan: ± 50 mm
label | b) Dimensions on plan: ± 50 mm
label | c) Level of surface trimmed to receive wall: ± 50 mm
label | d) Finished levels: ± 50 mm
label | — — — — — — — — — — —
label | Verifying Document - As-built records
label | Frequency - At completion
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SV
checklist | DS2681-SH58-ITP-TW-001 Bridge 3 Crane Pad and Cofferdam | itp |  |  |  |  | DS2681-SH58-ITP-TW-001 Bridge 3 Crane Pad and Cofferdam
section | SECTION 4 – CONSTRUCTION
checkpoint | 3.01 - Sheet piles
label | Inspection Point: Quality Control Activity - Prior to works
label | Acceptance Criteria - Prior to installation, a visual inspection of the sheet piles will be conducted to ensure they are in good condition. The inspection will verify that the sheet piles have the required length to reach the necessary depth for proper driving
label | Specification Reference - Please refer to Bridge 3 – Temporary Works Design.
label | Verifying Document - Visual
label | Inspection/Test: Key - V
label | Inspection/Test: By - SE
checkpoint | 3.02 - Steel Waler Beams
label | Inspection Point: Quality Control Activity - Prior to works
label | Acceptance Criteria - Confirm steel section 360UB44
label | Specification Reference - Dwg 2681-TW-003
label | Verifying Document - Visual
label | Inspection/Test: Key - V
label | Inspection/Test: By - SE
checkpoint | 3.03 - Welds
label | Inspection Point: Quality Control Activity - Prior to works
label | Acceptance Criteria - All welds to be visually inspected and if any defects are found, they need to be reported.
label | Specification Reference - Please refer to Bridge 3 – Temporary Works Design.
label | Verifying Document - Visual
label | Inspection/Test: Key - V
label | Inspection/Test: By - SE
checkpoint | 3.03 - Concrete
label | Inspection Point: Quality Control Activity - Before removing any walers
label | Acceptance Criteria - Report all QA for concrete to the Engineer including delivery dockets and report on placing before removing any Walers.
label | Specification Reference - Please refer to Bridge 3 – Temporary Works Design.
label | Verifying Document - Check
label | Inspection/Test: Key - H
label | Inspection/Test: By - SE
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.01 - Location and marking of the cofferdam and crane pad.
label | Inspection Point: Quality Control Activity - Prior to works
label | Acceptance Criteria - The final location of the cofferdam and the working platform should be clearly marked on-site, ensuring the dimensions and alignment with respect to the pier extension, and considering the proximity shown on the drawing.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - Prior to sheet piles instalation
label | Inspection Type (Visual, other) - Dimension inspection
label | Inspection: Key - D
label | Inspection: By - SV
checkpoint | 4.01 - Sheet piles installation
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - The sheet piles will be driven down with the excavator to just below the platform level, ensuring the design height is achieved and that the piles have reached rock level. Report sheetpile embedment depths to the TW Engineer
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - Driven down of sheet piles
label | Inspection Type (Visual, other) - Hold Point 1
label | Inspection: Key - C
label | Inspection: By - TWC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Top waler installation
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Check the levels of the underside of the waler to ensure it is just above the top of the new pier. Install and support the Top Waler. Drive the sheet piles around the waler. Weld the Top Waler in place.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - First waler installation
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.04 - Lagging installation
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - During the lagging installation between sheetpiles and bridge Abutment, ensure there is sufficient space for the formwork, with a minimum clearance of 900mm. The lagging must be securely fastened both to the sheet pile and the pier.
label | ○ As new boards are placed underneath, they may need to be held to the lagging above. Uuse vertical boards nailed to the lagging above if necessary to hold the new lagging in place.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - During construction
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.05 - Second waler
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Monitor excavation and ensure that measurements are being taken to not exceed depths.
label | ○ The TWC shall inspect the waler before excavation proceeds. Excavate to a maximum depth of 2.25m, then install the brackets and the second waler. Pack the space between the waler and the sheet piles with grout bags.
label | ○ Support the Waler using chains from the Waler above if necessary until excavation has continued far enough to weld the bracing leg to the bracket.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - During cofferdam excavation
label | Inspection Type (Visual, other) - Hold Point 2
label | Inspection: Key - I
label | Inspection: By - TWC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.06 - 3rd waler
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Monitor excavation and ensure that measurements are being taken to not exceed depths.
label | ○ Excavate to 3.58m (max) BGL, install brackets and install 3rd Waler.
label | ○ Pack between Waler & Sheetpiles with grout bags.
label | ○ Support the Waler as noted above if necessary as excavation proceeds.
label | ○ TWC to inspect Waler before excavation proceeds.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - During cofferdam excavation
label | Inspection Type (Visual, other) - Hold Point 3
label | Inspection: Key - I
label | Inspection: By - TWC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.07 - Welds
label | Inspection Point: Quality Control Activity - Welding review
label | Acceptance Criteria - All welds to be visually inspected by the TWC and any defects reported to the Engineer. Each of the 100mm long stubs are to be identified, marked and photos of each sent to the Engineer for approval.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - During welding process
label | Inspection Type (Visual, other) - Inspection/ Hold point
label | Inspection: Key - I
label | Inspection: By - TWC
checkpoint | 4.08 - Welds
label | Inspection Point: Quality Control Activity - Welding review
label | Acceptance Criteria - All welds to be 6mm Fillet Weld all round UNO.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - During welding process
label | Inspection Type (Visual, other) - Inspection/ Hold point
label | Inspection: Key - I
label | Inspection: By - SE
checkpoint | 4.09 - Platform level
label | Inspection Point: Quality Control Activity - Prior to works
label | Acceptance Criteria - The platform level must be 325mm below the road level at the center location of the bridge.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - Before platform works
label | Inspection Type (Visual, other) - Check
label | Inspection: Key - C
label | Inspection: By - SE
checkpoint | 4.10 - Reidbar
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Install reidbar ties 500mm below top of platform
checkpoint | 4.11 - Cofferdam excavation
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - TWC to inspect bracket braces before excavating to full depth. Fully de-water and clean out down to rock level
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - Cofferdam excavation
label | Inspection Type (Visual, other) - Hold Point 4
label | Inspection: Key - A
label | Inspection: By - TWC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.12 - Concrete toe
label | Inspection Point: Quality Control Activity - During construction
label | Acceptance Criteria - Cast concrete toe support 400mm thick. Report all QA for concrete to the Engineer including delivery dockets and report on placing before removing any Walers. Remove second and third walers after 7 days.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - After excavating to full depth
label | Inspection Type (Visual, other) - Hold Point 5
label | Inspection: Key - A
label | Inspection: By - TWC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.13 - Hydro response
label | Inspection Point: Quality Control Activity - After sheet pile installation
label | Acceptance Criteria - PVC sheeting is to start from the far side of the bridge and continue past the cofferdam, as advised by the waterproofing contractor.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - After sheet pile installation
label | Inspection Type (Visual, other) - Action
label | Inspection: Key - A
label | Inspection: By - SE
checkpoint | 4.14 - Hydro response
label | Inspection Point: Quality Control Activity - After sheet pile installation
label | Acceptance Criteria - Attach the PVC sheeting to the sheet piles and to the concrete bridge pier beneath the bridge.
label | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
label | Frequency - After sheet pile installation
label | Inspection Type (Visual, other) - Action
label | Inspection: Key - A
label | Inspection: By - SE
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | 5.01 - Final Handover
label | Inspection Point: Quality Control Activity - Documentation
label | Acceptance Criteria - All hold points must be formally reported to the Engineer for inspection. A photographic record of the inspected works shall be maintained. Proceeding beyond any hold point requires explicit approval from the Engineer.
label | Verifying Document - Permit to Load
label | Inspection/Test: Key - A
label | Inspection/Test: By - TWC