## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
3e057d11-4fde-4940-ad40-044528697159 | checklist | DS2681-SH58-ITP-M-003 Earthworks Materials | itp | DS2681-SH58-ITP-M-003 Earthworks Materials
58292683-ff6e-4b9c-a15c-e67e34c450e1 | section | SECTION 3 – RECEIVING INSPECTIONS
5e44d725-1630-472f-bd79-01ba92b790a4 | checkpoint | 3.1 - Pre-Construction Survey
b9b7905e-c23e-5cdb-a8f6-635d63445278 | note | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
31ff9d67-1ead-5222-b63c-29ab88a7560f | note | Specification Reference - Drone/GPS
c203eb51-f0a5-5ce8-b6d6-c0b614115687 | note | Acceptance Criteria - Receipt of survey by engineer
98bb493b-d4dd-57e1-a7c7-e83d973342b7 | note | Verifying Document - Topo Survey
0ee5708c-0c7f-5f17-bef2-aae0829e82b5 | note | Frequency - Prior to works - each lot
5647ce7f-29a9-5d0b-b62e-ca4bdc8de760 | note | Inspection Type (Visual, other) - Witness
c35d10d2-94d4-5b0c-9150-77ec04395548 | note | Inspection: Key - W
f9cec978-8728-5a00-96f6-234faab89a65 | note | Inspection: By (Role Key) - SPE & SV
fb6a885f-bc2e-44b8-bf18-5b5936d5de9e | checkpoint | 3.2 - Use of Flighty's Mound material for fill
83e9871d-9b43-5302-9dc6-d7ad045e5cda | note | Inspection Point: Quality Control Activity - N/A
19512bdd-e48b-51dc-89c4-ddfb0de869f2 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
9a4a79a1-2839-5ff4-a126-b0d3452930bf | note | Acceptance Criteria - Confirmation of use
34debe48-a486-546e-904b-6e8014a5a664 | note | Verifying Document - Mail Confirmation from Stantec Representative
6fac3a31-1810-5553-85f6-764a647fa647 | note | Frequency - Start of Earthowrks
5cfd1f51-236d-5777-9593-c8d3aca01c76 | note | Inspection Type (Visual, other) - Hold Point (where required)
9dcd6d82-1c02-5c55-8f6b-61d8d9ced0c4 | note | Inspection: Key - H
443625b6-2d56-5441-8eb8-c89c4b793db6 | note | Inspection: By (Role Key) - ER
83210422-9963-4264-bb3a-721408b0dc84 | signoff | AUTHORITY HOLDPOINT
f57b4c64-1650-4198-bbff-6b3f97bf845d | checkpoint | 3.3 - Use of Moonshine Rd Cut material to be used for fill
23f8223e-8878-53d3-a0b4-46e2e20161d7 | note | Inspection Point: Quality Control Activity - N/A
09355543-d1e1-5825-a9fc-1daeb67f5fa1 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
0c975a8c-c57d-505d-90a6-9cef5f592b6e | note | Acceptance Criteria - Confirmation of use
afb5a1e2-9d9b-593a-af56-f933dbe7038a | note | Verifying Document - Mail Confirmation from Stantec Representative
263b8a98-db66-5c08-91b7-43ddb035d10b | note | Frequency - Start of Earthowrks
ff7f016b-96ef-54bc-b0c7-6e9de2b2743a | note | Inspection Type (Visual, other) - Hold Point (where required)
e959f38a-476c-594c-bad8-8c5109c06a9d | note | Inspection: Key - H
5606d63e-4aa1-5450-9549-55346f1476fd | note | Inspection: By (Role Key) - ER
138b6ec4-b6f6-4d1f-83df-1d656388dcf6 | signoff | AUTHORITY HOLDPOINT
f8ec3898-e7a6-4d2e-9c03-9042496922bf | checkpoint | 3.4 - AP65 Material acceptance
12b60150-0d1a-5092-b38b-a943450949d2 | note | Inspection Point: Quality Control Activity - Specification Cl 17.1.11
8ff19d59-64b5-5ed9-87fc-a16e9060919e | note | Specification Reference - Material Testing and Compliance
f1bd496b-69e9-5504-9056-4bf90fb73070 | note | Acceptance Criteria - IANZ Testing
7b731e0d-5131-5a74-bf8c-b1abebe2a40d | note | Verifying Document - Testing report
3a9226aa-7744-5c32-b720-be008fc9a112 | note | Frequency - Every 1000m3 or change in material source
035aa4a9-d40b-570e-8c9c-72f347b723f5 | note | Inspection Type (Visual, other) - Hold Point
d6f21f79-9c71-50b0-a284-291368871795 | note | Inspection: Key - H
7619a487-0163-5a7f-8316-c16039c2ed5f | note | Inspection: By (Role Key) - ER
e36c2d94-b8f8-442b-b6fc-196ba4557a0c | signoff | AUTHORITY HOLDPOINT
0d369293-c495-45e7-8aba-cda22b54a1e0 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
1588c0dc-9eea-4e9a-8789-a22b28d2b3c1 | checkpoint | Inspection Point/ Signature & Date
f07723a8-9764-5ffd-b451-4922c8f1ca26 | date | Date:
44f8fdc4-4407-5786-b498-e4fe329d162c | textbox | Customer Requirements Verification Record / Location/ Hold Points
72ab6684-5339-492b-a21c-93214725af5a | signoff | Downer Signature