## zres_siteapp_NEW
Type | Name | Values | Prompting Name | Postfix | Resource Id
checklist | FH-927-QU-ITP006 - Asphalt Production - Rev 0 | itp | ITP006 - Asphalt Production
section | 1.0 - Paving Plant, Tools and Equipment
checkpoint | 1.1 - Minimum Requirements
label | Frequency - Each Lot
label | Acceptance Criteria - The plant must be calibrated by the Contractor prior to the commencement of production trials in accordance with Clause 5112(i) and the calibration checked and reliably maintained throughout the entire production for the Works.
label | Reference Documents - Volume 1: Clause 5112 (a)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed by Contractor
label | IP
label | Responsibility - Construction Manager
date | Date Completed:
checkpoint | 1.2 - Bitumen Usage
label | Frequency - Each Lot
label | Acceptance Criteria - Submission of results of verification testing of asphalt mixing plant devices against direct measuring of bitumen tank with mix/trial mix test results
label | Reference Documents - Volume 1: HP 5112-1
label | Inspection/Test Method - Submission
label | Record of conformity - Bitumen Usage Record
label | HP
label | Responsibility - Quality Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Storage and Handling of Aggregates, Added Filler and Bituminous materials
checkpoint | 2.1 - Storage and Handling of Aggregates
label | Frequency - Each Lot
label | Acceptance Criteria - Aggregates must be tested for compliance and compliance confirmed before delivery on site. The aggregates must be stockpiled separately at the quarry or mixing plant, stored to prevent contamination and segregation. Each size should be stored with at least 6 m of space between them or a wall to avoid mixing. Aggregates up to 10 mm must stay in free-draining stockpiles for at least 72 hours before use, with waterproof covers used during wet weather when the plant isn’t operating.
label | Reference Documents - Volume 1: Clause 5114 (a), 5131 (a)(i)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed by Contractor
label | IP
label | Responsibility - Plant Operator
date | Date Completed:
checkpoint | 2.2 - Storage of Added Filler
label | Frequency - Each Lot
label | Acceptance Criteria - Added filler must be stored in weatherproof storage bins or silos to prevent moisture absorption and the formation of lumps.
label | Reference Documents - Volume 1: Clause 5114
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed by Contractor
label | IP
label | Responsibility - Plant operator
date | Date Completed:
checkpoint | 2.3 - Storage and Handling of Bitumen
label | Frequency - Each Lot
label | Acceptance Criteria - Bitumen must be stored in clean tanks and not reheated above specified temperatures or stored longer than showed in Table 5114-1.
label | ○ The Contractor should keep records of heating and storage; if there are not records, bitumen must be used within 24 hours of delivery.
label | ○ Contaminated bitumen cannot be used for asphalt.
label | Reference Documents - Volume 1: Clause 5114 (c) and Table 5114-1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed by Contractor
label | IP
label | Responsibility - Plant Operator
date | Date Completed:
section | 3.0 - Mix Production Requirements
checkpoint | 3.1 - Moisture Content of Aggregate
label | Frequency - Each Lot
label | Acceptance Criteria - Moisture content must be determined in accordance with the requirements of Clause 5129(c).
label | Reference Documents - Volume 1: Clause 5116 (b)
label | Inspection/Test Method - Verify
label | Record of conformity - Moisture Test Report
label | TP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 3.2 - Particle Size Distribution Tolerance
label | Frequency - Each Lot
label | Acceptance Criteria - Individual samples of aggregate from stockpiles, deliveries, cold bins, or feeders must maintain consistent particle size distribution. This ensures that the overall particle size distribution of asphalt remains within specified limits defined by job requirements and production tolerances outlined in tables for coarse and fine aggregates.
label | Reference Documents - Volume 1: Clause 5116 (c)
label | Inspection/Test Method - Verify
label | Record of conformity - PSD Test Report
label | TP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 3.3 - Commencement of production of asphalt in each working period
label | Frequency - Not less than 48 hours prior to the commencement of a work period
label | Acceptance Criteria - Submission of production plan which must demonstrate that the hot storage capacity and the production capacity of the mixing plant is capable of suppling asphalt to complete the work proposed to be undertaken within that work period on time and to make the runway suitable for aircraft operation in the event of an asphalt plant breakdown
label | Reference Documents - Volume 1: HP 5116-1
label | Inspection/Test Method - Submission
label | Record of conformity - Production Plan
label | HP
label | Responsibility - Quality Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Mixing Temperature Requirements
label | Frequency - Each Lot
label | Acceptance Criteria - Tolerances of bitumen temperature, temperature of aggregates and Asphalt temperature when introduced into the mix are shown in Clause 5116 (f)
label | Reference Documents - Volume 1: Clause 5116 (f)
label | Inspection/Test Method - Verify
label | Record of conformity - Asphalt Production Records
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 3.5 - Mixing Efficiency
label | Frequency - Each Lot
label | Acceptance Criteria - For asphalt production, hot aggregate, filler, and bitumen must be mixed until particles are at least 97% coated, ensuring a homogeneous mixture per ASTM D2489.
label | Reference Documents - Volume 1: Clause 5116 (g)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Plant Operator
date | Date Completed:
checkpoint | 3.6 - Mixing Times
label | Frequency - Each Lot
label | Acceptance Criteria - Mixing time for asphalt should balance efficiency and prevent bitumen hardening. Dry mixing must last at least 10 seconds, while wet mixing should include bitumen addition (max 10 seconds) and ensure complete coating of all particles.
label | Reference Documents - Volume 1: Clause 5116 (h)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Plant Operator
date | Date Completed:
checkpoint | 3.7 - Production Tolerances
label | Frequency - Each Lot
label | Acceptance Criteria - All asphalt produced in accordance with the 'job mix' must comply with the properties specified in Tables 5116-4, 5116-5, 5116-6, & 5116-7
label | Reference Documents - Volume 1: Clause 5116 (j)
label | Inspection/Test Method - Verify
label | Record of conformity - Asphalt Mix Test Report
label | TP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 3.8 - Non-Conformed Production of Asphalt
label | Frequency - As required
label | Acceptance Criteria - If during the progress of the Works asphalt produced, with an aggregate particle size distribution and bitumen content within the tolerances specified in Table 5116-7, a non- conformance report and proposed disposition must be recorded and submitted
label | Reference Documents - Volume 1: HP 5116-2 and Table 5116-7
label | Inspection/Test Method - Notification
label | Record of conformity - NCR
label | HP
label | Responsibility - Quality Enginer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Non-Conforming Material
label | Frequency - As required
label | Acceptance Criteria - Asphalt that is overheated, inadequately mixed, contains moisture, or does not meet specifications is deemed nonconforming and must be removed from the site.
label | Reference Documents - Volume 1: Clause 5116 (k)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed by Contractor
label | TP
label | Responsibility - Quality Engineer
date | Date Completed:
section | 4.0 - Quality Assurance – Production
checkpoint | 4.1 - Sampling and Testing – Coarse Aggregates and Fine Aggregates
label | Frequency - Not less than 5 days prior the use of the aggregate in production of asphalt
label | Acceptance Criteria - The minimum frequency of sampling and testing for each coarse aggregate fraction must comply with the requirements of Table 5131-1.
label | ○ The minimum frequency of sampling and testing for each fine aggregate fraction must comply with the requirements of Table 5131-2.
label | Reference Documents - Volume 1: HP 5131-1
label | Inspection/Test Method - Submission
label | Record of conformity - Aggregate Test Reports
label | HP/ TP
label | Responsibility - Quality Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Added Filler
label | Frequency - Not later than 24 hours after each delivery
label | Acceptance Criteria - A test certificate confirming that the hydrated lime meets 5106 must be included with each delivery to the asphalt mixing plant. This certificate, along with the delivery docket, must be submitted to the Contract Administrator
label | Reference Documents - Volume 1: Clause 5131 (b)
label | Inspection/Test Method - Submission
label | Record of conformity - Added filler Certificate and docket
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.3 - Bitumen Test Certificates
label | Frequency - Not later than 24 hours after each delivery.
label | Acceptance Criteria - Each delivery of bitumen to the asphalt mixing plant must include a test certificate verifying compliance with specifications and corresponding to the delivered lot. The delivery docket, detailing quantity and delivery time, must be submitted to the Contract Administrator, along with a testing certificate for each new batch.
label | Reference Documents - Volume 1: Clause 5131 (e)(i)
label | Inspection/Test Method - Submission
label | Record of conformity - Bitumen Certificate and docket
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.4 - Sampling of bitumen from delivery vehicle at mixing plant
label | Frequency - 24 hours prior
label | Acceptance Criteria - Notice (24 hours prior) of time of bitumen delivery to mixing plant and taking of bitumen samples.
label | ○ Samples must be at least two (2) litres in sealed, 6ubmitte airtight steel cans with removable tops. They should be traceable to supplier records and handed to the Contract Administrator immediately after sampling.
label | Reference Documents - Volume 1: WP 5131-1 and Clause 5131 (e)(ii)
label | Inspection/Test Method - Notification
label | Record of conformity - This ITP signed by Contractor
label | WP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.5 - Non-Conforming Bitumen
label | Frequency - As required
label | Acceptance Criteria - If the test results indicate that the bitumen in the tank does not comply with the requirements of the Specification, the bitumen represented by the sample tested must be deemed to be non- conforming and must not be used to manufacture asphalt for the Works. A non-conformance report must be recorded and submitted immediately
label | Reference Documents - Volume 1: HP 5131-3
label | Inspection/Test Method - Submission
label | Record of conformity - NCR / This ITP signed by Contract Administrato r
label | HP
label | Responsibility - Quality Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Bitumen Emulsion and propriety products – Test Certificates
label | Frequency - Not later than 24 hours after each delivery
label | Acceptance Criteria - Each bitumen emulsion delivery must include a compliance test certificate and a delivery docket detailing the quantity, time, and date, both submitted to the Contract Administrator.
label | Reference Documents - Volume 1: Clause 5131 (d)(i)
label | Inspection/Test Method - Submission
label | Record of conformity - Bitumen Emulsion Certificate and docket
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.7 - Asphalt Production – Sampling & Testing
label | Frequency - Each Lot
label | Acceptance Criteria - The number of samples and sets of tests on each nominal size of asphalt produced in the work period must not be less than that specified in Table 5131-4
label | Reference Documents - Volume 1: Clause 5131 (e) (ii)
label | Inspection/Test Method - Verify
label | Record of conformity - Test Report
label | TP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.8 - Daily Bitumen Usage
label | Frequency - Each Lot
label | Acceptance Criteria - During each work period, the quantity of bitumen used in each production run for each nominal size of asphalt mix must be accurately recorded by dipping the bitumen storage tank or by recording the plant digital read- outs before and after each production run. The recorder bitumen usage must be included in the lot submission.
label | Reference Documents - Volume 1: Clause 5131 (e)(iii)
label | Inspection/Test Method - Verify
label | Record of conformity - Asphalt Production Records
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.9 - Mass of Asphalt
label | Frequency - Each Lot
label | Acceptance Criteria - The mass of each nominal size of asphalt mix produced in each work period must be determined, recorded and included in the lot submissions.
label | Reference Documents - Volume 1: Clause 5131 (e)(iv)
label | Inspection/Test Method - Verify
label | Record of conformity - Asphalt Production Records
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.10 - Supplementary Bitumen Content Determination
label | Frequency - Each Lot
label | Acceptance Criteria - Calculate and report the average bitumen content for each nominal size of asphalt based on the total bitumen used and asphalt mass produced, and include it in the lot submissions.
label | Reference Documents - Volume 1: Clause 5131 (e)(v)
label | Inspection/Test Method - Verify
label | Record of conformity - Asphalt Production Records
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.11 - Bitumen Temperature Recording
label | Frequency - Each Lot
label | Acceptance Criteria - The temperature of the bitumen in the storage tank must be recorded at the time of taking every bitumen volumetric reading and at intervals of not less than once every work period.
label | Reference Documents - Volume 1: Clause 5131 (e)(vi)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | 4.12 - Asphalt moisture content
label | Frequency - Each Lot
label | Acceptance Criteria - Asphalt moisture content must be determined at least once per lot when approximately 50% of the asphalt for the planned shift has been manufactured.
label | Reference Documents - Volume 1: Clause 5131 (e)(vii)
label | Inspection/Test Method - Verify
label | Record of conformity - Asphalt Production Records
label | IP
label | Responsibility - Quality Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: