## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP049 - ALER 3 AGL Equipment Installation | itp |  |  |  |  | FH-ZU2-QU-ITP049 - ALER 3 AGL Equipment Installation - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings.
label | — all drawings are the latest revision.
label | Reference Documents - Drawings / Aconex Register
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings and drawing registers
label | HP*
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Survey Checks
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Survey set out to be completed for all assets
label | Reference Documents - Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 1.4 - Submission & approval of shop drawings
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - HOLD POINT
label | Submit shop drawings to the principal’s representative for approval prior to fabrication commencement. Items to include but not limited to:
label | ○ DB-AGL1
label | ○ DB-AGL2
label | ○ CCRs
label | ○ SACs
label | ○ SCOs
label | ○ ILCMS equipment
label | Reference Documents - ZULU-BECA-001-SPC-00005 C2100 Page 10 Drawings 030-3100 set Approved Shop drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project Engineer / Site Engineer / Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Material Submission
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - HOLD POINT
label | Items to include but not limited to:
label | ○ Control Systems
label | ○ Power Control
label | ○ Switchgear
label | ○ Cables
label | Reference Documents - Drawings / Aconex Register
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project Engineer / Site Engineer / Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Off-site Inspections
label | Frequency - Each Lot
label | Acceptance Criteria - WITNESS POINT
label | ○ Switchboards shall be fully tested before leaving the manufacturer’s premises. Inspection and attendance on site for Factory Acceptance Testing for:
label | — Switchboards
label | — Distribution Boards
label | ○ Following these inspections FAT testing shall be submitted.
label | Reference Documents - ZULU-BECA-001-SPC-00005 C2121.20 Page 58 AS/NZS 3000 Drawings 030-3100 set
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, Factory Acceptance Tests
label | WP TP
label | Responsibility - Project Engineer / Site Engineer / Principal’s Representative
date | Date Completed:
section | 2.0 - Construction
checkpoint | 2.1 - Delivery of Materials to site
label | Frequency - Each Lot
label | Acceptance Criteria - Inspection of materials whilst still loaded on the truck prior to accepting the delivery on site.
label | ○ Identify any damage/defects prior to unloading of the material.
label | Reference Documents - ZULU-BECA-001-SPC-00005 Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Materials Inspection Checklist on ConQA
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.2 - Inspection of installed works
label | Frequency - Each Lot
label | Acceptance Criteria - AGL contractor to inspect the installation to confirm suitability and as per design, including but not limited to:
label | ○ Pits
label | ○ Conduits
label | ○ Slabs
label | ○ Structure
label | ○ Cable trays
label | Reference Documents - Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.5 - SCO
label | Frequency - Each Lot
label | Acceptance Criteria - Supply and installation of (Nos.04) SCOs as per drawings and approved shop drawings. Including but not limited to:
label | ○ Cubicle to be plinth mounted
label | ○ Cabling
label | ○ Labelling
label | Reference Documents - AS/NZS 3000 Drawings 030-3100 set Shop Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, ADB Safegate ITC
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.6 - SAC
label | Frequency - Each Lot
label | Acceptance Criteria - Supply and Installation of (Nos 04) SACs (with 36 x SDH-100-2000-PH Surge Diverters per Cubicle) as per drawings and approved shop drawings. Including but not limited to:
label | ○ Cubicle to be plinth mounted
label | ○ Conduit hood installed
label | ○ Cabling
label | ○ Labelling
label | Reference Documents - AS/NZS 3000 Drawings 030-3100 set Shop Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, ADB Safegate ITC
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.7 - ILCMs
label | Frequency - Each Lot
label | Acceptance Criteria - Supply and Installation of ILCMs equipment (including NCU cabinet, ASP cabinet, and existing SFAL) as per drawings and approved shop drawings. Including but not limited to:
label | ○ TFO 200W NO E 6.6A/6.6A 50/60HZ Installed
label | ○ SCF Complete Capsuled Installed
label | ○ Two SCI Series Circuit Inductors Installed
label | ○ Cabling
label | ○ Labelling
label | Reference Documents - AS/NZS 3000 Drawings 030-3100 set Shop Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, ADB Safegate ITC
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.8 - SCM
label | Frequency - Each Lot
label | Acceptance Criteria - Supply and Installation of SCM equipment as per drawings and approved shop drawings. Including but not limited to:
label | ○ SCM Cabinet Modems Labelled
label | ○ OFLEX CLASSIC 110 CY 2x1.5 installed from CCRs to SCM Cabinet
label | ○ OFLEX Cables tied and labelled on the cable tray
label | ○ OFLEX Cables terminated inside the SCM Cabinet
label | ○ SCM Cabinet Energised
label | Reference Documents - AS/NZS 3000 Drawings 030-3100 set
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, ADB Safegate ITC
label | TP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.9 - CCR
label | Frequency - Each Lot
label | Acceptance Criteria - Supply and Installation of CCR equipment as per drawings and approved shop drawings. Including but not limited to:
label | ○ 7.5 kW CRE CCR’s to be installed
label | ○ CCR Power supply Cables with 50A Plugs Installed
label | ○ Cables form CCR SCO to the 2 SCI Series Circuit Inductors with Female Connectors Installed
label | Reference Documents - AS/NZS 3000 Drawings 030-3100 set
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, ADB Safegate ITC
label | TP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.11 - DBs
label | Frequency - Each Lot
label | Acceptance Criteria - Confirm the following items are constructed in accordance with IFC design and specification.
label | ○ Size, colour, location
label | ○ Plinth (if required)
label | ○ Secure and anchored.
label | ○ Labels
label | ○ Tightness & alignment
label | ○ All wiring tidy and neat
label | Reference Documents - ZULU-BECA-001-SPC-00005 C2100.2 AS/NZS 3000 Drawings 030-3100 set
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, ADB Safegate ITC
label | TP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.12 - Cabling – Mains, Submains,
label | Frequency - Each Lot
label | Acceptance Criteria - Confirm the following items are constructed in accordance with IFC design and specification.
label | ○ Type, size, colour, quantities, location
label | ○ Secure
label | Verify and confirm the following tests as per AS/NZS 3000 (not limited to):
label | ○ Polarity Check
label | ○ Cable Loop Resistance (Ohms)
label | ○ Insulation Resistance (Core-Core& Core to Earth)
label | Reference Documents - ZULU-BECA-001-SPC-00005 C2111.5 AS/NZS 3000 Drawings 030-3100 set
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed, ADB Safegate ITC
label | TP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: