## STRUCTURE
STAGE | LEVEL | WINDOW NUMBER
STAGE 1
LEVEL 1
D101B
D102B
D103B
D104B
D105B
D106B
D107B
D108B
D109B
D110B
W1.20
W1.21
W1.22
LEVEL 2
D201B
D202B
D203B
D204B
D205B
D206B
D207B
D208B
D209B
D210B
W2.20
W2.21
W2.22
LEVEL 3
D301B
D302B
D303B
D304B
D305B
D306B
D307B
D308B
D309B
D310B
W3.20
W3.21
W3.22
LEVEL 4
D401B
D402B
D403B
D404B
D405B
D406B
D407B
D408B
D409B
D410B
W4.20
W4.21
W4.22
LEVEL 5
D501B
D502B
D503B
D504B
D505B
D506B
D507B
D508B
D509B
D510B
W5.20
W5.21
W5.22
STAGE 2
INTERNAL
00.02B
00.02C
00.06A
00.07A
00.08C
00.16A
00.18A
CT-W01
GROUND
DG.01
DG.02
LVG.01
LVG.02
LVG.03
LVG.04
WG.03
WG.04
WG.05
WG.06
LEVEL 2
W2.23
W2.24
LEVEL 3
W3.23
W3.24
LEVEL 4
W4.23
W4.24
LEVEL 5
W5.23
W5.24

## CHECKLIST
Windows Installation Checklist
3. INSPECT SITE
3.1 Work area is clean / clear & substrate is acceptable.
3.2 Site measure opening sizes are correct & plumb.
3.3 Rebates & waterproofing membrane is in place.
3.4 Sarking is in place, taped & fully returned into opening.
4. INSPECT PRODUCT
4.1 Doors & Windows received in good condition.
4.2 Windows allocated to correct locations per IFC shop drawings.
5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS:
5.1 Shroud sealed to subhead & subjamb correctly prior to install. (Photo Required)
5.2 Subsill located correctly off grid, relative to building & per IFC shop drawings.
5.3 Subsill installed with U-shaped 3 sided sealant. (Photo Required)
5.4 Subsill fitted with stopends, level, fully sealed & fixings sealed. (Photo Required)
5.5 Subsill water test of a 20% sampling. (Photo required)
5.6 Subhead & subjambs plumb / level, fully sealed & fixings sealed. (Photo Required)
6. INSTALL PERIMETER WEATHER SEAL:
6.1 External & internal 7 sided caulking. (Photo Required)
7. INSTALL & PROTECT WINDOW FRAMES & DOORS:
7.1 Remove all non-accessible protection tape & film. Trade clean glass.
7.2 Frames & doors installed plumb & correct height.
7.3 Windows open / close freely & latching correctly.
7.4 All infills fitted & hardware installed correctly. (Photo Required)
7.5 Sliding door panels secured with fixing kits & height-adjusted to 10mm cover. (Photo Required)
7.6 Protection tape & film to accessible areas. Work area clean. (Photo Required)
8. FINAL ADJUSTMENTS & INSPECTION:
8.1 Correct function of chainwinders, locks, latches hardware, closers etc.
8.2 All thresholds & fillers installed correctly.
8.3 All winder limiters do not exceed 125mm.
8.4 All fly screens installed correctly.
8.5 FINAL CHECK! Window / door is complete & without visible defect. Work area is clean. (Photo Required)