## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Windows Installation
Scope
Rows
|  | STAGE 1 - LEVEL 1 | dynamic | LEVEL 1 | STAGE 1
|  | STAGE 1 - LEVEL 2 | dynamic | LEVEL 2 | STAGE 1
|  | STAGE 1 - LEVEL 3 | dynamic | LEVEL 3 | STAGE 1
|  | STAGE 1 - LEVEL 4 | dynamic | LEVEL 4 | STAGE 1
|  | STAGE 1 - LEVEL 5 | dynamic | LEVEL 5 | STAGE 1
|  | STAGE 2 - INTERNAL | dynamic | INTERNAL | STAGE 2
|  | STAGE 2 - GROUND | dynamic | GROUND | STAGE 2
|  | STAGE 2 - LEVEL 2 | dynamic | LEVEL 2 | STAGE 2
|  | STAGE 2 - LEVEL 3 | dynamic | LEVEL 3 | STAGE 2
|  | STAGE 2 - LEVEL 4 | dynamic | LEVEL 4 | STAGE 2
|  | STAGE 2 - LEVEL 5 | dynamic | LEVEL 5 | STAGE 2
Columns
|  | 3.1 Work area is clean/clear & substrate is acceptable |  | 3.1 Work area is clean / clear & substrate is acceptable. | 3. INSPECT SITE
|  | 3.2 Site measure opening sizes are correct & plumb |  | 3.2 Site measure opening sizes are correct & plumb. | 3. INSPECT SITE
|  | 3.3 Rebates & waterproofing membrane is in place |  | 3.3 Rebates & waterproofing membrane is in place. | 3. INSPECT SITE
|  | 3.4 Sarking is in place, taped & fully returned into opening |  | 3.4 Sarking is in place, taped & fully returned into opening. | 3. INSPECT SITE
|  | 4.1 Doors & Windows received in good condition |  | 4.1 Doors & Windows received in good condition. | 4. INSPECT PRODUCT
|  | 4.2 Windows allocated to correct locations per IFC shop drawings |  | 4.2 Windows allocated to correct locations per IFC shop drawings. | 4. INSPECT PRODUCT
|  | 5.1 Shroud sealed to subhead & subjamb correctly prior to install |  | 5.1 Shroud sealed to subhead & subjamb correctly prior to install. (Photo Required) | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS
|  | 5.2 Subsill located correctly off grid, relative to building & per IFC shop drawings |  | 5.2 Subsill located correctly off grid, relative to building & per IFC shop drawings. | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS
|  | 5.3 Subsill installed with U-shaped 3 sided sealant |  | 5.3 Subsill installed with U-shaped 3 sided sealant. (Photo Required) | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS
|  | 5.4 Subsill fitted with stopends, level, fully sealed & fixings sealed |  | 5.4 Subsill fitted with stopends, level, fully sealed & fixings sealed. (Photo Required) | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS
|  | 5.5 Subsill water test of a 20% sampling |  | 5.5 Subsill water test of a 20% sampling. (Photo required) | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS
|  | 5.6 Subhead & subjambs plumb/level, fully sealed & fixings sealed |  | 5.6 Subhead & subjambs plumb / level, fully sealed & fixings sealed. (Photo Required) | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS
|  | 6.1 External & internal 7 sided caulking |  | 6.1 External & internal 7 sided caulking. (Photo Required) | 6. INSTALL PERIMETER WEATHER SEAL
|  | 7.1 Remove all non-accessible protection tape & film. Trade clean glass |  | 7.1 Remove all non-accessible protection tape & film. Trade clean glass. | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS
|  | 7.2 Frames & doors installed plumb & correct height |  | 7.2 Frames & doors installed plumb & correct height. | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS
|  | 7.3 Windows open/close freely & latching correctly |  | 7.3 Windows open / close freely & latching correctly. | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS
|  | 7.4 All infills fitted & hardware installed correctly |  | 7.4 All infills fitted & hardware installed correctly. (Photo Required) | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS
|  | 7.5 Sliding door panels secured with fixing kits & height-adjusted to 10mm cover |  | 7.5 Sliding door panels secured with fixing kits & height-adjusted to 10mm cover. (Photo Required) | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS
|  | 7.6 Protection tape & film to accessible areas. Work area clean |  | 7.6 Protection tape & film to accessible areas. Work area clean. (Photo Required) | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS
|  | 8.1 Correct function of chainwinders, locks, latches hardware, closers etc. |  | 8.1 Correct function of chainwinders, locks, latches hardware, closers etc. | 8. FINAL ADJUSTMENTS & INSPECTION
|  | 8.2 All thresholds & fillers installed correctly |  | 8.2 All thresholds & fillers installed correctly. | 8. FINAL ADJUSTMENTS & INSPECTION
|  | 8.3 All winder limiters do not exceed 125mm |  | 8.3 All winder limiters do not exceed 125mm. | 8. FINAL ADJUSTMENTS & INSPECTION
|  | 8.4 All fly screens installed correctly |  | 8.4 All fly screens installed correctly. | 8. FINAL ADJUSTMENTS & INSPECTION
|  | 8.5 FINAL CHECK! Window/door is complete & without visible defect. Work area is clean |  | 8.5 FINAL CHECK! Window / door is complete & without visible defect. Work area is clean. (Photo Required) | 8. FINAL ADJUSTMENTS & INSPECTION