## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Windows Installation Checklist
section | 3. INSPECT SITE
checkpoint | 3.1 Work area is clean / clear & substrate is acceptable.
checkpoint | 3.2 Site measure opening sizes are correct & plumb.
checkpoint | 3.3 Rebates & waterproofing membrane is in place.
checkpoint | 3.4 Sarking is in place, taped & fully returned into opening.
section | 4. INSPECT PRODUCT
checkpoint | 4.1 Doors & Windows received in good condition.
checkpoint | 4.2 Windows allocated to correct locations per IFC shop drawings.
section | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS:
checkpoint | 5.1 Shroud sealed to subhead & subjamb correctly prior to install. (Photo Required)
checkpoint | 5.2 Subsill located correctly off grid, relative to building & per IFC shop drawings.
checkpoint | 5.3 Subsill installed with U-shaped 3 sided sealant. (Photo Required)
checkpoint | 5.4 Subsill fitted with stopends, level, fully sealed & fixings sealed. (Photo Required)
checkpoint | 5.5 Subsill water test of a 20% sampling. (Photo required)
checkpoint | 5.6 Subhead & subjambs plumb / level, fully sealed & fixings sealed. (Photo Required)
section | 6. INSTALL PERIMETER WEATHER SEAL:
checkpoint | 6.1 External & internal 7 sided caulking. (Photo Required)
section | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS:
checkpoint | 7.1 Remove all non-accessible protection tape & film. Trade clean glass.
checkpoint | 7.2 Frames & doors installed plumb & correct height.
checkpoint | 7.3 Windows open / close freely & latching correctly.
checkpoint | 7.4 All infills fitted & hardware installed correctly. (Photo Required)
checkpoint | 7.5 Sliding door panels secured with fixing kits & height-adjusted to 10mm cover. (Photo Required)
checkpoint | 7.6 Protection tape & film to accessible areas. Work area clean. (Photo Required)
section | 8. FINAL ADJUSTMENTS & INSPECTION:
checkpoint | 8.1 Correct function of chainwinders, locks, latches hardware, closers etc.
checkpoint | 8.2 All thresholds & fillers installed correctly.
checkpoint | 8.3 All winder limiters do not exceed 125mm.
checkpoint | 8.4 All fly screens installed correctly.
checkpoint | 8.5 FINAL CHECK! Window / door is complete & without visible defect. Work area is clean. (Photo Required)