## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
da108f56-2cf7-4bea-900d-09b14be0acdb/1 | checklist | Windows Installation Checklist |  | Windows Installation Checklist |  | 1a6073f0-c1bc-41d9-a9f9-71dc655acd55
727ba50e-1f09-4cce-a9e8-9f6163ec8158 | section | 3. INSPECT SITE
f8a85932-ca23-49a8-870b-24b3c9391d7c | checkpoint | 3.1 Work area is clean / clear & substrate is acceptable.
9fd76142-1140-4efd-bba6-9e883afab6b3 | checkpoint | 3.2 Site measure opening sizes are correct & plumb.
8c702b1f-d1d2-42b3-83b6-43a37a3a9bb5 | checkpoint | 3.3 Rebates & waterproofing membrane is in place.
8bf5b0d6-71e0-4242-a12b-c80a28297759 | checkpoint | 3.4 Sarking is in place, taped & fully returned into opening.
21be1064-d918-4b16-8071-b786d5aafd72 | section | 4. INSPECT PRODUCT
359004ba-74b1-45a4-abee-042b1b2eb53a | checkpoint | 4.1 Doors & Windows received in good condition.
ffd8d308-8651-4236-8391-8d3098d4fd3f | checkpoint | 4.2 Windows allocated to correct locations per IFC shop drawings.
2bb74f0f-101e-492a-9f7c-4d55c409ee50 | section | 5. INSTALL SUBHEADS, SUBSILLS, SUBJAMBS & SHROUDS
2b8e6f8f-0aeb-4374-9afa-460448d7c613 | checkpoint | 5.1 Shroud sealed to subhead & subjamb correctly prior to install. (Photo Required)
cf90c63e-75f4-4510-9cd6-383777218d55 | checkpoint | 5.2 Subsill located correctly off grid, relative to building & per IFC shop drawings.
e6666a7c-6448-4bd1-bbe0-c4749fe93c99 | checkpoint | 5.3 Subsill installed with U-shaped 3 sided sealant. (Photo Required)
10a3c4e6-4824-461b-a534-4fd27b4b8f7a | checkpoint | 5.4 Subsill fitted with stopends, level, fully sealed & fixings sealed. (Photo Required)
dbca755d-107b-4b51-b9d3-5d90068bc41d | checkpoint | 5.5 Subsill water test of a 20% sampling. (Photo required)
29b0726b-00ab-4950-9000-6c69354b83ba | checkpoint | 5.6 Subhead & subjambs plumb / level, fully sealed & fixings sealed. (Photo Required)
8185fd9e-ab4b-457f-be2f-4d527a211e9d | section | 6. INSTALL PERIMETER WEATHER SEAL
e0eb6a1b-9d91-4560-8024-343ea590cb32 | checkpoint | 6.1 External & internal 7 sided caulking. (Photo Required)
df06c9be-8128-4c47-8326-b243b324e2a6 | section | 7. INSTALL & PROTECT WINDOW FRAMES & DOORS
7b3af715-5d1f-4da4-ba10-3f958431d2ea | checkpoint | 7.1 Remove all non-accessible protection tape & film. Trade clean glass.
c1bf723c-b0fd-41fc-ac60-12da2a7b1485 | checkpoint | 7.2 Frames & doors installed plumb & correct height.
31ab969c-89f9-48f1-b0d3-6c177918e198 | checkpoint | 7.3 Windows open / close freely & latching correctly.
89156a29-02e9-4cec-b0a3-b0d6b57e2b09 | checkpoint | 7.4 All infills fitted & hardware installed correctly. (Photo Required)
71f7df04-4b50-47f1-924f-8fe80e5a4a8d | checkpoint | 7.5 Sliding door panels secured with fixing kits & height-adjusted to 10mm cover. (Photo Required)
aca8998a-07e1-4554-b4e0-f2024dfe99dc | checkpoint | 7.6 Protection tape & film to accessible areas. Work area clean. (Photo Required)
1ef09b6b-0c56-4eb4-b299-b12f3d8cf3d9 | section | 8. FINAL ADJUSTMENTS & INSPECTION
dbecc4de-a4f4-418f-bdbb-c06a06d7a97b | checkpoint | 8.1 Correct function of chainwinders, locks, latches hardware, closers etc.
004ae1d2-ed5f-4e08-aa40-0eafa5919b01 | checkpoint | 8.2 All thresholds & fillers installed correctly.
9c80627a-9b79-44c5-9f40-e86dadedcf56 | checkpoint | 8.3 All winder limiters do not exceed 125mm.
5dc9ec40-01eb-4c56-b625-71e8f8f6fc31 | checkpoint | 8.4 All fly screens installed correctly.
80c1ca40-de68-40bd-b4d3-e673bfe20d10 | checkpoint | 8.5 FINAL CHECK! Window / door is complete & without visible defect. Work area is clean. (Photo Required)