## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
1160a0dd-a4be-5fa8-a1d1-ab35e05c56b0 | checklist | Add Dayworks Checklist |  | Dayworks | feb8889b-f085-4036-a74a-d10f9db6ebea
2d1f5d57-dc93-5aff-98dd-91532b123bc6 | checkpoint | Has an ATS / SI been received for this work
c202477a-d92d-4389-a502-b981fa335613 | textbox | Person requesting work:
dd7e962b-77f3-4dda-95d8-cc30ee0cf4db | textbox | Description of work
439b0f70-210b-4082-b5de-02ed56114b70 | textbox | Labour / operative undertaking work
0ac387b4-c483-4cbb-b1d7-04eff1209305 | textbox | Hours Worked:
fa2324f1-38d1-4614-8ef1-58a1393f1df9 | textbox | Materials Used:
f2e42fec-c4f0-5517-bba6-c7836c0af86d | checkpoint | Job Completed Satisfactorily
683a7547-43ae-5590-bcbc-a142953938db | checkpoint | Signed Off
edc345a4-18b4-519d-98a9-da58afd62bdf | checklist | QA - Rockwall |  | QA - Rockwall | e0e25c97-2e5a-4a81-892e-cf17530d73a1
676f10d4-88c8-5c20-84bb-2d093eb0994b | checkpoint | Plan identifying location of Rockwall followed
de686d72-804c-56c5-a299-329a006da28f | checkpoint | Rockwall cut to correct size 150mm past Tall wall/Firefly each side
8af8aa41-c9ac-5aa0-929c-2ec376f140e0 | checkpoint | Trapezoidal Rockwall fitted correctly to underside of Traydeck
0c9f90aa-cbce-570b-a0ad-d3503b140170 | checkpoint | Galv support angles fitted correctly 150mm each side
b5366393-bcb3-5c8d-af56-e6412de661fb | checkpoint | Inspection carried out ( note person / Time )
482c3b96-9cb2-5aca-9cc7-8b6e15c8b11a | checkpoint | Area complete
6b33b381-05e8-59ee-bd8a-9630eaf09545 | checkpoint | Request Sign Off

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Cavity Install |  | Cavity Install | 7aa659be-da8a-415f-b6d5-46eac762c2eb
| checkpoint | Plans and Specs followed ( please indicate)
| checkpoint | Fixed at correct centres for Claddings
| checkpoint | Fixing method correct
| checkpoint | Fixing type
| checkpoint | Fixing when penetrating Reavealshield is sealed correctly
| checkpoint | Drainage applied
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Wall complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Fire Baffle |  | Fire Baffle | bf25f155-161b-4b6f-ad33-92834a5f2cb5
| checkpoint | Interbatt cut to correct size
| checkpoint | Intermastic applied to bottom of truss
| checkpoint | Intermastic applied between layers
| checkpoint | Intermastic brushgrade applied to sheet edges
| checkpoint | 150MM Rockwool support fixed in correct position
| checkpoint | Rockwool cut to size
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Truss area complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Firefly |  | Firefly | b69d1377-9ed3-4f67-89f9-f9677903ca43
| checkpoint | Plan identifying location of Firefly followed
| checkpoint | Firefly to full depth of Purlin
| checkpoint | 50x25x.7 Galv angle fixed to purlin at 250c with 8g Tex Screws
| checkpoint | 25x.7 Galv Steel flat screwed to Durra Panel at 250c with 8g Tex Screws
| checkpoint | Minimum 150mm Laps at joins
| checkpoint | All ends complete into truss
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Gutter |  | Gutter | fbec7777-6e8c-4bc1-862f-b67e13239eee
| checkpoint | Material and guage is correct ( Please note )
| checkpoint | Plans followed and gutter heights/falls established
| checkpoint | Brackets installed correctly
| checkpoint | Steel Studs cut to correct length
| checkpoint | Steel Studs at correct centres ( please indicate )
| checkpoint | Sump locations identified
| checkpoint | Other specific Engineer details
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Gutter complete for tray
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Insulation |  | Insulation | 0f7b244e-d194-4880-8d6e-1cfefad54fb2
| checkpoint | Correct Size and R Value ( Please indicate )
| checkpoint | Insulation Friction fitted
| checkpoint | Strapping required
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Area complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Louvre Install Checklist |  | Louvre Install Checklist | 84342e7e-0aae-4bcd-8200-739af790bfa5
| checkpoint | Area clear wraps / tapes / flashing installed
| checkpoint | Correct louvre for location
| checkpoint | Check louvre for damage before install
| checkpoint | Louvre installed plumb
| checkpoint | Angle fixed with correct screws and correct spacings (identify)
| checkpoint | Hand over (area left clean)
| checklist | Ortech Infill Panel |  | Ortech Infill Panel | 56ef1861-c306-4d91-8be6-b6bf3bbdf18f
| checkpoint | Silicon drawings followed
| checkpoint | Bridging tees fixed
| checkpoint | 75mm Insulation cassette fitted into location
| checkpoint | Durra Panel fitted into location
| checkpoint | Back Wedges fitted to secure panels
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Ortech Panel System |  | Ortech Panel System | eac9e85c-4aad-496e-bf60-61c021cd6ef5
| checkpoint | Silicon drawings followed
| checkpoint | Correct I purlins located
| checkpoint | Bridging tees bolted with fixings provided
| checkpoint | Panel Frame complete
| checkpoint | 75mm Insulation cassette fitted into location
| checkpoint | Durra Panel fitted into location
| checkpoint | Back Wedges fitted to secure panels
| checkpoint | Panel Lifted into place
| checkpoint | Panel bolted with M20 Galv bolts @ 40mm
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Parapets |  | Parapets | b7f26999-670e-4314-96ab-8bc09202f1cf
| checkpoint | Material and guage is correct ( Please note )
| checkpoint | Track setout is in correct location
| checkpoint | Tracks are bolted/fixed as per Engineers plan
| checkpoint | Studs Installed correctly ( Specify studs centres and fixing type)
| checkpoint | Nogging installed correctly
| checkpoint | Nogging in place for services and sheet joins
| checkpoint | Wall is plumb and straight
| checkpoint | Other specific Engineer details
| checkpoint | Penetrations formed correctly
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Wall complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Plasterboard |  | Plasterboard | 8eaab8b1-a052-4f1d-bc66-65114e90bbbd
| checkpoint | Wall type identified correctly
| checkpoint | Correct Plasterboard cut to shape
| checkpoint | Plasterboard installed to location
| checkpoint | Screws correct size and centres ( please identify )
| checkpoint | Plaster applied to screwheads
| checkpoint | All joints single coat plaster with papertape
| checkpoint | Fire/Acoustic applied neatly where required (please identify )
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | RAB |  | RAB | 9d386403-6239-4a1c-a0cf-282b5b706517
| checkpoint | Plans and Specs followed
| checkpoint | Thermal break in place and inspected ( note person / time )
| checkpoint | All back flashings in place if required
| checkpoint | Sheets cut neatly and 1-2mm gaps at join
| checkpoint | Correct screwing . Specify type and centres
| checkpoint | Siesmic joints required
| checkpoint | Penetrations neatly formed
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Wall complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Revealshield and Liquiflash |  | Revealshield and Liquiflash | 48004dba-e5b4-4d28-b2c5-cdd83543b58f
| checkpoint | RAB or surface is clean of debris and moisture
| checkpoint | Direction of Installation ( Horizontal / Vertical )
| checkpoint | Revealshield rolled neatly at seams and throughout
| checkpoint | All laps 6 inches Horizontally or 3 inches Vertically
| checkpoint | Seams staggered vertically
| checkpoint | Laps are correct
| checkpoint | Backlaps are Liquiflashed
| checkpoint | Revealshield cut neat around penetrations
| checkpoint | Liquiflash is applied neatly around penetrations
| checkpoint | Liquiflash Inspection prior to installation of Windows and alike
| checkpoint | Aluminium tape used at transitions of other products
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Wall complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Roofing Iron |  | Roofing Iron | 0856e460-5e5d-4757-994e-1247de38d40f
| checkpoint | Material and guage is correct ( Please note )
| checkpoint | Sheets procured to right size
| checkpoint | Sheet mechanically fixed with screws provided to location
| checkpoint | Laps are correct
| checkpoint | Sheets perpendicular to purlins
| checkpoint | Sheets cut neatly around penetrations
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Steel Stud |  | Steel Stud | 0d1c3900-5f19-4f93-9fda-1ca76d940486
| checkpoint | Material and guage is correct ( Please note )
| checkpoint | Track setout is in correct location
| checkpoint | Tracks are bolted/fixed as per Engineers plan
| checkpoint | Studs Installed correctly ( Specify studs centres and fixing type)
| checkpoint | Nogging installed correctly
| checkpoint | Nogging in place for services and sheet joins
| checkpoint | Wall is plumb and straight
| checkpoint | Other specific Engineer details
| checkpoint | Penetrations formed correctly
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Wall complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off
| checklist | Tall Wall Encasement Framing |  | Tall Wall Encasement Framing | 9e812835-508d-431a-83a1-4f76ee02e1d4
| checkpoint | Plans / specs followed, correct type of timber used
| checkpoint | Check for location
| checkpoint | Top and Bottom plates correct fixings and spacings
| checkpoint | Studs correct fixings
| checkpoint | Correct centres
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area complete
| signoff | Request Sign Off
| checklist | Tall Wall Encasement Gib Linnings |  | Tall Wall Encasement Gib Linnings | c149a66f-5cc9-4398-bb7f-d076979197c5
| checkpoint | Gib type identified correctly
| checkpoint | Correct Plasterboard cut to shape
| checkpoint | Plasterboard installed to location (Tall Wall Beam)
| checkpoint | Screws correct size and centres ( please identify )
| checkpoint | Correct staggered sheets ( 300mm staggered )
| checkpoint | Plaster applied to screwheads
| checkpoint | All joints single coat plaster with papertape
| checkpoint | Fire sealant applied neatly where required ( please identify )
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area complete
| checkpoint | Revealshield applied as temporary watertightness
| signoff | Request Sign Off
| checklist | Timber Framing |  | Timber Framing | bde44c7d-824e-478c-8cfe-2e3734845883
| checkpoint | Material size and treatment is correct ( please indicate )
| checkpoint | DPC or Separartion required
| checkpoint | Check for correct location
| checkpoint | Plates fixed correctly ( specify fixing / Size / Centres )
| checkpoint | Studs Installed at correct centres ( indicate )
| checkpoint | Nogs installed correcting
| checkpoint | Nogging in place for services and sheet joins
| checkpoint | Wall is plumb and straight
| checkpoint | Other specific Engineer details
| checkpoint | Penetrations formed correctly
| checkpoint | Inspection carried out ( note Person / Time )
| checkpoint | Area left clean
| checkpoint | Wall complete
| checkpoint | Request Sign Off
| signoff | Add Signature / Request Sign Off