## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
be1fd787-0228-4fbc-91a6-aec2900758ce | checklist | V&B Underground services |  | V&B Underground services | 60baf8cd-58b5-4770-b38a-e2156a1a55ec
e0fbb1ad-5a95-4b02-bdd0-666d00da233c | section | Details
540eda5f-4c08-4b87-bffa-3fec9d9c365c | checkpoint | Location reference attached
f5938893-632b-58f3-825f-06bcc03fb107 | textbox | Description
0e4b34eb-132c-5777-b5da-c1063c647ce2 | dropdown | Service type | Hydraulics,Electrical
7581d4b6-2e2a-4f77-8f78-7a83d545bb70 | checkpoint | Setout/Excavation depth
09233f41-24b4-511c-94d5-010ab02f2357 | textbox | Excavation depth
002a864a-5c03-4f50-b850-5d75e0bc5ad6 | checkpoint | Subgrade testing and results
c262309f-6bb5-54bb-8f35-11dcfe81264a | note | Any soft sopts or undercut & associated remedial
1268241d-9387-4af8-b305-8f456e572bb0 | checkpoint | Granular type
b3669f0a-1ccf-401b-b49d-4f6d65d3c152 | checkpoint | Protection tape, tracerwire, magslab installed
68c471c8-77f0-49f0-bad7-34f681b04b4a | checkpoint | Backfill - GAP20 (150mm thickness)
92e451ae-189b-47db-8c98-1afd41557705 | checkpoint | Structual backfill (ATAP65/GAP65 200mm lifts)
96070988-88f0-4a7c-bc30-21a06e53348c | checkpoint | As-builts
dd021541-9832-4c16-9b33-63bd755d56db | checkpoint | Final Pass: Service works completed, reviewed and approved
e97fa2cb-c323-5308-b78c-fd38310def28 | note | Attach As-Built
b2bcf328-35d0-57f9-b12c-e1f0fa7f856c | note | FINAL - Pass when work(s) are completed, area clean & tidy

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | General - Upload of Documentation (V2) |  | Upload of - | 5ee361c1-9e5a-489c-b4e7-6541a8d6fa30
| checkpoint | Documentation filled out & attached
1cd6f3b0-7d1e-4d08-a052-48628074942f | note | Select "PASS" once the pdocumentation is completed and uploaded here
| signoff | Request Review
| checklist | H&S - Upload of Daily H&S Paperwork (V2) |  | H&S Upload of - | 6e976d07-6dcf-43b5-b83b-3410a45715e9
| checkpoint | H&S Paperwork filled out & attached
1cd6f3b0-7d1e-4d08-a052-48628074942f | note | Select "PASS" once the paperwork is completed and uploaded here
| signoff | Request Review
| checklist | QA - Bulk Excavation Checklist (V1) |  | Bulk Excavation Weekly Checks - | 49c1ecbc-c85d-42bb-b115-4ba4b3f6878f
| checkpoint | General Photos / Comments / Observations during excavation
| checkpoint | Excavation checked, correct and approved
f5416416-454b-47e2-9e94-536c885525ad | tickbox | Location accurate
29b8b571-2ab6-41ef-b1e0-6400d67a0008 | tickbox | Depth correct
2893f2fa-05ef-4e42-b40d-4f1ee99f040c | tickbox | Width correct
9645687c-aa81-43db-be7a-1e182504b26b | button | Any relevant setout / survey works recorded | Yes, N/A
| checkpoint | Excess Material Cleaned up and removed as required
| checkpoint | All relevant weekly loads recorded using load scanner
38ce68e3-e3aa-4f46-91a2-9277f931e69e | textbox | Total Volume Removed
7fe288ef-998f-4fda-849b-c9e72f78c906 | tickbox | Record of loads attached
| checkpoint | Bulk excavation weekly checks completed, reviewed and approved
da0d9f6c-b7dd-4942-9c51-aa10264b5a52 | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
| signoff | Request for approval/sign off
| checklist | QA - Detailed Excavation Checklist (V1) |  | Detailed Excavation Checklist (V1) - | 30d02cab-f59e-4c04-a988-0772f540021a
| checkpoint | Location reference attached
| checkpoint | General Photos / Comments / Observations during excavation
| checkpoint | Any soft spots or undercuts & associated remedial
| checkpoint | Excavation checked, correct and approved off accurate survey marks
2b89ec27-c336-4010-812b-3572b48a6398 | note | Location accurate
4cd6058a-d4b5-443b-b020-5298d87f46f8 | note | Depth correct (allow for site concrete if required)
cac3df3d-08aa-4e1c-a351-ab7a7b606c98 | note | Width correct (allow for boxing if required)
| checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
| checkpoint | Excess Material Cleaned up and removed as required
| checkpoint | Detailed excavation completed, reviewed and approved
c9f2aeeb-ceeb-4f85-9454-8ccdb83c2c79 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
377fa921-5de8-47c7-a536-cabb3d4de6a8 | button | Trades QA received & attached as applicable | PASS, N/A
| checklist | QA - Ductbanks |  | QA - Ductbanks | 3fc3f9b7-f9d7-4548-8012-b9abd9a020be
| section | Ductbanks
| checkpoint | Conduits were laid as per approved shop drawings
| signoff | Request signoff
| checkpoint | Conduits are joined & terminated in accordance to the manufacturers instructions and specifications
| checkpoint | Permanent adhesives were used, water-tight joints was made in conjunction with standard accessories
| checkpoint | Conduits saddles are provided prior to sand backfilling
| checkpoint | Concrete topping for duct bank is as per specifications
| checkpoint | Backfilled as per drawings and specifications
| checkpoint | Tracer wire, magslab and warning tape provided
| checkpoint | Ducts cleaned and tested and handed over to electrical/Telecom contractor
| section | Installation
| checkpoint | Installation Tested
| checkpoint | Subgrade tested and passed
636d4d5a-d442-5371-9c86-855c937b1a22 | textbox | Any undercutting required?
f07f9009-59a2-534e-9a59-2b39181c2e90 | textbox | Undercutting/other remedials as instructed by Jacobs (if required)
| checkpoint | Bedding material placed and compacted
31648032-4a41-59a7-80d0-d6b790024d4a | textbox | Cleggs/NDM test results for bedding:
| checkpoint | Geotextile installed (if applicable)
| checkpoint | Backfill material placed and compacted
b2054284-cfa4-56b8-b3a9-a7b4318454e3 | textbox | Cleggs/NDM test results for backfill:
| checkpoint | Geogrid installed (if applicable)
| checkpoint | Service placed at design RL?
| checkpoint | Invert levels checked and correct
| checkpoint | Voids filled with epoxy mortar or concrete
| checkpoint | Trades QA completed, received & reviewed
| checkpoint | General progress photos recorded
| signoff | Request signoff
| checklist | QA - Ductbanks |  | Ductbanks QA for Area: | a80d10f8-6527-454c-8145-cbdd9da25c2d
| checkpoint | Conduits were laid as per approved shop drawings
| signoff | Request signoff
| checkpoint | Conduits are joined & terminated in accordance to the manufacturers instructions and specifications
| checkpoint | Permanent adhesives were used, water-tight joints was made in conjunction with standard accessories
| checkpoint | Conduits saddles are provided prior to concrete pouring
| checkpoint | Concrete encasement for duct bank is as per specifications
| checkpoint | Backfilled as per drawings and specifications
| checkpoint | Tracer wire, magslab and warning tape provided
| checkpoint | General progress photos recorded
| checkpoint | Ductbanks QA completed, received & reviewed
| signoff | Request signoff
| checklist | QA - Earthing |  | QA - Earthing | f8c01173-5398-4628-9800-018231459137
| checkpoint | Points to be bonded is according to approved shop drawing
| checkpoint | Correct size and type of earth cable is provided
| checkpoint | Moulding to be use is correct size and type
| checkpoint | No visible damage to cable to be used
| checkpoint | Moulding should be clean and no heavy visible damage
| checkpoint | Disk seat should not be worn or chipped
| checkpoint | No exposed conductor within the caldweld connection
| checkpoint | Trades QA completed, received & reviewed
| checkpoint | General progress photos recorded
| signoff | Request signoff
| checklist | QA - Permanent Lime Stabilisation Checklist (V2) |  | Permanent Lime Stabilisation Checklist (V2) | 7e3ef3c0-0ce3-4157-9f97-bff301b4a79b
| section | Pre-Excavation
| checkpoint | Pre-excavation checks completed & approval to excavate
a6b2a3a8-6d15-42da-9ea9-263d26ddd957 | tickbox | Prestart completed and recorded (both for plant and activity)
474d7465-d025-4834-ad75-fb994c4d8837 | tickbox | Area accessible & acceptable
170eb730-bbae-4faf-879f-06c7ac67dd6a | tickbox | All workers signed onto TA
360f6b08-248f-49ca-b4ea-1a4fab5aa108 | tickbox | Hazardous substance register completed and reviewed
22ee934a-41ea-47a3-b992-7484c36ef793 | tickbox | Appropriate PPE and H&S precautions in place
| section | Pre-Stabilisation
| checkpoint | Location reference attached/detailed below
af4babc3-93d2-4bd5-9f49-424340bd1450 | textbox | Location / Grids:
| checkpoint | Weather: Is the weather acceptable? Record forecast conditions (Temp > 10°C, Wind < 25km/hr & No rain forecast)
| checkpoint | Survey: Design RL achieved? (+0mm and -30mm)
2fe4e9fc-14ed-4dc8-9cb7-6b1e6bef2faf | note | Spot check, location reference attached
| checkpoint | Survey: 3m straight edge on final level (10mm variance)
2ecb7573-debe-4b31-891f-c4dd0c871a8a | note | Spot checks
| checkpoint | Curing: Previously stabilised lift has been kept sufficiently moist to maintain OWC prior to placing of successive layer
| checkpoint | Stabilisation: Virgin material reviewed across area of intended stabilisation and confirmed as similar to material from plateau test
| checkpoint | Testing: Shear vane strength of in situ subgrade material acceptable
0e95567f-c955-415b-9420-5624ccf3ad5a | note | Ave for 10 consecutive tests > 140kPa, min > 100kPa (min 1 shear vane per 100m3)
| checkpoint | Pre-Stabilisation checks completed & approval to stabilise
| signoff | Request sign off
| section | Stabilisation and Compaction
| checkpoint | Plant: Record of plant on site used for stabilisation operation
| checkpoint | Duragrid: Type and spec as per drawing requirements (each roll checked)
| checkpoint | Duragrid: Placement and overlaps at joints as per drawing requirements (checked each 100m2)
f4bfa60f-78c9-4e3f-b907-fa64328a354a | note | Location and cross section reference attached
| checkpoint | Stabilisation: Lime and cement sheet testing performed and acceptable (1 test per 500m2)
| checkpoint | Stabilisation: Lime and cement material dockets uploaded
| checkpoint | Stabilisation: Continuity of stabilised layer (successive cuts shall lap by 1m min)
| checkpoint | Stabilisation: Overlapping on longitudinal joints (min of 100mm or 1/2 of layer depth, whichever is greater)
| checkpoint | Stabilisation: Rate of water application determined and agreed upon with Gideon?
64f99297-1348-4fbf-a3ce-8699f38236ca | textbox | Rate of Water Application:
| checkpoint | Stabilisation: Is the particle size distribution acceptable? Record number of pulveriser passes (minimum 2 passes)
97cb2cca-2c93-4b9a-8b0a-be22666cd134 | note | Provide photo(s)
| checkpoint | Stabilisation: Homogeneity achieved throughout depth of stabilised layer
b40ec094-4907-47a6-af44-19c583b43308 | note | Provide photo(s)
| checkpoint | Survey: Layer depth checks completed & within design layer tolerance (+0mm and -30mm)
| checkpoint | Testing: USC Sample for unconfined compressive strength testing (1 UCS test per lift)
| checkpoint | Stabilisation: Time between mixing and primary compaction of stabilised material is less than 2 hours?
| checkpoint | Stabilisation and compaction checks completed & approval to cure
c9fc1fda-d3c0-41f2-9176-3efb74831b69 | textbox | Compaction: What is the optimum number of roll passes determined from plateau testing?
93b3b2da-ca5e-4c2c-82b8-75faad74a548 | textbox | Compaction: What is the number of roll passes performed on site?
843ac3fe-5428-4320-802f-e7a35850d52d | textbox | Compaction: Who witnessed the final roll (i.e. proof roll)?
679821a7-8c86-4d04-9d9e-60d5f3ddbb23 | button | Compaction: Were there any soft spots/anomalies found? If so, attach a location reference for the area and confirm necessary remedy agreed upon | Yes, No, N/A
9187e704-3364-4de2-8ad8-aed76ebcbebf | textbox | If so, attach a location reference for the area and confirm necessary remedy agreed upon
| section | Preliminary Testing Results / Stabilisation Close Out
| checkpoint | Survey: Extents of stabilised areas clearly marked on site
| checkpoint | Testing: 95% MDD achieved
| checkpoint | Testing: Scala results of stabilised material acceptable (based off current calibration)
3ba45e52-1353-4a3b-b2f1-fbc875e340a8 | textbox | Testing: What is the current acceptable Scala calibration determined for stabilised material?
| checkpoint | Testing: Shear vane strength of stabilised material acceptable
8d444aa0-d0e6-403f-8abc-798efd42675a | note | Ave for 10 consecutive tests > 160kPa, min > 125kPa (min 1 shear vane per 100m3)
| checkpoint | HSE: Lime and cement is sufficiently mixed and dust is sufficiently supressed. Hawkins Ops Staff contacted to review site conditions to determine necessity of P2 masks
| checkpoint | Curing: Stabilised lift is kept sufficiently moist with watercart to maintain OWC while surface is exposed
| checkpoint | Preliminary testing results acceptable and stabilisation close out procedures completed
| signoff | Request sign off
| section | Review and Handover
| checkpoint | Sent necessary information to Hawkins/Jacobs Geotechnical Engineer for review
| checkpoint | Testing: Geotechnics final reports for NDM, shear vane and UCS (>320kPa) received and acceptable
7c326904-8eb1-4e6d-8f39-15b216ba47b4 | button | Was a Jacobs representative on site? | Yes, No, N/A
34f4c3e5-bf86-4c6e-9e1e-b37293e62085 | textbox | If so, what advise or changes to the ITP or Methodology were instructed/agreed upon on site (if any).
| signoff | Request sign off
| checklist | QA - Pipe Laying |  | QA - Pipe Laying | 1a9406d4-a00f-4277-9736-52490ade26ac
| section | Pipelaying
| checkpoint | Pipes were laid as per approved shop drawings
| checkpoint | Pipe grades are in accordance with the drawings
| checkpoint | Pipe materials comply with specifications
| checkpoint | Trench excavation to line level and grade
| checkpoint | Correct bedding provided
| checkpoint | Jointing system as per specifications and manufacturers recommendation
| checkpoint | Anchor/ thrust block provided (if any)
| checkpoint | Pipes flushed and cleaned
| checkpoint | Pipes tested in accordance with specifications
| signoff | Inspected by local authority (Council)
| checkpoint | Vents/rodding eye installed (If any)
| checkpoint | CCTV provided
| section | Installation
| checkpoint | Installation tested
| checkpoint | Subgrade tested and passed
12a0cde5-c3e3-5036-b348-2f9a4d1795db | textbox | Any undercutting required?
28b1c3a4-8f1d-5399-b3c7-ee6ecc6b25cf | textbox | Undercutting/other remedials as instructed by Jacobs (if required)
| checkpoint | Geotextile installed (if applicable)
| checkpoint | Bedding material installed to correct level
| checkpoint | Side support material installed to the correct level
| checkpoint | Haunching?
| checkpoint | Pipe benched with 25Mpa concrete inside the manhole
| checkpoint | 25Mpa concrete corbel around inlet and outlet pipes
| checkpoint | Voids filled with epoxy mortar or concrete
| checkpoint | Pipe overlay to correct level
| checkpoint | Backfill to the underside of pavement and compacted
fb8bc16e-8ebf-5670-9f64-6537808dd213 | textbox | Cleggs/NDM test results for backfill:
| checkpoint | Geogrid installed (if applicable)
| checkpoint | Service placed at design RL?
| checkpoint | Invert levels checked and correct
| checkpoint | Voids filled with epoxy mortar or concrete
| checkpoint | Trades QA completed, received & reviewed
| checkpoint | General progress photos recorded
| signoff | Request signoff
| checklist | QA - Pits and Vaults |  | Pits and Vaults QA for Area: | c0d000b4-97c4-4319-a2fd-0f77930595e9
| checkpoint | Pits size and dimensions are manufactured according to approved shop drawing
| checkpoint | Pulling irons are provided inside the pits
| checkpoint | Cast in bolts are present
| checkpoint | Earthing for pits/vaults provided
| checkpoint | No visible damage
| checkpoint | Pits / Vaults are installed based on the approved shop drawing
| checkpoint | Waterproofing for pits / vaults in place
| checkpoint | General progress photos recorded
| checkpoint | Pits and Vaults completed, received & reviewed
| signoff | Request signoff
| checklist | QA - Pits, Vaults and Manholes |  | QA - Pits, Vaults and Manholes | 2f6b50e3-6b6a-4899-aff4-62223b767b18
| section | Pits, Vaults and Manholes
| checkpoint | Item selected correctly
28d70a08-178f-599f-8b3e-c02788eae185 | dropdown | Item | Pit, Vault, Manhole, Ductbank
| checkpoint | Photo of item
| checkpoint | Size and dimensions are manufactured according to approved shop drawing
| checkpoint | No visible damage
| checkpoint | Pulling irons are provided inside the pits
| checkpoint | Cast in bolts are present
| checkpoint | Earthing for pits/vaults provided
| checkpoint | Drains for pits/vaults provided
| checkpoint | Ladder rung provided
| checkpoint | Benching for manholes provided
| checkpoint | Pits/Vaults cleaned and free from water
| checkpoint | Lids are installed and flushed to FFL
| checkpoint | Excavation, position, orientation and level verified and in accordance with the shop drawing
| checkpoint | Pipes are sealed and grouted
| section | Installation
| checkpoint | Subgrade tested and passed
18a6a1d3-c461-5e30-9ccf-9df7d8d9fd5a | textbox | Any undercutting required?
e80e9105-00a4-5d21-b108-3e3d23dfb5ad | textbox | Undercutting/other remedials as instructed by Jacobs (if required)
| checkpoint | Bedding material placed and compacted
4d33c28d-ccd5-585e-908e-1f3140316420 | textbox | Cleggs/NDM test results for bedding:
| checkpoint | Geotextile installed (if applicable)
| checkpoint | Backfill material placed and compacted
8be9cb28-67ec-5db1-a95f-afc44756b51d | textbox | Cleggs/NDM test results for backfill:
| checkpoint | Geogrid installed (if applicable)
| checkpoint | Service placed at design RL?
| checkpoint | Invert levels checked and correct
| checkpoint | Voids filled with epoxy mortar or concrete
| checkpoint | Trades QA completed, received & reviewed
| checkpoint | General progress photos recorded
| signoff | Request signoff
| checklist | QA - Retaining Wall Checklist |  | Retaining Wall Checklist | 14f6fa4d-e930-49a8-aaa7-8564fb44a00f
| section | Pre-Start
| checkpoint | Pre-start checks completed and approved
aaf825a7-a32b-5212-a1e6-34250ebb0eb8 | tickbox | Pre-start completed and recorded (both for plant, lifting equipment and activity)
297c1e4b-c170-5588-86a6-64cf7d98a65e | tickbox | Exclusion zone accessible & acceptable
6014cdbb-2f63-5aa2-a615-e923de5ec7bb | tickbox | All workers signed onto CBP and TA
5815bc80-2cd1-5ac3-9fa2-4e166f354ae0 | tickbox | Appropriate PPE and H&S precautions in place
| section | Pre-Retaining Wall Construction
| checkpoint | Location reference attached/detailed below
9070abb7-427f-51af-86b5-782390a37577 | textbox | Location / Grids:
| checkpoint | Foundation: All relevant Lime Stabilisation QA records reviewed and compliant with Lime Stabilisation ITP
| checkpoint | Design: Latest revision of Retaining Wall drawings are used for construction (confirm the set being used)
| checkpoint | Material: MagnumStone units are free of cracks, chips or other defects which may prevent the proper and safe installation of the units or reduce the long term strength of the wall structure
| checkpoint | Material: MagnumStone units are free of any excessive mud, wet concrete and like materials from coming in contact with the wall structure
| checkpoint | Material: MagnumStone units QA records (including concrete dockets) meet specification requirements
| checkpoint | Services: All necessary service penetrations are installed at the correct location, grade and as per the latest drawings (locations as-built)
| checkpoint | Base Levelling Pad: 50mm GAP10 compacted to the correct RL
095fe3c0-f759-5d35-9f73-d415d715da15 | tickbox | Spot survey checks attached
| checkpoint | Base Levelling Pad: Surface of GAP10 base pad is level horizon tonally and back to front
f5ed70be-a8c2-5b5c-923f-76b3b83fb761 | tickbox | Photo(s) taken
| checkpoint | Survey: Sufficient setout has been provided by the surveyor to begin unit placement
| checkpoint | Pre Retaining Wall construction checks completed & approved
| signoff | Request sign off
| section | Retaining Wall Construction
| checkpoint | Placement: Base blocks correctly placed and aligned (confirm surveyed offset and actual)
688dc0da-ff8b-5694-bb24-703c60755f38 | tickbox | Photo(s) taken
| checkpoint | Placement: Top surface is also free of debris prior to other units being installed above
b4869172-5731-56be-bc58-9a2a4cf9d89e | tickbox | Photo(s) taken
| checkpoint | Placement: Front of the interlocking toes of standard blocks are hard up against the front of the form face of the block below
2f93a608-bdf4-5f8e-bebd-25e82e5c1e72 | tickbox | Ensure 25mm steps between blocks and Photo(s) taken
d79e239e-b2bd-558b-89a0-fe117ce73eb4 | tickbox | Photo(s) taken of form face of block below
| checkpoint | Placement: MagnumStone units are level horizon tonally and back to front.
| checkpoint | Placement: Course is correct and as per the drawings (centre of lower block is aligned with the joint of upper blocks UNO)
5cd5b21a-26f3-5f3d-b28e-77167c1be0e2 | tickbox | Photo(s) taken
| checkpoint | Placement: MagnumStone extenders are tightly interlocked with the necessary and level horizon tonally and back to front
| checkpoint | Services: Subsoils location, grade and connection points as per the drawings
9248944c-6c9c-5ed7-b91c-892013c2da96 | tickbox | Photo(s) taken
4b9769ad-1afc-5ba3-aae8-8ca093392bec | tickbox | As-builts attached
| checkpoint | Retaining Wall construction checks completed & approved
| signoff | Request sign off
| checkpoint | Retaining Wall Backfill
| checkpoint | Backfill: Stabilised backfill (including associated QA) completed as per the drawings
| checkpoint | Backfill: A29 geotextile is placed against the battered edge - minimum lap 300mm
74d10db6-d95d-59d0-bbd8-78044cb00c37 | tickbox | Photo(s) taken
| checkpoint | Backfill: Backfilled MagnumStone units and behind the wall with drainage material (40/20) to agreed upon height to allow for further wall construction - all voids filled
| checkpoint | Retaining Wall backfill checks completed & approved
| signoff | Request sign off
| checklist | QA - Sediment Pond Checklist (V1) |  | Sediment Pond Checks | 4a91e763-615b-422e-b84f-c6885c62ce60
| checkpoint | Setout of pond completed as per design
| checkpoint | General photos and observations during excavation of pond
| checkpoint | Diversion bunding built up and acceptable
| checkpoint | Flock shed completed & functioning as designed
| checkpoint | Fence around pond completed
| checkpoint | Sediment Pond Completed & Reviewed
| signoff | Request for approval/sign off
| checklist | QA - Sediment Pond Weekly Checklist (V1) |  | Sediment Pond Weekly Checks - | 54ee7027-e22e-4acf-986b-1c26bb7eebd5
| checkpoint | General photos and observations of pond
| checkpoint | Diversion bunding maintained and acceptable
| checkpoint | Flock shed functioning as designed & levels checked (attach register)
| checkpoint | Fence around pond maintained
| checkpoint | Silt fence(s) checked
| checkpoint | Sediment Pond Weekly Checks Completed & Reviewed
| signoff | Request for approval/sign off
| checklist | QA - Subgrade |  | QA - Subgrade | 5ea35350-97ec-422c-ac74-f615308077cf
| checkpoint | Formation level conforms to the levels and grades within tolerances of +0mm to -25mm (Every 20m)
3e2ddf9c-d0c7-5ede-984d-91a81df1a7a7 | button | Tolerances of +0mm to -25mm (Every 20m) (add string sheet) | Yes, No, N/A
| checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
0a862832-4c4d-5d47-98c2-0b70b88978ca | button | <15mm from a 3.0m (Every 5m) | Yes, No, N/A
e3ba72cc-b998-5068-8214-9187531099ca | button | Provide test results | Pass/Fail Provide test results
| signoff | Clegg test top of subgrade every 10m
| checkpoint-no-value | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
88512ae0-edf2-5502-8ac5-6ba32ad0aa6a | button | Acceptance | Pass/Fail
| signoff | Completion Inspection of sub-grade for acceptance
| checkpoint | As-built documents received
8c432730-ff46-5a43-b227-adc77225b2a9 | button | Documents received | Yes, No, N/A
| checkpoint | General progress photos recorded
abebc120-c538-50f8-8f1a-581698ab1a5c | button | Photos recorded | Yes, No, N/A
| signoff | Request signoff
| checklist | QA - Trial Lime Stabilisation Checklist (V1) |  | Lime Stabilisation Checklist (V1) | 790c59e8-0697-4488-ad44-d8795a3441ea
| checkpoint | Pre excavation checks completed & approval to excavate
856719f3-3f3f-4cd4-bd67-a3907512761b | tickbox | Prestart completed and recorded
74a0f249-444a-417f-b2e3-715749966f4f | tickbox | Area accessible & acceptable
accfd1e0-91f7-4a3c-a165-089a83989b09 | tickbox | All workers signed onto TA
41224d9f-aa6d-4e0d-ac81-8ae85f7fbf4c | tickbox | Hazardous substance register completed and reviewed
f9ce224a-2a22-4b0a-830e-b89c3cf4c6d0 | tickbox | Appropriate PPE and H&S precautions in place
| checkpoint | Trial area cut to -300mm below RL43.2 and clay set aside for use in second lift
| checkpoint | Samples collected from excavated material for lab testing
| checkpoint | Insitu layer mixed, pulverized and stabilised as first lift
| checkpoint | Lime/Cement ratio captured or confirmed
| checkpoint | Record of stabilisation plant used
| checkpoint | 3 x Samples of stabilised material collected from first lift
| checkpoint | Compaction of first lift of stabilised material completed
748064f9-b69b-4ed0-b8ee-97574e26b1fb | textbox | Number of passes
677050a1-ed88-4a2b-8c4a-0d424c019568 | textbox | Tyoe and weight of roller used
5534480b-0b92-4181-8e26-eb32364ac1e0 | textbox | Record of shear vane tests during compaction attached
| checkpoint | Jacobs Geotech observed mixing and pulverizing prior to placement of second lift
| signoff | Request sign off
| checkpoint | Mix, pulverize and stabilise second lift
| checkpoint | Lime/Cement ratio captured or confirmed
| checkpoint | Record of stabilisation plant used
| checkpoint | 3 x Samples of stabilised material collected from first lift
| checkpoint | Compaction of first lift of stabilised material completed
be6b9890-e80d-411b-bb96-4a7133408828 | textbox | Number of passes
9460e685-2f51-4575-b60d-c814ed44046c | textbox | Tyoe and weight of roller used
9f786341-88a6-4708-90ba-e42c8102cbc5 | textbox | Record of shear vane tests during compaction attached (min. 150kPa)
| checkpoint | Jacobs Geotech observed placement and compaction of second lift
| signoff | Request sign off
| checklist | QA - Weekly Topsoil Removal Checklist (V2) |  | Week/Date: | 2e815947-4e5a-421c-a7f6-4e80322d5fd4
| checkpoint | General photos and observations during topsoil removal
| checkpoint | Considerations for environmental (document any controls below)
| checkpoint | All relevant weekly loads of topsoil recorded using load scanner
a8f3fd61-2553-441e-927a-4d616232a57f | textbox | Total Volume of Topsoil Removed
ebb59a08-6155-4fb6-aa50-8518891cba2a | tickbox | Record of loads attached
| signoff | Request for approval/sign off
| checkpoint | Site Entrance Road Cleanliness
2eaa324e-9aff-406b-aec8-4fe39a358a68 | button | Roadsweep Required | Yes,No
aaabd262-5880-4f5e-81b5-b76770ccde76 | note | Add any relevant photos
| checklist | V&B - Compliance Checklist (V1) |  | Compliance Documentation | 0f6c4bc3-9cb4-4ed7-a091-38d8841a5b94
| checkpoint | As Builts - recorded & attached here
| checkpoint | PS3 - completed & attached
| checkpoint | Any additional compliance documentation - completed & attached
2034c914-b71f-48ef-ad25-215fdc276946 | note | "pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
| checkpoint | All Compliance Documentation Checks Completed
673adb3d-36af-489b-8b1e-fc7403ca8bd7 | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
e729abe3-8651-4161-aab6-6492fb49849c | tickbox | Report with all Compliance Documentation checks sent to Main Contractor
013dd899-349a-4b9e-9dbc-c271f6378b3f | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor