## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
be1fd787-0228-4fbc-91a6-aec2900758ce | checklist | V&B Underground services |  | V&B Underground services | 60baf8cd-58b5-4770-b38a-e2156a1a55ec
e0fbb1ad-5a95-4b02-bdd0-666d00da233c | section | Details
540eda5f-4c08-4b87-bffa-3fec9d9c365c | checkpoint | Location reference attached
f5938893-632b-58f3-825f-06bcc03fb107 | textbox | Description
0e4b34eb-132c-5777-b5da-c1063c647ce2 | dropdown | Service type | Hydraulics,Electrical
7581d4b6-2e2a-4f77-8f78-7a83d545bb70 | checkpoint | Setout/Excavation depth
09233f41-24b4-511c-94d5-010ab02f2357 | textbox | Excavation depth
002a864a-5c03-4f50-b850-5d75e0bc5ad6 | checkpoint | Subgrade testing and results
c262309f-6bb5-54bb-8f35-11dcfe81264a | note | Any soft sopts or undercut & associated remedial
1268241d-9387-4af8-b305-8f456e572bb0 | checkpoint | Granular type
b3669f0a-1ccf-401b-b49d-4f6d65d3c152 | checkpoint | Protection tape, tracerwire, magslab installed
68c471c8-77f0-49f0-bad7-34f681b04b4a | checkpoint | Backfill - GAP20 (150mm thickness)
92e451ae-189b-47db-8c98-1afd41557705 | checkpoint | Structual backfill (ATAP65/GAP65 200mm lifts)
96070988-88f0-4a7c-bc30-21a06e53348c | checkpoint | As-builts
dd021541-9832-4c16-9b33-63bd755d56db | checkpoint | Final Pass: Service works completed, reviewed and approved
e97fa2cb-c323-5308-b78c-fd38310def28 | note | Attach As-Built
b2bcf328-35d0-57f9-b12c-e1f0fa7f856c | note | FINAL - Pass when work(s) are completed, area clean & tidy

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | COC |  | COC | 001cf3c9-d3cf-4a3e-a80f-0cd8b03d6e49
| checkpoint-no-value | Please upload COC here
| checklist | General - Upload of Documentation (V2) |  | Upload of - | 2290fe58-46e4-421e-a25b-1c3a2d26fa45
| checkpoint | Documentation filled out & attached
95303df3-a9e8-59b0-b6ba-bfbeadb5e4aa | note | Select "PASS" once the pdocumentation is completed and uploaded here
| signoff | Request Review
| checklist | H&S - Upload of Daily H&S Paperwork (V2) |  | H&S Upload of - | a7ac2e01-b8e6-4c21-85e2-128b609b8ce6
| checkpoint | H&S Paperwork filled out & attached
92a42965-65f2-520b-b6e2-77f19b2156d2 | note | Select "PASS" once the paperwork is completed and uploaded here
| signoff | Request Review
| checklist | QA - Bulk Excavation Checklist (V1) |  | Bulk Excavation Weekly Checks - | c08c76b6-3dee-404e-9203-5380e18d7d2b
| checkpoint | General Photos / Comments / Observations during excavation
| checkpoint | Excavation checked, correct and approved
8a79295f-a355-5d1d-944f-3eaa00ff46ba | textbox | Location accurate
5a476acd-a38c-5e84-9b14-ad18997e902e | tickbox | Depth correct
36743bef-2be1-54e1-af4f-9f0e6cf2a3a4 | tickbox | Width correct
ace437cc-fef3-5f96-9836-cd5fadb01eff | button | Any relevant setout / survey works recorded | Yes, N/A
| checkpoint | Excess Material Cleaned up and removed as required
| checkpoint | All relevant weekly loads recorded using load scanner
5c793406-bd0b-56d2-b867-566f98d0d805 | textbox | Total Volume Removed
98ffff8d-ad5e-5b50-9336-0678a71fee51 | tickbox | Record of loads attached
| checkpoint | Bulk excavation weekly checks completed, reviewed and approved
01963a34-f291-5ab9-8aef-09da09fa89dd | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
| signoff | Request for approval/sign off
| checklist | QA - Detailed Excavation Checklist (V1) |  | Backfill Checklist | 0b4c0473-f6b2-42e8-b21f-a713d78acf59
| checkpoint | Location reference attached
0ad80312-d917-5f6b-a567-b4da72ec232d | dropdown | zone | 1,2,3,4,5
| checkpoint | Sand blinding
fcca8131-611e-5158-b5f9-a77401a7e229 | note | Basecourse material
| checkpoint | Dockets checked
c85ec285-6cf2-5ff3-bd6c-8eada22c7e50 | note | Geotech Inspection
d0b948d5-a8c1-596c-8166-d34b2002497d | note | Sub basecourse material
| checkpoint | Dockets checked
cd593496-387f-546f-9c89-93e4d7ec115c | note | Depth correct (allow for site concrete if required)
| checkpoint | Material free of debris
| checkpoint | Detailed setdowns confirmed RL
9521d2a9-57e3-53db-8ae6-7a43d6a9ac41 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
30460729-4e27-5e98-bd81-98b187265c0e | button | Trades QA received & attached as applicable | PASS, N/A
| checklist | QA - Detailed Excavation Checklist (V1) |  | Detailed Excavation Checklist (General) | 44aade3b-7320-4e6c-a056-2d5e06a56fee
| checkpoint | Location reference attached
| checkpoint | General Photos / Comments / Observations during excavation
| checkpoint | Any soft spots or undercuts & associated remedial
| checkpoint | Excavation checked, correct and approved off accurate survey marks
0b03b576-7d18-5757-91a0-fab90f4697b0 | note | Location accurate
fb6eb47e-ffba-5c0c-a0c4-954a7cdc3a82 | note | Depth correct (allow for site concrete if required)
e80a4095-8741-501f-a8fc-ee595ad42ec2 | note | Width correct (allow for boxing if required)
| checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
| checkpoint | Excess Material Cleaned up and removed as required
ce5d19a7-eed3-5291-bf8e-1160e3d33e5b | note | Subgrade inspection (if applicable)
| checkpoint | Detailed excavation completed, reviewed and approved
1dfd44b9-0562-5696-8cfb-293a9f2d9cef | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
162cfaf5-be45-5b90-ad8e-112a882f2746 | button | Trades QA received & attached as applicable | PASS, N/A
| checklist | QA - Detailed Excavation Checklist (V1) |  | Detailed Excavation Checklist (Ground Beam) | 8a4bfbbf-d917-47bd-81e4-6fc23e73b87c
| checkpoint | Location reference attached
df95aed6-868f-5635-ad19-fa2b854fa7f5 | dropdown | zone | 1,2,3,4,5
be7cf387-6c09-5bff-9a05-0032ce1f00fb | dropdown | GroundBeam type | GB1, GB2, GB3, GB4
| checkpoint | Ground beam setout with working area included
b2f6e073-eeb4-5513-9ff3-c8c4151ece18 | note | Any soft spots or undercuts & associated remedial
| checkpoint | Excavation checked, correct and approved off accurate survey marks
7f91c46d-0ff0-5d67-9713-206a96a55862 | note | Location accurate
db278e0f-4c07-56d4-959d-78576c18256c | note | Depth correct (allow for site concrete if required)
e3a21c36-1156-5b11-a064-faa4836604e7 | note | Width correct (allow for boxing if required)
| checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
| checkpoint | Excess Material Cleaned up and removed as required
| checkpoint | Detailed excavation completed, reviewed and approved
ed7ad538-a6a8-5d3e-af25-0f350902a90d | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
20262bc4-6c52-5c57-bb64-b5dee8262e59 | button | Trades QA received & attached as applicable | PASS, N/A
| checklist | QA - Detailed Excavation Checklist (V1) |  | Detailed Excavation Checklist (Pilecap) | b89e9df2-5a92-4bb2-89ad-b07bbdc27e0e
| checkpoint | Location reference attached
cc213815-d0a0-501f-b3bd-84b7bc9dd7c7 | dropdown | Pile cap type | PC01, PC02, PC02a, PC03, PC04
| checkpoint | pilecap setout with working area included
59bbe05c-20b8-5361-a383-d45ba0bdbbfc | note | Any soft spots or undercuts & associated remedial
| checkpoint | Excavation checked, correct and approved off accurate survey marks
7753f912-c12b-5056-8392-cb4585c9158a | note | Location accurate
ed500f36-ebeb-5a11-8f61-efe367680130 | note | Depth correct (allow for site concrete if required)
2489899d-6078-54b6-bf06-6b479f8196f3 | note | Width correct (allow for boxing if required)
| checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
| checkpoint | Excess Material Cleaned up and removed as required
| checkpoint | Detailed excavation completed, reviewed and approved
876bc14e-1415-5f5e-b307-6fa2c773b59b | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
dee1c189-4318-507b-8701-62452c874f80 | button | Trades QA received & attached as applicable | PASS, N/A
| checklist | QA - Pipe Laying |  | QA - Pipe Laying (Drainage) | a55d66de-40fe-4723-90dd-dd0bcb94c3a6
| section | Pipelaying
| checkpoint | Pipes were laid as per approved shop drawings
| checkpoint | Pipe grades are in accordance with the drawings
| checkpoint | Pipe materials comply with specifications
4a48ccc2-0778-5cb8-880e-eb8ec223dd19 | dropdown | Pipe type | HDPE, uPVC, Subsoil
| checkpoint | Trench excavation to line level and grade
| checkpoint | Correct bedding provided
6c58e310-1bba-5bfe-a545-43813b073d62 | dropdown | Bedding material | Gap20, Pap7
| checkpoint | Jointing system as per specifications and manufacturers recommendation
| checkpoint | Anchor/ thrust block provided (if any)
| checkpoint | Pipes flushed and cleaned
c8a0885f-0a87-5a80-b659-9f088a550136 | textbox | Flood Test (if applicable)
| checkpoint | Pipes Pressure tested (if applicable)
| checkpoint | Pipes tested in accordance with specifications
| signoff | Inspected by local authority (Council)
| checkpoint | Vents/rodding eye installed (If any)
| checkpoint | CCTV provided
| section | Installation
| checkpoint | Installation tested
| checkpoint | Subgrade tested and passed
f4650683-9433-5c38-b29a-af52e62a0670 | textbox | Any undercutting required?
f612f991-0818-5be6-bdbc-66afb81c9a5f | textbox | Undercutting/other remedials as instructed by Hawkins (if required)
| checkpoint | Geotextile installed (if applicable)
| checkpoint | Bedding material installed to correct level
| checkpoint | Bedding material compacted in layers (if applicable)
| checkpoint | Side support material installed to the correct level
| checkpoint | Haunching?
| checkpoint | Pipe benched with 25Mpa concrete inside the manhole
| checkpoint | 25Mpa concrete corbel around inlet and outlet pipes
| checkpoint | Voids filled with epoxy mortar or concrete (if required)
| checkpoint | Pipe overlay to correct level
| checkpoint | Backfill to the underside of pavement and compacted
49311fdf-32a6-5eb2-b555-506de2cf732d | textbox | Cleggs/NDM test results for backfill:
| checkpoint | Geogrid installed (if applicable)
| checkpoint | Service placed at design RL?
| checkpoint | Invert levels checked and correct
| checkpoint | Asbuitl provided
| checkpoint | Trades QA completed, received & reviewed
| checkpoint | General progress photos recorded
| signoff | Request signoff
| checklist | QA - Pits, Vaults and Manholes |  | QA - Pits, Vaults and Manholes | e261683d-5f32-42aa-9e5a-81344a53a446
| section | Pits, Vaults and Manholes
| checkpoint | Item selected correctly
f0c000e6-aa5d-543d-8746-6b8e13e5dc1d | dropdown | Item | Pit, Vaults and Manhole
| checkpoint | Photo of item
| checkpoint | Size and dimensions are manufactured according to approved shop drawing
| checkpoint | No visible damage
| checkpoint | Pulling irons are provided inside the pits
| checkpoint | Cast in bolts are present
| checkpoint | Earthing for pits/vaults provided
| checkpoint | Drains for pits/vaults provided
| checkpoint | Ladder rung provided
| checkpoint | Benching for manholes provided
| checkpoint | Pits/Vaults cleaned and free from water
| checkpoint | Lids are installed and flushed to FFL
| checkpoint | Excavation, position, orientation and level verified and in accordance with the shop drawing
| checkpoint | Pipes are sealed and grouted
| checkpoint | Item tested in accordance with specifications
| signoff | Inspected by local authority (Council)
| section | Installation
| checkpoint | Subgrade tested and passed
a2253d5c-93fa-58df-963e-c5e8b8b637c9 | textbox | Any undercutting required?
bf3448b1-e7a6-5f25-815f-ce7ad1e5b77f | textbox | Undercutting/other remedials as instructed by Hawkins (if required)
| checkpoint | Undercut asbuilt (if required)
| checkpoint | Bedding material placed and compacted as per specification
af43be26-d875-5762-a7b5-5aa7ccc40249 | textbox | Cleggs/NDM test results for bedding:
| checkpoint | Geotextile installed (if applicable)
| checkpoint | Backfill material placed and compacted
739aadd3-5629-5efb-971d-bf1342a3d4ee | textbox | Cleggs/NDM test results for backfill:
| checkpoint | Geogrid installed (if applicable)
| checkpoint | Service placed at design RL?
| checkpoint | Invert levels checked and correct
| checkpoint | Voids filled with epoxy mortar or concrete
| checkpoint | Trades QA completed, received & reviewed
| checkpoint | General progress photos recorded
| signoff | Request signoff
| checklist | QA - Subgrade |  | QA - Subgrade | 6239c7ae-2d25-447b-b2f5-080c407c9b2d
| checkpoint | Formation level conforms to the levels and grades within tolerances of +0mm to -25mm (Every 20m)
baa85090-d80d-5287-85d8-355cfaf6b9f9 | button | Tolerances of +0mm to -25mm (Every 20m) (add string sheet) | Yes, No, N/A
| checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
f6d24c8b-d73f-5efb-97f1-fd2ba3eda5df | button | <15mm from a 3.0m (Every 5m) | Yes, No, N/A
1f96de51-8540-5b9b-a5ba-b614b3fa02dc | button | Provide test results | Pass/Fail Provide test results
| signoff | Clegg test top of subgrade every 10m
| checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
e82e4fa9-b11d-5735-a0eb-74dd6a5c7107 | button | Acceptance | Pass/Fail
| signoff | Completion Inspection of sub-grade for acceptance
| checkpoint | As-built documents received
2c0bc7c4-2106-563d-a527-88c8005fef9d | button | Documents received | Yes, No, N/A
| checkpoint | General progress photos recorded
6b2233b0-c8e9-5f88-b77a-c3aa1d36f245 | button | Photos recorded | Yes, No, N/A
| signoff | Request signoff
| checklist | V&B - Compliance Checklist (V1) |  | Compliance Documentation | bb723239-54e0-4d0e-9635-0e3436dc243f
| checkpoint | As Builts - recorded & attached here
| checkpoint | PS3 - completed & attached
| checkpoint | Any additional compliance documentation - completed & attached
087db37a-e8c3-59c1-9794-1c9eecb08d1b | note | "pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
| checkpoint | All Compliance Documentation Checks Completed
53c0d266-04b6-5d0a-ab6e-57cc62c4b5e2 | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
bab742ec-a452-545e-b1f5-cd3b95b7d8ee | tickbox | Report with all Compliance Documentation checks sent to Main Contractor
a47387d1-139b-52aa-9c50-6944dea7f169 | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor