## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
be1fd787-0228-4fbc-91a6-aec2900758ce | checklist | V&B Underground services |  | V&B Underground services | 60baf8cd-58b5-4770-b38a-e2156a1a55ec
e0fbb1ad-5a95-4b02-bdd0-666d00da233c | section | Details
540eda5f-4c08-4b87-bffa-3fec9d9c365c | checkpoint | Location reference attached
f5938893-632b-58f3-825f-06bcc03fb107 | textbox | Description
0e4b34eb-132c-5777-b5da-c1063c647ce2 | dropdown | Service type | Hydraulics,Electrical
7581d4b6-2e2a-4f77-8f78-7a83d545bb70 | checkpoint | Setout/Excavation depth
09233f41-24b4-511c-94d5-010ab02f2357 | textbox | Excavation depth
002a864a-5c03-4f50-b850-5d75e0bc5ad6 | checkpoint | Subgrade testing and results
c262309f-6bb5-54bb-8f35-11dcfe81264a | note | Any soft sopts or undercut & associated remedial
1268241d-9387-4af8-b305-8f456e572bb0 | checkpoint | Granular type
b3669f0a-1ccf-401b-b49d-4f6d65d3c152 | checkpoint | Protection tape, tracerwire, magslab installed
68c471c8-77f0-49f0-bad7-34f681b04b4a | checkpoint | Backfill - GAP20 (150mm thickness)
92e451ae-189b-47db-8c98-1afd41557705 | checkpoint | Structual backfill (ATAP65/GAP65 200mm lifts)
96070988-88f0-4a7c-bc30-21a06e53348c | checkpoint | As-builts
dd021541-9832-4c16-9b33-63bd755d56db | checkpoint | Final Pass: Service works completed, reviewed and approved
e97fa2cb-c323-5308-b78c-fd38310def28 | note | Attach As-Built
b2bcf328-35d0-57f9-b12c-e1f0fa7f856c | note | FINAL - Pass when work(s) are completed, area clean & tidy

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | COC |  | COC | 3dbfd811-8bc3-473f-91ff-ec88b8f6537a
| checkpoint | Upload COC here and press PASS
| checklist | Detailed Excavation Checklist |  | Detailed Excavation Checklist | b36ef117-d3ce-4824-8e8b-399433eb727e
| checkpoint | Location reference attached
| checkpoint | General Photos / Comments / Observations during excavation
| checkpoint | Any soft spots or undercuts & associated remedial
| checkpoint | Excavation checked, correct and approved off accurate survey marks
66eccdaf-8f50-533e-864c-4763fa95ad9e | note | Location accurate
8c2e0f2f-07b7-5093-9a11-a297a29155f6 | note | Depth correct (allow for site concrete if required)
7454301f-bee0-5d57-be13-573be32dd774 | note | Width correct (allow for boxing if required)
| checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
| checkpoint | Excess Material Cleaned up and removed as required
| checkpoint | Detailed excavation completed, reviewed and approved
b1e6d828-9279-5abb-b51f-ac81c5583a07 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
74e1eba6-e068-50dc-91f8-32a9d56b9076 | button | Trades QA received & attached as applicable | PASS, N/A