## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
be1fd787-0228-4fbc-91a6-aec2900758ce | checklist | V&B Underground services |  | V&B Underground services | 60baf8cd-58b5-4770-b38a-e2156a1a55ec
e0fbb1ad-5a95-4b02-bdd0-666d00da233c | section | Details
540eda5f-4c08-4b87-bffa-3fec9d9c365c | checkpoint | Location reference attached
f5938893-632b-58f3-825f-06bcc03fb107 | textbox | Description
0e4b34eb-132c-5777-b5da-c1063c647ce2 | dropdown | Service type | Hydraulics,Electrical
7581d4b6-2e2a-4f77-8f78-7a83d545bb70 | checkpoint | Setout/Excavation depth
09233f41-24b4-511c-94d5-010ab02f2357 | textbox | Excavation depth
002a864a-5c03-4f50-b850-5d75e0bc5ad6 | checkpoint | Subgrade testing and results
c262309f-6bb5-54bb-8f35-11dcfe81264a | note | Any soft sopts or undercut & associated remedial
1268241d-9387-4af8-b305-8f456e572bb0 | checkpoint | Granular type
b3669f0a-1ccf-401b-b49d-4f6d65d3c152 | checkpoint | Protection tape, tracerwire, magslab installed
68c471c8-77f0-49f0-bad7-34f681b04b4a | checkpoint | Backfill - GAP20 (150mm thickness)
92e451ae-189b-47db-8c98-1afd41557705 | checkpoint | Structual backfill (ATAP65/GAP65 200mm lifts)
96070988-88f0-4a7c-bc30-21a06e53348c | checkpoint | As-builts
dd021541-9832-4c16-9b33-63bd755d56db | checkpoint | Final Pass: Service works completed, reviewed and approved
e97fa2cb-c323-5308-b78c-fd38310def28 | note | Attach As-Built
b2bcf328-35d0-57f9-b12c-e1f0fa7f856c | note | FINAL - Pass when work(s) are completed, area clean & tidy

## Project Checklist Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
|  | checklist | QA - Ductbanks |  | QA - Ductbanks | 8f2092b4-d5ae-460a-b775-4a027db439a3
|  | section | Pre Installation
|  | checkpoint | Conduits were laid as per approved shop drawings
|  | signoff | Request signoff
|  | checkpoint | Conduits are joined & terminated in accordance to the manufacturers instructions and specifications
|  | checkpoint | Permanent adhesives were used, water-tight joints was made in conjunction with standard accessories
|  | checkpoint | Conduits saddles are provided prior to sand backfilling
|  | checkpoint | Concrete topping for duct bank is as per specifications
|  | checkpoint | Backfilled as per drawings and specifications
|  | checkpoint | Tracer wire, magslab and warning tape provided
|  | checkpoint | Ducts cleaned and tested and handed over to electrical/Telecom contractor
|  | section | Installation
|  | checkpoint | Subgrade tested and passed
|  | signoff | Request signoff
|  | checkpoint | Any undercutting required?
| 84540d0e-3aa2-526f-91f3-2e2ee600750c | tickbox | Yes
| 78eb780c-1436-56ce-95d5-dbde27b94a92 | tickbox | No
| 79566ef8-fb1f-594b-9281-4ead3ccdf34d | textbox | Undercutting/other remedials as instructed by Jacobs (if required)
|  | checkpoint | Bedding material placed and compacted
| e5bbe882-7537-5623-a902-0b3f4da433e4 | textbox | Cleggs/NDM test results for bedding:
|  | checkpoint | Geotextile installed (if applicable)
|  | checkpoint | Backfill material placed and compacted
| 297177c7-8638-54db-b634-5b921f39ec8b | textbox | Cleggs/NDM test results for backfill:
|  | checkpoint | Geogrid installed (if applicable)
|  | checkpoint | Service placed at design RL?
|  | checkpoint | Invert levels checked and correct
|  | checkpoint | Voids filled with epoxy mortar or concrete
|  | checkpoint | Trades QA completed, received & reviewed
|  | checkpoint | General progress photos recorded
|  | signoff | Request signoff
|  | checklist | QA - Pits, Vaults and Manholes |  | QA - Pits, Vaults and Manholes | dc602312-5ec6-476e-bbcd-beae4e46f9d0
|  | section | Pre Installation
|  | checkpoint | Photo of item
| a6885526-e287-50e2-be7e-40a5eeeac3e0 | dropdown | Item | Pit, Vault, Manhole, Ductbank
| f347dc2e-aeb8-599a-9fcf-6cc0193a41b3 | dropdown | Size and dimensions are manufactured according to approved shop drawing | Yes, No, N/A
|  | checkpoint | No visible damage
|  | checkpoint | Pulling irons are provided inside the pits
|  | checkpoint | Cast in bolts are present
|  | checkpoint | Earthing for pits/vaults provided
|  | checkpoint | Drains for pits/vaults provided
|  | checkpoint | Ladder rung provided
|  | checkpoint | Benching for manholes provided
|  | checkpoint | Pits/Vaults cleaned and free from water
|  | checkpoint | Lids are installed and flushed to FFL
|  | checkpoint | Excavation, position, orientation and level verified and in accordance with the shop drawing
|  | checkpoint | Pipes are sealed and grouted
|  | section | Installation
|  | checkpoint | Subgrade tested and passed
|  | signoff | Signed Off
|  | checkpoint | Any undercutting required?
| d2193782-a393-5ca1-8d77-2fbd3a3d45bf | tickbox | Yes
| 5550e530-5615-5222-b18d-79fa921f576b | tickbox | No
| e088be7f-be78-5a22-9c48-000f0045277d | textbox | Undercutting/other remedials as instructed by Jacobs (if required)
|  | checkpoint | Bedding material placed and compacted
| 5825fdc8-eda4-592f-bd77-97025d351a74 | textbox | Cleggs/NDM test results for bedding:
|  | checkpoint | Geotextile installed (if applicable)
|  | checkpoint | Backfill material placed and compacted
| b2c878a0-bcd5-559b-a1d1-04657fcd4927 | textbox | Cleggs/NDM test results for backfill:
|  | checkpoint | Geogrid installed (if applicable)
|  | checkpoint | Service placed at design RL?
|  | checkpoint | Invert levels checked and correct
|  | checkpoint | Voids filled with epoxy mortar or concrete
|  | checkpoint | Trades QA completed, received & reviewed
|  | checkpoint | General progress photos recorded
|  | signoff | Request signoff
|  | checklist | QA - Retaining Wall Checklist |  | QA - Retaining Wall Checklist | 0230dac1-fb00-4a7a-b849-e238d78727ba
|  | checkpoint | Pre Retaining Wall construction checks completed & approved
|  | checkpoint | Location reference attached
| 9da31052-1459-5994-aec9-52e2962fd5dd | textbox | Distance measured to the bottom of the pile toe
| 94e982ec-e1e9-55d6-99de-938d720f499e | textbox | Bored pile diameter
|  | signoff | Bored pile within tolerances (75mm horizontal position, 1:75 for pile verticality)
|  | checkpoint | Steel column location correct
|  | checkpoint | 75mm cover achieved between steel and column
|  | checkpoint | Steel posts shall be installed to the following max. tolerances (25mm in plan , 1:100 for post verticality)
|  | checkpoint-no-value | Approved Concrete Mix Code Ordered
| f31c4fcf-f504-5644-bc29-01d83a0281bd | textbox | Specify concrete mix code
|  | checkpoint | Photographs of Concrete dockets
| bcce0f55-f6e3-5fce-becc-92a90f3a467f | note | All relevant dockets photographed and attached
Multiple signoffs are not allowed |  | signoff | Ensure that 75% of the specified 28 days concrete compressive strength is achieved before the installation of the panels.
Multiple signoffs are not allowed |  | signoff | Provide lab results indicating 75% strength achieved
|  | checkpoint | Concrete Panel placed as per setout
|  | checkpoint | Bearing strip installed between the panel and the pile
|  | checkpoint | All reinforcing, shims and fixings line up with the appropriate items on the preceding work.
| ddc3c2fd-d44c-5d0d-af47-dc70ee21abc4 | textbox | Top of Concrete Panel RL
|  | checkpoint | Backfill: A19 geotextile is placed against cut face - minimum lap 300mm (photo)
|  | checkpoint | Subsoils location, grade and outlet points as per Jacobs instruction (photos and as-built)
|  | checkpoint | Backfilled behind the wall with drainage material (25) to agreed upon height - all voids filled (photo)
|  | checkpoint | Backfill between panels: 100mm thick compacted GAP40 - tested and passed
|  | signoff | Request sign off