## Master List Templates
Id | Type | Name | Values | Prompting Name
be1fd787-0228-4fbc-91a6-aec2900758ce | checklist | V&B Underground services |  | V&B Underground services
e0fbb1ad-5a95-4b02-bdd0-666d00da233c | section | Details
540eda5f-4c08-4b87-bffa-3fec9d9c365c | checkpoint | Location reference attached
f5938893-632b-58f3-825f-06bcc03fb107 | textbox | Description
0e4b34eb-132c-5777-b5da-c1063c647ce2 | dropdown | Service type | Hydraulics,Electrical
7581d4b6-2e2a-4f77-8f78-7a83d545bb70 | checkpoint | Setout/Excavation depth
09233f41-24b4-511c-94d5-010ab02f2357 | textbox | Excavation depth
002a864a-5c03-4f50-b850-5d75e0bc5ad6 | checkpoint | Subgrade testing and results
c262309f-6bb5-54bb-8f35-11dcfe81264a | note | Any soft sopts or undercut & associated remedial
1268241d-9387-4af8-b305-8f456e572bb0 | checkpoint | Granular type
b3669f0a-1ccf-401b-b49d-4f6d65d3c152 | checkpoint | Protection tape, tracerwire, magslab installed
68c471c8-77f0-49f0-bad7-34f681b04b4a | checkpoint | Backfill - GAP20 (150mm thickness)
92e451ae-189b-47db-8c98-1afd41557705 | checkpoint | Structual backfill (ATAP65/GAP65 200mm lifts)
96070988-88f0-4a7c-bc30-21a06e53348c | checkpoint | As-builts
dd021541-9832-4c16-9b33-63bd755d56db | checkpoint | Final Pass: Service works completed, reviewed and approved
e97fa2cb-c323-5308-b78c-fd38310def28 | note | Attach As-Built
b2bcf328-35d0-57f9-b12c-e1f0fa7f856c | note | FINAL - Pass when work(s) are completed, area clean & tidy

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
1a25719a-bc6c-5fd4-99aa-c704447a5c83 | checklist | Compacted Backfill Checklist (Pilecaps and Ground Beams) |  | Compacted Backfill Checklist (Pilecaps and Ground Beams)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f6b1e1d1-593b-5ef0-ac05-4adc89d2d1a5 | checkpoint | Location reference attached
72d3b0a6-a022-5778-a642-3e8b536fd2d4 | textbox | Description
c5cfa15b-adb7-59cb-a591-9e80657fe921 | checkpoint | Backfill compacted to 200mm layers and tested for compaction
4c42d41d-5f02-5b07-85e1-a268e3d6881d | checkpoint | Finish level minus 100mm
a27defdd-b7e1-5377-af23-8314c358401c | checkpoint | Level checked
c917330f-0985-5029-931a-77d103caf1ac | checkpoint | Signoff and handover
ad05ad2c-805c-5478-a2bc-4e26fa687976 | signoff | Request signoff
edbcfa3b-5b3a-459e-8608-99a4ee0922d9 | checklist | Compacted Backfill Checklist (Pilecaps and Ground Beams) - Revised |  | Compacted Backfill Checklist (Pilecaps and Ground Beams) - Revised
1d383bea-4503-446c-bcb3-e9b87ad4041a | section | Details
c0a3453c-0dcb-49ff-a53c-348baa7194f3 | checkpoint | Location reference attached
c3c5864c-547c-5bc7-b656-9a60b4ec72ba | textbox | Description
2df1569d-7967-463d-a143-facf2041936b | checkpoint | Backfill compacted to 200mm layers and tested for compaction (all lifts done)
61833e15-c76e-4e9a-84dd-71b16fe1ce97 | checkpoint | Backfill Lift 1
38b6f895-77d2-5bb4-b12a-dce627ec4bc0 | note | 300mm lift only for Lift 1
183c4bd7-5bfa-50fb-92f5-5fdf4b9e5f61 | date | Test date
c66d1546-c910-5af7-b3f5-39dc678b88d0 | textbox | Clegg Reading (CIV)
6b612d2b-7cc8-5993-801c-23587082a14c | textbox | Retest (CIV)
cfb4b7cc-ddbd-471a-92d0-87f0dcca5862 | checkpoint | Backfill Lift 2
7126933d-f45f-5ef0-bec6-04d5649a35d8 | note | Test every 200mm
f2805a09-5cf3-57c6-ac7d-784669e7f1de | date | Test date
abf9cfd1-3def-593e-b1fd-71511bfd6fdb | textbox | Clegg Reading (CIV)
8a83068b-31cb-5e50-905e-061f4f83d3e9 | textbox | Retest (CIV)
f14d0a30-0a07-4609-90e2-595c5bfea88b | checkpoint | Backfill Lift 3
a57b5b51-395d-5d91-aad7-fb4710bc4155 | note | Test every 200mm
37d18839-15a4-5056-bb28-2f111c06f35d | date | Test date
cfeeb685-438a-513b-ac8a-d931b686a220 | textbox | Clegg Reading (CIV)
e01bbb9b-02ad-5a50-aa1d-ce5b85c76cb1 | textbox | Retest (CIV)
3e1b991c-8578-4dcf-8949-59fdf61d98a5 | checkpoint | Backfill Lift 4
40277ba6-b4de-5aec-8211-e18d5a7ae63d | note | Test every 200mm
fb834175-aec4-5f62-bd41-ec68c19dbaad | date | Test date
d5508a46-39df-56ab-ba54-6ac52211f72a | textbox | Clegg Reading (CIV)
38894d7c-1ccd-58c2-ae68-0a16a8f87dd7 | textbox | Retest (CIV)
90df1dc5-6f48-4a00-80b7-1bfb2735be00 | checkpoint | Backfill Lift 5
b7830720-bf0f-5c87-918a-fd40659c49f8 | note | Test every 200mm
ba389874-c7dd-57f3-b071-95da513febd6 | date | Test date
c1f1f2f3-63e4-5ee1-9445-6e088098b87b | textbox | Clegg Reading (CIV)
be71aff8-f875-56f9-a29b-658150e50496 | textbox | Retest (CIV)
5959a28c-ed15-473f-acfe-a8accddee748 | checkpoint | Backfill Lift 6
b253359b-4ce8-5d2d-9680-b312415ddb51 | note | 300mm lift only for Lift 1
a032f696-1942-5067-a868-20b560c9e243 | date | Test date
2b42c037-237b-586d-b687-8b48e9c68424 | textbox | Clegg Reading (CIV)
f06118e9-e594-5846-9005-ba8a46e85e66 | textbox | Retest (CIV)
f27cb773-e490-4ad4-b797-092947672b8b | checkpoint | Backfill Lift 7
ce601438-3646-5988-8a1b-5ad6c1f443e2 | note | Test every 200mm
85bbf9d7-4cdd-5cca-acf7-6fe33b3f026e | date | Test date
b7ba92cb-509d-5f90-9b04-95d40a3484f8 | textbox | Clegg Reading (CIV)
f533b4ca-b963-51bc-a92d-c3286c793cd2 | textbox | Retest (CIV)
704de07a-3baf-4840-b9f6-9fdb79194401 | checkpoint | Backfill Lift 8
9c2ae66e-677d-5587-a393-fe9226660907 | note | Test every 200mm
346b93fb-7cfc-5937-88e3-cd422f6be0e0 | date | Test date
fe7b494e-a071-5358-b580-cfdfd67eff4c | textbox | Clegg Reading (CIV)
4ea0f674-f7e3-53f0-9d74-0f6b61876d24 | textbox | Retest (CIV)
83685cfd-2150-4a0d-a2c2-682533dec452 | checkpoint | Backfill Lift 9
aeb298d1-9460-5c82-b6f0-ff5e5abf6049 | note | Test every 200mm
3503afd1-ffeb-52ad-b9d3-d56955e767ad | date | Test date
3b40afe5-d1b2-5055-a244-cab84544ac4e | textbox | Clegg Reading (CIV)
cea1b9e3-bc60-5578-ba0c-e4d4340f60ce | textbox | Retest (CIV)
df67e2c1-c0e8-46a3-821e-fce27218e55f | checkpoint | Backfill Lift 10
ca81d4e9-d169-5032-b59a-e7d299284d52 | note | Test every 200mm
3db4f0d0-c0f2-5662-a353-7b12ad751085 | date | Test date
01bd857f-d28e-527a-85c3-7dae1c5ccbf2 | textbox | Clegg Reading (CIV)
10060c14-9672-5d30-a794-a4e4be820021 | textbox | Retest (CIV)
2dde8a3a-14fa-430d-97a1-82732f416944 | checkpoint | Finish level minus 100mm
3e6312a8-2ee6-4269-8548-971e7494d82c | checkpoint | Level checked
dfa96be9-7c06-4a63-8b11-4d5e6ef9b0e5 | checkpoint | Signoff and handover
c730406f-9077-41eb-b4a8-69ba33109187 | signoff | Request signoff
2fdede26-a6d0-5833-bec0-0b5deaee81a4 | checklist | Detailed Excavation Checklist (General) |  | Detailed Excavation Checklist (General)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f6b1e1d1-593b-5ef0-ac05-4adc89d2d1a5 | checkpoint | Location reference attached
fca7fdf9-e2cf-514e-8606-04001f456c0e | checkpoint | General Photos / Comments / Observations during excavation
982c3aeb-b665-596c-ae0e-0cee537c4f6a | checkpoint | Any soft spots or undercuts & associated remedial
7db476ef-cd09-5828-9782-ed4c261e8b0d | checkpoint | Excavation checked, correct and approved off accurate survey marks
7674c75c-1585-5b88-a001-c09c1ec6a715 | note | Location accurate
58b647bf-6f52-583d-94cf-9fce9a81b631 | note | Depth correct (allow for site concrete if required)
9799d51b-2406-59dd-a87b-7512391c359e | note | Width correct (allow for boxing if required)
9f0fc8d0-6ff3-5613-b248-bb4a82348ddb | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
e23a42b7-4555-5780-8a28-fac17d808a60 | checkpoint | Excess Material Cleaned up and removed as required
f2cb0e21-d1d4-5a9f-ad48-773cc64b5f89 | note | Subgrade inspection (if applicable)
42591e81-a83d-5485-8b9e-d8bdae180147 | checkpoint | Detailed excavation completed, reviewed and approved
29ce456d-07b0-525f-989f-98d7b187bc47 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
9d9d76cd-c5f7-59b9-9c1c-a46a10104064 | button | Trades QA received & attached as applicable | PASS, N/A
76c8243b-0756-5fdf-abfa-8fed71ebd5ea | checklist | Detailed Excavation Checklist (Ground Beam) |  | Detailed Excavation Checklist (Ground Beam)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f6b1e1d1-593b-5ef0-ac05-4adc89d2d1a5 | checkpoint | Location reference attached
74ee3235-0bb5-528d-a121-d1c46e667208 | dropdown | zone | 1,2,3,4,5,N1,P
1e787620-a429-5853-9fd0-f434fc656c18 | dropdown | Ground Beam type | GB1, GB2, GB3, GB4, GB5, GB6, GB7, GB8, GB9, GB11, GB12, GB13, GB14, GB14A, GB14B, GB15
01d41839-c8e0-590e-90e3-7c17d554764b | checkpoint | Ground beam setout with working area included
76ceef3d-fe55-5179-a47f-b59fa2215feb | note | Any soft spots or undercuts & associated remedial
7db476ef-cd09-5828-9782-ed4c261e8b0d | checkpoint | Excavation checked, correct and approved off accurate survey marks
1ee1b870-cb37-51aa-ab06-907719ffa5fa | note | Location accurate
a4647cd4-f8e6-5a87-b4b9-c385eac71e5b | note | Depth correct (allow for site concrete if required)
543cb5f2-e1cb-5ed8-99cf-a73ba4d0c1a7 | note | Width correct (allow for boxing if required)
9f0fc8d0-6ff3-5613-b248-bb4a82348ddb | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
e23a42b7-4555-5780-8a28-fac17d808a60 | checkpoint | Excess Material Cleaned up and removed as required
42591e81-a83d-5485-8b9e-d8bdae180147 | checkpoint | Detailed excavation completed, reviewed and approved
db650c8f-df35-5903-a7f3-8532701e85da | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
130e1973-1805-56d4-b34f-569c81d7af2b | button | Trades QA received & attached as applicable | PASS, N/A
f42a3464-a92d-592a-aa40-c4147d7c7f39 | checklist | Detailed Excavation Checklist (Pilecap) |  | Detailed Excavation Checklist (Pilecap)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f6b1e1d1-593b-5ef0-ac05-4adc89d2d1a5 | checkpoint | Location reference attached
ac61f454-0b8f-5a90-a4bd-ce559981f8c4 | dropdown | Pile cap type | PC01, PC02, PC02a, PC03, PC04, PC05, PC06, PC07, PC11, PC12, PC13, PC14, PC15
63ecf2b7-af98-5378-a51f-bb7e98ca549b | checkpoint | pilecap setout with working area included
41520d64-ff62-54f7-9ff8-fb50507544ed | note | Any soft spots or undercuts & associated remedial
7db476ef-cd09-5828-9782-ed4c261e8b0d | checkpoint | Excavation checked, correct and approved off accurate survey marks
db30934c-4555-5542-b4ed-78e80ef5c911 | note | Location accurate
3a5fb26a-d3c2-59f5-942f-f51830bfec9f | note | Depth correct (allow for site concrete if required)
cb9b0007-eade-5783-a03a-f7188a1f0d5e | note | Width correct (allow for boxing if required)
9f0fc8d0-6ff3-5613-b248-bb4a82348ddb | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
e23a42b7-4555-5780-8a28-fac17d808a60 | checkpoint | Excess Material Cleaned up and removed as required
42591e81-a83d-5485-8b9e-d8bdae180147 | checkpoint | Detailed excavation completed, reviewed and approved
cb52e0b4-9b97-5bda-a5eb-597db42a94c8 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
273c2471-4556-5a23-85ba-017e83cf0783 | button | Trades QA received & attached as applicable | PASS, N/A
eea410ca-5dda-5aaa-8507-c7781d426487 | checklist | Gap 40 Backfill Checklist (Pilecaps and Ground Beams) |  | Gap 40 Backfill Checklist (Pilecaps and Ground Beams)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f6b1e1d1-593b-5ef0-ac05-4adc89d2d1a5 | checkpoint | Location reference attached
e9f913bb-f398-5fd9-8ea8-fa4753e103f6 | textbox | Description
bd15c58b-3f81-5a4b-a489-fb66d6ee271d | checkpoint | Gap 40 to finish level minus 25mm
2c45fc4e-fd22-545b-9448-a82936af4da7 | checkpoint | Compaction checked
a27defdd-b7e1-5377-af23-8314c358401c | checkpoint | Level checked
40389937-4f94-571b-b306-b95deb9476d2 | checkpoint | Formation level conforms to the levels and grades within tolerances of +0mm to -25mm (Every 20m)
3e4bcd00-37d2-5e77-b1cf-1dfc1158bca7 | button | Tolerances of +0mm to -25mm (Every 20m) (add string sheet) | Yes, No, N/A
a3c7f041-c37f-55c4-a69b-b220f2766242 | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
1649a0cc-aa00-5035-8124-9461eebdf2b7 | button | <15mm from a 3.0m (Every 5m) | Yes, No, N/A
6a753a80-9a67-51b4-b7ad-83f1abd35297 | button | Provide test results | Pass/Fail Provide test results
c0067dd4-ee1b-5b15-8bc9-4a183ad8d459 | signoff | Clegg test top of subgrade every 10m
1b9d7b59-ea07-4c83-8052-bc3b813272c7 | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
891a745a-fcee-5f85-9ae3-db86a537a90d | button | Acceptance | Pass/Fail
30057335-4825-5cbb-9659-ac28aafeaa92 | signoff | Completion Inspection of sub-grade for acceptance
62152a6e-5df6-53d6-9523-4d3eed935e71 | checkpoint | As-built documents received
2048e8f4-32df-5aa4-b335-229772acbaf4 | button | Documents received | Yes, No, N/A
9982ed7f-426b-5db8-b3b3-73a5907eb8e2 | checkpoint | General progress photos recorded
a0014333-42fc-5162-b89e-eb849e86e9a6 | button | Photos recorded | Yes, No, N/A
4b8b6eb7-7a7c-5c2d-88c9-f8700b2edf75 | signoff | Request signoff
98938047-1b8c-51a6-a5ce-59d2dcb6c8d8 | checklist | General - Upload of Documentation |  | General - Upload of Documentation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c3a60420-62e9-58fc-8b74-f7d7305351f8 | checkpoint | Documentation filled out & attached
ecfaf948-b45a-53be-bad4-7dff1b335d12 | note | Select "PASS" once the documentation is completed and uploaded here
c8693568-3277-5c55-b62c-71b4d7090981 | signoff | Request Review
0898e43b-872e-56aa-a94f-3129f902850b | checklist | H&S - Upload of Daily H&S Paperwork |  | H&S - Upload of Daily H&S Paperwork
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
682a8011-74f7-55ed-a830-250697ee8f31 | checkpoint | H&S Paperwork filled out & attached
37661f55-c2f3-5d0f-8722-80bb31b0b2ec | note | Select "PASS" once the paperwork is completed and uploaded here
3c6dfc5e-cd15-5f3e-8b06-de093eb8b926 | signoff | Request Review
36de41d1-22ba-4fcb-834b-66b89a7521c1 | checklist | Roading QA Checklist |  | Roading QA Checklist
30838779-1b21-4dbf-ae89-24a5e8973225 | section | Details
713ad3fc-81fa-4fc5-978b-f689ba6357d1 | checkpoint | Location
0277a53e-97eb-598e-8d66-5971d1620176 | textbox
3c7d613d-e708-4920-881a-577f174a61c5 | section | Subgrade
afc2d853-ec87-49f0-bf1f-d09ef4d503f1 | checkpoint | Subgrade cut to design level
bdb84530-3d2f-4350-9455-7055d25cb3cb | checkpoint | Subgrade testing report
ad0503a8-6dc0-4320-aff0-7465b890ae92 | checkpoint | Any Subgrade failing detected
84a25ec8-3123-48ad-bae7-c1944592c1cb | checkpoint | Undercut Asbuilt
4608ecab-bd6a-4962-bede-d1bec6cc7a27 | checkpoint | Subgrade Asbuilt
0f610bfd-f3d4-40b5-9fcd-1448727a5734 | checkpoint | Subsoil photos
aa0b112b-5451-42b5-bb40-473f8be610b1 | section | Subbase
67f5e22f-1e16-48c2-b94e-62a6ea525599 | checkpoint | Type of material used
ae3f7bc7-8fc1-5fe1-8aa1-65d303501936 | textbox
4fcd7b9a-cf30-4142-9a9b-cd9d6bc313f1 | checkpoint | Compaction test report
754d8a47-456d-4cdf-967d-52a7a8d29eb0 | checkpoint | Subbase Asbuilt
5770eb78-f4e2-45af-94a9-6a8ddabe03a7 | section | Asphalt
6943a846-51d3-48c0-a0e8-33cbe1b3b3ce | checkpoint | Asphalt Mix type
acfef9be-5272-5b8c-98fb-a2c98660a1dd | textbox
656a7296-ea2b-47bf-b9b2-66bac168c29d | checkpoint | Asbuilt
08f80add-16ae-52e3-991a-141ecd2c35e9 | checklist | Sand Backfill Checklist (Pilecaps and Ground Beams) |  | Sand Backfill Checklist (Pilecaps and Ground Beams)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f6b1e1d1-593b-5ef0-ac05-4adc89d2d1a5 | checkpoint | Location reference attached
a44c25fc-fbdc-5f06-8bd9-b938078f0112 | textbox | Description
c15a7423-3d06-5f39-9fb1-e5c349eb5e32 | checkpoint | Sand backfill to thinnest level 25mm
a27defdd-b7e1-5377-af23-8314c358401c | checkpoint | Level checked
40389937-4f94-571b-b306-b95deb9476d2 | checkpoint | Formation level conforms to the levels and grades within tolerances of +0mm to -25mm (Every 20m)
85314a88-5e2e-5972-b822-0a30bbcf2ec4 | button | Tolerances of +0mm to -25mm (Every 20m) (add string sheet) | Yes, No, N/A
a3c7f041-c37f-55c4-a69b-b220f2766242 | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
f4979679-2429-53a1-8b26-3085962c60f8 | button | <15mm from a 3.0m (Every 5m) | Yes, No, N/A
5397b5cf-9c6a-5d32-bc0c-27e8d7f30c8c | button | Provide test results | Pass/Fail Provide test results
267f2824-2fc1-4a45-b899-f42ab1237ad6 | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
38852ec5-45e5-502c-9c42-2eda6d46788f | button | Acceptance | Pass/Fail
90ebac1d-a3b8-5425-a219-108eb004ec02 | signoff | Completion Inspection of sub-grade for acceptance
62152a6e-5df6-53d6-9523-4d3eed935e71 | checkpoint | As-built documents received
7db91df9-f7d9-57bf-8394-b28557bd88eb | button | Documents received | Yes, No, N/A
9982ed7f-426b-5db8-b3b3-73a5907eb8e2 | checkpoint | General progress photos recorded
16b28623-b697-5a70-bc38-06c2ff18e8e8 | button | Photos recorded | Yes, No, N/A
4b8b6eb7-7a7c-5c2d-88c9-f8700b2edf75 | signoff | Request signoff
f3b6975e-341e-583f-a7f4-73e57403bb4e | checklist | V&B - Compliance Checklist |  | V&B - Compliance Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
5cd0eaaf-b7cd-5efe-992a-c1fa1734f1a3 | checkpoint | As Builts - recorded & attached here
5896c275-6b52-52b9-8c09-1e1bcc5b1568 | checkpoint | PS3 - completed & attached
6034fe32-af7a-5920-adbf-212a9589f0a7 | checkpoint | Any additional compliance documentation - completed & attached
3fd24559-a379-5f4c-9d1d-f130ccfddf67 | note | "pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
6f3db279-a289-5d7d-9823-a913abf85e05 | checkpoint | All Compliance Documentation Checks Completed
5e566568-2a9b-5018-9a8b-c3a1ab25c39e | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
51b75576-70ca-5ba0-accb-1a5f437cf788 | tickbox | Report with all Compliance Documentation checks sent to Main Contractor
8b8b79e9-4556-5d9d-a658-467c135a62dd | note | Click on the QA Report button above this checklist on the CONQA app to send this completed documentation to the respective Main Contractor
3721cfcd-4a17-4894-9aab-361ca3b66c17/4 | checklist | V&B - Compliance Checklist- Detail Excavation (Services) |  | V&B - Compliance Checklist- Detail Excavation (Services)
673c4b26-97f8-4a91-8dd0-85f7c2e6fa94 | section | Details
64d5b563-4dec-4d70-87d1-8bb5fc9495a0 | checkpoint | Location
87b9e079-aa78-5a07-a1cf-9aa074e3a554 | dropdown | Zone | 1,2,3,4,5,N1,P
125225bc-21de-406c-ba99-6ca9ca0986e9 | checkpoint | Service type
8b580073-6cd0-5f25-9069-087e65958cb2 | dropdown |  | Sanitary Line, Sewer line, Stormwater
4850c9a6-5e86-43bc-b527-e83f92870a7b | checkpoint | Under ground beam
4f525e92-800d-4f06-ab0e-baadbea8aa5e | checkpoint | Setout
a61ae043-ee22-5e3c-bc42-50da2269c6cd | note | Excavation Depth
41e08cf4-c285-4672-8ef9-ce063fa5b43b | checkpoint | Subgrade testing and results
29e8b30a-9f5e-5a2a-aa10-5569ee3174a9 | note | Any soft spots or undercuts & associated remedial
334ba6a8-242c-457b-8444-cd873eaaf2de | checkpoint | Granular type - Bedding
f83889fd-960d-46b4-ad58-4f8715f22f06 | checkpoint | Correct pipe
58407460-48aa-5850-890a-4be60a491d75 | note | Material and Size
f2870f2b-6d7c-452a-bc5e-6e634b600b4f | checkpoint | Correct gradient
bf657880-b476-5ef4-9e3b-21f22f10da26 | note | Inverts and RL's
bff7aba9-5c88-4b7f-b48e-b2e291bcdbab | checkpoint | Surround Pipe works & material
89e56949-4289-4a96-a87d-3f8b452e585c | checkpoint | Council Inspection
63d39ed8-8d4b-54df-abe7-a19e6ce0ed49 | note | Hold-Point and Visual Inspection
1e9fa7da-19a2-40f3-941f-e2b3715ae59d | checkpoint | Backfill
8f81f720-775b-48b2-a763-88c9eb23e9c4 | checkpoint | As-built
b25a2f16-3749-5d2e-ac02-6e1ae2f5a6d7 | note | Invert of pipe and Lid Level
c7f14e37-c751-4323-b412-9b110fc41a8c | checkpoint | Final Pass: Service works completed, reviewed and approved
5e887629-cd37-5f8d-a43b-0294a63cc9cc | note | Attach As-Built
630545ef-8b1e-52df-abc3-aba6ffa993fc | note | FINAL - Pass when work(s) are completed, area clean & tidy