## Master List Templates
Id | Type | Name | Values | Prompting Name
be1fd787-0228-4fbc-91a6-aec2900758ce | checklist | V&B Underground services |  | V&B Underground services
e0fbb1ad-5a95-4b02-bdd0-666d00da233c | section | Details
540eda5f-4c08-4b87-bffa-3fec9d9c365c | checkpoint | Location reference attached
f5938893-632b-58f3-825f-06bcc03fb107 | textbox | Description
0e4b34eb-132c-5777-b5da-c1063c647ce2 | dropdown | Service type | Hydraulics,Electrical
7581d4b6-2e2a-4f77-8f78-7a83d545bb70 | checkpoint | Setout/Excavation depth
09233f41-24b4-511c-94d5-010ab02f2357 | textbox | Excavation depth
002a864a-5c03-4f50-b850-5d75e0bc5ad6 | checkpoint | Subgrade testing and results
c262309f-6bb5-54bb-8f35-11dcfe81264a | note | Any soft sopts or undercut & associated remedial
1268241d-9387-4af8-b305-8f456e572bb0 | checkpoint | Granular type
b3669f0a-1ccf-401b-b49d-4f6d65d3c152 | checkpoint | Protection tape, tracerwire, magslab installed
68c471c8-77f0-49f0-bad7-34f681b04b4a | checkpoint | Backfill - GAP20 (150mm thickness)
92e451ae-189b-47db-8c98-1afd41557705 | checkpoint | Structual backfill (ATAP65/GAP65 200mm lifts)
96070988-88f0-4a7c-bc30-21a06e53348c | checkpoint | As-builts
dd021541-9832-4c16-9b33-63bd755d56db | checkpoint | Final Pass: Service works completed, reviewed and approved
e97fa2cb-c323-5308-b78c-fd38310def28 | note | Attach As-Built
b2bcf328-35d0-57f9-b12c-e1f0fa7f856c | note | FINAL - Pass when work(s) are completed, area clean & tidy

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c3a7e657-ba7b-48a2-b763-11288bcab9cb | checklist | Compacted Backfill Checklist (Pilecaps and Ground Beams) |  | Compacted Backfill Checklist (Pilecaps and Ground Beams)
d346fb9d-d0a4-421e-84ee-ce2a604bcb7c | section | Details
155156c4-7458-4dea-8c45-36b8f2114766 | checkpoint | Location reference attached
3dcb78ac-6e58-5789-b751-dbcc11f69de2 | textbox | Description
ad9b3baa-baea-4705-ae11-90b0c6d97ff4 | checkpoint | Backfill compacted to 200mm layers and tested for compaction
1a17dfe0-7e92-4cac-8e2e-459e697063df | checkpoint | Finish level minus 100mm
ba269415-88b8-4864-8f76-cbccf3ee2996 | checkpoint | Level checked
0901bb0f-2967-4a3e-975d-9490144b6316 | checkpoint | Signoff and handover
93fa4912-deac-415f-8234-ab39a36813b2 | signoff | Request signoff
bc81fe6d-e99a-43e8-b572-4a44a1328f38 | checklist | Compacted Backfill Checklist (Pilecaps and Ground Beams) - Revised |  | Compacted Backfill Checklist (Pilecaps and Ground Beams) - Revised
b6502ae5-7618-47b0-bcbd-a3706ffa7c1b | section | Details
25c1d3ce-b35f-489a-97b3-f9e9b4b6830c | checkpoint | Location reference attached
8635841f-880c-5bbf-aae2-7c64de809f1e | textbox | Description
dd786b93-e2ca-438f-a806-77114b11c280 | checkpoint | Backfill compacted to 200mm layers and tested for compaction (all lifts done)
1a05074d-88e2-4ebd-8b56-4e3ccb6ccfee | checkpoint | Backfill Lift 1
192704c3-fed1-56a3-8ddd-2454439f3bd4 | note | 300mm lift only for Lift 1
56d397d6-7469-54b4-a755-fb955ef85b49 | date | Test date
7a2ac55c-0247-52e9-a50a-e0bf22cb55d2 | textbox | Clegg Reading (CIV)
0507abbd-360e-55c6-a39f-bf59d27b4839 | textbox | Retest (CIV)
da962b25-7253-4d77-8afa-e26230263c99 | checkpoint | Backfill Lift 2
00b7277f-3c7b-5398-a427-1191d592d2df | note | Test every 200mm
9b91d180-340f-5028-9fe8-5640b6d2791c | date | Test date
6f2d1673-8583-5b2b-8dbb-2c87fa809768 | textbox | Clegg Reading (CIV)
11e4cc28-bc54-5869-a417-c8bb7960b1d3 | textbox | Retest (CIV)
f521a1e2-74aa-4b5e-b9f2-781dd27e1fc6 | checkpoint | Backfill Lift 3
889cbb4e-2f97-55bd-af83-a4966fe10a6b | note | Test every 200mm
dd248cf0-bc3f-50d1-aa95-8a2eb4851a8b | date | Test date
529a705e-7a38-5f92-a4e0-2761f089b85c | textbox | Clegg Reading (CIV)
1b02c083-255b-534c-a2bf-e7a165299ae4 | textbox | Retest (CIV)
9ad1a3dc-f50d-4642-b6fc-d47777396e64 | checkpoint | Backfill Lift 4
ab1fecfe-536e-5cd9-8970-31268139efb4 | note | Test every 200mm
bc487eab-3b05-58bf-a0cb-8f71d9c589ab | date | Test date
a3faf0c3-cb5f-50f5-a220-5759d50fb8e4 | textbox | Clegg Reading (CIV)
fdedf7d2-0788-5db8-9332-319813c2de06 | textbox | Retest (CIV)
d18412b0-1c5f-42ab-9906-0bb0b7e1f74a | checkpoint | Backfill Lift 5
9d194aa5-01bd-51fe-bfa5-276c03e193d1 | note | Test every 200mm
e44c4b45-8348-5458-a9e2-23a4ecf5d024 | date | Test date
365e5efe-9890-5817-a796-48dfa9c9b649 | textbox | Clegg Reading (CIV)
f07e36b9-b7d9-5b37-8753-2064689aee17 | textbox | Retest (CIV)
d20e0b77-e579-4d02-88fb-49598311df10 | checkpoint | Backfill Lift 6
5a027c2c-7073-5afa-bd0d-5092c9f05013 | note | 300mm lift only for Lift 1
2c25b062-1b1b-5af2-922a-0404e54e662d | date | Test date
ada433db-77fc-5307-b183-20d3ea4ea331 | textbox | Clegg Reading (CIV)
f5f6f8c9-d4af-5040-a562-985c13828367 | textbox | Retest (CIV)
67ae975f-32cc-4b29-94ac-03310529ba86 | checkpoint | Backfill Lift 7
ea366541-cc34-530f-8c8f-21fad5efc36b | note | Test every 200mm
98f6842e-e135-58c2-8c48-e2b27709dbfb | date | Test date
35831bdd-3a1a-5b2a-8bea-676de044e386 | textbox | Clegg Reading (CIV)
00b5dccf-7b1d-5429-b315-8de81550602f | textbox | Retest (CIV)
26a8d318-0bfc-4392-8a6a-b9b35cf230ed | checkpoint | Backfill Lift 8
ca39dcf6-ab96-5929-a0cf-1f2d888cf3ba | note | Test every 200mm
e6f08f29-d021-5b85-9d97-75e92b3267ed | date | Test date
d02bdbd7-ad4d-5ea8-9d2b-83c6ccf5dc8a | textbox | Clegg Reading (CIV)
adc3f953-a02c-5104-ad1e-f35312f4562e | textbox | Retest (CIV)
f5fa8484-1875-476e-85b1-1cb1416c0525 | checkpoint | Backfill Lift 9
ee0a35f8-9980-57fc-bb05-65801fde9b4b | note | Test every 200mm
c834b1f5-8fe7-561a-9f4b-512934e07eaf | date | Test date
d71d5f55-0f35-5508-af54-209a177f2cec | textbox | Clegg Reading (CIV)
87562ae1-bd6b-570f-bf33-ceaf61e111d4 | textbox | Retest (CIV)
8039f614-ac5e-475a-b21a-bbe06060ebac | checkpoint | Backfill Lift 10
dc0466f9-383b-5f7a-9df7-846e660a3f28 | note | Test every 200mm
6192c2d8-62b5-5df4-9d3c-11bbf5e56b1a | date | Test date
21380b52-2a60-5a1e-8d98-2426e8c35969 | textbox | Clegg Reading (CIV)
b6e8cf52-4e08-59e3-8b80-a56e1c69d5ba | textbox | Retest (CIV)
0d97ad49-e5f8-40c6-a2fb-4a8679747e6d | checkpoint | Finish level minus 100mm
f7b9df68-eb6d-4942-a6a2-d4abaa0e65a4 | checkpoint | Level checked
6d7e3ad8-af2e-4af2-9af1-ec9f7630b22d | checkpoint | Signoff and handover
391f5b5c-cad7-4bd9-a390-556b70a6e269 | signoff | Request signoff
3eb00619-c3cd-4e91-9335-ce64fc72048a | checklist | Detailed Excavation Checklist (General) |  | Detailed Excavation Checklist (General)
b7724254-243b-4032-9b0a-ef95c002fc2d | section | Details
401f9128-3ca3-4685-8bd2-7a69f5438f88 | checkpoint | Location reference attached
a9cfd6d8-da54-4afe-808a-05707e684421 | checkpoint | General Photos / Comments / Observations during excavation
dac22b69-6280-4233-a84b-fefa7fd3d87f | checkpoint | Any soft spots or undercuts & associated remedial
763f80a2-1ad0-4ad2-99b9-117b5feb2517 | checkpoint | Excavation checked, correct and approved off accurate survey marks
01b801d3-eb83-5ca6-9fc4-16b45fd7fa68 | note | Location accurate
b0e9aecc-9153-51c4-9c4b-8dd8d2e033d0 | note | Depth correct (allow for site concrete if required)
81de9bc2-2bc0-5fea-870f-42c4cb4401ee | note | Width correct (allow for boxing if required)
d4d962b9-f2d5-4e5e-a2bc-057c0dc99df9 | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
0d633441-4685-4120-ada1-acdf99212795 | checkpoint | Excess Material Cleaned up and removed as required
623f31a8-4d88-52d8-a168-e15600a5af71 | note | Subgrade inspection (if applicable)
0fdff639-2dc9-40c2-847e-7cec56a7080b | checkpoint | Detailed excavation completed, reviewed and approved
7e251b1c-60e8-53f4-9d1e-76d8c9278e7a | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
404263f5-6503-5e00-a8b4-37224f492a66 | button | Trades QA received & attached as applicable | PASS, N/A
c943625a-e5f1-4ce0-8a87-ce7b3e802eaa | checklist | Detailed Excavation Checklist (General)(Pier) |  | Detailed Excavation Checklist (General)(Pier)
85a94ad5-35c9-4961-8d8e-043234ad28c0 | section | Details
65b1f46c-bcf0-4162-8d31-0ef89d624643 | checkpoint | Location reference attached
27be83c4-bb9b-40c3-abec-accbc85b25fd | checkpoint | General Photos / Comments / Observations during excavation
63bc3b4e-0973-4eba-82f9-34d6df02df43 | checkpoint | Any soft spots or undercuts & associated remedial
e43566b1-0c82-4bfe-8920-fc91bf61561d | checkpoint | Excavation checked, correct and approved off accurate survey marks
3cfe459a-dc96-5615-8cc5-f52173ec2d81 | note | Location accurate
5a4690ab-b68b-5829-872d-fcd52b46a156 | note | Depth correct (allow for site concrete if required)
996993ba-9fce-5f3d-b056-644e96529d5c | note | Width correct (allow for boxing if required)
85ef9941-3ad6-424f-95c8-71446cfeb117 | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
9457b95a-224b-49f1-aecb-2c854bfb1a1a | checkpoint | Excess Material Cleaned up and removed as required
04033c6f-102d-54b0-a448-b4cd74d80d2e | note | Subgrade inspection (if applicable)
bc85a9d2-fca4-43e5-a896-6a28237b1596 | checkpoint | Detailed excavation completed, reviewed and approved
826eaf40-1e14-5186-9b46-be39fc4da5e6 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
33afdb96-2a20-54ed-a9cd-24ee19564db0 | button | Trades QA received & attached as applicable | PASS, N/A
b4fd8a4c-b1a8-49b7-9281-9b45a9cd9004 | checklist | Detailed Excavation Checklist (Ground Beam) |  | Detailed Excavation Checklist (Ground Beam)
c0b86d34-46a6-4b30-a413-a26a344dca4f | section | Details
9e1c7e38-4345-4dac-95fd-0e1472eb7235 | checkpoint | Location reference attached
6dc625f4-f225-5c33-b6cb-3263421dfe13 | dropdown | zone | 1,2,3,4,5,N1,P
9a5d99cb-0cb9-5df9-9570-2c3132030e9f | dropdown | Ground Beam type | GB1, GB2, GB3, GB4, GB5, GB6, GB7, GB8, GB9, GB11, GB12, GB13, GB14, GB14A, GB14B, GB15
36794cca-1573-4482-8a9d-ca3fef2c7593 | checkpoint | Ground beam setout with working area included
a4790157-f8ba-53ce-9392-dee984528b74 | note | Any soft spots or undercuts & associated remedial
77250576-a243-437c-ad55-fd4e5f891f25 | checkpoint | Excavation checked, correct and approved off accurate survey marks
459dfc59-e17d-5e90-8268-41c5b498c687 | note | Location accurate
80b4f72c-0175-508a-b107-0f2382159857 | note | Depth correct (allow for site concrete if required)
7ff2edb2-f85b-5c23-9db5-3adfe6d2d8a4 | note | Width correct (allow for boxing if required)
f420516a-41a9-4f84-9f49-d54f7dfbaf6a | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
23f5e3b0-bcb2-4727-94af-0e39e9ec52fd | checkpoint | Excess Material Cleaned up and removed as required
55aa72da-8313-4452-87fc-fc6736931617 | checkpoint | Detailed excavation completed, reviewed and approved
b0653baa-0e74-538f-acfe-92b26dfc9e09 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
14aabd53-e85c-5cc0-a0c2-6b03810b29bf | button | Trades QA received & attached as applicable | PASS, N/A
8c550ddf-159d-4000-ba82-3f1d9bfc4830 | checklist | Detailed Excavation Checklist (Ground Beam)(Pier) |  | Detailed Excavation Checklist (Ground Beam)(Pier)
d7aaed8c-217b-40cb-9c85-d9dd971ff8a0 | section | Details
7b93cc12-96b1-4ecb-8d90-c834c31f1bc2 | checkpoint | Location reference attached
18f5beec-7cfc-5a77-911b-4289d58ad166 | dropdown | Stage | 1,2,3,4,5
47dd95d6-0851-4268-a8e0-0b92745f29f5 | checkpoint | Ground beam setout with working area included
36d744d5-b641-5594-884d-1434789a0f42 | note | Any soft spots or undercuts & associated remedial
6086c2ac-6735-4e04-8ded-8cebdc9b5d3f | checkpoint | Subgrade testing
b16ff066-1c93-5174-a0c9-3f87c1d350fe | note | Shear-vane Photos / Results / Comments
bd3fab22-f946-4083-93aa-905469211d30 | checkpoint | Excavation checked, correct and approved off accurate survey marks
699fc43b-8e7b-5c9d-b972-e2c7ac32a2e2 | note | Location accurate
f7f8ab04-6a62-537b-a06a-cc93bcb57b96 | note | Depth correct (allow for site concrete if required)
e52ebbe0-cfe3-590f-a2ab-073351551968 | note | Width correct (allow for boxing if required)
f6febb3c-b01d-44a4-af85-d41bc96d771b | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
d839e98e-f810-4ef2-a896-3ee4cf74a4b7 | checkpoint | Excess Material Cleaned up and removed as required
8d08b6d5-b6f9-493e-afd5-761f611b92bd | checkpoint | Detailed excavation completed, reviewed and approved
0a7343ee-833a-5ec9-a659-d53ee812f983 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
13813a19-9ace-5df7-99a4-3dbf69f6c3a5 | button | Trades QA received & attached as applicable | PASS, N/A
feecd863-a370-446f-bdfa-d0e58231367d | checklist | Detailed Excavation Checklist (Pilecap) |  | Detailed Excavation Checklist (Pilecap)
7f758396-dde1-42da-806d-14bac41fca6e | section | Details
2e45d524-1ffc-4342-a7c9-4a96d7a6f66f | checkpoint | Location reference attached
27365b3c-6c11-56cd-ae38-be17935a2b2b | dropdown | Pile cap type | PC01, PC02, PC02a, PC03, PC04, PC05, PC06, PC07, PC11, PC12, PC13, PC14, PC15
db973d80-f913-4353-aba4-3fea7d2f4c64 | checkpoint | pilecap setout with working area included
1e806a4d-8309-524a-a992-ea55d77dc8f0 | note | Any soft spots or undercuts & associated remedial
4bf11f7a-7003-4cbc-a704-e6d1920d7a26 | checkpoint | Excavation checked, correct and approved off accurate survey marks
693dff4e-fa6e-5a7b-81c8-722665e5b309 | note | Location accurate
1bfe42f5-a30f-5351-bece-ab0d747d5d88 | note | Depth correct (allow for site concrete if required)
3c13c869-a40b-5899-a733-f320e97f74db | note | Width correct (allow for boxing if required)
5c4f6b5b-4f80-4322-a67c-3498c1199069 | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
d6e60aa7-e4dd-4d15-a808-c73c2c3b1a8f | checkpoint | Excess Material Cleaned up and removed as required
12963ebd-872d-4b83-9b68-b0d2c6bccda5 | checkpoint | Detailed excavation completed, reviewed and approved
c3d447d3-6b39-57a9-b7fa-4822b217fd28 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
6524a955-3500-5d83-9e09-2a00b772defd | button | Trades QA received & attached as applicable | PASS, N/A
975d4d23-52a2-4775-942b-f032685c3bd1 | checklist | Detailed Excavation Checklist (Pilecap)(Pier) |  | Detailed Excavation Checklist (Pilecap)(Pier)
84c207e3-8438-4330-acb8-dbfc62dded8a | section | Details
14926ef2-6341-4000-b5ab-bb04203ea938 | checkpoint | Location reference attached
e80acc34-c637-428f-a7c4-0b154cbb728b | checkpoint | pilecap setout with working area included
ccd9d1c0-72fe-5341-a37c-560c6dd2e3c3 | note | Any soft spots or undercuts & associated remedial
101e235b-90f5-4b4a-a09d-6a19ac9640c8 | checkpoint | Subgrade testing
4f525390-e35f-5acd-8eb2-046c85393bf5 | note | Shear-vane Photos / Results / Comments
444f6266-de87-4584-8330-c69d218a750c | checkpoint | Excavation checked, correct and approved off accurate survey marks
abf94e0c-3dd8-5073-8dbf-df49c17955d4 | note | Location accurate
c82ef4bd-51ce-5f9f-839b-276d8dc4940e | note | Depth correct (allow for site concrete if required)
002285c1-363d-567b-a862-bca4ba0ff02e | note | Width correct (allow for boxing if required)
df8f2e71-5a20-4ce9-8178-5b6ddfe9b01c | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
e4b0fa65-8ef9-4aa4-848b-d299d7f5301d | checkpoint | Excess Material Cleaned up and removed as required
4b8e4b34-f46a-434b-b88c-a0df7982a608 | checkpoint | Detailed excavation completed, reviewed and approved
d947a42a-0943-545e-bf51-46671deaf8f0 | note | FINAL - Pass when work(s) are completed, area clean & tidy - ready for Concreting Contractor
5fa88c59-6433-5912-ac95-31010c706aab | button | Trades QA received & attached as applicable | PASS, N/A
25cd77c7-6ce0-4663-9f3e-fdb1f9065fd3 | checklist | Gap 40 Backfill Checklist (Pilecaps and Ground Beams) |  | Gap 40 Backfill Checklist (Pilecaps and Ground Beams)
57b8e21d-7cbb-46fc-80f8-6c61a438a234 | section | Details
47788fbf-30e4-4591-b500-6865943b0292 | checkpoint | Location reference attached
844c4157-1372-5232-bcc6-0220a5d65453 | textbox | Description
eb524e3e-e88c-45ea-bcfb-da6a48fe65e7 | checkpoint | Gap 40 to finish level minus 25mm
86d09f6a-3386-4f95-a4b4-fd691df00556 | checkpoint | Compaction checked
42bd37e8-5c29-44a5-b3a1-c7a0f0a715c6 | checkpoint | Level checked
aeaf81ae-133e-4b1c-a428-a1419ea30004 | checkpoint | Formation level conforms to the levels and grades within tolerances of +0mm to -25mm (Every 20m)
cc358046-ce99-56b7-8ab2-2877edd30570 | button | Tolerances of +0mm to -25mm (Every 20m) (add string sheet) | Yes, No, N/A
056dd97a-ee42-4b04-8491-5bc4ae309136 | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
65cd549b-ac0b-569a-ad78-337fb5ba916f | button | <15mm from a 3.0m (Every 5m) | Yes, No, N/A
92b3498e-61a6-5002-aa45-9727554cf658 | button | Provide test results | Pass/Fail Provide test results
69420d2a-f0d5-47bd-b203-b172490119ad | signoff | Clegg test top of subgrade every 10m
aa6e4ca2-edb3-46d8-b8e4-d9386dc86b30 | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
ea1f9e41-91fd-5d2a-9a1b-3f8555c856fc | button | Acceptance | Pass/Fail
7a5d8cb1-5fcc-498a-b155-481b8bedfc8a | signoff | Completion Inspection of sub-grade for acceptance
990315f2-726b-4e84-84db-215e7795081a | checkpoint | As-built documents received
783ea0de-f2fd-5614-b392-92fb21f69649 | button | Documents received | Yes, No, N/A
48dfd042-7dfd-4796-b501-a83c04707b75 | checkpoint | General progress photos recorded
7034bfe7-065f-5770-bcdc-57f9a42ed272 | button | Photos recorded | Yes, No, N/A
b7865c71-e70d-40dc-a365-a1e88727bce5 | signoff | Request signoff
7c9fe791-d79b-49f3-9268-97b2ac0e769a | checklist | General - Upload of Documentation |  | General - Upload of Documentation
5f93e082-b913-4f03-ad6a-69e4cb46b66a | section | Details
32b181d7-9cec-45a2-95b2-c1d0d3d2bb90 | checkpoint | Documentation filled out & attached
ec28c5e6-804a-51b8-94eb-fd3715ad337d | note | Select "PASS" once the documentation is completed and uploaded here
e70d1f71-3c2e-4f75-89d1-500c47284dc0 | signoff | Request Review
a392fd96-b1d4-4211-b8ce-c43e92bd92ca | checklist | H&S - Upload of Daily H&S Paperwork |  | H&S - Upload of Daily H&S Paperwork
6dafc620-afb3-4bb8-bfa6-96b57ee24f80 | section | Details
39d72fd4-7733-4dcc-80e9-7194c683f48f | checkpoint | H&S Paperwork filled out & attached
181ae756-c03f-5df2-8c95-4f118358ce81 | note | Select "PASS" once the paperwork is completed and uploaded here
2eb1c4c5-0ee0-4b06-80d2-15d2031fc9eb | signoff | Request Review
b1fbabff-8f59-4fc9-9557-bffc26c718cc | checklist | Roading QA Checklist |  | Roading QA Checklist
a593cd59-9bd2-477c-b603-5037fa23015f | section | Details
d59fdcd2-cc77-41b6-b8dd-db9546c9f8dc | checkpoint | Location
c483cb5c-7898-5ca2-b6fe-c5387d84ebb6 | textbox
72b08279-8514-48a1-a776-c9c4bbb11926 | section | Subgrade
9ae18e34-23f3-4bec-9877-3facfad3c75c | checkpoint | Subgrade cut to design level
e31ce428-21bb-45fa-b78a-cbacb46e93df | checkpoint | Subgrade testing report
105f8756-c383-4bd1-a6e6-a15e27ea3788 | checkpoint | Any Subgrade failing detected
679f59c2-eb0b-43fa-9572-69057e2d76e4 | checkpoint | Undercut Asbuilt
ac84f8e7-e3f8-49a0-9696-214dcdcc3b26 | checkpoint | Subgrade Asbuilt
aed95350-9c4a-4455-aa0d-c2b318df8c94 | checkpoint | Subsoil photos
f8d05430-315a-4eec-9e17-bec2fbecb04f | section | Subbase
17542252-cfed-42d6-985d-97f5e8228758 | checkpoint | Type of material used
42fdad77-fc14-5f2f-9190-ab9f1c865a63 | textbox
6a76ea3a-fb02-4506-a1cc-11ecaafe9f97 | checkpoint | Compaction test report
0432faae-bd44-4517-be54-28627345b593 | checkpoint | Subbase Asbuilt
0fdb91a3-284a-4ce7-8b1d-64f8a1a25da1 | section | Asphalt
1f8eba9d-f831-498e-9cb4-808056cc70d5 | checkpoint | Asphalt Mix type
a9bc8834-52ca-5313-ab7e-83640b0e53af | textbox
2b223ba7-bdf7-4aa2-aa18-0dfb5f02ed9a | checkpoint | Asbuilt
c912d066-7e3d-4fe8-a555-88f2f39fde6d | checklist | Sand Backfill Checklist (Pilecaps and Ground Beams) |  | Sand Backfill Checklist (Pilecaps and Ground Beams)
54bf98a8-be64-446d-8dde-dff22b4dd0df | section | Details
1fafb643-1356-4f50-b154-0614e93632a1 | checkpoint | Location reference attached
cb7bb273-a8bd-5bc7-89a1-3f6afee2fbf8 | textbox | Description
2bfc8895-fb22-42c6-9bb7-e4c314b8fd70 | checkpoint | Sand backfill to thinnest level 25mm
445ae54e-9eed-4beb-9e8c-77a0881d3744 | checkpoint | Level checked
881f1648-71ad-4a8a-96f2-69750993de07 | checkpoint | Formation level conforms to the levels and grades within tolerances of +0mm to -25mm (Every 20m)
ded1c1eb-1392-5a26-ab75-e5d27d0c1886 | button | Tolerances of +0mm to -25mm (Every 20m) (add string sheet) | Yes, No, N/A
7cb67729-041c-417c-94e0-26204dc286ce | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
f8017fa9-ae35-5f42-8d7f-23010ce47f42 | button | <15mm from a 3.0m (Every 5m) | Yes, No, N/A
cb89920e-1a21-5240-b908-dff0d30d8372 | button | Provide test results | Pass/Fail Provide test results
62634a29-1e04-4988-8fbb-ac5cf7bd40e2 | checkpoint | Deviation of <15mm from a 3.0m straight edge laid parallel (Every 5m)
0d63a3eb-d20d-5de6-a102-5d1ea48dfd33 | button | Acceptance | Pass/Fail
37f722c1-f6d3-4413-bd05-c34bff743a3f | signoff | Completion Inspection of sub-grade for acceptance
244ffe9a-ee2b-4750-854d-2ab8a5d744bc | checkpoint | As-built documents received
21d40db3-eabb-51db-8b62-fc9c0fc4ae6c | button | Documents received | Yes, No, N/A
23c993de-1e88-4378-8cce-d7f81f85f104 | checkpoint | General progress photos recorded
448d3381-320a-5371-b093-c1d2ef39727f | button | Photos recorded | Yes, No, N/A
2ca7b6f5-2b1d-4b20-bab9-2a36a91200d0 | signoff | Request signoff
ae58fc54-dc08-4750-a422-2a1ed5ef0877 | checklist | V&B - Compliance Checklist |  | V&B - Compliance Checklist
d7b0161e-2b8c-4d65-b868-31c3d70a53cb | section | Details
e2e039c0-054d-418b-a2d0-a66296324d8d | checkpoint | As Builts - recorded & attached here
41640fb9-59ed-47c8-a7d8-64504aec99b1 | checkpoint | PS3 - completed & attached
9f24a77f-3957-447b-b439-fc6be19fb04d | checkpoint | Any additional compliance documentation - completed & attached
2563f254-34c2-5b12-9a3b-de665ac5ba0c | note | "pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
fbd48c0f-1875-43e4-9d7d-14164bd4dc61 | checkpoint | All Compliance Documentation Checks Completed
6cc8c5f7-0409-53c8-859c-9e91a65eac39 | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
303e2a97-23b2-5100-8570-ce8ff700c155 | tickbox | Report with all Compliance Documentation checks sent to Main Contractor
3bf6ac3f-ae2d-54de-9aee-1f6532b5af05 | note | Click on the QA Report button above this checklist on the CONQA app to send this completed documentation to the respective Main Contractor
a0b3dbf1-3aec-450f-92e5-348f82baa91a | checklist | V&B - Compliance Checklist- Detail Excavation (Services) |  | V&B - Compliance Checklist- Detail Excavation (Services)
4aa095cd-bc10-4084-943f-e0f9438d2e24 | section | Details
e7045819-ffcb-4b6b-aebd-ae8939d7fbac | checkpoint | Location
eb7059c6-fc4e-529d-81e6-9afa1f3d50ee | dropdown | Zone | 1,2,3,4,5,N1,P
e240637b-2193-4cbe-9dfd-b256eebdc4e3 | checkpoint | Service type
f12f732d-175c-5d29-bc0c-66035fffa386 | dropdown |  | Sanitary Line, Sewer line, Stormwater
66aed403-ffac-479c-8ed6-b018ef29912c | checkpoint | Under ground beam
f1f7e0a7-bd85-47bd-b87e-9ac046b595b0 | checkpoint | Setout
0b3762f9-ef77-5aa7-a808-eea40a73b87f | note | Excavation Depth
83b31915-0b5a-4788-8861-a615d29df95f | checkpoint | Subgrade testing and results
56796221-a897-54da-9fc6-4dc71a2693ad | note | Any soft spots or undercuts & associated remedial
e9f1e376-fa34-49b9-b20d-3b7afcd6866f | checkpoint | Granular type - Bedding
f8fca944-e649-4b32-a3f9-592e638fe6c4 | checkpoint | Correct pipe
ef86d3be-34d2-594d-b41a-e3eeb756b4e1 | note | Material and Size
677c51cd-afef-4f4e-957f-0126c3f91ba6 | checkpoint | Correct gradient
5d1907c0-640c-5942-b2d4-c8e142e22237 | note | Inverts and RL's
23ce4f39-57c8-4a54-90df-1e980432be59 | checkpoint | Surround Pipe works & material
f1ef6c1a-129b-411f-97d3-f80b14cb7606 | checkpoint | Council Inspection
c3b69317-98b6-5e57-b6ab-d958081edeb4 | note | Hold-Point and Visual Inspection
1fea31fb-0bab-46f4-beac-65ed13f31416 | checkpoint | Backfill
5cbcfe4c-5e63-4b75-a9d8-fb820604946c | checkpoint | As-built
f2f0e727-88c4-58b9-bd3f-0278e1b71295 | note | Invert of pipe and Lid Level
3c23f4f0-e59c-456a-839d-7cfea6d45000 | checkpoint | Final Pass: Service works completed, reviewed and approved
a22670ab-cdb3-5eb2-a910-9b3f454d2f4e | note | Attach As-Built
a3fd5376-0685-5329-aad1-ffbe20286a36 | note | FINAL - Pass when work(s) are completed, area clean & tidy