## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
be1fd787-0228-4fbc-91a6-aec2900758ce | checklist | V&B Underground services |  | V&B Underground services | 60baf8cd-58b5-4770-b38a-e2156a1a55ec
e0fbb1ad-5a95-4b02-bdd0-666d00da233c | section | Details
540eda5f-4c08-4b87-bffa-3fec9d9c365c | checkpoint | Location reference attached
f5938893-632b-58f3-825f-06bcc03fb107 | textbox | Description
0e4b34eb-132c-5777-b5da-c1063c647ce2 | dropdown | Service type | Hydraulics,Electrical
7581d4b6-2e2a-4f77-8f78-7a83d545bb70 | checkpoint | Setout/Excavation depth
09233f41-24b4-511c-94d5-010ab02f2357 | textbox | Excavation depth
002a864a-5c03-4f50-b850-5d75e0bc5ad6 | checkpoint | Subgrade testing and results
c262309f-6bb5-54bb-8f35-11dcfe81264a | note | Any soft sopts or undercut & associated remedial
1268241d-9387-4af8-b305-8f456e572bb0 | checkpoint | Granular type
b3669f0a-1ccf-401b-b49d-4f6d65d3c152 | checkpoint | Protection tape, tracerwire, magslab installed
68c471c8-77f0-49f0-bad7-34f681b04b4a | checkpoint | Backfill - GAP20 (150mm thickness)
92e451ae-189b-47db-8c98-1afd41557705 | checkpoint | Structual backfill (ATAP65/GAP65 200mm lifts)
96070988-88f0-4a7c-bc30-21a06e53348c | checkpoint | As-builts
dd021541-9832-4c16-9b33-63bd755d56db | checkpoint | Final Pass: Service works completed, reviewed and approved
e97fa2cb-c323-5308-b78c-fd38310def28 | note | Attach As-Built
b2bcf328-35d0-57f9-b12c-e1f0fa7f856c | note | FINAL - Pass when work(s) are completed, area clean & tidy

## Project Checklist Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
|  | checklist | C - S - Manhole Installation |  | C - S - Manhole Installation | a2be656c-1743-451c-9bfd-2687278ee046
|  | checkpoint | Set-out completed, checked and accurate
|  | checkpoint | Excavation location and depth accurate
|  | checkpoint | Bedding depth and material correct
|  | checkpoint | Manhole installed to specified height and invert level
|  | checkpoint | Manhole risers & steps installed and joints sealed as specified
|  | checkpoint | Manhole benching completed and acceptable
|  | checkpoint | Concrete manhole cover installed and sitting correctly with hole covered if required
|  | checkpoint | Cast Iron lid installed and sitting at correct height
|  | checkpoint | Manhole installation completed as per the specifications
|  | checkpoint | Backfill completed & compacted as per the specifications
|  | checklist | C - S - Pipe Laying - Stormwater |  | C - S - Pipe Laying - Stormwater | 6b222107-7176-4cd0-a774-e759d8caa085
|  | checkpoint | Set-out completed, checked and accurate
|  | checkpoint | Excavation location and depth accurate
|  | checkpoint | Ground conditions checked and acceptable
|  | checkpoint | Bedding depth and material correct
|  | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
|  | checkpoint | Upstream & downstream manhole invert levels and gradient of the pipe line checked and acceptable
|  | checkpoint | Connections to manholes completed and approved
|  | checkpoint | Pipe laying completed as per the specifications
|  | checkpoint | Backfill completed & compacted as per the specifications
|  | checklist | CST - S - Completion Documents |  | CST - S - Completion Documents | 13eafa04-cd61-4142-adf6-423a259d5e96
|  | checkpoint | All relevant Compliance Documentation completed and attached above
DataPoint is missing 'button' values | a0b9dfcf-6c7e-5ddd-8851-5fd5ebea5adc | button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
| 10fa238d-05c3-560d-a891-f7eecd160351 | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
|  | signoff | Request Signoff