## res_1630-P200-SYM-QAC-ITP-0021.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CC0395 - ITP-001 - Bulk Earthworks | itp |  |  |  | Yes | CC0395 - ITP-001 - Bulk Earthworks REV1
section | Lot Conformance.
checkpoint-status | Lot Conformance
select | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | AUTHORITY HOLDPOINT
section | 1.0 Preliminaries
checkpoint-status | 1.1 - Determine lot size
label | Ref docs - Drawings
label | Acceptance criteria - What is the lot size? Prepare a lot map for traceability of the work area
text | Acceptance |  |  | m2
label | Key - S
label | Resp. - PE
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Lot Map
checkpoint-status | 1.2 - Survey set-out
label | Ref docs - Drawings, 3D Models
label | Acceptance criteria - Has the work area been set out for line and level?
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SE
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 1.3 - Excavation material classification
label | Ref docs - 530-SP‐C‐0004 - Earthwoks CL4.8
label | Acceptance criteria - Has the material being excavated been inspected with category agreed upon by Superintendent?
label | Tick category below:
bool | Top Soil
bool | Unsuitable Material
bool | Embankment Fill Material
bool | Rock Material
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - PE
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 1.4 - Fill material classification
label | Ref docs - 530-SP‐C‐0004 - Earthwoks CL6.1
label | Acceptance criteria - Has the material to be used been approved by Client (Material certificates to be provided)?
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - PE
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Material certification Test Report
checkpoint-status | 1.5 - Water management
label | Ref docs - ESCP – SEP
label | Acceptance criteria - Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SS
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
section | 2.0 Bulk Earthworks – Cut
checkpoint-status | 2.1 - Excavations From Cuttings
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.5
label | Acceptance criteria - The cuttings shall be so worked that the best material available, which in the opinion of the APA Representative is suitable material, shall be placed in embankments.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SS
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 2.2 - Batters
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.7
label | Acceptance criteria - The sides of cuttings shall be battered and trimmed to a clean and sharp profile, carried around bends in even curves all to lines and slopes as shown on the drawings provided or directed by the APA Representative.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SS
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 2.2 - Unsuitable Sub‐Grade Material
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.3
label | Acceptance criteria - Unsuitable and sensitive materials such as silt and or organic matter shall be removed from subgrades to the extent directed by the APA Representative.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - PE
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 2.3 - Sub‐Grades Affected By Moisture
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.4
label | Acceptance criteria - When a sub‐grade is unable to support construction equipment, or it is not possible to compact overlying pavement, only because of sub‐grade moisture content, then one or more of the following optional actions may be taken:
label | a) Allow the sub‐grade to dry to a moisture content that will allow compaction and theplacement of pavement material;
label | b) Scarify the sub‐grade to a minimum depth of 150 mm and work as necessary to accelerate drying. Re‐compact as specified when moisture content approaches optimum;
label | c) Excavate the soft material and replace with compacted select fill material in accordance with Section 4.4 above.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp. - PE
label | AllType Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 2.5 - Compaction of Sub‐Grade
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.8
label | Acceptance criteria - The sub‐grade shall be compacted to 98% relative dry density (standard compaction) to a depth of 150 mm. The frequency of testing to confirm this compaction shall be 1 test per 1 000 square metres
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp. - PE
label | AllType Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Bulk Earthworks - Fill
checkpoint-status | 3.1 - Unsuitable Foundation Material Preparation of Natural Surface
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.10
label | Acceptance criteria - Where in the opinion of the APA Representative the material exposed after stripping on which embankments are to be constructed is unsuitable, such material shall be removed and replaced by approved fill material. Any soft or saturated areas shall be surface drained.
button | Acceptance | Yes,No,N/A
label | Key - W
label | Resp. - PE
label | AllType Key - W
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 3.2 - Compaction of material below ground surface under embankments Preparation of Natural Surface
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.10
label | Acceptance criteria - The ground surface shall be compacted to 98% relative dry density (standard compaction) to a depth 150 mm below ground surface. The frequency of testing this compaction shall be at the rate of 1 test per 1 000 m2 of surface area.
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp. - PE
label | AllType Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 3.3 - Fill Material (Site won materials) Preparation of Natural Surface
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.10
label | Acceptance criteria - Only material approved by the APA Representative shall be used from cuttings in the construction of embankments. Generally the material used shall comply with the following:
label | – – – – – – – – – – – – – – – – – – – – –
label | Maximum particle size ¦¦ 50 mm
label | Percentage passing 0.075mm ¦¦ Not greater than 25% by weight
label | Liquid Limit ¦¦ Not greater than 25%
label | Plasticity Index ¦¦ Not greater than 10%
label | – – – – – – – – – – – – – – – – – – – – –
label | ○ All materials used in embankments shall be to the approval of the APA Representative.
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp. - PE
label | AllType Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 3.4 - Fill Material (Imported materials) Preparation of Natural Surface
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.13
label | Acceptance criteria - Where imported fill material is required, it shall be approved by the APA Representative.
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp. - PE
label | AllType Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 3.4 - Construction of Embankments
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.11
label | Acceptance criteria - Filling shall be carried out in uniform horizontal layers of not more than 200 mm of loose material and compacted as specified.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SS
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 3.5 - Trimming of Sub‐Grade
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.12
label | Acceptance criteria - The surface of the sub‐grade shall be compacted, trimmed, profiled and check levelled prior to placing of pavement materials. Design Level Tolerance +0 mm / ‐30 mm
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SS
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Survey Report
checkpoint-status | 3.6 - Compaction
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.12
label | Acceptance criteria - Earthworks to fill for roadway embankment shall be compacted to 100% relative dry density (standard compaction) for the first 300 mm of embankment depth immediately below the required pavement. All other earthworks to fill as shown on drawings provided or specified shall be compacted to 98% relative dry density (standard compaction).
button | Acceptance | Yes,No,N/A
label | Key - H
label | Resp. - PE
label | AllType Key - H
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | Test reports
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Conformance check
checkpoint-status | 4.1 - Width and alignment
label | Ref docs - Drawings
label | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SE
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) - Checklist
checkpoint-status | 4.2 - Subgrade level and shape
label | Ref docs - 530-SP‐C‐0003 – Bulk Earthwoks CL4.12
label | Acceptance criteria - Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
label | ○ Design Level Tolerance +0 mm / ‐30 mm
label | ○ Shape Tolerance of 25 mm maximum deviation from a 3 m straight edge laid in any direction.
button | Acceptance | Yes,No,N/A
label | Key - S
label | Resp. - SE
label | AllType Key - S
label | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
bool | As built report