## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-086-AX-LOT-XXX - Desc | itp |  |  |  |  | ITP 0086 - WELDING CARBON REINFORCEMENT
section | Lot Information
checkpoint | 1.0 Lot Information
textbox | Lot Created On
textbox | Lot Opened On
textbox | Work Commenced On
dropdown | Lot Type | CIL - Civil Lot
textbox | From and To Chainage
dropdown | Construction Element | SITE - Site General
dropdown | Activity | OTH - Other
dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
textbox | Engineer Responsible
textbox | comments
section | 1 - Preliminaries - Permits
checkpoint | 1.1 - Induction
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
note | - - - - - - - - -
note | Reference Documents: PMP Inductions Register
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of conformity: Site induction signed.
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.2 - Check that current revision drawings are being used
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
note | - - - - - - - - -
note | Reference Documents: Project Drawings / Drawing Register
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of conformity: Latest Revision Drawings
note | - - - - - - - - -
note | AP
note | - - - - - - - - -
note | Responsibility: Site Engineer / Site Foreman
checkpoint | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
note | Frequency: Prior to commencing
note | - - - - - - - - -
note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
note | - - - - - - - - -
note | Reference Documents:
note | Project Specs. Cl.1125.02 Cl.1125.07
note | Health and Safety Co-Ordination Plan
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: SWMS(s) signed
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
note | Responsibility: Site Engineer
section | 2 - Preliminary Works
checkpoint | 2.1 - Welding Procedure Qualification
note | Frequency: Prior to commencing
note | - - - - - - - - -
note | Acceptance Criteria:
note | Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding procedure has been qualified and reviewed by the Superintendent.
note | Submit the following documents:
note | • Qualified welding procedure
note | • Qualified welders record
note | • Welding supervisor qualifications
note | • Welding Test Plan
note | • Welding test certificates
note | - - - - - - - - -
note | Reference Documents: VicRoads CL611.14 AS1554.3 Section 4
note | - - - - - - - - -
note | Inspection / Test Method: Document Review
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
note | Responsibility: Site Engineer & Superintendent
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Construction Activities
checkpoint | 3.1 - Surface Preparation
note | Frequency: Prior to Welding
note | - - - - - - - - -
note | Acceptance Criteria: Surfaces to be welded are free of corrosion & paint or any other foreign material that may effect the quality of the weld
note | - - - - - - - - -
note | Reference Documents: AS1554.3 CL5.1
note | - - - - - - - - -
note | Inspection / Test Method: Onsite Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.2 - Assembly
note | Frequency: Ongoing
note | - - - - - - - - -
note | Acceptance Criteria:
note | Where reinforcing steel is to be assembled prior to welding, it shall
note | a) Bars are to be in the correct location
note | b) Before welding a butt splice, bars shall be not out of alignment by more than 0.1 times the diameter up to a max misalignment of 3mm
note | c) Parts to be spliced shall be into as close a contact as practical but not more than 0.25 times the diameter of the smaller bar but not more than 3mm
note | d) Tack weld, shall be subject to the same initial treatment (preheating). Tack weld that will be consumed in the final weld shall be cleaned. Defective tac weld shall be removed before final weld
note | - - - - - - - - -
note | Reference Documents: AS1554.3 CL5.2
note | - - - - - - - - -
note | Inspection / Test Method: Onsite Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.3 - Preheating
note | Frequency: Ongoing
note | - - - - - - - - -
note | Acceptance Criteria:
note | Please refer to table 5.3 to determine if preheating is required
note | Grade 500N, bar size less than 40mm pre heating is NOT required
note | - - - - - - - - -
note | Reference Documents: AS1554.3 CL5.3 Table 5.3
note | - - - - - - - - -
note | Inspection / Test Method: Onsite Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | 3.4 - Weather Conditions
note | Frequency: Ongoing
note | - - - - - - - - -
note | Acceptance Criteria:
note | Welds shall not happen when:
note | a) Temperature of the metal is colder than 0 degrees
note | b) Surfaces are wet. If surface can be dried pre heating is required to 20 degrees
note | c) During periods of high winds
note | - - - - - - - - -
note | Reference Documents: AS1554.3 CL5.5
note | - - - - - - - - -
note | Inspection / Test Method: Onsite Inspection
note | - - - - - - - - -
note | Record of conformity: Signed ITP
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
section | 4 - Testing
checkpoint | 4.1 - Inspection and Quality of Welds
note | Frequency: As per table 611.141
note | - - - - - - - - -
note | Acceptance Criteria: Testing shall not be less than what is shown in Table 611.141
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Table 611.141 Inspection and Quality of Direct Butt Splice Welds
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Inspection Process ¦¦ Minimum extent of inspection (% of welds, as no.) ¦¦ Detail of inspection of direct butt splice welds ¦¦ Quality requirements
note | Visual inspection ¦¦ 100 ¦¦ Each full weld circumference ¦¦ AS/NSZ 1554.3, Table 6.2
note | Non-destructive internal inspection by Radiography ¦¦ First two inspection lots :: 20 ¦¦ with a minimum of 12 bars inspected per lot, and at least 6 of these 12 bars to be examined at two directions, at least 60 degrees apart ¦¦ AS/NZS 1554.1, Table 6.2.1
note | Non-destructive internal inspection by Radiography ¦¦ Subsequent inspection lots after first two :: 10 ¦¦ If more than one weld in an inspection lot does not comply with the quality requirements, revert to extent of inpsection as for the first two inspection lots ¦¦ AS/NZS 1554.1, Table 6.2.1
note | Non-destructive surface inspection by Magnetic particle, or Liquid penetrant ¦¦ 5 ¦¦ Each full weld circumference ¦¦ AS/NZS 1554.3, Table 6.2
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | - - - - - - - - -
note | Reference Documents: VicRoads 611.14 AS1554.3
note | - - - - - - - - -
note | Inspection / Test Method: Test Reports
note | - - - - - - - - -
note | Record of conformity: Signed ITP, Test Reports
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
note | Responsibility: Site Engineer
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
textbox | Work Completed On
checkpoint | Lot Verification.
dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
textbox | Other:
dropdown | Lot Status | OUTSTANDING, CLOSED
textbox | Lot Closed On
textbox | comments