## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Subbie Rough-in Progression Checklist |  |  |  |  | Yes | Subbie Rough-in Progression Checklist | 109a3ff5-4162-48bc-9a24-aae4f937bffc
checkpoint-status |  |  | checkpoint | All work in Zone completed
label | b88dc3f8-1edb-51cc-8245-ada8b77a862e |  | note | Pass once all work complete
checkpoint-status |  |  | checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint-status |  |  | checkpoint | Rough-In completed to specification/drawings & Area left clean/tidy
label | 1ae44209-1c61-58ab-a916-d6cecd303e02 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Filters Fit-Off Checklist |  |  |  |  | Yes | Filters Fit-Off Checklist | 13fadb8a-a12d-4e63-8335-201af1d8cd94
checkpoint-status |  |  | checkpoint | Plenums clean of dirt & debris
checkpoint-status |  |  | checkpoint | Filters installed correctly as per schedule (Any Issues Comment below)
checklist-flat |  |  | checklist | Equipment Checklist |  |  |  |  | Yes | Equipment Checklist | 1b082861-caa5-4d38-bc47-6a411378262e
checkpoint-status |  |  | checkpoint | Correct unit installed as per latest drawing & schedule
button | fe01e783-b3e7-5252-9dab-c9ae43eade63 |  | button | Correctly supported with anti vibration as required | Yes, No
checkpoint-status |  |  | checkpoint | Flexible connections installed as required
checkpoint-status |  |  | checkpoint | Access available & access panels marked on drawing
label | e50b2b08-8393-5771-96a7-8cdade328957 |  | note | Marked up drawing attached below if applicable
button | 45f910c1-d95a-57df-a4e0-20116b9bd27e |  | button | Correctly labelled as per latest drawing | Yes, No
checkpoint-status |  |  | checkpoint | Seismic bracing to requirements
checkpoint-status |  |  | checkpoint | Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist-flat |  |  | checklist | Gripple Inspection Upload Checklist |  |  |  |  | Yes | Gripple Inspection Upload Checklist | 1bc5841e-4c36-4912-8736-b5c8ced2aab5
checkpoint-status |  |  | checkpoint | Gripple Seismic inspection completed
label | 4ad238dd-41b0-5b62-a3b9-314188a7589e |  | note | Attach report as applicable below
button | 042a4565-0cbd-55ff-8b72-0071c9d9dbed |  | button | Gripple inspector signature added below as applicable | Yes, No, N/A
holdpoint |  |  | signoff | If required - Click to request Gripple sign-off
checklist-flat |  |  | checklist | Subbie Testing Progression Checklist |  |  |  |  | Yes | Subbie Testing Progression Checklist | 2f05e8eb-b43c-4e56-b1f9-77a06c0de3ac
checkpoint-status |  |  | checkpoint | All work in Zone completed
label | 26b01a8a-58d0-5b2a-b5e2-ce1e87f12e55 |  | note | Pass once all work complete
checkpoint-status |  |  | checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint-status |  |  | checkpoint | Testing completed to specification/drawings & Area left clean/tidy
label | 800c0e80-9449-581c-937b-b15304745ebf |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | Flex Checklist |  |  |  |  | Yes | Flex Checklist | 3b35f532-fedb-4cab-abd9-34f3af72130a
checkpoint-status |  |  | checkpoint | Supported with duct saddle only, not from other trades materials
button | 7960c631-8670-5fcf-8942-4fd38b50628d |  | button | Not sagging on ceiling | Yes, No
button | 3dd23186-f127-563a-b74e-e944998a8177 |  | button | Dampers fully open | Yes, No
checkpoint-status |  |  | checkpoint | Correct as per latest drawing
checkpoint-status |  |  | checkpoint | Flex Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist-flat |  |  | checklist | Ductwork Checklist |  |  |  |  | Yes | Ductwork Checklist (2) | 5891394c-2b48-46cc-8152-0f1c9f179762
checkpoint-status |  |  | checkpoint | Ductwork delivered, protected & clean - i.e plastic wrapped
checkpoint-status |  |  | checkpoint | Marked off on latest drawing
button | aad637bb-89e7-5dc5-8f1f-c13b78571037 |  | button | Installed as per latest drawing | Yes, No
button | 13453be0-f522-56bc-8b5e-d1cfc66c4963 |  | button | Correct height as per drawing | Yes, No
button | 27cee1a9-3d80-553c-891a-787ec0020e80 |  | button | Duct flanges firmly bolted & sealed where required | Yes, No
button | e9885fe5-d5b8-596a-b0cc-30cea07e0642 |  | button | Cleats installed as required | Yes, No
button | fc441e6b-dae1-574e-a9ab-bc7d6a98fe48 |  | button | Insulated as required/ damage free | Yes, No
checkpoint-status |  |  | checkpoint | Supported to requirements
button | 4818b297-2c20-5160-b291-216885f8d42e |  | button | Correct hanger spacing | Yes, No
button | 710acb70-ebd3-52b5-9380-cecd010377d8 |  | button | Correct rod length | Yes, No
checkpoint-status |  |  | checkpoint | Volume dampers installed as per drawing
checkpoint-status |  |  | checkpoint | Smoke dampers installed as per drawing
button | 009aa372-bd4c-5fb6-83d9-ab6d668b4037 |  | button | Dampers open & free moving | Yes, No
checkpoint-status |  |  | checkpoint | Damage free post-install & Area left clean/tidy (Any Issues comment below)
checklist-flat |  |  | checklist | Drain Fit-Off Testing Checklist |  |  |  |  | Yes | Drain Fit-Off Testing Checklist | 5b83d350-bb40-4d43-828d-aee2323a781c
checkpoint-status |  |  | checkpoint | Drain has been terminated into tundish
checkpoint-status |  |  | checkpoint | Drain has had final test, traps are full
checklist-flat |  |  | checklist | Grilles Fit-Off Checklist |  |  |  |  | Yes | Grilles Fit-Off Checklist | 6bf0b047-11fd-47d8-a37f-77d8531c5844
checkpoint-status |  |  | checkpoint | Grilles, Registers, Diffusers fit off as per latest drawing/ schedule
button | e9d890ae-32ac-5e28-bce9-3c4652599059 |  | button | Free of any damage | Yes, No
button | ad1fa97a-b35b-5f09-9df4-311159ea13fd |  | button | Grilles installed flush to ceiling | Yes, No
button | 2ba165bb-2ce2-51a8-9de2-453f104dd565 |  | button | Boxes sealed to grill | Yes, No
button | 9dbec553-6ff4-51e2-ba88-020639421f58 |  | button | Grille finish/colour as per latest spec | Yes, No
checkpoint-status |  |  | checkpoint | Grilles Fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist-flat |  |  | checklist | Subbie Fit-off Progression Checklist |  |  |  |  | Yes | Subbie Fit-off Progression Checklist | 6d2b9223-a376-470c-80cf-0b01c04ebdaf
checkpoint-status |  |  | checkpoint | All work in Zone completed
label | 2d5db6d3-7098-5516-80fc-6c0628ee48f5 |  | note | Pass once all work complete
checkpoint-status |  |  | checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint-status |  |  | checkpoint | Fit-Off completed to specification/drawings & Area left clean/tidy
label | 5fa83d87-7f25-592e-b896-d44974e394c2 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat |  |  | checklist | As Builts Checklist |  |  |  |  | Yes | As Builts Checklist | 6ff4a56a-4d63-41c0-8a34-86880dd4f241
checkpoint-status |  |  | checkpoint | Update As-Built's of any know changes (Attach if applicable)
checklist-flat |  |  | checklist | Penetration Details |  |  |  |  | Yes | SYS - Penetration Details (old version) | 7173648c-ed0d-494e-9833-cc5671200070
checkpoint-status |  |  | checkpoint | Studio wall penetration sealing to requirements
checklist-flat |  |  | checklist | Cushion Boxes Checklist |  |  |  |  | Yes | Cushion Boxes Checklist | 8b6576b3-e256-43a1-9d6f-647bdaacb88a
checkpoint-status |  |  | checkpoint | Correct size as per latest schedule
checkpoint-status |  |  | checkpoint | Secured & sealed
button | 1a51a707-77e0-5139-9410-8341495a22c9 |  | button | Flexible duct connected neat & secure | Yes, No
checkpoint-status |  |  | checkpoint | Cushion box damper installed & open
checkpoint-status |  |  | checkpoint | Diffuser cut out marked on ceiling (Attach Photos if applicable)
checkpoint-status |  |  | checkpoint | Cushion Box Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist-flat |  |  | checklist | Pipework Checklist |  |  |  |  | Yes | Pipework Checklist | 9ddba090-45b9-4336-b3ba-d10fb7009a23
checkpoint-status |  |  | checkpoint | Installed as per latest drawing
checkpoint-status |  |  | checkpoint | Correct heights i.e. underside as per drawings
checkpoint-status |  |  | checkpoint | Pipe fittings complete
checkpoint-status |  |  | checkpoint | Clips complete
checkpoint-status |  |  | checkpoint | Insulation complete
checkpoint-status |  |  | checkpoint | Air bleed complete (installed at all floor high points)
checkpoint-status |  |  | checkpoint | Drain points complete
checkpoint-status |  |  | checkpoint | Correct flow and return checked
checkpoint-status |  |  | checkpoint | Access to valve sets checked'
checkpoint-status |  |  | checkpoint | No other services suspended from pipe work
checkpoint-status |  |  | checkpoint | Welds checked
checkpoint-status |  |  | checkpoint | Damage free
checkpoint-status |  |  | checkpoint | Piping cleaned and flushed
checkpoint-status |  |  | checkpoint | Pipe tested and recorded as per Pipe Testing ITP
checkpoint-status |  |  | checkpoint | Initial pipe pressure test (attach photo below)
checkpoint-status |  |  | checkpoint | 24hr pipe pressure test (attach photo below)
checklist-flat |  |  | checklist | Ductwork Checklist |  |  |  |  | Yes | Ductwork Checklist | a34a3ae3-f05c-4484-a47b-1a2fb4276128
checkpoint-status |  |  | checkpoint | Ductwork delivered, protected & clean - i.e plastic wrapped
checkpoint-status |  |  | checkpoint | Marked off on latest drawing
button | 5bded124-845b-5512-b32c-a4530e62e97f |  | button | Installed as per latest drawing | Yes, No
button | f28d6dba-d3a0-5f2e-812e-c10f3fcca61b |  | button | Correct height as per drawing | Yes, No
button | 835e68c7-eb54-5163-9020-795913c0771c |  | button | Duct flanges firmly bolted & sealed where required | Yes, No
button | c09183eb-6198-5425-9ec8-14fdb1f045cb |  | button | Cleats installed as required | Yes, No
button | f651eec6-831a-5d3f-b98d-9d64cfb62ff0 |  | button | Insulated as required/ damage free | Yes, No
checkpoint-status |  |  | checkpoint | Supported to requirements
button | 8e8be4f6-145c-5825-95a5-63e5db39f417 |  | button | Correct hanger spacing | Yes, No
button | c1b42b1e-3261-5e3e-932d-1969ed48b549 |  | button | Correct rod length | Yes, No
checkpoint-status |  |  | checkpoint | Volume dampers installed as per drawing
checkpoint-status |  |  | checkpoint | Motorised dampers installed as per drawing
button | 92d0dd5f-b15a-5acc-ab33-ce0b4df65bf0 |  | button | Dampers open & free moving | Yes, No
checkpoint-status |  |  | checkpoint | Acoustic penetration sealing to requirements
checkpoint-status |  |  | checkpoint | Acoustic duct mounts to requirements
checkpoint-status |  |  | checkpoint | Seismic bracing to requirements
checkpoint-status |  |  | checkpoint | Damage free post-install & Area left clean/tidy (Any Issues comment below)
checklist-flat |  |  | checklist | Access Panel Markup Checklist |  |  |  |  | Yes | Access Panel Markup Checklist | b70c9894-4e73-4452-b9d8-1b52c466c16a
checkpoint-status |  |  | checkpoint | Marked up completed & attached
button | bd339e67-eeba-5d7c-8596-379e43909138 |  | button | Submitted to draftsman | Yes, No
checklist-sectioned |  |  | checklist | Fit-Off Checklist (Full) |  |  |  |  | Yes | Fit-Off Checklist (Full) | c8e3abdf-3417-435a-8b1e-9177bc1487ef
checkpoint-group |  |  | section | Drain Fit-Off Testing
checkpoint-status |  |  | checkpoint | Drain has been terminated into tundish
checkpoint-status |  |  | checkpoint | Drain has had final test, traps are full
checkpoint-group |  |  | section | Grilles Fit-Off
checkpoint-status |  |  | checkpoint | Grilles, Registers, Diffusers fit off as per latest drawing/ schedule
button | e418f326-fd77-56e7-9da3-d4acdb826751 |  | button | Free of any damage | Yes, No
button | 8f4db4af-49b4-508d-8aaa-3bcf9ee2b885 |  | button | Grilles installed flush to ceiling | Yes, No
button | 12830ca9-bdea-523f-9e7e-636f120d5645 |  | button | Boxes sealed to grill | Yes, No
button | 55727a2b-63e1-5a33-934e-0362620de567 |  | button | Grille finish/colour as per latest spec | Yes, No
checkpoint-status |  |  | checkpoint | Grilles Fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checkpoint-group |  |  | section | Filters Fit-Off
checkpoint-status |  |  | checkpoint | Plenums clean of dirt & debris
checkpoint-status |  |  | checkpoint | Filters installed correctly as per schedule (Any Issues Comment below)
checklist-flat |  |  | checklist | Testing Checklist |  |  |  |  | Yes | Testing Checklist | d1788a8a-d9be-45fb-b042-7f78246917a6
checkpoint-status |  |  | checkpoint | Test passed with air/water
checkpoint-status |  |  | checkpoint | Test sighted by builder & signed off (Click to Add Signature below - If applicable)
button | da418233-4a22-5ef6-8841-71f0dfa29458 |  | button | Air bled from system | Yes, No
checklist-flat |  |  | checklist | Commissioning Checklist |  |  |  |  | Yes | Commissioning Checklist | debb5fbf-0a4f-4b2a-a9a5-e224f0e94cb2
checkpoint-status |  |  | checkpoint | Commissioning completed (Pass once below completed)
button | 14e154d5-7d81-59be-8c1f-44f06c73b53e |  | button | Any issues during commissioning | Yes, No
text | 10f2878c-9b5a-54f2-a07d-363d5b1fb624 |  | textbox | If Yes, please specify
boolean | f5544c25-8b1b-5bea-9d72-38c9c0a442b2 |  | tickbox | Any commissioning reports/results attached (If applicable)
checklist-flat |  |  | checklist | Drains Checklist |  |  |  |  | Yes | Drains Checklist | e094bfb4-3bd3-4227-bb0a-f2a692de34c3
checkpoint-status |  |  | checkpoint | Drains installed with fall to tundish
button | f8bbff5b-441c-586c-b713-cdac5bbdefdb |  | button | Pipes insulated as required | Yes, No
button | 65081be0-c166-5a3a-bd50-7f80d083d3e1 |  | button | Tundish installed | Yes, No
checkpoint-status |  |  | checkpoint | Drain has been tested (Test results attached if applicable)
checkpoint-status |  |  | checkpoint | Drain(s) Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checkpoint-status |  |  | checkpoint | Drain has had final test, traps are full
checklist-flat |  |  | checklist | Refrigeration Pipe Checklist |  |  |  |  | Yes | Refrigeration Pipe Checklist | f93b2e0c-dfd7-4cb7-ab63-2254fc57ac71
checkpoint-status |  |  | checkpoint | Correct IDU & ODU installed as per latest drawing & schedule
checkpoint-status |  |  | checkpoint | Installed as per latest drawings
checkpoint-status |  |  | checkpoint | No other services suspended from pipe work (Attach Photos below)
checkpoint-status |  |  | checkpoint | Installation damage free (Any Issues comment/attach Photos below)
button | c72dd8da-0ddd-5738-9771-82fdab1a3a62 |  | button | correct hanger spacing | Yes, No
checkpoint-status |  |  | checkpoint | Pipe labelled after insulation
boolean | 35754fdf-e66f-5a8d-9793-929b36b4c844 |  | tickbox | Photo of Label attached
checkpoint-status |  |  | checkpoint | Seismic bracing to requirements
checkpoint-status |  |  | checkpoint | Pipe Mains Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checkpoint-status |  |  | checkpoint | Pipework system pressure tested