## Table 1
|  |  | Inspection and Test Plan - Crushed Rock Classed | [7 empty] | Document # ITP-005
Client: | DTP |  | Construction Process: | Crushed Rock Class 4 |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Stud Road/ Mcfees Road | [5 empty] | Name: | Ruby Lewis | Name: Cameron Beattie |  |  | Name: | Cameron Beattie
Project: |  |  | Specifications: | VicRoads Specifications Section 173, 204, 304 & 812
Contract No: DOT38025 |  |  | Structure / Component: | Earthworks/Civil |  |  |  | Signed : |  |  | Signed :
|  |  | Location: |  |  | Signed :
[6 empty] | 2025-05-23 |  | Date : | 2025-05-23 |  | Date : | 2025-05-23
Lot No: |  |  | Lot Title: |  | Location: From ( |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Superintendent | Fulton Hogan | FH's Sub- contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the Project site | Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken |  | Prior to commencing | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP | Site Engineer, Site Foreman & Superintendent
1.3 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A
1.5 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.6 | Crushed Rock Mix design |  | Prior to Commencing Work | Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175. | VicRoads Spec. Cl.812.09 | Document Review | Mix Design VicRoads Approval | HP* | Site Engineer | N/A |  | N/A
2 | Placing Fill
2.1 | Transverse Joints |  | Check prior to placing material | Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres | VicRoads Spec. Cl.304.07 (a) Cl.304.07 (c) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.2 | Longitudinal Joints |  | Check prior to placing material | Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane. | VicRoads Spec. Cl.304.07 (a) Cl.304.07 (d) Cl.304.07 (e) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.3 | Lot Size |  | Check prior to placing material | A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser. | VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.4 | Proof Roll |  | After placing material | Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent | VicRoads Spec. Cl.304.08(b)(iv) Cl. 173 | Site Inspection | Signed ITP | WP | Site Engineer & Superintendent |  |  | N/A
3 | Testing Requirements
3.1 | Determine Testing Scale & Initial testing frequency |  | Prior to Testing | Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111. | VicRoads Spec. Table 204.161 VicRoads Spec. Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111 | Document Review/ Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.2 | Modified Compactive Effort |  | As per 3.1 | Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale A) 6 lot test Initial FrequencyTest No. - > 97.0% | VicRoads Spec. Table 304.081 | Site Inspection | Test Records | TP | Site Engineer | N/A |  | N/A
3.3 | Permeability Testing |  | As per 3.1 | Class 4 Crushed rock max 5x10^-9 m/sec. Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051 and allows FH to use 9x10-9 m/s Max permeability | Project Spec. Cl.3040.05(a) Table 3040.051 RFI-0085.01 | Site Inspection | Test Records from Supplier | TP | Site Engineer | N/A |  | N/A
3.4 | Survey Level |  | At completion | Scale A: - Minimum number of measurements per lot: 80 For Upper - Upper Subbase: Mean + 4mm to - 8mm with a maximum Standard Deviation of 8mm - Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm. - Base: Mean ± 5 with a maximum Standard Deviation of 8mm. | VicRoads Spec. Table 304.061 Table 304.062 | Site Inspection | Test Records | TP | Site Engineer | N/A |  | N/A
Notes
Final Inspection The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: | [7 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP Survey conformance point A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent