## Table 1
|  |  | Inspection and Test Plan - Subgrade Preparation | [7 empty] | Document # ITP-006
Client: Project: Contract No: | DTP Stud Road/ Mcfees Road DOT38025 |  | Construction Process: Specifications: Structure / Component: Location: | Subgrade Preparation VicRoads Specification Sections 204, 205 and 173 Earthworks/Civil |  | Prepared by: Name: Signed : | Ruby Lewis | Reviewed by : Name: Cameron Beattie Signed : |  |  | Approv Name: Signed | ed : | by : | Cameron Beattie
2025-05-23 | [7 empty] | Date : 23/05/2025 |  |  | Date : |  |  | 2025-05-23
Lot No: |  |  |  |  | Location: From ( | ) to ( | ) | Lot Size/ Quantity:
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Superintendent | Fulton Hogan |  |  | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the Project site | Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | N/A |  |  |  | N/A
1.2 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  |  |  | N/A
1.3 | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing | All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A |  |  |  | N/A
1.4 | Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken |  | Prior to commencing | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | PSP, CEMP, TMP, JSEA, SWMS, | Document Review | SWMS(s) signed | IP | Site Engineer & Superintendent | N/A |  |  |  | N/A
1.5 | Excavation Permit issued |  | Prior to commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document Review | Excavation Permit No. | IP | Site Engineer & Superintendent | N/A |  |  |  | N/A
2 | Construction Works
2.1 | Survey set-out |  | Prior to Commencing | Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. | Project Spec. Cl.1190.07 Latest IFC Drawings | Site Inspection | Compliance with latest IFC drawings Survey records & pegs on the ground | SCP | Site Engineer & Surveyor | N/A |  |  |  | N/A
2.2 | Unsuitable Material |  | During Excavation | Where unsuitable material is encountered, actions shall be: a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent | IFC Drawings | Visual Inspection | This ITP Signed off | IP | Project Engineer | N/A |  |  |  | N/A
2.3 | Material Category |  | Prior to Commencing | Prior excavation, Superintendent and Fulton Hogan responsible shall inspect each type of material encountered and, subject to verification by laboratory testing, agree on category of material in accordance with VicRoads Spec Section 204.04 | VicRoads Spec. Cl. 204.04 Cl. 204.06(c) | Document Review | Superintendent agreement Signed ITP | HP | Site Engineer & Superintendent |  |  |  |  | N/A
2.4 | Trimming and level conformity |  | Each Lot (one day's production) prior to Commencing | Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping not differ by more than 5 mm above or 15 mm below the specified level. Level at any point of sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns. Water shall not pond at any point. The mean and standard deviation of the departures from the theoretical surface level within each lot shall meet the requirements of Table 204.031. | VicRoads Spec. Cl. 204.03(f) Cl. 204.03(g) Table 204.031 | Survey Report | Survey Record | SCP | Site Engineer & Surveyor | N/A |  |  |  | N/A
2.5 | Acceptance of Rock Subgrade (when applicable) |  | Prior construction of the regulating layer | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review. | VicRoads Spec. Cl. 204.06(f) | Site Inspection/ Document Review | Superintendent acceptance Signed ITP | HP | Site Engineer & Superintendent |  |  |  |  | N/A
2.6 | Cut to Fill Zones |  | Each Lot (one day's production) prior to Commencing | All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material. | VicRoads Spec. Cl. 204.06(g) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  |  |  | N/A
3 | Testing for Compaction and Material Properties
3.1 | Proof Rolling |  | Each Lot (one day's production), prior to Commencing Fill | Test rolling of all fill layers and subgrade shall be in accordance with Section 173 and 204 of the VicRoads Standard Specification. Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling. | VicRoads Spec. Cl. 173.03 Cl. 204.12 | Site Inspection | Proof Rolling Register signed. | WP | Site Engineer & Superintendent |  |  |  |  | N/A
3.2 | Testing for Compaction and Material Properties |  | Testing as per table 204.141 of VicRoads Spec. for Roadworks and Bridgeworks | Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level= minimum compaction 99% MDD. Type B material 400mm below the top of Type B material and Top 150mm of cuts= minimum compaction 97% MDD. | VicRoads Spec. Cl. 173.04 Cl. 204.13 Cl. 204.14 Table 204.131 Table 204.141 | Site Inspection | Test Results | TP | Site Engineer | N/A |  |  |  | N/A
Notes
Final Inspection The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: | [7 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent