## Table 1
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [10 empty] | ITP-012
[14 empty] | Revision : 1 | 2025-05-23
Client: |  | DTP |  |  | Construction Process: |  |  | Prepared by: |  |  | Reviewed by : |  |  | Approved by :
Project: |  | Stud Road/ Mcfees Road |  |  | General Concrete Paving |  |  | Name: |  | Ruby Lewis | Name: | Cameron Beattie |  | Name: Cameron Beattie Signed : Date : 23/05/2025
Contract No: |  | DOT38025 |  |  | Specifications: VicRoads Specification Section 703
[5 empty] | Structure / Component: Concrete Pavements |  |  | Signed : |  |  | Signed :
[5 empty] | Location: |  |  | 2025-05-23 |  |  | Date : | 2025-05-23
Lot No: Lot Details: Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail | [7 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency |  | Acceptance Criteria |  | Reference Documents | Inspection / Test Method |  | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub- contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity |  | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision |  | Drawings and drawing registers | Visual inspection |  | ITP Signed | HP* | Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity |  | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP |  | QMP, TMP, SWMS, WP | Visual Inspection |  | ITP Signed | HP* | Engineer/ Site Foreman | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to start |  | Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works. |  | 703.17 | Verify |  | This ITP Signed | HP | Engineer/ Superintendent |  |  | N/A
2.2 | Excavation Permit |  | Each lot |  | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation |  | Excavation permit | Verify |  | ITP Signed | HP* | Engineer | N/A |  | N/A
2.3 | Excavation |  | Each Lot |  | Excavation completed to required depth to allow placement of the bedding layer |  | 703.2 | Verify |  | ITP Signed | IP | Engineer | N/A |  | N/A
2.4 | Bedding |  | Each Lot |  | All bedding material used shall be as follows: - 75mm thick layer of 20mm Class 2 crushed rock bedding for median infill - Bedding trimmed, moistened, and compacted as per Section 304 |  | 703.21 Drawings | Visual Inspection |  | ITP Signed | IP | Site Foreman | N/A |  | N/A
2.5 | Formwork |  | Each Lot |  | Formwork shall comply with the requirements of AS 3610 |  | 703.12 AS 3610 | Verify |  | ITP Signed | IP | Engineer | N/A |  | N/A
2.6 | Reinforcement |  | Each Lot |  | Reinforment used shall consist of SL62 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings). Reinforcement must comply with the requirements of AS/NZS 4671. |  | 703.13 | Verify |  | ITP Signed | IP | Engineer | N/A |  | N/A
2.7 | Concrete Quality |  | Each Batch |  | Check the deleivery of the batch is an approved concrete mix as ordered. VR330/32. Check for the time from plant to site,Check for the water qty added. |  | 703.13 | Visual Inspection |  | ITP Signed | IP | Engineer | N/A |  | N/A
2.8 | Concrete Placement |  | Each Lot |  | Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings. Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used. - N32 for concrete infill |  | 703.05(a) 703.08 | Visual Inspection |  | ITP Signed | IP | Engineer/ Site Foreman | N/A |  | N/A
2.9 | Record location of each batch |  | Each concrete pour |  | Batch location recorded on Load Batch Traceability Checklist |  |  | Checklist |  | This ITP Signed | IP | Engineer | N/A |  | N/A
2.1 | Surface Finish |  | Each Lot |  | Footpaths and other Surfacing shall be compelted with a wooden float. |  | 703.25 | Visual Inspection |  | This ITP Signed | IP | Engineer | N/A |  | N/A
2.11 | Pram Crossings |  | Each Lot |  | Ensure that pram crossings are constructed in accordance with requirements for access and mobility. |  | Booroondara Standard drawings | Verify |  | This ITP Signed | IP | Engineer/ Site Foreman | N/A |  | N/A
2.12 | Joints |  | Each Joint |  | Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board. Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material. |  | 703.26 | Visual Inspection |  | This ITP Signed | IP | Site Engineer/ Site Foreman | N/A |  | N/A
2.13 | Protection of concrete |  | Each Lot |  | All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause. Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days. |  | 703.27 | Verify |  | This ITP Signed | IP | Site Foreman | N/A |  | N/A
3 | Completion
3.1 | Carry out sampling of concrete - strength and consistency |  | Lot |  | Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379. The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379 |  | 703.11 | Checklist |  | ITP Signed/Test Records | TP | Engineer | N/A |  | N/A
3.2 | Tolerances |  | Each Lot |  | Where matching in with existing surface levels, the new surface shall be within ± 5mm existing. Section dimensions shall be constructed within the following tolerances: - 5mm and 15mm for width; or - ±3mm for dimensions less than 25mm. |  | 703.15 Drawings | Visual Inspection |  | This ITP Signed | IP | Engineer/ Site Foreman | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  |  |  | Position: |  | Signature: |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  |  |  | IP | Inspection point |  |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  |  |  | TP | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  |  |  | SCP | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent