## Table 1
[6 empty] | Inspection and Test Plan - Control and Supervision of the Works | [11 empty] | Document # ITP-015
[18 empty] | Revision : 1 | 2024-02-15
Client: |  |  |  | DTP |  |  | Construction Process: |  |  |  | Prepared by: |  |  | Reviewed by : |  |  |  | Approved by :
Project: |  |  |  | Stud Road/ Mcfees Road |  |  | Kerb and Channel |  |  |  | Name: |  | Ruby Lewis | Name: |  | Cameron Beattie |  | Name: Cameron Beattie Signed : Date : 23/05/2025
Contract No: |  |  |  | DOT38025 |  |  | Specifications: VicRoads Standard Specification – Section 703
[7 empty] | Structure / Component: Drainage |  |  |  | Signed : |  |  | Signed :
[7 empty] | Location: |  |  |  | 2025-05-23 |  |  | Date : |  | 2025-05-23
Lot No: Lot Details: Lot Size/ Quantity:
Item |  | Task/Activity Description |  |  |  | Inspection / Controls and Verification Detail | [7 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility | Checked by:
No. | [5 empty] | Frequency | Acceptance Criteria |  | Reference Documents |  | Inspection / Test Method |  | Record of conformity |  |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub- contractor | Date
1 |  | Preliminary Works
1.1 |  | Check for correct documentation |  |  |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision |  | Drawings and drawing registers |  | Visual inspection |  | ITP Signed | HP* |  | Project Engineer/ Site Foreman | N/A |  | N/A
1.2 |  | Implementation of all measures and controls |  |  |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP |  | QMP, TMP, JSEA, SWMS, WP |  | Visual inspection |  | ITP Signed | HP* |  | Project Engineer/ Site Foreman | N/A |  | N/A
2 |  | Construction Works
2.1 |  | Setting Out |  |  |  | Prior to start | Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works. |  | 703.17 |  | Verify |  | ITP Signed | HP |  | Project Engineer/ Superintendent
2.2 |  | Temporary Drainage Provisions |  |  |  | If Required | If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. |  | Cl 703.18 |  | Visual inspection |  | ITP Signed | WP |  | Project Engineer/ Site Foreman | N/A |  | N/A
2.3 |  | Bedding |  |  |  | Each lot | All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted. |  | Cl 703.21 |  | Visual inspection |  | ITP Signed | WP |  | Project Engineer/ Superintendent | N/A
2.4 |  | Pre-concrete check |  |  |  | Each lot | Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Concrete extrusion machines have minimum cement content of 320kg/m3. |  | Cl 703.08 |  | Verify |  | ITP Signed Ambient Temperature. °C Concrete Temperature. °C | HP*/ WP |  | Project Engineer/ Superintendent | N/A
2.5 |  | Concrete Placement |  |  |  | Each lot | Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches |  | VicRoads Spec Cl 703.23 |  | Site Inspection |  | ITP Signed | IP |  | Project Engineer | N/A
2.6 |  | Finish Surfaces |  |  |  | Each Lot | Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour |  | 703.25 |  | Visual inspection |  | ITP Signed | IP |  | Site Engineer/ Site Foreman | N/A
2.7 |  | Joints |  |  |  | Each joint | Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen |  | 703.26 |  | Verify |  | ITP Signed | IP |  | Project Engineer/ Site Foreman | N/A
2.8 |  | Backfilling |  |  |  | Each Lot | Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified. Layers shall not exceed 150mm compacted depth |  | 703.29 |  | Verify |  | ITP Signed | IP |  | Project Engineer | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  |  |  |  | Position: |  |  | Signature: |  |  |  | Date: / /
Legend
| HP |  | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent |  |  |  |  | IP |  | Inspection point |  |  | Formal Inspection to be done and recorded
| HP* |  | FH Hold Point |  | Work shall not proceed past the HP* until released by FH |  |  |  |  | TP |  | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point |  | An inspection which must be witnessed by the Superintendent |  |  |  |  | SCP |  | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point |  | Written or verbal approval given by the Superintendent